## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
8152580a-9256-5c5f-9e72-fe5edfe62d4b | checklist | ITP - Commissioning - 105 - Rev A | itp | ITP - Commissioning - 105 - Rev A
ac5ee1ee-5139-57b0-9c55-3196b7da263c | section | 3.01 General
4b182364-c9b8-5807-85b4-26cb6c506fc7 | checkpoint | 3.01.01 - Precondition Surveys
6a1a0114-788b-5715-8725-46aadf76c15e | note | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
b6f7bbd3-0083-594c-9a17-d212f72c0765 | note | Standard / Specification - PS 2.13
5c63b6ce-a360-5fa1-a978-40fce9aabf72 | note | Verifying Document - Precondition Survey
070d0402-94aa-5021-97c3-5f85114cac8e | note | Frequency - Prior to the Contractor taking possession of the Site.
30f2035b-b5cd-5c06-8f15-69621759200b | note | Verification Activity: Activity - H
d2276f8c-54ad-5857-84f6-64b24ff259e0 | note | Verification Activity: By - PM
430795d3-4bfe-5f72-9c6d-43419a384688 | section | 19.01 Road Opening
56b6ba2f-a55e-55e3-b6f8-b7a6537140c8 | checkpoint | Pre-Opening Safety Review
7407e386-56f4-5806-b324-f6d31fb0a4a8 | note | Acceptance / Conformance Criteria - Prior to opening the Works for use by the general travelling public, a pre-opening safety review will be undertaken by the Engineer and the Principal’s Road Safety Audit team, to approve the removal of any temporary works, speed limits and traffic management.
4aa437e8-718e-5209-b967-476eaf55b7b4 | note | Standard / Specification - PS 7.5.1
2797daa0-a1e9-554e-b182-401381487859 | note | Verifying Document - Report
6496ca1c-0888-5caf-b728-8eba40577ec9 | note | Frequency - Prior to opening the Works for use
48bc59ba-46f1-544c-b1bd-8c77945c8959 | note | Verification Activity: Activity - HP
4d27526b-18d1-5250-8823-da1d4336e3cc | note | Verification Activity: By - ENG
9be702de-e809-5aa6-81f8-906d6e0d7c9c | signoff | AUTHORITY HOLDPOINT
085be86f-f27a-5bd1-b4a2-4f4e55b2768d | checkpoint | Post Construction Safety Audit
caf70557-69fb-5572-b1a3-69911f468de4 | note | Acceptance / Conformance Criteria - Prior to the issue of Practical Completion, a post construction safety audit must be completed by the Engineer and the Principal’s Road Safety Audit team.
3abf80d6-3696-57a4-aad4-3e47c6221486 | note | Standard / Specification - PS 7.5.2
e2f321da-10ad-5b28-a00e-8487592178d1 | note | Verifying Document - Report
1fe06648-8627-5e8c-b996-e4465cb15d06 | note | Frequency - Prior to the issue of Practical Completion
4e8aeb48-0593-5f53-a4c9-29ae28de19ad | note | Verification Activity: Activity - HP
833f503a-a467-54e9-bc5e-50153576d883 | note | Verification Activity: By - ENG
b2bb42a9-8cae-5d0d-b55f-2414a28f87b2 | signoff | AUTHORITY HOLDPOINT
aa9a099a-2401-545c-b2fb-4fa79037ea1c | checklist | ITP - Earthworks - 101 - Rev 2 | itp | ITP - Earthworks - 101 - Rev 2
ac5ee1ee-5139-57b0-9c55-3196b7da263c | section | 3.01 General
4b182364-c9b8-5807-85b4-26cb6c506fc7 | checkpoint | 3.01.01 - Precondition Surveys
69cd2420-d366-54eb-958b-47ee6ba30c3b | note | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
8a300e3e-8b0d-50e1-92a8-acacc9470272 | note | Standard / Specification - PS 2.13
4012ae1e-5742-5bb3-bd88-9891dd0da569 | note | Verifying Document - Precondition Survey
5ee54bf7-4881-50be-9cbd-b6ca24fbed29 | note | Frequency - Prior to the Contractor taking possession of the Site.
4ee5ad50-8a49-5ef9-b2ce-6829404da63e | note | Verification Activity: Activity - H
042a86d8-9388-5bf2-bc39-fae98a19ea53 | note | Verification Activity: By - PM
2c4b8fd4-5150-5656-bda8-48bbc0f299cc | section | 4.01 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
eec51e33-e195-5fd4-8848-2a84896576bc | checkpoint | 4.01.01 - Source Property Tests and Sampling
c970b435-1a5a-5b52-9c63-6d3dc47a7b24 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, Los Angeles Abrasion, and Soaked CBR at least 2 weeks prior to importing to the site.
5fddf01b-636b-5c1b-9e0f-f9d479c784a9 | note | Standard / Specification - PS 15.7.3 Appendix XIII
c05f86e5-078b-56d0-a84d-743d12ed7c80 | note | Verifying Document - IANZ Lab Reports
0d61936a-619a-5486-b002-fd3bb8ecd191 | note | Frequency - 2 Test Per Material Per Source at least 2 weeks prior to importing to the site.
6c36e154-7375-5049-8d17-38c7ea3fb8aa | note | Verification Activity: Activity - HP
3ce79e68-2cd7-57fc-8b23-187278275664 | note | Verification Activity: By - ENG
943c57a3-9718-5eec-a0c4-4f254ca57b92 | signoff | AUTHORITY HOLDPOINT
e74ba8eb-c7ac-51ca-806d-ce6b2d151d6f | checkpoint | 4.01.02 - Testing for Layer Compaction - MDD
0eea5d39-c7a9-597e-95e8-2d3aa0eb79ce | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Heavy Compaction), Optimum Water Content, Air Voids, and Shear Vane Strength (Su) with Range of Moisture Contents.
3a7cfff1-f254-5419-911c-e86cf81791ad | note | Standard / Specification - PS 15.7.3 Appendix XIII PS 15.13
bac60110-709f-58ca-825f-eef1d568b6fe | note | Verifying Document - IANZ Lab Reports
28d0819b-7509-50e5-aaad-6484fe8c56af | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
93ed1431-f321-5f8b-8125-d991cf43a90b | note | Verification Activity: Activity - HP
5eecf011-989a-5420-a82b-eb0149a57904 | note | Verification Activity: By - ENG
1ad45696-b06f-57ba-991f-876ec2469f8a | signoff | AUTHORITY HOLDPOINT
cc28f368-5ec3-56d4-92e5-eeccc9eacb38 | checkpoint | 4.01.03 - Production Property Test Sampling
6c461bdf-e882-525f-a094-2bcc190ce2e7 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD).
4c2ef108-068a-59d0-b3de-60b2a95c6c7f | note | Standard / Specification - PS 15.7.3 Appendix XIII
6a814afb-0be7-53e5-8592-2862e1a765fd | note | Verifying Document - IANZ Lab Reports
efce84d9-b1b2-5d89-991c-9da04e5ba923 | note | Frequency - 0-400 M3 – 2 Tests
f89666dd-0f56-5b39-b7d2-2694b08c1b13 | note | ○ 400-1,500M3 – 3 Tests
ed92ad50-6f20-5df3-bdee-ddfd8f5eb73d | note | ○ 1,500-4,000M3 – 4 Tests
8473fabf-bde7-5cc9-8e93-e31e0d9d300b | note | ○ >4,000M3 - 1 Test For Each Additional 10,000M3
fd98181f-7bd9-5f53-8201-bb0c6813a688 | note | Verification Activity: Activity - H
29935793-de84-5fc9-9e9a-dc726b88856e | note | Verification Activity: By - PE
d3197014-3f06-5fe0-b1d9-aea439b97c54 | section | 4.04 Type A3 (Site Won Landscaping Fill)
bd572b98-794b-572a-b262-0d8895c651db | checkpoint | 4.04.01 - On Site track-able Testing
8fefcbaf-cb68-5917-9433-3d41137b8e4e | note | Acceptance / Conformance Criteria - Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it is ‘track-able’ by the contractor’s plant. This shall be determined before Sampling.
b4914206-8d0b-5414-9502-17ae4fad6e1c | note | Standard / Specification - PS 15.7.3
e51abaca-32b0-57d1-8544-f906b25a9fc0 | note | Verifying Document - Visual Site Record
aaf6e6a1-d9e9-5a27-86da-31e404a8a62d | note | Frequency - Prior to Sampling
d4f5a2c3-8d72-5a12-84a0-52e374ec9d02 | note | Verification Activity: Activity - W
21e39c46-937e-5756-bf3a-0fa20897c108 | note | Verification Activity: By - PE
bbfc5154-bf5f-5edf-b862-ca5b40d3d743 | checkpoint | 4.04.02 - Testing for Layer Compaction - MDD
da4431ef-f91b-5faf-a07f-ebe5b3ed0ce8 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Standard Compaction), Optimum Water Content, and Shear Vane Strength (Su) with Range of Moisture Contents.
75366e9f-f170-5da4-8e90-2ba29431f456 | note | Standard / Specification - PS 15.7.3, PS 15.13
01c254a6-d804-5850-b1b7-daee29774ece | note | Verifying Document - IANZ Lab Reports
cd00113d-ee85-5286-956b-580960ae86ae | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
9895d0dc-5a1e-556b-b3a4-f60bb935b694 | note | Verification Activity: Activity - HP
803e0adb-6908-539d-91c5-5f291f829291 | note | Verification Activity: By - ENG
787da1d7-76e7-5318-90fc-d7c5b66f0772 | signoff | AUTHORITY HOLDPOINT
1b403918-b691-5bde-88b7-f3ee9e087117 | checkpoint | 4.04.03 - Insitu Property Test Sampling
b2e3a0b7-200b-54bc-8753-e33bdade2178 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD) and inspected for deleterious materials such as boulder size fragments and organic materials.
da342694-bd84-565c-b303-933f704abeb3 | note | Standard / Specification - PS 15.7.3
3f8b0f56-e239-5878-82f3-25bd301b0188 | note | Verifying Document - IANZ Lab Reports
54187772-fb0a-5304-b22d-e6fef5571033 | note | Frequency - Prior to use
5f2c876f-b40e-5944-91db-1b5c4f101bfd | note | Verification Activity: Activity - HP
10ebcf48-ad4b-5c4f-ac90-4d24da87969d | note | Verification Activity: By - ENG
f4da45cc-ae32-586a-82a0-8191c8cf5c37 | signoff | AUTHORITY HOLDPOINT
540a5e70-44a2-557d-9a5c-b23f9eba4a3f | section | 4.05 Topsoil
20c79c91-2f0b-5e64-bc79-4fc755ec0ddc | checkpoint | 4.05.01 - Topsoil
c48a7814-415e-5bf0-90db-a1b8443b9fdd | note | Acceptance / Conformance Criteria - Topsoil is defined as the layer of material immediately below the ground surface comprising vegetation, tree roots, other non-decomposed organic matter, turf and humus. The Contractor is to stockpile and utilise site won topsoil for placement on the final batter slopes and for borrow site reinstatement as shown in the Contract Drawings.
e65a11a1-9f5f-5b9b-b31a-005bf9a0f5ad | note | Standard / Specification - PS 15.7.3
cf04a554-dfc6-58b4-9613-62ac16fdabb9 | note | Verifying Document - Site Record
ee11df60-1ce5-585b-8998-69594136d238 | note | Frequency - During Stripping
e137dc49-6b12-5bed-ab75-30d89abce352 | note | Verification Activity: Activity - I
11dd70c8-b8f1-5205-a62a-89a0d37a59b0 | note | Verification Activity: By - SE
d75e34e2-526e-508b-9139-1c41f905aee4 | section | 4.06 Geotextiles
94c5cd81-4c09-5866-a780-a6cb2b294715 | checkpoint | 4.06.01 - Geotextile on Undercut to Waste and Backfill
01a812e1-2a2b-5d7f-a9f9-4d80c94b831d | note | Acceptance / Conformance Criteria - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation.
c17089c8-cde6-5780-af0b-4d44cfe037e4 | note | Standard / Specification - PS 15.10.9
3752352a-df5a-53b2-8094-118f73546c7d | note | Verifying Document - Datasheet
8e7145b3-d717-57d4-8b68-f84837bcbada | note | Frequency - Prior to use
6f3350cc-a5e3-5922-90ec-ceba1cff1e25 | note | Verification Activity: Activity - R
ffc1a14f-5946-57d0-b15d-4eb1e2f5b1a3 | note | Verification Activity: By - SE
00122e61-34f7-53d5-a67f-e0c09f6146f3 | section | 5.01 Site Clearance
aa56f8f4-2f1d-53a7-90e0-bf9bff008cd2 | checkpoint | 5.01.01 - Site Clearance
76735cd9-4858-55a6-aa06-101f02518612 | note | Acceptance / Conformance Criteria - All trees, scrub, non-lawn vegetation and/or self-sown plants within the extent of the earthworks shall be removed to waste in accordance with Clause 3 and Clause 9.4 of TNZ F/1:1997 Specification for Earthworks Construction.
e2b43d2f-4215-5670-89ab-c3b1d39d5dd5 | note | Standard / Specification - PS 14.1.1 NZTA F/1 - 3
f35896e9-18bd-51fb-84bd-a516fea07908 | note | Verifying Document - Site Record
1c9aecd5-6527-5a3f-90f9-fb46fb1152c3 | note | Frequency - Prior to excavation
553d21dc-d656-5d11-a678-49e9091a7776 | note | Verification Activity: Activity - I
b8ac2dc9-f39d-5a4c-88d0-92ffc13d346b | note | Verification Activity: By - SE
0434188f-64e5-5961-b752-f68ed0678033 | checkpoint | 5.01.02 - Dump Site Approval
165908c4-435f-5b36-8fd9-df3fab4ecdd9 | note | Acceptance / Conformance Criteria - The locations of dump areas shall be agreed by the Engineer before use.
e22c6756-65e9-50b5-b8f9-e78161c44d04 | note | Standard / Specification - NZTA F/1 - 9.4
55d5c387-b48b-5e7f-9757-2749a36ece54 | note | Verifying Document - Site Record
f84ff3ba-d111-577e-814d-2f3b3ff0c62e | note | Frequency - Prior to Stockpiling
73737f8f-3ed5-5230-a5fa-7d12fd1ac08c | note | Verification Activity: Activity - HP
74ce0d35-f379-5262-b7f4-46543d42148d | note | Verification Activity: By - ENG
c082bbf0-64bb-5295-803d-efd5e36c07d2 | signoff | AUTHORITY HOLDPOINT
97e973d9-e87b-5abc-b883-a17a57730683 | checkpoint | 5.01.03 - Mulching
7c25105e-22ed-5c83-8240-5f58fa89da29 | note | Acceptance / Conformance Criteria - Where possible, cleared vegetation shall be mulched and stockpiled at a suitable site for future landscaping work.
39aa4f4e-e9d4-5b72-a53a-4a01c43363d6 | note | Standard / Specification - PS 14.1.1
54411dec-bc57-5533-afb7-0f38308d0bf6 | note | Verifying Document - Site Record
d3575c48-3185-5f98-b1fe-4784265e23ac | note | Frequency - During Clearing
449c8392-36d0-5a80-8ce1-30049ce1eaa6 | note | Verification Activity: Activity - R
07fddfa0-d1c0-5767-bf10-aa4ad5673f63 | note | Verification Activity: By - SE
4f7cfdbd-f8a4-5f17-a5dd-b36d0cb99ded | section | 6.01 General Earthworks
7b7266d6-ecf8-561a-b4ca-7b37880265fd | checkpoint | 6.01.01 - Earthworks Methodology
c228e36c-639a-5d64-84a6-17b814e6f41b | note | Acceptance / Conformance Criteria - The Contractor shall submit the construction and QA methodology for each element of Earthworks including construction, Haul roads, Site Access, dewatering, Wet weather, testing, inspection, and hold points for review and approval prior to works.
0b682de4-c8ae-51d1-9923-ecbfc85690dd | note | Standard / Specification - PS 15.13, PS 15.6.2, PS 15.10.13
b50a3242-4781-56d2-9c29-2bfa07bedacd | note | Verifying Document - Approved Methodology
9b77a527-c1c2-52d4-bf08-2baf8fe48a93 | note | Frequency - Prior to Earthworks
00c15935-b738-5367-8878-db856c582b87 | note | Verification Activity: Activity - HP
2e554e60-d952-5dd6-861b-a558370ee856 | note | Verification Activity: By - ENG
326a5f19-66e6-52e8-8259-accb86134d3f | signoff | AUTHORITY HOLDPOINT
ce70eb24-ffd6-534e-9bc3-84ccc496c6db | checkpoint | 6.01.02 - Temporary Excavation Approval
8b4c1814-1483-57a0-a93e-7cf0f5129205 | note | Acceptance / Conformance Criteria - The Contractor shall submit Temporary Excavations details to the engineer for approval prior to excavation.
33ca796d-57e5-58de-b34f-c32e6163735c | note | Standard / Specification - PS 15.13
c6d3b217-5879-5d04-b9ab-a032084546f6 | note | Verifying Document - Engineers Approval
de2c1bd3-ac7a-562d-817a-3f4a0bb05767 | note | Frequency - Prior to Excavation.
cd18a545-923b-5871-b92c-dee9402f4e29 | note | Verification Activity: Activity - HP
b2515f22-7df2-58c2-ac65-fe920a60c040 | note | Verification Activity: By - ENG
7f24d1ae-eaea-5164-a39d-b9602a701e03 | signoff | AUTHORITY HOLDPOINT
7be180f9-b731-51bf-aa2a-2646cc8a1c69 | checkpoint | 6.01.03 - Temporary Works Design
6bf13ae3-7a65-50e5-8ee5-356f37e5f99f | note | Acceptance / Conformance Criteria - The Contractor shall submit the temporary works design for Review and approval of prior to excavation.
34321cd1-593b-53a3-963f-41929191a96b | note | Standard / Specification - PS 15.13
725dbc6f-43b7-58dd-b840-2a9e1cc7a0a5 | note | Verifying Document - Approved Design
e4fec50b-b4eb-5cfa-bc23-b5a1182bdb5c | note | Frequency - Prior to Excavation.
2ac192cb-bf2e-52c2-b62a-50c4c4697492 | note | Verification Activity: Activity - HP
e421222d-e59e-5ba2-9fce-d91b87b2c1cd | note | Verification Activity: By - ENG
bd223daf-c7ae-5c7b-b6da-6f123e740f86 | signoff | AUTHORITY HOLDPOINT
55e3284f-9a58-588c-bbef-d9a461605980 | checkpoint | 6.01.04 - Temporary Stockpiles
baf815d3-1ef3-59b4-94ad-daf49ffc72eb | note | Acceptance / Conformance Criteria - Temporary stockpiles shall not be located within the footprint of the permanent works unless approved by the Engineer.
18b30793-18bf-5c62-9ab2-12c0e2ba5c49 | note | Standard / Specification - PS 15.6.5
cc98758a-ecad-5043-bcc8-3a0f6433d90f | note | Verifying Document - Engineers Approval
58eb1e17-79a1-52e1-b4e4-ff51e4c2a10c | note | Frequency - Prior to stockpiling
08cfbbd5-6e1b-5ca2-872e-ed4df362935a | note | Verification Activity: Activity - HP
8f11b887-eb69-534b-b326-59012efc3a5c | note | Verification Activity: By - ENG
a94c983f-b77c-5257-ba7c-2cf26f751c21 | signoff | AUTHORITY HOLDPOINT
9f916a51-531e-50f9-ab39-015b1c560d11 | checkpoint | 6.01.05 - Surplus Material
02f14ce9-3ef4-562b-b104-58d1241b50c7 | note | Acceptance / Conformance Criteria - Surplus or waste soils may be deposited outside the site boundaries with the written approval of the Engineer.
c85b74b4-9183-55a7-ae2f-345297038e49 | note | Standard / Specification - PS 15.1
ef2e0cf0-e7d5-51ba-8a6d-bbc82bdf9e2f | note | Verifying Document - Engineers Approval
a960256b-958b-5eb6-af8e-bc4d99728fb0 | note | Frequency - Each Occurrence
52fea67b-14ca-5826-8d8a-c11dc3466cf4 | note | Verification Activity: Activity - HP
4b1848f4-9510-5def-95f4-d24b7a6c808e | note | Verification Activity: By - ENG
291238e6-3d02-5ec2-b9a8-ab81fb7023ca | signoff | AUTHORITY HOLDPOINT
918a1145-c5ce-509f-bed1-f62ab59e0117 | checkpoint | 6.01.06 - As-Builts
db708295-8b31-57be-bec5-77dab4401720 | note | Acceptance / Conformance Criteria - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
a24bef18-ed19-5402-9911-8d0aa41611d7 | note | Standard / Specification - PS 15.11.7
44a3c1ca-2b3c-5bd8-bcd9-8166bc6a932f | note | Verifying Document - Survey Records
b240b2d4-ab96-5982-84a2-2fd25825db00 | note | Frequency - During Earthworks
f0563e63-58d2-5281-99f2-223329a109a7 | note | Verification Activity: Activity - D
0379ef52-f0a4-5de8-b838-16ad532332f7 | note | Verification Activity: By - SV
44d1c624-06c3-5e22-b6df-9c6af47c6102 | section | 6.02 Cutting and Subgrade
e2056d42-43d7-5262-8e7d-f3a1023524d6 | checkpoint | 6.02.01 - Cut slope inspections
f0c9e4d3-35fc-5484-b867-873378bcdcc6 | note | Acceptance / Conformance Criteria - Cut slope inspections will be required to allow inspection of the soils exposed and check for seepages. Inspection records are to include photographs, logged soils (to NZ Geotechnical Guidelines) and hand shear vane testing on fine grained soils. Results will be submitted to the Engineer.
a5050965-657c-5cb4-ba54-29f7a81a36c0 | note | Standard / Specification - PS 15.10.2, PS 15.13
0ca6644d-27bc-50cb-82c3-e9215beabdf8 | note | Verifying Document - Engineers Approval
ee095220-c54a-544f-8c85-d2e244c4a0fd | note | Frequency - Each Occurrence
6854b9e5-08d8-53bf-b4c4-25cc08b491a4 | note | Verification Activity: Activity - HP
3b8c7bd6-7173-5f1c-9873-a15adf5e3876 | note | Verification Activity: By - ENG
e91cf135-5c98-52a7-a54a-3c6af3be7601 | signoff | AUTHORITY HOLDPOINT
d2fbe478-ad1f-5048-8657-8f4e357aec4a | checkpoint | 6.02.02 - Dewatering
45ad7851-3863-514c-bd5d-d0013775f8f7 | note | Acceptance / Conformance Criteria - Trenches and excavations shall be dry at all times during construction works and a constant water level is to be maintained at 300mm below the base of the trench. No construction works may occur if there is any water in an excavation.
10bf3c53-35d3-54c6-aa6d-417ba63dc5da | note | Standard / Specification - PS 15.10.18
fbd2f8c6-64ab-5c47-af05-cb3418296a2c | note | Verifying Document - Site Records
bc3137ea-86db-5fc7-b231-fea3db637513 | note | Frequency - Ongoing
f642d9fb-44aa-5900-a964-19c664e82209 | note | Verification Activity: Activity - S
83904629-984d-510e-b1a8-050717dedc6a | note | Verification Activity: By - SE
0478f66f-1630-5596-ad8d-f38a4cc2b1c9 | checkpoint | 6.02.03 - Subgrade CBR Testing (Road and Embankment)
f3d10b4e-addd-5538-a957-2a37e0034faf | note | Acceptance / Conformance Criteria - The subgrade shall be tested for CBR via Shear Vane or Scala depending on site conditions. Testing to be undertaken to maximum 3m depth at 0.5m interval with hand auger holes required for test deeper than 900mm.
2ce0f2e8-1f40-5e35-8e0b-a78fd0b55a7b | note | This test shall be undertaken at the design subgrade level and at a depth of 300mm below the design subgrade level. Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material.
8b65a2ae-cac6-521a-a731-1c5b9ef6ea23 | note | ○ Shear Vane Average minimum su: > 60kpa
4ccae70e-9d5a-53e4-8f6b-a4e00f80f67e | note | ○ Shear Vane Single test minimum su: > 50kpa
3ff01897-8d7b-537a-9e0a-bdedcefe185a | note | ○ SCALA: Minimum 3 blows per 100mm penetration
630d469c-d4b6-528c-8e3d-4302c9510b53 | note | Standard / Specification - PS 15.10.4, PS 15.10.5 Appendix XIII
0c3bb1ce-aaf0-5272-9b8f-4d902e6bbc45 | note | Verifying Document - Shear Vane or Scala Report
85d3bae8-7bf8-56b3-9602-213fb78a5576 | note | Frequency - 4 test per 400M2
55a69f30-35b2-5c05-9282-92604524f101 | note | Verification Activity: Activity - I
8a1bfe00-8ce7-590a-a5cb-d9ae236fa6a6 | note | Verification Activity: By - SE
55b576e1-21ed-531a-aacd-d94250dc6129 | checkpoint | 6.02.04 - Undercut Subgrade Compaction
f841e758-4cd2-5891-b08c-751a3c88b535 | note | Acceptance / Conformance Criteria - The degree of compaction of each layer shall be such that when trimmed to a smooth surface, the resultant impression in the surface under a smooth wheel roller having a minimum loading of 6259kg per metre width of fill or equivalent as agreed by the Engineer, shall not be greater than 7 mm for bulk fill or 5mm for subgrade fill.
8fb02c88-5c79-5b58-a1dd-92a07552b833 | note | Standard / Specification - PS 15.10.4
a629293c-385f-5bce-b059-933f4c7d43dd | note | Verifying Document - Site Records
2a96cae7-3c6a-51cb-9454-6091224f2d6f | note | Frequency - Prior to Backfilling
4ff321f5-d0cb-5131-9bac-f2447b9cd5d8 | note | Verification Activity: Activity - S
9afabe93-cf7b-5ea2-9907-09925e3a24f2 | note | Verification Activity: By - SE
9bb70f82-94b7-566d-9ef1-4b61c37556a1 | checkpoint | 6.02.05 - Soft Road Subgrade Areas
6fd65fab-6193-5462-afeb-d69af1a8db96 | note | Acceptance / Conformance Criteria - Any soft area observed during rolling of the subgrade shall be referred to the Engineer.
d76e99d9-c656-55e3-acb1-1c1df46f6945 | note | Standard / Specification - PS 15.10.4
1be23212-e8df-5d9f-8313-9a5254ebe069 | note | Verifying Document - Notice
1c0d6418-f406-5f50-950c-5444425f50bf | note | Frequency - When Encountered
34656019-18b2-5fea-94d4-d598e2a8138a | note | Verification Activity: Activity - S
c035f040-40a1-576d-b193-c59e6a453dad | note | Verification Activity: By - SE
c3b7c71e-cfaa-5a96-a625-454bb0cc64fa | checkpoint | 6.02.07 - Finished Surfaces
9bec837e-b683-55ad-bd75-4a248c626262 | note | Acceptance / Conformance Criteria - The works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for Subgrade is 0 to -30mm before placing aggregate layers.
a6991efb-ab9a-5b99-bf23-cb2f8b77c50b | note | Standard / Specification - PS 15.6.8
be65fa83-a107-5342-9c6d-a54c8b435c69 | note | Verifying Document - Survey Records
887ad7d3-09f0-5edf-a3ba-45e2f89d1d67 | note | Frequency - Each Finished Surface
157d7177-0edf-5110-9131-f02c3d9f1433 | note | Verification Activity: Activity - D
1fe43a96-441d-52f3-9c61-b1ddff480ba2 | note | Verification Activity: By - SV
9149e6ff-1de8-5094-9b9f-ead6fee4ce61 | checkpoint | 6.02.08 - Subgrade Proof Roll and Foundation Inspection (Road and Embankment)
b64008e4-8e18-5171-b4ca-a72a0d91c282 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect the Foundation surface prior to Filling during the Proof Roll. No filling shall be undertaken until an inspection has been made and the Engineer has approved the cut and stripping of unsuitable materials. Visual Observation Across The Stripped Area Displacement < 15mm.
677d8b3a-9fe5-5e7f-9e11-0862609e0580 | note | Standard / Specification - Appendix XIII PS 15.13, PS 15.10.5
9841c2a6-be7e-500d-bcca-506f57b64c31 | note | Verifying Document - Engineers Approval
4e231911-13ab-5ecd-9b53-75b332d5bfb0 | note | Frequency - Prior to filling with 24h notice
c10bf413-07c4-5174-9e14-7c2fbcd9358d | note | Verification Activity: Activity - HP
950b4e24-66ad-5e1f-946a-4eebbe8609ed | note | Verification Activity: By - ENG
f05195d4-07ae-5bad-820d-5d958fa1f023 | signoff | AUTHORITY HOLDPOINT
cbfd5119-9511-5f05-a1a3-eb568e57c7a2 | section | 6.03 Filling General
6da130e7-ec1a-5eb6-b735-c0a7919ee1b0 | checkpoint | 6.03.01 - Compaction Trials
082af659-e5a1-5e55-bb14-86dcfa2c12cc | note | Acceptance / Conformance Criteria - The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (i.e. construction discs and scarifiers). The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements. The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial.
b932f253-0659-5483-8431-149e22a51f34 | note | Standard / Specification - PS 15.10.15
0ff16a2c-7e89-5fe7-97b9-0d0dc811e560 | note | Verifying Document - Trial Results
5fa74afb-d11f-58b9-9267-b51498af3937 | note | Frequency - During Works before placement of each material.
103d17fd-0df9-56e9-949a-dda4690eb715 | note | Verification Activity: Activity - R
66efe4f8-ef07-5b70-852c-a42dccaab6c1 | note | Verification Activity: By - PE
e6b0ff49-10c9-5967-b663-f2fc4e147aa3 | checkpoint | 6.03.04 - Geotextile on Undercut to Waste and Backfill
b66a3f7f-c101-55fc-a488-65023d32f225 | note | Acceptance / Conformance Criteria - Geotextile shall be laid across the undercut base and the sides and joints shall be overlapped in accordance with the manufacturers specification to prevent squeezing of the underlying foundation.
39fe306a-53bb-58ff-84b4-d25744279b95 | note | Standard / Specification - PS 15.10.9
2215bfc9-484e-5f67-adce-6df3c540172a | note | Verifying Document - Site Records
2d33a3f7-a446-54bb-a02a-dbae2920cdbb | note | Frequency - Prior to Backfilling undercuts
8477f682-7f40-53b2-9c76-46de57fde771 | note | Verification Activity: Activity - R
f661c483-12d8-5268-8d41-625af8658963 | note | Verification Activity: By - SE
29370bd4-2ff3-5032-ac70-4629fb46ed01 | checkpoint | 6.03.06 - Weaving or Pumping
bd1991d0-5093-5804-aff8-c52b44e7385d | note | Acceptance / Conformance Criteria - Any weaving or pumping of the soil or subgrade during the compaction process is likely to indicate that either the water content is excessive or the material has been over-compacted. If weaving or pumping is observed, the Engineer should be contacted to advise the appropriate solution.
e605ba42-46c5-5a4e-888c-2477e598e0b8 | note | Standard / Specification - PS 15.10.16
d39f9c2c-ed77-5b28-9068-8d5502076351 | note | Verifying Document - Site Records
68e095e6-4a9f-530e-83a7-48b3803bce4c | note | Frequency - When encountered
27e7c1ea-82b6-5046-a56c-510159c3d998 | note | Verification Activity: Activity - S
ed838f5a-7bf1-5227-8006-76b8f7af37f3 | note | Verification Activity: By - SE
8121b3c2-5c62-5f8a-95d7-1511aca62833 | checkpoint | 6.03.07 - Finished Surfaces
3070b6ed-33d2-59d9-86fa-a87d75982015 | note | Acceptance / Conformance Criteria - The proposed works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for earthworks construction purposes shall be level +/25mm unless stated otherwise, Subgrade; 0 to -30mm before placing aggregate layers, Bulk fill ±100mm, Preload and surcharge ±100mm, Batter slope tolerance ±100mm
3c16fa38-3eaf-5ad1-9f22-07ba1a84a45f | note | Standard / Specification - PS 15.6.8
816b2da5-1e05-56ee-b0d4-f4dad76d85e7 | note | Verifying Document - Survey Records
41c5a73c-3d7a-5d08-99a6-a6c30a41296c | note | Frequency - Each Finished Surface
d8403246-e1a7-5f1e-a63f-c616a6f86317 | note | Verification Activity: Activity - D
6183135d-77a3-5020-94fc-7c8fb634a0f3 | note | Verification Activity: By - SV
28941e1a-7c86-5b6c-b4be-2bd9aa06435c | checkpoint | 6.03.08 - Final Trimmed Shape Inspection
929f9aa7-dcab-55ef-848e-e713dd5186b9 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect final trimmed shape prior to placing topsoil or track rolled fill.
a0d0e862-2504-55af-b439-f3f7356c1fcf | note | Standard / Specification - PS 15.13
51f6149e-c97b-5a09-af39-5267730b4dd8 | note | Verifying Document - Engineers Approval
1d64599f-c05f-5017-bfc2-421633c38bf0 | note | Frequency - Prior to placing topsoil or track rolled fill.
ec8638c9-6512-5db2-95d2-d6d3f35119b8 | note | Verification Activity: Activity - HP
72c74c91-2072-5a09-8013-ca846e10480a | note | Verification Activity: By - ENG
2fa4e556-dcd6-5d59-898c-5d69fcba5b07 | signoff | AUTHORITY HOLDPOINT
9009fa4f-63e9-5b9f-b8f5-3feccfd591cc | section | 6.04 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
25dd2c92-e278-54c8-aa60-59679d5bfb86 | checkpoint | 6.04.01 - Imported Structural Fill Layers
6878fdaf-0bcd-5db1-a513-1fc0df376bbf | note | Acceptance / Conformance Criteria - The material shall be placed and compacted in layers no greater than 300mm thick.
8b06cea0-2762-5a10-b343-8660f98e0189 | note | Standard / Specification - PS 15.10.14
1a89ef0a-9801-51bc-aee0-85e181a5627d | note | Verifying Document - Site Records
30797fec-d05d-5e1d-9407-2ca3ce812dbc | note | Frequency - Each Layer
e9f5e8d3-b7f2-5398-be87-1d5e695a0fb9 | note | Verification Activity: Activity - R
d72c325b-87d7-5b7a-abca-566cc22d1211 | note | Verification Activity: By - SE
7d79ea5d-74fb-5020-a7fc-15bc0d20fe88 | checkpoint | 6.04.03 - Structural Fill Zone - Strength – Clegg Impact Value (CIV)
33972346-eaf4-5b1b-adab-39ff4c57e4e4 | note | Acceptance / Conformance Criteria - A1 Imported Structural Fill Strength shall be tested by Clegg Hammer every 200m3 per area per day per lift
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Minimum CIV = 18
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Average CIV= 20
b21d6bc2-fa63-5bc1-8d96-b05121b299af | note | Standard / Specification - Appendix XIII
9e78cce7-cd0a-5ffe-b4f7-52f1a5f40ad1 | note | Verifying Document - Clegg Results
edfa4ec3-1fcc-5df9-ba9c-81716eabe644 | note | Frequency - 1 Set (5 Tests – 5x5m Square Grid) Per 200m3 Of Placed Per Area Worked Of Day Per Lift
c952f64f-f2ef-5aeb-b6b7-5b247ddc0cdb | note | Verification Activity: Activity - I
e91737f2-9daa-590c-ba83-c4825556312f | note | Verification Activity: By - SE
e7febe44-92c4-5796-b0f2-b82320d4484e | checkpoint | 6.04.05 - Structural Fill Zone Insitu Density Insitu Compacted Dry Density Insitu Water Content
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - A1 Structural Fill Compaction shall be tested by NDM in Backscatter Mode every 200m3 per area per day per lift
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | ○ Average >95% Of In-Situ MDD
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | ○ Minimum >92% Of In-Situ MDD
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Standard / Specification - Appendix XIII
69d85f65-b61d-579d-940f-2b691894d755 | note | Verifying Document - NDM Results
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
e2147c12-4568-5322-b418-283ae63070af | note | Verification Activity: Activity - I
09a8aad4-3fc9-597d-b419-c865f36b4acc | note | Verification Activity: By - SE
b9a8462b-715b-5c2d-8c25-e4f73254a4ca | checkpoint | 6.04.06 - Solid Density
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - The Solid Density Of Aggregate Particles shall be tested by collecting 1 sample with every set of NDMS completed (1 Test Per 200m3 For That Material Type And Source). Test Results Provide Input To Acceptance Criteria For Insitu Compacted Dry Density Determined By Nuclear Moisture Density Gauge (NDM)
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - Appendix XIII
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Solid Density Lab Report
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - 1 Set (5 Tests) Per Material Type And Source Then 1 Test Per 200m3 For That Material Type And Source
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
504915a0-29d1-5b8a-891c-a7b613638c3c | checkpoint | 6.04.07 - Organic Content
f09d0ff0-01ec-50cb-9988-3a078371cb3d | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
5d4c6d19-d8fb-5765-9b80-10ed32dbffe9 | note | Standard / Specification - Appendix XIII
ea12d870-db9e-5048-94de-56f316678975 | note | Verifying Document - Site Records
4b4f2a35-1e50-5341-80c6-541a73664b53 | note | Frequency - Ongoing
f77c9bbc-fb8f-5e0f-86c9-c66a4643254e | note | Verification Activity: Activity - I
dbb35f07-7f2f-5414-a8b4-c69adbcef37c | note | Verification Activity: By - SE
f910ed7f-8370-57c8-b1bd-2fb721606286 | checkpoint | 6.04.08 - Completed Fill Approval
cb670aff-3430-5d2c-ac3e-1482548f09ee | note | Acceptance / Conformance Criteria - Prior to pavement construction the Engineer shall complete a Desktop review of all structural fill compaction testing for acceptance.
e3ea5880-55a7-54a4-9ee9-9323b972ab79 | note | Standard / Specification - PS 15.13
eb4e4dcc-9679-50a0-8275-a70670f63fd0 | note | Verifying Document - Engineer Approval
5b1465a0-9c5b-51b0-8b4b-9694e85f2324 | note | Frequency - Prior to Pavement Construction
a3b40c94-fe59-5b33-bcda-878d287d2995 | note | Verification Activity: Activity - HP
696e1611-579b-5ae6-b3d8-5701063db1b8 | note | Verification Activity: By - ENG
5e0c2555-3e93-5160-beb9-af9efce873aa | signoff | AUTHORITY HOLDPOINT
faf4f3a3-1299-5382-bb2c-73748ed0cb2e | section | 6.05 LANDSCAPE FILL
a57c22bd-882b-5e15-98f1-6cc1024a010c | checkpoint | 6.05.01 - Cohesive Fill Layers
c352122b-b969-515a-bd14-4ee2d6d77a2c | note | Acceptance / Conformance Criteria - Cohesive structural and non-structural fill material, shall generally be compacted in layers of less than 200mm thickness. All fill surfaces shall be sealed at the end of each day’s work.
eb2c9836-d46b-5735-a171-5b7c260a8373 | note | Standard / Specification - PS 15.10.16
16c87f21-2b6f-5a9e-950f-ce52726911a4 | note | Verifying Document - Site Records
f997564b-0a06-59cc-aaf8-0d04c169bb65 | note | Frequency - Each Layer
48daa9bc-dbe2-5457-aa35-ebb3d2f05eee | note | Verification Activity: Activity - R
a63751f3-0140-5d7c-80c1-864752f123ce | note | Verification Activity: By - SE
e9f6dd3e-48b2-53bf-8c70-05c59c2b86d9 | checkpoint | 6.05.03 - Non-Structural Fill - Air Voids
8e28b866-fa38-519b-918f-3d14bb22ecfb | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill compaction (Air Voids) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift.
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Average Maximum Air Voids < 8%
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Single Test Maximum Air Voids< 10%
b6a6dfee-f164-5998-9bdb-0af48b5f824e | note | Standard / Specification - Appendix XIII
bebdea1e-dece-5fe9-9b48-a107125b16b9 | note | Verifying Document - NDM Results
e003f7a2-352b-5d80-9fd5-e44eddfe06fe | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
3f5e0ef0-3697-5f92-8b8c-ec24df3f2e89 | note | Verification Activity: Activity - R
da65e1bd-770b-59ad-9793-ebeab9e626dd | note | Verification Activity: By - SE
2254b6f8-ca87-5831-8381-537164057ab6 | checkpoint | 6.05.04 - Non-structural Fill – Shear Strength (SU)
9edd37d7-9376-551e-84f9-b888b8840c61 | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill Strength shall be tested by hand held Shear Vane or Scala every 500m3 per area per day per lift of fill placed.
5b2f902a-75e1-52ba-831a-286d435423d5 | note | ○ Average Minimum Su > 60kPa
0d47f6a9-9a9c-5830-a715-20e29444a71c | note | ○ Single Test Minimum Su > 50kPa
cd8cbc5d-5199-51fe-8b4d-b38294c9026a | note | ○ Scala: Minimum 2 Blow Per 100mm up to 1.0m deep
3987cf23-05e1-5604-91fa-7c85db88248f | note | Standard / Specification - Appendix XIII
7cd5ddd4-8c1e-52f1-aeba-5f314cce96f9 | note | Verifying Document - Shear Vane or Scala Results
6c04cc44-a270-5c2c-903f-8ca50b667f73 | note | Frequency - 1 Set (5 Test) Per 500m3 Of Fill Placed Per Area Worked Per Day Per Lift
031b41c8-0684-5bd5-9692-1238e6978165 | note | Verification Activity: Activity - I
2f45e865-55b9-5d5f-94f9-2cda2e27e330 | note | Verification Activity: By - SE
67d2cb19-a2ab-56fe-9362-2a11a6148fa9 | checkpoint | 6.05.05 - Non-Structural Fill - MDD
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - Non-Cohesive Non-Structural Fill compaction (Dry Density) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift. 90% Minimum Dry Density (MDD).
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | Standard / Specification - Appendix XIII
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | Verifying Document - NDM Results
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
69d85f65-b61d-579d-940f-2b691894d755 | note | Verification Activity: Activity - I
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Verification Activity: By - SE
940c74e2-d6b4-59ce-a549-e065a128c6e6 | checkpoint | 6.05.06 - Non-Structural Fill - Granular Mixed Materials
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - Mixed non-structural material requires proof roll to ensure compliance with the 7mm requirement. Proof roll to be done where soils cannot be penetrated via shear vanes or scala
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - TNZ F1 Section 10.5.1
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Site Records
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - Formation level
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
c83c1a95-6cc3-5b55-ac8c-57dd36cf1a2e | checkpoint | 6.05.07 - Organic Content
f09d0ff0-01ec-50cb-9988-3a078371cb3d | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
5d4c6d19-d8fb-5765-9b80-10ed32dbffe9 | note | Standard / Specification - Appendix XIII
ea12d870-db9e-5048-94de-56f316678975 | note | Verifying Document - Site Records
4b4f2a35-1e50-5341-80c6-541a73664b53 | note | Frequency - Ongoing
f77c9bbc-fb8f-5e0f-86c9-c66a4643254e | note | Verification Activity: Activity - I
dbb35f07-7f2f-5414-a8b4-c69adbcef37c | note | Verification Activity: By - SE
8a6e4423-2a66-5b93-af2a-67e156f07a85 | checkpoint | 6.05.08 - Water content
cb670aff-3430-5d2c-ac3e-1482548f09ee | note | Acceptance / Conformance Criteria - The water content shall be tested by collecting 1 sample with every individual NDM test.
e3ea5880-55a7-54a4-9ee9-9323b972ab79 | note | Standard / Specification - Appendix XIII
eb4e4dcc-9679-50a0-8275-a70670f63fd0 | note | Verifying Document - Water Report
5b1465a0-9c5b-51b0-8b4b-9694e85f2324 | note | Frequency - Every NDM
a3b40c94-fe59-5b33-bcda-878d287d2995 | note | Verification Activity: Activity - I
696e1611-579b-5ae6-b3d8-5701063db1b8 | note | Verification Activity: By - SE
94ecb72f-b511-5fef-99c9-b75caaae5292 | checkpoint | 6.05.09 - Bulk Density, Dry Density, Air Voids
2ff13b7b-02c2-5a7b-8118-f41c41b17271 | note | Acceptance / Conformance Criteria - The Bulk Density, Dry Density, Air Voids shall be tested by collecting 1 sample (Sample Tube) for every 10 NDM Sets completed.
c39051d9-945b-528b-a585-33d79297aaee | note | Standard / Specification - Appendix XIII
dd793333-b4d3-5ea8-9644-25cf03ccc6e5 | note | Verifying Document - Lab Report
d69a3d8f-c798-532b-a15c-6f7e4df14e4c | note | Frequency - 1 Test Performed For Every 10 NDM Test Results Provide
2d5640eb-932b-5ba9-87eb-2c7ce14f8894 | note | Verification Activity: Activity - I
c9a19186-767d-535f-9741-6cc10a171f11 | note | Verification Activity: By - SE
c36b68ad-c33c-4832-a02c-4e28d1d9f3b8 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
daaa2836-5260-50ab-9bc4-072baf8584b0 | textbox | Contractor's Rep Name:
3e1b56aa-f9ad-51e4-bfcb-1576992c47a5 | textbox | Engineer's Rep. Name:
1bcac10e-3731-5870-adfa-4a36f39232a6 | date | Date:
22eb8dab-2be9-4b2a-8eb4-2c823136bd46 | signoff | Add Signature
7ef67510-0df3-5ffd-8f0a-98e6db786e5f | checklist | ITP - Fall Protection Fencing - 304 - Rev B | itp | ITP - Fall Protection Fencing - 304 - Rev B
4bda4dd5-6c7e-5f3b-95d6-b355b65894a7 | section | 4.20 Fall Protection Materials
0f8be9ea-2f02-50c1-9123-8159ff69358f | checkpoint | 4.20.1 - Fall Protection Fence Materials
d534393e-c98b-5a5f-88e5-64e66d165722 | note | Acceptance / Conformance Criteria - Safety fence design load shall be in accordance with NZS1170.1: Table 3.3 Type C3. All steelwork shall be hot-dip galvanised in accordance with AS/NZS 4680:2006.
12d18b70-4754-54df-b0ff-579be8bd10d9 | note | Standard / Specification - PS 18.6.1, PS 19.25.1
90acc04b-3d0d-5510-8d15-444e09a6130d | note | Verifying Document - Datasheets and Mill Certs
6f9bf2a8-5f37-5ea8-96fd-e2d3b5780181 | note | Frequency - Prior to use
d48e1a79-c7aa-5ef1-a62c-d564c2cf9fec | note | Verification Activity: Activity - R
f7301aa3-b12f-5a7d-9e03-de6ee2710e05 | note | Verification Activity: By - SE
46972395-5948-5e78-9495-0c404383cb43 | checkpoint | 4.20.2 - Fall Protection Fence Epoxy
3ffc1176-4a53-5979-a72b-936c446736ff | note | Acceptance / Conformance Criteria - SikaDur UA Epoxy Repair Mortar or a similar approved mortar.
888857b2-3f93-58fe-89ac-a581671c2523 | note | Standard / Specification - PS 18.6.1, PS 19.25.1
392e97e3-2841-5c62-b773-b72f484c18da | note | Verifying Document - Datasheets
40f5841d-63d4-5d85-b325-fa88721ace0b | note | Frequency - Prior to use
4fdf8ad1-79ab-520b-9bfd-d56df3e219ec | note | Verification Activity: Activity - R
06fbaaf7-5803-56b0-8dff-d480289c2989 | note | Verification Activity: By - SE
37a8b92e-54e2-52c6-a615-1158e70eafb6 | checkpoint | 4.20.3 - Fall Protection Fence Base plates
c6075165-c7cf-5771-a980-559c64682dfc | note | Acceptance / Conformance Criteria - Mild steel baseplate with holes shall be Hot Rolled Grade 250 complying with AS/NZS3678:2016 (AS/NZS3678-350).
4b41d91b-c9a0-5537-9d27-94e2b233a4e8 | note | Standard / Specification - PS 18.6.1, PS 19.25.1
e3de1f7a-75d1-5e92-a5f5-25a2f3f42cae | note | Verifying Document - Datasheets and Mill Certs
feb96f00-8423-5b78-8e42-23e3024b5011 | note | Frequency - Prior to use
548f3da1-c304-57d3-ad68-0a54878b7681 | note | Verification Activity: Activity - R
98c6c5e0-35ec-5a25-a348-f81fafe1cdd7 | note | Verification Activity: By - SE
c8b391db-10fa-5ea9-aff5-2da1abe64716 | section | 11.01 Fall Protection Fence
5b0cf638-dc9b-51ce-a49e-4d9030375a52 | checkpoint | 11.01.1 - Fall Protection Fence Installation
5e78e5a0-023d-5358-87d2-60f1d570d583 | note | Acceptance / Conformance Criteria - Safety fence system shall be Webforge and shall be installed in accordance with Manufacturers Specification. Posts are to be positioned vertically in both the longitudinal and transverse directions. All rough or sharp edges or protrusions to be buffed smooth. All rails should be jointed within post sphere. Rails should be fixed to spheres at every post by welding.
58981d55-b82d-5013-be23-19f6a0267f28 | note | Standard / Specification - PS 18.6.1
f67d5198-9982-5f30-a180-5d651f23c570 | note | Verifying Document - Site Records
dff54f59-1628-534e-baf3-fba07a7a30f1 | note | Frequency - Each Fence
e9a223e5-bd46-5699-8728-f4c94082ad53 | note | Verification Activity: Activity - S
ded1d516-b4e0-5a76-9117-231f6508bb02 | note | Verification Activity: By - SE
8a59d9b1-2b89-5675-8bbe-6baaede81f3a | checkpoint | 11.01.2 - Remedial Painting
59882d18-98a9-5b49-9eca-a354a36e21e3 | note | Acceptance / Conformance Criteria - Damaged galvanizing shall be coated / repaired in accordance with Appendix E of AS/NZS 4680, e.g., painted with 2 coats of an approved zinc rich paint, such as Resene AmorZinc110.
a7c73dbf-05f7-5c63-a377-239927478c22 | note | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
3a5234fa-ebd5-563a-ba5c-4f8600ceb0c9 | note | Verifying Document - Site Records
5a7b2e2d-a230-5478-a31c-3f8c81bc4ccb | note | Frequency - Each Occurance
a56d27ed-980e-5558-9655-59ad0eed1938 | note | Verification Activity: Activity - S
85fd877f-efe2-5dd3-87b6-85be6753d510 | note | Verification Activity: By - SE
311c9835-2305-59cb-abe7-1a9a995c3533 | checkpoint | 11.01.3 - Fall Protection Fence Post Spacing
f639cf18-f630-5fb8-906a-fed0ebdeef22 | note | Acceptance / Conformance Criteria - Post spacing shall not be larger than 2m. Posts should not be placed closer than 200mm from the edge of the wall joints.
3fca7d61-5a9f-5414-8dd6-69d272fe991f | note | Standard / Specification - PS 18.6.1, PS 19.25.1
3cc53b4f-b9f6-57c2-933c-b08339d96eed | note | Verifying Document - Site Records
dade21b3-c1a5-500b-81be-06503d6f7c03 | note | Frequency - Each Fence
bbda1d13-8103-5702-bf81-4e5c8bb99689 | note | Verification Activity: Activity - S
f40856f5-5826-5d3a-b06c-42750adb6290 | note | Verification Activity: By - SE
98d6617f-4b8b-5df7-9a26-783cfab914b1 | checkpoint | 11.01.4 - Fall Protection Fence Reinforcement scanning
db453017-d7c8-589f-b7ad-7c09b620e0d9 | note | Acceptance / Conformance Criteria - Reinforcement scanning shall be carried out at every post location. If clashes with reinforcement are identified, the following amendments shall be taken, posts at which the rail is not spliced shall be moved +/- 50mm along the handrail alignment.
3e78432c-2413-5ef8-8642-0819e67f694d | note | Standard / Specification - PS 18.6.1, PS 19.25.1
072b2370-4443-5d28-afb5-f91880ef6c56 | note | Verifying Document - Site Records
b56d3717-9372-545d-b5df-1f4d2ea9a0c6 | note | Frequency - Each Hole
393d8ad4-7644-53f4-b957-61455f4e1e00 | note | Verification Activity: Activity - S
a2e7cf3f-513b-52b3-9d45-b6c04ed64340 | note | Verification Activity: By - SE
c0ed3146-519c-5f38-a733-ab540b4b40de | checkpoint | 11.01.5 - Fall Protection Fence Drilling
c29235a9-78ce-5757-a844-f72a53d871a1 | note | Acceptance / Conformance Criteria - Holes for fixings shall be formed using a rotary hammer drill. It is not permissible to cut or core through reinforcement. Should reinforcing steel be struck, the hole shall be abandoned, cleaned out using compressed air and backfilled with SikaDur UA Epoxy Repair Mortar or a similar approved mortar.
b8afa223-5de7-5985-a995-a1efb68e2212 | note | Standard / Specification - PS 18.6.1, PS 19.25.1
4ead022c-6ddc-53fb-8d95-666535df23e7 | note | Verifying Document - Site Records
db05bafc-3fc0-5f5b-80be-cc5c53ad72dc | note | Frequency - Each Hole
d3d31e7f-a8cd-59f8-bb88-21465b794f98 | note | Verification Activity: Activity - S
78441b7e-6dcf-5ac2-9c0c-7c3e7e63037d | note | Verification Activity: By - SE
6dac5825-6180-5f4a-a542-c44264c74a0d | checklist | ITP - General - Materials ITP - 105 - Rev B | itp | ITP - General - Materials ITP - 105 - Rev B
02f0e5f8-3a33-58bf-90df-ac924cdb4cfe | section | 4.34 Traffic Service Materials
37b9beb5-1885-556a-953f-bfb6fec25b3d | checkpoint | Safe Lane Delineator Concrete
19effbef-acd9-5bba-8cd4-edd09af3e647 | note | Acceptance / Conformance Criteria - Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days.
11556913-143e-5a79-b295-e58a531a922e | note | Standard / Specification - PS 23.7
1e51a11f-b208-548b-9728-6988a9eb3597 | note | Verifying Document - Datasheet / Mix Design
2b8a80d6-ade4-5f4d-b7ae-a075f39a37cb | note | Frequency - Prior to use
70029cd3-8a69-5a56-b6df-e5533b787a3c | note | Verification Activity: Activity - R
34131b73-6801-5edf-aa76-ccffef0e9f20 | note | Verification Activity: By - SE
6a118cdd-d837-55d5-b532-c3cbd03ef65d | checkpoint | Guard Rail Concrete
7b5daa8a-a456-5d6b-b482-c32d078e8653 | note | Acceptance / Conformance Criteria - Unless otherwise stated, concrete shall have a minimum compressive strength of 20 MPa at 28 days.
897f28c5-1117-52e9-8e3a-730e6bd232be | note | Standard / Specification - PS 23.6 M23
365a79f5-48dc-509c-bd45-55a362614f7e | note | Verifying Document - Datasheet / Mix Design
d0815811-7bc0-5895-86f2-80c07013476f | note | Frequency - Prior to use
dc0f9c5e-1451-5bfc-9753-8a4a2d5362e8 | note | Verification Activity: Activity - R
0ef25134-ae5b-5bd8-97a8-d370f8b45ad2 | note | Verification Activity: By - SE
c3c9f4c4-9ddd-5661-bf1d-798d6934f56a | checkpoint | Proposed Guard Rails
6b7da4b7-4141-5b2b-8f71-f8536f65aff3 | note | Acceptance / Conformance Criteria - The Contractor shall submit details of proposed proprietary materials and systems.
2a51c5d9-e3d9-53c8-b1c0-3d8e6e6e278a | note | Standard / Specification - PS 23.6 M23
88bde7ba-f0f8-5454-9535-9abfb444237d | note | Verifying Document - Datasheets
4c382bdb-3c3a-59d5-8e0c-2c98b807c614 | note | Frequency - Prior to material order (4 weeks prior to installation)
2a1ed6c8-2749-5636-9ae9-e1c14485ab51 | note | Verification Activity: Activity - HP
e9ba087b-6e55-5584-86e8-3da57335eb09 | note | Verification Activity: By - ENG
18509b26-c4a0-5aa2-a6f7-afcb39a96fd4 | signoff | AUTHORITY HOLDPOINT
82da5651-012d-5576-9a33-350255a3c695 | checkpoint | Guard Rail Maintenance Instructions
e1cdbaee-e2cc-514a-a800-66ab3e626c0d | note | Acceptance / Conformance Criteria - The Contractor shall submit details of the manufacturers maintenance instructions for the type of barrier installed.
1b7e6f89-f7d1-538a-b099-18bdcd6c1a90 | note | Standard / Specification - PS 23.6 M23
63e1de03-5c91-522a-80e1-f3547a0e296d | note | Verifying Document - Maintenance Instructions
e5f2d397-ae98-5843-931b-ef3fabbc4569 | note | Frequency - Upon completion of the Guardrail Construction
4cedfcab-d534-5b2b-81a6-945812416df0 | note | Verification Activity: Activity - HP
d9bd5441-dacb-5a33-9533-6d42fd2fc7e0 | note | Verification Activity: By - ENG
766b14d6-08d5-5042-b913-4bd987b5f8bd | signoff | AUTHORITY HOLDPOINT
e220e36c-c5b4-56e1-99a1-aa71ea3dcc81 | checkpoint | Coloured Surfacing
c3280aae-0c49-5333-ac80-bfff342cd0d7 | note | Acceptance / Conformance Criteria - The contractor shall provide evidence to the Engineer before preparation and marking of the surfacing, that the material conforms in its entirety to the requirements of NZTA P33.
50d46e7e-37a3-5050-aab6-2261eb25036d | note | Standard / Specification - PS 23.4
b970b67a-86f4-5d20-ad4f-bbb766bd36d3 | note | Verifying Document - Datasheets
1c6a80ad-5161-5c93-937a-dee8244625c8 | note | Frequency - Prior to use
6951f0cf-ce48-5af0-8c4c-6133f05aa6c7 | note | Verification Activity: Activity - R
8b9d6c95-79cb-5c17-b4a1-90a2be02c375 | note | Verification Activity: By - SE
f3b9b3dc-7e64-5889-9e4a-f17c88433ce5 | section | 4.35 Sign Materials
fb4903dc-1453-54b3-a8f2-273cf6de2731 | checkpoint | Retro-reflective sheeting
3dce215c-cfc0-5046-9610-12de0c13412f | note | Acceptance / Conformance Criteria - All retro-reflective sheeting must be approved for use in New Zealand and comply with the following requirements of NZTA P24 Specification for Permanent Traffic Signs and AS/NZS 1906.1: 1993 Retro-reflective Materials and Devices for Road Traffic Control Purposes, Part 1 Retroreflective Sheeting.
f13be10c-440c-5800-88b5-509cabe716dd | note | Standard / Specification - PS 23.2.6
7bb8e3b1-6ca8-5d2c-adc5-c9e5ba135220 | note | Verifying Document - Datasheet
d74b35b3-6cf3-5686-ad58-f8a7fa5ff4bc | note | Frequency - Prior to use
e7dfc9b0-eb04-5476-b879-c47000c82a64 | note | Verification Activity: Activity - R
f68606e5-e9d3-5496-bfe5-c9a14a31861a | note | Verification Activity: By - SE
46263b37-660b-5112-a628-5e032b94ed06 | checkpoint | Anti-Graffiti Coating
79b57677-43f0-5383-b74b-83d9c28e070f | note | Acceptance / Conformance Criteria - Graffiti protective coating shall be applied to all ground mounted sign and shall be approved for such use by the reflective sheeting manufacturer and shall maintain all guarantees for the sign.
349a86fa-17b7-585a-8f27-d236b7d684a3 | note | Standard / Specification - PS 23.2.14
65118095-d333-5305-b6d0-cc0f3741bd08 | note | Verifying Document - Datasheet
9f92097f-2ab2-5da3-8e68-682e019efa5a | note | Frequency - Prior to use
d60ffc6e-6724-5e9b-9b7d-4810f4c4717a | note | Verification Activity: Activity - R
091e68ac-8f17-5f42-839c-8a7145f833d1 | note | Verification Activity: By - SE
4c977703-afab-5e4d-956b-48a72fadd524 | checkpoint | Dew Effect Coating
33a5d7fa-440c-55a1-8fca-85b63d0d1b3c | note | Acceptance / Conformance Criteria - All overhead mounted signs, except for bridge name plates, shall be manufactured with an overlay that is designed to prevent dew droplets forming to overcome the phenomenon known as ‘dew effect’.
4b1262a3-6343-5eff-aa85-7e7d9d6661a7 | note | Standard / Specification - PS 23.2.15
539a919e-0ebd-5553-9b32-9648967530c5 | note | Verifying Document - Datasheet
b91f0044-692a-5c59-b9ae-b837d6e37401 | note | Frequency - Prior to use
5e19220d-d846-522d-943c-69a2da62f596 | note | Verification Activity: Activity - R
9da37815-21e9-59f7-872f-c3a4e8fde045 | note | Verification Activity: By - SE
a9cd9ad9-2c06-5476-b2a3-985c9209bfbc | checkpoint | Sign Shop Drawings
8e1c1532-315a-5442-a4a0-b7f5d09d7289 | note | Acceptance / Conformance Criteria - The supplier shall prepare shop drawings detailing the panel layout, positions of channel framing, and assembly systems prior to the manufacture of any sign. The shop drawings shall be submitted for review and comment at least ten working days prior to manufacture of the sign.
e264514e-e5a4-5244-bdd2-3596c5a23831 | note | Standard / Specification - PS 23.2.6
9afd839b-5872-50aa-bd6a-3477f892a251 | note | Verifying Document - Shop Drawings
14685484-36c9-560e-bf91-66c289063cb4 | note | Frequency - At least ten working days prior to manufacture of the sign.
d6319ecb-b441-59fe-8c92-f85b5d809e3c | note | Verification Activity: Activity - R
cd3c81ee-8f3f-5ba8-8be6-17d962653c2d | note | Verification Activity: By - SE
4f9280e7-ef18-59f2-a42c-3ea123970d98 | checkpoint | Timber Posts
3a996301-55ec-5c03-ae1c-ed23f7a7de3a | note | Acceptance / Conformance Criteria - Timber posts shall not exceed 100mm x 100mm section size. They shall be Building Grade or Number 1 Framing grade timber as specified in NZS 3631, dried to 20-24% moisture content, and treated in accordance with the New Zealand Timber Preservation Council’s requirements as specified in NZS 3640 for Hazard Class H4. The timber finish may be gauged or dressed. The timber posts shall be primed and finished with white high gloss paint over the length above ground level.
92b2da43-b60c-5967-a4ed-1a05e1588330 | note | Standard / Specification - PS 23.2.19
c716603b-327a-53ef-b579-e76367dda318 | note | Verifying Document - Datasheet
5f62ed8f-846e-5519-8f0a-d0f7f6c1cc24 | note | Frequency - Prior to use
2843fad2-d046-5d81-b416-8a49e9fa43f0 | note | Verification Activity: Activity - R
796ab116-89a5-5aea-b306-dea439f70cbd | note | Verification Activity: By - SE
75e2e437-d482-56e0-b460-0b890c596457 | checkpoint | Steel Posts
dbeeee6f-0b7e-5a16-8afd-a9184868e8e1 | note | Acceptance / Conformance Criteria - Steel posts shall be of an approved frangible design. They shall be hot-dip galvanised and finished with white high gloss paint. The paint system shall be specified and applied in accordance with AS/NZS 2312.1. All poles shall be fitted with white PVC caps.
0f88510f-5e11-580d-b82b-0749cdbcbe07 | note | Standard / Specification - PS 23.2.20
fc6b81d9-18b6-593e-b125-0421b40f3e89 | note | Verifying Document - Datasheet
1ec08cee-0159-5a47-adad-3b2f0be7000c | note | Frequency - Prior to use
99532200-1ce7-5a05-984e-5cf3de2b909c | note | Verification Activity: Activity - R
67c34503-0627-5408-8b4e-bb8d536a556b | note | Verification Activity: By - SE
293ad53e-adf5-5508-87aa-30ebedb8b9b8 | checkpoint | Aluminium Poles
863cffe6-bf7d-5e04-9cd4-a37c4ca3e13a | note | Acceptance / Conformance Criteria - Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps.
c4b32707-9358-51eb-ae57-19d72ea58c21 | note | Standard / Specification - PS 23.2.21
aa713b37-4cb1-519a-ac76-1ee910bc72f2 | note | Verifying Document - Datasheet
7b8898f2-296e-5c3b-86f1-5054a4f11201 | note | Frequency - Prior to use
9c8ebb6a-fdce-5767-b1d0-fd076d58a157 | note | Verification Activity: Activity - R
c60d96a4-f828-54d1-a2c6-94e6bc7eb4d1 | note | Verification Activity: By - SE
a7659370-c03b-5db9-be5c-70e1fac35af5 | checkpoint | Impact Resistant System Posts
4710c456-f786-515b-a496-d3042e01ced1 | note | Acceptance / Conformance Criteria - Aluminium poles shall conform to Alloy 6261 T5 as required in NZTA P24. All poles shall be fitted with white PVC caps.
ce108f42-14de-5a4d-bb67-46edfcad8cbb | note | Standard / Specification - PS 23.2.22
8d5c8c69-a3d4-59bd-87fb-153a82392e27 | note | Verifying Document - Datasheet
0747509f-e000-5931-b474-84136822e767 | note | Frequency - Prior to use
2c4602e9-a9d6-50d1-ae5a-fd5a5972cf74 | note | Verification Activity: Activity - R
f5795dad-992a-5939-846f-b25ed8128b3b | note | Verification Activity: By - SE
ce15b766-20bc-5a42-abf4-193629c68e16 | checkpoint | Sign Fixings
d0faefd5-7ef1-535d-9d90-6653214f1906 | note | Acceptance / Conformance Criteria - All signs shall be installed using approved sign support channel bracket fittings that do not penetrate the front face of the sign. No bolts, rivets or other fixings shall penetrate the front face of the sign.
1d181827-41a8-5180-8173-8aa08bc8bf8f | note | Standard / Specification - PS 23.2.23
02b46a12-8d5d-5b22-945e-ba16116370b9 | note | Verifying Document - Datasheet
41c51abe-a946-5b67-923a-ac1b3dd21085 | note | Frequency - Prior to use
5b48e77b-bfff-5269-b657-1b4ba85d8e45 | note | Verification Activity: Activity - R
85ba5f30-a9a6-5a76-a30a-88145f85fdf9 | note | Verification Activity: By - SE
820304ce-df57-54a2-b804-b4117be4130d | checkpoint | Training
4c83b163-939f-5b18-84c0-7c701d9f7205 | note | Acceptance / Conformance Criteria - The installer shall demonstrate prior to undertaking the works that its staff has attended, or are scheduled to attend, a recognised training course in the handling, installation, and maintenance of retro-reflective road signs.
a0c41f0e-a69e-5b1c-8f8b-d8a0486ae02b | note | Standard / Specification - PS 23.2.25
55e29097-e69f-5ce0-a2fb-51aa7763f5ed | note | Verifying Document - Training Records
3a9431f2-ca78-58e7-84d7-3ff0ab122ba4 | note | Frequency - Prior to Installation
ed1350bb-3e24-51e9-bc49-ec5ca6553d26 | note | Verification Activity: Activity - R
270562aa-1793-522b-85cb-b5d45438ca95 | note | Verification Activity: By - SE
087c5fd4-dca6-58e0-a9d3-7e8072ca7fa2 | section | 4.36 Long-life Road Markings Materials
929fcfad-a6c0-52e3-9326-b04bc0f4f91b | checkpoint | Applicator Approval
c6d62225-8afe-5e56-ac75-1d32782ad7f4 | note | Acceptance / Conformance Criteria - The applicator(s) used for the contract works must be certified to NZTA/NZRF T/12. No installation shall commence without the written approval of the Engineer accepting the certification and suitability of the applicator(s) proposed.
178f3cee-0933-5db3-9ec2-9db96dd9018f | note | Standard / Specification - PS 23.5.2
fc96b716-4dff-5393-8b74-7c2440cece3d | note | Verifying Document - Engineers Approval
551ff9cc-b71b-50a4-b3a3-79f2e624f092 | note | Frequency - Prior to Installation
0ab51987-40ce-57a8-8d17-35950a846f6b | note | Verification Activity: Activity - HP
b27e809f-dab7-53e7-9549-e05c23c3025d | note | Verification Activity: By - ENG
4809d6fc-add4-5047-b9f2-5ff76f44bd75 | signoff | AUTHORITY HOLDPOINT
2a03fe63-f2cc-58e5-a7aa-d65a63771ef8 | checkpoint | Long-life Road Markings Materials, Marking System and Format
2e6ff3ac-8b10-5a9e-a24a-2ef936af96b5 | note | Acceptance / Conformance Criteria - Only products approved to NZTA specifications are to be used. The Contractor must submit to the Engineer details of each of the products that will be used in the contract works. The submission must include:
f7cd5004-dc69-53a7-a010-a05df17ca0ed | note | a) Material Type (Cold Applied or Thermoplastic)
aec81389-7d7a-5115-8de6-07c766653693 | note | b) Format of the marking (Structured only)
e6a279dc-62c0-52b2-be68-60c9a210a6e8 | note | c) M07 or M24 approval list with the product highlighted, or NZTA approval letter or NZTA interim approval letter.
bda77dc6-5cf9-5a4a-8286-0637abe66b9d | note | Standard / Specification - PS 23.5.3
2a5139b8-327d-5258-aa7b-0ea1ff6ad9fa | note | Verifying Document - Engineers Approval
b01f735a-f995-5f56-963d-2e50f69184fd | note | Frequency - Prior to Installation
c064fb27-4fc3-5304-aa5b-0283165cc307 | note | Verification Activity: Activity - HP
678dc05a-ac9f-5338-b0d2-01542ca5d1d4 | note | Verification Activity: By - ENG
d36eda99-126d-5e26-8960-7acb90647d95 | signoff | AUTHORITY HOLDPOINT
d2032dda-9e1c-5230-bb6f-47faa5a5760d | checkpoint | Installation Limitations
0bf56af8-d33c-5ed5-886d-73e68f393ccf | note | Acceptance / Conformance Criteria - The Contractor shall supply the Engineer with the Supplier Specifications or Instructions on Installation for the long-life road marking system proposed to be used. No installation shall commence without the written approval of the Engineer accepting the suitability of the long-life road marking system proposed.
2b0ef2d0-0596-5956-94b0-868678c0a834 | note | Standard / Specification - PS 23.5.4
1f6f287b-2435-5780-a7a4-ee365b44856e | note | Verifying Document - Engineers Approval
048412fd-c698-549a-812b-f814b81d3996 | note | Frequency - Prior to Installation
f5de9df8-3ce4-5e27-af41-d36e84d8ac72 | note | Verification Activity: Activity - HP
da7311c9-9980-5c3d-921c-5fe43833b284 | note | Verification Activity: By - ENG
d78e12e4-23b6-5bf8-87ea-bc0878f7b38e | signoff | AUTHORITY HOLDPOINT
ca3735be-2229-556c-8df4-4ca50f65cb52 | checkpoint | Glass beads
5072e5f4-25b9-540c-8961-8256985436ab | note | Acceptance / Conformance Criteria - The Contractor shall ensure that glass beads have appropriate adhesive coatings for the long-life road marking product being used. No installation shall commence without the written approval of the Engineer accepting the suitability of the glass beads proposed.
87def1d5-fa07-59b1-bc5d-0fc90487722b | note | Standard / Specification - PS 23.5.5
eb97bcf0-58e0-5809-bb0e-740fd09b6e6e | note | Verifying Document - Engineers Approval
b118aab4-d917-5446-a430-72724a6705f3 | note | Frequency - Prior to Installation
f3857a3b-367c-58c3-a308-e767d81baf03 | note | Verification Activity: Activity - HP
bd0ef787-75ad-5d2b-b536-3189daa82a00 | note | Verification Activity: By - ENG
bce6171e-7a67-5370-adfd-381532a6576d | signoff | AUTHORITY HOLDPOINT
4f67c6ff-9945-532a-87fc-d6a73512f2ec | checkpoint | Raised Pavement Markers
09ee1290-388b-56fd-b28f-f66021c89fcc | note | Acceptance / Conformance Criteria - All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers.
9a832092-c716-59f1-ad1f-e6c2026e7bc9 | note | Standard / Specification - PS 23.5.6
b81a8362-c37a-59c3-89bc-c29a41107ffc | note | Verifying Document - Datasheets
d4915b32-65d6-5a3a-9391-45979899323e | note | Frequency - Prior to Installation
71175db6-3e26-5c25-a0fb-1327e52b4be3 | note | Verification Activity: Activity - R
38bfb03e-6c97-52bb-a995-f97b06ccf160 | note | Verification Activity: By - SE
70c6888e-72be-506d-b844-57101dd8c7c9 | checkpoint | Application Crew
68f486db-6061-5dd0-9ca8-30cc5ca27080 | note | Acceptance / Conformance Criteria - The Contractor is to notify the Engineer of any proposed changes to the crew. The Contractor shall provide a CV outlining their qualifications, skills and experience related to installation of long-life road marking systems. No installation shall commence without the written approval of the Engineer accepting the suitability of the nominated crew or any changes proposed.
2b570fe8-c005-5353-83d3-d9d42d6f6bfb | note | Standard / Specification - PS 23.5.7
2680ba70-df9c-574c-ad9e-0558400320f4 | note | Verifying Document - Engineers Approval
8d867046-2cbf-5f55-b1ba-c4db9bb039ce | note | Frequency - Prior to Installation
9d3041fb-8333-53e0-adf3-ae7ed0f170cf | note | Verification Activity: Activity - HP
90db0cc0-28ad-57cb-bb97-a8f3ae543784 | note | Verification Activity: By - ENG
79e7d6ba-8c7f-52e7-8feb-2f59d3706cf0 | signoff | AUTHORITY HOLDPOINT
c5306618-fba2-5419-964f-5dc47278d733 | section | 4.37 Pavement Marking Materials
68304bfb-d1b4-50c5-8cba-2c659152c101 | checkpoint | High performance markings
1b35f74e-04fd-5bf1-9b21-37590416d494 | note | Acceptance / Conformance Criteria - All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified.
aad1074b-bef6-5bad-a569-3b53069807e7 | note | ○ The Contractor shall nominate the brand, type and proposed application methods for materials to be used. This information shall be provided for approval prior to application.
5be959c2-ba26-52f3-918a-19ad74750a50 | note | Standard / Specification - PS 23.3.1
03638dd2-7ae6-51dd-8545-2954456b1aa2 | note | Verifying Document - Datasheets
19e014e6-e653-5647-aa55-380f10193554 | note | Frequency - Prior to Installation
1781c2e3-e51d-59a5-9720-6dba69ab2c3a | note | Verification Activity: Activity - HP
dbbf64df-a14c-5c7a-a9fc-006279adaac1 | note | Verification Activity: By - ENG
98ac9afa-8858-5f5a-8789-1e8c1828b20c | signoff | AUTHORITY HOLDPOINT
1b753504-b0c2-4e5d-810a-c2ec2a2c5609 | checkpoint | Glass beads
05b93d96-8876-5297-ac9f-fefaf7cee856 | note | Acceptance / Conformance Criteria - All glass beads added to the paint for reflectorised line application shall be in accordance with AS/NZS 2009 Glass Beads for Road-Marking Materials and the current NZTA Policy and Testing Regime for Heavy Metals (T17).
f807fc4f-31e9-5027-90b8-b15cba3d389e | note | Standard / Specification - PS 23.3.1
ede378b3-c457-56bd-b491-bf5ef44fee82 | note | Verifying Document - Datasheets
cbea1fdb-7440-5e2d-bf18-906478070cbf | note | Frequency - Prior to Installation
814c7fe8-749e-523d-91fb-ddbff68e34fa | note | Verification Activity: Activity - R
638527ca-ddb5-5203-a357-cc638b2fc96d | note | Verification Activity: By - SE
8578d499-184d-44d0-a133-ac45142a4afc | checkpoint | Raised Pavement Markers
9a12fcac-cb77-5c68-ae1a-411960debb9b | note | Acceptance / Conformance Criteria - All raised pavement markers shall be in accordance with TNZ M/12 Raised Pavement Markers.
c46c1179-794f-5eec-826a-446e2c9fd7f8 | note | Standard / Specification - PS 23.3.1
e7a2dec4-cfc7-5a9f-b633-f9b7d502d36d | note | Verifying Document - Datasheets
99e8cd7f-b24c-5778-9025-40b83e492c6c | note | Frequency - Prior to Installation
f94c66fe-3eb5-5632-a05d-24c09f1deb0b | note | Verification Activity: Activity - R
5a418f48-a7de-5bec-8164-d57a806edcb3 | note | Verification Activity: By - SE
b8086ecc-f696-5e17-95b8-844cc78efc6a | checkpoint | Edge Marker Posts:
96017c4a-bca3-5743-81f3-a717cdfd642b | note | Acceptance / Conformance Criteria - Edge Marker posts shall be non-wood and shall comply with NZTA M14. Non-wood posts shall have current NZTA M14 type approval.
b69689ff-1b3f-5e5e-a676-d06a8b2a53ac | note | Standard / Specification - PS 23.3.1
388bb210-4a79-5b2b-b486-0971c88ad2ac | note | Verifying Document - Datasheets
2fdaa627-565d-5f3e-8dd2-77abe2fb3bbc | note | Frequency - Prior to Installation
ecdc37ab-5184-5446-86b9-2ba1487aa2dc | note | Verification Activity: Activity - R
31a70be2-7605-5693-bcf6-6ffc9ffb3dbf | note | Verification Activity: By - SE
34815f24-1def-541d-b84e-d248f5242ac7 | section | 4.38 Fencing Materials
6e27276f-e506-54c4-941a-944fc58b42e2 | checkpoint | Post and Wire Fencing Materials
8020a7d6-414b-5dcb-8a1f-3ed4dc5d194e | note | Acceptance / Conformance Criteria - All in ground timber posts shall be treated to H4 standard and all other timber shall be treated to H3 standard. All posts to be sunk to the required depth and supported to form a rigid boundary fence.
8695b7cc-5c33-50e1-b334-91958e3e16cd | note | Standard / Specification - PS 25.12.2
8e2f29d0-f567-5642-b6dc-4ff742323d0b | note | Verifying Document - Datasheet / Docket
9c2f0e01-4b60-5ffd-8add-e77fc664a118 | note | Frequency - Prior to Installation
94f85fb3-4643-50c7-b8f7-3133e87b4418 | section | 4.39 Landscaping Material Supply
cebfdad6-9811-5f03-bfb5-ac5c93b810d1 | checkpoint | Plant Supply
19885040-82fc-5df2-aabc-885fa142025b | note | Acceptance / Conformance Criteria - All plants shall be supplied true to the species and grades specified on the approved landscape plans and fill the specified planter bag. All street trees, unless specified otherwise, shall be of a minimum grade of 45 litres with a minimum 30mm calliper. All other stock shall be of minimum 2 litre grade for groundcover and 3 litre grades for shrubs.
35df21c1-dfb7-5794-a1e7-7c8d0b4cc54e | note | Standard / Specification - PS 25.2.1
7cbab7b9-5ec3-5833-9a70-26e566e482e2 | note | Verifying Document - Plant Details
f41b700a-4614-5ec6-9694-2b9d4cc02e6d | note | Frequency - Prior to supply
f2a9c150-3645-5d6c-a4df-3bb62f44f92c | note | Verification Activity: Activity - R
67bddbd2-a7db-5e0c-b4c7-3e0c574bbaf0 | note | Verification Activity: By - PE
7bbdd48e-cae5-51ac-bc10-d7dba5f0d74c | checkpoint | General plant species and quality
a4b9c1b0-5e49-5c6b-9915-8a7d42330b7b | note | Acceptance / Conformance Criteria - The Overseeing Organisation shall be provided with not less than five working days’ notice of dates upon which plants are to be delivered on site, so that arrangements can be made for quality inspection and confirmation of identification of plant material.
1f3f5dcd-980b-5874-9cfe-3e9c88f99fe7 | note | Standard / Specification - PS 25.2.1
b69f6bfe-e970-56d7-8bf1-03ea3c763e63 | note | Verifying Document - Notice
a9977f1c-781b-5ad0-8164-5785de4db402 | note | Frequency - 5 working day notice
cb543b8d-8764-568e-b3a1-4e8e0ecec5f7 | note | Verification Activity: Activity - R
3d79d9a7-ccd1-57aa-ae25-920e27a1a1a3 | note | Verification Activity: By - PE
a5403f9d-ea47-5d26-b2f7-5366ac8bc585 | checkpoint | Street tree grades, species, and form
bc4c30b6-ebfe-553f-b081-e2b801bc3b63 | note | Acceptance / Conformance Criteria - All street trees, unless specified otherwise, shall be of a minimum grade of PB 95 and be first grade nursery specimens. No substitution of species or grade shall be made without the written approval of the Engineer.
89bf71a0-b897-5a1f-b6e5-5a4928aa0961 | note | Standard / Specification - PS 25.2.2
6cbc26fc-43e1-512e-b249-7261516817a8 | note | Verifying Document - Plant Details
21bc7f78-e19c-55d3-ae27-a229f6e06ba4 | note | Frequency - Prior to supply
e90df438-f85f-5ef4-b09c-56571566a366 | note | Verification Activity: Activity - R
b04c6c17-f334-56b4-9f3f-275d8928801b | note | Verification Activity: By - PE
a899bdc3-6315-5702-aeae-7fab04624132 | checkpoint | Chemical applications for weed and pest control
a6ed2db8-1597-5d4f-b3f7-e45609f57aaf | note | Acceptance / Conformance Criteria - All chemical application on planted areas shall be carried out by qualified, trained personnel and according to NZS 8409 Management of Agrichemicals, any relevant local Herbicide Policy and manufacturers’ requirements.
39befe27-303c-5771-b963-6f855abc91f4 | note | Standard / Specification - PS 25.5.2
9ed3f02e-b92d-5a31-88d8-7b745e666add | note | Verifying Document - Qualifications and Datasheet
ba1b90db-30c7-5e57-8ca3-4677830ead0b | note | Frequency - Prior to Application
719c4c30-ef81-5b7d-aa86-b1b31af57e10 | note | Verification Activity: Activity - R
6516b74b-9e91-53a6-9f04-f2f47b0eb3f0 | note | Verification Activity: By - SE
8260d348-a4f0-5fc1-a453-caff6cea97e8 | checkpoint | Biodegradable plant guards
64b4da1b-57c7-5615-aec1-6c2288cf8e63 | note | Acceptance / Conformance Criteria - All plant and animal pest control used for the landscaping works shall fully comply with Section D of NZTA P39.
995579e8-9065-5f87-930b-b557042188b4 | note | Standard / Specification - PS 25.6
e50523c2-5fb6-526d-8775-d9255d879d51 | note | Verifying Document - Datasheet
3df408e2-8280-522e-9475-52efe70d4dc7 | note | Frequency - Prior to supply
733669f5-4afd-5fc2-be83-9f2bc40f17e1 | note | Verification Activity: Activity - R
e21ce141-3786-518a-95fd-c8df73ad4d85 | note | Verification Activity: By - PE
f6b8922e-b6e1-532d-88a2-e657324d53af | checkpoint | Fertilisers
39e467df-93c8-5527-8421-f175ecd84e71 | note | Acceptance / Conformance Criteria - Fertilisers shall be either an approved pelletised natural or organic fertiliser or an approved synthetic fertiliser.
7b1042ad-5fdd-5899-ac90-510970a1598d | note | Standard / Specification - PS 25.7.3.2
c7e469eb-0351-58ca-be81-c0578b76933f | note | Verifying Document - Datasheet
a127f36a-e752-57c3-b5d7-4b9f06ddfec1 | note | Frequency - Prior to supply
9eac1cf3-113e-585d-9149-50765a44fa6f | note | Verification Activity: Activity - R
92ab1bee-dca7-5bcb-8b40-c327d520061e | note | Verification Activity: By - PE
b99ce95e-6361-5c2d-89cf-62ecd71df6c7 | checkpoint | Imported Topsoil
30fc50a3-4815-5a5d-b48b-4679037c0c3d | note | Acceptance / Conformance Criteria - Topsoil, both imported and existing on site, shall be a loam soil of good quality, free draining, free of weeds and contaminates, free of building materials and debris, screened, health, and contain no pans.
46a3e3fb-e766-576e-b466-107a98b41262 | note | Standard / Specification - PS 25.8.1
6366ac05-bf66-5d50-b594-32aaf6db87e0 | note | Verifying Document - Datasheet
bb5b3f8b-9c18-57b5-8963-441a030dda1b | note | Frequency - Prior to supply
5d8ada70-4d57-54df-b0cc-d7b574e460e2 | note | Verification Activity: Activity - R
1535c5ed-e473-59ad-992a-dd1ce5724f1c | note | Verification Activity: By - PE
8d3a4ad4-b02f-5503-8724-d95ced184e2c | checkpoint | Biodegradable Weed Matting
7c56df14-2de0-587b-9561-baa4cf3bbcd3 | note | Acceptance / Conformance Criteria - The biodegradable weed matting shall conform with NZTA P39 and be coconut fibre mat, Woolmat or similar approved.
1e26a760-5795-5002-a72c-d520a91c5bb9 | note | Standard / Specification - PS 25.9.1
fd15424d-01fd-5433-ad51-d4680e368fd7 | note | Verifying Document - Datasheet
d36ccf4f-c625-5cbb-8e80-348d036b1767 | note | Frequency - Prior to supply
12ce1d95-cb97-59e2-be39-7a613f03560c | note | Verification Activity: Activity - R
bb5a6361-7d75-536f-8ba1-7c288db552a5 | note | Verification Activity: By - PE
ae398c82-552e-550f-ba5f-f6c8487df291 | checkpoint | Mulching fabric Testing
222b36e4-f63c-52fc-8a83-ee2152a8e68a | note | Acceptance / Conformance Criteria - A simple test to ascertain whether the mulching fabric is viable is to hold a sample to the sky. It should be mostly opaque. This density inhibits weed seeds trapped under the mulching fabric from sprouting, provides good moisture retention and assists with batter erosion control.
23a670e5-add1-559a-98c9-b2eb44d0f495 | note | Standard / Specification - PS 25.9.2
5578e51c-b663-5e4e-b7df-e76c53a3fe3d | note | Verifying Document - Test Results
fe5a90e2-9f63-599a-9c25-7d9bb0f7fe63 | note | Frequency - Prior to use
d0210e01-d3fb-502c-ae85-d5a8887babeb | note | Verification Activity: Activity - R
b19e2cd6-3e47-53e7-8bf9-5be590f1f2c2 | note | Verification Activity: By - SE
6f45ab60-5e94-56aa-96c7-ed81f3279779 | checkpoint | Mulch
df284f12-e82b-5ca1-b350-5bb2f3c72289 | note | Acceptance / Conformance Criteria - The mulch shall be supplied as scheduled, clean, and free of soil, sawdust and wood preservatives, and a sample shall be provided to the Engineer for approval prior to spread.
7de3ee7e-065e-507c-a320-d28e8079af48 | note | Standard / Specification - PS 25.9.2
e23d7adc-57a7-52e9-83b8-99a4cdf8e00a | note | Verifying Document - Engineers Approval
d62a26bd-ed46-5c7e-8d48-960e92470fcc | note | Frequency - Prior to use
7fdf5d24-f5d1-5d23-87b0-e16ad8d72347 | note | Verification Activity: Activity - HP
df6892d4-e396-54fc-abb1-9e5df513d6fb | note | Verification Activity: By - ENG
b661facb-74f7-5550-b001-91550738e5ba | signoff | AUTHORITY HOLDPOINT
47ad80b6-42aa-5697-80fd-76256ae1f480 | checkpoint | Turf / Instant turf
821eb557-e46f-57b1-92c2-286fe972682a | note | Acceptance / Conformance Criteria - The turf shall be of good quality in line with industry standards.
c126003d-e43b-5d6c-bbda-34d405c5a857 | note | Standard / Specification - PS 25.10.5
06ec02e3-60f0-5334-a06f-c6433af2c26c | note | Verifying Document - Datasheet
fb8e2ea0-14f2-5dfc-a8d9-7583ce52dd53 | note | Frequency - Prior to supply
e8f03fb9-b0a3-5a5d-ac11-6534c81f2719 | note | Verification Activity: Activity - R
ba3ad36d-7321-5a20-840e-681e2162b409 | note | Verification Activity: By - PE
99bff652-2153-57e6-8034-9240b42b0b0f | checklist | ITP - Kerb & Channel and Footpaths - 301 - Rev B | itp | ITP - Kerb & Channel and Footpaths - 301 - Rev B
b450594c-ec84-54ec-9f3f-1c2773ffab10 | section | 4.18 Kerb and Channel Materials
35d6a7e6-0b91-57b5-84fe-50f0cfd9f675 | checkpoint | 4.18.1 - Water and Aggregate
be5bf2bf-b7f0-553d-83fd-4c6e95443422 | note | Acceptance / Conformance Criteria - Water and aggregate for concrete shall comply with NZS 3121.
5a215f1b-60ab-5c36-8525-8b0602449b77 | note | Standard / Specification - PS 17.2.1
fda426a2-2352-550f-b2c8-50864efc9fcc | note | Verifying Document - Details / Mix Design / datasheet
a7b1ae37-fc22-543f-b1d3-4864d8108f54 | note | Frequency - Prior to use
804542b6-ac6f-57a6-815d-65b2be7fb0d1 | note | Verification Activity: Activity - R
88323dcb-a549-55e0-ba7f-64f6f54c6551 | note | Verification Activity: By - SE
5e32420e-78ef-566f-8eaf-7165303d8213 | checkpoint | 4.18.2 - Cement
168d81c6-7590-50a7-bc31-f1df0b22573b | note | Acceptance / Conformance Criteria - Cement shall comply with NZS 3122 Type GP.
47946d15-6767-522f-905e-650595871273 | note | Standard / Specification - PS 17.2.2
1bb1304b-581f-57e7-8463-f7b63841a3ff | note | Verifying Document - Details / Mix Design / datasheet
3f218ca8-5cf7-51b5-91a0-f270d456e597 | note | Frequency - Prior to use
ad10425b-eb9e-52cc-9512-c56a26e05be0 | note | Verification Activity: Activity - R
e5bafb61-d22b-553b-a482-ccf2fd6dbf5f | note | Verification Activity: By - SE
cfed8065-09b7-51e7-aa63-644d4fb6a58f | checkpoint | 4.18.3 - Concrete
227321ad-dc4f-52ca-ab2b-079a97c9e522 | note | Acceptance / Conformance Criteria - All concrete, except site concrete, shall be manufactured by an approved ready-mix plant unlesspecifically approved otherwise in writing by the Engineer.
3c29ede9-eb8d-5b0c-a580-771b54e061d9 | note | Standard / Specification - PS 17.2.3
d883e904-0de5-5c98-8acd-8a15771c8b41 | note | Verifying Document - Plant Details
fd1acf21-653e-50a9-b2c2-9d03c424a8a3 | note | Frequency - Prior to use
e4958fc7-50a3-53c4-b04c-4aad3883f610 | note | Verification Activity: Activity - R
3f63c732-b5ee-518a-b1d2-2547da65fffd | note | Verification Activity: By - SE
84ea3214-2794-56ba-ae54-8c0be1e48ced | checkpoint | 4.18.4 - 20MPa Concrete
49e8710c-e912-56d0-84c4-7f14e1a3a5e0 | note | Acceptance / Conformance Criteria - Concrete for structures shall be grade 20 and have a minimum crushing strength of 20MPa at 28 days except where otherwise specified.
7f6fde25-0b51-5845-bc7e-432bd0881a6a | note | Standard / Specification - PS 17.2.3
12af8429-6be2-5d4a-a9c7-aef78900c312 | note | Verifying Document - Mix Design
d46ad03e-e442-57f8-8c2f-a00bc533f7bd | note | Frequency - before the commencement of works
81dc0405-1c0c-59f1-ba45-d508b45ea5c4 | note | Verification Activity: Activity - HP
5adc0e8e-6297-512f-8d8e-5d474eaffb9f | note | Verification Activity: By - ENG
bbf9fbfe-236e-5726-9862-1822713aab3f | signoff | AUTHORITY HOLDPOINT
09c297e5-65aa-5e0c-a974-0d1e6283be28 | checkpoint | 4.18.5 - Mortar
f13f815f-73dc-584b-af5f-bbd24ddfb71d | note | Acceptance / Conformance Criteria - Mortar shall consist of two parts of fine, sharp, well graded sand to one part of cement measured by dry loose volume and well mixed by hand (unless otherwise specified), or in a suitable mechanical mixer, with just sufficient water to make it slightly moist. It shall be mixed in small quantities as required. Any mortar not used within 30 minutes of mixing shall be discarded.
baf0b90d-092b-59bc-91b6-922b136ee6fe | note | Standard / Specification - PS 17.2.4
8c2a6dd2-146a-5386-91e1-f7c230a1f3c3 | note | Verifying Document - Datasheets
79cf7990-0f77-5910-bca1-ced6eac4b2e8 | note | Frequency - Prior to use
ac70cd69-2d3d-5d3b-b9a0-1d2b899ab081 | note | Verification Activity: Activity - R
d6bbbb21-09d2-5a4d-9a76-8b39050a0877 | note | Verification Activity: By - SE
17bf4091-c90c-56a4-8dce-b1cdc35e4f9d | checkpoint | 4.18.6 - Reinforcing
ff92cf45-0025-5a84-91c8-81c914c5f593 | note | Acceptance / Conformance Criteria - Reinforcing shall be Grade 300 bars unless otherwise shown. Grade 430 bars shall not be substituted for Grade 300 bars without the approval of the Engineer. Welded wire fabric shall comply with AS/NZS 4671.
cbc4f871-bb3b-53d2-8fd2-aa68bcd6e3c5 | note | Standard / Specification - PS 17.2.5
7144abc7-39d1-5902-a41f-9bbf5ba47cd5 | note | Verifying Document - Mill Certs
63d97bf9-bbec-5bd7-8aaa-babd2a61ba77 | note | Frequency - Prior to Completion
f695a162-111a-506d-956a-f243031a6d81 | note | Verification Activity: Activity - R
9c1d510f-44be-57cd-a684-8ced0992afb4 | note | Verification Activity: By - SE
864eea11-fd83-503b-a405-f2d829407e82 | checkpoint | 4.18.7 - Kerb and Channel Concrete
301cae98-ba6b-5281-8689-8a0f2e97c0d5 | note | Acceptance / Conformance Criteria - Kerb and channel shall be cast in-situ using 20MPa concrete placed by an approved extruding machine operated by skilled personnel. The profiles shall be in accordance with the Drawings and shall be specifically approved by the Engineer before work is commenced.
11f4d84b-5222-5f86-bbb8-64be43567616 | note | Standard / Specification - PS 17.3.2
6eba89d2-e1c8-5397-a80b-112ca3a5ed28 | note | Verifying Document - Mix Design
3c80a496-6a9b-5a7d-a7cb-f78ed4bc7cff | note | Frequency - Before the commencement of works
57e0fae1-6728-5210-a269-e5cceec88611 | note | Verification Activity: Activity - HP
0556b86b-9ea7-56ec-8a94-d445ba637060 | note | Verification Activity: By - ENG
256883c6-3818-5119-8f1a-916efbf61e08 | signoff | AUTHORITY HOLDPOINT
f89e60d6-3e44-5ee7-888c-cf653f7f0ace | checkpoint | 4.18.8 - Machine Laid Kerb Channel Concrete
e2a5b46a-847e-5b91-a116-a5c909b5a2e8 | note | Acceptance / Conformance Criteria - Kerb and/or channel may be cast in situ using 25MPa concrete placed by an approved machine operated by skilled personnel. The profiles shall be in accordance with the Drawings and shall be specifically approved by the Engineer before work is commenced.
17fc7fde-b7bf-5be7-88ac-db875767918b | note | Standard / Specification - PS 17.3.4
a0092dbf-4d58-5fd0-ba55-413ac82fe9f0 | note | Verifying Document - Mix Design
623459f0-de21-548e-9fd0-f1e396ca6e98 | note | Frequency - Before the commencement of works
1b2840d4-40c0-57db-9e09-8657b5e31b83 | note | Verification Activity: Activity - HP
e250af6d-e43e-534d-acd9-295bbfa2d112 | note | Verification Activity: By - ENG
a81b8ec2-32ec-5a86-935b-9b633b8f5def | signoff | AUTHORITY HOLDPOINT
360e544e-001c-5ecd-9802-aa40a32da3ac | checkpoint | 4.18.9 - Island Infill Concrete
1bc18213-9965-59f0-a752-bdbc99c136e6 | note | Acceptance / Conformance Criteria - The new concrete shall be 100mm in depth, coloured “Indian Summer” and constructed in accordance with NZS 3109. The concrete shall have a 28-day compressive strength of 17.5 MPa.
9fa6b8e0-0d32-5722-ac4f-0e31cc08df16 | note | Standard / Specification - PS 17.3.6
ab2a4764-9abe-5a1a-94b3-deb0fb9548d1 | note | Verifying Document - Mix Design
a2c750b5-f76c-5b94-9d1d-1a28389700d3 | note | Frequency - Before the commencement of works
0f30ea9d-5e10-553e-80d8-41515e9e77bd | note | Verification Activity: Activity - HP
52fb4a28-a308-58c9-abab-fedeee00ff87 | note | Verification Activity: By - ENG
c54997e2-6199-57b8-9895-d1bca6b528e1 | signoff | AUTHORITY HOLDPOINT
c2502323-48da-5751-a099-38001ecb7ae4 | checkpoint | 4.18.10 - Kerb Profiles
b6789f3f-2dc7-56e7-adfc-de20535a70df | note | Acceptance / Conformance Criteria - The profiles shall be in accordance with the Drawings and shall be specifically approved by the Engineer before work is commenced.
3a6a6bf3-6a4e-57ab-8fd7-e8a05dee9457 | note | Standard / Specification - PS 17.3.2
0a1ea561-82d1-5dfe-9d07-f94f1c30de00 | note | Verifying Document - Profile Details
292014f1-d25d-5286-88c0-16dc1fe23e88 | note | Frequency - Prior to use
969fae7e-4f30-5f20-889f-e7e9bea01b8b | note | Verification Activity: Activity - R
99b9e027-ce62-531f-a250-c932b8c2431e | note | Verification Activity: By - SE
b7573628-0e56-559a-9352-52908fea995a | checkpoint | 4.18.11 - Shared Paths Concrete
336da877-4274-5646-a908-483d70472279 | note | Acceptance / Conformance Criteria - Shared path shall be constructed from 25MPa concrete and shall be 100mm thick. The concrete shall include 3% black oxide colouring.
cfd70809-dc89-5fae-b0ee-a90c9a0af3fb | note | Standard / Specification - PS 17.4
94cf8b49-2984-5f0c-9c3c-a956101bfa2a | note | Verifying Document - Mix Design
4a4b9333-bba9-534d-b5bd-6c4478603453 | note | Frequency - Before the commencement of works
67fd99e5-ccdf-50e0-a9c4-7e1bd95f0398 | note | Verification Activity: Activity - HP
1c89ba5d-b267-5685-9dcb-f33588dff937 | note | Verification Activity: By - ENG
9ea94921-3fb7-5bb8-bfda-dae1b167bc0f | signoff | AUTHORITY HOLDPOINT
1c8d5531-d41c-5ba8-bc71-3db35c3c411c | checkpoint | 4.18.12 - Roundabout Concrete Apron Concrete
8e723ab7-1a0e-52db-8492-2b1f660e2485 | note | Acceptance / Conformance Criteria - The roundabout apron shall be constructed from 40MPa concrete
0415aa84-ec35-538f-a33f-7a42c0f1614d | note | Standard / Specification - PS 17.4.2
33376cf6-bf6f-529f-b63f-c5e35f1fb2a3 | note | Verifying Document - Mix Design
fcd8e624-e658-568b-b5ec-2fa27884debb | note | Frequency - Before the commencement of works
ee3a082f-0b68-5e93-bdf5-6806930d96f2 | note | Verification Activity: Activity - HP
9d65e1c2-0fea-5572-b98f-53f823a97a1d | note | Verification Activity: By - ENG
dfdaa893-9356-5399-bda8-0dd0b104378b | signoff | AUTHORITY HOLDPOINT
8e13d980-e06d-53b0-9209-6b217d8d3ea5 | checkpoint | 4.18.13 - Driveway Access Concrete
23bdcb9d-be54-55d1-b6f6-e5a465ff4df2 | note | Acceptance / Conformance Criteria - The access roads shall be constructed from 20MPa concrete
1ce09dd8-83b2-59f9-aa2f-e97000d682d1 | note | Standard / Specification - PS 17.4.3
2f47e730-8ec2-5767-a520-82f8caf3613d | note | Verifying Document - Mix Design
aa13488a-cedd-5490-8f51-bab837f693dc | note | Frequency - Before the commencement of works
f70645f3-9a77-50da-9c97-0fa1aed37eaf | note | Verification Activity: Activity - HP
85a21515-fcda-5209-b5d8-499da012d0aa | note | Verification Activity: By - ENG
e6567858-b9f4-5377-99cd-f14240861000 | signoff | AUTHORITY HOLDPOINT
2b9e3009-cc4c-58fe-8df4-041e50d4e00b | section | 8.01 Machine Laid Kerb and Channel
b257ba37-167e-514b-81e9-fbc884bf53d8 | checkpoint | 8.01.1 - Saw Cutting
6cf388df-fc35-577f-8623-a9ae5415c96b | note | Acceptance / Conformance Criteria - Existing surfaces shall be sawcut at the limits of excavation if they are not to be reconstructed following the construction of the concrete kerbs and channels etc. Existing kerbs to remain shall be sawcut to 50mm depth on all exposed faces.
fd944808-c904-556d-9003-66844ce3abfc | note | Standard / Specification - Downer
f37553f4-4f0c-504b-891e-702ec78f0031 | note | Verifying Document - Photos
a6737b47-b898-54f9-804d-ee23eb45ecd0 | note | Frequency - Each Kerb
440f2025-0800-58df-945e-60a4604eea68 | note | Verification Activity: Activity - I
50af0888-61f8-5a50-bf06-6ec504987962 | note | Verification Activity: By - SE
8f3ad09d-7116-5c7c-bb26-1d7c1c8e1317 | checkpoint | 8.01.2 - Foundations
4c5a2760-066e-5ad6-bfca-1a62c5b87c61 | note | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
f1812c29-8ce2-536d-9038-19f6976fddce | note | Standard / Specification - Downer
6f0d0614-8f41-5a90-b2c6-a7ce7800124c | note | Verifying Document - Scala Report
5a7ae900-9a07-5858-9fba-6483e4ad7ead | note | Frequency - 20m
ab818df7-34f7-50dc-a738-458d1c5b1d0f | note | Verification Activity: Activity - I
d07cca8e-1f04-5a6e-a090-ab094b5b081d | note | Verification Activity: By - SE
f99bd44d-82ab-5015-9038-e529829529ab | checkpoint | 8.01.3 - Fill Compaction Testing
96c76541-70a9-5ddc-bc06-40876208d04c | note | Acceptance / Conformance Criteria - Fill shall be placed in horizontal lifts not exceeding 200mm in loose thickness and shall be compacted to at least 95 percent of the maximum dry density every 20m
0e8a6669-19b2-51d1-870a-b7cf1120bc31 | note | Standard / Specification - Downer
091b9c17-3d9c-530a-96d8-d96b7621d660 | note | Verifying Document - IANZ NDM Report
4c9b04b3-3871-5d07-a893-69209b12996c | note | Frequency - 20m
30df1319-c430-5cc1-92a8-22c0227339e7 | note | Verification Activity: Activity - I
1813f515-4dd0-5552-9ba9-3f6b928d5db2 | note | Verification Activity: By - SE
17911a48-52e9-5267-bac1-f4c40713c087 | checkpoint | 8.01.4 - Kerb String Line Inspection
b8f2be67-5b40-54a6-bb25-343c9a6892a1 | note | Acceptance / Conformance Criteria - Prior to laying, string lines will be inspected by the Engineer.
f9fe1f4a-7271-5167-9011-e9ccd9a91992 | note | Standard / Specification - PS 17.3.2
9525a333-b1b7-5f1d-8d92-0b3f08be853f | note | Verifying Document - Site Records
3c84b669-10a9-59d2-a22d-eca89b7e7e0e | note | Frequency - Prior to Pour
b3d3945b-0b9e-5b48-81c7-47814d539999 | note | Verification Activity: Activity - W
3a4d1cd0-9f74-5254-ab3f-6618a9593bbf | note | Verification Activity: By - ENG
3df325a3-ace5-5cff-9c4e-6dd2461ffcbb | checkpoint | 8.01.5 - Kerb
cf73faef-e540-5849-b69c-edb922217c89 | note | Acceptance / Conformance Criteria - Contraction joints (saw cut joints) in channels shall be formed at maximum 4m spacings, at right angles to the kerb line. The joint material shall be set flush with the surface and shall be a minimum of 25mm deep.
3b7bee5f-ec28-5670-a9b0-162a41ac7961 | note | Standard / Specification - PS 17.3.2
1871c867-9fbd-5095-9585-ab4979a4eba9 | note | Verifying Document - Site Records
d5ae75e3-8b02-5d40-855a-358a0739a8c6 | note | Frequency - Every 4m
5ea0feee-daf3-5823-a1c4-11849ac257a3 | note | Verification Activity: Activity - R
03f736ba-659b-5415-9e01-938f755c4258 | note | Verification Activity: By - SE
c0c96ea2-5633-54b8-ac19-219aae00d5de | checkpoint | 8.01.6 - Kerb Finish
09194d76-f3f8-5f5f-88c7-622da6846cf3 | note | Acceptance / Conformance Criteria - Concrete surfaces, un-trafficked by vehicles or pedestrians exposed to view above ground level, shall be smooth and comply with Finish F4 in NZS 3114. Horizontal concrete surfaces, trafficked by vehicles or pedestrians, shall be wood floated to comply with Finish U2 in NZS 3114.
4670f226-4665-5002-bcc4-c097779bbc4d | note | Standard / Specification - PS 17.3.2
19100c72-136c-58fd-b28e-756c9a3fe382 | note | Verifying Document - Site Records
33d58e13-2895-54d6-ace2-f475631baf6e | note | Frequency - Each pour
c9cbb6b8-c929-58f4-b127-5575052cdbb8 | note | Verification Activity: Activity - R
ff1848a5-c378-5162-b126-789cbdfc678c | note | Verification Activity: By - SE
156caa61-9855-51b3-9343-2f0eea3ee97b | checkpoint | 8.01.7 - Unreinforced Channel Contraction Joints
9f78cf9a-ae0e-583c-9e95-e8352c662cf7 | note | Acceptance / Conformance Criteria - Contraction joints in unreinforced channels shall be formed at 4-metre centres, at right-angles to the kerb line, by insertion of “Malthoid” D.P.C or equivalent strip. The joint material shall be set flush with the surface and shall be a minimum of 25mm deep. Contraction joints shall be coincident with joints in precast kerb blocks.
2671738c-5b2b-5942-9452-c0cd8e0aea0b | note | Standard / Specification - PS 17.3.3
6c0ffcb7-bfc7-5d67-ab83-b465840ad68c | note | Verifying Document - Site Records
0c22e6e5-4adc-5007-8e46-93d65daa1d4b | note | Frequency - Every 4m
1ee9f524-dcef-5412-babb-9004ad3a35cf | note | Verification Activity: Activity - R
1c588ba7-2104-55c5-a002-3f4c5081a940 | note | Verification Activity: By - SE
2dd54eb2-c6fb-5540-b9cc-bc87be03898e | checkpoint | 8.01.8 - Channel Finish
86a4fd35-0386-5850-bf2f-e8d1f84edc5a | note | Acceptance / Conformance Criteria - The top surface of channels shall be finished smooth and even with a steel trowel. Channels shallnot pond water at any point.
a2adc760-7f94-585d-8642-8cfc96ad41f4 | note | Standard / Specification - PS 17.3.3
b69d16dc-634c-5c18-8c1b-3156e67fa753 | note | Verifying Document - Site Records
399bace6-1acd-51ea-99bc-53a7e493f7cc | note | Frequency - Each pour
299d4570-263b-5430-bcde-f27115376a61 | note | Verification Activity: Activity - R
9bdcf3b9-1899-5e46-803f-f059da4cb580 | note | Verification Activity: By - SE
4dc57bfd-cff4-5fb6-83f9-8e016db99cf9 | checkpoint | 8.01.9 - Kerb and Channel Tolerances
7681ee2c-753c-5398-be80-ca1e5f8c5446 | note | Acceptance / Conformance Criteria - Tolerances for kerb and channel shall be ±5.0mm vertically and ±10mm horizontally. The deviation from a 4.0m straight edge shall not exceed 3.0mm.
0a82f234-6521-5757-9e64-8ff3c6d2bdb1 | note | Standard / Specification - 16.34.3
b2a381fd-0ffd-520e-b316-d9e8fed212cc | note | Verifying Document - Survey Records
3a1e17ef-29dc-572b-bc81-840e0123ba92 | note | Frequency - At the completion of the construction of kerb and channel
f46406e3-9b07-5481-b8bc-1043b1654325 | note | Verification Activity: Activity - I
d447dc3b-47b3-557f-ba1a-e609a62176ab | note | Verification Activity: By - SV
bcb5e257-4234-57b4-92fe-72748c4e50ea | checkpoint | 8.01.10 - Kerb and Channel Completion Inspection
5408ae0a-475b-5086-a22f-754d47964805 | note | Acceptance / Conformance Criteria - Engineer to review completed works including kerb and channel position, level and grade, and transitions between kerb types and at catchpit and catchpit manhole aprons / back entry lintels.
90e04a6b-59dc-5114-8cfc-346671ae967f | note | Standard / Specification - PS 16.38, PS 17.3.2
42b1bb3f-73ec-5cef-9526-91d9bdd32a65 | note | Verifying Document - K&C QA
c96872cf-a48f-5ee7-8611-2f1e440d9fe0 | note | Frequency - Upon compltion of K&C
5bcd98a0-64d4-5d95-879e-f2bae62d525a | note | Verification Activity: Activity - W
97fbd497-e3b9-548e-847e-f8493d868715 | note | Verification Activity: By - ENG
abd38c6a-ae0c-5330-8b48-d3f6e6165ee0 | checkpoint | 8.01.14 - Machine Laid Kerb and Channel - Concrete island infill
a9218090-c26d-5c43-a0f9-b560445017fc | note | Acceptance / Conformance Criteria - The base of the infill area shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved AP40 granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 100mm. Where infill is to be placed directly onto pavement surfacing, a 25mm thick sand bedding layer is to be provided. The base layer shall be well wetted with water immediately prior to the placing of concrete.
b03620f6-20d8-5e7f-bc3f-671857fa23b5 | note | Standard / Specification - PS 17.3.6
5e0b6178-81b3-52d1-86cc-c154143364a3 | note | Verifying Document - Site Records
279af7ab-efc4-50ce-8a31-5a81ce5674c5 | note | Frequency - Prior to Pour
2040fd97-cf60-58eb-91ff-3a01a56fae6c | note | Verification Activity: Activity - R
61e671a0-ffd4-537d-9670-50a43ab0fca5 | note | Verification Activity: By - SE
2494ec8d-e6d2-50f5-84a4-1bbfb52378de | checkpoint | 8.01.15 - Machine Laid Kerb and Channel - Contraction joints
f67c11ce-d078-5bb6-be23-58627d58e939 | note | Acceptance / Conformance Criteria - Contraction joints shall be formed at 5-metre maximum centres and at right-angles to the kerb line, by saw cutting or other approved method. Where a footpath adjoins the kerb, Contraction joints shall be coincident with joints in the footpath.
c3b57f4a-aca9-5acb-9f84-cff72a877fc3 | note | Standard / Specification - PS 17.3.4
953e8842-fbce-5bba-a8bc-f4f70dad761d | note | Verifying Document - Site Records
4791aeff-a766-55cf-8daf-905e01973ee2 | note | Frequency - Every 5m
af0b2243-51da-5eab-886d-cd2541ca4305 | note | Verification Activity: Activity - R
bb116a0c-9d63-58ac-96ac-0e610137c703 | note | Verification Activity: By - SE
eefa5f73-e1a7-5f02-9252-e6b6751a7606 | section | 8.01.17 Concrete Island Infill
2a037ef1-aca7-5149-9f6d-6f1ceda1ec9a | checkpoint | 8.01.18 - Foundations
45ac8a1b-e867-523b-8641-81c5447d04b3 | note | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
58377c51-3af0-59a4-9de7-36b0eaa9ca75 | note | Standard / Specification - Downer
e2372d6a-ec23-5fe9-81aa-7de02fae6a31 | note | Verifying Document - Scala Report
9369a171-89fb-56ad-8246-bc0f422ba36f | note | Frequency - 20m
64400ba3-e1ab-5f12-908d-ae4de590e967 | note | Verification Activity: Activity - I
c2e74d2a-8f64-5be4-b600-b1662c8429d2 | note | Verification Activity: By - SE
b498518e-e244-5306-9120-843fec76f199 | checkpoint | 8.01.19 - Concrete Island Infill Bedding
7d020bae-a73f-577c-9d73-91e1ce8349f8 | note | Acceptance / Conformance Criteria - The base of the infill area shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved AP40 granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 100mm.
d964d4b0-20e6-5dcb-9a00-c1428a5bae96 | note | Standard / Specification - PS 17.3.6
90f7bca8-f724-5566-be5b-5d284ca36b6b | note | Verifying Document - Site Records
438316db-a124-5837-bfb8-0e5dbcb0b645 | note | Frequency - Prior to Pour
ee3e78fd-74fc-5574-a2a2-57d95c67b15d | checkpoint | 8.01.20 - Fill Compaction Testing
3cdb3d31-8ad2-59a5-abcb-0cdcc7cd8aa3 | note | Acceptance / Conformance Criteria - Fill shall be placed in horizontal lifts not exceeding 200mm in loose thickness and shall be compacted to at least 95 percent of the maximum dry density every 20m
76141d2f-ac44-5b87-8be7-c20e17a3e414 | note | Standard / Specification - Downer
98cf1747-ebf0-5dcd-9ba5-ed75e9bf7e51 | note | Verifying Document - IANZ NDM Report
bfdc6180-085f-5a2a-bad8-39c0f845327c | note | Frequency - 20m
4bca33e9-c28c-5d56-b9df-aebe683591c4 | note | Verification Activity: Activity - I
259ababb-a4b6-582c-97b3-7cd46f60ec65 | note | Verification Activity: By - SE
291ced98-88ce-5ad1-b19b-eff80335f5bc | checkpoint | 8.01.21 - Concrete Island Infill Concrete Placement
f39d72e9-51c7-5dbe-9fe9-79935ef98311 | note | Acceptance / Conformance Criteria - The new concrete shall be 100mm in depth, coloured “Indian Summer” and constructed in accordance with NZS 3109.
dd077481-7e3f-5d35-8864-a7f450b23d08 | note | Standard / Specification - PS 17.3.6
fe48b36b-dfe1-58a8-afcd-cf17edb91710 | note | Verifying Document - Site Records
d0aef5ed-7622-542e-8129-ee41be18fcda | note | Frequency - Prior to Pour
abd4ca6c-508a-5186-9216-28d93cf8bf46 | note | Verification Activity: Activity - R
d547e7f6-8cb2-5f69-a2e2-5cf6aac1f7d4 | note | Verification Activity: By - SE
f94dea0d-a2f2-5950-a458-3db8c735444e | checkpoint | 8.01.22 - Concrete Island Infill - Construction Joints
5f9d1881-009f-52d2-aace-82cc7e165b20 | note | Acceptance / Conformance Criteria - The Contractor shall form construction joints every 4m by saw cutting or other approved method.
83cd5651-ef99-5fde-85f1-8a4f35051006 | note | Standard / Specification - PS 17.3.6
365062e5-0bdc-5923-9dd7-d044c9fea4f7 | note | Verifying Document - Site Records
dd392e34-0959-5fc4-bf64-29fb16003a22 | note | Frequency - Every 4m
649d978a-47b2-5f80-b0e8-10463d3986cf | note | Verification Activity: Activity - R
b083edbb-9e50-580d-9627-61f0fd9d8b60 | note | Verification Activity: By - SE
2c018550-bce4-5b2c-8f7a-db1b162ee682 | checkpoint | 8.01.23 - Concrete Island Infill Finishing
cb0454b8-f237-51fc-a779-883a893c21e2 | note | Acceptance / Conformance Criteria - The edges of the infill shall be neatly chamfered. Concrete shall be poured in one operation and without interruption between formed construction joints. The whole of the surface shall be screeded, and after the initial set, it shall be carefully broomed to achieve a NZS 3114 class U5 finish.
e536d3dc-6b1d-5731-9271-53b8690478f6 | note | Standard / Specification - PS 17.3.6
5cb91d59-5c6c-5712-baaa-1b69f621e389 | note | Verifying Document - Site Records
e6283326-9423-54c3-b702-3315f8a13520 | note | Frequency - Prior to Pour
5daeb881-a07f-5710-a24b-6b807388e919 | note | Verification Activity: Activity - R
f8b50a23-ada9-594b-9abc-4852f4081398 | note | Verification Activity: By - SE
0e9e7707-42e6-560d-83d5-647d158f3678 | checkpoint | 8.01.24 - Concrete Island Infill Curing
5d12cbd2-1e02-5cc0-97e5-9d85903d605c | note | Acceptance / Conformance Criteria - The finished work shall be kept continuously wet by approved means and shall be thoroughly protected from frost, from direct rays of the sun, and from drying winds, for at least seven days after pouring. The concrete shall be laid so no water ponding occurs on the surface after completion.
770b8af7-0c5e-57c7-9e79-c5f0b0c49477 | note | Standard / Specification - PS 17.3.6
a0e479b1-c22d-53d2-be9c-6f02db565afb | note | Verifying Document - Site Records
5c9713bf-181d-599d-b2a9-fab942ce4f84 | note | Frequency - At least seven days after pouring
deda4d81-8392-5ad9-93ba-62f63ce84512 | note | Verification Activity: Activity - R
6694150b-a490-52c5-9c4e-b18b561cd6f3 | note | Verification Activity: By - SE
723f886a-0feb-5ad0-a7f6-92f1a8173425 | section | 8.04 Shared Paths, Roundabout Concrete Apron and Driveway Access Road
c801d845-056a-599b-8806-9a9d5e54951b | checkpoint | 8.04.1 - Foundations
f08c83ca-4bb7-5da0-b22b-b9d2d09c14b7 | note | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
d92d4daf-c764-5d55-b62a-abd5013aec6e | note | Standard / Specification - Downer
f386da98-7a87-5f0a-b3dc-ef9b4eed966e | note | Verifying Document - Scala Report
5fa3a5e3-1e5b-5f1f-b72f-045b52690b5e | note | Frequency - 20m
b41311d1-96d8-5c01-939f-817d25d1243e | note | Verification Activity: Activity - I
84852e88-df43-598d-a014-37f231ab905e | note | Verification Activity: By - SE
4890ad9d-5070-54d8-86c9-341e9b921323 | checkpoint | 8.04.2 - Driveway Access Subgrade and Subbase
68c8c3e9-a5b1-5d0b-a463-c3515454afc4 | note | Acceptance / Conformance Criteria - As per Pavement Type D, the subgrade shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved NZTA M/4 (≥ 100MPa) granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 100mm. The granular base layer shall be well wetted with water immediately prior to the placing of concrete.
265724b3-ddc6-5994-9f9b-7dbfcd06b7c2 | note | Standard / Specification - PS 17.4.3
bf67cd14-ff1d-54f3-bf33-1a78578b94f1 | note | Verifying Document - Site Records
fafc2a03-f89f-5b9f-b8bc-e53f18b66a38 | note | Frequency - Prior to Pour
6dc85bf0-d621-5885-bfc4-19fda4752216 | note | Verification Activity: Activity - R
193bca02-6e85-5b70-b820-4875117dd1cd | note | Verification Activity: By - SE
ff8a514f-6d4e-5943-b74d-083486f23348 | checkpoint | 8.04.3 - Shared Paths and Roundabout Concrete Apron Subgrade and Subbase Installation
b10fdcb4-131f-518c-9c24-3aa4b082c157 | note | Acceptance / Conformance Criteria - The subgrade shall be excavated and trimmed to achieve a firm, uniform surface, and a layer of approved AP20 granular material shall be placed and compacted with a mechanical compactor to a minimum thickness of 50mm.
daff9e8e-2ee4-5700-872d-53e7f15ef866 | note | Standard / Specification - PS 17.4
12e803a9-44ea-5e1a-b14f-b11601d296d3 | note | Verifying Document - Site Records
aaec6e4e-9b35-55e8-ba14-85930c0fb2e2 | note | Frequency - Prior to Pour
2a302336-9f71-5939-b37e-4f9bcafd338f | note | Verification Activity: Activity - R
dd30b4a1-8dbc-597f-8316-5fc0af41a302 | note | Verification Activity: By - SE
c711bf3f-14b0-5879-94a9-2461a9a33646 | checkpoint | 8.04.4 - Fill Compaction Testing
be1674fb-8758-55db-9c6f-71e0700ea0ce | note | Acceptance / Conformance Criteria - Fill shall be placed in horizontal lifts not exceeding 200mm in loose thickness and shall be compacted to at least 95 percent of the maximum dry density every 20m
ffef5c7c-6c83-54d5-9599-6567d656b348 | note | Standard / Specification - Downer
8576edbd-e726-5b87-a4ee-bbf2d0f8f8f5 | note | Verifying Document - IANZ NDM Report
7a6eede5-30d6-5879-bfdb-497da1a3ebed | note | Frequency - 20m
c459f722-9f93-5c9c-98d6-e47a2b4f1312 | note | Verification Activity: Activity - I
c502c423-f9fc-5af5-b8e8-c68cf234305f | note | Verification Activity: By - SE
2ddfb512-8613-535f-b97e-9069bcf82226 | checkpoint | 8.04.5 - Granular Base Prep
36e0f658-9afa-524b-b152-13e219705318 | note | Acceptance / Conformance Criteria - The granular base layer shall be well wetted with water immediately prior to the placing of concrete.
c9a6687c-7c2c-51c8-be70-d86cf36f2718 | note | Standard / Specification - PS 17.4
14edf572-db73-502b-9c2f-823f94987a8d | note | Verifying Document - Site Records
0d0845c5-9db4-53bd-b843-5c38f76c1ff5 | note | Frequency - Prior to Pour
fa4dabba-a159-5c98-941c-4c26708cbff9 | note | Verification Activity: Activity - R
744ccad1-2fd5-5020-b40e-ab0d1d095162 | note | Verification Activity: By - SE
6359a822-8137-5ec7-8d4e-dafb28d4dcf0 | checkpoint | 8.04.6 - Shared Paths, Roundabout Concrete Apron and Driveway Access - Construction Joints
0b882b1a-54ed-57de-b2ef-1a900961c4af | note | Acceptance / Conformance Criteria - The Contractor shall form construction joints every 4m by saw cutting or other approved method. Concrete shall be poured in one operation and without interruption between formed construction joints.
9cafa865-1754-5522-b566-e7614e98b275 | note | Standard / Specification - PS 17.4
eb12bbad-e734-5c68-bb76-45e1465ed3cd | note | Verifying Document - Site Records
9fc046fb-8005-549a-bf1e-58887a8a6394 | note | Frequency - Every 4m
b4651f5b-9f01-55f5-a66c-90ea5ec3cda8 | note | Verification Activity: Activity - R
fab696dc-0501-54e9-9b6e-48de8ebfebbd | note | Verification Activity: By - SE
d197552b-01b6-5707-b9d6-f6e3ec0b5ef6 | checkpoint | 8.04.7 - Roundabout Concrete Apron - Reinforcing Placement
d8a8bb25-3650-50a2-8864-9ed882e5cb00 | note | Acceptance / Conformance Criteria - D12 reinforcing bars spaced at 400mm centres radially and D12 reinforcing bars spaced 300mm centres centrally placed as per the drawings and shall be 200mm thick.
786087d0-e7d3-5049-ace2-1f0437dc445d | note | Standard / Specification - PS 17.4.2
2d08e922-7f39-57cd-9c58-8b7287186b5b | note | Verifying Document - Pre Pour
ab0164af-b5f5-5e5a-a789-b5cab5c805e8 | note | Frequency - Prior to Pour
e8c24c0e-12b8-5896-acc5-a2cea17ef3f8 | note | Verification Activity: Activity - R
503e75d7-fe14-576c-8d97-c183402b2cb8 | note | Verification Activity: By - SE
57654067-c819-5e72-a640-7572be11815b | checkpoint | 8.04.8 - Roundabout Concrete Apron - Expansion Joints
d5683c9d-716e-503c-bf42-cfd7f4f2dba8 | note | Acceptance / Conformance Criteria - Expansion joints shall be formed at maximum spacings of 21m.
bc28bd0f-ed2f-55ca-b2ee-628ec7c95ec3 | note | Standard / Specification - PS 17.4.2
03c26c18-06fe-522a-9c2c-338ef3cd8ea1 | note | Verifying Document - Post Pour
b6b7b8bc-93f9-5d93-a88c-0416afe24063 | note | Frequency - Every 21m
e47d62e9-1384-570c-a2d0-12b44b9456ab | note | Verification Activity: Activity - R
420a722a-821b-52e2-bd00-c839bcfe93a8 | note | Verification Activity: By - SE
1b585713-327d-5587-bf75-f233291a93d1 | checkpoint | 8.04.9 - Shared Paths, Roundabout Concrete Apron and Driveway Access - Finishing
c2bcbca2-eeb5-5f52-8f10-6c1783c780ac | note | Acceptance / Conformance Criteria - The edges of the paths shall be neatly chamfered. The whole of the surface shall be screeded and after the initial set it shall be carefully broomed transversely to present a non-skid surface. The surface shall comply with NZS 3114 class U5.
e06d7939-8b7f-5f39-9d45-79238a9bdc61 | note | Standard / Specification - PS 17.4
f005448d-8f90-5551-ba48-cfe3c1597707 | note | Verifying Document - Site Records
76ad6bf5-12e7-52f9-a20a-d2d7b70027a3 | note | Frequency - Prior to Pour
6e4308fd-c142-5fa2-8ce3-8908f7da2d56 | note | Verification Activity: Activity - R
9519d298-1154-58db-81f2-dda793bc14c3 | note | Verification Activity: By - SE
41cb4814-44f3-53a0-aadf-5d0d2de84aa7 | checkpoint | 8.04.10 - Shared Paths, Roundabout Concrete Apron and Driveway Access - Curing
8fa66357-cfdc-5fb2-b31c-b58102f29038 | note | Acceptance / Conformance Criteria - The finished work shall be kept continuously wet by approved means and shall be thoroughly protected from frost, from direct rays of the sun, and from drying winds for at least seven days after pouring. The boxing supporting the vertical faces shall not be removed for at least 36 hours after the concrete is placed.
df9d0a8b-72ae-5b46-b0b3-52f1a2b364a2 | note | Standard / Specification - PS 17.4
3629b9ac-7c68-58c6-92ad-2ceda059e4f8 | note | Verifying Document - Post Pour
823cc156-5bf2-5c6d-8ecd-3c65163fa854 | note | Frequency - At least seven days after pouring
b42fd021-fde1-5e65-84e5-c2aed2377d6f | note | Verification Activity: Activity - R
373f7378-24bb-5c2c-98c4-b80a37141cc5 | note | Verification Activity: By - SE
a476c803-0aa3-453a-8f72-36fa99bee60d | checklist | ITP - Landscaping - 808 - Rev C | itp | ITP - Landscaping - 808 - Rev C
1d2e0072-56af-48a7-9416-0dc539db938f | section | 3.01 General
ff4b4364-79ea-48f6-930b-70c0ac4c5ec1 | checkpoint | Precondition Surveys
61276d27-4ce2-5805-a2c7-280f806758ef | note | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
4c89c611-f944-5ffd-aa78-2e0cf5cb0672 | note | Standard / Specification - PS 2.13
60784003-912e-57f2-bfd0-e6fb477c2aa6 | note | Verifying Document - Precondition Survey report and plan
d8b4ece1-a41d-533c-b2ca-479c3ca297c6 | note | Frequency - Prior to the Contractor taking possession of the Site.
025fa2ed-48f4-5866-9f1f-438a14381c58 | note | Verification Activity: Activity - H
d81da605-21ad-5917-9192-d6f5006f39d5 | note | Verification Activity: By - PM
98ac207f-6d04-4630-85c3-943b271b00c4 | section | 4.39 Landscaping Material Supply
467d8de4-4d2c-4e17-b807-8d05c741f4dd | checkpoint | 4.39.1 - Nursery Inspection
0b7ef3af-d52c-55d9-b0d5-bc289d71d2b7 | note | Acceptance / Conformance Criteria - All plants inspected at nursery
2ae58b33-5654-5504-bb4e-999eb647ea56 | note | Standard / Specification - P39 G-3.1 & 3.4
81e7767d-4633-51ab-853a-74ad8d474d5d | note | Verifying Document - Inspection Record
413bd48d-c76e-5adc-92ac-a73032476bc1 | note | Frequency - Invite SPEC to inspect minimum 10 days before delivery.
627734f6-2651-5267-a95e-0242a16caacd | note | Verification Activity: Activity - HP
512b799f-6249-5db8-af98-7afd80dc5914 | note | Verification Activity: By - SPEC
e738cd08-7e9e-4385-9ed6-858c3be35e80 | signoff | AUTHORITY HOLDPOINT
cbbd011e-6b84-46e5-ad0f-c77ae8ab9fa2 | checkpoint | 4.39.2 - Plant Substitution
be390618-a40a-5fbf-ae40-b36024c0c8ed | note | Acceptance / Conformance Criteria - Approval of Contractors proposed plant species substitution
746498a3-dc90-55aa-adba-7cba3565fd4f | note | Standard / Specification - P39 G-3.1
a9771c41-ce71-56fa-bd2c-f4cdcfca89a9 | note | Verifying Document - Designers Approval
1fff9b8e-f193-5b2e-aeda-8bc14d997a58 | note | Frequency - as need basis
4e8ebbf5-4117-5b86-836a-a7a908e891a5 | note | Verification Activity: Activity - HP
e5bca657-3ba4-51c9-919c-d5d7292bbec3 | note | Verification Activity: By - WSP
d8c5835c-1f6e-483e-b1b9-a0540f187e10 | signoff | AUTHORITY HOLDPOINT
bcb5954b-9f49-4189-b5ff-d0a321cea7e7 | checkpoint | 4.39.3 - Topsoil Testing
1f58c2ad-9439-577d-91de-65580afb22a6 | note | Acceptance / Conformance Criteria - Proposed topsoil sampled and laboratory tested to F-3.1 and 3.2
43b079ba-b852-53c1-bab4-4aa13add2481 | note | Standard / Specification - PS 25.8.1, P39 F-3.1,3.2
815f7993-e233-5bf7-8cd7-40e6f2a91e3f | note | Verifying Document - Lab report
aaefce81-5ee7-5e87-a3ab-31727fe2887f | note | Frequency - Prior to supply
a66a3ab2-e686-50a3-967e-573b54be7636 | note | Testing Quantity Required - 10 equal samples mixed. 1kg supplied to lab
eeeeb453-a7f7-54bc-80a0-bbc46b4451d4 | note | Verification Activity: Activity - HP
c8a2cb06-bc8d-53d5-acd9-4a93c6491026 | note | Verification Activity: By - ENG
04462bee-f84a-4801-a7ed-e04fa7a0747c | signoff | AUTHORITY HOLDPOINT
e6db45ac-6aa7-4491-9eb0-177e7a257b35 | checkpoint | 4.39.4 - Topsoil Sample Inspection
6933ef19-495a-5a89-9080-0245576fad32 | note | Acceptance / Conformance Criteria - Representative sample kept on site for landscape Architects inspection, if requested
5a6fec86-5348-537e-a73a-3fe8fd49fd89 | note | Standard / Specification - P39 F-3.2.1
10c2e5f8-96c5-5eef-b68a-668b21da9191 | note | Verifying Document - Sample
569bdef8-6fb1-5559-801a-d1df1a08aa83 | note | Frequency - Upon request
92847365-14c4-5a77-985c-f234994f6009 | note | Verification Activity: Activity - I
93740384-7ea8-5d38-9767-d12f9f998079 | note | Verification Activity: By - PE
987fbd34-4322-4b7d-99db-5718c7a32b16 | checkpoint | 4.39.5 - Topsoil Remediation
4c911e6a-0900-5de4-b423-8e55abe1b635 | note | Acceptance / Conformance Criteria - Topsoil improvement methodology (if required by testing) and grassed area fertilisation methodology and programme
56104de4-5a76-5e9e-a62f-5716b866c45f | note | Standard / Specification - P39 B-4, P39 F-3.2, PS 25.10.2
6d182795-24a3-56a8-b914-fb90b6f690f4 | note | Verifying Document - NTC
1ae9057e-380e-51bd-b1ff-fc517543b557 | note | Frequency - Prior to placement
72dcac1f-ab41-51e0-8b20-ae3660088349 | note | Verification Activity: Activity - R
d63460ba-afca-5b81-89e7-97a9d5a61bd9 | note | Verification Activity: By - PE
a5a02ce1-15cf-45c9-b57d-a50c92370970 | checkpoint | 4.39.6 - Biodegradable Weedmat supply
f367ce9c-dbb9-53bc-b207-88f4bc95f4eb | note | Acceptance / Conformance Criteria - Datasheet and sample of all types of biodegradable matting and netting supplied to Engineer.
f0805bf7-04bb-54e8-9438-4d3a1102ffdd | note | Standard / Specification - PS 25.9.1, P39 B-4, P39 G-3.9
72a864b7-f54e-5ac7-8612-bcf335e8f714 | note | Verifying Document - NTC
86c51210-6aad-5039-a4df-2ae956c88d64 | note | Frequency - Prior to procurement
64daece4-40fb-55be-8a8c-784f4fcb8182 | note | Verification Activity: Activity - HP
22ece9dd-c92a-5a7e-93d1-ffad7e9face4 | note | Verification Activity: By - SPEC
b5646535-a93e-4ba4-8840-fcdca19b99f8 | signoff | AUTHORITY HOLDPOINT
0f606c10-6d26-4750-8148-f3e7f54ec850 | checkpoint | 4.39.7 - Mulch supply
bcced6ed-3ae2-5efa-ae80-e79c576e0007 | note | Acceptance / Conformance Criteria - Sample of bark or arb mulch provided to Engineer for approval
d9ac7ebf-7eec-5e77-9ae8-fe850bd5f0a1 | note | Standard / Specification - PS 25.9.2.1, P39 B-4, P39 G-3.9
05cf20c9-ae1f-588a-99cb-863cd5d18ec2 | note | Verifying Document - NTC
f53a67b6-9e6f-56b6-aa0c-633dfe0039fa | note | Frequency - Prior to procurement
49a07ea6-d0f3-55a1-ab9c-f031579e1348 | note | Verification Activity: Activity - HP
37c748a0-2b48-51af-a253-90aa741bee14 | note | Verification Activity: By - SPEC
16ea6ec9-0be7-424d-8b4b-9967ae6ad626 | signoff | AUTHORITY HOLDPOINT
288d3e58-e03b-4040-9455-1fab53a8bde8 | checkpoint | 4.39.8 - Grass/Hydroseed
a5e2e4d8-58e5-5c48-b4c5-705347fcedad | note | Acceptance / Conformance Criteria - Provide Supplier's grass seed brand and seed mix, and application rate for Engineers approval
05bb64f0-32b4-5bc5-8674-b39a0844c2a4 | note | ○ Provide Supplier's hydroseed mix for Engineers approval
86482372-3e85-56e9-ad55-ca40e396a364 | note | Standard / Specification - P39 H-2.1, P39 I-2.2
05e3e015-082f-501b-8193-4814e86d0980 | note | Verifying Document - NTC
12257205-0a58-5876-adc3-2c1a7d674205 | note | Frequency - Prior to procurement
c30dfafb-4eec-5335-b277-685a1ba82fd5 | note | Verification Activity: Activity - HP
020b38d2-fd4d-504c-9ef9-509dab2d4ee3 | note | Verification Activity: By - SPEC
5a6c8808-2244-442c-a924-d738298ad715 | signoff | AUTHORITY HOLDPOINT
475d81d4-5be3-4ef0-9a1d-933fa9ac4af0 | checkpoint | 4.39.9 - Turf / Instant turf (if required)
5474b260-75b1-5a9a-bef3-027a4e66c849 | note | Acceptance / Conformance Criteria - Provide Supplier's installation and maintenance rquirements to Engineer
5ae1547d-054e-574c-a37b-1363351aa129 | note | Standard / Specification - PS 25.10.5
38f7e02c-f659-5f8f-bf2e-77feba61e357 | note | Verifying Document - Datasheet
12cbfff2-8a04-527f-a080-0f98040100c2 | note | Frequency - Prior to installation
557c52df-1eee-5fcf-848c-3ee691e373cf | note | Verification Activity: Activity - R
28634229-220e-58bd-a6e3-670105da89d5 | note | Verification Activity: By - PE
9615f871-f7cc-4ea2-a419-dcac7b064f42 | checkpoint | 4.39.10 - Fertilisers
9c39dd91-4e92-5a0b-9e30-296d5ae3d656 | note | Acceptance / Conformance Criteria - provide fertiliser product details to Engineer for planting, turf, grass and hydrograss
f9f97505-a585-58e5-9b52-2ba6333743da | note | Standard / Specification - PS 25.7.3.2
c2dfef11-3f6f-591f-a237-0a84fdfb8b39 | note | Verifying Document - Datasheet
3763ce48-7898-528d-8170-d9c136944546 | note | Frequency - Prior to procurement
ab7faa79-f792-5c48-b8ff-c600dc27f720 | note | Verification Activity: Activity - R
f4745562-6633-5828-8be0-526c7dfcf0fd | note | Verification Activity: By - SPEC
ce04d0b4-d191-428c-994d-57463765d7f1 | checkpoint | 4.39.11 - Contractor to develop hard landscaping materials ITP once the design has been completed
2a91f6d5-2f2c-5c6b-be29-c7e6b48ce426 | note | Verification Activity: By - SPEC
dcb1aa9b-e903-4115-87be-aa10d4b2b5b5 | section | 18.01 Site preperation & Topsoiling
6aeae20d-c68c-413f-b7ae-0f23adb1dc94 | checkpoint | 18.01.1 - Work Plan
06250ebf-35b8-5ccc-8277-7734ee753c2a | note | Acceptance / Conformance Criteria - A detailed work plan shall be prepared for all landscape works,
19d8bad8-886b-5407-a89c-12ae5bc7e694 | note | Standard / Specification - P39 B-5.1
30387896-424a-5257-a951-2796ee919612 | note | Verifying Document - Work Plan
a3510f18-8a5d-54a4-a841-92ee1b6820b5 | note | Frequency - Two weeks prior to landscape works
2d3838d2-2719-59b6-8a87-12afbc0a58f6 | note | Verification Activity: Activity - R
aaa4f23a-fdc1-5ec8-8bc4-dfecdc57489f | note | Verification Activity: By - SPEC
2780d708-091a-488c-b5fe-4859bd638684 | checkpoint | 18.01.3 - Topsoil Depth check
09ebcf59-6498-5993-83b7-5ee1990addf6 | note | Acceptance / Conformance Criteria - Topsoil depth check. (Planted areas topsoil 300mm, grassed areas 100mm, pb95 tree pits 1000x1000x1000)
e0a03f2b-d326-57b6-8cee-3473f035fd76 | note | Standard / Specification - P39 F-3.2.1
c3493190-656f-51b7-8d1d-e4025444b488 | note | Verifying Document - Survey Plan showing depth generated from before/after survey.
799a5ae9-bb08-50a9-bb3f-7453a70fa9f2 | note | Frequency - During Placement
590fdc1f-9298-572c-98bc-3fbf1d6b3657 | note | Testing Quantity Required - Random manual dig check by Eng.
2be2d512-14cc-5fcb-8c2e-4a8ec4b29c26 | note | Verification Activity: Activity - HP
29e6e2f0-75af-585f-b94f-7e1a7d49d317 | note | Verification Activity: By - ENG
8eae02aa-7f44-4aec-9fc2-7b7e648f5e8b | signoff | AUTHORITY HOLDPOINT
36981856-a10c-4388-9a70-d27d2e20ba5f | checkpoint | 18.01.4 - Pest Plant and Animal Control methodology
b672e44f-ccdb-5739-bded-3ebc6b85093e | note | Acceptance / Conformance Criteria - Submit methodology for approval
a55e5354-177b-547a-bb46-e0c418fc955d | note | Standard / Specification - P39 D-4.2, PS 25.5.2
b24fc889-09bb-57d1-bd9e-b7ead4d02933 | note | Frequency - Prior to commencing operations
77a81969-f38f-5654-97d3-1975831e8240 | note | Verification Activity: Activity - R
50427d44-1902-57c5-82b1-dc6d1630724a | note | Verification Activity: By - PE
635d6251-cbc2-4711-b634-7c11f9cf5ddf | checkpoint | 18.01.5 - Pest Control notification
73693dea-2a16-5370-902e-18a6ff08446f | note | Acceptance / Conformance Criteria - written notification to Engineer 2 days before pest control or spraying operations. at least 24hr notice to landowners
c5b535cc-19c1-505a-9226-b8b4d891cb9f | note | Standard / Specification - P39 D-4.2, 4.5, 4.5.2.2
d00da78e-6244-5063-8088-f55db794df8a | note | Verifying Document - NTE, letter
f95776f9-6538-536d-a4e1-24fc03c8f8bc | note | Frequency - before each operation
027704ff-e47f-5da9-91e0-b7e769f2381c | note | Verification Activity: Activity - R
d0187bea-43c2-515c-87e0-63655f630afe | note | Verification Activity: By - PE
681c639b-4702-4d00-b203-bfefb11e1e27 | checkpoint | 18.01.6 - Mulch Depth
4b4ded58-9cc9-5d9c-9050-88209065a7ec | note | Acceptance / Conformance Criteria - 100mm depth for all planted areas once settled, not less than 75mm for trees
e75afb46-2de5-568c-a604-afe065776fbd | note | Standard / Specification - P39-K-6.6
6c34dca0-694c-5566-a017-eb0f707b7d92 | note | Verifying Document - Inspection Record
0b268225-771e-5bb7-a381-55415ab77bcf | note | Frequency - Following planting
402cb4d1-3092-5a63-9240-13a8ac30a880 | note | Testing Quantity Required - Mulch checked during planting audit
550ad262-6f48-516d-a828-9ddc11559d55 | note | Verification Activity: Activity - D
ddec080f-e8a1-5156-9a75-c6a9334b9067 | note | Verification Activity: By - PE
8033ec34-4ad5-4021-95dc-ecc29b0ebca1 | section | 18.03 Planting & Grassing
86e98277-b77f-4add-b2e8-f0f6f095887e | checkpoint | 18.03.01 - Plant Delivery
b35cb060-42fa-5ac6-b636-e8068f9b1750 | note | Acceptance / Conformance Criteria - Inspect all plants upon delivery to site.
344d5795-626f-5919-82ea-528cc0a327ee | note | ○ Provide written notice to Eng min 2 days before delivery
d81807ca-ae1e-534a-bed2-89b24d9bc468 | note | Standard / Specification - PS 25.7.1, PS 25.1.6, P39 B-4
af5c5944-5638-57b7-8fca-86e926c8ea30 | note | Verifying Document - Inspection Record
108ac609-5e22-5d4c-b23e-eaa1fd2295f9 | note | Frequency - During/Following delivery
41b71bac-11be-5182-a091-facd7282054f | note | Verification Activity: Activity - I/HP
436ad587-d95b-5d23-b01a-9396bc8ff425 | note | Verification Activity: By - SPEC
1b0f5bea-924a-4085-bce5-a362ae4f5af2 | signoff | AUTHORITY HOLDPOINT
0f14ea1d-db6a-45c3-8f9f-267a35f1d344 | checkpoint | 18.03.02 - Planting or seeding Notice
d1624837-d04c-582c-bb92-5356974ff2fc | note | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Planting or seeding.
0bb54bb5-f581-5f38-85e5-ec24520d3fc3 | note | Standard / Specification - PS 25.1.6, P39 B-4
f3ebada0-6e8c-5d0c-a372-fa6ead04a6f6 | note | Verifying Document - NTE
e8c0185e-7851-5114-88d2-202a20d01360 | note | Frequency - At least two days prior
afc1952a-9035-5ab2-9e9f-110c179a0c53 | note | Verification Activity: Activity - R
e8f95d4b-ba7d-57c3-97e3-af6f4ffcd3f8 | note | Verification Activity: By - PE
5830e88a-8b5f-40a4-a3f4-d3ba3342576a | checkpoint | 18.03.03 - Peg Sample Areas
d93ee01a-45c4-50ca-bcae-eb1fda79dff2 | note | Acceptance / Conformance Criteria - The Landscape Archtect Stantec will identify sample areas to be audited to P39 B-6.1 for each planting type, and supply a sample area plan to the Contractor for pegging.
81917b93-ac1b-5e64-b924-4676817fbbb8 | note | Standard / Specification - P39 B-6.1
7b95a8b3-fbc8-55d9-b77e-edd7868afca3 | note | Verifying Document - Planting Sample Plan
29de0202-7dbc-5de8-836f-5d328884e5e4 | note | Frequency - Following Planting
5451f281-f594-5c70-9dfe-c92f9dc97d6d | note | Testing Quantity Required - For planting areas < 2,000 m2, 2 No. sample areas each min. 5% of planting area.
3cb2075d-9da0-531f-a602-7e8eeb231edb | note | ○ For planting areas > 2,000 m2, 2 No. sample areas each min. 2% of planting area.
bed183ed-f50f-5567-a3f7-8c477df0b929 | note | Verification Activity: Activity - O
de8957c7-2e7c-5ef5-b3bd-8bd4bb3d9b3f | note | Verification Activity: By - SPEC
08cd5d6e-8374-4b39-85a1-15221cc1fdeb | checkpoint | 18.03.04 - Plant set out
e1cd7e57-2d8f-56d4-9415-74c2092bc005 | note | Acceptance / Conformance Criteria - Following sample area pegging, the Landscape Architect will audit sample area quantities and species composition to P39 B:6 and G:4.5 for each planting mix. Minimum of 95% plant count
5dc54cb4-326c-5a59-a530-efecfd6ad1f9 | note | Standard / Specification - P39 G-4.5, B-6
f5bd298f-3b74-511f-8b74-422e5e8151d2 | note | Verifying Document - Planting
f9d027eb-5548-529a-b38d-662e9cf2692f | note | Frequency - Prior to planting until all treatments achieved.
78d43094-a07c-5af5-ae02-644418eed8f8 | note | Testing Quantity Required - For planting areas < 2,000 m2, 2 No. sample areas each min. 5% of planting area.
dc8ff38c-720f-599b-bad8-8424ac088fbb | note | ○ For planting areas > 2,000 m2, 2 No. sample areas each min. 2% of planting area.
87a1f986-d060-502e-9ca2-44f4ccba7706 | note | Verification Activity: Activity - HP
6dcbcd20-9f3d-51c8-8c90-5f9be1df0fc9 | note | Verification Activity: By - SPEC
76fd3f02-8b23-4071-9c17-e01422b721f4 | signoff | AUTHORITY HOLDPOINT
f33b7d4e-e135-45d1-a3e5-1c1b461d8c79 | checkpoint | 18.03.05 - Planting Sampling and Inspection
1b780692-6cb2-5fc5-a06f-153338c7466e | note | Acceptance / Conformance Criteria - Condition of acceptance inspection - once areas are planted, the Landscape aarchitect will hold an inspection to sample each treatment for density, composition and quality of workmanship.
a2fc9f0b-f270-5820-b9d8-625db91c5e5e | note | ○ 95% plant density and correct species composition
44fbf09b-a58c-5f88-8e75-ddec14e53bb1 | note | Standard / Specification - P39 B-6.1, 6.2
f7bf8b2d-a851-5269-ba51-f084489044b1 | note | Verifying Document - P39 B-6.3, Planting sample report, B-6.2 checklist, and NTC
c86b9ad0-efc3-5c93-a268-7eea521939fd | note | Frequency - Following Planting
a8c23267-ad39-56c8-8b64-ae46a105aa34 | note | Testing Quantity Required - Planting areas < 500 m2, 1 per 50m2, min. 5.
44a25f6f-8fc8-5c88-a676-a643b8cc668b | note | ○ <2000m2, 1 per 100m2, min. 10
1f349563-5bfc-5008-a4ea-08491221a626 | note | ○ <5,000m2, 1 per 200m2, min. 25.
289cae4c-b755-5ae9-8b9d-49dd62d0d071 | note | ○ <10,000, 1 per 500, min. 40
d4167c7f-cf3b-5095-8539-26724796a7c3 | note | – Note this is total planting m2 not sample areas
fb3415e1-97bd-51a8-aa3d-5412fbf48043 | note | – Repeat sample if >2 faults in >20% of sample. If >2 faults in >20% of average of 2 sample sites, then check all plants in planting area
bfe34f40-c38b-5648-96ad-406e8f4216ea | note | Verification Activity: Activity - I
0e33ca7c-858d-55c3-a057-73b67cfe3d40 | note | Verification Activity: By - SPEC
d37b5439-14e4-469c-8e31-a7b1953169c9 | checkpoint | 18.03.06 - Grass and Hydro-seeding
3b16f82f-d0bb-585b-b2f3-382fa183a793 | note | Acceptance / Conformance Criteria - Estbalishment 95% coverage, weeds visible not >4, bare patches <100mm diamter
f7ec559e-8659-58f0-9ed6-0b010dff8392 | note | Standard / Specification - SP39 B7 & B8
dee168f4-62bd-5d66-8019-fd5523bbc428 | note | Verifying Document - P39 B-6.3, Planting 3-month maintenance inspection report, B-6.2 checklist, and NTC
bac19804-085d-52f2-b538-5d6dd07cb482 | note | Frequency - Following planting and every 3 month inspection
dca76544-519e-552d-89d9-2962cd11859f | note | Verification Activity: Activity - V
fc6e12dd-6987-57df-a713-dc0df04aa9ce | note | Verification Activity: By - ENG
faf90001-6558-421b-9c69-a809e4bface1 | checkpoint | 18.03.07 - Maintenance Regime submission (if not already provided as part of work plan)
91aaaed7-e722-5098-9a51-e400c0dc69ee | note | Acceptance / Conformance Criteria - Review of regime by Landscaping Architect (Stantec). Approvals sought by local authorities for pest management and confirmed acceptance by WSP.
40155189-4820-56a7-8eb0-a7b8dd37a815 | note | Standard / Specification - P39 K-2.1
71fa86cd-5f38-57bc-981e-42c4fbfb4dc5 | note | Verifying Document - SPEC review and Designer approval
58e1e584-2628-501a-b70e-cb0cd040ad60 | note | Frequency - prior to installing planting works.
e918f8d9-f75c-5020-b0dc-b8a755212c27 | note | Verification Activity: Activity - R
231cfebb-3bd9-515d-a347-6cb863fe28e3 | note | Verification Activity: By - SPEC/WSP
77192fca-f3c2-45af-97c4-5ffaae4c6929 | checkpoint | 18.03.08 - Site visit maintenance period Notice
4161d805-b2f4-5c30-862a-7b2a74068335 | note | Acceptance / Conformance Criteria - Written notice to the Engineer, at least 5 days prior to Site visits during maintenance period. Contractor to submit report
726bec07-6b57-5d80-bcfe-24898ae014a9 | note | Standard / Specification - PS 25.1.6, P39 B-4 & K-2.1
3acbf728-8cd2-537f-8bac-aad57aeed67c | note | Verifying Document - Notice
d228744a-46a1-5c3a-8b03-ae6cfc8c0818 | note | Frequency - At least five days prior
d4e21f76-5691-5eee-9fa7-ce1637e02497 | note | Verification Activity: Activity - R
5521bc2b-2261-52fd-80ef-13dc18343fe1 | note | Verification Activity: By - PE
0fc31e66-52e5-401b-9c44-7856b0fac825 | checkpoint | 18.03.09 - Defects Liability Reporting
edf4f439-effd-508b-8cf5-0b6ebaf51556 | note | Acceptance / Conformance Criteria - Plants inspected and measured for growth, checked for health - quartely inspectons until achieved targets. Observe grass coverage 80% canopy coverage, 100% survival of trees and grass areas 95% - <100mm dia gap acceptable defects liability period and maintenance period for 5years
6673ec2c-414e-5ace-8e2f-7fc0be39b4dd | note | Standard / Specification - P39 Section K 6.3 & 6.4 & section B 6,7,8
a26b848a-4799-5fc1-8239-39bb988ac6c8 | note | Verifying Document - P39 B-3 & B-6.3, Planting 3-month maintenance inspection report, B-6.2 checklist, and NTC
b9bc5ded-7403-500f-baa4-3ceb3ebf20ba | note | Frequency - Every 3 months during defects liability and maintenance period (5years)
e285ff8a-bea3-5e5b-aff2-0dd2479cff91 | note | Testing Quantity Required - Planting areas < 500 m2, 1 per 50m2, min. 5.
dfc64fed-9960-50fb-bf19-040baf5c8ed2 | note | ○ <2000m2, 1 per 100m2, min. 10
1d839eb1-6fc2-56c7-94d5-9a74056679b2 | note | ○ <5,000m2, 1 per 200m2, min. 25.
7206a966-84ab-5b1c-8564-60686d8fb0d3 | note | ○ <10,000, 1 per 500, min. 40
c0a504e4-4286-5d14-b7bc-6855447e8d6e | note | – Note this is total planting m2 not sample areas
87e105b2-893e-5a64-abff-85555a7b441c | note | Verification Activity: Activity - I
d2fac01c-a03e-578e-9590-64a3ee6146f5 | note | Verification Activity: By - SPEC
099f042e-ec13-4dc7-bf79-6693e03dda32 | checkpoint | 18.03.10 - Final End of maintenance Inspection
38cab069-cd53-5f6b-bf38-88cf5666e067 | note | Acceptance / Conformance Criteria - 100% Large plants >PB27 healthy, maximum 10% small plant loss, 80% plant canopy, planted area weeds limited to 4 visible at any point
c8c95e9b-c90e-5d77-b149-479a8663e4b9 | note | ○ 95% grass cover, weeds <4 visible, no kikuyu
0e26afe3-7e0f-5d5e-8858-cd1360ac6b38 | note | Standard / Specification - P39 A-2, P39 G-1, P39 H-4.7, P39 K-1.1
9c05f0ae-d400-5e24-bc25-f03bef752764 | note | Verifying Document - End of Planting Defects Liability
8233ea63-7f76-57a4-9b42-1d1c0738af0c | note | Frequency - 1 inspection upon completion of defects and maintenance period
65e30a54-a715-506e-9c13-64d969bc455c | note | Verification Activity: Activity - I/V
478472d5-1f47-5120-8a8b-418db06330a0 | note | Verification Activity: By - SPEC
31631c49-baad-444e-b7ff-9af123f299db | section | 18.04 Fencing
cd36f435-f31c-4866-8ee3-0a82afe9fdc2 | checkpoint | 18.04.01 - Temporary Stockproof boundary Fence
a16f272c-0030-5a21-8c7b-fec53365d27d | note | Acceptance / Conformance Criteria - Record of Landowner liaison confirming temporary fence
701aa5fa-5a5f-5ddc-b134-53e6b81da8f0 | note | Standard / Specification - PS 25.12.1
77f8a5ac-dc63-5824-8481-ed1d6dca177e | note | Verifying Document - Comms
fe98e4f6-cf5a-514a-b2db-59ddff173fa6 | note | Frequency - Prior to Installation
9b0d4797-a497-5c82-8b7e-ee3fb0feb6af | note | Verification Activity: Activity - S
4448b50a-2814-55e2-a2e9-57202082503a | note | Verification Activity: By - PE
34707784-bc33-488b-b8f4-8d0413616d61 | checkpoint | 18.04.02 - Permanent Stockproof boundary Fence
38532c75-1693-5695-90cd-d6c8a86b7c06 | note | Acceptance / Conformance Criteria - Fenceline ground contour finalised prior to discussing fence with landowner
bba0ad62-76fb-5c1d-9b46-9302f0c4354e | note | Standard / Specification - PS 25.12.2
490104c0-0763-57cf-8f8f-9d2123031c8a | note | Verifying Document - Comms
e7370152-23e3-53d2-b44d-64cd82016ab1 | note | Frequency - Prior to Installation
af5d3910-3186-585a-9539-ccdca94257ff | note | Verification Activity: Activity - I
2e19635a-1eaf-5522-8dd9-34ce5198b806 | note | Verification Activity: By - PE
2fe2c81b-a30a-4535-b9f6-78b5c4576f61 | checkpoint | 18.04.03 - Permanent Stockproof boundary Fence
2a9171fd-2e76-588b-afde-2226216ed2ae | note | Acceptance / Conformance Criteria - Record of Landowner liaison confirming permanent 7-wire P&W fence and gate provision in accordfance with landowner agreement
7ef034c9-d944-5546-ada9-63df4d475472 | note | Standard / Specification - PS 25.12.2
f7f07dd0-7796-542d-bc33-96e25d38d29e | note | Verifying Document - Comms
2398411e-6908-54d0-b8a9-f7be60cefdab | note | Frequency - Prior to Installation
a463d879-7eb5-5f7e-ad16-d94363f15916 | note | Verification Activity: Activity - R
cc34103b-d315-5afd-b3c0-081a401f7b8e | note | Verification Activity: By - PE
941784f4-b54a-4f03-b6f1-722ef6787c1c | checkpoint | 18.04.04 - Permanent Stockproof boundary Fence
08f0893b-ff1b-566c-895c-1c46619c3741 | note | Acceptance / Conformance Criteria - Fence postion tolerance survey
79ec0446-a818-5c6e-8dc7-beda66ac98da | note | Standard / Specification - PS 25.12.2
5ef9847e-4639-5ac9-8d77-a9f8c7428a1f | note | Verifying Document - Asbuilt dwg
36f2ced3-739e-53c6-bcdc-f75fd3f7fc00 | note | Frequency - Within 10 days of installation
24318dab-1ec4-597e-84f8-0db33e63baab | note | Verification Activity: Activity - S
1103b153-fb13-5340-bf79-ee74954ade53 | note | Verification Activity: By - SV
c387de43-5739-4d2b-ab9d-bb270bb92361 | section | 18.05 Hard Landscaping
da95d9e5-c579-4eff-98c7-a747afcd4781 | checkpoint | 18.05.1 - Contractor to develop hard landscaping ITP once the design has been completed
f8169281-4054-5eb0-8961-0d73378d3028 | checklist | ITP - Landscaping ITP - 105 - Rev B | itp | ITP - Landscaping ITP - 105 - Rev B
94f85fb3-4643-50c7-b8f7-3133e87b4418 | section | 4.39 Landscaping Material Supply
cebfdad6-9811-5f03-bfb5-ac5c93b810d1 | checkpoint | Plant Supply
6013dc01-7f7a-5fb2-b919-a1a405ec2ad5 | note | Acceptance / Conformance Criteria - All plants shall be supplied true to the species and grades specified on the approved landscape plans and fill the specified planter bag. All street trees, unless specified otherwise, shall be of a minimum grade of 45 litres with a minimum 30mm calliper. All other stock shall be of minimum 2 litre grade for groundcover and 3 litre grades for shrubs.
f7a2c923-7d84-52ca-b0a6-0e238eb5561a | note | Standard / Specification - PS 25.2.1
9f0e302c-d759-5fc1-80f8-0683fe5590fa | note | Verifying Document - Plant Details
0ac10f90-4640-51ec-8cad-25e03aabf7cc | note | Frequency - Prior to supply
f343491e-23c3-5a66-bba6-777017929bc3 | note | Verification Activity: Activity - R
3858b479-1270-5c92-9216-5e404be92e7a | note | Verification Activity: By - PE
7bbdd48e-cae5-51ac-bc10-d7dba5f0d74c | checkpoint | General plant species and quality
75d14631-5d69-589b-bb44-d6f1707f7d3c | note | Acceptance / Conformance Criteria - The Overseeing Organisation shall be provided with not less than five working days’ notice of dates upon which plants are to be delivered on site, so that arrangements can be made for quality inspection and confirmation of identification of plant material.
ee483c09-2452-5d72-9e0f-4390fb7ae2a2 | note | Standard / Specification - PS 25.2.1
0f713d64-6f53-51af-b254-cd7729d21496 | note | Verifying Document - Notice
e1f64988-c2b6-5979-829c-aacc01bbbb45 | note | Frequency - 5 working day notice
7725478b-81fa-5843-8c43-0727f1b18203 | note | Verification Activity: Activity - R
f5e94614-18c8-5b12-9e5a-5dd0bb129c8d | note | Verification Activity: By - PE
a5403f9d-ea47-5d26-b2f7-5366ac8bc585 | checkpoint | Street tree grades, species, and form
e748244b-966d-5914-989c-e7779fdf78cd | note | Acceptance / Conformance Criteria - All street trees, unless specified otherwise, shall be of a minimum grade of PB 95 and be first grade nursery specimens. No substitution of species or grade shall be made without the written approval of the Engineer.
af19172a-b668-57c3-ac22-2125a950cd44 | note | Standard / Specification - PS 25.2.2
e48dc7ee-16ed-5e15-a71f-30490c68707e | note | Verifying Document - Plant Details
19982371-e576-5c4d-83f5-9f16a6ab5638 | note | Frequency - Prior to supply
4a8277a1-1e71-5c9e-a9fd-387310a3539e | note | Verification Activity: Activity - R
f259ccc7-6c0f-5506-8031-f54f7dce2cbc | note | Verification Activity: By - PE
a899bdc3-6315-5702-aeae-7fab04624132 | checkpoint | Chemical applications for weed and pest control
bc74fbdb-c572-5b88-8d23-1c91f15259a9 | note | Acceptance / Conformance Criteria - All chemical application on planted areas shall be carried out by qualified, trained personnel and according to NZS 8409 Management of Agrichemicals, any relevant local Herbicide Policy and manufacturers’ requirements.
4b7d4619-7b7b-5755-b265-a185c61e158e | note | Standard / Specification - PS 25.5.2
f6d6e221-4bf0-50c6-8e0d-a0d161923e32 | note | Verifying Document - Qualifications and Datasheet
dc423baa-62f5-56df-b0e5-867d92517992 | note | Frequency - Prior to Application
a4120363-e0bd-5bfc-87c1-4904510793f5 | note | Verification Activity: Activity - R
96d04d3e-09c3-5c78-8ae2-0c3444b0bb29 | note | Verification Activity: By - SE
8260d348-a4f0-5fc1-a453-caff6cea97e8 | checkpoint | Biodegradable plant guards
c85b03aa-b30a-5621-b6e0-acad5fb31be2 | note | Acceptance / Conformance Criteria - All plant and animal pest control used for the landscaping works shall fully comply with Section D of NZTA P39.
baf3db5d-ccd0-59d1-90c7-04f96343d77b | note | Standard / Specification - PS 25.6
38d14915-af5d-58fa-8f63-30a8852f6dda | note | Verifying Document - Datasheet
d2ddb919-a501-57d9-b138-725827bfbab7 | note | Frequency - Prior to supply
ce231b36-8be8-514e-b525-4b3b875b0f36 | note | Verification Activity: Activity - R
a20dda52-65f2-5d12-9ee5-ee29dff51fdb | note | Verification Activity: By - PE
f6b8922e-b6e1-532d-88a2-e657324d53af | checkpoint | Fertilisers
f082134e-2d2c-5fb7-9aa2-3cf32d6add4c | note | Acceptance / Conformance Criteria - Fertilisers shall be either an approved pelletised natural or organic fertiliser or an approved synthetic fertiliser.
3e875243-3df7-5441-9e1c-96014e187d4a | note | Standard / Specification - PS 25.7.3.2
fe93d4f2-4aa2-5536-9ea0-f90f1e84a5bb | note | Verifying Document - Datasheet
be122392-28bf-5fd8-8039-b055726a0fa9 | note | Frequency - Prior to supply
ef3e576e-9a5a-56fe-af89-c53e061b99a4 | note | Verification Activity: Activity - R
070dad3f-3cc0-5d2e-b5f0-104fd220f521 | note | Verification Activity: By - PE
b99ce95e-6361-5c2d-89cf-62ecd71df6c7 | checkpoint | Imported Topsoil
81a3621e-6544-50f4-87ea-384ce11fe7ec | note | Acceptance / Conformance Criteria - Topsoil, both imported and existing on site, shall be a loam soil of good quality, free draining, free of weeds and contaminates, free of building materials and debris, screened, health, and contain no pans.
b5330616-77b1-533f-b523-cf00033b4148 | note | Standard / Specification - PS 25.8.1
1ffd1694-cfa0-5f27-8608-0ef384b16f75 | note | Verifying Document - Datasheet
6deec557-fd20-5085-a282-e7edca2f1929 | note | Frequency - Prior to supply
a37d3fe3-05e2-5ed8-b620-c5c96cbd47cd | note | Verification Activity: Activity - R
5749a673-61db-5138-aee9-205e3b4f3391 | note | Verification Activity: By - PE
8d3a4ad4-b02f-5503-8724-d95ced184e2c | checkpoint | Biodegradable Weed Matting
aeea720f-c39a-5536-9df2-3a5f90281108 | note | Acceptance / Conformance Criteria - The biodegradable weed matting shall conform with NZTA P39 and be coconut fibre mat, Woolmat or similar approved.
3110a170-9474-5626-bd72-d624f4f8c5fe | note | Standard / Specification - PS 25.9.1
48595675-986b-5b2c-9eb5-3278b910e000 | note | Verifying Document - Datasheet
efade557-3887-513f-822e-e04a33a3be9f | note | Frequency - Prior to supply
dce99f95-d43f-550e-9473-4b9d64f6a96b | note | Verification Activity: Activity - R
dc202b62-1a3b-50b9-9f1c-3ebc61d4f5d0 | note | Verification Activity: By - PE
ae398c82-552e-550f-ba5f-f6c8487df291 | checkpoint | Mulching fabric Testing
8cfeca5d-f613-51fd-9d45-6d3fc49699c9 | note | Acceptance / Conformance Criteria - A simple test to ascertain whether the mulching fabric is viable is to hold a sample to the sky. It should be mostly opaque. This density inhibits weed seeds trapped under the mulching fabric from sprouting, provides good moisture retention and assists with batter erosion control.
4a30383e-9859-5eb0-8d5f-670abdf1efc4 | note | Standard / Specification - PS 25.9.2
967cde47-0119-578d-9ff2-8e7733297350 | note | Verifying Document - Test Results
05f9934b-0514-55f5-9c61-bb6a5aacb236 | note | Frequency - Prior to use
09f1cc48-c4bd-51e9-a521-6cd75c8afa8a | note | Verification Activity: Activity - R
315a288a-bd91-5764-b816-c30d25de0e9c | note | Verification Activity: By - SE
6f45ab60-5e94-56aa-96c7-ed81f3279779 | checkpoint | Mulch
cc461f53-1f5b-5f25-8106-fa0d07a9760a | note | Acceptance / Conformance Criteria - The mulch shall be supplied as scheduled, clean, and free of soil, sawdust and wood preservatives, and a sample shall be provided to the Engineer for approval prior to spread.
93d2d1fa-48e4-511f-8a63-60d3a518ad3d | note | Standard / Specification - PS 25.9.2
5c363e6f-dbb0-595f-98f5-fc5b1ff46360 | note | Verifying Document - Engineers Approval
a15a1ce9-95f1-57bf-9a60-864d63a291d3 | note | Frequency - Prior to use
acc19601-0302-5c58-8785-e87a67043a24 | note | Verification Activity: Activity - HP
138f7244-1898-50c8-9fce-80efad7e704b | note | Verification Activity: By - ENG
b661facb-74f7-5550-b001-91550738e5ba | signoff | AUTHORITY HOLDPOINT
47ad80b6-42aa-5697-80fd-76256ae1f480 | checkpoint | Turf / Instant turf
32038790-e66d-5136-8038-a729b88120c3 | note | Acceptance / Conformance Criteria - The turf shall be of good quality in line with industry standards.
5e8983b6-7b3e-5ce3-829e-769917872b77 | note | Standard / Specification - PS 25.10.5
6e7dea17-0e68-58f5-b09b-a52933906539 | note | Verifying Document - Datasheet
a8cc2ac0-dc9c-5e4f-89ba-e68d87ff8b83 | note | Frequency - Prior to supply
c3fb147b-8650-57e5-b10c-ebeb1c372623 | note | Verification Activity: Activity - R
b9ce34ad-c5ba-53cb-81a1-1b92e022510d | note | Verification Activity: By - PE
efcc22ec-82af-5d63-8aac-53a4ae0fa874 | section | 18.01 General
f9e7fa82-f3fa-5c4c-bccf-36b9727b31b7 | checkpoint | Topsoil Placement Inspection
58222808-42b1-5074-af48-d9484e4b3259 | note | Acceptance / Conformance Criteria - The Engineer shall inspect the cut surfaces prior to the placement of topsoil and planting.
3b45b03e-ace4-5ff9-80d8-74991809ecc6 | note | Standard / Specification - PS 15.10.10
0785f815-6061-5067-b03d-26bc34445bbd | note | Verifying Document - Engineers Approval
b6fd3a6b-35f2-502e-993f-0d1312d73700 | note | Frequency - Prior to Topsoil Placement
c9ede99e-9f5b-50f1-a92a-a3d5d10b43d2 | note | Verification Activity: Activity - HP
16c495e9-8060-5c6e-b1f9-f9c134e70405 | note | Verification Activity: By - ENG
5c222ef8-bd6b-5fc2-bc77-b277f6168bd8 | signoff | AUTHORITY HOLDPOINT
5f1db3fa-7c1f-501d-bbeb-a1f1d099d864 | checkpoint | Setting out Notice
64efbb79-a497-5f1f-b7d2-bcd1631c2f6d | note | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Setting out.
6954ae97-53c2-52ab-a58b-7d25bfd34a8b | note | Standard / Specification - PS 25.1.6
d2cb3243-30ac-5df1-adb7-40498350f248 | note | Verifying Document - Notice
862febdb-f37a-5aa3-8c5a-6946498ac658 | note | Frequency - At least two days prior
df4b10b2-3b73-5023-b2f3-7605e7a823e0 | note | Verification Activity: Activity - HP
5577adab-e471-5810-8984-1cc83075606c | note | Verification Activity: By - ENG
1aefc999-d2ba-5661-a1ca-2602094b4de2 | signoff | AUTHORITY HOLDPOINT
e7101a80-a107-5eb3-a61a-a5f1d4c4dc27 | checkpoint | Applying herbicide Notice
3a665f83-6d37-58c6-a41a-44f54f45345a | note | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Applying herbicide.
f7999ccb-f478-549d-a69b-35afb41e36e0 | note | Standard / Specification - PS 25.1.6
ecc0eb9f-a55d-5844-9161-ecea8379d491 | note | Verifying Document - Notice
8f7cf3e4-1f35-518c-ac36-8b9adb240df2 | note | Frequency - At least two days prior
b5af2eb3-c2dc-5755-819d-20250ffcfd15 | note | Verification Activity: Activity - HP
e70aad34-73c2-55a7-bac2-3fb56a1e65ee | note | Verification Activity: By - ENG
f02a34c8-81d5-5b33-b1ff-e62810e0dbf9 | signoff | AUTHORITY HOLDPOINT
97df7f17-d930-58d5-8ae7-19973c1a1c64 | checkpoint | Cultivation of planting areas Notice
f6bfebd5-8056-54a7-b1e9-385c981f4a51 | note | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Cultivation of planting areas.
00a828bf-6c88-5f63-a83a-a581c974185b | note | Standard / Specification - PS 25.1.6
f99f45e4-8f68-5978-8249-65cc768a4299 | note | Verifying Document - Notice
01ab72a4-96cb-519b-a617-e8ed539009c5 | note | Frequency - At least two days prior
394d2f62-20a2-5044-9dbb-789aac8ebeb8 | note | Verification Activity: Activity - HP
3edd335a-929c-5808-8ca6-5607d3ab9ada | note | Verification Activity: By - ENG
e02e48f7-9020-5369-8100-86e5db8e9d2f | signoff | AUTHORITY HOLDPOINT
3e554094-5725-526b-a72a-d524e4973f9b | checkpoint | Delivery of plants and trees Notice
fb1c5201-8f91-55ff-84f2-d3122a205084 | note | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Delivery of plants and trees.
e2b36fd5-69e7-539f-a006-291e3bfee0a9 | note | Standard / Specification - PS 25.1.6
ae4e07f9-c0b8-5d68-9ebf-8940d0cc8902 | note | Verifying Document - Notice
9d1ed526-41c3-5827-81ed-5c1b5a059314 | note | Frequency - At least two days prior
03541ca1-a948-5bec-af7e-354dc608afc4 | note | Verification Activity: Activity - HP
0d9b7230-b40f-5c1f-83e4-9a1fa35f2a5a | note | Verification Activity: By - ENG
9d659904-1958-57cc-97c9-106e417b9ee2 | signoff | AUTHORITY HOLDPOINT
0d848a5c-79f4-5e18-803e-6128cc0a9d86 | checkpoint | Planting or seeding Notice
ff49847f-24c8-5a67-b344-71bf4bd13cbc | note | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Planting or seeding.
e411bb63-5058-55ef-912a-72def6d25603 | note | Standard / Specification - PS 25.1.6
30e9893b-06d9-5987-bf48-c3806cd89734 | note | Verifying Document - Notice
6e093a96-018d-5f2d-96c8-b91dd54f6096 | note | Frequency - At least two days prior
2529ef5e-42fb-5753-9bb9-ead6bbd3b184 | note | Verification Activity: Activity - HP
12d58eba-18ac-59c4-83ff-e34f7695470c | note | Verification Activity: By - ENG
eed1e50b-f8d3-50b7-a3ff-8237a85bb08c | signoff | AUTHORITY HOLDPOINT
1c772260-b10d-5b43-b60e-b04af5f26663 | checkpoint | Site visits during maintenance period Notice
47ea230a-5ec0-5174-9036-cb473b8a6eeb | note | Acceptance / Conformance Criteria - The Contractor shall provide written notice to the Engineer, at least two days prior to Site visits during maintenance period.
3e209460-46e3-502d-8651-2bb510924f9d | note | Standard / Specification - PS 25.1.6
1b5eb422-c315-54f4-ab39-74cd3b5f7b92 | note | Verifying Document - Notice
4277d88b-56ba-5896-b70e-abff1d532fdf | note | Frequency - At least two days prior
fe7db0ee-68d6-5aeb-98f8-c7cda05da891 | note | Verification Activity: Activity - HP
c992d4a8-5e8f-5b49-bf9d-eed2ac00170e | note | Verification Activity: By - ENG
20ed9ee6-e19b-5a58-9282-7f2aa755bd18 | signoff | AUTHORITY HOLDPOINT
67384eba-3a0d-5404-a2b7-6586e1442790 | section | 18.02 Weed, Pest, and Litter Control
026eafbd-3108-5524-aca3-0233525e9965 | checkpoint | Litter control
e1df593d-5230-5741-b4b3-a9cec9fe4070 | note | Acceptance / Conformance Criteria - The planting area shall be kept clear of all rubbish, including domestic and building materials.
ab4addaf-737c-57ec-a506-974a1695306e | note | Standard / Specification - PS 25.5.1
60848a4b-dd59-509c-8d00-edca12695ce8 | note | Verifying Document - Site Records
193caf84-7526-5efe-a201-cdc3e584d469 | note | Frequency - Ongoing
4601ab9f-3cdf-5411-82cf-d1a9ca34f883 | note | Verification Activity: Activity - S
da570741-4115-56d4-ad2b-e72a478887f7 | note | Verification Activity: By - SE
636796fb-b2e7-5404-a99a-39f95b8d1b59 | checkpoint | Spraying Operations
3f80badb-82b3-5908-b937-bcd077016917 | note | Acceptance / Conformance Criteria - All spraying operations shall be carried out in windless, dry conditions, when rain is not imminent for at least 12 hours and at times which minimise possible hazards or disruption to the public, animals or other beneficial fauna. Care shall be taken to prevent spray drifting onto non-target areas or plants and comply with notification requirements as required by the proposed Waikato Regional Plan.
9623320c-434f-598e-aa95-03639aab485d | note | Standard / Specification - PS 25.5.2
39a9a84b-0fa5-5cfd-bb5f-2fc72bc881c6 | note | Verifying Document - Site Records
1761fe4c-0a47-5096-b1c5-17c94a82c20f | note | Frequency - Each Application
04bb480f-d5cd-579d-8a47-d953aee3f149 | note | Verification Activity: Activity - R
01a1d29a-1eb1-5065-bb74-d3dbb0bd2012 | note | Verification Activity: By - SE
2ea30d4c-a99c-5b61-adf3-92af65742cdb | checkpoint | Chemical weed control in planting areas
5431b189-f58d-56c5-a2df-cc9c8bf6d581 | note | Acceptance / Conformance Criteria - Chemical weed control in planting areas shall be kept within the edge of the planting beds, within a maximum of 500mm of tree trunks, within 50mm of the edge of any undefined mulch surface, and within 50mm of any posts or the base of any landscape structures.
dcd82133-037f-5a13-8937-51145eba0bed | note | Standard / Specification - PS 25.5.2
6396819c-1e12-5309-8a2d-64a291fefd2d | note | Verifying Document - Site Records
9351bc9f-56b7-5a38-a4e1-3bc3173feb85 | note | Frequency - Each Application
d8165f9e-572d-5dd4-bef2-4dcd959f15d7 | note | Verification Activity: Activity - R
2eabc19b-9f8f-5f0f-873a-7c690a829b04 | note | Verification Activity: By - SE
2770d536-e3cd-4d8d-bab0-ff02458f6473 | checkpoint | Biodegradable plant guards
f6596d0f-763f-55b4-8244-b21b33f19dce | note | Acceptance / Conformance Criteria - All plants to be fitted with biodegradable plant guards.
000c013b-38e5-5aeb-85c3-d900f30551f2 | note | Standard / Specification - PS 25.6
d5bd1ddb-5d35-5e0f-9f4d-cdc26e633d95 | note | Verifying Document - Site Records
ccbaa216-87b1-5208-9aa3-892e7b93d915 | note | Frequency - Each Plant
80d8707c-6436-5ce6-965a-41341336ef72 | note | Verification Activity: Activity - R
7529786c-19d1-5b4e-a53e-f1bbd810bd82 | note | Verification Activity: By - SE
0245c2b5-b47b-57e0-a8d2-e019282beadb | section | 18.03 Planting
91a6f152-246e-5ca3-89cc-d7ef44d2ca12 | checkpoint | Planting Layout
10e9a539-acb5-5855-92e9-bdba963f1958 | note | Acceptance / Conformance Criteria - All plants shall be positioned in the locations and in the quantities shown on the drawings., Planting Schedule and Typical Cross Sections for inspection and authorisation by the Engineer prior to planting.
8daf41af-8a9a-5024-a1bf-7562fded3640 | note | Standard / Specification - PS 25.7.1
c2ae9ce8-dae3-5679-b06f-463e024606b7 | note | Verifying Document - Site Records
7934fe43-4634-5584-b2ba-93c1dec1b2bf | note | Frequency - Prior to Planting
0ecd96bd-8c8b-5dcf-9e6f-5ebd9097be6e | note | Verification Activity: Activity - HP
915d1dca-4544-5937-a9c1-24cb0fb736b0 | note | Verification Activity: By - ENG
33e0575b-45aa-5ef8-bf3f-2b24bdb55325 | signoff | AUTHORITY HOLDPOINT
5e7c3934-fb84-5a65-924e-bba61c23aefd | checkpoint | Specimen and street trees
6632f74d-f116-5409-ac2c-80107e783c68 | note | Acceptance / Conformance Criteria - Newly planted specimen trees shall be staked with two 50 x 50 x 1.8m rough sawn Pine H4 treated or hardwood stakes with at least one third of their length (600mm) in the ground and at least 1.0m exposed minimum, or as specified on the plan with the approval of the Overseeing Organisation.
ed715475-8ce3-57f7-90d2-9a26a2f8fe57 | note | Standard / Specification - PS 25.7.2.1
16144b60-6eb3-5fb3-ae28-903be1808106 | note | Verifying Document - Site Records
8668fc36-f587-5011-8457-9952d653b799 | note | Frequency - Each Tree
dd2d5248-8397-5ab9-87e2-b14906793955 | note | Verification Activity: Activity - R
b99d3aa3-123c-5cff-a95d-16dd053bac0a | note | Verification Activity: By - SE
40b61210-5602-5e3e-98ba-c165b84d4635 | checkpoint | Irrigation and Fertilising
52bc4507-d26d-5b3c-985f-9ff8b0317924 | note | Acceptance / Conformance Criteria - During installation and establishment, the soil in all planting areas moisture shall be retained to ensure active plant growth throughout the growing season (September – May)..
a3fbd1c3-8cf0-53ff-89a6-36a2cdc5fb6b | note | Standard / Specification - PS 25.7.2.3
926093f4-6765-5c4d-9017-d55952469495 | note | Verifying Document - Site Records
fd53fc2a-1a14-5716-a6fe-12b79955b569 | note | Frequency - Each Area
7af0b96e-1762-521e-bb20-887d48cf7ae0 | note | Verification Activity: Activity - S
8aff2ef7-65ea-5d04-9898-f3ff9497eb05 | note | Verification Activity: By - SE
c17c178f-8b87-5c44-bbf6-5852e952f2e7 | checkpoint | Fertilising
b43bf8a7-0626-54ca-91af-7327e073256f | note | Acceptance / Conformance Criteria - Generally, some form of fertiliser shall be applied to planting depending on the soil type. For shrubs and trees, all fertiliser shall be well mixed with the backfilled soil. For bedding or groundcover all fertiliser shall be well mixed with the site topsoil prior to planting.
dd215dad-30fa-53ab-8857-7d2867e53256 | note | Standard / Specification - PS 25.7.3.2
db256947-821d-5b7a-b8cf-cbd498cc8382 | note | Verifying Document - Site Records
f50ba15d-e9d0-5cd6-9638-358955cff695 | note | Frequency - Each Area
183fae55-8abb-5577-ba0b-64fa1ffeae02 | note | Verification Activity: Activity - S
e4fefcc6-9340-5539-bba1-ba50b2c9027f | note | Verification Activity: By - SE
f13209d5-e412-5458-b06c-52edd25966d1 | checkpoint | Plantings
3da0c09a-ba57-5d3d-a9a7-9452566f0789 | note | Acceptance / Conformance Criteria - All specimen tree plantings shall have two-year slow release fertiliser tablets installed at the time of planting.
b07ecdec-6b86-5a94-a139-db6794641f9c | note | Standard / Specification - PS 25.7.3.3
8d818204-ab08-586d-9389-f11325c464fd | note | Verifying Document - Site Records
20c72060-f758-50fa-9f83-c77d81f3a1f3 | note | Frequency - Each Tree
f6874e20-f5a7-565c-aa07-e9e7fcd5fd69 | note | Verification Activity: Activity - R
a6145589-aff0-5089-879a-2ccb5a61b613 | note | Verification Activity: By - SE
678203b8-7e1c-5fe2-820f-5ceb0b46c40c | checkpoint | Topsoiling (1)
ba8c186d-3920-500d-9b14-70193f2d51d5 | note | Acceptance / Conformance Criteria - All topsoil and operations relating to topsoil for the project shall fully conform to Section F of NZTA P39.
a491f791-782d-567d-be61-9621ba682a8c | note | Standard / Specification - PS 25.8.1
21435210-d0b2-50c7-80d6-0ba99b73b1dd | note | Verifying Document - Site Records
00e71205-5664-5291-a0c2-2581dc7fc85d | note | Frequency - prior to planting.
99bf0c5e-f9f5-5bce-8454-c027d2c437fe | note | Verification Activity: Activity - V
6cc371b9-9162-56fd-9108-f545463171da | note | Verification Activity: By - SE
e4d5c257-ef66-57de-82fb-650887aee12e | checkpoint | Topsoiling (2)
273ea76f-9062-5c89-82c9-4a0a9a50a729 | note | Acceptance / Conformance Criteria - All new planting areas on existing topsoil shall be deep ripped to a minimum of 300mm prior to planting.
7403fc2e-c365-51eb-8591-50f219edddf9 | note | Standard / Specification - PS 25.8.1
2b7b7159-8611-5bc5-ad38-64c02dd2f2c0 | note | Verifying Document - Site Records
dd2d9512-f74d-5e8d-a572-71b49d65facf | note | Frequency - prior to planting.
58c57930-a424-5ce0-a9aa-d1e8b222fa66 | note | Verification Activity: Activity - V
b827995d-31c3-5692-a548-3418d29a101b | note | Verification Activity: By - SE
e7f7a2a8-6c3f-5ab9-a857-499ff39a7ce9 | section | 18.04 Biodegradable Weed Matting and Mulching
7e5a64f3-aac6-528a-ab22-fb7778f98e13 | checkpoint | Biodegradable high density mulch matting
752ffa7d-2b54-529e-a51d-b11dacb04080 | note | Acceptance / Conformance Criteria - The blanket shall be installed according to the Manufacturer’s directions and shall include stapling the blanket at a minimum of 1 metre centres and perimeter edges buried to 300mm depth buried soil.
90105c6f-cd44-5bbe-8e57-d92da3331212 | note | Standard / Specification - PS 25.7.1
3ca332b9-3638-5286-833c-ff29f7603052 | note | Verifying Document - Site Records
ff6462cf-ee21-52d4-ae1d-7268d38fdaaf | note | Frequency - Each Area
fd6e6bdc-e001-57a7-b97a-fd284347eb45 | note | Verification Activity: Activity - R
270f0ae6-6594-59bc-8892-fc82f8680c51 | note | Verification Activity: By - SE
cc47875f-efbf-5fe9-8999-2b9f1d04e76e | checkpoint | Flat Site Mulch
d24a9a43-5ae6-5d03-b278-b2db3786bc04 | note | Acceptance / Conformance Criteria - On sites flatter than a 1:2 grade (1.0m high by 3.0m metres long), bark or arb mulch shall be spread evenly to a depth of 80-100mm over the planted area, creating an inverted cone hollow around each plant stem with a maximum 25mm depth around plant stems.
4602ed8a-ddeb-57d9-b77a-8359e16baa60 | note | Standard / Specification - PS 25.9.2
f579426c-4ec8-5cf0-94fa-6ffc46be0aa0 | note | Verifying Document - Site Records
2a905e5f-7ba5-5493-b8e7-8c03eadb504f | note | Frequency - Each Area
9de682cc-0b03-5cbe-8d99-b727afc742f0 | note | Verification Activity: Activity - R
c0c4bf1e-95f7-5d6d-ace2-7a210fd7d02d | note | Verification Activity: By - SE
fb7f5a22-a6b8-5b1c-aa5e-b445b22ec57b | checkpoint | Steep Site Mulch
66675a8f-e441-5cfc-9f06-11c6e6612396 | note | Acceptance / Conformance Criteria - On slopes steeper than 1:2 mulching for weed control shall consist of an Engineer approved matting with the following criteria:
9e3cbc1e-80ce-552c-a661-231f0d05ff7d | note | Standard / Specification - PS 25.9.2
203fae60-ae42-5c9f-83e9-931d17908a1b | note | Verifying Document - Site Records
da870e1c-dcd4-5cba-9cf3-2c028a1808c3 | note | Frequency - Each Area
e98eeeee-58dc-583c-8a5d-723b564cf322 | note | Verification Activity: Activity - R
22d2f63f-ec41-58ef-94dc-3b408fd7d43a | note | Verification Activity: By - SE
02de62ec-4d3c-5d25-b7ba-2aed1e61e7ba | checkpoint | Very Steep Slopes Mulch
757bb2d8-3f94-5444-adec-c0936483e3c6 | note | Acceptance / Conformance Criteria - On steep slopes (1 in 4) with erosion issues that are receiving planting, biodegradable netting with no geotextile or geonet content shall be used at the Engineer’s discretion.
f3f74240-1f6c-5710-a2f7-202e188a400a | note | Standard / Specification - PS 25.9.2
97cfd863-e1fc-5693-a44b-926c85570599 | note | Verifying Document - Site Records
65d29fe1-efe7-5df5-8421-d5ed971205cf | note | Frequency - Each Area
c287e48f-4343-5196-b0c6-795b83825bb8 | note | Verification Activity: Activity - R
034db315-df2c-5ac2-8291-022c1fa733d0 | note | Verification Activity: By - SE
2304a4bb-d7d7-59b0-8d20-b389a18ac121 | section | 18.05 Grassing, Sowing and Turfing
283dc6bd-25af-597d-80e8-da366bc899e1 | checkpoint | Preparation for sowing or turfing
42a74bf7-07ea-5650-b116-427b21e48df6 | note | Acceptance / Conformance Criteria - Excessive compaction of subsoil in existing grassed areas shall be relieved to achieve satisfactory long-term growing conditions. All topsoil removed to permit contract works to be carried out shall be stockpiled for reuse. All new grass areas shall be built on soil prepared to industry best practice standards. Sloped areas shall be neatly contoured into adjoining grassed areas. Perennial weeds shall be controlled with industry best practice methods.
42f22d56-1b2e-5dd9-8e7e-ce412a998762 | note | Standard / Specification - PS 25.10.1
883730f1-0534-5559-956c-25c24a922d18 | note | Verifying Document - Site Records
a515b698-27c6-572a-b2d0-b77b008f0cad | note | Frequency - Each Area
74185360-26a8-551a-9418-b8c7ccceeb4a | note | Verification Activity: Activity - S
3dd64292-e000-50b0-a4f1-bf68ce09884f | note | Verification Activity: By - SE
d8d3dd3e-5d1a-4efd-aa21-5bfebf2e4eca | checkpoint | Fertilisers
f88555fa-0031-5ed6-90fb-80ea7428a56c | note | Acceptance / Conformance Criteria - Fertilisers shall be lightly arrowed into the topsoil, 2-3 days prior to seed sowing, at the following rates at 200kg/ha. This shall be followed one month after sowing, with an application of: Di-ammonium Phosphate (DAP) 100 kg/ha.
23f0b9a0-f030-552d-b389-0b783a222b88 | note | Standard / Specification - PS 25.10.2
502adcc4-a2cc-5e0c-ba38-9d38487b58e1 | note | Verifying Document - Site Records
b2a09885-3aab-5705-9d72-ae47a30f196f | note | Frequency - 2-3 days prior to seed sowing and 1 month after sowing
d81e1c0c-4402-572b-bed2-e42fd9a3215a | note | Verification Activity: Activity - S
a6c2ebf7-b9d5-5c3b-9f53-4400719113da | note | Verification Activity: By - SE
248eb036-60b7-52ba-9c8a-4c1ffa1f5ec1 | checkpoint | Grass sowing
b0682c74-82f2-5fed-83e5-c3fdf3c4d190 | note | Acceptance / Conformance Criteria - On large areas the seed shall be “check” sown in at least two directions and surface rolled with suitable flat roller. On small areas the grass seed shall be evenly applied and raked into the soil.
35f4351e-28b8-5028-8ed2-3b3c661e8296 | note | Standard / Specification - PS 25.10.3
afc68a78-8685-536b-a04a-a969eae1952b | note | Verifying Document - Site Records
9d14bbcb-3a23-52f9-837f-122b3630231c | note | Frequency - Each Area
2153b853-f066-5e26-81b0-2579cba9c751 | note | Verification Activity: Activity - S
53b42cfc-1410-5e8b-a0c3-ee0205c7c052 | note | Verification Activity: By - SE
0052136b-b06c-592b-8996-4770e11c0f01 | checkpoint | Establishment of sown areas
7a32507a-9ca6-514b-acd3-3687a2d85731 | note | Acceptance / Conformance Criteria - Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state. Grassed areas shall be watered as required to achieve an efficient germination of the seed. Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces.
8b6599aa-b929-5816-b8eb-ad8b78c4002c | note | Standard / Specification - PS 25.10.4
f3c952e8-0d20-5dd2-bcbc-4289c8cf79cf | note | Verifying Document - Site Records
e4eae9dd-0f39-5a98-94cd-9af49680587e | note | Frequency - Each Area
302fd95e-c81a-5189-b41d-7e1d1729bbe1 | note | Verification Activity: Activity - S
9d398b4c-63b8-59ab-8d98-e72e8f82dedb | note | Verification Activity: By - SE
b1606534-eb0d-5f99-8455-683dcea5ac0f | checkpoint | Grassed areas adjacent hardscape
ecde8d65-c8b5-5458-9853-6ac9ad245c52 | note | Acceptance / Conformance Criteria - If base of grass level is 30mm lower or more than adjacent hardstand, grass will need to be removed min 1m back from path, soil put back in, levelled and re-consolidated to spec and grass res-own to correct level. If less than 30mm top dressing at 10mm each time, over time will be acceptable until the correct level is achieved.
22ea21b6-c47f-51f7-a0e9-a5688523edd3 | note | Standard / Specification - PS 25.10.4
057b0227-0f9f-5804-9e7c-ff078242c0e3 | note | Verifying Document - Site Records
b482f5a7-b102-5359-be6d-eb9716b70430 | note | Frequency - Each Area
5e8d1b2b-ae0f-5186-919f-1101c3794384 | note | Verification Activity: Activity - S
e1630edc-f20d-5524-9291-480c3571d56c | note | Verification Activity: By - SE
ebd2e533-06bd-408f-9a6f-cd1ac2943cef | checkpoint | Turf / Instant turf
75bd7488-7fec-5d21-9164-54f138fc9b56 | note | Acceptance / Conformance Criteria - Turf shall be installed and maintained in accordance with supplier’s requirements.
8c35143b-4834-52d2-a97e-7c47267a2043 | note | Standard / Specification - PS 25.10.5
7a829614-20cc-5e48-95e8-25ed55236c1d | note | Verifying Document - Site Records
31edd63e-3416-53d9-975f-4225860768d9 | note | Frequency - Each Area
53c52792-db89-5e04-b7ce-7a7ab0b924d6 | note | Verification Activity: Activity - S
de186dab-2752-5428-a534-dd65420f8209 | note | Verification Activity: By - SE
a70432dc-7d13-59ba-b4b0-331cbf42277c | checkpoint | Slope areas
0857649f-e618-54d8-960d-5d9ed26bfa34 | note | Acceptance / Conformance Criteria - In all sites, except natural gully systems, where the slope gradient is steeper than 1:3 (one metre high by three metres long), it is preferable that the embankment is either scarified or grooved on an angle to a depth of 200mm, from the top of the bank to the base. This assists topsoil adhesion and prevents separation of the top 150mm topsoil from the base material due to gravity and/or glazed/planning of base material.
0f410cd1-2a65-55f3-b257-c981a5a7d9b0 | note | Standard / Specification - PS 25.10.6
c00a54d8-34f9-54b3-8e29-639459e51e30 | note | Verifying Document - Site Records
8d9f7100-ecf4-5889-8f1d-c7180103a177 | note | Frequency - Each Area
52eb5adc-0714-5bba-99ca-6c9c72c41f2c | note | Verification Activity: Activity - S
a1aebe89-7644-5087-8fab-f4a0f0adc93e | note | Verification Activity: By - SE
56f93ee9-b86e-5801-86fb-3982c8bcbddb | section | 18.06 Fencing
888c420a-6b39-501b-87e0-bedb123e2fb6 | checkpoint | Seven Wire Fencing Order
2f5c5927-d6e7-5120-a322-984a754e5f69 | note | Acceptance / Conformance Criteria - The Contractor is to liaise with the property owner to establish the preferred spacing and order of the seven wires.
aab3e80a-79c1-561d-a684-ced1da564057 | note | Standard / Specification - PS 25.12.2
beea47f4-7efc-5714-a502-ebd8a2362fd7 | note | Verifying Document - Comms
c67a6340-0526-54c3-866d-466da07715a6 | note | Frequency - Prior to Installation
f82ad62e-71f5-515b-8424-14f0d876e8de | note | Verification Activity: Activity - R
00233260-3604-552d-82ce-b046b10a2ccb | note | Verification Activity: By - PE
7b5d4c6d-f9a3-577d-9521-361f3d3de258 | checkpoint | Post and Wire Fencing Installation
9637f3b7-eac6-54b1-9cb3-b7400d4c101f | note | Acceptance / Conformance Criteria - New seven wire standard boundary fence shall be erected with the following Offset tolerances 0.0m towards the centreline and 0.0m to 0.3m away from the centreline. The fence shall be vertical, and the grade shall generally follow the contour of the ground.
5ee3c81f-9f73-5b85-8bc7-a0f07c8f8c20 | note | Standard / Specification - PS 25.12.2
ac598ca7-8296-5fbc-9c8d-3af04819d016 | note | Verifying Document - Survey Records
b0f43d9d-fdaf-58e5-bb18-bd797052d98f | note | Frequency - Each Fence
b0f5016c-1cd7-5f84-9f85-b40edc00a60f | note | Verification Activity: Activity - I
afe4d912-8ebe-5fa5-8690-e209686971ec | note | Verification Activity: By - SV
28d686ae-9210-506d-a035-d8a19d76e84d | checklist | ITP - Pavement - Type A - 104.1 - Rev 3 | itp | ITP - Pavement - Type A - 104.1 - Rev 3
dc44bdfa-8be5-58ec-8b02-ddb40309eb3f | section | 4.23 General Pavement Materials
cfc61591-4db6-5f5c-b38b-5d59198b06a2 | checkpoint | 4.23.01 - TX180 Triaxial Geogrid
eb275acc-f0e0-5cbb-aba2-802b823d5206 | note | Acceptance / Conformance Criteria - The Contractor is to supply the product details to the Engineer for approval prior to installation on site.
6b28d1b6-958e-5726-9840-c529acb5fa53 | note | Standard / Specification - PS 20.3.1
39744e82-5e68-56c1-a4a3-8a084b0b32bd | note | Verifying Document - Datasheet
33e7764c-ce20-57c5-b2a1-0a5afe8d17ef | note | Frequency - Each Item
c8db2289-470e-5611-a873-866516a5bb49 | note | Verification Activity: Activity - R
dec10c4f-0ec1-5fa1-860f-eafdf179ee2e | note | Verification Activity: By - SE
26844f90-2cb2-5c40-9048-6e2661d67d85 | section | 4.24 AP65 Subgrade Improvement Layer (SIL) - B/2 Materials (Pavement Type A,B,C)
e75edad3-1c86-5a1f-8bfc-6c857e9980f6 | checkpoint | 4.24.01 - Source Property Tests and Sampling
d3559f9d-3087-5750-9a5b-be0889679e73 | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
e2162fec-05ab-5b93-81ac-6c195f765af4 | note | Standard / Specification - PS 20.4.1
78d83eff-5137-5398-9234-b8865eb916da | note | Verifying Document - IANZ Lab Reports
26da03a4-8a77-5a44-b1ba-56de43b9f945 | note | Frequency - 10,000m3
b7e6eaaa-7096-500c-97cb-26be62ac0184 | note | Verification Activity: Activity - HP
8fe09806-d705-5d61-8530-d1c11072e1af | note | Verification Activity: By - ENG
821e2d25-ab3d-56d6-9cfb-48b3ace0c405 | signoff | AUTHORITY HOLDPOINT
c4148dc8-e4d4-5aa8-8fef-8272efd80760 | checkpoint | 4.24.02 - Crushing Resistance
e18f3add-d27e-5ced-a876-d94de1556043 | note | Acceptance / Conformance Criteria - The crushing resistance shall be not less than 100kN when the aggregate is tested in accordance with NZS:4407: Test 3.10
7ceff534-5a43-5945-ad11-3456b904f6d1 | note | Frequency - 10,000m3
b6069329-ba1f-5175-8985-d8f60d13dd70 | checkpoint | 4.24.03 - Weathering Quality Index
232e8f46-7dd3-53be-a9ad-87d2a6af8baf | note | Acceptance / Conformance Criteria - The aggregate shall have a weathering quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11.
20a54835-34ae-5f49-abb5-4f987cf13cc5 | note | Frequency - 10,000m3
45df2110-45a1-588c-91e6-d377885c2a01 | checkpoint | 4.24.04 - CBR
68a03242-7a04-58b0-919d-1f2aea0e3858 | note | Acceptance / Conformance Criteria - The material shall have a minimum CBR of 40 when compacted to New Zealand heavy compaction standard in accordance with NZS4402 Test 4.1.2 at water content between 4% and 6% by weight of aggregate. CBR testing shall be in accordance with NZS 4407 Test 3.15.
b1719e5c-9ee3-57b7-b9d8-c2f932f1aad3 | note | Frequency - 10,000m3
ab25b02a-711a-5787-97ca-cae645f22451 | checkpoint | Production Property Test Sampling
5dc3b87a-8cd7-5ed1-b1ee-58eb3dba7c1c | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
e94ec950-cd7c-5663-9f02-56884a2b6720 | note | Standard / Specification - PS 20.4.1
f15750c3-7d0c-5ac1-ae6e-5379289faa3a | note | Verifying Document - IANZ Lab Reports
153b082e-26d5-5422-954b-915790b4307a | note | Frequency -
7218844b-678f-57b3-9293-7d47ab73aba6 | note | – – – – – – – – – – – – – –
347db7ee-8887-5d01-851f-b26fced57eef | note | Quantity ¦¦ No. of Samples
41da5358-5552-5c16-b2c4-970d8e238df1 | note | – – – – – – – – – – – – – –
4f2fad2c-5193-589b-b1cd-348551a5bae6 | note | 1 m3 to 400 m3 ¦¦ 2
088e7db3-858c-508f-be3a-373701788b76 | note | 400 m3 to 1,500 m3 ¦¦ 3
229df48d-adbe-503a-8cb4-47c2117c29bc | note | 1,500 m3 to 4,000 m3 ¦¦ 4
a2900c6b-6608-580f-ac62-d5ac1a6d3853 | note | – – – – – – – – – – – – – –
b8c212f4-62ce-5ea0-a5f5-c413e7c9f9a9 | note | Verification Activity: Activity - HP
dc534644-e2a3-5abc-8a0d-f78a4f51400a | note | Verification Activity: By - ENG
8aaa1ba6-266e-5753-9a17-79ca51cfd9c2 | signoff | AUTHORITY HOLDPOINT
76f36ba6-c628-5d91-bad4-888b123dfe37 | checkpoint | 4.24.05 - Aggregate Fractions
5bbbeb17-43e9-52d1-adbe-300244bc32f6 | note | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 50% by weight shall have two or more broken faces. It shall be free of organic matter.
15784ab2-861d-5279-85f9-e10aa41ebdf4 | note | Frequency -
7bad7763-0e4b-5baa-a352-ab0f9a84ac10 | note | – – – – – – – – – – – – – –
7731c330-ac66-5eab-939c-4cb9addf8c1d | note | Quantity ¦¦ No. of Samples
1dbfcba8-dba2-5763-bccb-ae165327fd11 | note | – – – – – – – – – – – – – –
21958f19-d6df-5763-89cc-4954fdb84eba | note | 1 m3 to 400 m3 ¦¦ 2
d783f07c-4679-50e6-b4aa-88ed61306d95 | note | 400 m3 to 1,500 m3 ¦¦ 3
c21487f6-a5e3-5964-858e-800cb3204995 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
c53a3f36-2026-528c-8730-3ddfd887c686 | note | – – – – – – – – – – – – – –
1209906b-8364-5eca-8677-804139a6cda2 | checkpoint | 4.24.06 - Sand Equilavent
2a0dede4-ae07-5734-9884-f2878e75a215 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 30 when the aggregate is tested according to NZS 4407: 1991: Test 3.6. The sand equivalent test may be neglected if the grading test shows less than 4% passing the 75-micron sieve.
607b9bcc-fe53-5483-81bc-db8a442d510a | note | Frequency -
b493bd02-f417-552b-af4d-633696a0dadf | note | – – – – – – – – – – – – – –
d17175b1-a4bb-58ca-aab2-2312e17c805b | note | Quantity ¦¦ No. of Samples
3e7ded3c-4d9a-5f6f-b85c-eb3ea18371a0 | note | – – – – – – – – – – – – – –
329c942f-06c2-5aac-b79f-1871f4e16444 | note | 1 m3 to 400 m3 ¦¦ 2
ee0f83a1-b19d-56c6-ad87-3f1b571bf980 | note | 400 m3 to 1,500 m3 ¦¦ 3
fa290cb7-6e5a-5813-8b28-ca3d08bfd107 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
637e5935-9476-5347-95f4-29ab5f0d68fc | note | – – – – – – – – – – – – – –
f34df8ef-5ff5-5f46-a6b6-8daff95862ec | checkpoint | 4.24.07 - Plasticity Index
a9f9c83b-1334-5d6f-9dd8-ffdc3c00895c | note | Acceptance / Conformance Criteria - The Plasticity Index shall be no less than 8 when the aggregate is tested according to NZS 4407: Test 3.4.
0ff4bdf6-b502-537c-a4ea-244fb1ca8966 | note | Frequency -
58cd39e3-a01c-54f7-92be-980705824686 | note | – – – – – – – – – – – – – –
3e0b1d3f-a307-5835-9d1e-9561c8e96e99 | note | Quantity ¦¦ No. of Samples
bae533eb-ed77-50e8-b895-c65416b77261 | note | – – – – – – – – – – – – – –
866db60b-72ac-5123-862d-fb1e3bbbea98 | note | 1 m3 to 400 m3 ¦¦ 2
872584c7-06c8-54e4-bb04-73228329bc27 | note | 400 m3 to 1,500 m3 ¦¦ 3
02ffc0d4-cd56-5da4-9adc-0ec3d740754e | note | 1,500 m3 to 4,000 m3 ¦¦ 4
3ad0eee7-f8d1-5c04-a1ad-ffe173d116cf | note | – – – – – – – – – – – – – –
29355a6c-cc0e-5a25-b68f-e8c21e9ded67 | checkpoint | 4.24.08 - Clay Index
7e0fcf9c-8f43-562f-93d5-e9fb8a069454 | note | Acceptance / Conformance Criteria - The Clay Index shall be no less than 5 when the aggregate is tested according to NZS 4407: Test 3.5
a18474ef-6bd0-572a-94fc-d93f39688d04 | note | Frequency -
8aceff72-39b8-5bbc-bb81-7bead7c2c1ea | note | – – – – – – – – – – – – – –
0e59c9a0-6d41-54e4-b0c7-524ec9a46749 | note | Quantity ¦¦ No. of Samples
c7031077-d945-5256-b8fd-52664a0c4e64 | note | – – – – – – – – – – – – – –
840fe95e-6fea-5b70-a7b9-d5d6f7883db3 | note | 1 m3 to 400 m3 ¦¦ 2
e2c5138d-9102-5ad4-a54d-38483db3897d | note | 400 m3 to 1,500 m3 ¦¦ 3
e3df1684-35e9-5d91-81bf-c01427ee61ff | note | 1,500 m3 to 4,000 m3 ¦¦ 4
713e2a14-cd20-5581-873e-1d89d8f3d966 | note | – – – – – – – – – – – – – –
be3abd89-23f0-57a2-953e-bd23a6a8c558 | checkpoint | 4.24.09 - Wet Sieving
d04c7da0-0aea-57a7-80aa-39651656cd7b | note | Acceptance / Conformance Criteria - When tested according to NZS: 4407: Test 3.8.1 Standard Method by Wet Sieving or Test 3.8.2 Subsidiary Method by Dry Sieving, the grading of the aggregate shall fall within their respective envelopes defined below or as directed by the Engineer.
0e75a41c-112f-544b-a036-3b346c136662 | note | Frequency -
2f5fb48d-7c48-5221-bc81-c66188d0f1d6 | note | – – – – – – – – – – – – – –
00b2a99b-b4e5-55f4-a748-d50d9cf425c3 | note | Quantity ¦¦ No. of Samples
4a904526-dcff-5140-acab-aa45d50f7e33 | note | – – – – – – – – – – – – – –
25dde087-f72b-56eb-82ac-fe926f24c08e | note | 1 m3 to 400 m3 ¦¦ 2
6902d93b-b7be-584f-bdfe-7586cb65d435 | note | 400 m3 to 1,500 m3 ¦¦ 3
b3b1ba58-0ec1-5eac-a77e-c6edf7cad05e | note | 1,500 m3 to 4,000 m3 ¦¦ 4
44aa639a-0611-57e5-8098-c7683a441b61 | note | – – – – – – – – – – – – – –
c124d68f-2b35-5659-b3a4-c565239e94ef | checkpoint | 4.24.10 - Testing for Layer Compaction - MDD
eb3552b1-21c5-5d51-a2ee-a1448d9ff13b | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for SIL construction shall be the maximum laboratory dry density using Heavy compaction.
ac575479-1740-5f1f-9b2c-28d02d49a866 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.4.1
0e4d1e78-56aa-5357-83ef-0815a117a7dd | note | Verifying Document - IANZ Lab Reports
c862ccd8-0d12-5391-a1cd-dbb236ab7f4e | note | Frequency - 5,000m2
042d84d5-4a01-53a4-9236-019965c91f22 | note | Verification Activity: Activity - R
15f8ae9d-dfd7-592a-95c3-27bdfd569fb9 | note | Verification Activity: By - PE
c12729c5-67f6-5d43-b1f2-57394d510061 | section | 4.26 GAP65 Subgrade Improvement Layer - B/2 Materials
347684f7-e1c7-5e11-ad68-cbfef2b04889 | checkpoint | 4.26.01 - Source Property Tests and Sampling
0db67a2c-4842-510f-b373-d349ffe7325f | note | Acceptance / Conformance Criteria - The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
4024816f-cf24-5d0e-9ed9-662f93390b30 | note | Standard / Specification - PS 20.9.1
fd7a85da-0c2a-59c1-ba71-475bf206d125 | note | Verifying Document - IANZ Lab Reports
ebd6989e-4996-5228-aa5e-7877982567f1 | note | Frequency - 10,000m3
67774f6f-b8e0-5e53-96e6-4c764a97ec15 | note | Verification Activity: Activity - HP
0130f621-f545-5eb1-984f-2fb87f95176e | note | Verification Activity: By - ENG
21763a79-b0fc-5f07-a2bc-5a044a2a7ee3 | signoff | AUTHORITY HOLDPOINT
c80204b2-f1b8-5861-9b87-7b0389a79aa0 | checkpoint | 4.26.02 - Production Property Test Sampling
2715851f-641c-5500-8774-1e281a7b1283 | note | Acceptance / Conformance Criteria - The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
569f0a78-a929-5ed0-a4b9-9a28857cb6b8 | note | Standard / Specification - PS 20.9.1
eff36539-1e27-5ef8-80f4-98d968ddaee8 | note | Verifying Document - IANZ Lab Reports
26415d47-53e5-5e39-aed3-d7c4f2ea7777 | note | Frequency -
f318226d-6c46-527b-9e06-c2cb0844467e | note | – – – – – – – – – – – – – –
47cb0837-4f1a-5a71-a7d0-bccdf603b946 | note | Quantity ¦¦ No. of Samples
37037217-ee28-594f-91bf-2883128f2d09 | note | – – – – – – – – – – – – – –
e0ec16ea-7879-5e18-a667-39189d82d974 | note | 1 m3 to 400 m3 ¦¦ 2
975796be-e84b-51db-81f1-d86028440fd0 | note | 400 m3 to 1,500 m3 ¦¦ 3
4415e3e8-84d0-58fd-aa67-c3c3c4716552 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
47226527-9481-52e5-bf31-176acb7f0f67 | note | – – – – – – – – – – – – – –
2abf0a9a-5b34-5365-be05-2369dced5659 | note | Verification Activity: Activity - HP
25315bd7-8cd3-5910-b021-dfb660353d93 | note | Verification Activity: By - ENG
fcbd0b78-66c4-52db-a924-1c9d0e913898 | signoff | AUTHORITY HOLDPOINT
0af9249c-48a9-550f-ae9e-c6f4cfa0fd7d | checkpoint | 4.26.03 - Testing for Layer Compaction - MDD
301b5806-e420-5156-8b68-4d3fbf8aa8fc | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for GAP65 SIL construction shall be the maximum laboratory dry density using Heavy compaction.
005b9869-d017-5b98-a960-c6ec769c2989 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.9.1
e7db43be-15b3-5e4b-a26d-6ce2fbfa39b4 | note | Verifying Document - IANZ Lab Reports
721b1b26-bdd6-5a7f-8b6a-0687627f2cba | note | Frequency - 5,000m2
8e9c48ee-cd8d-5f36-a5e2-0d1b75fb4e71 | note | Verification Activity: Activity - R
238d1e42-c9b8-5e22-a2a2-d9e5a72b0dbc | note | Verification Activity: By - PE
2acdd5f1-32ac-5faa-8b88-3bea1a6d6ab7 | section | 4.30 NZTA M27 2020 - STONE MASTIC ASPHALT MATERIALS
210fcf50-fae8-5a16-bddc-909108432f14 | checkpoint | 4.30.01 - Coarse Aggregate - Property Tests and Sampling
38609e58-1739-544b-b4a2-2d1a4498a76c | note | Acceptance / Conformance Criteria - The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, Bulk SG and Density, Absorption, and Particle Size Distribution
2876a93e-0b96-5360-acf8-ea900f26d0fe | note | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.1
0bf92c30-ab5f-50b0-9115-ccea7b562f8c | note | Verifying Document - IANZ Lab Reports
a9297d20-39e7-5757-ad7b-2638fa31d912 | note | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
d4bfa928-d081-5990-af79-53ec225972ce | note | Verification Activity: Activity - H
912e9352-c363-5572-b8f5-83bdcd540813 | note | Verification Activity: By - PE
5d046762-3ad1-5b69-a01c-8359e1fd11b0 | checkpoint | 4.30.02 - Fine Aggregate - Property Tests and Sampling
e3f39f9e-0231-5752-81d7-89138fa05bc9 | note | Acceptance / Conformance Criteria - The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, Bulk SG and Density, Absorption, and Particle Size Distribution
f0f0938d-37dc-54e2-8ce5-c5726ccebad5 | note | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.1
cb4ad1a4-368f-5b8a-9248-acb19744d6bc | note | Verifying Document - IANZ Lab Reports
d007a0ea-755e-59a1-89e0-530efa6f4795 | note | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
ad87c10d-8723-5b91-822a-cc2eddf1a23b | note | Verification Activity: Activity - H
2d82290c-3b61-5cd6-ab27-fa487458fec9 | note | Verification Activity: By - PE
eba5749e-1122-5932-b8f4-867c68e0f113 | checkpoint | 4.30.03 - Mineral Filler
cf1bc6c3-41ef-56b3-a89b-c711bda60c3e | note | Acceptance / Conformance Criteria - Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt.
ee034af1-6b0b-5406-8f6f-94c74d21dfb0 | note | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.2 ASTM D242
dcba61d1-e0e8-58c8-a6fd-7fdfb67f03ea | note | Verifying Document - IANZ Lab Reports
b207ce4a-c249-595f-9af5-5a79a45abe98 | note | Frequency - Prior to use
8644ecc0-8c1a-5380-943a-aa3e0cf07709 | note | Verification Activity: Activity - H
cc64cd92-bdac-5b36-8139-b16a92c7d907 | note | Verification Activity: By - PE
132d7154-1055-5fb7-ac28-fb50add81e62 | checkpoint | 4.30.04 - Bitumen
9ea48a9b-ab21-58ab-a60e-6d3f3fedcbc4 | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
4eec4f1e-3636-577d-bca5-977bc511cdcc | note | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.4.1, NZTA M01-A
3a821957-00da-5453-89e6-db0809bcf24f | note | Verifying Document - IANZ Lab Reports
b75c75d9-182c-5152-829b-6321651ce85d | note | Frequency - Prior to use
ddb515ae-4f1c-59e7-8f77-527e5e5a33c8 | note | Verification Activity: Activity - H
5f7dc6b4-ce48-51dd-a11b-9f703d1b8455 | note | Verification Activity: By - PE
46a61941-0f49-5cc4-9374-0f3efcb3d89f | checkpoint | 4.30.05 - Mix Design Approval
121b9d77-3770-56ea-bb23-e1d8abd26750 | note | Acceptance / Conformance Criteria - The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use.
db5cff24-7036-5811-abec-58c62cab3807 | note | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 3.1 , 3.6
26c8f2bf-c1ab-5380-aef4-f2229de01aec | note | Verifying Document - Approved Mix Design
b467f87c-70f7-597c-884d-37f9cbb489c4 | note | Frequency - Prior to Use
241a7bce-7295-5f24-bf1b-519f346a214e | note | Verification Activity: Activity - HP
93320131-84f0-512f-8447-b5f977f07c35 | note | Verification Activity: By - ENG
f1280a95-c783-5daf-9f62-cb9f12c6e95e | signoff | AUTHORITY HOLDPOINT
4b8b3e3f-abfb-552c-8b9a-d02e9d221fa8 | section | 4.32 Sealing Chip Supply
dc0bdfbb-dcfe-5f1b-864a-6564086b5926 | checkpoint | 4.32.01 - Sealing Chip - Source Property Tests and Sampling
0987cc7d-4a62-57d4-a9b5-b3f85647aa2d | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
2dcbc060-c14c-5b51-b4ae-4495b3371e51 | note | Standard / Specification - PS 21.1.1 TNZ M/6: 2019 - 4
583f0ab6-98ec-55f2-8f4d-15c22513b04b | note | Verifying Document - IANZ Lab Reports
b9452372-e643-5d4e-804b-5ae73417c8e7 | note | Frequency - Before Supply and Every 10,000m3 Thereafter
b6366bdb-f185-5d89-b65e-a9db35967664 | note | Verification Activity: Activity - R
bb2db9e8-e5ea-521f-a851-b1d37d8daabe | note | Verification Activity: By - SE
14761c8b-a8dc-52c5-ac4b-8b828dbd7c6f | checkpoint | 4.32.02 - Sealing Chip - Production Property Test Sampling
9c5e6222-2b4e-5944-8b0a-686a84e875cd | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
50177839-94cd-5fc5-8e8f-e65990a78abe | note | Standard / Specification - PS 21.1.1 TNZ M/6: 2019 - 5
2b03fbe5-238a-5e1a-a4a6-2fce1e8f705c | note | Verifying Document - IANZ Lab Reports
01de661d-e3ae-5d8f-8442-be6d811ddf2d | note | Frequency - Every 500m3
1073cfe2-e5ce-59d9-bdd3-f4e1cef8ac67 | note | Verification Activity: Activity - R
8b07fd72-8ee9-5fbd-9f7c-94583b638acd | note | Verification Activity: By - SE
ba197f5f-8424-5ec1-a3d9-dadedbf26007 | section | 4.33 Bitumen Supply
1c072438-aaf9-58a3-9d3f-4562dc4413df | checkpoint | 4.33.01 - Bitumen - Quality Testing
1224eb32-74b0-5413-b590-9deb53210aa4 | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
f7bb8c91-f481-5e43-a9b8-3ce417e1b2e6 | note | Standard / Specification - PS 21.1.1 NZTA M01: 2022 - 6
51378185-cb95-52f9-ad4c-e2000fb8f7e1 | note | Verifying Document - IANZ Lab Reports
0fdfbad6-961f-5f44-bfb1-c849b10c51bc | note | Frequency - One test per grade supplied
ceb7fe19-417f-548e-a83c-26e7b4b76e26 | note | Verification Activity: Activity - R
ef84b470-c80d-5c43-afe0-7aef4434315e | note | Verification Activity: By - SE
2e0b4d70-3e4a-54f0-9c3c-db969a116315 | checkpoint | 4.33.02 - Bitumen - Supply Testing
bdc99482-93d8-5aac-a556-edbeb3993ccd | note | Acceptance / Conformance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
b0b0557e-2030-5dc7-94c2-86ffad7d4d79 | note | Standard / Specification - PS 21.1.1 NZTA Q05: 2022 - 6.2
c08651a8-a2ff-526e-8cf1-25e00d00ec25 | note | Verifying Document - IANZ Lab Reports
98673ba4-ec0f-5acb-a811-3619ad2e03aa | note | Frequency - Every 200 tonnes supplied.
123b6a7c-3d74-5152-87c8-4b55c8ec4ddd | note | Verification Activity: Activity - R
8fdaaea9-e7c6-5557-a6fa-43252c57f61c | note | Verification Activity: By - SE
2b18b70e-b064-539a-bbe2-652876ead08a | checkpoint | 4.33.03 - Adhesion Agents
8cc47c22-8349-5225-896f-a8f708190a31 | note | Acceptance / Conformance Criteria - When used, Adhesion agents must be approved & blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents.
426d54cd-651a-507b-ab26-2de02f635ef1 | note | Standard / Specification - TNZ M13
8d9669d5-a3d5-5e69-a719-a83a35971670 | note | Verifying Document - Binder Aggregate Adhesion Test
44d9a855-4690-5aad-a088-f785feed826b | note | Frequency - Each Adhesion Agent and Dosage Rate for a Particular Chip Source
e40bb8fa-6cec-5fab-bcc4-3f527a28b352 | note | Verification Activity: Activity - R
8d4a83ce-de10-5250-a32e-0232ff1954b5 | note | Verification Activity: By - SE
8f4bd0a5-2c00-5e11-be9d-a8061092d736 | checkpoint | 4.33.04 - Sprayer Certification
282e4525-947e-5a7f-a85b-67194285ca71 | note | Acceptance / Conformance Criteria - The binder shall be applied with a bitumen distributor, operated in accordance with BCA E/2, Specification for Performance of Bitumen Distributors administered by the New Zealand Bitumen Contractors' Association Inc.
360d84af-a4da-5d9a-9be1-44813d7670ed | note | Standard / Specification - TNZ P3 TNZ P4
e5d40eef-334f-5487-84f3-a0a54d31511b | note | Verifying Document - E2 Cert
49f32913-9a5f-5354-a1e9-b937121d7ae0 | note | Frequency - Each Sprayer
74717482-618f-50e0-aa2b-969234a107d2 | note | Verification Activity: Activity - R
515d90f7-6301-5fde-8bd7-05f72a358dba | note | Verification Activity: By - SE
02958b5a-5ebd-51c0-9468-f8abb27c9de0 | section | 4.34 Hi-Lab 65 Material Pavement Type A,B
eb562677-ae1e-56c0-bd1e-78ae996a097d | checkpoint | Hi-Lab 65 - Source Properties
2f8b25a5-fc04-5f73-bddb-f1981af8a493 | note | Acceptance / Conformance Criteria - The Hi-Lab aggregate shall be crushed from quarried rock and consist of hard, sound material of uniform quality, free from soft or disintegrated stone or other deleterious material.
c887a772-8daa-5007-9357-6073fe15d1d8 | note | ○ Source property testing shall beOnly one set is needed if HI-LAB40 and 65 come for the same source
c261905e-ed44-5100-8a83-36613d80745e | note | Standard / Specification - NZTA B10 - 2.2.1, 2.3.5
bc31d9e5-2a4b-5e2d-911e-0c2353fc03f3 | note | Verifying Document - IANZ Lab Reports
c7246ea9-9799-5215-96b3-536ff237b024 | note | Frequency - One test for every 10,000m³
6edf3639-ba9e-5689-9f1b-4a4faebf95ff | note | Verification Activity: Activity - HP
23ab8b73-700b-5812-82c4-b5bbdd9ee5aa | note | Verification Activity: By - ENG
6e353bb2-bbdb-5f33-9e07-0646c75fc100 | signoff | AUTHORITY HOLDPOINT
61903216-c0dd-5e21-a86d-90ca29993957 | checkpoint | 4.34.01 - Crushing Resistance
323ffd4e-9bce-5652-8d1a-254c6248b6d4 | note | Acceptance / Conformance Criteria - < 10% Fines @ 160kN
04676339-7e18-572f-91fd-c218104a2018 | note | Standard / Specification - NZS 4407 Test 3.10
299b3f6b-35ea-59ab-a4e4-08d4de0634bf | note | Verifying Document - IANZ Lab Reports
0dbcec1f-520b-5629-aa33-090514d0a531 | note | Frequency - One test for every 10,000m³
4d53405b-9478-52ec-b483-d08d0d531834 | note | Verification Activity: Activity - HP
e24d3fe3-1134-5d15-adf8-973dde9c5421 | note | Verification Activity: By - ENG
fc856423-920e-52d6-b8e8-de27efbc3b57 | signoff | AUTHORITY HOLDPOINT
87b037ab-6c0c-5548-bce2-ad9c4565bfff | checkpoint | 4.34.02 - Weathering Quality Index
57cb7ec1-71e9-56ec-bb53-36691ddf5c28 | note | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
081620a3-8301-51bd-a783-3e2d91fa8a08 | note | Standard / Specification - NZS 4407 Test 3.11
58b8bf1e-6a6d-57f7-a333-4679b0d55d35 | note | Verifying Document - IANZ Lab Reports
1e3b4f53-120f-5152-ac4d-33a81fd9e76c | note | Frequency - One test for every 10,000m³
3645fccd-6de7-55f7-a06a-c2af1391f464 | note | Verification Activity: Activity - HP
d2696e6f-fdd9-56bf-9699-a822eda12d83 | note | Verification Activity: By - ENG
de152f62-5b10-59c9-89b9-6d9b0f8a3728 | signoff | AUTHORITY HOLDPOINT
bdc4a671-9f50-59cb-8327-92a910c7b3ed | checkpoint | 4.34.03 - Ethylene Glycol Accelerated Weathering
5b51d316-7ae6-588d-971b-760623a33ae9 | note | Acceptance / Conformance Criteria - Proportional change < 30%
5beb550b-edcb-57ee-a8da-41099dbf8b51 | note | ○ Note: If the result for the source rock exceeds 30%, further testing to detect the presence of smectite clays shall be carried out using X-ray diffraction. If the aggregate is shown contain trace amounts only of smectite clays (i.e. XRD <100 counts) then the source rock may be considered compliant with this criterion
f213c98e-6dd3-51a1-823f-a3445793a646 | note | Standard / Specification - NZTA T20
fd1027c2-41f4-508e-a831-4adf3ec0d845 | note | Verifying Document - IANZ Lab Reports
c1975883-dee0-52ca-ad5a-7d597ec16958 | note | Frequency - One test for every 10,000m³
08059552-ff7a-5522-849f-2bd41a055723 | note | Verification Activity: Activity - HP
50f36a1b-4ca8-53e6-b274-20f157fc2df4 | note | Verification Activity: By - ENG
60483818-a26b-559d-881f-107b3f615916 | signoff | AUTHORITY HOLDPOINT
d6bd15eb-c4ba-582e-9ed1-0d37a77f1680 | checkpoint | 4.34.04 - Solid Density
dab00749-3993-5149-8f23-9d9018b11f1f | note | Acceptance / Conformance Criteria - The solid density of the Hi-Lab shall be determined in accordance with NZS 4407 Test 3.7.1 Solid Density of Aggregate Particles.
2a145f41-3ccb-56f0-93d0-9de533329f2d | note | Standard / Specification - NZS 4407 Test 3.7.1 Solid Density of Aggregate Particles
22090bec-d2f5-5e0b-b66b-4152c7be3957 | note | Verifying Document - IANZ Lab Reports
c0862061-af36-52af-89e7-ea110e2d7b51 | note | Frequency - Two tests per aggregate source then one test every 5,000m³
29057344-9f47-510a-ace4-b9ae543eb97a | note | Verification Activity: Activity - HP
fba60311-69d2-5678-ae52-43cccc17f0a7 | note | Verification Activity: By - ENG
89797393-33cd-5c65-811c-af4a28f5adcd | signoff | AUTHORITY HOLDPOINT
01cecd36-b7d4-59e8-91ab-257e38deed9e | checkpoint | Hi-Lab 65 - Production Properties
35fd4fff-5161-5239-88d2-1365d50b5863 | note | Acceptance / Conformance Criteria - The Hi-Lab 65 shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Broken Faces, Aggregate Flakiness Value, and Grading.
4c483d0f-14d8-57bc-95de-4f1345fea33c | note | Standard / Specification - NZTA B10 - 1.2.1
d2f3876e-8e92-57fb-b3f4-877c8ff9ef44 | note | Verifying Document - IANZ Lab Reports
9dcae97d-2d22-5b1e-871d-1ac248a99c21 | note | Frequency - Test for every 1,000 tonnes of material produced
34628dd3-8d40-595c-be0f-ccf3568f3da6 | note | Verification Activity: Activity - HP
277536d2-563a-5679-b5fd-97ba49460eb4 | note | Verification Activity: By - ENG
e45073ec-9dfb-51b2-994a-d676e493f6d9 | signoff | AUTHORITY HOLDPOINT
876700e5-1191-52be-9306-0c485e04dcd9 | checkpoint | 4.34.05 - Two Broken Faces
72bf0537-01ac-56e9-8b0e-05afadd76e45 | note | Acceptance / Conformance Criteria - 100% of sample
78745ed6-6858-5296-9fa2-d26e0c240e21 | note | ○ Note: Hi-Lab aggregate produced from a hard rock quarry source using angular and broken feedstock need not be tested for Broken Faces Content which may be assumed to be 100%.
1fe2b849-1da5-5e34-be61-137947ac24f2 | note | Standard / Specification - NZS 4407 Test 3.14
7f6c0421-cdee-5305-9ea5-cf00ae06e3dd | note | Verifying Document - IANZ Lab Reports
940d8e9c-a711-5460-bfa0-d41a658616e5 | note | Frequency - Test for every 1,000 tonnes of material produced
debe376a-7653-531e-8a54-42734e88ae2a | note | Verification Activity: Activity - HP
39a4fd92-a9e1-504b-8659-40d4e26f8482 | note | Verification Activity: By - ENG
11251e42-cd63-5327-aa50-91a778eb7470 | signoff | AUTHORITY HOLDPOINT
14002a20-d1c2-52a2-8760-f52bec35d8aa | checkpoint | 4.34.06 - Clay Index (<0.075mm)
c5f5fea3-62ca-5fe7-9ff7-2595577f9012 | note | Acceptance / Conformance Criteria - 5 maximum
1d2c7442-226c-537b-b066-c0d5beeff8ea | note | Standard / Specification - NZS 4407 Test 3.5
1a4b558a-2ccc-55e7-a1e8-2c77d3a7b175 | note | Verifying Document - IANZ Lab Reports
4078cc2d-72d6-565d-8bc7-2deb85539e90 | note | Frequency - Test for every 1,000 tonnes of material produced
f25d0f72-074b-52c3-b3c9-b6cc5ce2cdb8 | note | Verification Activity: Activity - HP
afd41f73-2eda-5eed-8723-a13dee73751f | note | Verification Activity: By - ENG
450b6635-c172-5d7b-b30e-beb1caa7d328 | signoff | AUTHORITY HOLDPOINT
524842e9-73e1-57e7-9c9a-aedde973bfe5 | checkpoint | 4.34.07 - Plasticity Index
f5257b7b-9db5-5f3c-8fb5-8437ba2685d6 | note | Acceptance / Conformance Criteria - 8 maximum
6ec091d4-8135-5698-8c78-f0c50c789057 | note | Standard / Specification - NZS 4407 Test
ffe2362d-149b-5cf9-8348-f9fc36c01e22 | note | Verifying Document - IANZ Lab Reports
a4d35ee0-c540-5c34-a48a-1dcfd5853ab6 | note | Frequency - Test for every 1,000 tonnes of material produced
751dec8b-f747-54bc-9c5e-4cd240a5d2ed | note | Verification Activity: Activity - HP
0a14f624-83b9-5036-9baf-1353471e83c0 | note | Verification Activity: By - ENG
8767007b-5c90-5d39-a992-fc122ea9e108 | signoff | AUTHORITY HOLDPOINT
9a11aa9c-cddd-56da-8583-505da547064e | checkpoint | 4.34.08 - Aggregate Particle Size Distribution
d058ba29-2a07-5d82-8c6f-40399cc15aa9 | note | Acceptance / Conformance Criteria - The particle size distribution during production of the blended Hi-Lab products shall comply with the limits in Table 0.3.
7038969c-01f3-58ab-bc2a-a64ab9a56e08 | note | ○ A minimum sample of 90kg of aggregate shall be used for each test.
107faf7f-705f-5549-8ef9-b608d3061340 | note | Test results shall be evaluated as follows:
946b14ba-5701-5c16-9335-03e2fc98cd25 | note | (a) The rolling average results of five consecutive test samples shall be within the upper and lower limits for each test sieve
46495750-71f4-541f-b503-6d7620d4f987 | note | (b) No individual test result shall be outside the envelope formed by the lower buffer zone and the upper limit.
e87bc324-f9e4-564a-a34d-0acca2ea73c0 | note | ○ Note: Experience has shown that a blending plant with a minimum of three component feed bins is required to produce a consistently compliant Hi-Lab aggregate product.
642c0ae3-08a6-598b-afb1-aa1c0d008fc5 | note | – – – – – – – – – – – – – –
fd5ef903-e591-550d-bc33-b9deda56459c | note | Table 0.3 Hi-Lab 65 Particle Size Distribution Limits
97a51ad0-3f2b-5f76-8d09-2787ff2dd73f | note | Sieve Size (mm) ¦¦ Lower Buffer / Lower Limit / Upper Limit
dc7d5ab6-d25c-57ca-9fd5-8cab28e48b82 | note | – – – – – – – – – – – – – –
b2a6a581-6178-5000-be7e-a02321fb865b | note | 63.0 ¦¦ - / 95 / 100
3689032d-8d21-5eba-8053-0bd2a012dde2 | note | 37.5 ¦¦ 35 / 40 / 50
0547f42a-4654-5f36-b79a-8c0d26f6b900 | note | 19 ¦¦ 15 / 20 / 30
eac4344e-234c-558a-9853-10e35ffbac18 | note | 9.5 ¦¦ 10 / 12 / 16
42f667c9-3a95-5f3e-b6e9-9d37b778f15e | note | 4.75 ¦¦ 9 / 10 / 14
96847dd1-e916-5bc7-843d-308ffafa78f5 | note | 2.36 ¦¦ 6 / 7 / 12
814afd53-ec39-5255-aa82-4dcb0e83484e | note | 1.18 ¦¦ 4 / 5 / 10
3a866db0-a7e5-534d-98a9-fddf9dff82e3 | note | 0.075 ¦¦ - / 0 / 6
84f0431b-b94c-5af6-aa5a-3cac5c58857a | note | – – – – – – – – – – – – – –
9a902226-ef71-5c45-abb2-512db82c95f3 | note | Standard / Specification - NZS 4407 Test 3.8.2
ccde93bf-a52e-5972-922c-f9c98136e2a3 | note | Verifying Document - IANZ Lab Reports
436ff914-5baf-590d-9fd0-e606f58446a6 | note | Frequency - Test samples shall be drawn and tested for every 1,000 tonnes produced. A minimum of 5 production test samples shall be drawn and tested for any one production lot.
ff7081c6-bb4d-5362-8e41-7c3ed7c72653 | note | Verification Activity: Activity - HP
6880eeb7-0247-5955-90e1-2c5226b552fc | note | Verification Activity: By - ENG
e3454e63-b504-57ae-83a2-92c59c58fa01 | signoff | AUTHORITY HOLDPOINT
690d9740-fbd2-59ff-9863-e3cb2335f32f | checkpoint | 4.34.09 - Aggregate Flakiness Value
0e4d8fe0-116a-5423-8a4a-5b8c023ae3a9 | note | Acceptance / Conformance Criteria - The percentage of flaky particles for each of the aggregate test fractions coarser than 9.50mm specified by AS 1141.15 Table 1 shall be determined and reported, and the Flakiness Value for each size fraction comply with the minimum requirement of Table 0.5:
7f6a593f-4bb9-50c3-afa2-1f3760b55690 | note | – – – – – – – – – – – – – –
aef24a5a-be4f-5446-bf3f-e881f90fdc0a | note | Table 0.5 Aggregate Flakiness Value Requirement for Each Fraction
9abedb67-1bee-53b1-8336-d9527ac7029c | note | Aggregate Grade ¦¦ Test Method ¦¦ Requirement
889fe766-fa4d-5b31-b253-6f72e5f4b52b | note | – – – – – – – – – – – – – –
855c8e17-7b85-57aa-b08c-e20f812c46e4 | note | Hi Lab 65 ¦¦ AS 1141.15 ¦¦ < 30%
d9cf4194-873c-5665-8121-1a63747f23bf | note | Hi-Lab 40 ¦¦ AS 1141.15 ¦¦ < 30%
fae3cdef-40b0-5519-9112-aa11dfa764af | note | – – – – – – – – – – – – – –
b303ef47-6de6-528e-bb2b-25ec9f15a98e | note | Standard / Specification - Method of AS 1141.15
efecb35e-6ace-5c91-b33f-8e4e352c8dc2 | note | Verifying Document - IANZ Lab Reports
c789013e-2457-5a27-9825-1e0a0896ac9f | note | Verification Activity: Activity - HP
4a32385f-f397-5767-8f7f-c8d1ca5830aa | note | Verification Activity: By - ENG
4d96f701-0a5c-5590-ae84-8f653cbc2bec | signoff | AUTHORITY HOLDPOINT
7e147702-bd9b-563b-aa01-1f11f9cba4bd | section | 4.35 Hi-Lab 40 Material Pavement Type A
2926ce2f-aee1-57db-b367-f2a57f15b1bf | checkpoint | Hi-Lab 40 - Source Properties
8025906c-57c7-5457-8a3f-bcfbb8df679b | note | Acceptance / Conformance Criteria - The Hi-Lab aggregate shall be crushed from quarried rock and consist of hard, sound material of uniform quality, free from soft or disintegrated stone or other deleterious material.
792bf1c8-ac47-5f5c-af60-34aaafecf0fd | note | ○ Source property testing shall beOnly one set is needed if HI-LAB40 and 65 come for the same source
f1a7b658-2667-5520-a40d-05cc3b5de93b | note | Standard / Specification - NZTA B10 - 2.2.1, 2.3.5
ea43db70-1d04-52ae-b67b-284563c2d859 | note | Verifying Document - IANZ Lab Reports
5e9d6d1c-3cac-5734-b630-ad99957b2fcc | note | Frequency - One test for every 10,000m³
63651bbc-4285-5659-872f-3755853dde33 | note | Verification Activity: Activity - HP
761a6480-ff7e-51c8-b854-3ac1d2e62cbf | note | Verification Activity: By - ENG
cdfad855-1026-550f-81f5-e200f6e1914a | signoff | AUTHORITY HOLDPOINT
f6861998-97a2-50c5-8818-2028d98237b7 | checkpoint | 4.35.01 - Crushing Resistance
abbcf2cf-cdbe-5657-b2b6-81066017a653 | note | Acceptance / Conformance Criteria - < 10% Fines @ 160kN
a661c0c4-28e4-54d5-81c4-10d20950e5f9 | note | Standard / Specification - NZS 4407 Test 3.10
53a207e3-4341-5122-87d9-f90f49a42703 | note | Verifying Document - IANZ Lab Reports
edc4f541-c18c-5cf3-80cd-6ba938cd4855 | note | Frequency - One test for every 10,000m³
a97e52d4-8067-5d33-87a4-46b929b5f610 | note | Verification Activity: Activity - HP
f80e4f9e-9d68-54ae-a043-98308050d5ad | note | Verification Activity: By - ENG
9976b4e2-74c3-5f69-8298-6da5575eb8ba | signoff | AUTHORITY HOLDPOINT
906c30d7-1cc5-54e1-9389-cbecc1615fa4 | checkpoint | 4.35.02 - Weathering Quality Index
ebc181f9-ecf1-518b-a4bf-05b26d33848a | note | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
19df86e3-f491-5269-b335-66bd8967c91a | note | Standard / Specification - NZS 4407 Test 3.11
133628b2-91ef-5543-9dfd-77e114df1338 | note | Verifying Document - IANZ Lab Reports
6b7f78c4-fbe2-57a8-9246-ef182525f62b | note | Frequency - One test for every 10,000m³
fd9bcb36-9269-583c-8048-afe8701dea0e | note | Verification Activity: Activity - HP
44e42f6c-4a15-5dc5-9377-c01a9f351693 | note | Verification Activity: By - ENG
987c4aa7-6625-5c18-988d-e6a882bdb55c | signoff | AUTHORITY HOLDPOINT
291d21ce-bf2d-5ba0-9f92-c37d42b06841 | checkpoint | 4.35.03 - Ethylene Glycol Accelerated Weathering
22237d8c-b90b-538a-bf6a-335d6743e60e | note | Acceptance / Conformance Criteria - Proportional change < 30%
c03127b4-0c1d-559a-ba69-ff2432ddea90 | note | ○ Note: If the result for the source rock exceeds 30%, further testing to detect the presence of smectite clays shall be carried out using X-ray diffraction. If the aggregate is shown contain trace amounts only of smectite clays (i.e. XRD <100 counts) then the source rock may be considered compliant with this criterion
8111a7ab-405f-5136-96f1-e8b4d62d97d0 | note | Standard / Specification - NZTA T20
e86eddfd-2475-5257-ad56-3daf3701e6cf | note | Verifying Document - IANZ Lab Reports
921a6816-deba-5f76-8c02-cbc2f87e4b5b | note | Frequency - One test for every 10,000m³
1d9dd9db-e555-5305-b809-607fbfcbf4c6 | note | Verification Activity: Activity - HP
a13f1a39-07f4-5698-86a3-5f97ef670ada | note | Verification Activity: By - ENG
dc6a68c9-cd5d-5f59-898f-bc79fd767c00 | signoff | AUTHORITY HOLDPOINT
f18ddd43-28c9-5f5b-a07d-06460413a28c | checkpoint | 4.35.04 - Hi-Lab 40 - Solid Density Testing
99ab4973-10c7-511f-a8e1-7b920cf4fd81 | note | Acceptance / Conformance Criteria - The solid density of the Hi-Lab shall be determined in accordance with NZS 4407 Test 3.7.1 Solid Density of Aggregate Particles.
36966d9f-f947-5552-abad-22449817fbac | note | Standard / Specification - NZS 4407 Test 3.7.1 Solid Density of Aggregate Particles
fdcc7444-714f-5d55-a4c9-43e09e935b73 | note | Verifying Document - IANZ Lab Reports
b3b2f34f-3509-5936-a3f0-86e986da843f | note | Frequency - Two tests per aggregate source then one test every 5,000m³
a9ec5311-6f5c-5565-908f-f811e28570ac | note | Verification Activity: Activity - HP
82e97e7f-49d6-596a-9c82-0de6f689c963 | note | Verification Activity: By - ENG
c69da515-b434-5c22-bdb0-6e2988888ceb | signoff | AUTHORITY HOLDPOINT
bed35c2a-b998-5053-9e4b-e79e381d2e4a | checkpoint | Hi-Lab 40 - Production Properties
6c6d89c9-5042-5cf5-b524-12b2a445c6ea | note | Acceptance / Conformance Criteria - The Hi-Lab 40 shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Broken Faces, Aggregate Flakiness Value, and Grading.
9f2b71ae-ddf0-585b-b8f9-fe2266b4c599 | note | Standard / Specification - NZTA B10 - 1.2.2
ed9eea96-099c-5df3-9d7d-0ecaacc5212f | note | Verifying Document - IANZ Lab Reports
e3e420c1-1629-579d-8bad-43bc27cccf78 | note | Frequency - Test for every 1,000 tonnes of material produced
794d144e-57ae-5bb8-af4e-11671c36ea0e | note | Verification Activity: Activity - HP
5efb1a45-87c7-5857-8d93-080151a5e8b9 | note | Verification Activity: By - ENG
a16339bc-4d40-51d0-a3b6-bdb28681a2a4 | signoff | AUTHORITY HOLDPOINT
7b015446-871b-51c4-ab71-fdbfc02a386b | checkpoint | 4.35.05 - Two Broken Faces
78934e21-29f8-50a2-9229-c9f2dd109701 | note | Acceptance / Conformance Criteria - 100% of sample
162d6d00-3610-51a5-80d6-f7208b2450d6 | note | ○ Note: Hi-Lab aggregate produced from a hard rock quarry source using angular and broken feedstock need not be tested for Broken Faces Content which may be assumed to be 100%.
789a114a-8a0a-5898-a18c-f035e8c3b2db | note | Standard / Specification - NZS 4407 Test 3.14
9a25d6f2-093b-588e-bc55-d7fe81c4ef51 | note | Verification Activity: Activity - HP
b702d901-eb43-5398-ab07-348ba9e98f1d | note | Verification Activity: By - ENG
da32049c-13a5-5aea-9e46-d09923ee5705 | signoff | AUTHORITY HOLDPOINT
2840e04b-c728-5bc1-a7f3-60c6155263f0 | checkpoint | 4.35.06 - Clay Index (<0.075mm)
92ef0f64-bf04-5a29-9520-83340e6c1185 | note | Acceptance / Conformance Criteria - 5 maximum
9b1bcfb5-5ebc-5744-ae78-105af122a602 | note | Standard / Specification - NZS 4407 Test 3.5
80d95a66-7945-5501-8ac7-274bfaf77269 | note | Verification Activity: Activity - HP
ccaf2b3a-bf77-5b4f-860b-82da09c77243 | note | Verification Activity: By - ENG
118e8449-e355-5907-a304-76d328e3f6ab | signoff | AUTHORITY HOLDPOINT
cbf8bc81-d5a1-544b-9695-5d072b84818c | checkpoint | 4.35.07 - Plasticity Index
70e86df7-aac1-5eb2-8d1a-b617ea745af1 | note | Acceptance / Conformance Criteria - 8 maximum
d74bcc0c-3115-5d73-9fb9-5441f095a0d8 | note | Standard / Specification - NZS 4407 Test
112bc2a7-797f-57ab-9529-8d8907503710 | note | Verification Activity: Activity - HP
8792631a-df3c-5403-9a56-ee9afc813960 | note | Verification Activity: By - ENG
d771df89-46a7-5ec2-96df-a5134fdb2a29 | signoff | AUTHORITY HOLDPOINT
1187858f-673d-54ac-a76e-242a4fa769a1 | checkpoint | 4.35.08 - Aggregate Particle Size Distribution
4ba80899-0754-5bfe-9070-0277a1f6fdf4 | note | Acceptance / Conformance Criteria - The particle size distribution during production of the blended Hi-Lab products shall comply with the limits in Table 0.4.
bae61c8a-12af-514f-bc7f-f075a217d16e | note | ○ A minimum sample of 90kg of aggregate shall be used for each test.
ffd0812b-f72b-5eff-b866-7d5a91c6e444 | note | Test results shall be evaluated as follows:
0d84a040-cad6-5722-bf3d-46d47820f94b | note | (a) The rolling average results of five consecutive test samples shall be within the upper and lower limits for each test sieve
e7c9b31f-e278-5703-a9f7-00ad24442d5a | note | (b) No individual test result shall be outside the envelope formed by the lower buffer zone and the upper limit.
e87a5e93-67b2-5b7a-afe8-6bd34eb6ea1f | note | ○ Note: Experience has shown that a blending plant with a minimum of three component feed bins is required to produce a consistently compliant Hi-Lab aggregate product.
231d8e7d-a91e-58a1-8759-f2f9ed77b74e | note | – – – – – – – – – – – – – –
f8bca76a-4625-533a-929b-a63617ab0ef0 | note | Table 0.4 Hi-Lab 40 Particle Size Distribution Limits
620be2a0-ea3b-5bfa-90fd-7fc6868640f5 | note | Sieve Size (mm) ¦¦ Lower Buffer / Lower Limit / Upper Limit
63c12376-18bc-59a8-9c13-a599ea41e593 | note | – – – – – – – – – – – – – –
0d3688c8-d7d3-5d2c-ac76-09f512017347 | note | 37.5 ¦¦ - / 90 / 100
d247cd9c-e262-5056-b0c4-9a84dffe87f2 | note | 19.0 ¦¦ 20 / 25 / 35
204bd3d5-e898-5a7b-b9b4-7d26746bfb1a | note | 9.5 ¦¦ 13 / 15 / 20
3d5b6c0a-6762-5eff-aa21-a3feb9a4b25a | note | 4.75 ¦¦ 9 / 10 / 15
469e52d6-6e05-50dc-af7e-384a556d820a | note | 2.36 ¦¦ 6 / 7 / 12
4a98df29-4533-59b3-9ac1-6ffa649759d3 | note | 1.18 ¦¦ 3 / 4 / 10
6aa0013c-8e9d-5283-b261-874c00370f37 | note | 0.075 ¦¦ - / 0 / 6
0b5f775f-d2ed-5efc-9bad-67ef991156b0 | note | – – – – – – – – – – – – – –
f947371e-b5d9-58a5-b580-b4d36153ca96 | note | Standard / Specification - NZS 4407 Test 3.8.2
61e18f16-926c-5163-bc35-a864ba600228 | note | Verification Activity: Activity - HP
21191301-36e0-5d4b-aa1e-b317f31a5c4e | note | Verification Activity: By - ENG
ce962e2b-ebe8-587e-a4a2-160ea9d491ca | signoff | AUTHORITY HOLDPOINT
20322e58-b641-56da-b915-c4e808dc010c | checkpoint | 4.35.09 - Aggregate Flakiness Value
d24614c9-7f1f-55b3-b98b-50154e7e7d25 | note | Acceptance / Conformance Criteria - The percentage of flaky particles for each of the aggregate test fractions coarser than 9.50mm specified by AS 1141.15 Table 1 shall be determined and reported, and the Flakiness Value for each size fraction comply with the minimum requirement of Table 0.5:
5c1d2890-0744-5df1-bb72-0f7ccad0e1c1 | note | – – – – – – – – – – – – – –
3c90b3b8-e55f-583f-af28-f2ba67d460d7 | note | Table 0.5 Aggregate Flakiness Value Requirement for Each Fraction
dc1f88a3-fbe6-54c4-a440-bd7dc9eb58c8 | note | Aggregate Grade ¦¦ Test Method ¦¦ Requirement
252d746d-1187-5715-9462-72b523bf4e00 | note | – – – – – – – – – – – – – –
1df956d7-5403-519c-892d-9954dbebb615 | note | Hi Lab 65 ¦¦ AS 1141.15 ¦¦ < 30%
cbbaf3e3-8c49-5330-89fc-9aa31b1007e0 | note | Hi-Lab 40 ¦¦ AS 1141.15 ¦¦ < 30%
08a339c6-feab-5ccd-9615-d7438c68b166 | note | – – – – – – – – – – – – – –
1e532fb5-9f21-5dbd-a063-39114a4faae7 | note | Standard / Specification - Method of AS 1141.15
9f83959d-65f5-5dde-8717-33f9aeaf4340 | note | Verification Activity: Activity - HP
3c925601-d7a2-50a3-8199-7b514252d66d | note | Verification Activity: By - ENG
ce979df0-31dd-5ab0-b322-74984c97c3f2 | signoff | AUTHORITY HOLDPOINT
c4741654-e2c2-58e5-9d21-98ad26ac307b | section | 4.36 Hi-Lab General Material (Pavement Type A,B)
3785bf16-ad90-5eee-b6f5-dc77d4773dc0 | checkpoint | 4.36.01 - Portland Cement Stabilising Agent
7fb295e3-3df9-59ee-9450-713bfc3e083c | note | Acceptance / Conformance Criteria - Cement shall comply with NZS 3122 Specification for Portland and blended cements (general and special purpose) for GP, GB, LH
6e86a9ce-bbf8-5e1a-9651-71401d9afa48 | note | ○ General purpose Portland cement, type GP, shall be used unless otherwise specified in the Contract Documents. Note that high-early strength cement, type HE, shall not be used as a stabilising agent.
4d699c98-37e9-5edf-8ca8-fb8ef5354a9f | note | Standard / Specification - NZTA B10 - 2.4.1
d181529d-b765-5bf1-bef5-ad2441ce3ebf | note | Verifying Document - Datasheet
07c5f21e-3d2d-5df3-b14b-04b4e06f3c40 | note | Frequency - Prior to Use
f146592f-95f0-5507-9772-f76a408cd943 | note | Verification Activity: Activity - R
c2267889-b709-578e-8776-91e927bbb1ce | note | Verification Activity: By - SE
c1b7ac1d-1776-50c9-bde2-bed2b9423232 | checkpoint | 4.36.02 - Water Supply
8a6b5489-236e-5f0e-b9a9-f68227a690cd | note | Acceptance / Conformance Criteria - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening or strength of the stabilised material. Water from sources other than public supply shall have its suitability established to the satisfaction of the Engineer.
d09e06bf-566f-5003-a256-0b3000a82811 | note | Standard / Specification - NZTA B10 - 2.4.2
c4914dfd-f1b4-50fe-8e8c-6332711fc0c0 | note | Verifying Document - Site Records
ff0cd093-f144-5433-afcf-b3949f8487e7 | note | Frequency - Prior to Use
731bf96c-e09e-52c9-ba39-f30636c7eba0 | note | Verification Activity: Activity - R
b42a6b4a-8c3a-5b41-8227-56e19f43fa1a | note | Verification Activity: By - SE
45233c43-9bac-5fb3-b4ab-289322865089 | checkpoint | 4.36.03 - PAP 7 - Choking Aggregate
2cc60763-4871-5da9-b95c-2197e19b9fd5 | note | Acceptance / Conformance Criteria - PAP 7 crusher dust choking aggregate can be a by-product of the Hi-Lab crushing or sealing chip production with all passing the 9.5mm sieve. The aggregate source properties (crushing resistance and quality of fines) shall be equal to or better than the required source properties for Hi-Lab aggregate.
96706da2-d8ee-5caa-af05-f159ff52fa5d | note | Standard / Specification - NZTA B10 - 2.3.6
e36a662a-9d3e-52a3-ad71-f967afc5e9ea | note | Verifying Document - IANZ Lab Reports
55aa7ec3-0500-58c4-846b-6394b17cde2f | note | Frequency - Test for every 1,000 tonnes of material produced
89ab4c54-85bb-565f-ab4c-7f921c856b69 | note | Verification Activity: Activity - R
e885f0a1-181c-56e2-869b-c2f7c9c241d3 | note | Verification Activity: By - SE
5c06996c-2bca-59b6-9169-db0320db268e | section | 13.01 Triaxial Geogrid
99b55b72-d146-5ae8-b0fc-f76fd148b574 | checkpoint | 13.01.01 - Triaxial Geogrid storage and Inspection
2a40a7fa-9e4b-5af6-b3c7-6cf871959d37 | note | Acceptance / Conformance Criteria - The geogrid is to be checked once delivered to site to confirm there is no damage that may effect its performance. The material shall be stored out of direct sunlight to ensure no degradation of the material occurs prior to installation.
5b77095f-5a1a-5692-be19-1e5859b50382 | note | Standard / Specification - PS 20.3.1
3150ef1b-d6d3-5c12-bef8-14d3d53cf4ec | note | Verifying Document - Site Records
64b4a64a-3011-5e5b-8c04-7c06fe6e57e5 | note | Frequency - Prior to use
89bad5ec-8b42-55b5-94c0-43254989aae7 | note | Verification Activity: Activity - R
dcb28c5f-75dc-5d2a-a7ec-fc91ff1784f3 | note | Verification Activity: By - PE
8d8dfff0-e687-5803-92af-8df0ca82d843 | checkpoint | 13.01.02 - Triaxial Geogrid Installation
532699d7-1e20-571d-a8d0-ef2366908118 | note | Acceptance / Conformance Criteria - The triaxial grid is to be installed in accordance with the manufacturer’s specification. Where overlaps are required they shall confirm with the manufacturers installation specification.
a7ed573b-5ce5-50b4-bd4e-1c6408dbb4e0 | note | Standard / Specification - PS 20.3.1
7df1f161-53c3-569f-bf71-29d36755b11b | note | Verifying Document - Site Records
9b4fa08a-e3d6-5c0a-8066-2c3a010f89cc | note | Frequency - During Installation
5178bba6-77fc-5e76-b1e8-b91904e7e30f | note | Verification Activity: Activity - R
7dac2049-9269-546a-ad82-bdffd4f04dc1 | note | Verification Activity: By - PE
80572c52-4639-5317-a3b8-448a7a44836e | section | 13.02 AP65 Subgrade Improvement Layer Pavement Type A,B,C
34462ba7-0596-5d92-aa44-3f4c0644d233 | checkpoint | 13.02.01 - Material Placement
fc8c6152-eda4-523f-9324-83496424e477 | note | Acceptance / Conformance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout
96210c87-8e61-5e22-a937-d23684241da9 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 5.1
211049dc-0791-5f9f-a233-0861eefb3563 | note | Verifying Document - Survey / Level Checks
e71da70a-cc98-58e7-9465-2ddb55a71cc4 | note | Frequency - Continuous monitoring.
d2c8e17f-c308-5854-aeea-d62d6163ca80 | note | Verification Activity: Activity - I
c8cd5851-2c12-5b4e-b06c-1030b19783f3 | note | Verification Activity: By - SV / PE
c086377c-d141-5896-83ea-ffd0f27d9116 | checkpoint | 13.02.02 - Plateau Density Tests
dd06a1ed-6b6f-5ef8-8436-8f2afa75f436 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC.
f7c22317-b7b3-5efb-b221-8935a8b9f2ef | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
0b0f5550-82f7-58c5-b283-1cd3d19e9bd3 | note | Verifying Document - MDD and Plateau Reports
041e25d1-7f94-5183-a078-0f132a40cf3f | note | Frequency - 1 test per 5,000m2
b62f8411-b629-5768-a54e-faf9c3bf3337 | note | Verification Activity: Activity - HP
a7c0b97d-e179-506d-b47e-df5851ef35ba | note | Verification Activity: By - ENG
6c3d2e59-f982-5043-85a7-0aa2242113a2 | signoff | AUTHORITY HOLDPOINT
2eecc68a-d5d8-574a-a2f9-42b62be6259d | checkpoint | 13.02.03 - SIL Pavement Layer Compaction
4c07fcd9-9d14-5850-9797-61f11dd13c9f | note | Acceptance / Conformance Criteria - The compaction density for the lower layers must be at least 81% of aggregate Solid Density. The nuclear gauge in direct transmission is used for reporting in-situ density.
4148dd47-3096-54a4-8679-7a5728209697 | note | Standard / Specification - NZTA B10 Notes
983eb9bb-6f16-57d1-a788-92d9e0ede9ae | note | Verifying Document - NDM Report
a2322d7d-2154-54a7-a8b4-e2bddedd1168 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
b4226c90-d64a-50a4-ba70-2a2f3e499343 | note | Verification Activity: Activity - HP
367df162-16d4-58a7-8a26-f6351cb1b9fc | note | Verification Activity: By - ENG
5d2a9c4f-9fb9-5fe3-878d-95a7bdaf77d8 | signoff | AUTHORITY HOLDPOINT
66c2b306-e56b-52a2-92a0-2f3a73a7833b | checkpoint | 13.02.04 - SIL Layer thickness.
087f7d91-b6d9-5903-bc12-1b48121ba685 | note | Acceptance / Conformance Criteria - The SIL layer shall be monitored for Layer thickness.
b57923b6-5232-500e-85e5-568eac72e8a6 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
e2d450b6-d393-5b02-9600-105188d1f346 | note | Verifying Document - Survey / Level Checks
5e3ac5b4-3f46-5f83-b579-9b6b2e1de2d2 | note | Frequency - 1 test per 20m
672feb15-f760-5db8-b6a6-df8e3c60a7a3 | note | Verification Activity: Activity - W
9c3853f0-e8e7-50b3-9a75-707bba2b43c1 | note | Verification Activity: By - SV / PE
793a5b8f-1431-5d59-b0d5-57842aca4233 | checkpoint | 13.02.05 - Surface Shape
9c5d49b3-5230-5a50-9d04-25ab9bea8580 | note | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.
3a346d62-a22c-5ad6-b5c2-2432cff2b6f2 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
1bdef458-ef09-5dff-99f0-c62ccb4d5b36 | note | Verifying Document - Survey / Straight edge Report
a5b6da0c-fcfd-5a0f-af17-3c8f1da50974 | note | Frequency - Prior to sealing
1bdc6c6a-8005-56f8-9dec-245eb3e1106b | note | Verification Activity: Activity - I
6f71188a-6187-5a0a-be74-3646d7c7bf92 | note | Verification Activity: By - SV / PE
e3a25849-16b3-5921-a3ae-953690edba8a | checkpoint | 13.02.06 - Holding Water
dfd94a39-bbf3-5fc6-ae13-ec99e2867c9d | note | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
087ffc63-7714-514a-a2c1-27b226dff49f | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
3e0fa93e-c419-5791-b9e2-c7749127004a | note | Verifying Document - Survey
746d53d2-aabc-5016-82cf-5650cb58db6e | note | Frequency - Prior to sealing
7bdc5261-fd20-5e82-a84c-6f4a9ae2c64f | note | Verification Activity: Activity - I
8ee59d7c-b134-5caf-b81e-857f1beb55f5 | note | Verification Activity: By - SV / PE
ae8a2da6-e5fd-5e94-827d-5579c23340f6 | checkpoint | 13.02.07 - Proof Rolling
5c9bb22f-5bd6-50ef-86d5-8df0aad2cfe9 | note | Acceptance / Conformance Criteria - SIL layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass.
4d894cdd-d773-57bf-b27b-f3c79e08d0c8 | note | Standard / Specification - PS 20.5.2.2
4d4f34f0-77bd-5b4e-9982-84b073fc0a20 | note | Verifying Document - Site Records
27f2e544-86b0-5d7d-8c40-ea9e15e51e83 | note | Frequency - Before proceeding with works
19e901ca-07b2-5f09-979b-ebf07ce37254 | note | Verification Activity: Activity - HP
26dc879b-4c6d-532f-b6d2-8fd6c1b18e5d | note | Verification Activity: By - ENG
9d203b5d-2a33-519b-a6fd-88f1e7ac7540 | signoff | AUTHORITY HOLDPOINT
c6646e17-3b34-5db0-a14d-c6780c356c80 | checkpoint | 13.02.08 - Benkelman Beam
2cafbb2f-4cc4-50cd-a3a7-3bc5100e25f2 | note | Acceptance / Conformance Criteria - be ˂ 1.5mm (95th%) and max ≤1.8mm
d230af26-b96c-5216-943b-0142edfd41c2 | note | Standard / Specification - B10 Notes
ae25dbd5-8712-531f-94e9-cf3cf4b3a818 | note | Verifying Document - Report
324321a1-310d-55e0-86d6-b7e5cb7f24b7 | note | Frequency - All Lanes
680aeb07-ff74-5add-a8c7-453dd64910ec | note | Verification Activity: Activity - R
97bc2e9d-3dac-53e1-b515-16b6da39525f | note | Verification Activity: By - SE
32bd79f6-98db-5025-bd0d-dbc869fd9c5d | section | 13.04 Hi-Lab Plant and Staff
21d614b8-ae0e-5bea-bbb6-6ccdc98559ee | checkpoint | 13.04.01 - Plant for Supply of Cement
24e3d3be-7478-5011-ba84-ca802099228e | note | Acceptance / Conformance Criteria - For areas greater than 500m², cement shall be delivered to the site in purpose built bulk tankers unless otherwise approved by the Engineer. Each bulk tanker shall be issued a Certificate of Loading that contains the following information which shall form part of the project quality plan.
a235460e-ca55-5cc4-bb5e-16e26b0eb897 | note | Standard / Specification - NZTA B10 - 3.1
2f018d2c-6c20-5907-857b-35432144a779 | note | Verifying Document - Certificate of Loading
dd155f5f-35a7-575b-af82-82ff71f83cbd | note | Frequency - Each Tanker For areas greater than 500m²
6ae35c52-3377-5be2-8ccd-02a3625c01bb | note | Verification Activity: Activity - R
e9fb2f25-4441-5fa0-8f35-07f86a7cbb87 | note | Verification Activity: By - SE
904cfb36-9b72-5214-88e7-5984f5bbc3ed | checkpoint | 13.04.02 - Plant for Spreading Chemical Stabilising Agents
b3e23823-338f-5caf-b31d-a9d59553f11c | note | Acceptance / Conformance Criteria - The spreading equipment shall be capable of varying the spread width to cater for different road widths. The spread rate should be consistent along the spread width of the equipment.
3a2b4638-4afe-57be-b052-e4cd4ad322ee | note | Standard / Specification - NZTA B10 - 3.2
5965a3a8-7e83-5f43-a039-39dac2ad479f | note | Verifying Document - Methodology
e9a90c6f-ef07-5bb0-9ea9-1726a3b20486 | note | Frequency - Prior to Works
e3aae3ec-8a1f-5d38-bbf8-f2c60a38c0cc | note | Verification Activity: Activity - R
398dd3b8-1f3e-5f21-b80c-5d4a09cea84a | note | Verification Activity: By - SE
2c51062a-faa0-56c2-abd3-673b934077a0 | checkpoint | 13.04.03 - Plant for Stabilisation Process
b57a4edb-5fde-5161-bb25-7119a1bfe6fb | note | Acceptance / Conformance Criteria - The plant used for the mixing shall be a purpose-built recycling machine. It shall be from a reputable manufacturer having a demonstrable track record and manufacturing history for the equipment used.
4fe14af7-72a3-5fe1-9e31-73b4391aa235 | note | Standard / Specification - NZTA B10 - 3.3
4dc51588-1867-5153-b80f-38c8762bbf2a | note | Verifying Document - Methodology
28ca5d97-85fb-5f93-8887-985e98c90427 | note | Frequency - Prior to Works
993cbcae-9079-51e1-9bbc-590c8c9a8ea8 | note | Verification Activity: Activity - R
22527279-2bfe-5a26-ad69-b0957863fb1b | note | Verification Activity: By - SE
efc111f7-b676-5e52-a35f-cb1de6c8f7cb | checkpoint | 13.04.04 - Primary Compaction Equipment
ab81185e-1ed8-52d7-9ef1-a598765a7187 | note | Acceptance / Conformance Criteria - A steel drum roller (i.e. having a smooth drum) is required for the initial placement of aggregate. The roller shall have a gross weight of at least 12 tonnes. For primary compaction, the Contractor shall use GPS control to ensure all areas of the pavement receive the required number of passes with each type of roller.
6d0ae59f-12ed-5b9b-b32f-c1e9d99c274a | note | Standard / Specification - NZTA B10 - 3.4
6f9db75d-51bf-580f-88a0-22e454c017ab | note | Verifying Document - Methodology
46d0634c-4b39-5ae7-acc9-ba0605100e7f | note | Frequency - Prior to Works
ad0b862b-ec7d-5498-848c-b58b2986d26d | note | Verification Activity: Activity - R
dd61da39-ef9a-5a08-9581-78a0911cfa6a | note | Verification Activity: By - SE
5fef0619-d2ca-5729-b448-ab9ec6eb184f | checkpoint | 13.04.05 - Personnel Training and Experience
186c7c44-9173-5426-9842-908b1742f71e | note | Acceptance / Conformance Criteria - The Contractor shall submit a list of such personnel to the Engineer for approval. Where approved personnel are not available the Contractor shall cease operations.
3b984d17-e5a6-55e2-b0a2-6d8a3a614a56 | note | Standard / Specification - NZTA B10 - 4.2
af5b84d5-0609-59ba-95a1-5ebc3532e8a7 | note | Verifying Document - Methodology
4458fa3f-42d8-5c06-aac4-5a1aa9f59e03 | note | Frequency - Prior to Works
7beaf81b-655f-51e4-a09d-268cf677514c | note | Verification Activity: Activity - HP
061da9a4-9af8-5e77-9027-597c3243ec1a | note | Verification Activity: By - ENG
1ec346a4-5991-5ee9-a97c-cd1c95e68e51 | signoff | AUTHORITY HOLDPOINT
6a6fd14f-b31e-57ab-8db5-2ef2b7dcc479 | section | 13.05 Hi-Lab Pavement Trial
614077d6-2d9e-5e0f-b4ed-962af8821086 | checkpoint | 13.05.01 - Pavement Trial
f18578e2-ca42-517f-bf52-cb13bd81faf7 | note | Acceptance / Conformance Criteria - The Constructor shall construct a pavement test trial of Hi-Lab sub-base and basecourse pavement to verify design assumptions, material properties and construction methodology. The trial shall be undertaken in the presence of the Designer using the construction procedures, equipment and operating personnel proposed for the work in the placing, stabilising, compaction and finishing of the individual layers.
0db23b87-004a-5eea-95eb-d072a8fa7bef | note | Standard / Specification - NZTA B10 - 5
7199bd2a-91a0-55d3-82d2-3af3e3c48a11 | note | Verifying Document - Conforming Trail and Test Results
8d452b65-4c0c-57c7-bb17-7fb7599f9320 | note | Frequency - Prior to Hi-Lab Construction
46d04ae1-28a4-5c2e-9380-0609e903a0a5 | note | Verification Activity: Activity - HP
3481f70c-797a-546d-89d8-05973023718d | note | Verification Activity: By - ENG
fa28a3d8-05b8-577b-b0fc-772edfdddc32 | signoff | AUTHORITY HOLDPOINT
4967a333-afa6-5e74-8cec-18a3e873810e | section | 13.06 Hi-Lab Construction
2f7a441c-0118-5c13-919c-0e919b8601ec | checkpoint | 13.06.01 - Production Quality Plan
86b030d2-f3d3-5848-a913-59a471565921 | note | Acceptance / Conformance Criteria - The Contractor shall prepare a Production Plan for approval by the Engineer prior to commencement of delivery of Hi-Lab aggregate to site, detailing all aspects of its Hi-Lab production process, how it will achieve compliance with this specification, and procedures in the event of non-compliance or plant breakdown. The Production Plan shall include the Contractor’s detailed methodology.
ae1f3190-1a4a-54d4-ae8b-6c33120ed139 | note | Standard / Specification - NZTA B10 - 4.1
385d2db3-72ac-5b36-9282-fa3a2f98de83 | note | Verifying Document - Production Plan
808c412c-bba9-5d8f-a249-6b280a55dd65 | note | Frequency - Prior to commencement
8497d4f6-a542-5580-ae52-ea58c6fd7543 | note | Verification Activity: Activity - HP
d8b6ff90-4ee1-56de-a5ee-854ed9e33794 | note | Verification Activity: By - ENG
e7f3690a-12eb-5c38-9ad7-675143e0f2e8 | signoff | AUTHORITY HOLDPOINT
241989c9-bd98-52d4-90c0-a05be274c20c | checkpoint | 13.06.02 - Daily production sketches
8e470100-5b0f-5d29-9330-b1bafaf23af2 | note | Acceptance / Conformance Criteria - Daily production sketches shall also be produced for approval by the Engineer ahead of each forthcomingday’s work.
cc61807e-2745-5892-b4d1-2e6e352b48ad | note | Standard / Specification - NZTA B10 - 4.1
2721081c-173a-5143-909a-d446d68438a3 | note | Verifying Document - Production sketches
5718a267-8d96-5d6c-ba3e-a979f68dc636 | note | Frequency - Daily Prior to commencement of days work
1c78a660-d1f6-5139-87be-b017ee4498c1 | note | Verification Activity: Activity - HP
464d98ff-e908-5837-a7ff-f6412af6bad2 | note | Verification Activity: By - ENG
7a8832cc-acaf-5453-b024-a92e84e3b62f | signoff | AUTHORITY HOLDPOINT
697c85b5-705b-5096-bb3e-4cb741e0b5b7 | checkpoint | 13.06.03 - Initial placement of aggregate
9dc15d31-0a3d-5842-9d33-cb11429865f1 | note | Acceptance / Conformance Criteria - The Contractor is responsible for ensuring the surface level after spreading and compaction prior to stabilisation will result in final layer thickness and finished levels after stabilisation that are within the required tolerances.
57dc6f50-14d1-556a-829c-9bcdf429e682 | note | Standard / Specification - NZTA B10 - 4.3.2
6d139095-6478-509c-b8dc-5fcb2a762504 | note | Verifying Document - Survey Records
f213faf3-dcc0-5cb0-a392-fdd8b0f6d09b | note | Frequency - prior to stabilisation
5fad6d3a-a071-50fb-9b4e-4f080a20a4b0 | note | Verification Activity: Activity - I
85de7e2a-a9d1-5039-83f9-abd6640a9a8f | note | Verification Activity: By - SV
03a3c627-80e9-50dd-b363-057f624a1faf | checkpoint | 13.06.04 - Cement Mat Test
5b969248-2205-5e18-bca8-de84f9a486f8 | note | Acceptance / Conformance Criteria - The cement spread rate shall be measued by a 1m² canvas Mat Test every 250m2 and be Within ±0.5kg/m² of the specified rate.
3246ed67-2868-5e2c-b00c-ff1896e0ff38 | note | Standard / Specification - NZTA B10 - 4.4.1
18ca35b5-a505-5b10-95ef-c8eb8ca9f9e6 | note | Verifying Document - Test Results
64b18861-0310-56d3-aee7-a74d6c8c2ce3 | note | Frequency - Every 250m²
f735f047-094e-5f3b-8292-668474ae0404 | note | Verification Activity: Activity - I
12a44547-8b26-5cdb-9291-41f58470e340 | note | Verification Activity: By - SE
dab7d40a-bbe0-56ad-8ec0-37522cd9b398 | checkpoint | 13.06.05 - Cement Average usage test
6c0e57ae-2e02-52bc-af9c-3390442d6fce | note | Acceptance / Conformance Criteria - The Average usage of cement spread rate shall be measued by comparing tonnes used (from delivery docket) with measured area and be Within ±2.5% of the specified rate.
2f388278-08ab-5248-8de6-4232d809b3fc | note | Standard / Specification - NZTA B10 - 4.4.1
d6f837b4-6bcf-5d23-8f63-259c31ffd1a7 | note | Verifying Document - Test Results
bc6240b6-b7fd-5215-971b-025fe87c4bf2 | note | Frequency - Upon emptying the spreader and bulk tanker
a73b86e5-b007-54ba-a4c3-60f568e3fb62 | note | Verification Activity: Activity - I
10e21e5c-5d43-56a3-b9b5-517c4ee44bd2 | note | Verification Activity: By - SE
8513219b-8a79-545a-bf0d-5b9039345c37 | checkpoint | 13.06.06 - Weather limitations
eedcf99a-d78a-5272-afac-aa5bd56985f6 | note | Acceptance / Conformance Criteria - Spreading of cement on the road ahead of stabilisation shall not continue when the cement becomes a dust problem due to dryness or when the wind speed exceeds 25km/hr. No spreading of cement shall commence if it is raining. If rain is likely to start before the cement can be mixed into the aggregate, then spreading shall not take place.
4fbf2fe6-040e-5991-a476-187517cbfd78 | note | Standard / Specification - NZTA B10 - 4.4.2
2e6669d0-72ad-5600-9e34-0230fd5a10f3 | note | Verifying Document - Site Records
932cf954-be51-54a1-bbc6-d87ab76cc66e | note | Frequency - Duing stabilisation
f9511c68-0270-5b25-8b2e-df612a76d50e | note | Verification Activity: Activity - R
1758be89-1bfa-50c6-86d8-0c40d417e03d | note | Verification Activity: By - SE
3389e69d-d29b-5b48-a884-62ac8400c9eb | checkpoint | 13.06.07 - Time limitations
2c037fa2-bc1c-5675-a16d-f61d045b35bc | note | Acceptance / Conformance Criteria - The maximum time period, from mixing of the materials to completion of primary compaction, shall be 2.0 hours. Unless specifically justified in the approved Production Plan, stabilisation shall commence no later than 10:00 am and the area to be stabilized shall not exceed 4,000m² per day, unless agreed otherwise by the Engineer, to ensure sufficient time to complete the full stabilisation process.
af6447fb-79c5-551d-a0b6-e5ad5eb6884a | note | Standard / Specification - NZTA B10 - 4.4.3
3dab9dcf-5781-58bf-8c52-93ca0a8a7720 | note | Verifying Document - Site Records
e5948c30-73fe-508f-8efd-100a1d5227fd | note | Frequency - Duing stabilisation
64b7c279-30f8-5e7c-b63d-4aae2a3bd4ca | note | Verification Activity: Activity - R
c4dc552c-2aa4-560e-8617-1408da46f1f0 | note | Verification Activity: By - SE
2b3dda1e-0034-524f-8b33-a879d7175a27 | checkpoint | 13.06.08 - Stabilisation/Addition of Water
72f7007c-4083-504a-b5a9-aa62a9b81549 | note | Acceptance / Conformance Criteria - The Contractor shall continuously monitor the moisture content of the material behind the recycler and in consultation with the Engineer adjust the rate of water injection as necessary. The Contractor shall also monitor continuously for blocked nozzles or any other risk to the consistency of the mixture. The stabilisation area shall not exceed 4000m2 per day, with a maximum single stabilisation run length of 225m, unless agreed otherwise by the Engineer.
b3bdfeaa-28bd-5b06-a6e6-2722ad38cf27 | note | Standard / Specification - NZTA B10 - 4.5.1
aa0e029e-7c79-5f1d-b796-24e9573302b7 | note | Verifying Document - Site Records
2069b1f7-9d3e-5c58-b90c-aa3d05cce589 | note | Frequency - Duing stabilisation
04b1aba2-7b01-5af6-a4d2-54226296a663 | note | Verification Activity: Activity - R
d0c15c66-865e-5f3a-854d-c0cf38278779 | note | Verification Activity: By - SE
97c51ad4-59cd-5a8e-b7c6-ec5beb678474 | checkpoint | 13.06.09 - Control of mixing depth
0182877b-f767-5474-bf15-6b24811781c0 | note | Acceptance / Conformance Criteria - The Contractor shall determine the mixing depth so that the final stabilised layer thickness after compaction meets the contract requirements. During stabilisation the depth of the cut shall be physically measured at both ends of the mixing drum at least once every 50m. The measured stabilisation depth shall confirm full mixture of the placed Hi-Lab layer at full depth with no untreated materials present at the bottom of the test hole.
6b7ac677-9d3d-51d3-8a82-c5dd149a78fe | note | ○ The maximum allowable variation from the specified depth of cut is –5mm and +15mm.
39845bd8-8687-51a8-8e31-17767d6c7ac8 | note | Standard / Specification - NZTA B10 - 4.5.2
51160cb4-a812-5228-8b71-efff625a5c8f | note | Verifying Document - Survey Records
384670aa-7b6b-5719-a767-ffa4e2233d13 | note | Frequency - Duing stabilisation
d34549ee-11dc-50ad-aa8b-b1b11c15c1f7 | note | Verification Activity: Activity - I
5d710c89-9c24-5e18-ae7a-46094c491148 | note | Verification Activity: By - SV
d8d44e3f-90cc-5f13-a9de-5a6001544f66 | checkpoint | 13.06.10 - Overlap on longitudinal joints
b8670b08-7e11-5bff-a9b3-93081bbc8751 | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 100mm or half the layer thickness, whichever is greater. Overlap width shall be increased if any dry material is noticed between runs. The locations of longitudinal joints shall be agreed between the Contractor and Engineer and recorded in the production plan.
b6c35cfe-7444-5763-b6db-ca6b6342b50f | note | Standard / Specification - NZTA B10 - 4.5.3
1a4a3feb-bc96-53ba-a1a1-8740063d4c96 | note | Verifying Document - Production Plan
230065d6-4f13-5678-9ec1-bca9711d9ffc | note | Frequency - Duing stabilisation
a42e9a61-e52b-5776-af06-5ab8a3749c72 | note | Verification Activity: Activity - I
58fef054-8384-5ad2-b682-58c2e080bcc1 | note | Verification Activity: By - SE
45743f7b-9ced-573e-ad47-b6b8a96da711 | checkpoint | 13.06.11 - Continuity of stabilised layer
6d19c89c-8401-5448-b39e-241db04c516f | note | Acceptance / Conformance Criteria - The exact location of the end of the cut shall be carefully marked. This mark shall coincide with the position of the centre of the mixing drum at the point at which the supply of cement ceased. To ensure continuity of the stabilised layer, the next successive cut shall be started 3m behind this mark. This tie-in length shall be reduced to 1m for stabilised layers older than 7 days. Cement shall be spread on the overlap for the next run.
492931fe-93fc-524b-bacf-a6f5aab5528b | note | Standard / Specification - NZTA B10 - 4.5.4
e686bf8b-d0f4-5341-a379-2ca01a8957fa | note | Verifying Document - Daily Production Drawings.
d0d41a51-22a6-5661-8a1d-c8a9ef6109ce | note | Frequency - Duing stabilisation
da12d516-a1c7-5fae-9b71-7606c619ee9a | note | Verification Activity: Activity - R
750f1c4c-4598-5acf-b711-9610acda47ee | note | Verification Activity: By - SE
d4f61fb8-d23f-5bf1-af02-b5ff76b715eb | checkpoint | 13.06.12 - Daily production sketches
7d8a8f9d-6686-5a1a-a11e-bdcf50d00f75 | note | Acceptance / Conformance Criteria - The Contractor shall sample the material behind the stabiliser for particle size distribution analysis using the specified method below and advise the Engineer of the result as soon as practicable. The sample frequency shall be a minimum of 5 samples per 4000m2. The samples shall be representative of the full stabilised area.
380bf4eb-7227-5bb1-b080-d9ad9cbd50fc | note | Standard / Specification - NZTA B10 - 4.5.5
1fdf2c17-24ac-5421-82a0-993f0519f7ca | note | Verifying Document - Test Results
c74a8e76-d885-512c-8cbc-ed54264e05b7 | note | Frequency - A minimum of 5 samples per 4000m2
31e36b17-6b65-51be-b165-8ac0ad9de065 | note | Verification Activity: Activity - R
02e08e03-81cd-5f3d-be08-16a23989a13c | note | Verification Activity: By - SE
24997435-e1c0-5242-9839-3ba46fa256ea | checkpoint | 13.06.13 - Primary Compaction
773c8651-dd2b-5966-aa99-44684f3d5fd7 | note | Acceptance / Conformance Criteria - Primary compaction shall be monitored for conformance to the methodology
2eded30a-7c88-5b08-bf26-6312bfb67c4a | note | Standard / Specification - NZTA B10 - 4.6.1
df8c0ae8-e819-53fe-a983-00566bf1170d | note | Verifying Document - Site Records
1167cebb-6b67-5aed-a469-080b9358e811 | note | Frequency - Duing Compaction
024a30ca-6f81-5a61-b18f-1e3e633cfb78 | note | Verification Activity: Activity - R
eb59c807-eaaf-582c-9717-3bf9960097f5 | note | Verification Activity: By - SE
8c391b9e-98a3-5c00-becd-b32057c8a1b9 | checkpoint | 13.06.14 - Secondary Compaction and Choking
f032f338-9e23-58d1-a1fd-1dcb4a21c82f | note | Acceptance / Conformance Criteria - Secondary Compaction and Choking shall be monitored for conformance to the methodology
1c7bc7c4-d956-5b4f-bcee-42f6a7f490fc | note | Standard / Specification - NZTA B10 - 4.6.2
e359e8e0-4278-5904-9fcb-4f2470aaef4e | note | Verifying Document - Site Records
1824b90a-21b5-563c-b48c-29b7c76abe26 | note | Frequency - Duing stabilisation
28061884-79aa-5f35-ba19-29a30ddad521 | note | Verification Activity: Activity - R
d3ee1272-b707-533d-970a-aed3425d781e | note | Verification Activity: By - SE
218712d4-3a1a-5157-9683-e8c3a9f94208 | checkpoint | 13.06.15 - Surface prior to placing next Hi-Lab layer and/or sealing
9c02a491-c3f3-5d2a-ad65-6a881732c64d | note | Acceptance / Conformance Criteria - Fines shall be removed and broomed to produce a mosaic surface prior to placing the next Hi-Lab layer or sealing. The surface shall not have any loose fines and/or “caked” laminations of fines, and shall be a mosaic stone surface free of fines.
3774388a-4347-5e65-a526-49eb2c932661 | note | Standard / Specification - NZTA B10 - 4.6.3
70da0bb4-dae3-5b6d-b928-08f231eca027 | note | Verifying Document - Site Records
9f2229d1-298f-5cfa-9c79-4a1d53914799 | note | Frequency - Prior to placing next Hi-Lab layer and/or sealing
2db7b3b9-9365-5f07-8765-50d5fe4c9cda | note | Verification Activity: Activity - R
74253199-2ddc-5133-a095-c1a601223c91 | note | Verification Activity: By - SE
268cbc70-6685-5d3f-8850-94a9ad3c98fd | checkpoint | 13.06.16 - Surface shape
13f396ed-7194-51a8-8647-9559cfb46fa3 | note | Acceptance / Conformance Criteria - The surface shape of the completed pavement layer shall be such that, when all loose aggregate is removed, it conforms to the shape specified within the tolerances in Table 4.3.
e4c4e909-726e-5f59-9eea-7c44448e87d8 | note | Standard / Specification - NZTA B10 - 4.6.4
41d4e912-7daf-53f3-a68f-9fc4afd807d8 | note | Verifying Document - Survey Records
92503338-69c8-5134-ad23-bd36e13b497d | note | Frequency - Each Layer (Subbase / Basecourse)
06fa73bf-c233-539e-965f-4b7bd98403db | note | Verification Activity: Activity - I
58a9463a-5a06-5eb9-b447-07d0a404d607 | note | Verification Activity: By - SV
6e12d4f7-3bc6-5f43-b2d3-aad17cbcb157 | checkpoint | 13.06.17 - Crossfall
38d0541f-7c1b-5fb8-9082-0b45d0aaa044 | note | Acceptance / Conformance Criteria - The crossfall between two points more than 2.0m apart, transverse to the centreline, shall not depart from the design crossfall by more than 0.5%.
fff8ab4e-ca89-53ef-86e6-5099dbb2b579 | note | Standard / Specification - NZTA B10 - 4.6.5
fc0602ea-060f-5b20-9abe-11d72011307d | note | Verifying Document - Survey Records
b6111b94-a098-54fd-8212-57fb9bcfcad7 | note | Frequency - Each Layer (Subbase / Basecourse)
c76df370-41b4-5f9c-a31c-11f04cf8832b | note | Verification Activity: Activity - I
1daa56b3-14c2-5604-b41d-e7710432f69d | note | Verification Activity: By - SV
a71ee757-04be-514b-9de2-d912dbfdac56 | checkpoint | 13.06.18 - Hi-Lab Protection
1e5f92cb-7379-5d75-a06c-f8bd499420b8 | note | Acceptance / Conformance Criteria - No construction equipment shall be driven on any Hi-Lab aggregate layers until at least 48 hours have passed following completion of secondary compaction. At no time during the construction of the Hi-Lab pavement layers shall any haulage of earthworks and/or drainage construction activities e.g. excavators be allowed, only construction activities directly associated with the construction of the Hi-Lab layers, e.g. placement of aggregate.
964ee244-c790-5dcb-8cc2-7475451017fa | note | Standard / Specification - NZTA B10 - 4.6.6
01dd290d-7616-5be8-bde8-cab8036a2e0e | note | Verifying Document - Site Records
63fcee61-968d-5ff2-b48f-ee3803b3de61 | note | Frequency - at least 48 hours have passed following completion of secondary compaction
09b20b43-7719-556e-8e19-59f86a750511 | note | Verification Activity: Activity - R
e90867d6-9b6d-5452-a960-2adae3f8c3da | note | Verification Activity: By - SE
f611315c-1219-5e61-84d1-246db55a1ae1 | checkpoint | 13.06.19 - Hi-Lab Maintenance
4a0a791f-9dab-5d41-9679-16adf6fb768f | note | Acceptance / Conformance Criteria - For a minimum of 48 hours after stabilisation the Contractor shall
dd52b1bc-5d22-5057-93c4-7d38836406c3 | note | (a) provide additional PAP7 running course, if required (using clause 10 of NZTA B02 as a guide)
e3e19220-a4a5-5523-9846-aa69aee4ad3f | note | (b) keep the surface damp but not wet to prevent drying and ravelling
1e2ec47a-56a7-5781-a652-fc1300632534 | note | (c) drag-broom the whole surface, keeping a balanced distribution of PAP7.
ffab20db-9797-56ef-8782-133bc25da673 | note | Standard / Specification - NZTA B10 - 4.6.6
d2e6a1cf-27d6-59cb-b084-4ed5675a8705 | note | Verifying Document - Site Records
f82a3605-a66c-50d3-9ccf-d198b04c09c3 | note | Frequency - at least 48 hours have passed following completion of secondary compaction
e2c499b3-e233-5fce-b0cb-3760550c18b1 | note | Verification Activity: Activity - R
ee2f3536-485f-56a2-9c32-77a16ca08de1 | note | Verification Activity: By - SE
3c8ac544-6888-5930-bcae-e157c38465c9 | checkpoint | 13.06.20 - Compaction Testing - Subbase and Basecourse - Moisture Corrected - Direct Transmission against Solid Density
af098043-71ab-5ee4-b35e-d68931de7b80 | note | Acceptance / Conformance Criteria - The degree of compaction for the Hi-Lab layer shall be determined by direct transmission, a hole shall be drilled to accommodate the probe to the full depth of the Hi-Lab layer and/or layers. The probe shall be set at increasing increments of 50mm and a measurement shall be recorded for each depth setting. This process shall be repeated twice with a 180 degree rotational off-set around the hole. Tests shall be Moisture corrected.
5892267d-652e-5e00-bf24-99210acd1c71 | note | ○ Average Value 83 %
6d91728d-f2c2-5b1a-8456-f4010f7afee1 | note | ○ Minimum Value 81 %
89d82d70-0372-52a4-b389-110104b286a8 | note | Standard / Specification - NZTA B10 - 4.6.7
3cb66c12-5308-5d87-8478-9d3fd72f5d39 | note | Verifying Document - Test Results
4951941c-1775-552d-99db-13d3b6f0e7f3 | note | Frequency - At least five (5) randomly selected areas per 4,000m² or part thereof. For lot sizes larger than 4,000m² additional testing shall be undertaken at a rate of 1 test per 1000m²
17a488e2-3c16-50ed-a24a-c0295c85923f | note | Verification Activity: Activity - I
abb708b3-4284-5d54-833b-de5872586c94 | note | Verification Activity: By - SE
9735dae7-2d5a-5b5e-bc06-364203d2973c | checkpoint | 13.06.21 - Moisture Correction Cores
f2095300-85f6-53f0-b488-99d29c63094e | note | Acceptance / Conformance Criteria - A minimum of two core samples per 4,000m² or lot size whichever is the lesser, shall be taken within 0.5m of the probe hole to be used for moisture correction. After oven drying to calculate moisture correct, the same core sample shall be used for ITS.
eabf81a2-3c62-5988-b5a1-ef9ef192d3b9 | note | Standard / Specification - NZTA B10 - 4.6.7
702f1ffa-2c6f-5e59-a826-4519c43d8d2a | note | Verifying Document - Test Results
8aa7b166-4e08-520b-a3d8-785f7e400994 | note | Frequency - A minimum of two core samples per 4,000m² or lot size, whichever is the lesser
47023392-e4a0-5c7b-ab87-20df5faadeef | note | Verification Activity: Activity - I
c5ca2ef0-34f8-5cfa-9fb0-588779e9e4fa | note | Verification Activity: By - SE
2e0c41c7-05dc-52d8-8810-f5b46e527098 | checkpoint | 13.06.22 - Coring
788e8d51-e87a-580c-b232-b13092c075f3 | note | Acceptance / Conformance Criteria - After a minimum of 7 days post stabilisation the Contractor shall take 200mm diameter core samples from representative locations in the stabilised layers for Indirect Tensile Strength (ITS) testing. If the Hi-Lab basecourse is placed prior to 7 days after sub-base construction, both layers shall be cored together at least 7 days after basecourse construction.
7b772ef0-29f5-5d4f-9914-dc4358b56a42 | note | Standard / Specification - NZTA B10 - 4.7.1
b325eeb6-0d7f-5540-bbcc-b0e118fe9d88 | note | Verifying Document - Test Results
1e474a5a-a5d7-5628-9814-52ed70cd2003 | note | Frequency - One core is required per 2,000m² lot or part thereof for each stabilised layer.
5861300a-000d-5a74-9be8-3c7bb7bc318c | note | Verification Activity: Activity - R
c28fe129-0105-5833-887b-e599ac716a00 | note | Verification Activity: By - SE
1dea0bca-63d1-5d52-99fd-a97730d18266 | checkpoint | 13.06.23 - Hi-Lab Sub-Base Deflection Testing
dcedf624-6fae-5872-9c62-fd155b1b365a | note | Acceptance / Conformance Criteria - Benkelman beam testing shall be carried out on top of the Hi-Lab sub-base layers in accordance with TNZ T01 specification at 10m intervals in alternating wheel paths for all lanes, within 7 days after stabilisation. All measured deflection measurements from each construction lot shall meet 95 the percentile ≤ 0.4mm (max < 0.5mm)
4fbdc099-c73f-5052-972e-cece5f4d565d | note | Standard / Specification - NZTA B10 - 4.8
d7b559cf-762b-55e3-8ade-9073e83198fb | note | Verifying Document - Test Results
9059d2cc-e046-56e9-ae1d-0edb508ea1a6 | note | Frequency - Prior to Next Layer / Surfacing
a33e12a3-a07f-5692-b9ae-bdf17ab51d3a | note | Verification Activity: Activity - HP
8a44d037-bae6-5c06-b8c1-d02dd4d5ba60 | note | Verification Activity: By - ENG
d748e447-661b-5f42-91bb-a370188e19bc | signoff | AUTHORITY HOLDPOINT
dc5d2f91-477d-5b38-bfbc-112810b6c337 | checkpoint | 13.06.24 - Hi-Lab Basecourse Deflection Testing
fb506bfa-0439-515e-ad2d-dc794265f5fd | note | Acceptance / Conformance Criteria - Benkelman beam testing shall be carried out on top of the Hi-Lab basecourse layers in accordance with TNZ T01 specification at 10m intervals in alternating wheel paths for all lanes, within 7 days after stabilisation. All measured deflection measurements from each construction lot shall meet 95 the percentile ≤ 0.3mm (max < 0.4mm)
e050aac8-3e40-59bb-b2f9-fd43cf5ec056 | note | Standard / Specification - NZTA B10 - 4.8
450d5527-904d-58be-9359-dfd880581914 | note | Verifying Document - Test Results
d4749671-d3b5-565e-881c-0216ff0df1f5 | note | Frequency - Prior to Next Layer / Surfacing
f8708bc8-d9e1-5e73-910c-50dad1cd3acf | note | Verification Activity: Activity - HP
7a8de570-5a0b-56ed-bb02-d81c3ce23838 | note | Verification Activity: By - ENG
6415bbd5-7eba-5b7e-a59e-d906f037defc | signoff | AUTHORITY HOLDPOINT
46a2b057-7dc4-5e97-b9ce-4ecc203327de | checkpoint | 13.06.25 - Hi-Lab Pre Chipseal inspection
53ffe0fd-b585-5345-b285-62f2e581c1a6 | note | Acceptance / Conformance Criteria - Before sealing, the Contractor shall advise the Engineer that the pavement surface has been prepared in accordance with this specification although final sweeping may not have been performed. The Engineer shall be given the opportunity to inspect the swept pavement surface for approval.
2c63190f-61d9-55f9-94f7-b9c2d6991580 | note | Standard / Specification - NZTA B10 - 4.9
6a7cfa1d-4bb0-50e5-bc6a-a210d1024a89 | note | Verifying Document - Engineers Acceptance
ddd46e44-df7c-572e-8928-00e775a2ec8d | note | Frequency - Before sealing
720877d3-9614-55a3-a715-eb63c6283396 | note | Verification Activity: Activity - HP
494ec0d9-3483-5f6c-8b39-4df7701d294f | note | Verification Activity: By - ENG
2ec83722-b96f-59d2-b7f7-eca45b816518 | signoff | AUTHORITY HOLDPOINT
cf581b77-bb0b-5a4a-8328-5257b97c4f87 | checkpoint | 13.06.26 - Hi-Lab Basecourse Surface - Pre Asphalt NAASRA
bf68a812-03a0-5451-80d1-93431a78af59 | note | Acceptance / Conformance Criteria - For in-service chip seal surfacing - the 100m moving average lane roughness of Hi-Lab basecourse shall not exceed a NAASRA (100m rolling avg/km) < 75 counts/km.
4ba9a719-86a6-568e-860b-80582d424863 | note | Standard / Specification - NZTA B10 - 4.9
e09181b8-16a6-58ee-9acb-88b149e02315 | note | Verifying Document - Test Results
92cb903c-5be9-5b22-abcf-90d7e8ddec54 | note | Frequency - Prior to Asphalting
ebec4da3-e0f3-5a66-bebe-5249216eb354 | note | Verification Activity: Activity - HP
525bea7c-1d93-571e-92ff-5fa89b18ac24 | note | Verification Activity: By - ENG
f9ba2cdc-eb17-50cd-98b5-194c045d5d59 | signoff | AUTHORITY HOLDPOINT
710d2ca2-5422-5f19-ad1d-f29ae63a3fd7 | checkpoint | 13.06.28 - Hi-Lab Pre Levelling
75e43b08-a2e0-5a1f-b15f-99ad1ba5fcd1 | note | Acceptance / Conformance Criteria - The Constructor shall submit the asphalt pre-levelling methodology to the designer for review and approval prior to implementation.
de79cdcf-dca2-5897-93d3-aab436b74ea3 | note | Standard / Specification - NZTA B10 - 4.9
7a042401-2068-55ea-af21-f8759bde378a | note | Verifying Document - Methodology
e9bf2c67-bbcd-5312-8654-ac91999427e8 | note | Frequency - Prior to Asphalting
3e1070d7-c1f0-57f9-87a2-ae3e9dfb99cc | note | Verification Activity: Activity - HP
ab9beac0-4665-5208-aa77-99144c8c011c | note | Verification Activity: By - ENG
3bbabf6b-65cc-5e8e-96f3-25c0e2c17837 | signoff | AUTHORITY HOLDPOINT
4a20b055-87ba-53bb-9189-bcd3365ffdf7 | checkpoint | 13.06.29 - Hi-Lab Pre Asphalt inspection
2b0e6f62-68c7-52d9-bc11-39f7c023720d | note | Acceptance / Conformance Criteria - Before sealing, the Contractor shall advise the Engineer that the pavement surface has been prepared in accordance with this specification although final sweeping may not have been performed. The Engineer shall be given the opportunity to inspect the swept pavement surface for approval.
5d329e5e-25ed-5cf0-8b3b-cdb5b8cde833 | note | Standard / Specification - NZTA B10 - 4.9
d30d677c-2729-5cb0-b9a7-61c7ffc3a5d6 | note | Verifying Document - Engineers Acceptance
d6408d0f-7e1a-5544-bdcb-c19cbb8f7601 | note | Frequency - Before Asphalting
cc5843a0-0356-53bb-aa85-669741664f85 | note | Verification Activity: Activity - HP
89efce3a-2062-514f-8fe3-43b2c8b1004d | note | Verification Activity: By - ENG
8732e577-30a6-5cc7-8c2f-cd019bafc80c | signoff | AUTHORITY HOLDPOINT
4579d018-56a6-5dff-9e43-0376c57cfbb5 | section | 14.02 Chipsealing
8a02dcd5-5e49-5f19-b403-71144ec78eae | checkpoint | 14.02.01 - Sealing Procedure
4a2704eb-bceb-5bb0-ac7f-c75b55cc1ea0 | note | Acceptance / Conformance Criteria - Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, P4, P17, and Q/1.
5e1728df-7231-502c-9f29-bae12bc2e911 | note | Standard / Specification - M/1, M/6, M/13, P/3, P4, P17, and Q/1.
5fdde78c-05ed-5261-8fe0-30ebf3e64e80 | note | Verifying Document - Methodology / Construction Pack
711f5bf4-4511-5d78-b724-3cbb4aefe736 | note | Frequency - Prior to Sealing
ea48665b-55c4-5696-971a-6cd4cdc38abb | note | Verification Activity: Activity - R
14ecaa5c-070d-5551-a37b-cf1263a72010 | note | Verification Activity: By - SE
ada53fa2-4291-5b07-83fd-c5bf5658f253 | checkpoint | 14.02.02 - Seal Design / Binder application rate
382fb975-3729-5c49-bfd9-dc67cf55c008 | note | Acceptance / Conformance Criteria - The sealing design including binder application rate to suit the surface conditions shall be approved by the Design Engineer prior to sealing.
5f6dd59b-b177-564d-a0c8-f2834497586a | note | Standard / Specification - TNZ P3 TNZ P4
7efb9976-351f-5f8b-93fb-5f8ce40f3039 | note | Verifying Document - Approved Seal Design
45afc476-5672-5482-ad82-aebdfd4f6ad7 | note | Frequency - Prior to Sealing
d871e8d6-aabb-50bf-834b-5932721e0db5 | note | Verification Activity: Activity - HP
24ff89de-6b68-5bb9-9543-6b233bf28729 | note | Verification Activity: By - ENG
cbc739c1-0f8e-53cd-93a8-a1286c12c3f8 | signoff | AUTHORITY HOLDPOINT
c9fe788e-994f-5558-a4d7-63f0b4bcc03b | checkpoint | 14.02.03 - Presealing Requirements
047ff856-b8c1-52ba-bd82-e292845f78d2 | note | Acceptance / Conformance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 60%.
f5fdfe1d-1924-583d-9f1e-3ec6e2ec4e53 | note | Standard / Specification - TNZ B02
5952ff60-0de7-5dd0-a0c4-3a533dc46dd8 | note | Verifying Document - NDM Report
abda4594-91a3-5ccd-8338-803a7cd989a3 | note | Frequency - Min 5 Tests Per Lot 1000m2 Max Lot Size
9fab31f7-3fbe-5e2c-be3a-cca371935af4 | note | Verification Activity: Activity - HP
a195f025-ba6e-55ca-b477-cfdc55060f3a | note | Verification Activity: By - ENG
c23627bd-3900-5db8-88bb-f4cfc71e2be7 | signoff | AUTHORITY HOLDPOINT
0ae77eda-811f-5505-81cf-ad3d9cc0f205 | checkpoint | 14.02.04 - PreSeal inspection
4d1f6013-7c4c-5751-a2ed-7306aa7f5563 | note | Acceptance / Conformance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
18a6404b-a817-5550-8472-fdda9d0cd373 | note | Standard / Specification - TNZ P3 TNZ B02
2c17e30a-647f-5baa-8ac4-8c237f6b0e3d | note | Verifying Document - Hold Point Release
363b9d50-d2a8-5366-a68a-31fb79455514 | note | Frequency - A minimum of 24 hours’ notice of intention to seal.
a11b6128-3dff-55f8-81f9-7cff57033213 | note | Verification Activity: Activity - HP
99d4f988-7dfc-5ae3-8d7e-0265a8036442 | note | Verification Activity: By - ENG
3ae86b65-5743-592b-9e95-7c2fe7c32173 | signoff | AUTHORITY HOLDPOINT
ffdd19fc-5e7d-5126-a571-17726917b679 | checkpoint | 14.02.05 - Spray Temperature
756ba8f9-e13e-595b-81c2-5fb81ea69e3d | note | Acceptance / Conformance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
c761cd02-b0dc-5507-9d8c-87c124a0582b | note | Standard / Specification - TNZ P3
b2b79d11-06a2-5ffc-b798-f934cdfb446b | note | Verifying Document - Site Notes
0ad08bbf-f938-590c-b27f-72190b05b15d | note | Frequency - Prior to Seal
1a4876ff-598a-525f-86c4-a8b61a443bea | note | Verification Activity: Activity - I
cb29a383-ee50-5309-b496-7c13dc661198 | note | Verification Activity: By - SE
0dcbadfc-dfc4-5614-9349-ce2d47f98f3b | checkpoint | 14.02.06 - Binder Sampling
0a43b769-2b7a-5e27-a7fc-87d587eaad5b | note | Acceptance / Conformance Criteria - A minimum of two samples per bitumen distributor load shall be taken. The first of these samples shall be taken at the end of the initial spray run and the other immediately before the final spray run. Bitumen to be tested on Engineers instruction.
a8134afc-73a4-5ffc-83c6-5ea296550d56 | note | Standard / Specification - TNZ P3
11df5113-7374-520b-a00c-67f834d232ec | note | Verifying Document - Site Notes
65f03b6a-0088-51e0-a376-062217407592 | note | Frequency - Each Worksite
1feae969-32bb-5739-8bbe-543144d6ff2e | note | Verification Activity: Activity - I
4e0010a7-0903-5e3a-abbf-699cd809593d | note | Verification Activity: By - SE
bd02d977-a52a-556b-91ff-b98ba5e13bf2 | checkpoint | 14.02.07 - Quantity of Binder Sprayed
78eaa615-e19f-550a-8671-04eeafd3f5ec | note | Acceptance / Conformance Criteria - The quantity of binder sprayed in any spray run, measured by dipstick reading, shall not vary from the amount directed by more than 50 litres plus 4% of the amount directed.
cd9e6e79-3156-5e29-a249-577c4145119b | note | Standard / Specification - TNZ P3
8b399004-6650-5b3f-b0f2-9b3e3da8607a | note | Verifying Document - Site Notes
87640119-4b14-531b-9c74-7da52100b7d1 | note | Frequency - Every Spray Run
29c879a7-dfa6-5c85-907d-d254a8e15fa4 | note | Verification Activity: Activity - I
3537da61-4ab7-52ae-99c4-62f3c183dec1 | note | Verification Activity: By - SE
3360a235-e28c-535e-ba36-1d4bc26aebd4 | checkpoint | 14.02.08 - Chip Application
5d6b6e09-2ef2-5ea6-8d6f-977420a8392e | note | Acceptance / Conformance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
0477e93c-c54c-5d7f-aff8-f9d456640836 | note | Standard / Specification - TNZ P3
569558f8-1c70-5eb9-895b-c796722c7326 | note | Verifying Document - Site Notes
f39b7f4b-97a0-56a4-b49e-80fb65ef9dcb | note | Frequency - Every Spray Run
76f031c5-e9f8-5e9c-847b-6260d3318f5e | note | Verification Activity: Activity - I
5a63112f-246d-5e3e-be3b-a9e024308d08 | note | Verification Activity: By - SE
28a4f134-dc17-5564-b5ee-68cd1156c666 | checkpoint | 14.02.09 - Surplus Chip Removal
a918f82e-f46f-57a8-ae40-b54691aae467 | note | Acceptance / Conformance Criteria - Surplus chips shall be removed from the sealed surface prior to the removal of the temporary speed restriction signs.
2f89a2c9-9ce6-566e-998e-6863f3468cba | note | Standard / Specification - TNZ P3
cdfca57f-161c-5079-86b1-7a17e81d12a9 | note | Verifying Document - Site Notes
b717d0e9-c292-5ce3-9f22-1b5dd47e9705 | note | Frequency - 24 hours of Completion of any Section of Seal.
3ea8c3aa-8e98-5015-a667-c8eefe9fe20c | note | Verification Activity: Activity - R
12bebbd4-e24e-59cf-9041-386572188280 | note | Verification Activity: By - SE
8e0b0105-681f-58b6-851b-e319fa540427 | checkpoint | 14.02.10 - Post Seal Inspections
05306da3-4b52-51b8-aa6b-c6a388be05b6 | note | Acceptance / Conformance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
449b7014-c80a-5b81-9e3b-c9e4504f4df0 | note | Standard / Specification - TNZ P3
ced77de2-bebf-5a21-aca2-ba693077232a | note | Verifying Document - Engineers Acceptance
2d0da6ec-25eb-524a-929f-1dcde5da8274 | note | Frequency - Prior to TM Removal and After Final Sweeping
a840f286-0c6b-57a6-b13d-e6fb68406793 | note | Verification Activity: Activity - HP
4000bcd2-d87f-5643-a7a5-8a265d425503 | note | Verification Activity: By - ENG
53fb941f-2e01-574a-9547-69f4057ddfd9 | signoff | AUTHORITY HOLDPOINT
a4cec822-66da-55a1-825f-9e472e9ccfe3 | checkpoint | 14.02.11 - Chipseal Repairs
fe4cf0e6-e7e4-5db4-8908-fb191478a276 | note | Acceptance / Conformance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
4705894b-5054-55a5-9ad6-0db93614ace0 | note | Standard / Specification - TNZ P3
50212966-10fe-5f05-b1aa-43fddec0389f | note | Verifying Document - Approved Repair Methodology
bdd292c6-b204-5729-8dc0-7be2e981d679 | note | Frequency - Prior to Repairs
2190a8d3-661e-5104-bef0-52123cc93ca2 | note | Verification Activity: Activity - HP
c1dfc902-16c0-5655-897a-b990c5c04ae0 | note | Verification Activity: By - ENG
21a6df80-a2a2-52db-b4ab-47a1d69759f1 | signoff | AUTHORITY HOLDPOINT
858d1fca-02ce-5ab6-97d6-54293d261807 | section | 14.04 Construction Activity - NZTA M27 - Specification for stone mastic asphalt.
81cbcad2-8ee6-57c5-acf3-bf655c1f8dd0 | checkpoint | 14.04.01 - Construction Trail
b829364e-241e-5006-89f5-2424bbdf8300 | note | Acceptance / Conformance Criteria - Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. SMA manufactured in the production trial can also be used in the construction trial provided that it meets the requirements of the specification.
818b6e9b-6ea8-556b-9201-89763ae5dec9 | note | Standard / Specification - PS 21.2.1 NZTA M27:2020 - 7
765c8215-8213-53a9-96a7-84406557c8ac | note | Verifying Document - Test Results
b0ac0af3-271d-548b-a23f-20de939070f9 | note | Frequency - As Required, two days before the site work is due to commence.
43e84d02-19eb-5e1d-a28f-85c361d0cb8b | note | Verification Activity: Activity - I
1d89ed17-9ace-5524-8084-d1a5ec01e85f | note | Verification Activity: By - PE
6813627f-2d6c-5604-b669-1504a38bb377 | checkpoint | 14.04.02 - Paving Plan
3addc382-738d-529b-8691-fa1ce916c502 | note | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
0d70d4e4-a672-5e6f-9fe1-e7089acce754 | note | Standard / Specification - NZTA M27:2020 - 8, 9
cf329939-6f2f-5536-a540-4cf63fa7bc19 | note | Verifying Document - Construction Work Pack
2915dc72-667b-5e1b-ba9c-ba08ad6b1a42 | note | Frequency - 7 days prior to construction of the asphalt pavement.
a70c6cd1-e28f-544d-b66d-e2aa7f0f81bc | note | Verification Activity: Activity - HP
714db262-579b-534a-8e5e-c6d0d0c0f602 | note | Verification Activity: By - ENG
359ddbf5-2f8b-55e0-896a-23e625ec62f2 | signoff | AUTHORITY HOLDPOINT
ce5ca11c-fdca-55c5-88f3-9a7740885c2d | checkpoint | 14.04.03 - Preparation of Area to be Paved
8d66f727-df96-5db6-bb09-d0fb4994f465 | note | Acceptance / Conformance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
49ebabbd-221b-5545-b7bd-36c5c46a7473 | note | Standard / Specification - NZTA M27:2020 - 9
744fb93f-5b22-595c-98f7-82174c5950db | note | Verifying Document - Site Notes
3c7bdd4a-2c83-572a-bb7d-6e3f3a986add | note | Frequency - Pre Seal
24b6f187-2e4f-5639-b9a7-c45a51d9fd7d | note | Verification Activity: Activity - I
eafd0916-9efc-5f49-9567-ded3b595f2a3 | note | Verification Activity: By - PE
ec5fe480-95f5-542a-ba78-bb3941cf9998 | checkpoint | 14.04.04 - Protection of Services
b1450a7e-d1fa-5926-92af-c46863c51090 | note | Acceptance / Conformance Criteria - The Contractor shall prevent tack coat, binder, aggregate, asphalt or other material used on the work from entering, adhering or obstructing gratings, hydrants, valve boxes, inspection pit covers, kerbs and other road fixtures
84a86049-a096-5ac2-acb2-68b7427ff93d | note | Standard / Specification - NZTA M27:2020 - 9
1c6c12be-f285-50df-8708-a29efe8e5242 | note | Verifying Document - Environmental Inspections
5770afab-5fd6-5852-9b72-b01fc2a782fb | note | Frequency - Daily
f96e2099-29ab-59db-bc3b-09959d5baa9f | note | Verification Activity: Activity - R
7c1c4e59-7f5d-5539-b6ec-0ef64a7e2e4c | note | Verification Activity: By - SE
508d635d-807d-5c3c-9d1a-7dd6970a856c | checkpoint | 14.04.05 - Ambient Conditions for Placing
d070a84a-433e-5290-8392-d12ecbe872a0 | note | Acceptance / Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
0a1c75c3-d5e1-563f-8750-b3f30576408a | note | Standard / Specification - NZTA M27:2020 - 9
ddb99b18-fc81-5eba-be7f-73c7bdf5baaf | note | Verifying Document - Site Notes
f0417578-b234-5101-b02d-ba55f71770ff | note | Frequency - Pre Seal
0e66a1df-38a8-5097-bc0b-a7d9a1238d44 | note | Verification Activity: Activity - H
2aea6436-9bd1-5078-bb19-ebf08af402a0 | note | Verification Activity: By - SE
58f05e5d-7a8c-5186-a487-93541a70e98b | checkpoint | 14.04.06 - Tack Coating
7c6eb46f-0c0f-51df-9da7-a5a60830597d | note | Acceptance / Conformance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. Where SMA is to be spread over clean, freshly placed asphalt, the Engineer can direct the Contractor to omit the tack coat.
e16ea7ef-1d3d-5a01-b411-e6605213238e | note | Standard / Specification - NZTA M27:2020 - 9
52a7ec9f-2e6c-5eb6-9dad-1d495e6c0636 | note | Verifying Document - Site Notes
88039652-d49e-5fc3-b766-3e8ff9fd107f | note | Frequency - Prior to Paving
71128965-8b94-5695-bfc6-7f10679aaa5e | note | Verification Activity: Activity - I
466f91ba-6598-53c2-8cb0-cf9802195a2e | note | Verification Activity: By - PE
83aa1453-be4e-5785-a7df-eb150ff02789 | checkpoint | 14.04.07 - Asphalt Production Conformance - Grading and Binder
95236ca4-e579-51e8-b43a-7a9ed0d4bf43 | note | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass. Refer clause 5.2 and table 5.2 for frequency and tolerances
ec52a0ab-427f-55d0-8311-881ac34b8c71 | note | Standard / Specification - NZTA M27:2020 - Table 3.1, 5.1 & 5.2
d2446939-8dae-54cc-bfe4-ac167d1e2c39 | note | Verifying Document - Test Results
e88fd4a5-b18d-51a1-ae3b-0e3d74aee58c | note | Frequency - 1 per 200T
589e2941-c575-5c13-b738-b5e55acdd964 | note | Verification Activity: Activity - I
d0635266-a049-50c2-bf22-7c4dc42f8f6f | note | Verification Activity: By - PE
a3439220-bcd8-539c-b5b7-63e66f3188ac | checkpoint | 14.04.08 - Asphalt Production Conformance - Volumetrics
e3c62bb8-55a3-49a4-b0ae-3770e40a7e2e | note | Acceptance / Conformance Criteria - Conforming volumetric testing. Refer clause 5.2 and table 5.2 for frequency and tolerances
f8256dc1-35f9-405a-8eff-22f87e2a69c5 | note | Standard / Specification - NZTA M27:2020 - Table 3.1, 5.1 & 5.2
560249a6-db89-4dcf-886d-c68d1a192047 | note | Verifying Document - Test Results
2097e674-377a-419a-a8df-db726623e92e | note | Frequency - 1 per 600T
62855a92-443f-4155-8b23-6ac939e1bcf1 | note | Verification Activity: Activity - R
eddd6156-262b-4d03-ac9c-f4e9b3d29c06 | note | Verification Activity: By - SE
6bd3537e-614d-518b-9a75-d9d5e094a0e1 | checkpoint | 14.04.09 - Core Thickness
d9cb2d03-fc0d-5d73-82c8-c5a0c0cb97ec | note | Acceptance / Conformance Criteria - The layer thickness determined from measurements on the cores is LCV of no less than the specified thickness - refer clause 9.7
ba717c2b-5fc5-5585-8506-cc7578ead47f | note | Standard / Specification - NZTA M27:2020 -
71dcb340-61cc-5411-957d-4a7cd94ba176 | note | Verifying Document - Lab Report
eddd9208-0c06-5c16-93d8-bc45e1414d32 | note | Frequency - Mat - min 8 per lot (day) (1 for every 300 m²) Joints - min 3 per lot (1 for every 100m)
1b7fff74-ff0a-5e5e-815e-0e485d0e21f9 | note | Verification Activity: Activity - R
fc36a356-2fdd-53ff-b52e-d96d5d73d759 | note | Verification Activity: By - SE
06d1fa65-7a70-5f7a-83ab-705c72fe901f | checkpoint | 14.04.10 - Mat Density
97115db1-6e28-5aef-9d7a-32357bbd9066 | note | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot
08b0c736-1e7e-5724-8e4e-bb7966700e15 | note | Standard / Specification - ASTM D5361 NZTA M27:2020 - 9
1902367d-1e9b-58bf-845a-aed9a1bbcdd3 | note | Verifying Document - Cores
246a7278-c482-5584-9521-9e4e306a84b7 | note | Frequency - min 8 per lot (day) (1 for every 300 m²)
fc9ad767-8aba-52b6-83a8-f4314df53bb6 | note | Verification Activity: Activity - R
14786077-36aa-5fbf-ba61-2a7d89fdb789 | note | Verification Activity: By - PE
c8413aac-02aa-5fea-b11f-87505c0c4dc1 | checkpoint | 14.04.11 - Joint Density
3495045f-7862-53fa-b769-cc2768a68363 | note | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100 m of joint with a minimum of three representing each lot
1c2f1b28-15b8-57d1-89d5-a8d428478198 | note | Standard / Specification - NZTA M27:2020 - 9
73921705-28f4-5b17-8a9e-c948b77daf21 | note | Verifying Document - Cores
d66f2c1b-b62a-59b4-bcf5-fd8a3231839b | note | Frequency - min 3 per lot (day) (1 per 100 m of joint)
c02594ae-c539-5fd3-a308-51bac9ad26a1 | note | Verification Activity: Activity - R
9affcc95-ca75-5b62-99c0-e076a86a1378 | note | Verification Activity: By - PE
b8164e79-0652-52a9-9c6a-4f1d1cb35924 | checkpoint | 14.04.12 - Density Testing
e4df0276-ef17-52db-bc4a-ae357f6b917a | note | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
3cb9315f-0714-5048-8c5c-ab1e2b177581 | note | Standard / Specification - NZTA M27:2020 - 9
f9c2468a-6562-5dc2-9546-2c9ceb2bf5d4 | note | Verifying Document - Lab Report
89876f6c-0ed7-5742-a942-e11c9bc4eb13 | note | Frequency - within 24 hours of them being cut from the pavement
114fa33f-495e-5c0c-add3-e38351a5fb21 | note | Verification Activity: Activity - I
c8713a55-455f-5d9a-9ab9-26adf1150beb | note | Verification Activity: By - PE
51784f52-b233-5853-afd7-e6dd19e4af60 | checkpoint | 14.04.13 - NDM Density
c06b329d-6d28-56b6-8251-338a459298ab | note | Acceptance / Conformance Criteria - NDMs are to be completed at the time of pacing to ensure compile when cores are taken
e9eec6d2-671c-5827-9713-488a1ddd7144 | note | Standard / Specification - NZTA M27:2020 - 9
14a00cf0-ecdf-52c5-93a4-2688bd60896b | note | Verifying Document - IANZ Lab Report
6df7474e-5b22-57d9-a84d-31cbf4cadc94 | note | Frequency - min 8 per lot (day)
dd54f5dd-922c-51e7-a562-f8eec247aac9 | note | Verification Activity: Activity - I
0d11afdd-a10c-5d83-86a9-709848f48e2c | note | Verification Activity: By - PE
077a1b31-e544-5b86-81dd-d5cc05ae05a8 | checkpoint | 14.04.14 - Transverse truth of the surface
72067892-9776-501d-b956-47b218bebc3b | note | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge.
fc128c79-b367-501b-a116-b1a5c4b7c5f6 | note | Standard / Specification - NZTA M27:2020 - 9
828a1ff9-c685-545f-9800-47616f7ea216 | note | Verifying Document - Site Notes
10562850-5b8a-5adb-a708-00e71ba90c4f | note | Frequency - Post Seal
8f2f04be-7fe0-56be-8a31-85725ba08b03 | note | Verification Activity: Activity - I
0c6eb3f0-7e40-51ac-b52c-f34141dd510f | note | Verification Activity: By - SE
5e8d35db-3d51-5475-8ea9-89430aba78dd | checkpoint | 14.04.15 - Finished Pavement Level, Alignment, and Thickness
4f413da4-9cdf-5f41-aba6-934af34cf8e5 | note | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements.
49977093-4d04-5849-b852-5365120d3bb0 | note | Standard / Specification - NZTA M27:2020 - 10
0fb35f10-d088-5060-b2c1-10adb83a0fa4 | note | Verifying Document - Survey
6282bf57-8f3c-5047-88fc-4344dd15a8af | note | Frequency - Continuous thought construction
da93352a-b099-5d58-a84a-9eb7b4ef486f | note | Verification Activity: Activity - I
534d34de-14dd-5003-a33f-b9e6b5aa6c2f | note | Verification Activity: By - SE
35612da6-dfce-53fc-a4b0-a220727f10b6 | section | 14.05 Roughness
bcb7970f-6ae4-5bf2-b8e2-868871a1de0d | checkpoint | 14.05.01 - For a Chip Sealed Surface
f16358d4-a7a7-54c1-8a10-a3e1a7fcc5f0 | note | Acceptance / Conformance Criteria - Target is an average of 60 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 70 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km.
f491f1cb-58b8-5808-8eff-4ae2d8fc8a53 | note | Standard / Specification - PS 21.4.1
67f71065-b1fc-5bb1-9514-354b6c569f58 | note | Verifying Document - Test Report
dc8a5575-eb67-5b2e-893c-00679921e36a | note | Frequency - Prior to sealing
ffbcdcc9-2692-595c-b0d9-a829dc94f4e0 | note | Verification Activity: Activity - HP
0742a3d7-ec48-57cb-bd64-97db8c7191a4 | note | Verification Activity: By - ENG
6c3ba941-1777-5501-9249-247d90f91522 | signoff | AUTHORITY HOLDPOINT
f8bd57a9-846b-5828-88de-6d7d62f6fd73 | checkpoint | 14.05.02 - For an Asphaltic Concrete Surface
bb09d009-61c9-543b-affc-c20d37681688 | note | Acceptance / Conformance Criteria - Target is an average of 50 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 60 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km.
dc739d87-e34d-54ee-b29f-4aea95d96cb1 | note | Standard / Specification - PS 21.4.1
6094f803-83de-5a26-8351-019306c8ada0 | note | Verifying Document - Test Report
23694c00-ea21-5b87-811e-790facfdb7c2 | note | Frequency - Prior to sealing
885818ab-0692-54b1-b122-ec72f7dad47e | note | Verification Activity: Activity - HP
22185179-e8bc-5903-94b8-171604ea6610 | note | Verification Activity: By - ENG
b8bafe1f-4b75-5b87-857f-d269c0bcf8c8 | signoff | AUTHORITY HOLDPOINT
e16b3ed5-409b-5176-b427-1231353994c8 | section | 14.06 Skid Resistance
b0053e02-fe90-5f9b-8826-998d139bda13 | checkpoint | 14.06.01 - Skid Resistance
681e0214-8423-538c-b91c-4273c146e1b1 | note | Acceptance / Conformance Criteria - The surfacing shall meet the requirements specified in the Transport Agency’s T10:2010 Skid Resistance Deficiency Investigation and Treatment Selection, and any other subsequent amendments.
70753d68-ded5-52c9-98e6-3ec5a769a4dc | note | Standard / Specification - PS 21.5.1
0a2fab12-bafb-5d9c-9d54-942a0e7e15b7 | note | Verifying Document - Prior to Project Completion
fda9aae7-4599-580c-b17d-33b472ccab69 | note | Frequency - Prior to sealing
caa6cae3-194a-52f0-9ffa-463a952cd44c | note | Verification Activity: Activity - HP
63aed61d-e731-5a24-b7e1-cd552d01049b | note | Verification Activity: By - ENG
629b7c55-9012-52d8-befe-d8f7f7908625 | signoff | AUTHORITY HOLDPOINT
49374933-1643-533f-818e-c424d84b32b2 | checklist | ITP - Pavement - Type B - 104.2 - Rev 3 | itp | ITP - Pavement - Type B - 104.2 - Rev 3
dc44bdfa-8be5-58ec-8b02-ddb40309eb3f | section | 4.23 General Pavement Materials
cfc61591-4db6-5f5c-b38b-5d59198b06a2 | checkpoint | 4.23.01 - TX180 Triaxial Geogrid
da98e085-0d05-58d0-becb-b118df507374 | note | Acceptance / Conformance Criteria - The Contractor is to supply the product details to the Engineer for approval prior to installation on site.
632c77f1-5cff-544c-aedb-76a3ed3d96f2 | note | Standard / Specification - PS 20.3.1
d6565375-5483-5bca-8e57-6c5b3136e802 | note | Verifying Document - Datasheet
992ece6d-3865-5552-bab8-7d8217c94fc5 | note | Frequency - Each Item
0debbcd0-d137-5fdc-8ee9-1b5b4485c58d | note | Verification Activity: Activity - R
f345e16b-0515-5389-b99f-dda3bd494b56 | note | Verification Activity: By - SE
26844f90-2cb2-5c40-9048-6e2661d67d85 | section | 4.24 AP65 Subgrade Improvement Layer (SIL) - B/2 Materials (Pavement Type A,B,C)
e75edad3-1c86-5a1f-8bfc-6c857e9980f6 | checkpoint | 4.24.01 - Source Property Tests and Sampling
9cf2c04f-6b7b-5a8f-ad22-1ccbd7d48338 | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
89ffcfeb-1328-58bc-bfe5-903f216d6b36 | note | Standard / Specification - PS 20.4.1
22b11937-c1f8-57a7-8275-74c7ccd1499e | note | Verifying Document - IANZ Lab Reports
2929be7b-7c37-522a-940d-cb17fe092e8c | note | Frequency - 10,000m3
b9ea1bdb-d2ed-5642-b203-792baa0f01e2 | note | Verification Activity: Activity - HP
11e211df-c49b-50f3-8934-a748842d4cde | note | Verification Activity: By - ENG
821e2d25-ab3d-56d6-9cfb-48b3ace0c405 | signoff | AUTHORITY HOLDPOINT
c4148dc8-e4d4-5aa8-8fef-8272efd80760 | checkpoint | 4.24.02 - Crushing Resistance
73ade936-788b-5847-9cc2-e26a0f05e1fa | note | Acceptance / Conformance Criteria - The crushing resistance shall be not less than 100kN when the aggregate is tested in accordance with NZS:4407: Test 3.10
eea0ed36-9406-5efe-af46-888030155801 | note | Frequency - 10,000m3
b6069329-ba1f-5175-8985-d8f60d13dd70 | checkpoint | 4.24.03 - Weathering Quality Index
9b48e4a9-a39c-555b-ba51-f01d66107626 | note | Acceptance / Conformance Criteria - The aggregate shall have a weathering quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11.
5e42a5a8-f743-57cd-b397-43f8a4bd4bd0 | note | Frequency - 10,000m3
45df2110-45a1-588c-91e6-d377885c2a01 | checkpoint | 4.24.04 - CBR
04d65930-be75-529c-81ef-0052de539b3b | note | Acceptance / Conformance Criteria - The material shall have a minimum CBR of 40 when compacted to New Zealand heavy compaction standard in accordance with NZS4402 Test 4.1.2 at water content between 4% and 6% by weight of aggregate. CBR testing shall be in accordance with NZS 4407 Test 3.15.
026dfe34-c82a-5c59-b712-c94d749ee619 | note | Frequency - 10,000m3
ab25b02a-711a-5787-97ca-cae645f22451 | checkpoint | Production Property Test Sampling
9750a452-43c2-5f59-9260-66c87738b492 | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
d2c9d6a8-0d0d-5b23-8f38-8a8ab1131ce5 | note | Standard / Specification - PS 20.4.1
a308dfc8-bf6d-5726-8b4f-5a9d2df4b974 | note | Verifying Document - IANZ Lab Reports
0d964c5d-c77e-5334-ad18-61d52ddca6e4 | note | Frequency -
0c8c3b15-bddc-54dc-b14a-70191d342765 | note | – – – – – – – – – – – – – –
faea1701-8bf9-51f3-8922-06786be6d04e | note | Quantity ¦¦ No. of Samples
7c10ce86-fa7b-5e4d-b428-12263c4dfae8 | note | – – – – – – – – – – – – – –
0b5bcbda-642a-56fe-bd05-1b8fa7067161 | note | 1 m3 to 400 m3 ¦¦ 2
7be02c6c-376c-5ed8-9a41-ff0261aec975 | note | 400 m3 to 1,500 m3 ¦¦ 3
9062c9bd-c42b-5d7e-8a26-7236f6588858 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
dab88199-cdcf-5665-b0c4-522086a3cb39 | note | – – – – – – – – – – – – – –
00f2366f-3c91-5d7f-b422-cc8f415f4b7d | note | Verification Activity: Activity - HP
6ba81ea1-840a-5d74-bcc4-6914b486bc71 | note | Verification Activity: By - ENG
8aaa1ba6-266e-5753-9a17-79ca51cfd9c2 | signoff | AUTHORITY HOLDPOINT
76f36ba6-c628-5d91-bad4-888b123dfe37 | checkpoint | 4.24.05 - Aggregate Fractions
5bc6f250-9e90-5c0a-a2dc-7723367c68a0 | note | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 50% by weight shall have two or more broken faces. It shall be free of organic matter.
09f99327-3db5-5bc2-bdcc-67d28f9816c4 | note | Frequency -
1fc9e89a-e7f8-5fea-a47b-bcc799652b71 | note | – – – – – – – – – – – – – –
6d3ba992-7f95-55c3-b533-b19a1be93426 | note | Quantity ¦¦ No. of Samples
0459c831-b75e-5aca-91fd-45117a81d7d1 | note | – – – – – – – – – – – – – –
9434e4f1-b9f7-54d7-9eb1-5d79d7fc2147 | note | 1 m3 to 400 m3 ¦¦ 2
1822c410-9687-5c02-ba1f-a2ad7d07ef03 | note | 400 m3 to 1,500 m3 ¦¦ 3
de8230e6-3573-5dac-b10b-868670c3001d | note | 1,500 m3 to 4,000 m3 ¦¦ 4
270907d4-e72c-5b04-849a-decdec0e8642 | note | – – – – – – – – – – – – – –
1209906b-8364-5eca-8677-804139a6cda2 | checkpoint | 4.24.06 - Sand Equilavent
74b09ca6-6fa5-5d2d-8399-df20d2c7619d | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 30 when the aggregate is tested according to NZS 4407: 1991: Test 3.6. The sand equivalent test may be neglected if the grading test shows less than 4% passing the 75-micron sieve.
af94741a-d3a7-535d-bb44-bcbd27bb36cf | note | Frequency -
5076f573-778e-55e4-90e3-9ac5162ba5bc | note | – – – – – – – – – – – – – –
f7b0fa40-f68a-59b4-b6d1-c349e90f2b76 | note | Quantity ¦¦ No. of Samples
5ad5f6c6-ec9e-53e7-b91f-de9280b4545a | note | – – – – – – – – – – – – – –
7e2ad39c-1fc8-553f-bf5c-842ec541a028 | note | 1 m3 to 400 m3 ¦¦ 2
fe60e80f-df89-51de-baed-e5b1d2e1977c | note | 400 m3 to 1,500 m3 ¦¦ 3
269f60a7-3e9b-5af2-9740-9d43fae5f535 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
56dacb92-d1cc-5d06-8947-04622fb1fb35 | note | – – – – – – – – – – – – – –
f34df8ef-5ff5-5f46-a6b6-8daff95862ec | checkpoint | 4.24.07 - Plasticity Index
93d8b7d9-d42a-5572-a3c2-af6abd90e4c9 | note | Acceptance / Conformance Criteria - The Plasticity Index shall be no less than 8 when the aggregate is tested according to NZS 4407: Test 3.4.
a2dd09f6-8e44-5e6a-9dac-047fb3aff167 | note | Frequency -
af258ea6-76d8-52b7-863a-e96b58816aea | note | – – – – – – – – – – – – – –
aa940e13-dbdb-5ea7-a5db-d52013f09ba3 | note | Quantity ¦¦ No. of Samples
f6fcb1c9-8487-569b-8a4c-37dfe1ff3615 | note | – – – – – – – – – – – – – –
bd693983-3356-56cc-bf01-93afc96b8093 | note | 1 m3 to 400 m3 ¦¦ 2
bf087022-2d0e-5e40-a1d0-f1c8264ae3f4 | note | 400 m3 to 1,500 m3 ¦¦ 3
d62482bb-08dc-56ee-9926-bc9a4aa42ba4 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
65b64db9-fbc1-53ad-afbc-5d9e60a0d519 | note | – – – – – – – – – – – – – –
29355a6c-cc0e-5a25-b68f-e8c21e9ded67 | checkpoint | 4.24.08 - Clay Index
baca95ff-1dac-54dc-83a7-9e1a57a7a382 | note | Acceptance / Conformance Criteria - The Clay Index shall be no less than 5 when the aggregate is tested according to NZS 4407: Test 3.5
2016312f-fbce-5141-97e6-557e8f5ac7ec | note | Frequency -
fe5173d5-9c3f-5d2a-88c9-769f2da465c6 | note | – – – – – – – – – – – – – –
b91880e7-2ca1-5f56-a8cc-64ec7e9a878b | note | Quantity ¦¦ No. of Samples
72ff6463-7e8f-5fa8-ad0d-d54c27a729d3 | note | – – – – – – – – – – – – – –
6c0fe1a0-5d32-52af-b2f7-bd6dd9ab24d0 | note | 1 m3 to 400 m3 ¦¦ 2
2cd2c302-0fab-5423-b330-221b30a51062 | note | 400 m3 to 1,500 m3 ¦¦ 3
4ba796f3-5bfc-5ca3-90ea-836759232ac3 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
096fab36-8b3d-5a66-bae9-5dc776f0c0a4 | note | – – – – – – – – – – – – – –
be3abd89-23f0-57a2-953e-bd23a6a8c558 | checkpoint | 4.24.09 - Wet Sieving
ace9b97f-704b-57a6-a891-463a479b1bf6 | note | Acceptance / Conformance Criteria - When tested according to NZS: 4407: Test 3.8.1 Standard Method by Wet Sieving or Test 3.8.2 Subsidiary Method by Dry Sieving, the grading of the aggregate shall fall within their respective envelopes defined below or as directed by the Engineer.
f1ab8dbd-67b4-5717-90cb-97470f26dad4 | note | Frequency -
e6d7410d-5505-5e30-b204-ae18ac94043d | note | – – – – – – – – – – – – – –
94747cc8-5530-5f58-aa43-7ed1828133bd | note | Quantity ¦¦ No. of Samples
47004bdc-127e-5657-ab6f-2c51c19c0e8b | note | – – – – – – – – – – – – – –
55924cb9-6fdd-5103-bc1b-893b572bdfb0 | note | 1 m3 to 400 m3 ¦¦ 2
16fda175-89b9-55e8-a46d-900e0b669e52 | note | 400 m3 to 1,500 m3 ¦¦ 3
31f0457d-f26a-5c59-8fc2-ab6a40b6ae88 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
bbbb6678-d396-5e38-a0f7-c1709c86153f | note | – – – – – – – – – – – – – –
c124d68f-2b35-5659-b3a4-c565239e94ef | checkpoint | 4.24.10 - Testing for Layer Compaction - MDD
e296e448-e098-515d-b486-0ea4eaaea638 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for SIL construction shall be the maximum laboratory dry density using Heavy compaction.
1f85cf61-391d-5d30-8c2a-525f755f2589 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.4.1
cde52cde-6767-54c1-9cb8-8f117bcdf0f9 | note | Verifying Document - IANZ Lab Reports
a9697d7d-4e6a-5bcf-8eda-c42a8d57efdd | note | Frequency - 5,000m2
171099b4-7603-5663-b0e4-f4d7a110b5bc | note | Verification Activity: Activity - R
793f58af-ebd9-5140-85fe-796e4f6364a5 | note | Verification Activity: By - PE
c12729c5-67f6-5d43-b1f2-57394d510061 | section | 4.26 GAP65 Subgrade Improvement Layer - B/2 Materials
347684f7-e1c7-5e11-ad68-cbfef2b04889 | checkpoint | 4.26.01 - Source Property Tests and Sampling
dc69d1e9-48bf-5344-b426-77a7ae11dbd1 | note | Acceptance / Conformance Criteria - The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
2985620a-c9f1-5e17-8ab0-41698a299b3f | note | Standard / Specification - PS 20.9.1
31ddae00-ba78-5d37-bffd-139faae1358c | note | Verifying Document - IANZ Lab Reports
a4c7b5fd-8466-52dc-9e8b-7b586352518a | note | Frequency - 10,000m3
a7559f83-8737-5cdd-99f3-b74dd3690012 | note | Verification Activity: Activity - HP
6d01db06-df09-53c9-96db-677983768da2 | note | Verification Activity: By - ENG
21763a79-b0fc-5f07-a2bc-5a044a2a7ee3 | signoff | AUTHORITY HOLDPOINT
c80204b2-f1b8-5861-9b87-7b0389a79aa0 | checkpoint | 4.26.02 - Production Property Test Sampling
99dcaa90-168b-5b39-a64c-f183770fb8c0 | note | Acceptance / Conformance Criteria - The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
4016ef7a-db9d-5b13-b06f-60275330ed75 | note | Standard / Specification - PS 20.9.1
f71186f6-bcac-5b8b-83bd-8ad6182d4add | note | Verifying Document - IANZ Lab Reports
52c394f8-afab-5c6a-9d3c-cdd4f06c7527 | note | Frequency -
a75843c4-e03e-52f3-b27b-1622919f466d | note | – – – – – – – – – – – – – –
3c20ff9c-5be6-5ff8-9c64-c96300eef198 | note | Quantity ¦¦ No. of Samples
b059b65e-efa9-55a5-b490-8d4ddb3a53c0 | note | – – – – – – – – – – – – – –
465f0aac-676c-5b92-9014-5d2b053404fc | note | 1 m3 to 400 m3 ¦¦ 2
16b0d2e8-bda9-5b54-8b7b-f04f0570fee4 | note | 400 m3 to 1,500 m3 ¦¦ 3
51f16e51-3bc2-5102-bb1b-263a08ef7ead | note | 1,500 m3 to 4,000 m3 ¦¦ 4
2ba279c9-d855-53f0-b438-7e5c11c17a8f | note | – – – – – – – – – – – – – –
ef0d5aae-d973-541d-ba05-debb9c7cb6e2 | note | Verification Activity: Activity - HP
9d25be0c-4ca1-5b01-a0f9-191571aef474 | note | Verification Activity: By - ENG
fcbd0b78-66c4-52db-a924-1c9d0e913898 | signoff | AUTHORITY HOLDPOINT
0af9249c-48a9-550f-ae9e-c6f4cfa0fd7d | checkpoint | 4.26.03 - Testing for Layer Compaction - MDD
4189073a-6eec-596c-a555-59fb9a5a6668 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for GAP65 SIL construction shall be the maximum laboratory dry density using Heavy compaction.
3ab2ac89-04b8-5d49-aeb5-38cf73db323b | note | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.9.1
9fa8d3d5-7743-50da-b3a9-b073cefb9726 | note | Verifying Document - IANZ Lab Reports
e45e573a-f407-5ebe-aec2-53c7232186ef | note | Frequency - 5,000m2
58aa66b2-db47-5d05-b4b8-96f421336e37 | note | Verification Activity: Activity - R
ff6270e3-4c8d-5afd-9b10-8e2e8fd59122 | note | Verification Activity: By - PE
0f6cbb1a-9614-523a-b161-f8f43a49ffc9 | section | 4.29 NZTA M10 2020 - DENSE GRADED ASPHALTIC CONCRETE MATERIALS
5043cd42-4c7d-5320-ac64-b5124cdbc741 | checkpoint | 4.29.01 - Coarse Aggregate - Property Tests and Sampling
1b563a1a-eccd-5f77-9a9a-a9fbf9bed651 | note | Acceptance / Conformance Criteria - The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, and Particle Size Distribution
c8b3134a-2681-57e8-9011-203b556b5d1a | note | Standard / Specification - PS 21.2.1 NZTA M10:2020 - 2.1
18954d18-cb7c-59b5-b689-126e94853ece | note | Verifying Document - IANZ Lab Reports
63120355-0e29-5b3d-ad36-02b55dd1ae9b | note | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
4f3d7cc0-8ce9-5643-991f-2d23b944c4bf | note | Verification Activity: Activity - H
9ce48f6f-34aa-5ab9-9db0-468753780348 | note | Verification Activity: By - PE
4f570d06-ae83-50ad-b62b-8f4fbfcb7ac1 | checkpoint | 4.29.02 - Fine Aggregate - Property Tests and Sampling
f08b88bf-f2ab-5f16-9a3c-ffaa6d1cfff5 | note | Acceptance / Conformance Criteria - The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, and Particle Size Distribution
8eddd8bb-c15d-5215-83fa-876a8bc422a8 | note | Standard / Specification - PS 21.2.1 NZTA M10:2020 - 2.1.
1b7c84fa-ef93-5b7b-ad8e-dcde43fa1e7b | note | Verifying Document - IANZ Lab Reports
8eae82b1-ea3a-5d42-9e62-7898dd675fd3 | note | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
61fa0809-140e-54a6-8ee1-c94a2a3be77d | note | Verification Activity: Activity - H
9a83595d-b1a6-5074-8df1-ac66490eb1ed | note | Verification Activity: By - PE
00387a6f-89e1-5157-83ae-389ac90e3c60 | checkpoint | 4.29.03 - Mineral Filler
fcfea0ff-f414-5711-af0f-ac43085463e0 | note | Acceptance / Conformance Criteria - Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt.
8b2fe52f-de16-5e48-955a-deb04f3801a7 | note | Standard / Specification - PS 21.2.1 NZTA M10:2020 - 2.2 ASTM D242
2f5caf74-4e10-581b-928c-731a29ac3d9c | note | Verifying Document - IANZ Lab Reports
36f74cd2-8a44-5823-8da1-70e028792a29 | note | Frequency - Prior to use
4d680435-49e3-573b-882e-3603ca5e20ab | note | Verification Activity: Activity - H
ca15fd1d-6aa5-5b3b-a85b-0c255aed2f26 | note | Verification Activity: By - PE
20701139-9595-52c4-9d92-23f642bab043 | checkpoint | 4.29.04 - Bitumen
a8b52c23-f0ed-50b7-873e-1dc16b3600f0 | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
88277355-6289-5909-aef4-4414f0aca2b9 | note | Standard / Specification - PS 21.2.1 NZTA M10:2020 - 2.3.1, NZTA M01-A
0d4f5465-a452-53d5-92e4-8e61d765fe40 | note | Verifying Document - IANZ Lab Reports
ef11abeb-ae89-5447-b40e-69d06f8dda5c | note | Frequency - Prior to use
f7854c12-0407-549a-9297-03ed3705e141 | note | Verification Activity: Activity - H
429b6656-e805-56c0-9a3a-b342860ed542 | note | Verification Activity: By - PE
f3961bb6-17a1-5c43-8c5b-e44abee0813d | checkpoint | 4.29.05 - Mix Design Approval
f9b1da01-2ed4-54fd-a515-7550f0866e2a | note | Acceptance / Conformance Criteria - The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use.
bb2a4147-65d7-56af-b1b0-4cd4c125228a | note | Standard / Specification - PS 21.2.1, PS 20.7.5 NZTA M10:2020 - 3.1 , 3.6
4ded92e0-aba7-5a8a-ada3-7ceca376b4dd | note | Verifying Document - Approved Mix Design
27c0ced7-4842-55b5-9a40-bbaf2fd494e9 | note | Frequency - No less than 10 working days prior to the pre-paving planning meeting
ab14788a-8565-553e-9601-ca6c2d33b823 | note | Verification Activity: Activity - HP
009f71e3-3674-5ad2-ae38-5ef0e57911d5 | note | Verification Activity: By - ENG
24531e0b-f96f-563c-b97a-0cd94021b5bc | signoff | AUTHORITY HOLDPOINT
2acdd5f1-32ac-5faa-8b88-3bea1a6d6ab7 | section | 4.30 NZTA M27 2020 - STONE MASTIC ASPHALT MATERIALS
210fcf50-fae8-5a16-bddc-909108432f14 | checkpoint | 4.30.01 - Coarse Aggregate - Property Tests and Sampling
4852b262-60a2-53b3-adb4-ad39fff91663 | note | Acceptance / Conformance Criteria - The Coarse Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Weathering Quality Index, Crushing Resistance, Broken Faces, Bulk SG and Density, Absorption, and Particle Size Distribution
e25b4fd7-98e0-52f6-946c-df29db9cb3a5 | note | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.1
7c01c499-7007-5f0a-bc75-4ffaedf5cb6a | note | Verifying Document - IANZ Lab Reports
5ed5955f-dd73-5913-945d-bc44f9fdc891 | note | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
f0840617-7328-50e1-bad7-6e5041ce5523 | note | Verification Activity: Activity - H
96dd3d91-a009-5f6d-8580-5becbbed74fb | note | Verification Activity: By - PE
5d046762-3ad1-5b69-a01c-8359e1fd11b0 | checkpoint | 4.30.02 - Fine Aggregate - Property Tests and Sampling
b127d2dd-3132-56b5-a64e-fc9b0ff3f420 | note | Acceptance / Conformance Criteria - The Fine Aggregate shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Sand Equivalent, Bulk SG and Density, Absorption, and Particle Size Distribution
82c5983f-ce8f-58ac-b6dd-2c16b12fb6f2 | note | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.1
69378d7e-1863-5b3d-865a-fcc2a92f1e37 | note | Verifying Document - IANZ Lab Reports
20df964e-81fb-5b0a-8bc2-63894d6750fc | note | Frequency - Source Properties every 10 000m3 / 1 per annum. Production Properties every 750 tonne.
6c9439e9-042e-56ca-b068-c743dc8b60d0 | note | Verification Activity: Activity - H
3f113214-aa4b-5ffe-b5c7-1977e93950bb | note | Verification Activity: By - PE
eba5749e-1122-5932-b8f4-867c68e0f113 | checkpoint | 4.30.03 - Mineral Filler
512be874-0e1c-5981-b3c8-11583753c105 | note | Acceptance / Conformance Criteria - Filler shall be consistent in mineral composition. It shall be dry, and free from lumps, clay, organic matter or other material deleterious to asphalt.
f93d357a-6105-51b6-8e29-8a3da355ce61 | note | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.2 ASTM D242
0f1ab89b-922e-5761-9781-cba503cefbe7 | note | Verifying Document - IANZ Lab Reports
01e52077-0880-5ffc-8f62-0d48532d6fdc | note | Frequency - Prior to use
2d5d6ffe-5b94-5e65-bef0-91e425ae172c | note | Verification Activity: Activity - H
0a7be478-2a94-58fb-ada6-067f6e353389 | note | Verification Activity: By - PE
132d7154-1055-5fb7-ac28-fb50add81e62 | checkpoint | 4.30.04 - Bitumen
7d7b046e-b206-52fc-8500-ca341b1d78d7 | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01-A specification.
f2f65a31-c141-5b25-bfbe-0aeeda009765 | note | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 2.4.1, NZTA M01-A
ca68d723-813b-5b38-88b7-c4178a16a347 | note | Verifying Document - IANZ Lab Reports
daf6d472-04cc-5403-b3a4-30acb68ce188 | note | Frequency - Prior to use
33c659bd-3752-525a-a303-3d6dfe5cb3ee | note | Verification Activity: Activity - H
152278fb-4453-593b-b494-9d01a5255896 | note | Verification Activity: By - PE
46a61941-0f49-5cc4-9374-0f3efcb3d89f | checkpoint | 4.30.05 - Mix Design Approval
9e29d9e5-9fec-583b-a697-588dc02cc1d0 | note | Acceptance / Conformance Criteria - The Contractor’s mix design shall be assessed by the Engineer for compliance with the requirements of this specification including a production trial, job mix formula, and be currently Validated. The Engineer’s approval of the mix design is a prerequisite for its use.
40713bc3-7fdc-513b-a603-17130ad99f66 | note | Standard / Specification - PS 21.3.1 NZTA M27:2020 - 3.1 , 3.6
2622cd54-e1d6-5567-a02c-3151db9bbafc | note | Verifying Document - Approved Mix Design
bada1d7b-f14d-5b52-80a3-8bfb675249e8 | note | Frequency - Prior to Use
c8608fad-996d-5934-b26f-0e5f518e4ce3 | note | Verification Activity: Activity - HP
ce538261-e238-55ed-a136-a6d0cda6ee67 | note | Verification Activity: By - ENG
f1280a95-c783-5daf-9f62-cb9f12c6e95e | signoff | AUTHORITY HOLDPOINT
2b43b80f-ded8-55a7-8d16-c45f3a9c0841 | section | 4.31 Tack Coating Materials
ae972a0d-7b4c-55e1-ba25-7f025670b1ad | checkpoint | 4.31.01 - Bitumen - Quality Testing
ad388c5f-35da-58b1-851c-439bfed0944c | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
59cad7b5-d000-54b3-8df7-f828827a5cdd | note | Standard / Specification - NZTA M01: 2022 - 6
98c7329b-96df-5ab9-9992-ee2d3449a9c7 | note | Verifying Document - IANZ Lab Reports
12ddbae4-a6c8-57d6-9c28-8f15745df60b | note | Frequency - One test per grade supplied
753877d3-b073-5969-8f71-e053e45546c1 | note | Verification Activity: Activity - R
3ed0eb29-9392-5389-b92e-e85925bd20f9 | note | Verification Activity: By - SE
4b8b3e3f-abfb-552c-8b9a-d02e9d221fa8 | section | 4.32 Sealing Chip Supply
dc0bdfbb-dcfe-5f1b-864a-6564086b5926 | checkpoint | 4.32.01 - Sealing Chip - Source Property Tests and Sampling
82b9a9df-0b41-588c-9575-4738ee2047f2 | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
3fae47ed-4e98-544d-b610-781f1e3b134a | note | Standard / Specification - PS 21.1.1 TNZ M/6: 2019 - 4
11cc3479-d0aa-5991-be3c-f410c343b802 | note | Verifying Document - IANZ Lab Reports
5d9d407d-9745-5642-810f-3ad2847c9892 | note | Frequency - Before Supply and Every 10,000m3 Thereafter
925c7e3b-11fc-5768-baf8-7a6f5ecf875c | note | Verification Activity: Activity - R
811efc43-cc87-5509-8818-0f001cdfa039 | note | Verification Activity: By - SE
1f20e1cc-10ba-5a77-a90a-b033f90a4508 | checkpoint | 4.32.01 - Sealing Chip - Production Property Test Sampling
d51bdca6-62a1-57ee-952a-2e0199f44fc2 | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
2df8206c-6ba8-5d2d-92b7-28f03f380cdc | note | Standard / Specification - PS 21.1.1 TNZ M/6: 2019 - 5
c908213b-343c-5581-acb3-d9e26e9b72dd | note | Verifying Document - IANZ Lab Reports
e8d10b83-57f5-5aac-b16f-d279734723fb | note | Frequency - Every 500m3
6c527124-5a6b-5ef3-aca9-ad73e4e62d2e | note | Verification Activity: Activity - R
638b3646-4c45-5bc1-be78-291a2e59346b | note | Verification Activity: By - SE
ba197f5f-8424-5ec1-a3d9-dadedbf26007 | section | 4.33 Bitumen Supply
1c072438-aaf9-58a3-9d3f-4562dc4413df | checkpoint | 4.33.01 - Bitumen - Quality Testing
e1e1657d-79a2-579c-934d-fae225abc59e | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
21f4663a-7e37-59d9-8808-8ee75754bf87 | note | Standard / Specification - PS 21.1.1 NZTA M01: 2022 - 6
0fd05c94-cf73-537b-9cd6-85505bb999f8 | note | Verifying Document - IANZ Lab Reports
c20c3e73-a436-5575-8183-f3f8e864b753 | note | Frequency - One test per grade supplied
54dd5d86-903e-575c-8492-3e2a973704c8 | note | Verification Activity: Activity - R
6fa5636c-e371-5786-848b-95c7f6d66f26 | note | Verification Activity: By - SE
2e0b4d70-3e4a-54f0-9c3c-db969a116315 | checkpoint | 4.33.02 - Bitumen - Supply Testing
732a614e-aa58-5838-8786-3af7d9628309 | note | Acceptance / Conformance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
6bd717d6-ece5-5886-9fee-bad5bfe895a2 | note | Standard / Specification - PS 21.1.1 NZTA Q05: 2022 - 6.2
8818d281-a831-574c-b8a2-42abbc834185 | note | Verifying Document - IANZ Lab Reports
cfb4382c-7841-5d6e-ad0e-72d1da6a3434 | note | Frequency - Every 200 tonnes supplied.
e24c0feb-3538-5091-b4a1-500112af968b | note | Verification Activity: Activity - R
c725102d-d179-5376-9ec8-0a83fd1d7d55 | note | Verification Activity: By - SE
2b18b70e-b064-539a-bbe2-652876ead08a | checkpoint | 4.33.03 - Adhesion Agents
91125f69-3fc6-5685-8b8c-b597a9cf3f73 | note | Acceptance / Conformance Criteria - When used, Adhesion agents must be approved & blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents.
9cd6e57b-00b0-5926-802e-18ff7560bf8e | note | Standard / Specification - TNZ M13
56024763-74c0-5906-b7e8-d03880d84b3b | note | Verifying Document - Binder Aggregate Adhesion Test
b2aa1be1-7dd5-5b25-a83b-29cb9920e857 | note | Frequency - Each Adhesion Agent and Dosage Rate for a Particular Chip Source
8989ce4b-7d21-59c1-888c-e9c8361f010e | note | Verification Activity: Activity - R
5aa33a9b-7ab8-5fa8-8e03-6976c0a6fe93 | note | Verification Activity: By - SE
8f4bd0a5-2c00-5e11-be9d-a8061092d736 | checkpoint | 4.33.04 - Sprayer Certification
dda25e4d-4897-5f7b-897b-75c5ba3ca077 | note | Acceptance / Conformance Criteria - The binder shall be applied with a bitumen distributor, operated in accordance with BCA E/2, Specification for Performance of Bitumen Distributors administered by the New Zealand Bitumen Contractors' Association Inc.
a9f66d89-6015-5f99-9e2e-421dc138aaba | note | Standard / Specification - TNZ P3 TNZ P4
0be7d80e-8e14-5349-8c19-b64bb20ab682 | note | Verifying Document - E2 Cert
d39da271-57b1-5582-b931-3d749f8e0841 | note | Frequency - Each Sprayer
851e0625-acd2-5d94-a134-ea841fca7f19 | note | Verification Activity: Activity - R
10905a45-60fb-5fe5-8dad-38d3855ac152 | note | Verification Activity: By - SE
02958b5a-5ebd-51c0-9468-f8abb27c9de0 | section | 4.34 Hi-Lab 65 Material Pavement Type A,B
eb562677-ae1e-56c0-bd1e-78ae996a097d | checkpoint | Hi-Lab 65 - Source Properties
b2f1406a-69a6-5409-8249-afcf794f7e62 | note | Acceptance / Conformance Criteria - The Hi-Lab aggregate shall be crushed from quarried rock and consist of hard, sound material of uniform quality, free from soft or disintegrated stone or other deleterious material.
d535dfe4-2881-52f7-8274-5e12c197a561 | note | ○ Source property testing shall beOnly one set is needed if HI-LAB40 and 65 come for the same source
197cb8c4-5bbe-54ad-b3b3-2f7fa6fc359a | note | Standard / Specification - NZTA B10 - 2.2.1, 2.3.5
8c2e8960-d1cb-5a93-83fa-225bfd24b5bc | note | Verifying Document - IANZ Lab Reports
6193efa2-e65a-5b72-9212-f1eebd534984 | note | Frequency - One test for every 10,000m³
4f37141b-7c87-5980-9756-d9ad394a0f4e | note | Verification Activity: Activity - HP
c3d251c6-bb92-5924-9424-0c14d0bda063 | note | Verification Activity: By - ENG
6e353bb2-bbdb-5f33-9e07-0646c75fc100 | signoff | AUTHORITY HOLDPOINT
61903216-c0dd-5e21-a86d-90ca29993957 | checkpoint | 4.34.01 - Crushing Resistance
95fbacc8-d364-5bef-967c-008a14602389 | note | Acceptance / Conformance Criteria - < 10% Fines @ 160kN
86363671-17f4-55fe-95aa-be58a9359c6c | note | Standard / Specification - NZS 4407 Test 3.10
4b2629e1-89bc-5bf7-b900-5250074b074e | note | Verifying Document - IANZ Lab Reports
021b587b-5698-548a-892e-7ca026187452 | note | Frequency - One test for every 10,000m³
1d0ee483-13c1-5934-9c81-c08f9a552e02 | note | Verification Activity: Activity - HP
6d7cf7d1-8189-5ac2-bd17-5e0479e9b255 | note | Verification Activity: By - ENG
fc856423-920e-52d6-b8e8-de27efbc3b57 | signoff | AUTHORITY HOLDPOINT
87b037ab-6c0c-5548-bce2-ad9c4565bfff | checkpoint | 4.34.02 - Weathering Quality Index
84bfd323-f72c-57be-98bc-e2da0f0c99cf | note | Acceptance / Conformance Criteria - AA, AB, AC, BA, BB or CA
e0075307-a79e-598f-ac83-0a6b7b5ed7e2 | note | Standard / Specification - NZS 4407 Test 3.11
28268867-5253-55c4-bbd0-cb0773647a37 | note | Verifying Document - IANZ Lab Reports
125d40e3-f0d2-5324-9141-83d881c07074 | note | Frequency - One test for every 10,000m³
2c200020-2498-5d55-9f8e-d3764d62405c | note | Verification Activity: Activity - HP
e33d4f2f-c576-59b4-9929-384cd026ad84 | note | Verification Activity: By - ENG
de152f62-5b10-59c9-89b9-6d9b0f8a3728 | signoff | AUTHORITY HOLDPOINT
bdc4a671-9f50-59cb-8327-92a910c7b3ed | checkpoint | 4.34.03 - Ethylene Glycol Accelerated Weathering
9eee3673-c0f6-53ad-86c7-9ed9d2036c86 | note | Acceptance / Conformance Criteria - Proportional change < 30%
7252a5f1-a220-5a18-bcf0-da9087e6fb24 | note | ○ Note: If the result for the source rock exceeds 30%, further testing to detect the presence of smectite clays shall be carried out using X-ray diffraction. If the aggregate is shown contain trace amounts only of smectite clays (i.e. XRD <100 counts) then the source rock may be considered compliant with this criterion
f6f31cca-ecc3-5b75-a097-68e0a766c367 | note | Standard / Specification - NZTA T20
140be1a4-ad75-5485-b615-e6bdeab08d70 | note | Verifying Document - IANZ Lab Reports
af4ee437-c0da-58ff-ae14-7e6e051455c3 | note | Frequency - One test for every 10,000m³
fc222b4c-ac5f-56fa-a616-ea74fb6dcc73 | note | Verification Activity: Activity - HP
02efddfa-bc8c-5770-b601-2f1a4db56679 | note | Verification Activity: By - ENG
60483818-a26b-559d-881f-107b3f615916 | signoff | AUTHORITY HOLDPOINT
d6bd15eb-c4ba-582e-9ed1-0d37a77f1680 | checkpoint | 4.34.04 - Solid Density
9a2581b2-e318-5650-acb7-23964d08a3b5 | note | Acceptance / Conformance Criteria - The solid density of the Hi-Lab shall be determined in accordance with NZS 4407 Test 3.7.1 Solid Density of Aggregate Particles.
e489411e-85e6-5e70-8eb0-bd72e7dd5133 | note | Standard / Specification - NZS 4407 Test 3.7.1 Solid Density of Aggregate Particles
76d3b277-7ac4-5dd3-afd3-53f18ce899ff | note | Verifying Document - IANZ Lab Reports
208e68b3-f284-5be7-82c2-531a25deca5f | note | Frequency - Two tests per aggregate source then one test every 5,000m³
b9f6600c-bf2d-5504-bb27-72b54fc39335 | note | Verification Activity: Activity - HP
d7645033-6656-56c1-a110-1756eadc5090 | note | Verification Activity: By - ENG
89797393-33cd-5c65-811c-af4a28f5adcd | signoff | AUTHORITY HOLDPOINT
01cecd36-b7d4-59e8-91ab-257e38deed9e | checkpoint | Hi-Lab 65 - Production Properties
c24aa2be-3b48-5da3-813e-0b3698274c62 | note | Acceptance / Conformance Criteria - The Hi-Lab 65 shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fines, Broken Faces, Aggregate Flakiness Value, and Grading.
225abc26-1c97-5653-a322-3e3a57449cbe | note | Standard / Specification - NZTA B10 - 1.2.1
b258b3ed-6d48-5686-86a8-b69b6cca8c90 | note | Verifying Document - IANZ Lab Reports
9dfa004f-6d68-5930-be22-a02a41597760 | note | Frequency - Test for every 1,000 tonnes of material produced
4e4ca129-a73b-5ee0-90a7-a0aeba8faf91 | note | Verification Activity: Activity - HP
ca045907-02e1-52d3-b965-b523db959826 | note | Verification Activity: By - ENG
e45073ec-9dfb-51b2-994a-d676e493f6d9 | signoff | AUTHORITY HOLDPOINT
876700e5-1191-52be-9306-0c485e04dcd9 | checkpoint | 4.34.05 - Two Broken Faces
791db397-e4e6-505f-91b4-4a77ed95a1c3 | note | Acceptance / Conformance Criteria - 100% of sample
d171a8d3-f0c4-5957-93e3-14e49d126377 | note | ○ Note: Hi-Lab aggregate produced from a hard rock quarry source using angular and broken feedstock need not be tested for Broken Faces Content which may be assumed to be 100%.
692d529d-94dc-58b2-b297-cc55659b70ba | note | Standard / Specification - NZS 4407 Test 3.14
19caeb25-68e7-5dc6-bb8f-119cbe98c2b2 | note | Verifying Document - IANZ Lab Reports
18fb10b1-4127-5cdf-bae6-3c534bc67bc4 | note | Frequency - Test for every 1,000 tonnes of material produced
6e57703d-f56b-598e-aa91-cc582abeb350 | note | Verification Activity: Activity - HP
46af81a6-50ef-54aa-b9a0-887097f6d379 | note | Verification Activity: By - ENG
11251e42-cd63-5327-aa50-91a778eb7470 | signoff | AUTHORITY HOLDPOINT
14002a20-d1c2-52a2-8760-f52bec35d8aa | checkpoint | 4.34.06 - Clay Index (<0.075mm)
5bc9dca7-29d5-5def-a3e9-570c8eb5ae76 | note | Acceptance / Conformance Criteria - 5 maximum
5679d6c1-d26a-5eee-a6eb-eb472c5bf6ac | note | Standard / Specification - NZS 4407 Test 3.5
bea09bbf-fc22-5200-9165-5159916b9e38 | note | Verifying Document - IANZ Lab Reports
b5cf3bfd-2292-5ed4-ad39-992e63313e6b | note | Frequency - Test for every 1,000 tonnes of material produced
108ee858-a99f-56e8-998f-dc9db44bef9e | note | Verification Activity: Activity - HP
64ad4d07-9736-5356-b27b-799ddcb10d40 | note | Verification Activity: By - ENG
450b6635-c172-5d7b-b30e-beb1caa7d328 | signoff | AUTHORITY HOLDPOINT
524842e9-73e1-57e7-9c9a-aedde973bfe5 | checkpoint | 4.34.07 - Plasticity Index
10b91100-e926-5e3d-9675-123b0ecb4bed | note | Acceptance / Conformance Criteria - 8 maximum
be1358b2-3a83-589d-b802-86a2c8408185 | note | Standard / Specification - NZS 4407 Test
146affaf-7b9c-5a96-9c08-7f5d3463439d | note | Verifying Document - IANZ Lab Reports
24a3f1dd-b97f-5b67-a2cc-e2aaa5b31885 | note | Frequency - Test for every 1,000 tonnes of material produced
868de516-9444-5886-ba3e-bb3e1643deac | note | Verification Activity: Activity - HP
6ec8c718-707e-5a39-8b22-877f4ef9e7d5 | note | Verification Activity: By - ENG
8767007b-5c90-5d39-a992-fc122ea9e108 | signoff | AUTHORITY HOLDPOINT
9a11aa9c-cddd-56da-8583-505da547064e | checkpoint | 4.34.08 - Aggregate Particle Size Distribution
d298569a-1e14-5f81-a68e-f2ba45215dcc | note | Acceptance / Conformance Criteria - The particle size distribution during production of the blended Hi-Lab products shall comply with the limits in Table 0.3.
b479058a-6aa4-596b-a9de-b08605d97df1 | note | ○ A minimum sample of 90kg of aggregate shall be used for each test.
4b184fa4-2cee-53ba-be84-5cf1229f43cb | note | Test results shall be evaluated as follows:
d39365a7-7284-58e2-927d-5437db226c53 | note | (a) The rolling average results of five consecutive test samples shall be within the upper and lower limits for each test sieve
b186dd07-a6cd-5335-9b1f-e16b3e4ce08e | note | (b) No individual test result shall be outside the envelope formed by the lower buffer zone and the upper limit.
fdc7b7df-3475-5c6d-b201-76222ef25581 | note | ○ Note: Experience has shown that a blending plant with a minimum of three component feed bins is required to produce a consistently compliant Hi-Lab aggregate product.
b7d7249e-ebe1-534a-a937-5ef12518f61d | note | – – – – – – – – – – – – – –
967d394d-69fe-53e3-ab95-8af3e55aaa6c | note | Table 0.3 Hi-Lab 65 Particle Size Distribution Limits
ff7d1e69-cff6-570e-afb9-16243c42c3a1 | note | Sieve Size (mm) ¦¦ Lower Buffer / Lower Limit / Upper Limit
696f2a6d-ab2c-5362-a05c-290c78021586 | note | – – – – – – – – – – – – – –
4be27169-4234-5e7f-bb9b-fe2a6824d5b3 | note | 63.0 ¦¦ - / 95 / 100
0f50976a-ee6f-5ef9-9109-bf557c4a37a5 | note | 37.5 ¦¦ 35 / 40 / 50
9afdd379-50c1-564c-8d63-de4112699a5d | note | 19 ¦¦ 15 / 20 / 30
3423e552-c90a-5d0c-a3c1-ad381fcdde50 | note | 9.5 ¦¦ 10 / 12 / 16
73421d5d-a162-5a66-bd43-79854a74a023 | note | 4.75 ¦¦ 9 / 10 / 14
105ea7a3-7acb-5d42-85f1-63edba319ef6 | note | 2.36 ¦¦ 6 / 7 / 12
95a1dae0-5d4a-5327-8441-68839e1ff007 | note | 1.18 ¦¦ 4 / 5 / 10
de3aca86-caaf-557a-a749-90251b38c78d | note | 0.075 ¦¦ - / 0 / 6
91ddbe3e-1d9c-5622-8c72-e4775893992b | note | – – – – – – – – – – – – – –
2633d40b-02bb-5033-bce0-b9a05590eac6 | note | Standard / Specification - NZS 4407 Test 3.8.2
8eb1d3ac-54cb-5a31-bcf1-bdaaa3537a06 | note | Verifying Document - IANZ Lab Reports
3bfe56c8-3505-51cd-b01a-137bdb9cf0bc | note | Frequency - Test samples shall be drawn and tested for every 1,000 tonnes produced. A minimum of 5 production test samples shall be drawn and tested for any one production lot.
daa71d3a-05ea-530f-b4f6-d3c7a9aebafb | note | Verification Activity: Activity - HP
5e52ba74-9788-59d2-bc44-d573522cb18c | note | Verification Activity: By - ENG
e3454e63-b504-57ae-83a2-92c59c58fa01 | signoff | AUTHORITY HOLDPOINT
690d9740-fbd2-59ff-9863-e3cb2335f32f | checkpoint | 4.34.09 - Aggregate Flakiness Value
7711dddd-e57a-5aa3-98e9-2dc17da4f026 | note | Acceptance / Conformance Criteria - The percentage of flaky particles for each of the aggregate test fractions coarser than 9.50mm specified by AS 1141.15 Table 1 shall be determined and reported, and the Flakiness Value for each size fraction comply with the minimum requirement of Table 0.5:
aa378c1c-07c4-5f9a-b37e-764009c10301 | note | – – – – – – – – – – – – – –
6169527e-8a69-5ecb-99ea-d616deeae350 | note | Table 0.5 Aggregate Flakiness Value Requirement for Each Fraction
3490544e-facf-5e2f-81f2-0b46cddba266 | note | Aggregate Grade ¦¦ Test Method ¦¦ Requirement
580dcff4-9935-5418-b7e7-3297346e251f | note | – – – – – – – – – – – – – –
522db386-f8bf-5bb3-9351-fb8c72147a7e | note | Hi Lab 65 ¦¦ AS 1141.15 ¦¦ < 30%
e53be5d5-de01-5790-bb36-32833166c3b0 | note | Hi-Lab 40 ¦¦ AS 1141.15 ¦¦ < 30%
624433a7-6893-57fd-93b4-b36b4da5648d | note | – – – – – – – – – – – – – –
eb0b7ebf-e53f-5fe5-ae25-a6d57a6a16cb | note | Standard / Specification - Method of AS 1141.15
5a8b9887-61ca-5e70-afd0-9a99b220dab7 | note | Verifying Document - IANZ Lab Reports
50ad338b-cc59-5da4-bec6-6ef6faa41083 | note | Verification Activity: Activity - HP
71300b74-998d-5e16-a0e3-4d2b2fbee08b | note | Verification Activity: By - ENG
4d96f701-0a5c-5590-ae84-8f653cbc2bec | signoff | AUTHORITY HOLDPOINT
c4741654-e2c2-58e5-9d21-98ad26ac307b | section | 4.36 Hi-Lab General Material (Pavement Type A,B)
3785bf16-ad90-5eee-b6f5-dc77d4773dc0 | checkpoint | 4.36.01 - Portland Cement Stabilising Agent
bff48a57-5454-5b1e-8f91-f17302cf0e36 | note | Acceptance / Conformance Criteria - Cement shall comply with NZS 3122 Specification for Portland and blended cements (general and special purpose) for GP, GB, LH
ce97cd43-ce9e-532d-b4bf-3c4ca9cc803d | note | ○ General purpose Portland cement, type GP, shall be used unless otherwise specified in the Contract Documents. Note that high-early strength cement, type HE, shall not be used as a stabilising agent.
04e34c7e-41dd-5466-a621-b1a22bfde07e | note | Standard / Specification - NZTA B10 - 2.4.1
0e645766-122b-541e-9ee2-112cc31a8b70 | note | Verifying Document - Datasheet
525c1c18-7a7e-510c-a7de-5636305d096a | note | Frequency - Prior to Use
34f57ff4-f499-5c51-b364-0afd7ed59d23 | note | Verification Activity: Activity - R
b58ccae3-3d70-565c-ae9c-f6d9bcc43dda | note | Verification Activity: By - SE
c1b7ac1d-1776-50c9-bde2-bed2b9423232 | checkpoint | 4.36.02 - Water Supply
2b441536-c914-5a0c-9ef1-eed48b317905 | note | Acceptance / Conformance Criteria - The Contractor shall be responsible for ensuring that the water for stabilisation, construction and curing of stabilised layers is free from impurities that may deleteriously affect the setting, hardening or strength of the stabilised material. Water from sources other than public supply shall have its suitability established to the satisfaction of the Engineer.
a26e2ae1-ba0d-5aab-adcd-181a42be240d | note | Standard / Specification - NZTA B10 - 2.4.2
80592b6c-1289-5467-b23e-1d1d20dec8ed | note | Verifying Document - Site Records
5d2aa0f9-f9ea-5a8d-9804-b0c4901e4b51 | note | Frequency - Prior to Use
ad043ba0-b123-5e59-a6ed-7f8f971b1f92 | note | Verification Activity: Activity - R
caf3fcef-f56e-5836-943f-7b4ac3e419d0 | note | Verification Activity: By - SE
45233c43-9bac-5fb3-b4ab-289322865089 | checkpoint | 4.36.03 - PAP 7 - Choking Aggregate
49f5ccc8-dfd3-54b3-872f-5c01441fb314 | note | Acceptance / Conformance Criteria - PAP 7 crusher dust choking aggregate can be a by-product of the Hi-Lab crushing or sealing chip production with all passing the 9.5mm sieve. The aggregate source properties (crushing resistance and quality of fines) shall be equal to or better than the required source properties for Hi-Lab aggregate.
ebd9753f-8da9-55e4-83b9-2f658e32470c | note | Standard / Specification - NZTA B10 - 2.3.6
3eafd0fb-4de4-53be-bf31-13ad7ab65808 | note | Verifying Document - IANZ Lab Reports
31bda933-2fce-547d-9d65-ff6bd7cefe05 | note | Frequency - Test for every 1,000 tonnes of material produced
0cb1e0ba-57bf-59ab-b94e-cf7ec7f5196e | note | Verification Activity: Activity - R
157a645b-59c7-506e-a5c7-fd230337d3e6 | note | Verification Activity: By - SE
5c06996c-2bca-59b6-9169-db0320db268e | section | 13.01 Triaxial Geogrid
99b55b72-d146-5ae8-b0fc-f76fd148b574 | checkpoint | 13.01.01 - Triaxial Geogrid storage and Inspection
2bbec92d-5608-5ec6-a2cf-3a62db96626f | note | Acceptance / Conformance Criteria - The geogrid is to be checked once delivered to site to confirm there is no damage that may effect its performance. The material shall be stored out of direct sunlight to ensure no degradation of the material occurs prior to installation.
e89529cb-f94b-5741-bfbe-6712efdff3e9 | note | Standard / Specification - PS 20.3.1
7ce5a204-b35f-57fb-8f89-925e13a36354 | note | Verifying Document - Site Records
ba0c9adc-8ede-5a90-b7da-7838d6fd378c | note | Frequency - Prior to use
8af66184-ecfb-5d4f-8d4f-4700bc1111e3 | note | Verification Activity: Activity - R
16fcc9a6-d749-56eb-8e6e-3547623583f2 | note | Verification Activity: By - PE
8d8dfff0-e687-5803-92af-8df0ca82d843 | checkpoint | 13.01.02 - Triaxial Geogrid Installation
9116712a-94a2-510e-91de-3df88662413d | note | Acceptance / Conformance Criteria - The triaxial grid is to be installed in accordance with the manufacturer’s specification. Where overlaps are required they shall confirm with the manufacturers installation specification.
911d0966-3f83-5e2c-abb7-68f7e7566959 | note | Standard / Specification - PS 20.3.1
aa1f968b-dbab-502d-a410-88d5d0519b8e | note | Verifying Document - Site Records
5004b2d3-c5dc-5788-87b4-7e30eac70890 | note | Frequency - During Installation
9a68cb93-7f30-538a-a733-7c067b787075 | note | Verification Activity: Activity - R
739f7ec5-5487-52ea-b4c5-9bc47f5d941b | note | Verification Activity: By - PE
80572c52-4639-5317-a3b8-448a7a44836e | section | 13.02 AP65 Subgrade Improvement Layer Pavement Type A,B,C
34462ba7-0596-5d92-aa44-3f4c0644d233 | checkpoint | 13.02.01 - Material Placement
a9ae0c80-811d-5f37-9dd5-fbf5f09edfe4 | note | Acceptance / Conformance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout
21b4140b-75dc-54af-bf74-006a6f29f649 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 5.1
9a043036-256e-57f8-a15a-15fd099d1f8a | note | Verifying Document - Survey / Level Checks
cddeed54-00ac-5d10-8675-1465b7e5996a | note | Frequency - Continuous monitoring.
d6049dec-89c5-5f97-91aa-70b19aacfb8e | note | Verification Activity: Activity - I
170a241d-2836-55ad-9742-fc72f2632842 | note | Verification Activity: By - SV / PE
c086377c-d141-5896-83ea-ffd0f27d9116 | checkpoint | 13.02.02 - Plateau Density Tests
093376ec-2a4a-5ca6-9dff-ff3750702a7a | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC.
1f9eda07-80e9-5ebc-b36a-9e23cb403b45 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
4e07b800-ad23-533b-8ca5-28aba15c5ceb | note | Verifying Document - MDD and Plateau Reports
699cf3e1-8f32-580c-a27f-c47e49993b47 | note | Frequency - 1 test per 5,000m2
44d11602-246a-537b-a3e2-9806c0a9dfe7 | note | Verification Activity: Activity - HP
aef10c52-5a5a-5061-8af4-41b552558aaf | note | Verification Activity: By - ENG
6c3d2e59-f982-5043-85a7-0aa2242113a2 | signoff | AUTHORITY HOLDPOINT
2eecc68a-d5d8-574a-a2f9-42b62be6259d | checkpoint | 13.02.03 - SIL Pavement Layer Compaction
886fb3c9-4234-57ce-891f-c38be85c8a0a | note | Acceptance / Conformance Criteria - The compaction density for the lower layers must be at least 81% of aggregate Solid Density. The nuclear gauge in direct transmission is used for reporting in-situ density.
3e17e954-be98-51c6-a101-2ca6a30e3280 | note | Standard / Specification - NZTA B10 Notes
aef5188e-7b7e-5906-877b-22d4e4664771 | note | Verifying Document - NDM Report
2cbe1248-35ae-5973-89b7-91f54a443db1 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
fec41c69-9ba6-59f7-852f-e660fc95104a | note | Verification Activity: Activity - HP
29fa2380-0ddb-5f3c-8241-034eefe3f900 | note | Verification Activity: By - ENG
5d2a9c4f-9fb9-5fe3-878d-95a7bdaf77d8 | signoff | AUTHORITY HOLDPOINT
66c2b306-e56b-52a2-92a0-2f3a73a7833b | checkpoint | 13.02.04 - SIL Layer thickness.
e469ce29-fdbb-5ba0-b02b-bea8977407d5 | note | Acceptance / Conformance Criteria - The SIL layer shall be monitored for Layer thickness.
d7707e2e-b4ee-5818-ad87-abca2b15d27b | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
6d5bffde-027b-5449-8129-8d1b3c1cfe8b | note | Verifying Document - Survey / Level Checks
6a741fd4-b4b6-52f8-82a4-492a6f6ae71a | note | Frequency - 1 test per 20m
7dda900b-d319-56d9-8765-9e2090c97054 | note | Verification Activity: Activity - W
4c1eb75e-eddb-5e0f-a605-474f0638a0f1 | note | Verification Activity: By - SV / PE
793a5b8f-1431-5d59-b0d5-57842aca4233 | checkpoint | 13.02.05 - Surface Shape
a597a4e3-9e3b-5139-9346-ba0ab7655e81 | note | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.
4b23acb6-e5b1-5aae-bae9-36cbf4403564 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
fdf63230-60d0-53d3-b547-01ca2a1bb037 | note | Verifying Document - Survey / Straight edge Report
04020970-2528-55fd-bc8e-8686aa6617ca | note | Frequency - Prior to sealing
4d924158-315e-5576-a915-f8de3fd578e8 | note | Verification Activity: Activity - I
785044e8-ae3b-5541-b851-3dc7ac0d9409 | note | Verification Activity: By - SV / PE
e3a25849-16b3-5921-a3ae-953690edba8a | checkpoint | 13.02.06 - Holding Water
4cbca33b-5cfc-591b-95d1-af49b6418b43 | note | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
e93d5acc-df89-52af-aed6-14f0b314a0c4 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
03c184fc-666e-59ee-b637-47897e5fe0a2 | note | Verifying Document - Survey
bb20c48b-cda5-5427-92bf-53dd085e05f4 | note | Frequency - Prior to sealing
ea2b7862-5fa7-5da6-8d8e-286231cd3c95 | note | Verification Activity: Activity - I
050f3455-1ed2-5675-84c5-60da813b9694 | note | Verification Activity: By - SV / PE
ae8a2da6-e5fd-5e94-827d-5579c23340f6 | checkpoint | 13.02.07 - Proof Rolling
69896ce4-39bb-5eef-b746-3888339f550e | note | Acceptance / Conformance Criteria - SIL layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass.
7b1f2c99-ea96-5714-a481-de028d1da1b4 | note | Standard / Specification - PS 20.5.2.2
06790094-8850-55a4-b497-0cdada4a1bd0 | note | Verifying Document - Site Records
f0ecbbe8-a3e1-5267-8247-1e910f10d502 | note | Frequency - Before proceeding with works
d70a4043-9c8f-510b-bd63-b2a2dcb23892 | note | Verification Activity: Activity - HP
d6be5d08-d3ce-50ba-b6d0-45aef02e755b | note | Verification Activity: By - ENG
9d203b5d-2a33-519b-a6fd-88f1e7ac7540 | signoff | AUTHORITY HOLDPOINT
c6646e17-3b34-5db0-a14d-c6780c356c80 | checkpoint | 13.02.08 - Benkelman Beam
58baeb5c-5260-51c0-bd2e-cb45fe4d7031 | note | Acceptance / Conformance Criteria - be ˂ 1.5mm (95th%) and max ≤1.8mm
6ec7f474-d84d-5cfb-afeb-7832c84e8e7a | note | Standard / Specification - B10 Notes
5d2cd522-7b86-55af-add3-685065d50ab7 | note | Verifying Document - Report
63876cca-dd5b-5696-aa3f-6802a88aff41 | note | Frequency - All Lanes
47ba5c0a-92d7-5722-98de-ffd363246e8d | note | Verification Activity: Activity - R
2b5d8829-62a2-5404-b45e-9a88ea0acb54 | note | Verification Activity: By - SE
32bd79f6-98db-5025-bd0d-dbc869fd9c5d | section | 13.04 Hi-Lab Plant and Staff
21d614b8-ae0e-5bea-bbb6-6ccdc98559ee | checkpoint | 13.04.01 - Plant for Supply of Cement
0239f5dc-4bb6-5eaa-bbc6-1ab28e9ae91e | note | Acceptance / Conformance Criteria - For areas greater than 500m², cement shall be delivered to the site in purpose built bulk tankers unless otherwise approved by the Engineer. Each bulk tanker shall be issued a Certificate of Loading that contains the following information which shall form part of the project quality plan.
4d0928d5-f108-5ab4-ac12-81306d2344ce | note | Standard / Specification - NZTA B10 - 3.1
8eee6329-4a1b-5ee7-9700-c8506b2148b3 | note | Verifying Document - Certificate of Loading
57702c7a-c481-5930-be25-b7d5fe816a06 | note | Frequency - Each Tanker For areas greater than 500m²
a3938f08-1f42-59d4-af5d-93ce7e0c23e4 | note | Verification Activity: Activity - R
944acd7e-a673-5c6d-a69b-5c18fb7770d7 | note | Verification Activity: By - SE
904cfb36-9b72-5214-88e7-5984f5bbc3ed | checkpoint | 13.04.02 - Plant for Spreading Chemical Stabilising Agents
997610a5-de6f-5e15-ab9f-64d7e5f6031e | note | Acceptance / Conformance Criteria - The spreading equipment shall be capable of varying the spread width to cater for different road widths. The spread rate should be consistent along the spread width of the equipment.
60afd910-e85a-5a39-8f6b-223bc7b8d510 | note | Standard / Specification - NZTA B10 - 3.2
1c3d20eb-91e6-5be2-a278-3f493eb1abcc | note | Verifying Document - Methodology
e0a8333b-70f3-5e72-81fa-fa1d1d08b2cb | note | Frequency - Prior to Works
108fba11-1fbb-55bb-96bf-a31dd5bb583f | note | Verification Activity: Activity - R
935a155a-d500-5b40-9c7a-6fb2ba41f61a | note | Verification Activity: By - SE
2c51062a-faa0-56c2-abd3-673b934077a0 | checkpoint | 13.04.03 - Plant for Stabilisation Process
a881e21d-55bc-5297-8d4f-634a4bbeed4d | note | Acceptance / Conformance Criteria - The plant used for the mixing shall be a purpose-built recycling machine. It shall be from a reputable manufacturer having a demonstrable track record and manufacturing history for the equipment used.
32694a5c-d7ed-5db6-a9c8-6bc3587ff4eb | note | Standard / Specification - NZTA B10 - 3.3
29373c80-ee37-5436-af35-f290232db389 | note | Verifying Document - Methodology
5f770ca1-2f99-518a-8a98-29dfdbf8354e | note | Frequency - Prior to Works
a7e72e14-5ae6-5d4c-9031-77cf2e137c38 | note | Verification Activity: Activity - R
d539d98d-381f-5d44-ba25-bb9c5d94040c | note | Verification Activity: By - SE
efc111f7-b676-5e52-a35f-cb1de6c8f7cb | checkpoint | 13.04.04 - Primary Compaction Equipment
3766ac32-2f3a-5656-ac7d-832889e07e13 | note | Acceptance / Conformance Criteria - A steel drum roller (i.e. having a smooth drum) is required for the initial placement of aggregate. The roller shall have a gross weight of at least 12 tonnes. For primary compaction, the Contractor shall use GPS control to ensure all areas of the pavement receive the required number of passes with each type of roller.
60c7b6e4-d239-551c-a03f-e0e5f8dee59a | note | Standard / Specification - NZTA B10 - 3.4
d91dc6b7-2e30-5fec-8a2d-7dffd339c8cb | note | Verifying Document - Methodology
e7742e9a-3441-53b5-833e-ed0e9d42f96c | note | Frequency - Prior to Works
a87264ac-3652-5807-ab4f-b800084a9344 | note | Verification Activity: Activity - R
b1e078fb-b1c0-55e0-903f-da48578930a3 | note | Verification Activity: By - SE
5fef0619-d2ca-5729-b448-ab9ec6eb184f | checkpoint | 13.04.05 - Personnel Training and Experience
fcc4a9fd-69bc-5f49-8995-b53a9d0ad5f9 | note | Acceptance / Conformance Criteria - The Contractor shall submit a list of such personnel to the Engineer for approval. Where approved personnel are not available the Contractor shall cease operations.
48ced155-36eb-5a73-90dd-0040f713ec98 | note | Standard / Specification - NZTA B10 - 4.2
73f86c9c-60a2-52f9-81ba-5c9dfb1eb25f | note | Verifying Document - Methodology
33a11344-a3a3-5f54-a07f-85f374b963b8 | note | Frequency - Prior to Works
1c09cb8f-f795-5399-a130-cc0061c00536 | note | Verification Activity: Activity - HP
07fbc22c-876b-5acc-847f-6d7154e5c662 | note | Verification Activity: By - ENG
1ec346a4-5991-5ee9-a97c-cd1c95e68e51 | signoff | AUTHORITY HOLDPOINT
6a6fd14f-b31e-57ab-8db5-2ef2b7dcc479 | section | 13.05 Hi-Lab Pavement Trial
614077d6-2d9e-5e0f-b4ed-962af8821086 | checkpoint | 13.05.01 - Pavement Trial
769cbac5-e4ea-5594-98d2-18b35acdafb7 | note | Acceptance / Conformance Criteria - The Constructor shall construct a pavement test trial of Hi-Lab sub-base and basecourse pavement to verify design assumptions, material properties and construction methodology. The trial shall be undertaken in the presence of the Designer using the construction procedures, equipment and operating personnel proposed for the work in the placing, stabilising, compaction and finishing of the individual layers.
8dd0573f-9954-526d-81fb-cc7286f8ba2a | note | Standard / Specification - NZTA B10 - 5
8fb913df-e151-5462-8336-1f6dbf5dc65f | note | Verifying Document - Conforming Trail and Test Results
913f2513-4fcc-565c-a466-be9062d7cf03 | note | Frequency - Prior to Hi-Lab Construction
fd122142-f137-55ab-8488-c8d0d4b94954 | note | Verification Activity: Activity - HP
0776875a-953f-5606-9975-6a1898e4c7e0 | note | Verification Activity: By - ENG
fa28a3d8-05b8-577b-b0fc-772edfdddc32 | signoff | AUTHORITY HOLDPOINT
4967a333-afa6-5e74-8cec-18a3e873810e | section | 13.06 Hi-Lab Construction
2f7a441c-0118-5c13-919c-0e919b8601ec | checkpoint | 13.06.01 - Production Quality Plan
f608f53a-107f-5656-9537-1a9a6f3da9eb | note | Acceptance / Conformance Criteria - The Contractor shall prepare a Production Plan for approval by the Engineer prior to commencement of delivery of Hi-Lab aggregate to site, detailing all aspects of its Hi-Lab production process, how it will achieve compliance with this specification, and procedures in the event of non-compliance or plant breakdown. The Production Plan shall include the Contractor’s detailed methodology.
6cc427e6-d4d8-5981-80b6-0b19cffd500f | note | Standard / Specification - NZTA B10 - 4.1
3e6067a6-1ac1-5fa8-bccd-c2a0f4c2f4c4 | note | Verifying Document - Production Plan
10c18e80-8363-51d9-8023-5e1d086685fa | note | Frequency - Prior to commencement
3e9c822b-2a7e-55f2-9ced-52a19ddda259 | note | Verification Activity: Activity - HP
980cbf0a-a7c0-543c-aaa6-c6a8c81ee6e9 | note | Verification Activity: By - ENG
e7f3690a-12eb-5c38-9ad7-675143e0f2e8 | signoff | AUTHORITY HOLDPOINT
241989c9-bd98-52d4-90c0-a05be274c20c | checkpoint | 13.06.02 - Daily production sketches
a35e0141-717f-54da-b33e-f2197420a929 | note | Acceptance / Conformance Criteria - Daily production sketches shall also be produced for approval by the Engineer ahead of each forthcomingday’s work.
cc0d86ca-e187-55a9-880d-94bc0fb8395a | note | Standard / Specification - NZTA B10 - 4.1
2e60c94b-5a3c-5d47-8f63-5c28dca53401 | note | Verifying Document - Production sketches
a2fc03ed-e884-564a-85ea-e1faf3053f34 | note | Frequency - Daily Prior to commencement of days work
0f01ad39-91ae-5c74-9868-dadfbec54712 | note | Verification Activity: Activity - HP
3b4697a7-e95f-5744-a754-e4795da65ceb | note | Verification Activity: By - ENG
7a8832cc-acaf-5453-b024-a92e84e3b62f | signoff | AUTHORITY HOLDPOINT
697c85b5-705b-5096-bb3e-4cb741e0b5b7 | checkpoint | 13.06.03 - Initial placement of aggregate
e77e7364-ed09-5dba-8d6b-9d0719b1d5ed | note | Acceptance / Conformance Criteria - The Contractor is responsible for ensuring the surface level after spreading and compaction prior to stabilisation will result in final layer thickness and finished levels after stabilisation that are within the required tolerances.
cf3f12aa-051f-5dd8-b8b1-266220f03a36 | note | Standard / Specification - NZTA B10 - 4.3.2
4ad6af39-9872-53b4-b0cd-13892b8c9c4f | note | Verifying Document - Survey Records
fffe5826-9c22-582c-a52b-8e6b648df2d0 | note | Frequency - prior to stabilisation
bc739a16-b9fc-58b0-b1fb-c69ecd40f719 | note | Verification Activity: Activity - I
7d4984ec-9fdd-5235-9528-1025d1c81f0c | note | Verification Activity: By - SV
03a3c627-80e9-50dd-b363-057f624a1faf | checkpoint | 13.06.04 - Cement Mat Test
7f9668b2-7dba-5f90-83c8-522aa29efe0e | note | Acceptance / Conformance Criteria - The cement spread rate shall be measued by a 1m² canvas Mat Test every 250m2 and be Within ±0.5kg/m² of the specified rate.
4d74cfcd-90e6-53e4-a50e-641961560aaa | note | Standard / Specification - NZTA B10 - 4.4.1
9de89cbf-a73d-5d65-a338-c713a0f6ffa0 | note | Verifying Document - Test Results
1925964d-4081-5d78-8f5f-afc88bf2b0ba | note | Frequency - Every 250m²
0b960be9-732e-525d-9da3-8660e7eec94c | note | Verification Activity: Activity - I
74457528-d975-5052-a745-b8d0a4efcddd | note | Verification Activity: By - SE
dab7d40a-bbe0-56ad-8ec0-37522cd9b398 | checkpoint | 13.06.05 - Cement Average usage test
c7c9d2cf-8535-5c94-ba97-94dcfb8a7b56 | note | Acceptance / Conformance Criteria - The Average usage of cement spread rate shall be measued by comparing tonnes used (from delivery docket) with measured area and be Within ±2.5% of the specified rate.
527c1fa0-a407-5dad-961b-9d8234e7d270 | note | Standard / Specification - NZTA B10 - 4.4.1
59ac7cb7-9147-522b-b34b-c87df48da432 | note | Verifying Document - Test Results
bf597ceb-3624-501f-9be5-7f3b97e94741 | note | Frequency - Upon emptying the spreader and bulk tanker
2a743a81-f175-5d8e-9cba-41f9e293c71e | note | Verification Activity: Activity - I
7c8c01ff-5c8f-5f3c-bb2a-319790a8f064 | note | Verification Activity: By - SE
8513219b-8a79-545a-bf0d-5b9039345c37 | checkpoint | 13.06.06 - Weather limitations
8b36d006-df09-59b7-81e6-f80c9edc460d | note | Acceptance / Conformance Criteria - Spreading of cement on the road ahead of stabilisation shall not continue when the cement becomes a dust problem due to dryness or when the wind speed exceeds 25km/hr. No spreading of cement shall commence if it is raining. If rain is likely to start before the cement can be mixed into the aggregate, then spreading shall not take place.
4120af66-13ea-5280-80f7-208977672642 | note | Standard / Specification - NZTA B10 - 4.4.2
3d5c5621-e697-58f3-a879-d1c9af921d14 | note | Verifying Document - Site Records
5d3b0176-25a3-5ab4-8ebc-609276d2b8dd | note | Frequency - Duing stabilisation
dd785f47-adbb-5a0b-9825-4b2b89700177 | note | Verification Activity: Activity - R
646eeeb6-d620-5e82-a41c-7d53e89342b6 | note | Verification Activity: By - SE
3389e69d-d29b-5b48-a884-62ac8400c9eb | checkpoint | 13.06.07 - Time limitations
55c5a7c7-5e0d-593e-8880-1af2de735fc9 | note | Acceptance / Conformance Criteria - The maximum time period, from mixing of the materials to completion of primary compaction, shall be 2.0 hours. Unless specifically justified in the approved Production Plan, stabilisation shall commence no later than 10:00 am and the area to be stabilized shall not exceed 4,000m² per day, unless agreed otherwise by the Engineer, to ensure sufficient time to complete the full stabilisation process.
dfb81861-9f6c-572a-9acb-a361b3af92ff | note | Standard / Specification - NZTA B10 - 4.4.3
6cf88b92-171a-5144-a448-304497fe231f | note | Verifying Document - Site Records
cc9911e2-fbd8-5b28-a9f0-f6b7042e2016 | note | Frequency - Duing stabilisation
a41b5a02-7b43-59ad-82b3-c6e78f9c9bbf | note | Verification Activity: Activity - R
fa912b9a-695a-57f4-bccb-5b188858f749 | note | Verification Activity: By - SE
2b3dda1e-0034-524f-8b33-a879d7175a27 | checkpoint | 13.06.08 - Stabilisation/Addition of Water
fd26810f-0d7f-5f06-9c51-623f151382ed | note | Acceptance / Conformance Criteria - The Contractor shall continuously monitor the moisture content of the material behind the recycler and in consultation with the Engineer adjust the rate of water injection as necessary. The Contractor shall also monitor continuously for blocked nozzles or any other risk to the consistency of the mixture. The stabilisation area shall not exceed 4000m2 per day, with a maximum single stabilisation run length of 225m, unless agreed otherwise by the Engineer.
e14e9ef0-79d1-54af-8251-7c2c45e66304 | note | Standard / Specification - NZTA B10 - 4.5.1
cfbd7f28-829f-5f46-aed0-cc8fa2193220 | note | Verifying Document - Site Records
be424a37-e193-5709-8cf3-56c9035f1dd3 | note | Frequency - Duing stabilisation
aa723f9b-8b34-5beb-9d33-425dd08ca64a | note | Verification Activity: Activity - R
488b1df2-5193-536b-9149-e6a1b244336a | note | Verification Activity: By - SE
97c51ad4-59cd-5a8e-b7c6-ec5beb678474 | checkpoint | 13.06.09 - Control of mixing depth
8d95cbfc-214b-5ce2-9442-8bfd82443869 | note | Acceptance / Conformance Criteria - The Contractor shall determine the mixing depth so that the final stabilised layer thickness after compaction meets the contract requirements. During stabilisation the depth of the cut shall be physically measured at both ends of the mixing drum at least once every 50m. The measured stabilisation depth shall confirm full mixture of the placed Hi-Lab layer at full depth with no untreated materials present at the bottom of the test hole.
fba6f2d5-e29a-5331-ae64-4e5aef278e5f | note | ○ The maximum allowable variation from the specified depth of cut is –5mm and +15mm.
292420c5-069b-5c48-bd3c-2b44c0e16818 | note | Standard / Specification - NZTA B10 - 4.5.2
2c2b6568-04c3-55d7-8790-509971d860af | note | Verifying Document - Survey Records
9d347aec-71a9-5005-81cd-a0510fae5af9 | note | Frequency - Duing stabilisation
acda9bbe-0de4-53bf-aae1-4a20de9d3f3c | note | Verification Activity: Activity - I
84e6a7cf-cfd2-56d7-a0c8-b4cddc63a012 | note | Verification Activity: By - SV
d8d44e3f-90cc-5f13-a9de-5a6001544f66 | checkpoint | 13.06.10 - Overlap on longitudinal joints
d6dcfc93-9ed3-5b4e-ab2e-e929022fd011 | note | Acceptance / Conformance Criteria - To ensure complete stabilisation across the full width of the road, longitudinal joints between successive cuts shall overlap by a minimum of 100mm or half the layer thickness, whichever is greater. Overlap width shall be increased if any dry material is noticed between runs. The locations of longitudinal joints shall be agreed between the Contractor and Engineer and recorded in the production plan.
4a452d3b-c427-5d91-8e60-2c38195f30a5 | note | Standard / Specification - NZTA B10 - 4.5.3
7a0bb099-8a08-54f2-93ef-5e717cee6cac | note | Verifying Document - Production Plan
ff338510-aeac-517a-9f6b-bac1954f42ca | note | Frequency - Duing stabilisation
625fc65a-56f1-5d18-9347-e4ab83596f8e | note | Verification Activity: Activity - I
6a48027f-0456-52c8-9c2f-9d62e1968157 | note | Verification Activity: By - SE
45743f7b-9ced-573e-ad47-b6b8a96da711 | checkpoint | 13.06.11 - Continuity of stabilised layer
5f42c5f5-f32a-5dab-97be-68bdd544faa2 | note | Acceptance / Conformance Criteria - The exact location of the end of the cut shall be carefully marked. This mark shall coincide with the position of the centre of the mixing drum at the point at which the supply of cement ceased. To ensure continuity of the stabilised layer, the next successive cut shall be started 3m behind this mark. This tie-in length shall be reduced to 1m for stabilised layers older than 7 days. Cement shall be spread on the overlap for the next run.
1b11b6c6-9842-5b7a-969e-1a1df75782d1 | note | Standard / Specification - NZTA B10 - 4.5.4
a7533850-1211-5e6f-be75-5990bb03ed6e | note | Verifying Document - Daily Production Drawings.
104a3276-11dd-5aea-85e7-7a1da89354be | note | Frequency - Duing stabilisation
d5056f48-9b40-5b8f-ba99-fa1ebaf60eae | note | Verification Activity: Activity - R
1fa57f4e-3dfc-514d-988e-cbedc9b959bd | note | Verification Activity: By - SE
d4f61fb8-d23f-5bf1-af02-b5ff76b715eb | checkpoint | 13.06.12 - Daily production sketches
c871987f-f9a3-5f0d-8728-dc9c9e1999ea | note | Acceptance / Conformance Criteria - The Contractor shall sample the material behind the stabiliser for particle size distribution analysis using the specified method below and advise the Engineer of the result as soon as practicable. The sample frequency shall be a minimum of 5 samples per 4000m2. The samples shall be representative of the full stabilised area.
d3264715-c169-54f6-88c0-a92bcb248efa | note | Standard / Specification - NZTA B10 - 4.5.5
42487bc5-c16b-57ad-b699-c69113c9456f | note | Verifying Document - Test Results
908b6069-78d2-5975-b8b0-d5b264dc0c4f | note | Frequency - A minimum of 5 samples per 4000m2
4edda2da-ed45-552f-8806-5a63cbf2dfdb | note | Verification Activity: Activity - R
69d6a0e6-2c4f-5b6e-a3ad-718ba518f716 | note | Verification Activity: By - SE
24997435-e1c0-5242-9839-3ba46fa256ea | checkpoint | 13.06.13 - Primary Compaction
e02129af-73c7-5990-a5bc-3b45a0741832 | note | Acceptance / Conformance Criteria - Primary compaction shall be monitored for conformance to the methodology
b2c59de3-066c-545b-8259-ede62ea0c036 | note | Standard / Specification - NZTA B10 - 4.6.1
fa7abd12-4051-5f06-8b01-658b7f35f6b8 | note | Verifying Document - Site Records
cf94d5ac-a124-5612-8680-0d6c87993a32 | note | Frequency - Duing Compaction
5e842105-2b7b-5471-b10f-d322011ffdca | note | Verification Activity: Activity - R
82166b3f-2c29-5641-bf73-feafc8286200 | note | Verification Activity: By - SE
8c391b9e-98a3-5c00-becd-b32057c8a1b9 | checkpoint | 13.06.14 - Secondary Compaction and Choking
37360509-3ba9-5b1d-a80f-d5505cb8edb1 | note | Acceptance / Conformance Criteria - Secondary Compaction and Choking shall be monitored for conformance to the methodology
67781bcc-a8d2-5633-b8fe-862e96c1ad26 | note | Standard / Specification - NZTA B10 - 4.6.2
1e3dea6f-afcd-53c4-95b1-293c8353cf06 | note | Verifying Document - Site Records
57fbbcf7-9abc-597a-89cb-187e8b4deb2a | note | Frequency - Duing stabilisation
82bb35c0-96b1-5017-bdb5-59eb58a6029b | note | Verification Activity: Activity - R
81f9dda4-d9f5-5e58-965c-aa1bfbfd3bed | note | Verification Activity: By - SE
218712d4-3a1a-5157-9683-e8c3a9f94208 | checkpoint | 13.06.15 - Surface prior to placing next Hi-Lab layer and/or sealing
9a646307-caa3-5664-b156-aae460ea7653 | note | Acceptance / Conformance Criteria - Fines shall be removed and broomed to produce a mosaic surface prior to placing the next Hi-Lab layer or sealing. The surface shall not have any loose fines and/or “caked” laminations of fines, and shall be a mosaic stone surface free of fines.
47a6b9da-e4db-504f-ab55-437488854e0b | note | Standard / Specification - NZTA B10 - 4.6.3
d3f344be-ba5f-5b9d-9785-089b9009ff7e | note | Verifying Document - Site Records
82e9dd74-c55d-5718-a147-72fa1cf5abe6 | note | Frequency - Prior to placing next Hi-Lab layer and/or sealing
dd7efa33-e70f-55b8-ad71-62be1cb43d06 | note | Verification Activity: Activity - R
df7e9905-5fad-5768-b153-b1c62bde2e08 | note | Verification Activity: By - SE
268cbc70-6685-5d3f-8850-94a9ad3c98fd | checkpoint | 13.06.16 - Surface shape
33abea90-78c4-5b1f-adc7-18f9e0b897da | note | Acceptance / Conformance Criteria - The surface shape of the completed pavement layer shall be such that, when all loose aggregate is removed, it conforms to the shape specified within the tolerances in Table 4.3.
3efb5ae5-0f86-56ae-a29e-94ce38e025af | note | Standard / Specification - NZTA B10 - 4.6.4
346a8417-cb79-5933-99d1-c69ab4a263bb | note | Verifying Document - Survey Records
ffd92476-0e64-5ed7-9995-6314cffca35f | note | Frequency - Each Layer (Subbase / Basecourse)
8832a125-a915-5921-acc0-c6f8a3ac85f1 | note | Verification Activity: Activity - I
caec36ae-6c95-5dad-b567-0ff510e65921 | note | Verification Activity: By - SV
6e12d4f7-3bc6-5f43-b2d3-aad17cbcb157 | checkpoint | 13.06.17 - Crossfall
1e4217de-ccd0-5620-8ccc-41455bb854c6 | note | Acceptance / Conformance Criteria - The crossfall between two points more than 2.0m apart, transverse to the centreline, shall not depart from the design crossfall by more than 0.5%.
60bd514e-f6c9-55de-bc44-bff8763f7e42 | note | Standard / Specification - NZTA B10 - 4.6.5
ee19d33b-3c32-53db-bd1c-aa06f985111c | note | Verifying Document - Survey Records
74199470-e3c0-5daa-adb9-9c7f151a7e56 | note | Frequency - Each Layer (Subbase / Basecourse)
5b1dfd5c-5aa2-5db2-be58-d6b79117e5e0 | note | Verification Activity: Activity - I
6d2ab168-94e2-5af5-b4fb-c9fd0e0deea3 | note | Verification Activity: By - SV
a71ee757-04be-514b-9de2-d912dbfdac56 | checkpoint | 13.06.18 - Hi-Lab Protection
29422071-cc70-59e3-8e7c-fa375af4583b | note | Acceptance / Conformance Criteria - No construction equipment shall be driven on any Hi-Lab aggregate layers until at least 48 hours have passed following completion of secondary compaction. At no time during the construction of the Hi-Lab pavement layers shall any haulage of earthworks and/or drainage construction activities e.g. excavators be allowed, only construction activities directly associated with the construction of the Hi-Lab layers, e.g. placement of aggregate.
875fd5a1-2431-5d5a-bc84-d66a5feded33 | note | Standard / Specification - NZTA B10 - 4.6.6
5cf79cbb-5dc9-5758-a6a5-a55f08cc58d2 | note | Verifying Document - Site Records
d3e849f4-52cf-5b02-83d9-b1e8ec82a91e | note | Frequency - at least 48 hours have passed following completion of secondary compaction
4894ea64-c0b1-520e-8df2-2a4355e38cea | note | Verification Activity: Activity - R
4aed90b9-bfc5-54b8-b62a-9db4e0b1ff84 | note | Verification Activity: By - SE
f611315c-1219-5e61-84d1-246db55a1ae1 | checkpoint | 13.06.19 - Hi-Lab Maintenance
114c0e99-ca20-5c42-89e5-9f2c073696bc | note | Acceptance / Conformance Criteria - For a minimum of 48 hours after stabilisation the Contractor shall
a7b72a8d-f65f-55a0-bd01-3b8a43025bbb | note | (a) provide additional PAP7 running course, if required (using clause 10 of NZTA B02 as a guide)
346ee5e8-10d6-5fb0-93dd-02b070782cad | note | (b) keep the surface damp but not wet to prevent drying and ravelling
468e6bb2-9347-515d-b146-be6f50331575 | note | (c) drag-broom the whole surface, keeping a balanced distribution of PAP7.
4baa6654-562a-5838-a3e9-df85bb3f3b3e | note | Standard / Specification - NZTA B10 - 4.6.6
0f9d124a-4541-5257-a236-c005b025f98d | note | Verifying Document - Site Records
ad41f35d-f1c5-5d50-910d-c51c57348f5d | note | Frequency - at least 48 hours have passed following completion of secondary compaction
21055ddd-0148-5dc4-a5bb-e4ddba034ec9 | note | Verification Activity: Activity - R
335d8106-a7f7-5f7f-a3a9-f4fe032d78c1 | note | Verification Activity: By - SE
3c8ac544-6888-5930-bcae-e157c38465c9 | checkpoint | 13.06.20 - Compaction Testing - Subbase and Basecourse - Moisture Corrected - Direct Transmission against Solid Density
c20be1e0-5ce6-5d8e-bef8-21b5df91873b | note | Acceptance / Conformance Criteria - The degree of compaction for the Hi-Lab layer shall be determined by direct transmission, a hole shall be drilled to accommodate the probe to the full depth of the Hi-Lab layer and/or layers. The probe shall be set at increasing increments of 50mm and a measurement shall be recorded for each depth setting. This process shall be repeated twice with a 180 degree rotational off-set around the hole. Tests shall be Moisture corrected.
0aa2f989-234d-5dd3-9f43-2fb0dcb10278 | note | ○ Average Value 83 %
9a155c2f-7c64-57c4-b2dc-5bf3c7b30a18 | note | ○ Minimum Value 81 %
b3489105-a961-5a5e-a121-057482df9b0f | note | Standard / Specification - NZTA B10 - 4.6.7
c3ca5556-8e10-585d-b42f-02170b60ffe6 | note | Verifying Document - Test Results
764e92bf-8378-5835-94cf-f2c2bc19a7db | note | Frequency - At least five (5) randomly selected areas per 4,000m² or part thereof. For lot sizes larger than 4,000m² additional testing shall be undertaken at a rate of 1 test per 1000m²
dba06177-40a9-5d8c-839d-1e9ce55461bf | note | Verification Activity: Activity - I
cc506851-3bdf-5073-aa56-dee60b948dca | note | Verification Activity: By - SE
9735dae7-2d5a-5b5e-bc06-364203d2973c | checkpoint | 13.06.21 - Moisture Correction Cores
20bafaf4-60f4-5107-8b4a-4c6f259e90f9 | note | Acceptance / Conformance Criteria - A minimum of two core samples per 4,000m² or lot size whichever is the lesser, shall be taken within 0.5m of the probe hole to be used for moisture correction. After oven drying to calculate moisture correct, the same core sample shall be used for ITS.
e8cc8626-72c9-52e1-b3b5-670367a56903 | note | Standard / Specification - NZTA B10 - 4.6.7
9998e15f-bc79-5b1d-8af6-b0170ccbd921 | note | Verifying Document - Test Results
a27435c5-611a-59da-bfa6-f4e49f0dde78 | note | Frequency - A minimum of two core samples per 4,000m² or lot size, whichever is the lesser
0de69379-a43e-5677-8e43-15a60abbefce | note | Verification Activity: Activity - I
a8d9f867-61f7-5d51-b8fe-b59f3c91b84b | note | Verification Activity: By - SE
2e0c41c7-05dc-52d8-8810-f5b46e527098 | checkpoint | 13.06.22 - Coring
53b3bd1a-9bb1-55cc-9f9a-1676038ba6eb | note | Acceptance / Conformance Criteria - After a minimum of 7 days post stabilisation the Contractor shall take 200mm diameter core samples from representative locations in the stabilised layers for Indirect Tensile Strength (ITS) testing. If the Hi-Lab basecourse is placed prior to 7 days after sub-base construction, both layers shall be cored together at least 7 days after basecourse construction.
1da5e333-5c14-5c14-89f4-0a85e9252aef | note | Standard / Specification - NZTA B10 - 4.7.1
206cac20-aea4-5bee-af8b-0a2c72907e89 | note | Verifying Document - Test Results
5f8ccfd1-cb72-5ab2-ad8d-d214067c7d25 | note | Frequency - One core is required per 2,000m² lot or part thereof for each stabilised layer.
70106e34-6ba3-58a2-9494-f9f800bae08b | note | Verification Activity: Activity - R
2fa2c90e-186a-5887-9bc9-36794af92239 | note | Verification Activity: By - SE
1dea0bca-63d1-5d52-99fd-a97730d18266 | checkpoint | 13.06.23 - Hi-Lab Sub-Base Deflection Testing
dc26f065-d6bb-54fc-817b-7f5c87bc0867 | note | Acceptance / Conformance Criteria - Benkelman beam testing shall be carried out on top of the Hi-Lab sub-base layers in accordance with TNZ T01 specification at 10m intervals in alternating wheel paths for all lanes, within 7 days after stabilisation. All measured deflection measurements from each construction lot shall meet 95 the percentile ≤ 0.4mm (max < 0.5mm)
d2c6bbfc-a14b-5e7a-8b07-d373145a78b6 | note | Standard / Specification - NZTA B10 - 4.8
89226f3c-60b6-5751-83fc-bfbe3c03d8f7 | note | Verifying Document - Test Results
2074b372-a16e-50b9-a322-7e6da39cdb0c | note | Frequency - Prior to Next Layer / Surfacing
181fd81a-40b2-59dd-9a36-39e017af6737 | note | Verification Activity: Activity - HP
a5634c94-e6e6-5ec1-bf3f-b32e69935231 | note | Verification Activity: By - ENG
d748e447-661b-5f42-91bb-a370188e19bc | signoff | AUTHORITY HOLDPOINT
dc5d2f91-477d-5b38-bfbc-112810b6c337 | checkpoint | 13.06.24 - Hi-Lab Basecourse Deflection Testing
8e65e8a9-0a8d-5f6f-bd76-8a6d28d6e949 | note | Acceptance / Conformance Criteria - Benkelman beam testing shall be carried out on top of the Hi-Lab basecourse layers in accordance with TNZ T01 specification at 10m intervals in alternating wheel paths for all lanes, within 7 days after stabilisation. All measured deflection measurements from each construction lot shall meet 95 the percentile ≤ 0.3mm (max < 0.4mm)
62c76a76-e197-585f-bd6a-ddb2a3ff93f7 | note | Standard / Specification - NZTA B10 - 4.8
bfe4de69-ff0a-50ac-9faf-350174f3db26 | note | Verifying Document - Test Results
e80f0130-a5da-5ea4-9978-90c6375ef92f | note | Frequency - Prior to Next Layer / Surfacing
aa322553-939b-590e-b3f1-8dc87f023971 | note | Verification Activity: Activity - HP
b33a3ee0-f037-5f51-8866-5bf4293db990 | note | Verification Activity: By - ENG
6415bbd5-7eba-5b7e-a59e-d906f037defc | signoff | AUTHORITY HOLDPOINT
46a2b057-7dc4-5e97-b9ce-4ecc203327de | checkpoint | 13.06.25 - Hi-Lab Pre Chipseal inspection
9b191f50-6e09-5f86-bd4b-f0e4242c868e | note | Acceptance / Conformance Criteria - Before sealing, the Contractor shall advise the Engineer that the pavement surface has been prepared in accordance with this specification although final sweeping may not have been performed. The Engineer shall be given the opportunity to inspect the swept pavement surface for approval.
c3442f3c-5c77-5777-b8c7-4671a319370d | note | Standard / Specification - NZTA B10 - 4.9
edef44b0-e4d3-5099-81b8-7027a2cd7424 | note | Verifying Document - Engineers Acceptance
b6d39fc8-8acc-5881-aefe-2627e6e3cbbc | note | Frequency - Before sealing
5dd3e318-3958-5b6c-9c41-b4a2d0d88aae | note | Verification Activity: Activity - HP
4f6d571b-9ec4-5b88-aa00-7594fe574a97 | note | Verification Activity: By - ENG
2ec83722-b96f-59d2-b7f7-eca45b816518 | signoff | AUTHORITY HOLDPOINT
cf581b77-bb0b-5a4a-8328-5257b97c4f87 | checkpoint | 13.06.26 - Hi-Lab Basecourse Surface - Pre Asphalt NAASRA
c71afffa-30f2-5466-b62c-415f334c344b | note | Acceptance / Conformance Criteria - For in-service chip seal surfacing - the 100m moving average lane roughness of Hi-Lab basecourse shall not exceed a NAASRA (100m rolling avg/km) < 75 counts/km.
09c10c46-d84a-595b-a605-7272eecf4ac6 | note | Standard / Specification - NZTA B10 - 4.9
b72f08bb-9964-570c-8a21-d05e3e103cc0 | note | Verifying Document - Test Results
80323b5a-fb8d-55b1-a762-d65db13c1c03 | note | Frequency - Prior to Asphalting
ba57d95a-d664-5928-bc71-1ead698cba28 | note | Verification Activity: Activity - HP
0066e63f-41a8-5b2e-abb0-8aae051558c4 | note | Verification Activity: By - ENG
f9ba2cdc-eb17-50cd-98b5-194c045d5d59 | signoff | AUTHORITY HOLDPOINT
710d2ca2-5422-5f19-ad1d-f29ae63a3fd7 | checkpoint | 13.06.28 - Hi-Lab Pre Levelling
3ece08c3-8e21-54d2-aa47-df5db647c823 | note | Acceptance / Conformance Criteria - The Constructor shall submit the asphalt pre-levelling methodology to the designer for review and approval prior to implementation.
e44c07de-c900-5c98-ac71-1d59430bf953 | note | Standard / Specification - NZTA B10 - 4.9
10134e9a-be21-53f1-a84b-acfc45386858 | note | Verifying Document - Methodology
86702236-9229-5b5d-8cff-d9ac9e147fbd | note | Frequency - Prior to Asphalting
85d48a23-6afa-5d8b-a3e5-42191cac3518 | note | Verification Activity: Activity - HP
764e4f92-cc52-5552-8a03-b823cd7b7007 | note | Verification Activity: By - ENG
3bbabf6b-65cc-5e8e-96f3-25c0e2c17837 | signoff | AUTHORITY HOLDPOINT
4a20b055-87ba-53bb-9189-bcd3365ffdf7 | checkpoint | 13.06.29 - Hi-Lab Pre Asphalt inspection
82859049-bf5c-55d8-80cf-0c7ca8c42500 | note | Acceptance / Conformance Criteria - Before sealing, the Contractor shall advise the Engineer that the pavement surface has been prepared in accordance with this specification although final sweeping may not have been performed. The Engineer shall be given the opportunity to inspect the swept pavement surface for approval.
82babf09-9647-5a4c-9ced-085b3d181f5d | note | Standard / Specification - NZTA B10 - 4.9
887a4078-e936-538e-95c2-2df51afc9499 | note | Verifying Document - Engineers Acceptance
6ba5df7b-26eb-5420-b5a5-df2c985b6e3d | note | Frequency - Before Asphalting
cf08803d-5853-5982-b074-6a2383215e5e | note | Verification Activity: Activity - HP
7708e3e0-a02e-50ea-b523-f917b12e550d | note | Verification Activity: By - ENG
8732e577-30a6-5cc7-8c2f-cd019bafc80c | signoff | AUTHORITY HOLDPOINT
01e80a0d-fbe9-5390-82f7-adef244f9f9a | section | 14.01 Structural Asphalt
71c791df-acd9-5394-b9ab-87849fc3e0e2 | checkpoint | 14.01.01 - Pre-Paving Planning Meeting
6e9a546b-5e03-5a7d-8b82-e1568a1f3a36 | note | Acceptance / Conformance Criteria - No less than 48 hours prior to the commencement of asphalt construction a pre-paving planning meeting shall be held
eb2d5d3b-cc19-57b4-8efc-a21fb80765d9 | note | Standard / Specification - PS 20.7.6
169be556-9592-5a61-b187-3e0992c9f214 | note | Verifying Document - Meeting Record
31684294-c7fe-57e7-8ea1-253b87057204 | note | Frequency - No less than 48 hours prior to the commencement of asphalt
fedfa0d1-4890-5953-b770-45a24693e1ce | note | Verification Activity: Activity - HP
b054568b-f135-509c-b333-bdf69fd234a8 | note | Verification Activity: By - ENG
43db3173-10ce-52b7-89c3-1ce46aa30e6e | signoff | AUTHORITY HOLDPOINT
fabf8396-eaec-50f1-9fb1-08aa0268f5ab | section | 14.03 Construction Activity - NZTA M10 - Specification for dense-graded asphaltic concrete
d9ba015d-4ed1-5d0e-b38a-d7ca0b83e37b | checkpoint | 14.03.01 - Construction Trail
755354da-fd78-5ee1-bfae-672bb2d8674b | note | Acceptance / Conformance Criteria - Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. Asphalt manufactured in the production trial can also be used in the construction trial if it meets the requirements of the specification.
81456e1a-c12b-5d58-b2f4-199cb82838d0 | note | Standard / Specification - PS 21.3.1 NZTA M10:2020 - 7
2f2413af-d972-58d2-9bbf-676b0b85fad7 | note | Verifying Document - Test Results
c44b2cf7-fd31-5aaf-a286-9d922dec94df | note | Frequency - As Required, two days before the site work is due to commence.
37794619-dd75-5111-bf8d-a5ea9ca517b8 | note | Verification Activity: Activity - I
7bb74110-1213-54fd-b0f1-8f6b7a361886 | note | Verification Activity: By - PE
dc66f832-8727-52d8-9e25-4430ebf5e982 | checkpoint | 14.03.02 - Paving Plan
5dce77ae-08dd-50a8-8ac3-b70d88e9ae1d | note | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
55fceaea-eb12-5968-8022-90d8686d0ced | note | Standard / Specification - NZTA M10:2020 - 8, 9
9bfb1586-65ca-55c0-be19-858f565e70d9 | note | Verifying Document - Construction Work Pack
1fd23c99-3a1c-5f22-87f3-bdb96d0fce10 | note | Frequency - 7 days prior to construction of the asphalt pavement.
a3ea93a4-3f6a-57e9-846e-e211a59de1ee | note | Verification Activity: Activity - HP
1222edc6-2df9-5e5c-b075-faeccb2a6dfb | note | Verification Activity: By - ENG
1cb5f60e-936c-5933-b2d8-2c1dffdb519a | signoff | AUTHORITY HOLDPOINT
f1b55bb9-7077-5c36-bcdb-1d298ac1a406 | checkpoint | 14.03.05 - Ambient Conditions for Placing
6f4918a9-598a-5dfc-b5af-e751d7b4d512 | note | Acceptance / Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C, for SAC the minimum temperature is 5°C
f8ae69f6-d106-57d3-84b3-2c69bdec7db3 | note | Standard / Specification - NZTA M10:2020
2d548a20-a68d-5c02-8c6c-6fff551085d7 | note | Verifying Document - Site Notes
473a3c2e-7fb4-57fe-9421-f1bfbb4e7034 | note | Frequency - Pre Seal
c8aea03e-f630-5a76-9cbc-cff257e44cb4 | note | Verification Activity: Activity - H
4f58b515-56c8-55f4-9d10-a549565c8dca | note | Verification Activity: By - SE
99a6b2db-1c82-538e-85c3-8fdb54b15c74 | checkpoint | 14.03.06 - Tack Coating
bd33b60e-eb31-548c-9a31-606814ff90ef | note | Acceptance / Conformance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat.
82b4a30b-9974-5b18-908f-cd2b3ad8ec01 | note | Standard / Specification - NZTA M10:2020 - 9
b421e271-20bf-5ac8-a980-8a010a55d4bb | note | Verifying Document - Site Notes
d32940c3-9a8a-53b0-88b1-7eeb3bb9ea4e | note | Frequency - Prior to Paving
9e133c7a-8189-5880-8977-797b1a2142ef | note | Verification Activity: Activity - I
58117028-e194-5ba8-a2a8-cdca91ca1300 | note | Verification Activity: By - PE
370d7efd-40fc-556a-910d-d7f6043e6e7d | checkpoint | 14.03.07 - Asphalt Production Conformance - Grading and Binder
8b00d341-891b-55ce-8de2-75deaf10bda7 | note | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass. Refer clause 5.2 and table 5.2 for frequency and tolerances
a7113eec-623e-5980-8310-5dc2f5a5e233 | note | Standard / Specification - NZTA M10:2020 -Table 3.1, 5.1 and 5.2
f2ce8fba-7af4-5343-a27e-0cc72e2e521a | note | Verifying Document - Test Results
7c1e3aa3-7c80-52a4-b7b1-dcc3cb6a0a8e | note | Frequency - 1 per 200T
459dfc65-69b5-5151-8f44-d42da95fc465 | note | Verification Activity: Activity - I
eef35c16-0c2c-57ed-a7c5-31438a4319f8 | note | Verification Activity: By - PE
66aec51e-2e1a-5258-9c3f-75c10b666cd2 | checkpoint | 14.03.08 - Asphalt Production Conformance - Volumetrics
f39db1c7-4993-5a3c-b17b-fccf87716a6e | note | Acceptance / Conformance Criteria - Conforming Volumetric testing. Refer clause 5.2 and table 5.2 for frequency and tolerances
6298bfd8-46ec-5ceb-8b6b-ee90a7d8f3dd | note | Standard / Specification - NZTA M10:2020 - Table 3.1, 5.1 and 5.2
dc5aedeb-c426-5aae-9bc2-522d08929878 | note | Verifying Document - Test Results
9553859d-5c22-5bc6-8930-fab40b5e30a0 | note | Frequency - 1 per 600T
bafb6592-e54d-5e1f-96ff-6bd6c54f170a | note | Verification Activity: Activity - R
82584835-1e1c-5d42-9682-3c528f785f0a | note | Verification Activity: By - SE
0aecd9f3-570d-5a19-b9d5-04ceb4a37284 | checkpoint | 14.03.09 - Core Thickness
d41599f9-6434-543c-9288-bf9f6571e0a4 | note | Acceptance / Conformance Criteria - The nominal thickness for the set or lot of cores shall be equal to or greater than the specified nominal thickness.
00052fd7-8c46-5616-85ee-96014475e3e6 | note | Standard / Specification - NZTA M10:2020
6fc87537-ac8d-5ae7-b8c9-e90d8ecd9cbc | note | Verifying Document - Lab Report
aa70c97b-5a76-52bd-89e1-009b7e8ed1aa | note | Frequency - Mat - min 8 per lot (day) (1 for every 300 m²) Joints - min 3 per lot (1 for every 100m)
052030d1-9d59-5667-a045-0f7155bf920e | note | Verification Activity: Activity - R
28b36d15-8667-5f78-b593-6c52aef2489d | note | Verification Activity: By - SE
f6994cad-2fdd-5881-9b51-42aa86c6773c | checkpoint | 14.03.10 - Joint Density
3df80193-31d7-53b9-bbb7-75ea17b4507f | note | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100m of joint with a minimum of three representing each lot
80585415-c825-50bd-965e-329296b31f51 | note | Standard / Specification - NZTA M10:2020 - 9
f963756f-bb4f-5893-b0c8-8a72307a02f2 | note | Verifying Document - Cores
f4f90a13-2e6d-59aa-92a4-00f2b3ab4989 | note | Frequency - min 3 per lot (day) (1 per 100 m of joint)
2d18028f-7b03-5eaf-a22c-a0d8f7a419e6 | note | Verification Activity: Activity - R
fc5feffe-9c6a-5557-9344-daad1874fb9e | note | Verification Activity: By - PE
3a4777c8-04aa-5df7-be12-87141109d5f5 | checkpoint | 14.03.11 - Density Testing
c534caf8-3c2b-5b0d-8010-8693dee91b37 | note | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
14b4df7d-11fa-5291-b07d-d3321993f186 | note | Standard / Specification - NZTA M10:2020 - 9
d0d77ece-3601-5a32-a8a4-b6f207f5a75f | note | Verifying Document - Lab Report
077ac7c2-8709-56cd-ad9c-c9e168b7e7be | note | Frequency - within 24 hours of them being cut from the pavement
0bf75b98-fefd-5da1-8e9b-5c3d49175da7 | note | Verification Activity: Activity - I
322348e7-1dcc-5ee1-b1be-2ac00775fdea | note | Verification Activity: By - PE
83bd1600-3b31-5d97-b7f5-9ae112a12dd7 | checkpoint | 14.03.12 - NDM Density
1f737c6b-18c3-5667-a544-e777f444ee21 | note | Acceptance / Conformance Criteria - NDMs are to be completed at the time of placing to ensure compliance when cores are taken
1c129f2c-4c22-5ffd-bb68-f194a19ff247 | note | Standard / Specification - NZTA M10:2020 - 9
670ea8b9-ac3f-5716-93fd-0dc2bdf69f5c | note | Verifying Document - IANZ Lab Report
e1b3dd2a-f7ed-50b9-944f-48794242dfbf | note | Frequency - min 8 per lot (day)
5751060e-c9c0-53a5-92b5-e8a9e6c7ae39 | note | Verification Activity: Activity - I
33b1405a-d778-575e-89b8-6a071c76ffa1 | note | Verification Activity: By - PE
da37be10-eee1-57da-b096-5f82b9b17e58 | checkpoint | 14.03.13 - Transverse truth of the surface
d1c323bd-c758-59e7-810f-9deda31d8137 | note | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge.
f0167bde-300d-5590-869d-65db4540e1dd | note | Standard / Specification - NZTA M10:2020 - 9
703a6e72-9a4b-504d-a329-539980446521 | note | Verifying Document - Site Notes
30b4a09f-c2f3-5b70-aa4a-371ad386ab7a | note | Frequency - Post Seal
544af562-4983-52c2-8eb1-edf2ef09e217 | note | Verification Activity: Activity - I
1f5316a9-09e9-57f5-8cc5-6b3b31674556 | note | Verification Activity: By - SE
58831243-e15b-5210-977d-b1addf9686cf | checkpoint | 14.03.14 - Finished Pavement Level, Alignment, and Thickness
4afe1778-5919-5248-a589-001b6d6007b1 | note | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements.
acdd77f4-944b-5e52-9f66-4804e93473fa | note | Standard / Specification - NZTA M10:2020 - 10
62709098-9887-5db3-b807-d925b1260643 | note | Verifying Document - Survey
8e25c3cb-d0b5-5a08-8f83-e3b72da45203 | note | Frequency - Continuous thought construction
d29ebaeb-15ed-5255-bac2-e60f4146b89c | note | Verification Activity: Activity - I
b5c198e8-827f-5fd3-a151-f48da734405e | note | Verification Activity: By - SE
858d1fca-02ce-5ab6-97d6-54293d261807 | section | 14.04 Construction Activity - NZTA M27 - Specification for stone mastic asphalt.
81cbcad2-8ee6-57c5-acf3-bf655c1f8dd0 | checkpoint | 14.04.01 - Construction Trail
22f18b53-cdde-5176-989d-bc9eefe59580 | note | Acceptance / Conformance Criteria - Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. SMA manufactured in the production trial can also be used in the construction trial provided that it meets the requirements of the specification.
7b9bb74c-cfa2-5597-ad9a-5e095ab21774 | note | Standard / Specification - PS 21.2.1 NZTA M27:2020 - 7
aaf2d37e-68c0-55f0-9cfe-83a3adcdf728 | note | Verifying Document - Test Results
f77558d1-84df-5611-a8dc-93a372845be3 | note | Frequency - As Required, two days before the site work is due to commence.
e65222d4-e7e6-5452-a1c8-76df14efd711 | note | Verification Activity: Activity - I
a003997b-d9b7-58ed-9dce-b8ab1c77d421 | note | Verification Activity: By - PE
6813627f-2d6c-5604-b669-1504a38bb377 | checkpoint | 14.04.02 - Paving Plan
b1ec0608-365d-5bb2-b67f-c421c09d3dba | note | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
b28257bf-7217-5973-b004-f4c9fa74d471 | note | Standard / Specification - NZTA M27:2020 - 8, 9
ac787f6a-9bae-5944-a901-ae4d9aaac9a6 | note | Verifying Document - Construction Work Pack
1af04a12-0a74-5be1-8fb6-83871eaf8715 | note | Frequency - 7 days prior to construction of the asphalt pavement.
cea49697-678d-5cef-9a1d-8f8952cac5d4 | note | Verification Activity: Activity - HP
2d005715-84b1-502f-9eaa-6a8241ee6cb3 | note | Verification Activity: By - ENG
359ddbf5-2f8b-55e0-896a-23e625ec62f2 | signoff | AUTHORITY HOLDPOINT
508d635d-807d-5c3c-9d1a-7dd6970a856c | checkpoint | 14.04.05 - Ambient Conditions for Placing
81bac104-b334-5a45-9d63-64b21af8359d | note | Acceptance / Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C,
f03994c9-77b6-530d-8c2f-558ee35442b1 | note | Standard / Specification - NZTA M27:2020 - 9
b9db0ec6-58af-52eb-97f8-235f5253a5d8 | note | Verifying Document - Site Notes
5d5c4faa-af20-510a-ada6-592199921cc8 | note | Frequency - Pre Seal
7841e6cc-d580-5235-b25d-8cad0408f059 | note | Verification Activity: Activity - H
0b98e9ff-0ba6-56ab-b876-b364bc5996fa | note | Verification Activity: By - SE
58f05e5d-7a8c-5186-a487-93541a70e98b | checkpoint | 14.04.06 - Tack Coating
7953cf7a-36aa-5799-8c61-43f0a69dc313 | note | Acceptance / Conformance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat. Where SMA is to be spread over clean, freshly placed asphalt, the Engineer can direct the Contractor to omit the tack coat.
a70d6d9c-6647-5fe8-9acb-685bc06e1ce8 | note | Standard / Specification - NZTA M27:2020 - 9
d3bfdf08-2b97-516f-a119-61cea4da9c55 | note | Verifying Document - Site Notes
b5067282-cf58-5a3b-a7b2-cd24fba11bfa | note | Frequency - Prior to Paving
74751138-fcee-5245-b411-b55e7dbd9637 | note | Verification Activity: Activity - I
4f6166b9-2c3d-5bed-84e9-fb0db4e97f2e | note | Verification Activity: By - PE
83aa1453-be4e-5785-a7df-eb150ff02789 | checkpoint | 14.04.07 - Asphalt Production Conformance - Grading and Binder
75daf60e-92c2-58ae-8052-dbe6ed17b088 | note | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass. Refer clause 5.2 and table 5.2 for frequency and tolerances
6c4284b8-596c-57a7-9f91-9b790f08111a | note | Standard / Specification - NZTA M27:2020 - Table 3.1, 5.1 & 5.2
6f1d544c-3c4e-5f5e-841f-9c7c3d5c33bc | note | Verifying Document - Test Results
5fb6d580-cfd9-59f1-903f-11bd8e125adb | note | Frequency - 1 per 200T
56f50ebf-60f2-503a-a2ad-a770b79da7ca | note | Verification Activity: Activity - I
4991cf81-436b-5346-aa41-a7abe2256a2b | note | Verification Activity: By - PE
a3439220-bcd8-539c-b5b7-63e66f3188ac | checkpoint | 14.04.08 - Asphalt Production Conformance - Volumetrics
bb7e0f54-aa14-4349-91e7-212e29b5cde1 | note | Acceptance / Conformance Criteria - Conforming volumetric testing. Refer clause 5.2 and table 5.2 for frequency and tolerances
ce3b7251-e0cb-4b88-a367-f403bbc96a00 | note | Standard / Specification - NZTA M27:2020 - Table 3.1, 5.1 & 5.2
0853c90e-bf26-41c8-92e7-6538b751de68 | note | Verifying Document - Test Results
8320575e-8a2d-4da3-a41c-5a27ba443f9a | note | Frequency - 1 per 600T
54efd82b-9749-4f35-ad11-15ebd7a452e6 | note | Verification Activity: Activity - R
a6f27267-3568-49ca-b9b4-dc9b8ccfbb74 | note | Verification Activity: By - SE
6bd3537e-614d-518b-9a75-d9d5e094a0e1 | checkpoint | 14.04.09 - Core Thickness
4cd24579-d854-5a5b-aba2-9562cb3a34f8 | note | Acceptance / Conformance Criteria - The nominal thickness for the set or lot of cores shall be equal to or greater than the specified nominal thickness.
0dd6064d-f181-5501-af32-08a67e31a87c | note | Standard / Specification - NZTA M27:2020 -
7bf37d05-85b4-5d2f-adbf-35d1f3c647b3 | note | Verifying Document - Lab Report
eeea7c7c-b548-5ae8-9938-b853552b8075 | note | Frequency - Mat - min 8 per lot (day) (1 for every 300 m²) Joints - min 3 per lot (1 for every 100m)
659649ff-e2e7-5311-9135-4ce4e211203a | note | Verification Activity: Activity - R
651d0b2f-3f74-52f9-b2af-c6781991ed3b | note | Verification Activity: By - SE
06d1fa65-7a70-5f7a-83ab-705c72fe901f | checkpoint | 14.04.10 - Mat Density
838f4067-0e84-587c-a9c1-a26d2a7f1591 | note | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be cut from the pavement at a rate of one core for every 300 m² with a minimum of eight cores representing each lot
138f2e70-b9aa-5773-aacb-36786feb1ab9 | note | Standard / Specification - ASTM D5361 NZTA M27:2020 - 9
e7728daa-3fc2-5088-908c-608cbc4e4eaf | note | Verifying Document - Cores
cf77ae37-a563-5609-92d6-66ccf9f5ea07 | note | Frequency - min 8 per lot (day) (1 for every 300 m²)
70a79e33-2ad5-54a7-bc83-26d4115c3631 | note | Verification Activity: Activity - R
fc7ace57-6422-558c-8ab3-19138b15df1c | note | Verification Activity: By - PE
c8413aac-02aa-5fea-b11f-87505c0c4dc1 | checkpoint | 14.04.11 - Joint Density
622930e3-00f6-552d-aa31-c256e4058d80 | note | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100 m of joint with a minimum of three representing each lot
a9f8ae40-1ffe-55a7-bfbd-2ea363614e1b | note | Standard / Specification - NZTA M27:2020 - 9
be08e55a-a75b-5617-99f7-24d38195b109 | note | Verifying Document - Cores
e5fe1c65-f179-5800-b918-5e45ebfb4ecb | note | Frequency - min 3 per lot (day) (1 per 100 m of joint)
f5a26cf6-cdec-5945-a569-3942afb0119d | note | Verification Activity: Activity - R
1125e27f-8fa7-565f-a417-835766816646 | note | Verification Activity: By - PE
b8164e79-0652-52a9-9c6a-4f1d1cb35924 | checkpoint | 14.04.12 - Density Testing
233a91ee-2917-5a51-8b6e-8e57ec7e7978 | note | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
83357bad-e322-5809-af31-9f76f3f29033 | note | Standard / Specification - NZTA M27:2020 - 9
8284a8da-0e9c-517f-8f11-d4e1d0e33ecb | note | Verifying Document - Lab Report
61e107d3-b518-5b3e-85fe-a42d6def7b15 | note | Frequency - within 24 hours of them being cut from the pavement
3d19c135-e5b0-501d-af79-d5c9a9938971 | note | Verification Activity: Activity - I
dd8f38f7-30fe-5685-ab5b-09fb21aa4972 | note | Verification Activity: By - PE
51784f52-b233-5853-afd7-e6dd19e4af60 | checkpoint | 14.04.13 - NDM Density
7fd49f39-9405-52cb-9894-f1da7e5a05fc | note | Acceptance / Conformance Criteria - NDMs are to be completed at the time of pacing to ensure compile when cores are taken
ad1a683e-ca6d-5829-883d-b54d8464c1ad | note | Standard / Specification - NZTA M27:2020 - 9
5388aa4c-5879-50bd-915c-c91b90e22f43 | note | Verifying Document - IANZ Lab Report
ab21c2c1-726f-5c20-82ef-8515cef56b36 | note | Frequency - min 8 per lot (day)
20c2a91c-acca-59a0-ba2c-923f014632a6 | note | Verification Activity: Activity - I
c2a10dbb-6c21-5dc1-af69-efd19e74dd2f | note | Verification Activity: By - PE
077a1b31-e544-5b86-81dd-d5cc05ae05a8 | checkpoint | 14.04.14 - Transverse truth of the surface
580339a4-b825-585b-bee4-8f48c863989f | note | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge.
a294d0d3-9efb-5cee-9300-5300651b7de4 | note | Standard / Specification - NZTA M27:2020 - 9
05e7d72b-748a-5121-a8e2-7283ca10981e | note | Verifying Document - Site Notes
76069f9d-df1f-57ee-8e5a-5953bd091621 | note | Frequency - Post Seal
e36d49f9-eabd-5f49-b68b-f46b0f1bd667 | note | Verification Activity: Activity - I
41a5fb06-69c4-55c9-b79b-318540313a5a | note | Verification Activity: By - SE
5e8d35db-3d51-5475-8ea9-89430aba78dd | checkpoint | 14.04.15 - Finished Pavement Level, Alignment, and Thickness
607fa103-bb2c-59b7-b05f-f9389cf67258 | note | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements.
e6fa4176-0244-529d-b067-4cbf82c409e0 | note | Standard / Specification - NZTA M27:2020 - 10
3137fe3e-8053-510f-95d9-8c60820511ee | note | Verifying Document - Survey
1cb820d7-d784-5e7e-9192-af2a516eda9a | note | Frequency - Continuous thought construction
24d7eb53-402d-5072-b865-82169e34b2da | note | Verification Activity: Activity - I
51d5fd0d-59d2-5eb0-94c9-2860cdfdd2a4 | note | Verification Activity: By - SE
35612da6-dfce-53fc-a4b0-a220727f10b6 | section | 14.05 Roughness
bcb7970f-6ae4-5bf2-b8e2-868871a1de0d | checkpoint | 14.05.01 - For a Chip Sealed Surface
0fd10073-e696-55ad-8e1c-5a1f2759847e | note | Acceptance / Conformance Criteria - Target is an average of 60 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 70 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km.
265d7cc3-784f-5480-977f-bcc16e56b72b | note | Standard / Specification - PS 21.4.1
376e40e7-df67-5369-960d-da07e0e8407d | note | Verifying Document - Test Report
aefb82f3-c2ca-5ec7-88cf-5dadfa0f2e7b | note | Frequency - Prior to sealing
281049c6-12d7-59cd-b596-f83270b3469f | note | Verification Activity: Activity - HP
c31949a9-36f6-5b77-b1db-7bacc2292ccd | note | Verification Activity: By - ENG
6c3ba941-1777-5501-9249-247d90f91522 | signoff | AUTHORITY HOLDPOINT
f8bd57a9-846b-5828-88de-6d7d62f6fd73 | checkpoint | 14.05.02 - For an Asphaltic Concrete Surface
93e626fc-8c78-56ca-9ea1-1a376c437383 | note | Acceptance / Conformance Criteria - Target is an average of 50 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 60 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km.
4c467b47-6741-59d2-b556-17a43be1b7cb | note | Standard / Specification - PS 21.4.1
194802ba-cb50-5bbb-bf77-c7fe4af70043 | note | Verifying Document - Test Report
4a6e636a-f4ed-5ab1-b5d7-17c772b1c1cf | note | Frequency - Prior to sealing
b223d344-2e29-505b-9875-908b5bb10eed | note | Verification Activity: Activity - HP
d1c6b7e9-fcde-5b2b-a4af-e53c40171533 | note | Verification Activity: By - ENG
b8bafe1f-4b75-5b87-857f-d269c0bcf8c8 | signoff | AUTHORITY HOLDPOINT
e16b3ed5-409b-5176-b427-1231353994c8 | section | 14.06 Skid Resistance
b0053e02-fe90-5f9b-8826-998d139bda13 | checkpoint | 14.06.01 - Skid Resistance
50d227a1-059d-5891-a73b-ee069d0a3343 | note | Acceptance / Conformance Criteria - The surfacing shall meet the requirements specified in the Transport Agency’s T10:2010 Skid Resistance Deficiency Investigation and Treatment Selection, and any other subsequent amendments.
9e1f44c0-131b-5ac5-8620-0f2e4b3fd271 | note | Standard / Specification - PS 21.5.1
fb9471c2-bef1-59b2-9536-5b222dc32078 | note | Verifying Document - Prior to Project Completion
7c0d8f4e-4145-55e8-b40c-c88ad073ed45 | note | Frequency - Prior to sealing
dfd410cb-e31e-55d4-9edf-7f7bb3c03fa9 | note | Verification Activity: Activity - HP
accab75d-bf4b-50dd-9e54-8b736e97f202 | note | Verification Activity: By - ENG
629b7c55-9012-52d8-befe-d8f7f7908625 | signoff | AUTHORITY HOLDPOINT
3c29e03e-01df-57ca-8b56-fd7eaaeaa08a | checklist | ITP - Pavement - Type C - 104.3 - Rev 3 | itp | ITP - Pavement - Type C - 104.3 - Rev 3
26844f90-2cb2-5c40-9048-6e2661d67d85 | section | 4.24 AP65 Subgrade Improvement Layer (SIL) - B/2 Materials (Pavement Type A,B,C)
e75edad3-1c86-5a1f-8bfc-6c857e9980f6 | checkpoint | 4.24.01 - Source Property Tests and Sampling
97b02390-ba74-5071-a989-65d19d1ded04 | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
f655ff7f-5be8-534c-96ae-6fd8d8ea5655 | note | Standard / Specification - PS 20.4.1
ca88be9a-f0ce-5226-80a1-10bde49e7257 | note | Verifying Document - IANZ Lab Reports
98a8e2c3-a654-553c-8e8c-67e23fdb2e39 | note | Frequency - 10,000m3
81c900f7-c3ec-5c50-a2d1-463f2843ec03 | note | Verification Activity: Activity - HP
d70b76d2-be8a-5d3c-85dd-1b89bfbd800b | note | Verification Activity: By - ENG
821e2d25-ab3d-56d6-9cfb-48b3ace0c405 | signoff | AUTHORITY HOLDPOINT
c4148dc8-e4d4-5aa8-8fef-8272efd80760 | checkpoint | 4.24.02 - Crushing Resistance
34ca198e-2550-5cd3-8784-efe9b3efefd1 | note | Acceptance / Conformance Criteria - The crushing resistance shall be not less than 100kN when the aggregate is tested in accordance with NZS:4407: Test 3.10
049c862b-1475-5dfd-9320-70688af5ea24 | note | Frequency - 10,000m3
b6069329-ba1f-5175-8985-d8f60d13dd70 | checkpoint | 4.24.03 - Weathering Quality Index
5ffcee71-e1fb-5ae3-81aa-1ac779395727 | note | Acceptance / Conformance Criteria - The aggregate shall have a weathering quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11.
b4bd14e0-be7c-521d-a3f5-ba0aca0be0ec | note | Frequency - 10,000m3
45df2110-45a1-588c-91e6-d377885c2a01 | checkpoint | 4.24.04 - CBR
2f03731e-cff2-583f-9eaa-675e932e92ec | note | Acceptance / Conformance Criteria - The material shall have a minimum CBR of 40 when compacted to New Zealand heavy compaction standard in accordance with NZS4402 Test 4.1.2 at water content between 4% and 6% by weight of aggregate. CBR testing shall be in accordance with NZS 4407 Test 3.15.
f9419b70-144c-52db-aed1-c81302f100ed | note | Frequency - 10,000m3
ab25b02a-711a-5787-97ca-cae645f22451 | checkpoint | Production Property Test Sampling
ce38af12-8ffc-57e3-be19-8eadcb4b3cf6 | note | Acceptance / Conformance Criteria - The SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
c90dbb5c-634c-588b-8c2b-9af0696567b8 | note | Standard / Specification - PS 20.4.1
1618c7d8-5d2a-5fb5-927a-ff35a9f090df | note | Verifying Document - IANZ Lab Reports
430e1fad-f43e-5dfa-9c3e-cbbc771f7a9d | note | Frequency -
5640e762-0351-51ea-b38f-001095a104a0 | note | – – – – – – – – – – – – – –
a7941b0a-cc7f-5415-ae4f-4879d5a7f5f5 | note | Quantity ¦¦ No. of Samples
78028f66-6b3e-501a-a62e-be2c8eb0c6a7 | note | – – – – – – – – – – – – – –
ce2f9d23-70c5-5787-95f6-a1c13e1f97b1 | note | 1 m3 to 400 m3 ¦¦ 2
afaf7960-c9cc-584a-8811-db3667762ceb | note | 400 m3 to 1,500 m3 ¦¦ 3
b8a21925-75f1-5993-a498-1dbe9ba81a35 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
e02a4721-aa19-57a9-b239-c0c4bff652a0 | note | – – – – – – – – – – – – – –
c66cbf73-31a1-5e89-b7f7-6521050d5fa0 | note | Verification Activity: Activity - HP
e0957a4b-9b15-5900-9b48-bf8cb6dcba34 | note | Verification Activity: By - ENG
8aaa1ba6-266e-5753-9a17-79ca51cfd9c2 | signoff | AUTHORITY HOLDPOINT
76f36ba6-c628-5d91-bad4-888b123dfe37 | checkpoint | 4.24.05 - Aggregate Fractions
44062c71-dee3-5a49-aa77-0dc75f232ccf | note | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 50% by weight shall have two or more broken faces. It shall be free of organic matter.
a4a99094-0e4f-544e-bf04-eff75738914e | note | Frequency -
54160454-41fb-5879-bc76-6371f5fd69e5 | note | – – – – – – – – – – – – – –
2d013838-baff-5fd9-a056-f1b84f32193b | note | Quantity ¦¦ No. of Samples
efe739af-eed8-5639-bf94-8fa4280369c4 | note | – – – – – – – – – – – – – –
d61d2364-9903-5d9d-a281-385973f99b22 | note | 1 m3 to 400 m3 ¦¦ 2
7ac96fa7-4f57-550b-b62e-83b7b23185fd | note | 400 m3 to 1,500 m3 ¦¦ 3
c182e1d4-89b9-5ba1-a66b-1a40a41ce2d4 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
4aa61d4f-df2f-529f-9bef-3b937e829faa | note | – – – – – – – – – – – – – –
1209906b-8364-5eca-8677-804139a6cda2 | checkpoint | 4.24.06 - Sand Equilavent
a3ab5492-9fef-5faf-84bd-88d3dbb2fdc4 | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 30 when the aggregate is tested according to NZS 4407: 1991: Test 3.6. The sand equivalent test may be neglected if the grading test shows less than 4% passing the 75-micron sieve.
a2fc2d6b-af85-533d-bdbd-4a9f37bbd34f | note | Frequency -
174ee001-bcd0-52d1-ae82-f2b0e11e1b76 | note | – – – – – – – – – – – – – –
a7add01f-1015-5d9d-8eb8-035b2cb6d2fb | note | Quantity ¦¦ No. of Samples
5f121f2f-3286-5e26-b507-599f4bdd34ab | note | – – – – – – – – – – – – – –
ba009307-41f7-50cc-8a82-14983b9491e3 | note | 1 m3 to 400 m3 ¦¦ 2
c02081cb-2ef4-5762-acd8-a8e8a1d0542d | note | 400 m3 to 1,500 m3 ¦¦ 3
c713ff0e-dab6-5b77-a05a-90a8be2dffa6 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
61ea755a-6149-5707-9094-eee637054bb7 | note | – – – – – – – – – – – – – –
f34df8ef-5ff5-5f46-a6b6-8daff95862ec | checkpoint | 4.24.07 - Plasticity Index
74d48e3a-f62a-5eb7-803b-762773025505 | note | Acceptance / Conformance Criteria - The Plasticity Index shall be no less than 8 when the aggregate is tested according to NZS 4407: Test 3.4.
3368dd96-565c-5aba-b7b1-249e8036491a | note | Frequency -
4982ea98-aadc-51b3-b10f-26681e01e239 | note | – – – – – – – – – – – – – –
972c6000-639e-5b21-9af0-f770b56b66c2 | note | Quantity ¦¦ No. of Samples
2a13463b-8473-566b-acff-358ec834203b | note | – – – – – – – – – – – – – –
0e5e0731-8399-5ed3-b009-a475aeb34edc | note | 1 m3 to 400 m3 ¦¦ 2
d5069ab6-5735-50d5-947b-4a2d7ad20054 | note | 400 m3 to 1,500 m3 ¦¦ 3
7a3ce371-2e90-55c1-97ef-0e8aaa3efc41 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
ace143d3-32f0-5da1-a3fa-bbe59d5072a2 | note | – – – – – – – – – – – – – –
29355a6c-cc0e-5a25-b68f-e8c21e9ded67 | checkpoint | 4.24.08 - Clay Index
10705005-dabb-5051-8986-8d3c1a1efc08 | note | Acceptance / Conformance Criteria - The Clay Index shall be no less than 5 when the aggregate is tested according to NZS 4407: Test 3.5
7857d978-d5b6-54c4-b7df-0460aad1107e | note | Frequency -
eb1379b9-7a97-53c4-b736-d8cae61a0555 | note | – – – – – – – – – – – – – –
49fd8f56-d72a-5dd6-b05d-318c8761196e | note | Quantity ¦¦ No. of Samples
3c99cb8e-793f-5dff-9e10-1b8e7664c377 | note | – – – – – – – – – – – – – –
cd31fac7-9df2-511a-a7c4-f6965ef64b43 | note | 1 m3 to 400 m3 ¦¦ 2
adb6e5c8-4c8f-55b4-b3ae-ee76cc074b0c | note | 400 m3 to 1,500 m3 ¦¦ 3
0b8c581f-bfc4-5e3c-b023-9168e0d93f1b | note | 1,500 m3 to 4,000 m3 ¦¦ 4
90acd120-4f97-57c0-a36a-62bd0c19a0bc | note | – – – – – – – – – – – – – –
be3abd89-23f0-57a2-953e-bd23a6a8c558 | checkpoint | 4.24.09 - Wet Sieving
a9d6da2e-d40c-5906-9f4f-462bf4ede5b8 | note | Acceptance / Conformance Criteria - When tested according to NZS: 4407: Test 3.8.1 Standard Method by Wet Sieving or Test 3.8.2 Subsidiary Method by Dry Sieving, the grading of the aggregate shall fall within their respective envelopes defined below or as directed by the Engineer.
507cdb47-5d15-5816-9920-89fb42b499df | note | Frequency -
2e73974d-053e-5c13-93e0-3a102ab8faa0 | note | – – – – – – – – – – – – – –
cd861873-0bf6-5e9f-953d-81bdc77f758f | note | Quantity ¦¦ No. of Samples
51d5fe8a-e9ad-59a8-bbd2-b16b0c00d867 | note | – – – – – – – – – – – – – –
bc50d507-237c-5cbb-ab63-2525ce910f68 | note | 1 m3 to 400 m3 ¦¦ 2
7a3d8bf6-bc45-541a-bbb6-9159c939c8f7 | note | 400 m3 to 1,500 m3 ¦¦ 3
058d7951-8047-5304-9ae1-6fbcedcf545f | note | 1,500 m3 to 4,000 m3 ¦¦ 4
1996ae3d-f0aa-5177-b7f3-e3f59b236629 | note | – – – – – – – – – – – – – –
c124d68f-2b35-5659-b3a4-c565239e94ef | checkpoint | 4.24.10 - Testing for Layer Compaction - MDD
cb4cdbaf-0397-5691-b19a-18f847e3a91c | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for SIL construction shall be the maximum laboratory dry density using Heavy compaction.
352e5519-d11d-5dc8-974e-93397b4043e0 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.4.1
38d32e5c-6c10-5ab0-8a1d-7e9e17ac96e6 | note | Verifying Document - IANZ Lab Reports
28bf0dd5-abe9-56f9-9ccc-35bf2fd61e4d | note | Frequency - 5,000m2
93716a10-f40d-5ae3-8e99-e1a2d74e49ed | note | Verification Activity: Activity - R
03297927-5339-59a0-b852-3c5726397674 | note | Verification Activity: By - PE
fcc197d6-6ca4-522c-9a22-98f87561493a | section | 4.25 WHAP65 Sub-Base - B/2 Materials (Pavement Type C)
fc2530bb-d29f-5bbe-bfec-07d181dce84b | checkpoint | 4.25.01 - Source Property Tests and Sampling
a8f13a26-c351-57d2-b0e9-d2f18d75ab34 | note | Acceptance / Conformance Criteria - The WHAP65 Sub-Base shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
bc69cc76-e826-58b4-ac22-59c5f9265dae | note | Standard / Specification - PS 20.5.1.1
3d90418d-cfca-5464-a706-d95d682fefb5 | note | Verifying Document - IANZ Lab Reports
a9cf5c55-eb12-5963-a497-afae683d64ce | note | Frequency - 10,000m3
4d71ad46-3cc0-5867-9e3b-6eac2f2e9f66 | note | Verification Activity: Activity - HP
d1eab7ae-bfa0-5e90-9859-ce4115034e27 | note | Verification Activity: By - ENG
6bc62c6a-6519-55bc-816e-58f1c41ee4ca | signoff | AUTHORITY HOLDPOINT
6d607d84-976e-5314-8f5f-7fbe54f578ef | checkpoint | 4.25.02 - Crushing Resistance
14329cf7-fafb-5fb4-b723-cc86e0720f4c | note | Acceptance / Conformance Criteria - The crushing resistance shall be not less than 130kN when the aggregate is tested in accordance with NZS:4407: Test 3.10
5a6d9e71-f384-5f09-879e-bacde24b67cb | note | Frequency - 10,000m3
e86afacf-6723-5cb0-a64e-bc764e64fbec | checkpoint | 4.25.03 - Weathering Quality Index
86b9f33b-7ec6-581c-9db3-723504e70c8d | note | Acceptance / Conformance Criteria - The aggregate shall have a weathering quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11.
fd1d3ca1-83d1-5500-994e-f539811fda03 | note | Frequency - 10,000m3
3756364c-8ae0-5a6c-a0cb-4a539341cc5c | checkpoint | 4.25.04 - CBR
2ec973f0-92c5-5b37-afb5-c71bebcc539c | note | Acceptance / Conformance Criteria - The material shall have a minimum CBR of 40 when compacted to New Zealand heavy compaction standard in accordance with NZS4402 Test 4.1.2 at water content between 4% and 6% by weight of aggregate. CBR testing shall be in accordance with NZS 4407 Test 3.15.
94f1a454-92dc-5bc3-9cf4-629c174281b1 | note | Frequency - 10,000m3
23b4ad42-6d83-400f-9359-35c5aca1b04a | checkpoint | Production Property Test Sampling
83f7efb1-2972-578e-9f66-636070f3eee6 | note | Acceptance / Conformance Criteria - The WHAP65 Sub-Base shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
1f10bfd3-082c-5107-9583-2ef8d0171bfb | note | Standard / Specification - PS 20.5.1.1
fd7af1aa-953b-5733-b6a8-3c19df9117ce | note | Verifying Document - IANZ Lab Reports
ae2e3654-3c4d-5c9c-8fe9-a00e4d024351 | note | Frequency -
bd8d73ca-2be0-531b-b2ce-5abd911ab562 | note | – – – – – – – – – – – – – –
d357494a-8de5-5d54-8953-cec3b5a7e1e3 | note | Quantity ¦¦ No. of Samples
63696a70-5db6-592a-8983-e330e1465b1e | note | – – – – – – – – – – – – – –
079bfa55-fb87-58d6-96c5-923af4e421a4 | note | 1 m3 to 400 m3 ¦¦ 2
78d732cc-f745-5bb0-bc56-af8093f424fa | note | 400 m3 to 1,500 m3 ¦¦ 3
f9b7293c-deee-512a-8d78-cad39b5eaa8e | note | 1,500 m3 to 4,000 m3 ¦¦ 4
711e8a8a-cea0-51a0-aeab-5afa32fb193f | note | – – – – – – – – – – – – – –
bb7a97eb-523c-576b-8f13-cf2d954815c1 | note | Verification Activity: Activity - HP
d6f655b1-9b34-59ad-970d-a9fc03ba4be0 | note | Verification Activity: By - ENG
f5b6eb17-28bc-5490-86e6-5f5c52ade99e | signoff | AUTHORITY HOLDPOINT
89adf437-af1b-5196-8f02-8ffd3c2a93c2 | checkpoint | 4.25.05 - Aggregate Fractions
13928abe-31ae-5288-8e03-43e249ef1e1f | note | Acceptance / Conformance Criteria - In each of the aggregate fractions between the 63.0mm and 4.75mm sieves, not less than 50% by weight shall have two or more broken faces. It shall be free of organic matter.
741d69c2-dd44-5169-b550-3a7d521a1629 | note | Frequency -
4eb2772a-e1e7-52dd-8ff5-2fe92ca101bf | note | – – – – – – – – – – – – – –
e52e91bb-a8ad-5e39-b52b-6585735f0058 | note | Quantity ¦¦ No. of Samples
d2ed5158-a47f-581c-860a-f2748d47b037 | note | – – – – – – – – – – – – – –
760d31e1-2332-590c-addf-040ef3d36a21 | note | 1 m3 to 400 m3 ¦¦ 2
76ac27ad-d68c-5520-beb7-00ce7b9e6319 | note | 400 m3 to 1,500 m3 ¦¦ 3
40d4bd88-d405-5ffc-95c7-9a996b0addee | note | 1,500 m3 to 4,000 m3 ¦¦ 4
aabd9365-b848-57e8-ba2f-c4046277281f | note | – – – – – – – – – – – – – –
20d86d11-82fb-58df-96d2-4d7d2b63e3fa | checkpoint | 4.25.06 - Sand Equilavent
246554ab-2055-5770-8d10-1a8edd074bfc | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 25 when the aggregate is tested according to NZS 4407: 1991: Test 3.6. The sand equivalent test may be neglected if the grading test shows less than 4% passing the 75-micron sieve.
77c24f7f-92f5-5b6b-8cbb-bb8b9379a1dc | note | Frequency -
84e458d0-1844-51c8-9d6f-97db5927ca75 | note | – – – – – – – – – – – – – –
5bc31d42-8629-5e8a-b1fa-aab557922ef9 | note | Quantity ¦¦ No. of Samples
51ab78c7-d082-5473-9dff-c7914111c13a | note | – – – – – – – – – – – – – –
b56f5e64-1058-550b-af3f-800640444858 | note | 1 m3 to 400 m3 ¦¦ 2
fb4094fc-15b1-56d4-b05a-69ee629e119c | note | 400 m3 to 1,500 m3 ¦¦ 3
ede761c4-3bcc-5191-916b-1b0c6cb3a964 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
429b4b03-fd7b-5508-8db6-eb33fd2afb5c | note | – – – – – – – – – – – – – –
19c242c3-ad60-5004-8e4f-2ad098c0d4e3 | checkpoint | 4.25.07 - Wet Sieving
82a45f6b-434b-57f0-84f2-cf2246bfa00a | note | Acceptance / Conformance Criteria - When tested according to NZS: 4407: Test 3.8.1 Standard Method by Wet Sieving or Test 3.8.2 Subsidiary Method by Dry Sieving, the grading of the aggregate shall fall within their respective envelopes defined below or as directed by the Engineer.
f2dfc277-c1e2-59f3-9067-9e2241204ae4 | note | Frequency -
bb6c49a4-e349-5c19-93a8-1fe11f250df1 | note | – – – – – – – – – – – – – –
e46accd0-995d-5f90-953e-66259599ceed | note | Quantity ¦¦ No. of Samples
60ce39be-31dd-5868-8fb1-3cabe5c4e06b | note | – – – – – – – – – – – – – –
7248e531-0646-5477-be4d-27b3231882b0 | note | 1 m3 to 400 m3 ¦¦ 2
15b785c2-1dac-5bb7-8330-11a6038c634e | note | 400 m3 to 1,500 m3 ¦¦ 3
c567e4e0-3639-57f9-bd9f-6fc69cf23206 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
806c6fc1-e528-5887-94c8-61db133c5dd2 | note | – – – – – – – – – – – – – –
dae3318f-7c6a-59f2-a076-4c300b882da3 | checkpoint | 4.25.08 - Testing for Layer Compaction - MDD
57776726-1e39-5f41-9b00-d24b0c516d2b | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for WHAP65 Sub-Base construction shall be the maximum laboratory dry density using Heavy compaction.
8fcadab5-0e99-511c-88a9-c6f5089f30e9 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.5.11
3ae62e1f-25ec-576e-b07c-77c66b8d7091 | note | Verifying Document - IANZ Lab Reports
615a3237-fba4-5921-bd60-03a75d79c30d | note | Frequency - 5,000m2
dd9e1393-43ea-5bf3-938d-950ad8e9ef17 | note | Verification Activity: Activity - R
485a8a65-99b6-51b5-be2e-b4228cb984a9 | note | Verification Activity: By - PE
c12729c5-67f6-5d43-b1f2-57394d510061 | section | 4.26 GAP65 Subgrade Improvement Layer - B/2 Materials
347684f7-e1c7-5e11-ad68-cbfef2b04889 | checkpoint | 4.26.01 - Source Property Tests and Sampling
cc4b0ca0-bb16-59ac-98d7-fab289a87514 | note | Acceptance / Conformance Criteria - The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, and California Bearing Ratio.
b0cb1c89-274b-54ad-8937-6687de1b2280 | note | Standard / Specification - PS 20.9.1
474d62b0-7aec-5c22-8fcd-1182638533b6 | note | Verifying Document - IANZ Lab Reports
6a3a4eb1-2b53-5e98-8a64-800db2e98117 | note | Frequency - 10,000m3
0a21a303-31e4-50c4-bd6f-435b3d528a7e | note | Verification Activity: Activity - HP
d95c7dc3-dbf2-52b8-9ac2-a9429141a539 | note | Verification Activity: By - ENG
21763a79-b0fc-5f07-a2bc-5a044a2a7ee3 | signoff | AUTHORITY HOLDPOINT
c80204b2-f1b8-5861-9b87-7b0389a79aa0 | checkpoint | 4.26.02 - Production Property Test Sampling
6bc46dc5-d457-578e-81f8-6ad5874f1983 | note | Acceptance / Conformance Criteria - The GAP65 SIL shall be sampled and tested by an IANZ Accredited laboratory for Quality of Fine, Broken Face Content, Grading, Aggergate Fractions, and Be free of organic matter.
c93ec2a6-bcd5-59fc-a768-150f4b927a83 | note | Standard / Specification - PS 20.9.1
8b6de2aa-d40f-5217-87f3-60eba71f1d94 | note | Verifying Document - IANZ Lab Reports
5371154e-3681-5f51-a53e-9d3e7d5b64a6 | note | Frequency -
277e7c23-7311-543e-b351-7ca46149514c | note | – – – – – – – – – – – – – –
0070ff59-c84f-5c50-9d2a-f7df388f4493 | note | Quantity ¦¦ No. of Samples
1edc09b9-e7dd-5d23-a029-ce6be2856285 | note | – – – – – – – – – – – – – –
17dce437-1113-56a9-a36b-28343194af6b | note | 1 m3 to 400 m3 ¦¦ 2
c32af8d2-50ca-5d05-997c-abd28533d6ca | note | 400 m3 to 1,500 m3 ¦¦ 3
6cb4eb9b-ac2b-5b7f-9e4f-10d94e721e54 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
f8d3ad66-41dc-587e-a388-02355db18654 | note | – – – – – – – – – – – – – –
a51c1eaa-3a20-5f00-93d1-28efb17fd6fd | note | Verification Activity: Activity - HP
5a340bf6-745d-59d0-b59b-bd70444cbc8e | note | Verification Activity: By - ENG
fcbd0b78-66c4-52db-a924-1c9d0e913898 | signoff | AUTHORITY HOLDPOINT
0af9249c-48a9-550f-ae9e-c6f4cfa0fd7d | checkpoint | 4.26.03 - Testing for Layer Compaction - MDD
7086840f-c8e1-56ac-83a3-36fa6c768e26 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for GAP65 SIL construction shall be the maximum laboratory dry density using Heavy compaction.
b2619c76-9294-59e2-93eb-cefb3d598ae5 | note | Standard / Specification - TNZ B/02: 2005 - 7.5 PS 20.9.1
e1726dd0-22c2-5af9-9035-78867377b425 | note | Verifying Document - IANZ Lab Reports
d0a6bd79-9c82-53d1-a8fc-e9e726dec88a | note | Frequency - 5,000m2
8a32a366-fb96-535c-a0ef-03d785ef6d68 | note | Verification Activity: Activity - R
591c6031-87ad-5144-aaac-f99b72a97753 | note | Verification Activity: By - PE
ee46d9de-2d20-542a-8078-e0ba5906a077 | section | 4.28 TNZ M/4 - AP40 Material Approval (Pavement Type C,D)
b4bd8b1a-51db-5104-8b72-fbefe05bcef1 | checkpoint | 4.28.01 - Crushing Resistance
1fbfa52c-b2e4-5a84-abd5-44dbe1f5a547 | note | Acceptance / Conformance Criteria - When tested in accordance with NZS 4407 : 1991, Test 3.10, The Crushing Resistance Test, under a load of 130 kN less than 10% fines passing 2.36 mm sieve size shall be produced.
56e33568-98e7-5760-a1fa-6c9431b3ddd3 | note | Standard / Specification - TNZ M/4 Spec Clause 3.3.1
f1be62b8-1967-42c6-af3a-b327c7a9f148 | signoff | AUTHORITY HOLDPOINT
e3cffbdf-b3a4-5366-860b-78de7ad605e4 | checkpoint | 4.28.02 - Weathering Quality Index
7be13d64-f11f-5522-ab24-cc5c210e0436 | note | Acceptance / Conformance Criteria - The aggregate shall have a quality index of AA, AB, AC, BA, BB or CA when tested according to NZS: 4407: Test 3.11.
0624fc54-42c2-5b0a-895a-55fec4d46a82 | note | Standard / Specification - TNZ M/4 Spec Clause 3.3.2
8f1d7a62-d6a1-48f2-afba-ae417e525b86 | signoff | AUTHORITY HOLDPOINT
34614a9a-68dc-581d-9d21-8c83eba35977 | checkpoint | 4.28.03 - CBR
c3afaa46-23fd-5291-a634-769b1c64d51d | note | Acceptance / Conformance Criteria - The sample shall be:
d3d2b88e-21e1-50be-8235-0b38130d7ebb | note | (a) compacted in accordance with NZS 4402 : 1986, Test 4.1.3 New Zealand
82ceda09-ce56-5ccf-996b-625b9d445aad | note | ○ Vibrating Hammer Compaction Test at Optimum Water Content and;
e9c4ba93-b82c-51de-931f-1491023eec74 | note | (b) tested in accordance with NZS 4407 : 1991, Test 3.15 The California Bearing Ratio Test (without a surcharge for at least 4 days). The soaked CBR of the basecourse aggregate shall not be less than 80%.
2ecdd748-d537-5302-a456-03c9cd972a9f | note | Standard / Specification - TNZ M/4 Spec Clause 3.3.3
caa8b2ef-b8d2-494e-ab6b-735706eb7404 | signoff | AUTHORITY HOLDPOINT
dd1269bf-c139-5b0b-9f86-6d462b82491e | checkpoint | 4.28.04 - Sand Equivalent
d3b7a8e0-c9d5-550a-b5f0-fad6f2a2244f | note | Acceptance / Conformance Criteria - The sand equivalent shall not be less than 40 when the aggregate is tested according to NZS 4407: 1991: Test 3.6.
505ded73-c812-5ae2-b6ab-71e239ff33a9 | note | Standard / Specification - TNZ M/4 Spec Clause 4.2.1.1
f508efd0-507f-506c-9c49-37ad6967b00b | note | Frequency -
c9f3c8b4-f615-5f81-8ac9-51df60fcb3b2 | note | – – – – – – – – – – – – – –
e252bc62-65ec-57b4-835a-3fc2e5e6688f | note | Quantity ¦¦ No. of Samples
0a537518-5d47-54ff-9571-0ba54d8c9dc0 | note | – – – – – – – – – – – – – –
e7bcf5fe-e871-5652-bb7b-01f3a8a1fbc9 | note | 1 m3 to 400 m3 ¦¦ 2
aef69a2f-a465-5a3d-a587-2b2b82e51c73 | note | 400 m3 to 1,500 m3 ¦¦ 3
3e6f3148-fd75-5e5c-9eeb-a46d99f29320 | note | 1,500 m3 to 4,000 m3 ¦¦ 4
b04ce6fc-ffec-51c5-8489-03867890d629 | note | – – – – – – – – – – – – – –
fe3116fd-3727-4aad-ab47-067a8c067815 | signoff | AUTHORITY HOLDPOINT
eebf1315-6ac8-59e0-98e9-e2c8b90895a4 | checkpoint | 4.28.05 - Clay Index
2441e717-1ba0-571c-99de-b8f48a304527 | note | Acceptance / Conformance Criteria - The clay index of the fraction of basecourse passing the 75μm sieve shall not be greater than 3 when the aggregate is tested according to NZS 4407 : 1991, Test 3.5 Clay Index Test.
39c6491c-54e8-5ba6-b071-88fe84187357 | note | Standard / Specification - TNZ M/4 Spec Clause 4.2.1.2
a7325f33-4145-4ea9-872b-627179973d94 | signoff | AUTHORITY HOLDPOINT
3bc61e30-01eb-5429-976f-6011c174c9d1 | checkpoint | 4.28.06 - Plasticity Index
b5f2b1d9-1318-5c7f-aa2f-434ae5beb307 | note | Acceptance / Conformance Criteria - The plasticity index of the fraction of basecourse passing the 425μm sieve shall not be greater than 5 when the aggregate is tested according to NZS 4407 : 1991, Test 3.4 Plasticity Index Test.
90db7f8b-7b3f-506e-8154-c91808c97b3a | note | Standard / Specification - TNZ M/4 Spec Clause 4.2.1.3
35ac47af-f5ee-47cf-ba3e-3a32df240b2d | signoff | AUTHORITY HOLDPOINT
f737f452-29e1-5908-b6b1-93f47be68777 | checkpoint | 4.28.07 - Broken Face Content
00396ff3-667a-59d6-b9b8-729e110900ca | note | Acceptance / Conformance Criteria - The aggregate broken face content in each of the three aggregate fractions between the 37.5mm and 4.75mm sieves shall not be less than 70% by weight and shall have two or more broken faces, when tested according to NZS 4407 : 1991, Test 3.14 Broken Face Test.
99eeadc8-c1be-5654-972b-b7913a6e1597 | note | Standard / Specification - TNZ M/4 Spec Clause 4.2.2
bdab8a36-b336-4ec9-862d-5b14d0184747 | signoff | AUTHORITY HOLDPOINT
d11ec0c1-35aa-57ae-9884-16fcd3a95e7a | checkpoint | 4.28.08 - Particle Size Distribution
7c7fc213-46a7-5d33-a69b-7ebbf22ebbf7 | note | Acceptance / Conformance Criteria - The particle-size distribution of the aggregate shall conform with the envelope limits defined in both Tables 2 and 3 below, when the aggregate is tested according to NZS 4407 : 1991, Test 3.8.1 Wet Sieving Test.
09f7607f-1f44-5336-abda-5505c751ac4c | note | ○ If testing has been performed to show that the dry sieving method is not significantly different to the wet sieving method at 95% confidence limit for the same aggregate then dry sieving method may be used.
8c535914-1991-5a58-a217-959178f02288 | note | – – – – – – – – – – – – – –
f9ab8ff8-5e53-56cf-bc34-3989f1e4d73e | note | Table 2: Particle Size Distribution Envelope Limits for an Individual Sample
9884a93f-7326-5fda-af98-71e1492718f7 | note | Test Sieve Aperture ¦¦ AP40 (Max size 40mm) ¦¦ AP20 (Max size 20mm)
85119f70-3fa9-5053-a4b7-b1a51239dbb1 | note | – – – – – – – – – – – – – –
9cb6f73d-781c-5a0b-9114-ede56e2b382c | note | 37.5mm ¦¦ 100 ¦¦ -
638402af-2694-5d62-8ef1-23f46e253820 | note | 19mm ¦¦ 66 - 81 ¦¦ 100
56f4993d-7a77-5aa8-b54d-b8aad4ad121f | note | 9.5mm ¦¦ 43 - 57 ¦¦ 55 - 75
f1a799f8-336b-5161-90bc-bce86e1d275c | note | 4.75mm ¦¦ 28 - 43 ¦¦ 33 - 55
1902d3f0-607a-56b6-9e3a-916cd0b0dc71 | note | 2.36mm ¦¦ 19 - 33 ¦¦ 22 - 42
20daf1c2-a2a0-5daf-9cf8-24341d9d697f | note | 1.18mm ¦¦ 12 - 25 ¦¦ 14 - 31
bdac4d50-f763-52cc-81db-cd5ab7acf024 | note | 600µm ¦¦ 7 - 19 ¦¦ 8 - 23
c07d9ad4-1e23-53dc-b692-05bdee2d6a03 | note | 300µm ¦¦ 3 - 14 ¦¦ 5 - 16
282d1bf8-40dc-5dc5-82cb-2b4a46d7abf9 | note | 150µm ¦¦ 0 - 10 ¦¦ 0 - 12
d72793d5-a3c3-572c-a2cc-f30fbdc9d789 | note | 75µm ¦¦ 0 - 7 ¦¦ 0 - 8
8bf1782d-e56a-51cd-98a3-d203fc8da7b3 | note | – – – – – – – – – – – – – –
60252523-57d3-52c1-9324-c12ce1f159cf | note | – – – – – – – – – – – – – –
84a8031d-50ca-587f-8d51-4a5bee955694 | note | Table 3: Particle Size Distribution Shape Control
aba99fa3-42fc-5905-9dd6-1ce36a0e48b6 | note | Fractions ¦¦ AP40 (Max size 40mm) ¦¦ AP20 (Max size 20mm)
44a55009-48d5-5e28-b1cf-474e463255b0 | note | – – – – – – – – – – – – – –
2c6aded4-33da-5abd-8726-a6c5f43ada29 | note | 19mm - 4.75mm ¦¦ 28 - 48 ¦¦ -
1fe29cae-76ad-5ae6-8a83-a08cc185c517 | note | 9.5mm - 2.36mm ¦¦ 14 - 34 ¦¦ 20 - 46
913e14ac-ad96-51b8-b9d7-e238f26455bb | note | 4.75mm - 1.18mm ¦¦ 7 - 27 ¦¦ 9 - 34
8ce58a7d-2252-550a-8121-36cabbdfde3c | note | 2.36mm - 600µm ¦¦ 6 - 22 ¦¦ 6 - 26
0011a6ae-a4cb-54cc-974c-71322bf4aa2f | note | 1.18mm - 300µm ¦¦ 5 - 19 ¦¦ 3 - 21
7b9a35fc-c1fe-55f9-90ad-531d7ed9ad5b | note | 600µm - 150µm ¦¦ 2 - 14 ¦¦ 2 - 17
22524664-0d5b-52f0-9721-68c0dd9fd92a | note | – – – – – – – – – – – – – –
695a3efc-190a-551d-8b8d-aad9cde8c3f2 | note | Standard / Specification - TNZ M/4 Spec Clause 4.2.3
4d7e8e96-fcd5-4378-9c40-b4bbd3c2b01e | signoff | AUTHORITY HOLDPOINT
81ce5302-4df9-5604-91cc-74835b78f200 | checkpoint | 4.28.09 - Testing for Layer Compaction - MDD
c6f091b5-3aa4-5b52-a982-323906b3e218 | note | Acceptance / Conformance Criteria - The Maximum Dry Density (MDD) for construction shall be the maximum laboratory dry density at optimum water content (OWC).
a683443f-9dc9-5e4f-8d92-c40231a63de5 | note | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.5 NZS 4402:1986 - 4.1.3
dd4864a1-4353-54c7-a0f0-f93f10558a33 | note | Verifying Document - IANZ Lab Reports
924a90df-3b51-5197-8ae4-2190e1f5f672 | note | Frequency - 5,000m2
eada4bcb-f3ec-5ee7-b4fe-613751238e9e | note | Verification Activity: Activity - R
02b670c2-b4be-5547-b9f8-ea967133c102 | note | Verification Activity: By - PE
36d05abe-d8a2-4bbf-a0ac-f042c0fa5dd1 | signoff | AUTHORITY HOLDPOINT
4b8b3e3f-abfb-552c-8b9a-d02e9d221fa8 | section | 4.32 Sealing Chip Supply
dc0bdfbb-dcfe-5f1b-864a-6564086b5926 | checkpoint | 4.32.01 - Sealing Chip - Source Property Tests and Sampling
ad87f6ad-c244-528a-83db-e4468d26eafb | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Resistance, Weak Particles Test, Skid Resistance, and PSV
9a8b95c7-e9db-5c2f-87fc-7051d239ceed | note | Standard / Specification - PS 21.1.1 TNZ M/6: 2019 - 4
0ac25cc5-1a48-5bb1-b6b2-83d091d5d0e3 | note | Verifying Document - IANZ Lab Reports
2e8b71df-daee-556d-9547-dd7463c0bfc8 | note | Frequency - Before Supply and Every 10,000m3 Thereafter
926d9318-1881-5ba3-baed-7efdcf5a81a7 | note | Verification Activity: Activity - R
510b70d3-1109-5cfd-b6ad-77794dde91c1 | note | Verification Activity: By - SE
14761c8b-a8dc-52c5-ac4b-8b828dbd7c6f | checkpoint | 4.32.02 - Sealing Chip - Production Property Test Sampling
666ec528-5828-5829-a84d-43522ddbd668 | note | Acceptance / Conformance Criteria - The Sealing Chip shall be sampled and tested by an IANZ Accredited laboratory for Cleanness, Size and Shape, and PSD for G5 / G6
91e227f6-2f15-5058-bcf2-e6b6b158526b | note | Standard / Specification - PS 21.1.1 TNZ M/6: 2019 - 5
32049d0f-ebba-58ea-b1e6-05a6384ca678 | note | Verifying Document - IANZ Lab Reports
956a58c6-e226-5f05-951b-42802a261cee | note | Frequency - Every 500m3
e72c2825-37d0-5326-a4c5-0e9e84f0d72b | note | Verification Activity: Activity - R
5583b441-aba2-5432-9289-7407aa379f2b | note | Verification Activity: By - SE
ba197f5f-8424-5ec1-a3d9-dadedbf26007 | section | 4.33 Bitumen Supply
1c072438-aaf9-58a3-9d3f-4562dc4413df | checkpoint | 4.33.01 - Bitumen - Quality Testing
4ca4334a-e9bb-53ac-9eca-a281a99b546b | note | Acceptance / Conformance Criteria - The binder grade shall be a performance-graded binder complying with the requirements of NZTA M01.
51d9559d-a3cc-57e3-9a53-d6a0b83cc038 | note | Standard / Specification - PS 21.1.1 NZTA M01: 2022 - 6
66116f83-3179-5c80-bb73-6100596d2e26 | note | Verifying Document - IANZ Lab Reports
47e13aad-b943-5bc2-8079-0cd4c07563a2 | note | Frequency - One test per grade supplied
bb5407d5-0e8f-51b9-a82f-cca891bb5290 | note | Verification Activity: Activity - R
7d076bcd-0635-518c-9995-993f81ca5730 | note | Verification Activity: By - SE
2e0b4d70-3e4a-54f0-9c3c-db969a116315 | checkpoint | 4.33.02 - Bitumen - Supply Testing
f4040a8d-1ea0-5b8c-9386-052a3ab214a5 | note | Acceptance / Conformance Criteria - The binder shall have benchmark parameter testing completed complying with the requirements of NZTA Q05.
cdcdf68c-c632-5e21-8fa7-23e206ba7152 | note | Standard / Specification - PS 21.1.1 NZTA Q05: 2022 - 6.2
5556ad42-254f-5244-b15e-9a07e2cd71da | note | Verifying Document - IANZ Lab Reports
4cc63031-b0eb-511e-9171-9c48c30a0a18 | note | Frequency - Every 200 tonnes supplied.
66842384-871c-54b3-a944-7515491f6473 | note | Verification Activity: Activity - R
16095d54-614b-5ec0-9bc1-62b003e5b888 | note | Verification Activity: By - SE
2b18b70e-b064-539a-bbe2-652876ead08a | checkpoint | 4.33.03 - Adhesion Agents
ffb43967-0be2-5d2f-a207-9fbaaaa4aece | note | Acceptance / Conformance Criteria - When used, Adhesion agents must be approved & blended in accordance with the requirements of TNZ M/13 Specification for Adhesion Agents.
010bec37-a75f-516d-98c6-95d646fc1bfe | note | Standard / Specification - TNZ M13
9c5a5193-33e0-5a32-ac57-d2aff7a86788 | note | Verifying Document - Binder Aggregate Adhesion Test
8c09b981-c8da-5015-8ab7-93d4ce69510a | note | Frequency - Each Adhesion Agent and Dosage Rate for a Particular Chip Source
5e8bb625-65e3-5d78-b26b-f0eab333ead4 | note | Verification Activity: Activity - R
43c43e28-38c3-5c32-a58c-3526351f6d65 | note | Verification Activity: By - SE
8f4bd0a5-2c00-5e11-be9d-a8061092d736 | checkpoint | 4.33.04 - Sprayer Certification
2449702d-d379-5391-b576-df9ac1a55eb3 | note | Acceptance / Conformance Criteria - The binder shall be applied with a bitumen distributor, operated in accordance with BCA E/2, Specification for Performance of Bitumen Distributors administered by the New Zealand Bitumen Contractors' Association Inc.
4156efd2-44fb-5dce-992f-0b9d5b4ba392 | note | Standard / Specification - TNZ P3 TNZ P4
633090d0-58e6-5120-9cb5-40a6f526fe99 | note | Verifying Document - E2 Cert
ee4b3739-a7d1-5d21-8bd6-b431608b32b9 | note | Frequency - Each Sprayer
585c52d1-12cb-5070-a9e6-a473b7b77d70 | note | Verification Activity: Activity - R
f39d2962-8a3e-5519-902f-48a7fca91664 | note | Verification Activity: By - SE
80572c52-4639-5317-a3b8-448a7a44836e | section | 13.02 AP65 Subgrade Improvement Layer Pavement Type A,B,C
34462ba7-0596-5d92-aa44-3f4c0644d233 | checkpoint | 13.02.01 - Material Placement
46f75dd5-1f24-510e-9232-dc89dc86b27c | note | Acceptance / Conformance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout
fbb14917-43f4-506b-8891-6cd5f4e17a92 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 5.1
5bac546a-f862-5f5e-acf6-d8971cf9a36f | note | Verifying Document - Survey / Level Checks
913b69f8-de28-56cf-b8f4-e686553b44e4 | note | Frequency - Continuous monitoring.
8679202a-7693-5f41-8621-2914fa000b7a | note | Verification Activity: Activity - I
ef113653-e18d-597c-b4b7-cd9caf5c596b | note | Verification Activity: By - SV / PE
c086377c-d141-5896-83ea-ffd0f27d9116 | checkpoint | 13.02.02 - Plateau Density Tests
51136676-d21a-5034-8127-f11d8b9118d3 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC.
e8cc3e68-b8da-5169-91ce-a392eac0669b | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
176ca1ce-de8a-5393-bdeb-e871b547182d | note | Verifying Document - MDD and Plateau Reports
01b6a9a9-b78e-5e2d-a332-2b0edc57e22c | note | Frequency - 1 test per 5,000m2
9ab35b9d-a844-5b22-9d67-ef7ac2181b8a | note | Verification Activity: Activity - HP
8502125f-90f2-5b90-b94e-d7a9275e8259 | note | Verification Activity: By - ENG
6c3d2e59-f982-5043-85a7-0aa2242113a2 | signoff | AUTHORITY HOLDPOINT
2eecc68a-d5d8-574a-a2f9-42b62be6259d | checkpoint | 13.02.03 - SIL Pavement Layer Compaction
0999e92b-724b-5c32-97f0-580257906e88 | note | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
1344ffe4-8d25-5cab-b222-5dc6db638099 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.6
d14a6e11-dc17-5d39-b6d5-fe2de0886699 | note | Verifying Document - NDM Report
816737a6-25e0-56d6-b595-4badcbc407d9 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
ba359498-1a54-5ca2-934d-c899abcf4dfd | note | Verification Activity: Activity - HP
df625915-05e1-5a82-bc5c-2df27c981af4 | note | Verification Activity: By - ENG
5d2a9c4f-9fb9-5fe3-878d-95a7bdaf77d8 | signoff | AUTHORITY HOLDPOINT
66c2b306-e56b-52a2-92a0-2f3a73a7833b | checkpoint | 13.02.04 - SIL Layer thickness.
713812c8-5bb7-559f-bdd8-f534f702c1a5 | note | Acceptance / Conformance Criteria - The SIL layer shall be monitored for Layer thickness.
811d3822-f34e-5de9-9cd6-a457e8da04f6 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
4ffa596c-af43-5369-a243-8a60d6b0d4f9 | note | Verifying Document - Survey / Level Checks
baea54d4-62d9-5afa-b420-1ca479d7e4e4 | note | Frequency - 1 test per 20m
399faf59-96d6-5753-9923-f6c9683b90a8 | note | Verification Activity: Activity - W
010f1784-3d73-50da-bcd5-da1ebc81ba39 | note | Verification Activity: By - SV / PE
793a5b8f-1431-5d59-b0d5-57842aca4233 | checkpoint | 13.02.05 - Surface Shape
84078007-afc6-509c-870a-a122625492f7 | note | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.
f20f4403-0664-5ea0-ab73-c56cc0ad561e | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
9c8b126c-0b13-5e9d-98ba-5ff1a1973a05 | note | Verifying Document - Survey / Straight edge Report
a6cb5aca-0666-5d91-a13f-6c55e6d5a84c | note | Frequency - Prior to sealing
6afae405-30c8-57ef-880a-305341f30856 | note | Verification Activity: Activity - I
4b4df198-b83c-52f7-bd57-d01475d4dd09 | note | Verification Activity: By - SV / PE
e3a25849-16b3-5921-a3ae-953690edba8a | checkpoint | 13.02.06 - Holding Water
15505fa2-beba-5377-b9dc-2d725a0f88f6 | note | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
ec36d017-0526-5d2a-9c14-b5986cbf5345 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
56fee9d4-19f0-5dd1-b03a-ec1c855ecc1e | note | Verifying Document - Survey
9965d0ed-cc2b-5b01-8bb4-62997144e555 | note | Frequency - Prior to sealing
449c2144-918b-5438-ac79-2b83f765f71c | note | Verification Activity: Activity - I
0703064c-bb8e-5d05-8041-1ca3df5681c6 | note | Verification Activity: By - SV / PE
ae8a2da6-e5fd-5e94-827d-5579c23340f6 | checkpoint | 13.02.07 - Proof Rolling
092d1b93-84f4-5f46-a839-e06160c666f9 | note | Acceptance / Conformance Criteria - SIL layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass.
715231fb-7dac-5d92-850a-87b79a3a5076 | note | Standard / Specification - PS 20.5.2.2
98d3a7f6-0099-5645-a556-b438233a3e42 | note | Verifying Document - Site Records
07817ef5-275d-5409-b097-f04bc754bf65 | note | Frequency - Before proceeding with works
707c306e-5b93-5ba3-89f0-5519be037175 | note | Verification Activity: Activity - HP
bd48985a-ba8a-595f-aed5-e2eaecae8532 | note | Verification Activity: By - ENG
9d203b5d-2a33-519b-a6fd-88f1e7ac7540 | signoff | AUTHORITY HOLDPOINT
c6646e17-3b34-5db0-a14d-c6780c356c80 | checkpoint | 13.02.08 - Benkelman Beam
65d1ab80-b372-5e66-9ab7-778570850697 | note | Acceptance / Conformance Criteria - be ˂ 1.5mm (95th%) and max ≤1.8mm
f70956e8-a85e-57b9-a437-9793e193b3d2 | note | Standard / Specification - B10 Notes
dfe1c362-83fc-5139-917d-eefbef5e3f79 | note | Verifying Document - Report
51573dcf-db11-5a96-bb33-0cdd3fe9c094 | note | Frequency - All Lanes
943ab12b-e11c-5e3e-8385-f91f783300ac | note | Verification Activity: Activity - R
2912b31c-e3f4-5c49-9523-e902fc33ff49 | note | Verification Activity: By - SE
15acaaef-6b2c-5aed-a809-1e4b054a1064 | section | 13.03 Construction Of Unbound WHAP65 Sub-Base Pavement Type C
5c138321-57a0-50a4-a63f-f1d0bad2e706 | checkpoint | 13.03.01 - Material Placement
65f2804e-b1ea-5263-b1d8-9292512e0eeb | note | Acceptance / Conformance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout
883c9c8b-9668-5b48-9995-3cb966f4a1cf | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 5.1
288d6f36-2245-51f9-b909-ac38c09deeef | note | Verifying Document - Survey / Level Checks
34d16671-d3d9-5f48-a0fa-ccf543618326 | note | Frequency - Continuous monitoring.
a03c15d9-7df2-59c4-986b-307e934ab3f2 | note | Verification Activity: Activity - I
e6bccbd7-6e66-55d0-9deb-1a7f198418f1 | note | Verification Activity: By - SV / PE
d536e45e-b290-5928-9e7d-4f3b9f77cee5 | checkpoint | 13.03.02 - Plateau Density Tests
de28d5ac-4d02-5cd1-abe0-4495a09cfbfe | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC. The Contractor shall determine the minimum number of roller passes required to produce pavement layer compaction at OWC.
47d63276-5d44-562a-86e5-d20a47743f2d | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
134dbb84-d303-5286-aaea-4af819911ae9 | note | Verifying Document - MDD and Plateau Reports
d709131e-b721-552e-8a15-83e76ea4bb1e | note | Frequency - 1 test per 5,000m2
accaef70-b531-57ba-9bc1-45078a0e5884 | note | Verification Activity: Activity - HP
bc2829e4-e698-578c-b5bf-9ce1ac1e939a | note | Verification Activity: By - ENG
a31d4bb6-6a44-5124-8c19-a224e93d521b | signoff | AUTHORITY HOLDPOINT
36212045-804f-5af7-abaf-c4af236857f2 | checkpoint | 13.03.04 - WHAP65 Sub-Base Pavement Layer Compaction
eb5b6126-e6f2-57ff-839f-151222c073b1 | note | Acceptance / Conformance Criteria - Mean Value ≥ 95 Minimum Value ≥ 92
4d2c09b3-245d-578d-bf7b-b827b8c6b80e | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.6
1ece55f9-dcd6-5917-a3eb-ac8713c55a72 | note | Verifying Document - NDM Report
4786edc0-980a-58b0-a7d0-19fc7cc0d13f | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
69f5e93a-3a04-526a-8944-9cf4748c6f9a | note | Verification Activity: Activity - HP
b5017f71-72c9-5d53-b6f7-d4ae2a4799ff | note | Verification Activity: By - ENG
18548d54-267e-59d6-a39e-9400d0c3aee8 | signoff | AUTHORITY HOLDPOINT
c223237c-3b5f-55bf-acef-125dc5f5531f | checkpoint | 13.03.05 - WHAP65 Sub-Base Layer thickness.
c0884732-0e98-5e82-a2b0-f50d2aa64618 | note | Acceptance / Conformance Criteria - The Sub-basecourse shall be monitored for Layer thickness.
4f210e93-ebff-56b1-9da0-a8d52636e473 | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.5
91d8bc4d-9249-501b-9736-3c8a677cbcc6 | note | Verifying Document - Survey / Level Checks
e57916a3-ead8-501f-9435-16bb845606bf | note | Frequency - 1 test per 20m
87800e68-104f-5910-9a18-c9c15e97274c | note | Verification Activity: Activity - W
bb0738c4-d195-58a1-8882-852e9d079680 | note | Verification Activity: By - SV / PE
b612415f-6895-5b8b-9857-070171e38a4c | checkpoint | 13.03.06 - Surface Shape
345f56d8-0bcb-5dff-b2da-e295d1a8dd86 | note | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual.
4e91b49c-5b5e-538e-9b13-cd73fc71c5bf | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
1a490f4d-1f77-5965-b3e9-ebceb40a5912 | note | Verifying Document - Survey / Straight edge Report
601b4542-f28d-5adc-bdee-247bc6b01c22 | note | Frequency - Prior to sealing
674df6f3-b3eb-5c36-9197-3bf43f05e7fa | note | Verification Activity: Activity - I
ab9bd2f2-d050-5257-9041-abb58f2f7836 | note | Verification Activity: By - SV / PE
062d293b-9ed4-5296-a0cd-4993084f2c29 | checkpoint | 13.03.07 - Holding Water
c17e3e28-272a-50b7-8656-cb1a44b8431f | note | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
547eec2b-0e53-5b95-9dbd-c186fb6e1b2e | note | Standard / Specification - PS 20.5.2.1 TNZ B/02: 2005 - 7.7
305b4033-4a98-5256-a040-b8c3df7149c3 | note | Verifying Document - Survey
4f900d34-51cb-5c30-8a7c-e842842d16eb | note | Frequency - Prior to sealing
85216c99-e287-593f-ab07-f30d85f8d5d3 | note | Verification Activity: Activity - I
cebce912-9930-5818-bccc-ccb56adbae57 | note | Verification Activity: By - SV / PE
62f09d63-7704-5b87-8c51-226331b2d93e | checkpoint | 13.03.08 - Proof Rolling
800e9e35-cb4e-5f0c-855a-c3d2ea953c8a | note | Acceptance / Conformance Criteria - Sub-base layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass.
85f048cf-a12c-5f20-a35b-3d0c9d29fbd7 | note | Standard / Specification - PS 20.5.2.2
a49f5570-e38b-5734-b532-f277663abe62 | note | Verifying Document - Site Records
577758da-82c3-5321-81a9-9724d068741e | note | Frequency - Before proceeding with works
7dbd8e6e-8440-5267-b869-efb181951412 | note | Verification Activity: Activity - HP
f5b54446-867f-5090-b6b4-a7f0ff499388 | note | Verification Activity: By - ENG
b9b923a4-0d2e-5fc7-8b29-096c11fc713a | signoff | AUTHORITY HOLDPOINT
ce08d865-02ea-5fa2-b6db-5313ad9d514e | section | 13.07 Construction Of Basecourse – NZTA M/4 AP40 Pavement Type C
68935ff5-2817-55fd-9b91-fad9b47a49d5 | checkpoint | 13.07.01 - Material Placement
8cce7e6b-8994-5acd-83aa-2ed773d0e0b2 | note | Acceptance / Conformance Criteria - The Dimensional tolerances, uniformity, contamination and segregation shall be Continuous monitored throughout
3340e55e-3b30-566e-b65f-7d370cf24f49 | note | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 5.1
859142cf-00c4-5fab-858f-62443dbac5c1 | note | Verifying Document - Survey / Level Checks
a7e602fa-f859-58ce-9557-28dcffc79436 | note | Frequency - Continuous monitoring.
2e1541c8-023e-59b8-86b7-b763470ed7de | note | Verification Activity: Activity - I
35285c3e-4a09-574d-bda2-b6806d74db2c | note | Verification Activity: By - SV / PE
93bde6b5-85fd-5837-bbdf-12d9eb7b4ccf | checkpoint | 13.07.02 - Greenfield Sites Plateau Density Tests
1243f681-3942-5677-9876-70ee42b28963 | note | Acceptance / Conformance Criteria - The plateau density tests shall be undertaken on 100m test strips using a variety of compaction plant typical of that to be used on site. Testing shall be at OWC.
ef1e2d9f-d359-538b-b1e4-1c1f92724093 | note | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.5
c04ff994-d73e-5832-9317-489e80a6df38 | note | Verifying Document - MDD and Plateau Reports
545c5795-2739-5c3f-bf61-cd60dac9a430 | note | Frequency - 1 test per 5,000m2
881ba2fa-0e1d-5f83-9847-ca1545f86a5b | note | Verification Activity: Activity - HP
cc2e1f3a-b39a-58bc-83c7-d813f61a4f9c | note | Verification Activity: By - ENG
f9f36ec2-5835-559d-814f-276ec73a603f | signoff | AUTHORITY HOLDPOINT
fd753b1f-ff40-5edb-ba12-65b1609fec73 | checkpoint | 13.07.04 - Basecourse Pavement Layer Compaction
765e7b3d-f9ee-5800-b73d-5c16c0be9a15 | note | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95
23313949-abd0-5ab4-a9ff-de9d0415629a | note | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.6
1d9bee48-d62f-578f-821f-35e9a51d84ef | note | Verifying Document - NDM Report
a7c54d83-8f07-5be0-9e59-e2327f287031 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
db58d9e8-185a-5f4e-acbe-30e80258880a | note | Verification Activity: Activity - HP
4ce40972-2c77-51d8-b473-875839aaea88 | note | Verification Activity: By - ENG
f97ec9c4-b6fd-5476-80a3-f281fa349113 | signoff | AUTHORITY HOLDPOINT
d3fe0435-4019-5a7b-9ca8-a627c32fee84 | checkpoint | 13.07.05 - Basecourse Layer thickness.
cd9e69d2-abaf-5d70-9100-89901973b859 | note | Acceptance / Conformance Criteria - The Basecourse shall be monitored for Layer thickness.
64ff3a09-5102-5560-a8a3-f24ab8e52448 | note | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.5
2548ad1d-8b5d-511f-b96b-a88c6ec8dbf4 | note | Verifying Document - Survey / Level Checks
89c6cd4f-3e31-58d9-bd00-3b7803749205 | note | Frequency - 1 test per 20m
b98b27ba-10ff-5ee6-8716-670a75f5a9a7 | note | Verification Activity: Activity - W
ea86e00d-0fca-5e71-adc0-c1ea0aa56393 | note | Verification Activity: By - SV / PE
c942a25c-e737-5eba-8802-0e0cc510f5c3 | checkpoint | 13.07.06 - Surface Shape
cd23aea4-74f6-5ed7-b483-a574dcd8852d | note | Acceptance / Conformance Criteria - The standard of smoothness shall be such that there is no point in the surface that varies more than 10 mm from a 3 m straight edge placed on the road and any deviation from the straight edge is gradual..
40818f85-fe4a-5007-a87e-db3a4a7a94f1 | note | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.7
3b1948b1-a638-5fb7-9d6e-a9e0ce34a689 | note | Verifying Document - Survey / Straight edge Report
e1844fd2-fa00-54ae-8949-3b6a1ac1735d | note | Frequency - Prior to sealing
edf95929-256b-5d00-8d63-cf187ae6a6b5 | note | Verification Activity: Activity - I
387ef005-a71e-5514-a306-d842d25c6a79 | note | Verification Activity: By - SV / PE
c0f6ab5d-020c-55ce-94d0-1b8ac2d877cb | checkpoint | 13.07.07 - Holding Water
ae926712-137c-577c-ba40-311b72a1a1d3 | note | Acceptance / Conformance Criteria - No area of the completed surface shall have any depression that will allow water to pond where lateral or longitudinal fall is greater than 1%
e36a1201-c05f-5893-90de-305cae78c56a | note | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.7
4bb29093-9efc-54e0-97a3-946a794c89a4 | note | Verifying Document - Survey
c29b83b2-9060-551f-a083-813caffd9605 | note | Frequency - Prior to sealing
de3228f2-ad4f-5f03-97e6-35e983e94a54 | note | Verification Activity: Activity - I
2d602d72-25d7-5ff1-8080-1829e7d2f946 | note | Verification Activity: By - SV / PE
51976618-c9a1-5596-92a4-deee7967ed06 | checkpoint | 13.07.08 - Running Course
13b1d723-7a2b-5ab7-92ff-c5054ae6947a | note | Acceptance / Conformance Criteria - If running course is used it shall be spread uniformly over the pavement surface and maintained until removed. During working hours traffic shall be channelised by suitably defined traffic lanes with frequent transverse shifts of the defined lanes to obtain an even spread of traffic over the entire surface.
7ae1bd07-05c5-5c45-bb00-f8716e35f246 | note | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 10.1
8e3622c1-8c26-59c1-97ec-3fab05467763 | note | Verifying Document - Site Notes
25db6b28-3869-504a-a6b1-ad37ab11addd | note | Frequency - Prior to sealing
645f9c10-99eb-542b-8ba6-6d31d59d0bf0 | note | Verification Activity: Activity - S
cff60d1a-3c03-5b1b-8a3c-64a20208748b | note | Verification Activity: By - SUP
182d285a-d599-5a2c-879b-9d5a9b73169f | checkpoint | 13.07.09 - Surface Finish post sweeping
e8afa081-22ef-5221-a594-4fabd4016a6f | note | Acceptance / Conformance Criteria - The basecourse surface finish, as distinct from the surface shape, shall present a tightly consolidated surface when swept.
439193f8-3654-512d-92a1-2b9c309b6073 | note | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 7.8
af86e71b-a99d-5415-85c2-9e30ca097b17 | note | Verifying Document - Photos
f14479d4-3f21-5f39-9a02-222cb4720b93 | note | Frequency - Prior to sealing
774c9875-68d1-54c4-a923-f3ba161d4a75 | note | Verification Activity: Activity - R
01115c0d-785e-595a-83c2-65691ae0e903 | note | Verification Activity: By - PE
72b5539a-1698-5e34-9dc2-6a4e298bc35f | checkpoint | 13.07.11 - Presealing Requirements
06fdae30-208c-5f6d-9a8e-4f1af115f205 | note | Acceptance / Conformance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 60%.
21dc83bc-1479-567e-bdfb-de69dc0a179b | note | Standard / Specification - PS 20.8.1 TNZ B/02: 2005 - 12
586e834f-1032-564e-a23c-6d580d944e8b | note | Verifying Document - NDM Report
fbd96918-5557-5812-8282-de52ffd65155 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
7b0885fa-ff97-5dac-9807-ea47847fc95f | note | Verification Activity: Activity - HP
8ac70af4-d159-55e5-9b4c-6068e04f770e | note | Verification Activity: By - ENG
0114a86a-3291-5d45-b580-dc1a53589b64 | signoff | AUTHORITY HOLDPOINT
4579d018-56a6-5dff-9e43-0376c57cfbb5 | section | 14.02 Chipsealing
8a02dcd5-5e49-5f19-b403-71144ec78eae | checkpoint | 14.02.01 - Sealing Procedure
0bd41e9d-c4bc-50e6-81e7-660da3a86411 | note | Acceptance / Conformance Criteria - Sealing shall be carried out in accordance with TNZ or NZTA Specifications M/1, M/6, M/13, P/3, P4, P17, and Q/1.
0a7eb9a8-59a0-54fa-989d-7ec1f33e0b37 | note | Standard / Specification - M/1, M/6, M/13, P/3, P4, P17, and Q/1.
d242cc94-624d-521d-85a7-9b03a42075fe | note | Verifying Document - Methodology / Construction Pack
44b8c790-1462-578b-83f5-bd7d4fdce75a | note | Frequency - Prior to Sealing
9422610b-2fcd-586b-8bf1-20771cd726d8 | note | Verification Activity: Activity - R
14d62112-5c16-5989-bc80-432306d50cf8 | note | Verification Activity: By - SE
ada53fa2-4291-5b07-83fd-c5bf5658f253 | checkpoint | 14.02.02 - Seal Design / Binder application rate
051abffd-5a12-503c-8a60-40eba1e2a9a3 | note | Acceptance / Conformance Criteria - The sealing design including binder application rate to suit the surface conditions shall be approved by the Design Engineer prior to sealing.
af9811e4-549c-593e-bc39-d063280a8f2a | note | Standard / Specification - TNZ P3 TNZ P4
faa9a4d1-05e7-5caf-85e2-3d9ff802f70a | note | Verifying Document - Approved Seal Design
3b3557a9-c5a3-596c-9cb3-b35aaaa73625 | note | Frequency - Prior to Sealing
11d625cc-b4a7-5f86-8e72-4b6db56447b8 | note | Verification Activity: Activity - HP
7170d878-d649-5ec7-90a6-b55a41b385df | note | Verification Activity: By - ENG
cbc739c1-0f8e-53cd-93a8-a1286c12c3f8 | signoff | AUTHORITY HOLDPOINT
c9fe788e-994f-5558-a4d7-63f0b4bcc03b | checkpoint | 14.02.03 - Presealing Requirements
ce78c953-d86d-5cbd-bf4a-7dffe128b8b9 | note | Acceptance / Conformance Criteria - The seal coat shall not be applied unless the water content at each test point of the basecourse layer is such that the degree of saturation (DOS) is less than 60%.
da7950e3-a6b2-5c64-9a10-112d9e6da2f2 | note | Standard / Specification - TNZ B02
0a686415-5186-5dbe-a396-c0ed338e0225 | note | Verifying Document - NDM Report
da4211e0-17f3-506d-b0c2-fa8baac99479 | note | Frequency - Min 5 Tests Per Lot 1000m2 Max Lot Size
3af94cf0-a73f-5b49-b6c3-fcc7ea03b631 | note | Verification Activity: Activity - HP
165d0cda-a648-54f8-944e-2a2252f8ad35 | note | Verification Activity: By - ENG
c23627bd-3900-5db8-88bb-f4cfc71e2be7 | signoff | AUTHORITY HOLDPOINT
0ae77eda-811f-5505-81cf-ad3d9cc0f205 | checkpoint | 14.02.04 - PreSeal inspection
6bfde61c-c3a7-5b07-b8a5-527b367bed12 | note | Acceptance / Conformance Criteria - The road shall be reasonably dry before the binder is applied, and no spraying with asphaltic binder shall be carried out when the air temperature measured within the confines of the sealing course is below 10oC in the shade. The Engineer shall be given the opportunity to inspect the site.
7d383289-afb0-5535-b533-d399ad004d8b | note | Standard / Specification - TNZ P3 TNZ B02
1f99a71b-2272-517c-9101-5fd274e62ba4 | note | Verifying Document - Hold Point Release
f426f61c-4388-5b26-a5b8-8459c559d725 | note | Frequency - A minimum of 24 hours’ notice of intention to seal.
e0f41c5e-b750-51f6-b27c-a54f5a924c2e | note | Verification Activity: Activity - HP
63f7deab-8b04-5b48-89e5-ae5190a22cd2 | note | Verification Activity: By - ENG
3ae86b65-5743-592b-9e95-7c2fe7c32173 | signoff | AUTHORITY HOLDPOINT
ffdd19fc-5e7d-5126-a571-17726917b679 | checkpoint | 14.02.05 - Spray Temperature
b0720278-535e-5fbb-b529-6f3c9d9ea736 | note | Acceptance / Conformance Criteria - The emulsified asphalt may be sprayed at the temperature at which it is received from the manufacturing plant except that no emulsified asphalt shall be sprayed at a temperature in excess of 90oC or below 20oC.
e7b6cb7e-1a3f-5bd8-bca2-afde2820f1fc | note | Standard / Specification - TNZ P3
ab3a99bb-caf5-57f7-876e-db4edd79cac3 | note | Verifying Document - Site Notes
31600695-0190-5c6b-abc7-1864ba21f1fa | note | Frequency - Prior to Seal
ce942e17-8e78-53a8-9bcd-120aa7d9ce6e | note | Verification Activity: Activity - I
75150a47-141c-5930-9c81-9e376211501e | note | Verification Activity: By - SE
0dcbadfc-dfc4-5614-9349-ce2d47f98f3b | checkpoint | 14.02.06 - Binder Sampling
6bff410f-041b-595e-a2cc-25fa7eac467f | note | Acceptance / Conformance Criteria - A minimum of two samples per bitumen distributor load shall be taken. The first of these samples shall be taken at the end of the initial spray run and the other immediately before the final spray run. Bitumen to be tested on Engineers instruction.
ae985cfc-a520-5dc5-b04f-27cee662d921 | note | Standard / Specification - TNZ P3
cf32d20c-eac3-5604-a17c-14504032c3d1 | note | Verifying Document - Site Notes
493fb92e-92f9-5812-a555-174cd7bdf877 | note | Frequency - Each Worksite
ec694beb-ba24-51b3-a248-016a3feb7c02 | note | Verification Activity: Activity - I
abbcb8ec-31cc-5a03-b378-6519078cdf66 | note | Verification Activity: By - SE
bd02d977-a52a-556b-91ff-b98ba5e13bf2 | checkpoint | 14.02.07 - Quantity of Binder Sprayed
c0f0fe3e-636a-56b3-b2fb-bf7542d720f8 | note | Acceptance / Conformance Criteria - The quantity of binder sprayed in any spray run, measured by dipstick reading, shall not vary from the amount directed by more than 50 litres plus 4% of the amount directed.
fd8cfb49-288c-5c75-bc70-bcf6d65f05f5 | note | Standard / Specification - TNZ P3
d3b3e770-b407-55af-8bbb-5937c2f6b9a1 | note | Verifying Document - Site Notes
671fda07-2133-53d5-aad7-8b4d2ac5420c | note | Frequency - Every Spray Run
7c7ecb94-9cb0-52ec-bef6-e10a0735d6cf | note | Verification Activity: Activity - I
161bceeb-005a-5013-b25f-a02165762534 | note | Verification Activity: By - SE
3360a235-e28c-535e-ba36-1d4bc26aebd4 | checkpoint | 14.02.08 - Chip Application
c34f8ada-7c79-59b0-948b-7a76d8f45f41 | note | Acceptance / Conformance Criteria - All binder sprayed shall be covered with chips across the full sprayed width, apart from necessary longitudinal laps, within five minutes of spraying.
eaeb892d-609e-57c7-8adf-5e524f75d616 | note | Standard / Specification - TNZ P3
56a9f218-f721-59c0-91aa-91f5dc48a250 | note | Verifying Document - Site Notes
96e48e90-d99e-57e0-ab2e-0810de172490 | note | Frequency - Every Spray Run
edcbdc66-0c13-5902-97e5-21a032d09b18 | note | Verification Activity: Activity - I
e497aa9b-1f1a-5567-a80e-2a049f6ab72c | note | Verification Activity: By - SE
28a4f134-dc17-5564-b5ee-68cd1156c666 | checkpoint | 14.02.09 - Surplus Chip Removal
2cd6afcc-1d91-57ec-8714-b06442c5662c | note | Acceptance / Conformance Criteria - Surplus chips shall be removed from the sealed surface prior to the removal of the temporary speed restriction signs.
1b46aa57-f919-5ac2-a5e5-9598a4ba9105 | note | Standard / Specification - TNZ P3
12039689-f737-5fbf-8f02-815ba225b254 | note | Verifying Document - Site Notes
1d8c5b99-a511-567f-8eee-137967d20c4f | note | Frequency - 24 hours of Completion of any Section of Seal.
2c6aa6d3-2a8b-55ee-9c20-6d0d4446ce58 | note | Verification Activity: Activity - R
a043dce9-7e2c-521e-a853-8c8cfcb0ef0d | note | Verification Activity: By - SE
8e0b0105-681f-58b6-851b-e319fa540427 | checkpoint | 14.02.10 - Post Seal Inspections
c5fe2402-0b7b-5bc2-abba-63d9f1abb7ee | note | Acceptance / Conformance Criteria - The Engineer will inspect the sealcoat immediately prior to the removal of the temporary speed restriction and after final surplus chip removal is completed.
d2743936-2a7a-50f2-b688-5d9e67f2701e | note | Standard / Specification - TNZ P3
03e0fc91-8cff-5256-9671-cbe69db85abf | note | Verifying Document - Engineers Acceptance
34c7709c-d4e0-5b9d-b338-3c28ac318604 | note | Frequency - Prior to TM Removal and After Final Sweeping
3d642967-b192-5019-bfc0-69cccbd19c97 | note | Verification Activity: Activity - HP
ad54a2b1-c15c-53e3-8b0d-791a96ff8729 | note | Verification Activity: By - ENG
53fb941f-2e01-574a-9547-69f4057ddfd9 | signoff | AUTHORITY HOLDPOINT
a4cec822-66da-55a1-825f-9e472e9ccfe3 | checkpoint | 14.02.11 - Chipseal Repairs
0ef52d45-3822-5c4f-9d5c-5dafb96c9ed1 | note | Acceptance / Conformance Criteria - The Contractor shall make no repairs without the prior approval of the Engineer for the methods to be used.
0dc5828d-bcc9-5d40-8de3-47d6230ea281 | note | Standard / Specification - TNZ P3
7ca3d02f-0367-5834-92fd-2af74d773318 | note | Verifying Document - Approved Repair Methodology
aeb7c1ac-1ca2-59a0-833d-baa6a76f4ad0 | note | Frequency - Prior to Repairs
f4f2d297-4840-5a35-ab43-e9e8b686150d | note | Verification Activity: Activity - HP
136d943b-3148-5d11-9350-7afebcba71f7 | note | Verification Activity: By - ENG
21a6df80-a2a2-52db-b4ab-47a1d69759f1 | signoff | AUTHORITY HOLDPOINT
fabf8396-eaec-50f1-9fb1-08aa0268f5ab | section | 14.03 Construction Activity - NZTA M10 - Specification for dense-graded asphaltic concrete
d9ba015d-4ed1-5d0e-b38a-d7ca0b83e37b | checkpoint | 14.03.01 - Construction Trail
445b2eab-7ced-5e20-9aa8-aac6f55b1c4a | note | Acceptance / Conformance Criteria - Where a construction trial is specified in the contract, and not less than two days before the site work is due to commence, all the Contractor’s plant and personnel proposed for use on the job shall carry out a construction trial in the presence of the Engineer. Asphalt manufactured in the production trial can also be used in the construction trial if it meets the requirements of the specification.
d2facd27-9792-5555-8e0f-d0bbf887f28a | note | Standard / Specification - PS 21.3.1 NZTA M10:2020 - 7
a166f5df-f999-5fa8-bce7-8e9e1b042fb2 | note | Verifying Document - Test Results
2a2abcb8-b667-5f4b-ae9f-2d1aed763395 | note | Frequency - As Required, two days before the site work is due to commence.
8549639f-f9fa-5459-aec3-21f151259cef | note | Verification Activity: Activity - I
c3f02f40-2fd7-57de-a39e-92845b300266 | note | Verification Activity: By - PE
dc66f832-8727-52d8-9e25-4430ebf5e982 | checkpoint | 14.03.02 - Paving Plan
5daa8371-4f58-5f73-a12b-a69faec77a87 | note | Acceptance / Conformance Criteria - The Contractor shall prepare and submit a paving plan to the Engineer for approval not less than 7 days prior to construction of the asphalt pavement.
c9631379-3344-591e-96f6-f8faf87005d8 | note | Standard / Specification - NZTA M10:2020 - 8, 9
4899c315-2435-525c-89cb-3eaedbc0fb5c | note | Verifying Document - Construction Work Pack
80a9dc49-320b-5b2b-ac9b-89f3cedafa6d | note | Frequency - 7 days prior to construction of the asphalt pavement.
e35033f1-b4a1-5bfd-b094-b2c6daf3a111 | note | Verification Activity: Activity - HP
ea69089b-b488-5426-a094-f31ec320d6e0 | note | Verification Activity: By - ENG
1cb5f60e-936c-5933-b2d8-2c1dffdb519a | signoff | AUTHORITY HOLDPOINT
c60c5b72-1afc-5afc-b057-92e697de7c4f | checkpoint | 14.03.03 - Preparation of Area to be Paved
19a98f31-2b97-5bea-a9a2-7fc7d8cfd79c | note | Acceptance / Conformance Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping. All fatty and unsuitable patches shall be removed. Depressions and other irregularities shall be patched or corrected.
1fd90bb2-480a-5f9d-bd17-6ca55134f35a | note | Standard / Specification - NZTA M10:2020 - 9
e273236d-61ff-5ea4-9b8e-ec3c88a8d12a | note | Verifying Document - Site Notes
f39d1eb2-396a-535f-9f62-5458f14bead4 | note | Frequency - Pre Seal
0965f28d-857b-577b-9915-c5ea8685e881 | note | Verification Activity: Activity - I
2b3abf13-1066-51c9-a314-f99b31a81ae9 | note | Verification Activity: By - PE
91375a47-81b0-5bda-99f4-b8f1aae32c6f | checkpoint | 14.03.04 - Protection of Services
c7b284e3-d853-5de7-9332-633618f70d03 | note | Acceptance / Conformance Criteria - The Contractor shall prevent tack coat, binder, aggregate, asphalt or other material used on the work from entering, adhering or obstructing gratings, hydrants, valve boxes, inspection pit covers, kerbs and other road fixtures
e5a0dbea-5606-5b50-8a32-c3725d51ed91 | note | Standard / Specification - NZTA M10:2020
3cba49df-a5be-5947-a409-df06727fa50b | note | Verifying Document - Environmental Inspections
073277ca-412e-5019-9a27-4acfda4fdc76 | note | Frequency - Daily
7eb645eb-98a4-5119-8cf2-63747e2abefb | note | Verification Activity: Activity - R
a485ce33-b3d0-5073-82d5-8dcc394a45f0 | note | Verification Activity: By - SE
f1b55bb9-7077-5c36-bcdb-1d298ac1a406 | checkpoint | 14.03.05 - Ambient Conditions for Placing
353368a7-afe3-5b0d-a7c8-a76260afc159 | note | Acceptance / Conformance Criteria - Wearing course asphalt shall not be placed when the pavement surface temperature is less than 10°C, for SAC the minimum temperature is 5°C
c8628e32-dc97-5b2b-947e-2f7aa0629a9e | note | Standard / Specification - NZTA M10:2020
8df41807-32a4-589b-9ec0-2b0c94945ae2 | note | Verifying Document - Site Notes
3e234ba9-bf0a-53ff-8ae2-70a940c3b916 | note | Frequency - Pre Seal
6fbed706-009f-528a-9506-a598cb3898f1 | note | Verification Activity: Activity - H
311d8ba2-7365-53ec-b49d-52fa2438c652 | note | Verification Activity: By - SE
99a6b2db-1c82-538e-85c3-8fdb54b15c74 | checkpoint | 14.03.06 - Tack Coating
1cb68408-796a-5555-82cf-9490b97fa203 | note | Acceptance / Conformance Criteria - Tack coat shall be applied to the cleaned surface prior to placing asphalt. Tack coats shall be applied using a distributor. The use of a hand lance shall be minimised to ensure an even application of the tack coat.
164a15ff-6cc0-53a2-8bd0-d16f8484d3d4 | note | Standard / Specification - NZTA M10:2020 - 9
4cd4a8ac-b021-5ef1-b4f3-03e12235180a | note | Verifying Document - Site Notes
c74d7ffc-e3ca-5ff7-a126-d9e947a0c40b | note | Frequency - Prior to Paving
a513f743-3197-5ae8-9e02-528469ab10be | note | Verification Activity: Activity - I
e49745fb-14ad-581d-a8ee-df56afff11b3 | note | Verification Activity: By - PE
370d7efd-40fc-556a-910d-d7f6043e6e7d | checkpoint | 14.03.07 - Asphalt Production Conformance - Grading and Binder
426dbd12-ce65-57be-bfe7-4ae70b96136a | note | Acceptance / Conformance Criteria - Conforming Grading and Binder content by mass. Refer clause 5.2 and table 5.2 for frequency and tolerances
04a6a52f-cd11-5f27-a6ce-fb2217d94335 | note | Standard / Specification - NZTA M10:2020 -Table 3.1, 5.1 and 5.2
c870700a-4706-5db7-95f7-cb6d55654cf4 | note | Verifying Document - Test Results
0718e1c8-a893-5ba7-a6ed-341d3682b21d | note | Frequency - 1 per 200T
39bec684-3a67-5bfc-bdb3-a74d8737218d | note | Verification Activity: Activity - I
3d536cc7-3648-59cf-9fab-effa81d197d1 | note | Verification Activity: By - PE
66aec51e-2e1a-5258-9c3f-75c10b666cd2 | checkpoint | 14.03.08 - Asphalt Production Conformance - Volumetrics
1be85a69-7cff-5b40-8214-027be36b10f8 | note | Acceptance / Conformance Criteria - Conforming Volumetric testing. Refer clause 5.2 and table 5.2 for frequency and tolerances
44e87a96-a4b5-5069-adfb-3840bd4a4d36 | note | Standard / Specification - NZTA M10:2020 - Table 3.1, 5.1 and 5.2
d59adf31-ec32-5415-a20c-11f4ff40d686 | note | Verifying Document - Test Results
7024e868-07ed-5337-9361-e8f1c3009110 | note | Frequency - 1 per 600T
bb835ef8-cd7b-5a2f-ab97-a110426a6451 | note | Verification Activity: Activity - R
8cf8575e-6583-5471-8a82-cbf97ee21099 | note | Verification Activity: By - SE
0aecd9f3-570d-5a19-b9d5-04ceb4a37284 | checkpoint | 14.03.09 - Core Thickness
8bd5bd35-492a-51c5-af2d-eb40a505a2f1 | note | Acceptance / Conformance Criteria - The nominal thickness for the set or lot of cores shall be equal to or greater than the specified nominal thickness.
97b14159-0de7-5ebc-b565-5fdb3833884c | note | Standard / Specification - NZTA M10:2020
dc776c0a-438c-5449-b936-83418324b334 | note | Verifying Document - Lab Report
81a0cbaf-09a9-5ea7-9c3d-e8654c791eb0 | note | Frequency - Mat - min 8 per lot (day) (1 for every 300 m²) Joints - min 3 per lot (1 for every 100m)
f6c4cded-02d9-5f66-a999-ae9490469c58 | note | Verification Activity: Activity - R
aa97b743-bf54-53c4-926e-d554a401a941 | note | Verification Activity: By - SE
f6994cad-2fdd-5881-9b51-42aa86c6773c | checkpoint | 14.03.10 - Joint Density
851d1c91-e983-5603-8ac0-e4e49597ca10 | note | Acceptance / Conformance Criteria - 150 mm nominal diameter Cores shall be taken from randomly located distances along joints at the rate of one per 100m of joint with a minimum of three representing each lot
f02b356d-50e2-5d97-b51e-3c3620c02ead | note | Standard / Specification - NZTA M10:2020 - 9
58863498-4960-5c65-b0c7-4f83925ffacb | note | Verifying Document - Cores
b50df8e6-dfcc-5774-b6ee-905d93b3ddf5 | note | Frequency - min 3 per lot (day) (1 per 100 m of joint)
8658f7a1-4cd6-5a33-b255-ab485af0478c | note | Verification Activity: Activity - R
d844ff95-7041-5a57-8b98-de2089e77b86 | note | Verification Activity: By - PE
3a4777c8-04aa-5df7-be12-87141109d5f5 | checkpoint | 14.03.11 - Density Testing
683ee160-4e86-5bb9-a042-6ca7cb5a8f1f | note | Acceptance / Conformance Criteria - The upper and lower characteristic values of in-situ air voids for that lot shall comply within the maximum and minimum characteristic limits specified in Table 9.2
0888cef5-0849-5846-ac2d-a62a50258ffa | note | Standard / Specification - NZTA M10:2020 - 9
276877ad-5b4b-51a6-85fa-80439fcb11a2 | note | Verifying Document - Lab Report
bf86dde8-b50f-5fdb-9c57-e4e2be51dd5f | note | Frequency - within 24 hours of them being cut from the pavement
31f32f1f-aaae-5a17-b5e9-329402a71557 | note | Verification Activity: Activity - I
d6617beb-4f6e-5a1a-919e-7291b81394a9 | note | Verification Activity: By - PE
83bd1600-3b31-5d97-b7f5-9ae112a12dd7 | checkpoint | 14.03.12 - NDM Density
a99f142a-6acc-5013-878d-c0756e90dc47 | note | Acceptance / Conformance Criteria - NDMs are to be completed at the time of placing to ensure compliance when cores are taken
299d8b74-4984-56c9-9a43-ab2d1cba0ddb | note | Standard / Specification - NZTA M10:2020 - 9
a803ddb7-956f-5744-ae83-acb4316a20f0 | note | Verifying Document - IANZ Lab Report
37beda74-833f-5636-88b8-b945909dc839 | note | Frequency - min 8 per lot (day)
e1b959b4-04c5-53a4-8c5f-fdadacbb29cf | note | Verification Activity: Activity - I
5b2e60ad-8e18-5b90-ac5b-e7bd39211519 | note | Verification Activity: By - PE
da37be10-eee1-57da-b096-5f82b9b17e58 | checkpoint | 14.03.13 - Transverse truth of the surface
cc943133-b19e-5079-b82e-03a29dea7de1 | note | Acceptance / Conformance Criteria - The transverse truth of the surface shall be checked with a 3 m straight edge over the straight cross-fall portion of the cross-section for irregularities, which vary more than 5 mm under this straight edge.
1762e50b-e5d9-5190-9ea1-3cb4416a2b0f | note | Standard / Specification - NZTA M10:2020 - 9
31d6db87-96d6-5c71-961d-fcbd90df89e6 | note | Verifying Document - Site Notes
fe1b1f32-008b-5ef2-8995-e5b4f8ea44d4 | note | Frequency - Post Seal
f556768b-7502-5ebe-b560-f7ee23f4c23f | note | Verification Activity: Activity - I
928f3a01-0bb7-5ab9-a5a8-3d8d3cdfa723 | note | Verification Activity: By - SE
58831243-e15b-5210-977d-b1addf9686cf | checkpoint | 14.03.14 - Finished Pavement Level, Alignment, and Thickness
2de60a61-4475-57a7-ab50-a5f9de7287e6 | note | Acceptance / Conformance Criteria - The level at the top of each layer of asphalt, horizontal location of any point on the pavement, and specified layer thickness shall be surveyed and conform with tolerances and contract requirements.
c5146769-1881-5f5b-a5ab-3e9cd389bd2f | note | Standard / Specification - NZTA M10:2020 - 10
cbd572be-4dca-56fc-bca8-a99ec9b7185b | note | Verifying Document - Survey
8ae9e8bd-f90e-539f-84db-7d18e45cdd1d | note | Frequency - Continuous thought construction
ea7c86b9-bcf0-582e-85af-2ccfb13e16ec | note | Verification Activity: Activity - I
7a5fa09d-ca8e-52fd-92d7-287a2c6c2dd9 | note | Verification Activity: By - SE
35612da6-dfce-53fc-a4b0-a220727f10b6 | section | 14.05 Roughness
bcb7970f-6ae4-5bf2-b8e2-868871a1de0d | checkpoint | 14.05.01 - For a Chip Sealed Surface
9f99141b-1172-5e94-89b3-0680ebe18bbe | note | Acceptance / Conformance Criteria - Target is an average of 60 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 70 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km.
0a37ac7e-113c-55cc-ad37-bb095ad77d67 | note | Standard / Specification - PS 21.4.1
ebd4dcef-f1b9-5bdc-93da-203b4f10200f | note | Verifying Document - Test Report
f8908dd9-ab09-520d-a355-181c6a580593 | note | Frequency - Prior to sealing
ee52582c-2877-5e71-93dc-7f7684d7cb5f | note | Verification Activity: Activity - HP
07e2ca08-fa33-5877-a868-06a862969f8f | note | Verification Activity: By - ENG
6c3ba941-1777-5501-9249-247d90f91522 | signoff | AUTHORITY HOLDPOINT
f8bd57a9-846b-5828-88de-6d7d62f6fd73 | checkpoint | 14.05.02 - For an Asphaltic Concrete Surface
036d95a2-931f-5c4c-8deb-6f3a3d196b6b | note | Acceptance / Conformance Criteria - Target is an average of 50 NAASRA counts/km for the 100m moving average Maximum 100m moving average of 60 NAASRA counts/km. No 20m reading in any lane shall exceed 100 NAASRA counts/km.
235c7598-9946-5553-b9c1-9d307b597cff | note | Standard / Specification - PS 21.4.1
13fe123f-3860-54bb-b291-ef4f0de5682b | note | Verifying Document - Test Report
9301bf3f-3fa5-5a88-adea-38386ea3823a | note | Frequency - Prior to sealing
8d3ff43b-0503-5857-a565-c5465ce03b75 | note | Verification Activity: Activity - HP
46514fb7-a879-5cc8-8aef-c2e6c5e30d6f | note | Verification Activity: By - ENG
b8bafe1f-4b75-5b87-857f-d269c0bcf8c8 | signoff | AUTHORITY HOLDPOINT
e16b3ed5-409b-5176-b427-1231353994c8 | section | 14.06 Skid Resistance
b0053e02-fe90-5f9b-8826-998d139bda13 | checkpoint | 14.06.01 - Skid Resistance
cc4232e0-5530-5547-94cd-acbb837a1ed9 | note | Acceptance / Conformance Criteria - The surfacing shall meet the requirements specified in the Transport Agency’s T10:2010 Skid Resistance Deficiency Investigation and Treatment Selection, and any other subsequent amendments.
44d6ddcf-2ddf-5c0b-b561-f9b786b5ac20 | note | Standard / Specification - PS 21.5.1
4d7599b0-2f36-5bd2-acf9-6b472d4c8f5d | note | Verifying Document - Prior to Project Completion
2a181732-e9f2-57c0-99b0-a7c19ed2d0c3 | note | Frequency - Prior to sealing
a43bd79c-8bb2-5556-af83-cb72c9525b83 | note | Verification Activity: Activity - HP
cd72586d-a454-5f7e-8c62-b116e6439e2c | note | Verification Activity: By - ENG
629b7c55-9012-52d8-befe-d8f7f7908625 | signoff | AUTHORITY HOLDPOINT
4e62a024-24f3-4d1d-a827-cde225a7e31e | checklist | ITP - Retaining Wall Construction - 303 - Rev C | itp | ITP - Retaining Wall Construction - 303 - Rev C
788236be-1bb3-462c-a7fe-ecf2657fa6e9 | section | 4.19 Retaining Wall Materials
13d2a07b-abdf-4de6-b6ed-35d59cd1a20c | checkpoint | 4.19.1 - Retaining Wall Concrete including site concrete, pile concrete and capping concrete (Pile Concrete Mix Design / Tremmie Mix Design)
eb0e8e28-86b7-520b-bef3-ba23ba622c3b | note | Acceptance / Conformance Criteria - All concrete shall have a minimum 28-day compressive strength of 30 MPa for both piles and the capping beam. The contractor shall submit the proposed concrete mix including slump to the Engineer before the commencement of works
8c773d6e-2e59-5326-aa95-e75060c0a82e | note | Standard / Specification - PS 18.2.5, PS 18.5.1
58a98d2f-33ae-5cf8-b90a-4acb87d7f2bb | note | Verifying Document - Mix Design
fbde0b1a-dc9b-55bd-b9a6-ff65015f276c | note | Frequency - before the commencement of works
d624ebab-efcb-5608-bf1c-8a395dfe8e7a | note | Verification Activity: Activity - HP
aeec2237-c8c1-5745-a798-d0b043faa24c | note | Verification Activity: By - ENG
d11e2117-c1cd-41a0-8505-865b5bae1ae4 | signoff | AUTHORITY HOLDPOINT
451a1f49-7ef4-4a3f-80ca-aa68e8b30e88 | checkpoint | 4.19.2 - Hot-dip Galvanising
1e8cb928-f5b2-5d01-89ed-015ecbcdfc03 | note | Acceptance / Conformance Criteria - Steel sections, and all associated fittings shall be hot dip galvanised, in accordance with AS/NZS 4680. All alterations to fittings shall be hot dip galvanised following fabrication.
87b43d36-add0-5978-8bb7-3c3a686f21da | note | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
ef8c2149-85c2-5ad9-a75f-0da462b5086f | note | Verifying Document - Datasheet
2365f46c-f813-5346-8582-31fa8c3f8327 | note | Frequency - Prior to Works
300fb3a1-ae38-5548-b173-de3ebc008317 | note | Verification Activity: Activity - R
ab0054fa-45d8-5bb0-959b-60427cbbe37a | note | Verification Activity: By - SE
ea21574e-a46c-4592-94be-473b9ebc4f79 | checkpoint | 4.19.3 - Steel Piles
c3b56b4b-7010-5eeb-8315-a51850300fbd | note | Acceptance / Conformance Criteria - Steel piles shall be 310 UC137, mild steel Grade 300, complying with NZS 3404 and galvanised in accordance with AS/NZS 4680. Only new steel pile section to be used. All piles and production certificates shall be made available for inspection by the Engineer at any time.
b946f326-590d-5c91-a889-394f439d3335 | note | Standard / Specification - PS 18.2.4, PS 18.2.1, PS 18.2.2
713e7f38-62a0-57da-a975-ac7c5dc18b32 | note | Verifying Document - Mill Certs
35e7b825-1455-5b64-b857-06e278e578da | note | Frequency - Prior to Works
e9864212-55e1-59f6-8a16-491bf8c3aeec | note | Verification Activity: Activity - R
2953d0b9-2963-5a00-b115-70bd64bee8e6 | note | Verification Activity: By - SE
dc760361-bd81-453d-a46f-ab7b40c2f49f | checkpoint | 4.19.4 - Steel Reinforcement Compliance
827af98c-e835-59e2-8524-63a4f1b992c2 | note | Acceptance / Conformance Criteria - Conformin Steel Reinforcement Mill Certs conforming to AS/NZS 4671 shall be supplied.
b9dd3fe6-11b5-5657-9ad3-e09529cc17b6 | note | Standard / Specification - AS/NZS4671 & NZS3109
e8135d31-2872-5616-a093-e3c29c79719f | note | Verifying Document - Detail Sheets and Mill Certificates
129b31f8-dd06-5d46-90df-65c7b990e8d8 | note | Frequency - Prior to ordering steel
bab8cd47-e2e8-5648-8bfc-0966f5591b06 | note | Verification Activity: Activity - W
b0c0b5e0-3729-5fd4-9295-5938c9d93281 | note | Verification Activity: By - SE
8c40514a-441b-42f8-bf14-7d75ae45fdc4 | checkpoint | 4.19.5 - Capping Steelwork
1f48d729-7007-5dc0-9fbf-39fd4686254f | note | Acceptance / Conformance Criteria - All grade 500E (MA) reinforcement shall comply with AS/NZS 4671 and be manufactured using micro alloy Process. Quench and tempered is not permitted.
5d34bcc2-0115-5a01-aee0-fc38c69ecfe1 | note | Standard / Specification - PS 18.5.2
924c11cf-c29a-5cc8-98f2-eae060a88785 | note | Verifying Document - Detail Sheets and Mill Certificates
55284858-bd66-54dc-95c0-0886be610673 | note | Frequency - Prior to ordering steel
422b8337-4467-5dbf-a1db-0623b99c5a18 | note | Verification Activity: Activity - HP
6732c850-5153-51e4-b117-affbd648b5c6 | note | Verification Activity: By - ENG
88c36671-de83-49c9-b853-2042ef5695f3 | signoff | AUTHORITY HOLDPOINT
6fa414c2-dccc-4fb1-bc75-be5e5f501a41 | section | 9.01 Pile Construction
ea3a9b91-6f13-435d-adbe-74386c956c26 | checkpoint | 4.19.6 - PFC & UC Steelwork
c24c2de1-e8c6-555d-b741-23853a31228d | note | Acceptance / Conformance Criteria - Sections shall be grade 300 unless noted otherwise. All PFC & UC's to be grade 350 unless indicated otherwise All structural steel welding to comply with AS/NZS 1554 Class G.P. All welds to be 6mm minimum continuous fillet welds, unless noted otherwise.
231f62c2-b25d-547d-a7df-e959cc9f8976 | note | Standard / Specification - PS 18.5.2
2314fdd5-d5c6-5135-aca0-6fd0fd6240c1 | note | Verifying Document - Detail Sheets and Mill Certificates
8b7fc390-162e-58a2-b836-fc0e684cd4c7 | note | Frequency - Prior to ordering steel
22bd3387-8fbf-51cc-9d2f-985376595836 | note | Verification Activity: Activity - HP
e40265a5-174e-5d68-9e38-5ae140338aad | note | Verification Activity: By - ENG
f9f47e4f-169c-4af3-992e-ca5f1c001d64 | signoff | AUTHORITY HOLDPOINT
7ee36003-3390-4b21-bbf0-e47987b8c471 | checkpoint | 9.01.1 - Contractor’s Methodology for Pile Construction
80bbd022-75a6-58ce-90a6-d247ed6cbfe7 | note | Acceptance / Conformance Criteria - The Contractor shall submit to the Engineer for acceptance his methodology for the construction of the steel soldier piles at least two weeks prior to commencement of the works.
f26b60ea-38be-5393-adcb-f490df61df45 | note | Standard / Specification - PS 18.3.1, PS 18.1.2
4b739d45-ac5a-53da-90e4-29202b20ac44 | note | Verifying Document - Approved Methodology
0fba3257-029c-57e5-af77-4de69037a216 | note | Frequency - At least two weeks prior to commencement of the works.
3a0e1477-157e-5118-83d4-b4c1e86ca127 | note | Verification Activity: Activity - HP
43e474b2-e904-5d6f-b46e-e01e4294ae21 | note | Verification Activity: By - ENG
47176cb5-d7fc-4dae-a187-c70195ac5a48 | signoff | AUTHORITY HOLDPOINT
6f562c70-4f41-4afa-954c-d9b309525968 | checkpoint | 9.01.2 - Setting Out
15164b4e-80f1-5032-8040-03754ab2aa94 | note | Acceptance / Conformance Criteria - The Contractor shall be responsible for the correct setting out of all works, including set out of the position of the piles and anchors correctly to reflect the requirements of the specification and drawings.
9c9a3a5d-7a58-541a-bc1a-82f53f553243 | note | Standard / Specification - PS 18.4.2
a28eb173-aead-56fc-9ef0-bd5485d66631 | note | Verifying Document - Survey Records
6ed0e5f1-4540-5d67-aaca-178196a9b95b | note | Frequency - Each Pile
7afaeaaf-2b8d-5ebd-95fa-168017f74b65 | note | Verification Activity: Activity - S
f487acd9-358b-549e-b996-2f37af405f4c | note | Verification Activity: By - SE
7363c1d1-567c-46e4-953d-953dc0f42d73 | checkpoint | 9.01.3 - Setout Approval
5b050de3-c2cc-51b8-a6af-17f1e7b25657 | note | Acceptance / Conformance Criteria - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer.
d2356953-c8a5-5ac8-a4d9-35acaa382f50 | note | Standard / Specification - PS 18.4.2
ff47d44c-687b-5db4-b63b-d25a211d1f7c | note | Verifying Document - Engineers Approval
e2a35e9f-dad5-595e-bb55-92ae93ed6e4c | note | Frequency - Each Pile beofre excavation
cf9970c9-b61c-5963-8670-11d42a02673c | note | Verification Activity: Activity - HP
ac492bfb-f9bc-577a-8201-d0c922f32ae8 | note | Verification Activity: By - ENG
8816ec34-0f08-4d4a-bdf7-438d88823e90 | signoff | AUTHORITY HOLDPOINT
91d1983a-1082-4e73-824d-d9c575ac7d21 | checkpoint | 9.01.4 - Depth of Foundation
27d94b1b-3772-5e35-9524-c727c8d2d581 | note | Acceptance / Conformance Criteria - The Engineer will advise the depth of founding for each cylinder based on the driller’s ground description log, examination of the material from the excavation and samples at no more than 0.5 m intervals.
9507c00d-0479-558d-8f79-c6878d73cab6 | note | Standard / Specification - PS 18.3.2
bd51e68b-7184-5277-ab27-489a12c6a888 | note | Verifying Document - Engineers Approval
8a47eb7f-0dff-5857-a520-282e78ac38b9 | note | Frequency - Each Pile Before Survey and Concrete
d0052f56-d92d-5caf-90c5-4a419bd656b5 | note | Verification Activity: Activity - HP
1a5a4837-1196-5e97-9f7a-781f66e60026 | note | Verification Activity: By - ENG
b34ae62c-9733-405c-8d77-65d4a68360fc | signoff | AUTHORITY HOLDPOINT
4e0580f6-408c-4420-b26a-b63bb79d9a61 | checkpoint | 9.01.5 - Pilling Records
ba860b68-1264-5b48-9dce-9d51fb603c5b | note | Acceptance / Conformance Criteria - The pile driller shall maintain a daily record of the progress of the piling with time recorded, and details of drilling equipment used, casing installed, groundwater levels and ground conditions recorded. The daily records from the driller shall be submitted no later than noon the following day.
751dd713-8020-5c51-a8ba-f84011319a62 | note | Standard / Specification - PS 18.3.2
5fc5aef0-5295-50dc-aa6a-1d34a9eadfc7 | note | Verifying Document - Pilling Records
2cbde389-3809-5d4a-aa8c-a50d518335c6 | note | Frequency - Daily
873be76b-2895-5ec6-b256-862733a2d4fe | note | Verification Activity: Activity - I
34fe1736-2b38-52c6-b5dc-39e7dbe38dc2 | note | Verification Activity: By - SE
3eca93f3-8374-48e0-baba-796b66136207 | checkpoint | 9.01.6 - Pilling Timming
b7c7b08d-c59c-5334-8549-4997541cff49 | note | Acceptance / Conformance Criteria - During pile construction, none of the pile holes shall be kept open for more than 48 hours and no more than 4 piles under construction at one time.
1ee74a4f-9655-5a0d-aae9-155ab23ef49b | note | Standard / Specification - PS 18.3.2
c4e5591a-7f22-5d01-80b1-40af82bde42c | note | Verifying Document - Survey Records
87b78d2b-4c28-5373-8b6f-883842afd598 | note | Frequency - Each Pile
3c1ef372-061a-5896-8d55-6b8142d075db | note | Verification Activity: Activity - S
d447ce88-8857-5aa9-ad5a-43e2545baef9 | note | Verification Activity: By - SE
30f30a1f-b932-4745-9d27-cbd288cc8462 | checkpoint | 9.01.7 - Pile Excavation Survey
959f106e-21a1-5321-84d4-73799045d811 | note | Acceptance / Conformance Criteria - On completion of excavation, the Contractor shall survey the final reduced level of founding for each cylinder, measured to the nearest 0.01 m, and submit the surveyed final reduced levels for approval to the Engineer, prior to placing reinforcement and concrete.”
31f7f3da-402e-56d5-842f-012e43fd3afe | note | Standard / Specification - PS 18.3.2
14e51f82-3c25-5faf-9a5c-a017adaecad3 | note | Verifying Document - Survey Records
a2298aa0-e90b-5850-adc9-8edd7966d2e9 | note | Frequency - Each Pile before concrete
57b23958-35ba-5ddb-8705-fbd86d604cbd | note | Verification Activity: Activity - HP
3b352bbb-973e-5778-ba0a-aaed91502093 | note | Verification Activity: By - ENG
9f21100a-589e-4b4b-964e-11ccd65ab9e7 | signoff | AUTHORITY HOLDPOINT
3ce9e332-e5b2-4a00-9e99-e2ddf58f7ee5 | checkpoint | 9.01.8 - Construction Tolerances for Piles
13a9cc7e-71bd-542d-97bb-8b7ac5a1cf01 | note | Acceptance / Conformance Criteria - The allowable positional tolerances of the concrete piles shall be ± 50 mm. The completed pile shall be plumb to within 1% of vertical, as determined by the angle from the vertical.
0ed00902-c6ed-5d5c-b9d5-5fc3289ab0a9 | note | Standard / Specification - PS 18.3.3
1ab45036-1485-536d-846d-8a52b165a5b8 | note | Verifying Document - Survey Records
055c49b1-5fd2-573d-a43d-0fe3e6cabafa | note | Frequency - Each Pile
ab623cc4-88ae-57f2-8a90-510e72ccf848 | note | Verification Activity: Activity - I
a4b27676-8433-5ed5-94bb-156bb09568ab | note | Verification Activity: By - SV
f6580b7b-162b-4bf9-889c-215919c934e4 | section | 9.02 Monitoring Points and Survey
32bacd3b-f6d5-4d23-8d53-9605cbbbf960 | checkpoint | 9.02.1 - Monitoring Surveys / Deformation Surveys
8fd26e4f-e486-5f89-8bf2-0bcfe7479e76 | note | Acceptance / Conformance Criteria - Monitoring / Deformation Surveys shall be completed on all Structures as agreed with the engineer using installed monitoring pins or fix location on structures.
bdaea1ae-82a5-5c72-a1ca-3169441c5b32 | note | Standard / Specification - PS 18.7.1
26906c94-48dc-5d49-aee3-d235f654f13d | note | Verifying Document - Survey Records
6380b20c-0e5e-5753-8aa5-062d6aef08a0 | note | Frequency - As Required
0e9a0251-6dbe-54a3-ae1c-4b88e160d4f0 | note | Verification Activity: Activity - I
5b0fea63-45fb-5eba-b6ac-2e7854b04afe | note | Verification Activity: By - SV
ac7f50b9-5a75-4edc-9a87-23cb609bab3a | section | 9.03 As Built Records
61dc189e-c87e-4573-8b20-e0b9e47da0a1 | checkpoint | 9.03.1 - As-build drawings
f4035b14-7b40-5394-ab83-435e8028e597 | note | Acceptance / Conformance Criteria - As-build drawings showing survey points and final construction layout of capping beam
3f0332fb-7955-5659-89e2-847d77fbc96f | note | Standard / Specification - PS 18.7.2, PS 18.1.1
292c078b-4bef-5c19-8ef0-db4bac915957 | note | Verifying Document - As-build drawings and Survey records
cf129932-e454-5ad7-8eca-e403d41e880d | note | Frequency - All above ground Stormwater Systems
84bc4ef2-a034-5ea6-9ff2-5a45cc0b7ac3 | note | Verification Activity: Activity - R
09e63fb7-e6dc-528b-b821-533f4fceb187 | note | Verification Activity: By - SE
9e4652c0-8529-578b-a25a-583b78a4a515 | checklist | ITP - Stormwater - 102 - Rev A | itp | ITP - Stormwater - 102 - Rev A
cd5ff378-db9c-558d-92cc-e5570599c85d | section | 4.09 Stormwater Aggregate Materials
39ec763e-b98a-5657-a12d-70d01702cdd6 | checkpoint | 4.09.01 - Controlled Low Strength Materials - CLSM
e30489f9-a04f-5cf2-a8b8-a1d64aafc784 | note | Acceptance / Conformance Criteria - The use of CLSM by the Contractor will require approval from the Engineer on a case-by-case basis.
091f1233-36f6-59c2-a114-5a9cbffaf061 | note | Standard / Specification - PS 16.8.1, PS 16.37
65440023-3bc4-5ea4-aedf-910648b32aea | note | Verifying Document - An application submitted to the Engineer for approval, to use CLSM.
eec52394-604f-54b1-8371-aa99f2c10f5d | note | Frequency - An application submitted to the Engineer for approval, to use CLSM.
cc7d0ced-7247-5a89-b1bb-b30d877c484a | note | Verification Activity: Activity - HP
3a39c2cd-8899-59c2-a7bf-0f4b48462f79 | note | Verification Activity: By - ENG
ad0f8196-cfdd-55ad-bd16-d45b25f9397e | signoff | AUTHORITY HOLDPOINT
f925da67-4250-55a8-8f00-1a19e17d004b | checkpoint | 4.09.02 - AP65 Aggregate
f20dade9-dfb9-5485-b74a-09fbb2006905 | note | Acceptance / Conformance Criteria - AP 65 Aggregate is to be a crushed product with a maximum granule size of 65mm and be a graded, clean durable aggregate which meets Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities requirements
4c7241d9-2545-571c-b259-e43b7ba3d6e1 | note | Standard / Specification - PS 16.8.2.1, PS 16.9.1.2, PS 16.6, PS 16.37
cf26aced-4700-5e6f-94c8-807785f65747 | note | Verifying Document - IANZ Lab Reports
40ddf80d-d914-588b-bada-68693606f6f0 | note | Frequency - Submitted to Engineer for approval
cf4d0602-c16c-5ce0-b205-b0e2aa3f728f | note | Verification Activity: Activity - HP
704f7779-50d9-5cb8-be23-6f4a12cac89c | note | Verification Activity: By - ENG
498c79da-0f25-5de4-98c9-2ee152c74839 | signoff | AUTHORITY HOLDPOINT
fac428ce-f73b-5571-b51f-9bdd11ed2a9a | checkpoint | 4.09.03 - AP40 Aggregate
a2239a4d-683d-5575-a157-c4dd322ecdb0 | note | Acceptance / Conformance Criteria - AP 40 aggregate is to be a crushed product with a maximum granule size of 40mm and be a graded, clean, durable aggregate and which meets Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities requitements
0c639d89-be0a-5371-99af-d67e17926e7a | note | Standard / Specification - PS 16.8.2.2, PS 16.9.1.2, PS 16.6, PS 16.37
41a3f70d-fc04-5990-98fc-19df8b0c3219 | note | Verifying Document - IANZ Lab Reports
e36ff9fe-55f5-5198-adbd-c76e8e833b79 | note | Frequency - Submitted to Engineer for approval
0877341c-8b8d-5f2e-a2c2-6a3b69bcd2cd | note | Verification Activity: Activity - HP
0cc8e900-78f3-52f2-9110-05fc85635f42 | note | Verification Activity: By - ENG
27964652-3920-5fc8-975b-325c79c9ce48 | signoff | AUTHORITY HOLDPOINT
2f83b187-72b2-5db7-80bc-58c2cf4142af | checkpoint | 4.09.04 - AP20 Aggregate
21194d5b-23cd-5b4d-a2df-104f0a5c4170 | note | Acceptance / Conformance Criteria - AP 20 aggregate is to be a crushed product with a maximum granule size of 20mm and be a graded, clean, durable aggregate and which meets Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities requirements
95b3e2cf-4c63-57d7-a824-a3ce011a9b2f | note | Standard / Specification - PS 16.8.2.3, PS 16.9.1.2, PS 16.6, PS 16.37
32b6384d-7688-590c-a2a0-edde67b1fe1a | note | Verifying Document - IANZ Lab Reports
fbcd560b-3c92-5a50-8fa9-95ac8475bff0 | note | Frequency - Submitted to Engineer for approval
7771bb81-b9c1-5442-b5de-72000969e936 | note | Verification Activity: Activity - HP
0136a962-b1ca-5509-b280-3ea4f8ffef77 | note | Verification Activity: By - ENG
2d1cb47b-bbd2-5594-aab8-f2c2dc81ac2d | signoff | AUTHORITY HOLDPOINT
0ad38278-cc4d-558c-b2c1-120f6cd7f879 | checkpoint | 4.09.05 - Bed, Haunch Zone Material and Side Zone - Gap 7
74e9462c-41e8-5b18-ad42-c0680332f552 | note | Acceptance / Conformance Criteria - For bed and haunch zone well graded GAP 7 will be used and tested for Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities
ca30a4ed-1447-56db-b388-39aa0cc54c58 | note | Standard / Specification - PS 16.9.2.1, PS 16.9.1.2, PS 16.6, PS 16.37
12f414c2-3f28-5a85-bc60-a66178c276a9 | note | Verifying Document - IANZ Lab Reports
72a41e48-9d1d-5d09-9dcb-91a30defc107 | note | Frequency - Submitted to Engineer for approval
5958e648-e524-551e-830a-b853383a1d53 | note | Verification Activity: Activity - HP
e8740316-f640-5245-9e26-48a5dabcf412 | note | Verification Activity: By - ENG
78ff32b8-ee94-5521-b1ad-8905da3b5910 | signoff | AUTHORITY HOLDPOINT
6d049330-946c-58b2-8983-86ffbb096276 | checkpoint | 4.09.06 - Alternative Bedding
3c2428c4-fcda-5da0-b9be-7a21856564da | note | Acceptance / Conformance Criteria - If the Contractor wishes to propose a different material from that specified in this section, the Contractor shall submit to the Engineer
17376173-ad20-52e0-ba8d-07c850da4aad | note | Standard / Specification - PS 16.9.2.1, PS 16.9.1.2, PS 16.37
3692c496-44dd-57a0-8f63-0131667d6b6a | note | Verifying Document - Statement from the concrete pipe supplier
88ad1bdd-d340-559a-859f-c40552c42d2d | note | Frequency - Submitted to Engineer for approval
6893ecf4-1086-50e1-a808-e624a5866082 | note | Verification Activity: Activity - HP
467f2f40-279f-5725-ac2c-49357a478eee | note | Verification Activity: By - ENG
580acf08-98c7-5ba6-925a-c6039f00c265 | signoff | AUTHORITY HOLDPOINT
b9f8de3a-706a-52a1-ab00-3cb4d37ab203 | checkpoint | 4.09.07 - Overlay Zone Material (for concrete pipes)
3c1699a2-804a-5cbc-aef8-75947b07f04b | note | Acceptance / Conformance Criteria - Materials for the overlay zone GAP 20 shall be used which has been tested for Grading, Weathering Index, Crushing Index
391522af-5f70-5a9f-b1d4-4784d5b69df8 | note | Standard / Specification - PS 16.9.2.2, PS 16.37
5aa051d3-d2c8-5d8b-b85e-281603b87f3c | note | Verifying Document - IANZ Lab Reports
0f03f16d-7215-5225-9938-b5aeb69f65b5 | note | Frequency - Submitted to Engineer for approval
3e4ccc18-0827-5f59-a582-62a1dedf832c | note | Verification Activity: Activity - HP
b99863c6-a8a6-56d8-9e17-4d3e04586d89 | note | Verification Activity: By - ENG
76e662d4-d57f-5932-beb8-3d1824b930c0 | signoff | AUTHORITY HOLDPOINT
23bf3a00-741a-5445-b6d3-6516f33ef183 | section | 4.10 Stormwater Pipe Materials
966173e6-ba82-5746-a0f1-bd750dfd2756 | checkpoint | 4.10.01 - Steel Work
377c6d37-c687-5743-8314-354c3b107a51 | note | Acceptance / Conformance Criteria - All cut surfaces shall be protected with a corrosion protection coating i.e., zinc rich paint.
a680ed0b-fe68-5038-b64e-237f05726449 | note | Standard / Specification - PS 16.8.4
f0bf0e5c-6730-5202-a688-d643fbc2a8f3 | note | Verifying Document - Datasheet
96357d27-8b22-5a04-9175-84239c6b139e | note | Frequency - Prior to use
3ce56403-c7b4-5562-b05b-5b59c00b388a | note | Verification Activity: Activity - R
a6a11009-c128-5b38-bec3-3faf34121dc2 | note | Verification Activity: By - SE
3dc4f55f-3ee1-54f1-a86c-bc36c3154d2d | checkpoint | 4.10.02 - Steelwork
d7a3d44c-e869-55ab-87ff-92c520cc5de6 | note | Acceptance / Conformance Criteria - Unless otherwise specified, all steel work shall be fabricated from mild steel conforming to the requirements of AS/NZS 3679.1:2010 and AS/NZS 4680:2006.
2e1e777a-a237-5d3c-9182-aa79b1ef7d31 | note | Standard / Specification - PS 16.8.1
5398d8f5-edee-58f8-879d-f8b31a566f21 | note | Verifying Document - Datasheet
e7cfe74a-3f9d-5081-b0bc-22c0bd672074 | note | Frequency - Prior to use
6476b188-ba1b-5682-a208-c4e9ac2b4070 | note | Verification Activity: Activity - R
a0fe7edf-f43b-5ce6-a07d-3e4399db7357 | note | Verification Activity: By - SE
1f7657f2-c308-50a9-bc68-e681cde4d937 | checkpoint | 4.10.03 - Welding
5cbd83a4-7889-554d-b54b-1d139247951d | note | Acceptance / Conformance Criteria - All welding shall be carried out in compliance with AS/NZS 1554:2003-2017 and by suitably qualified welders.
04e3f181-f4d2-514c-a5ed-d22ea9e208ee | note | Standard / Specification - PS 16.8.4
b1753c78-e3c6-594a-8f9f-bd6975b2aba1 | note | Verifying Document - Welders Certs
dbfc5792-db96-5252-b737-973d749f3d9f | note | Frequency - Prior to Welding
be8636a9-5920-510f-8e32-fb8a411cd148 | note | Verification Activity: Activity - R
12a634dd-f647-5953-85b5-bb7ec734b9b1 | note | Verification Activity: By - SE
f38e0496-44f9-5523-b480-8807bac727eb | checkpoint | 4.10.04 - Steel Fitting Corrosion Protection
5a5262f1-d065-5eae-b5b6-a14f4f031790 | note | Acceptance / Conformance Criteria - Steel fittings shall be shop assembled as large as practicable before hot dip galvanising or zinc metal spray to AS/NZS 2312.2:2014 and AS/NZS 4680:2006, to minimise the number of field welds and bolted joints required.
8d66b788-6836-52ca-9fc4-d1e113e35d46 | note | Standard / Specification - PS 16.8.4.1
af6f3bba-42f8-552a-9aef-bde75f2916e6 | note | Verifying Document - Datasheet
629513b7-e0a4-5c56-ac97-ae87559ea76b | note | Frequency - Prior to use
5d601df4-2110-521b-a0ec-3b86cad828a1 | note | Verification Activity: Activity - R
f4452ee0-9fde-55bf-9491-2f4b16e59486 | note | Verification Activity: By - SE
539fc29b-524a-5fd0-8585-fb4978b1dc05 | checkpoint | 4.10.05 - Hot Dip Galvanised
df09fd84-38ea-58d8-8c2d-492bdc7b659d | note | Acceptance / Conformance Criteria - All ferrous metalwork except standard galvanised pipe shall be hot dip galvanised to HDG900 unless otherwise specified.
d54bca03-4dc0-5b45-8950-75c80022314d | note | Standard / Specification - PS 16.8.4.1
49e992f8-080a-577c-b274-ac42a6ae9d2c | note | Verifying Document - Datasheet / Cert
ebdb4d40-336e-592f-9c3c-567112203839 | note | Frequency - Prior to use
f422cfe4-0cd1-55dd-8d0d-f24a6946e6da | note | Verification Activity: Activity - R
df2f202a-bfb7-546b-bad0-9a95d48fced0 | note | Verification Activity: By - SE
7d2cc53f-df6a-5667-9d53-523d519af11b | checkpoint | 4.10.06 - Fastenings
46b5a0a6-1c42-5a0c-894e-4544c2ed4211 | note | Acceptance / Conformance Criteria - All fastenings associated with manholes or drainage structures shall be either hot dipped galvanised or stainless steel. Zinc Plated fastenings shall not be permitted
b206b242-7cef-5c5c-9060-48280fc2dd7e | note | Standard / Specification - PS 16.8.4.2
6eda162d-b203-55a2-a46c-fe5edb486ffe | note | Verifying Document - Datasheet
a1fb4db4-bdb6-5644-b79a-e73d07a9dcea | note | Frequency - Prior to use
d375c42e-7b24-5de3-95a8-5951a7f24a5f | note | Verification Activity: Activity - R
2c3b8511-72f8-57f5-a1bc-31e99ac82b6f | note | Verification Activity: By - SE
7b4a1eea-cc77-5fb6-b4bd-077480ddf4e2 | checkpoint | 4.10.07 - Concrete pipes and fittings
cf91cef2-fef8-5a53-a759-c653455421cc | note | Acceptance / Conformance Criteria - Concrete pipes and fittings shall comply with the requirements of AS/NZS 4058:2007 for concrete pipes
751d06ed-6d5e-502d-8d82-01bdc7c21606 | note | Standard / Specification - PS 16.9.1.1, PS 16.37
ed2e82ef-ce0f-5ea6-88db-d86ed4d50680 | note | Verifying Document - Datasheets
295f87ca-e57e-52d5-9575-b1d6c8ba68c4 | note | Frequency - Prior to use
bfec91b0-b29a-52b1-ad4c-43134da140c4 | note | Verification Activity: Activity - W
ae52bb51-1449-5b5b-bbbe-81b4ad7c78d3 | note | Verification Activity: By - ENG
e4e40574-e42e-5205-a2f4-e000b57235a5 | checkpoint | 4.10.08 - Quality of Pipe and Precast Units
707fcce3-744b-587d-a7f5-39fbb0eff86a | note | Acceptance / Conformance Criteria - IANZ Accredited Manufacturers certificate to NZTA F/3 (refer to Appendix F)
789d4545-9be8-5dd1-bd5c-a362ac56701e | note | Standard / Specification - PS 16.34
c21071c5-daf8-5bc5-8524-9d8c84c4f82c | note | Frequency - For every pipeline delivered (as soon as they are delivered)
3b73bba7-b54b-54cb-8654-0d2ee13ed325 | section | Stormwater Structure Materials
88d8e271-ad5a-56d9-9f89-d653447565e2 | checkpoint | Precast Catchpits
c937119d-ccba-5579-9e94-2a25c2ca1c15 | note | Acceptance / Conformance Criteria - All catchpits shall be precast concrete suitable for HN-HO-72 traffic loading.
5b134087-3e81-5c9a-87ef-2cd8fc8ae6cc | note | Standard / Specification - PS 16.10.1
3a158ccc-5a8e-5d42-a148-748e032bac68 | note | Verifying Document - Datasheet
5541601f-a654-5a80-a28d-a5ca962c32cb | note | Frequency - Prior to use
a0153a0c-38fb-5a17-ab1b-7f489c783895 | note | Verification Activity: Activity - R
477973bb-1148-5250-bbb3-e1c8cdae87d9 | note | Verification Activity: By - SE
093074c6-a0b2-52b2-bc9e-35125688642b | checkpoint | Catchpit Lids
f2903a11-7dc7-5c6f-9f13-322e5ff49afe | note | Acceptance / Conformance Criteria - Non-Rock 510mm Class D Heavy Duty type lids or similarly approved shall be used unless otherwise specified on the drawings. Heavy Duty type lids to be suitable for HN-HO-72 traffic loadings that are cycle friendly.
fae726b1-0f23-52ac-a6f8-6827d7529822 | note | Standard / Specification - PS 16.10.2
19b5ce7c-3115-5dae-8455-0de9c205972a | note | Verifying Document - Datasheet
67ec4116-0be3-52dd-9ef7-e7f25cd71ca9 | note | Frequency - Prior to use
5ab56e84-c4c8-5df7-940c-8c7f3c6a8987 | note | Verification Activity: Activity - R
1e0d344b-903f-575c-bdb7-4008a8839c1a | note | Verification Activity: By - SE
19aeb6ad-5e7f-5bd6-91c8-7f67d08fcb42 | checkpoint | Precast concrete manhole
4c8f658d-c028-568c-88df-bc2bec73e9b0 | note | Acceptance / Conformance Criteria - All precast concrete manholes shall be manufactured in accordance with NZS 3109:1997. All manholes shall be suitable for HN-HO-72 traffic loading.
dd6ee6e5-95d2-5b68-975d-25d5ffbfdee1 | note | Standard / Specification - 16.15.1
27ae4c66-7e65-574b-b984-54411eb77025 | note | Verifying Document - Datasheet
af0dc79e-54ad-5cc6-8bf1-113d6dee4d44 | note | Frequency - Prior to use
cfef9c36-3ace-5446-999b-a43566defe79 | note | Verification Activity: Activity - R
2ee8fa7e-1ad4-5531-ae56-878c841420b5 | note | Verification Activity: By - SE
5b2627d0-2e58-5354-b504-083208f67e39 | checkpoint | Catchpit Grates and Frames
d81f0d9b-b5c5-5c57-b19f-5e5cf779a556 | note | Acceptance / Conformance Criteria - Catchpits grates and frames shall be grey cast iron suitable for HN-HO-72 traffic loadings.
92deca03-5a00-5730-af20-f54f1adf37c4 | note | Standard / Specification - PS 16.10.1
1ba6003e-4acf-5ff8-91d2-42296dcd048f | note | Verifying Document - Datasheet
e0a7f3f3-ed5b-5f99-a9de-0451af7a3e59 | note | Frequency - Prior to use
786fd196-bdee-503c-9ee0-23186cc75c51 | note | Verification Activity: Activity - R
4d85e376-020a-57f5-8854-af60fec42c8f | note | Verification Activity: By - SE
78bd5447-2d58-54bf-9df7-470807cc975d | checkpoint | Scruffy domes lids
76cf877b-24b4-5bbe-9155-b40135d67abb | note | Acceptance / Conformance Criteria - Scruffy domes lids shall be galvanised steel Hynds Type 2 scruffy domes (unless noted otherwise in the drawings), or similar approved.
d64233aa-fa04-50d9-a6ff-755e4c04dbeb | note | Standard / Specification - PS 16.16.2
d547d270-4e66-5f2a-acc3-8ad67f9b3b3a | note | Verifying Document - Datasheet
1a7a8c3e-9ff0-5451-8f4c-7ddd17136e61 | note | Frequency - Prior to use
77a57a57-8147-5ff4-b62b-7cc8a8c3fd10 | note | Verification Activity: Activity - R
6e8dd5af-1c9d-5eed-8f79-2270540b94b4 | note | Verification Activity: By - SE
efe26448-c3e6-566c-ae3f-bf30238202e4 | checkpoint | Cement Mortar
e83b7c8d-838e-521e-b099-a1ac97da944e | note | Acceptance / Conformance Criteria - Cement mortar shall be Durability Class M4 in accordance with NZS 4210:2001, with a minimum compressive strength of 12.5MPa.
d93a2cb0-2737-5a19-b712-f7a90e88e3c8 | note | Standard / Specification - PS 16.8.1
a358f62d-7eee-5465-be21-49e3d4658661 | note | Verifying Document - Datasheet
057ce013-ca94-5210-8802-57c8057f3b67 | note | Frequency - Prior to use
4add4b7b-c29f-5c52-a36a-463f8d74cd34 | note | Verification Activity: Activity - R
96effd1b-b82a-5314-8819-0552f268356a | note | Verification Activity: By - SE
f69f37b4-c66d-5755-9c93-286cea0b7b08 | checkpoint | Epoxy Mortar
2803cfff-f05b-5fa6-af6d-d7d33011f2a3 | note | Acceptance / Conformance Criteria - Epoxy mortar for use in manhole riser joining or repairing of damaged or cut concrete (to provide cover to reinforcing due to cutting of precast units) shall be Hynds (MSR) or Humes Hume bond (or similar approved), applied in accordance with the manufacturer’s recommendations.
40f62655-366d-509c-b8f5-b400c39f1e15 | note | Standard / Specification - PS 16.8.1
d9b15cf0-ad91-5739-ae59-415fec707211 | note | Verifying Document - Datasheet
c48b4140-83de-5281-811d-b3795f24e42c | note | Frequency - Prior to use
203177cb-78b5-5b84-a521-91eb8f4bb409 | note | Verification Activity: Activity - R
a2e4ea47-b66f-5d8f-902e-09350a0b64b3 | note | Verification Activity: By - SE
4a348f4b-a593-5389-b2df-846d82038c21 | checkpoint | Precast Headwalls and Wingwalls
6213dc41-c9bc-5599-af5b-81df4e9514a7 | note | Acceptance / Conformance Criteria - Precast concrete headwalls or wingwall units shall be manufactured in accordance with NZS 3109:1997.
4479de59-8082-54c3-a8ba-aee9a90a0d5b | note | Standard / Specification - PS 16.13.1
4793e04d-01b8-5103-9b82-9549abdc2415 | note | Verifying Document - Datasheet
c41a80f9-acb8-5e95-966f-99626f3d83ab | note | Frequency - Prior to use
64b90417-da12-5044-af5c-ffafe45a5817 | note | Verification Activity: Activity - R
6ca3565f-946a-5d1a-b64a-7d6b57494c69 | note | Verification Activity: By - SE
c46fbfa8-380d-5cbe-a4b0-0e736b31d68b | checkpoint | Erosion protection matting
29f7955b-338d-508c-9586-6dd5ccb7c71f | note | Acceptance / Conformance Criteria - Erosion protection matting (coir Blanket or similar approved) is to be 100% biodegradable.
042ac40a-37c4-585a-bed9-1e52a714a109 | note | Standard / Specification - PS 16.13.1
9f8eaa13-daef-559d-bfa6-8e60cbe69524 | note | Verifying Document - Datasheet
77e0e57e-1bbd-5c83-a08c-0271c59e4176 | note | Frequency - Prior to use
ce6c7dc4-e28f-5e1f-ae03-65159e2c7281 | note | Verification Activity: Activity - R
dc8bae03-ad38-5352-b2c4-97b5b93746e7 | note | Verification Activity: By - SE
5b553bc0-ff79-542c-9634-1b731ecd982d | checkpoint | Precast Soakage Pit
92d1e12b-8bc5-5d61-bbec-cb8dbcc3804b | note | Acceptance / Conformance Criteria - All precast concrete Soakage Pit manholes shall be manufactured in accordance with NZS 3109:1997.
7271cd5d-7543-53c5-8532-58841072f24a | note | Standard / Specification - PS 16.12.2.1
669d8b05-0d63-51d7-a8b6-328b8b265395 | note | Verifying Document - Datasheet
4d9738e2-637a-57d1-ac26-02909570eb41 | note | Frequency - Prior to use
d504f1f1-8ac7-5214-b6b5-b0198e0777ab | note | Verification Activity: Activity - R
e0f1084f-c245-5951-8df3-a60bc00d8b18 | note | Verification Activity: By - SE
979e7733-19d7-51d8-8344-f947f0c4fc03 | checkpoint | Insitu Manhole Concrete
e64033a4-9f00-5ef6-a7a6-60381abb6d0e | note | Acceptance / Conformance Criteria - Manholes shall be constructed 20MPa insitu concrete.
1ed988b1-5877-5569-a935-3605b67c9072 | note | Standard / Specification - PS 16.12.2.2
924f835f-2fe4-54cb-af0d-d2dc898ce496 | note | Verifying Document - Datasheet / Mix Design
96a0b5e3-39f5-57ec-8c8f-47ed0c03fc14 | note | Frequency - Prior to use
164a4368-9b37-5b4d-975b-996ad53c55f1 | note | Verification Activity: Activity - R
f670b87d-a71e-5244-a7a9-6cc1be1dfe2b | note | Verification Activity: By - SE
2ea57910-8c8c-5196-a3d2-5ceb596fbc25 | checkpoint | Manhole Sealant
c4019075-b51b-5a2a-a9b1-54577e186383 | note | Acceptance / Conformance Criteria - All joints between ring segments of precast manholes and chambers shall be sealed with ‘Grey Butyl Manhole Sealant – Hynds (SM9020)’ or similar and approved.
8cb84cac-fb53-5061-8959-01c2c2d86dd8 | note | Standard / Specification - PS 16.12.2.2
e570e715-569d-58bb-bc3c-938429fe6136 | note | Verifying Document - Datasheet
bbf4f412-bb85-5fd0-8b3a-b6fb23f758c6 | note | Frequency - Prior to use
026a0b64-7fb5-5b19-8149-3ce972a6193d | note | Verification Activity: Activity - R
35325e5c-cdce-5e26-9cc2-dcf2dfc81750 | note | Verification Activity: By - SE
b4cf8b52-6853-512f-9289-65e3b8e4fb5d | checkpoint | Head and Wing wall Insitu Concrete
37a91f9f-bb26-5756-9144-92015cb47515 | note | Acceptance / Conformance Criteria - Headwall and wingwall insitu reinforcing shall be steel grade 500E.
d47e7fea-3edf-5574-ae45-610b24fd3917 | note | Standard / Specification - PS 16.13.2
320b5c08-ad5a-52a9-ac73-71c6a8730e2f | note | Verifying Document - Mill Certs
24ba4c06-9eb7-5793-acab-09f336d3aab8 | note | Frequency - Prior to use
a925f5d1-e4da-54ba-9c82-849e5465aac5 | note | Verification Activity: Activity - R
23c8ea15-d6e2-5e4f-ab1c-2bd27957ea81 | note | Verification Activity: By - SE
bd845031-c77f-5c40-a992-04b864e26387 | checkpoint | Head and Wing wall Reinforcing
aaf8f92c-c01c-5725-9973-97a7443122b3 | note | Acceptance / Conformance Criteria - The headwall and wingwall cast in-situ concrete shall be 40MPa
aeaede8b-78dc-53d7-b235-060d5658038a | note | Standard / Specification - PS 16.13.2
31862813-3836-5e91-ba8f-c7ef6589f22f | note | Verifying Document - Mix Design
d7c2c955-f5a1-5ce6-b6dd-d989541ff6be | note | Frequency - Prior to use
e9ca799e-2630-5f4e-92f7-99c7fca30705 | note | Verification Activity: Activity - R
758d0350-d1c3-5418-a9f3-456c16a1ca75 | note | Verification Activity: By - SE
cfd464f7-8406-5aaf-91cf-00f786460477 | checkpoint | Soakage Pit Insitu Concrete
2b946692-fd81-54ab-a732-29bf37281dd4 | note | Acceptance / Conformance Criteria - Soakage Pits shall use 25MPa concrete.
6fe54b1b-08c4-5505-b528-65de2841d046 | note | Standard / Specification - PS 16.12.2.2
d0b4e723-a66f-5a27-b81d-e07b74af0297 | note | Verifying Document - Mix Design
a3dca25d-b67b-5456-acdd-160a635c654a | note | Frequency - Prior to use
d08965eb-9802-5af7-941e-d2beeb7b392f | note | Verification Activity: Activity - R
32d38444-2531-567f-b521-03cf771baabf | note | Verification Activity: By - SE
f9d83a3e-d5b1-56a3-941d-d9e22ec7f358 | checkpoint | Benching Concrete
bdbff518-2ae0-5e4c-9516-77620fd49bbf | note | Acceptance / Conformance Criteria - Benching shall be 20MPa concrete
bc58c2cf-4bdd-563f-9bf5-64f823d2f684 | note | Standard / Specification - PS 16.15.2
bfa1d0c1-12ed-5b46-9ef7-8caf0bdf4453 | note | Verifying Document - Mix Design
8d24b826-3a7b-543d-a70b-b3a3c73e93b8 | note | Frequency - Prior to use
1d1cdf93-dc1c-567b-8ab0-c4d41db52db8 | note | Verification Activity: Activity - R
126f1ec5-a41a-554a-a36b-0b468b53835d | note | Verification Activity: By - SE
47784b3b-2e2b-5025-85b1-0b202af4d60b | section | Stormwater Rip Rap Materials
08bb8ab2-8a01-5a53-8a9e-89f30d6bbdef | checkpoint | Rip Rap Rock Source Properties
5d2ac7fe-6c29-50fd-90e4-66c2bc70064c | note | Acceptance / Conformance Criteria - The Riprap Source shall be tested for Point Load Strength, UCS Rock, Weathering Index, Crushing Resistance, and Solid Density.
888fb658-168c-5d7d-93f8-db0dc103a904 | note | Standard / Specification - PS 16.8.3
bfcbfe8b-68df-5797-9d8d-9ce606d35d74 | note | Verifying Document - IANZ Lab Reports
4cea9ff9-8abd-5b25-8cd5-5423e96469bb | note | Frequency - 1 per 1000m3
ff38cb98-b324-5f90-aef6-8180a8d13236 | note | Verification Activity: Activity - HP
fed9edd0-37cb-5531-9a39-85599aee693d | note | Verification Activity: By - ENG
464a2016-bb49-51f6-bc48-8872ae382ffd | signoff | AUTHORITY HOLDPOINT
28ed066e-c70f-5109-9ca0-3b0bc16d1b6a | checkpoint | D50=150mm RipRap - Grading
d8fc3399-006a-52f5-9067-d0c74b5c7d51 | note | Acceptance / Conformance Criteria - The D50=150mm RipRap grading for the drainage design shall be in general accordance with Auckland Council Technical Report TR2013/018
305f7eaf-ffaf-5d5b-b459-9245d4e66138 | note | Standard / Specification - PS 16.8.3
2c7798d2-94e2-5d96-b985-170e9355dcfc | note | Verifying Document - IANZ Lab Reports
8b54b130-c770-5cd3-9d8d-0301f808c42d | note | Frequency - 1 per 1000m3
c0bc4987-dc4f-5ef5-b9f5-06399d3f9032 | note | Verification Activity: Activity - HP
7499c43d-a449-5e59-b8b8-c1097281bf92 | note | Verification Activity: By - ENG
00d8763d-2156-5eef-bf80-93721014cef8 | signoff | AUTHORITY HOLDPOINT
ac0fd6f7-0924-5eb2-9715-6e8602c1710d | checkpoint | D50=250mm RipRap - Grading
9a273695-eb29-5e38-928d-c9aced65aa49 | note | Acceptance / Conformance Criteria - The D50=250mm RipRap grading for the drainage design shall be in general accordance with Auckland Council Technical Report TR2013/018
e6956247-8a18-5f94-b9d8-d8cf3acc1f61 | note | Standard / Specification - PS 16.8.3
11855f4f-f662-5a1c-a6e4-84a6f415887e | note | Verifying Document - IANZ Lab Reports
07eb8e77-0f1f-561e-9cf1-cbbaf6295c3d | note | Frequency - 1 per 1000m3
6ffb8563-d25e-5305-99cd-375286aabc02 | note | Verification Activity: Activity - HP
d94a883c-34d1-5396-a871-5134939efc4a | note | Verification Activity: By - ENG
01736f73-b24f-5ca4-ac1c-c6f99396fdb9 | signoff | AUTHORITY HOLDPOINT
93232804-bf1f-54a7-ba4c-a82963b5cbb4 | section | Subsoil Drainage Materials
663ec603-0c7b-57a2-8839-daa0af3a1523 | checkpoint | Subsoil Drainage Pipe
5f11d6ef-d3c4-54f8-aee6-bc7d6316510f | note | Acceptance / Conformance Criteria - Pipes shall be high density polyethylene (HDPE) smooth bore perforated corrugated plastic pipe as shown on the Drawings and shall comply with the requirements of NZTA F/5.
763ee716-d6c3-5656-9dd7-97abcf876a8e | note | Standard / Specification - PS 16.11.1
ba06aecb-653a-54b4-b9f6-694c9e5443cb | note | Verifying Document - Datasheet
c266e3b7-e0c8-5672-8e07-5bb16dc70f78 | note | Frequency - Prior to use
8dbd61b4-3390-5762-b467-a37a3d9614ea | note | Verification Activity: Activity - R
ba221a4d-8a87-5032-843f-99a6d10bcdc6 | note | Verification Activity: By - SE
a13884ea-9bb7-55eb-a3bf-bb8ccac48854 | checkpoint | Filter Material
dcede6a6-e5af-5474-949d-4aa3ba924e7f | note | Acceptance / Conformance Criteria - Filter material shall be placed around drainage pipe as shown on the Drawings and shall comprise no fines AP20/AP40 material.
d793f47f-5d1c-52f3-a83c-8fc7739f44b1 | note | Standard / Specification - PS 16.11.1
ca931fad-85be-5f9d-844c-88524285eebf | note | Verifying Document - Datasheet
ecd42e7a-05ca-5f8f-9d1e-9e46d50e18e6 | note | Frequency - Prior to use
af2ea9b8-f4fa-505e-969a-df9d272eb54c | note | Verification Activity: Activity - R
6230b079-8e3a-507d-b05c-763651fb82bf | note | Verification Activity: By - SE
acc12408-3fb2-5ab7-8e31-22a328e1d063 | section | HDPE Liner
50262df9-bda3-41ca-8ce2-3b8af5a1477b | checkpoint | HDPE Liner
cce30d83-5be4-5d54-976a-266e59bf5399 | note | Acceptance / Conformance Criteria - The liner is to be 1mm thick HDPE material complying with GRI GM13 and fixed to the surface in accordance with the manufacturer’s specifications.
1978c5ed-d64c-5f9b-be42-86030ed8bc5a | note | Standard / Specification - PS 16.19.1
59cabbd2-a983-5453-805a-6c0a638ee48f | note | Verifying Document - Datasheet
c613b4d8-e829-55ce-af8c-eb107e8e4563 | note | Frequency - Prior to use
d67cbf6c-0c7e-522f-ab2d-81ff2ee11b41 | note | Verification Activity: Activity - R
6b5a5713-c9f6-5ac6-8d89-41d6574dd06c | note | Verification Activity: By - SE
b2ee111b-85dd-5d91-b1c7-987c8cd64a33 | checkpoint | HDPE Liner Bedding
2ca470c8-1f19-5b6d-aed0-af396a9a1ec7 | note | Acceptance / Conformance Criteria - The sand membrane shall be clean sand free from contamination.
13ba086a-0ba4-508e-8a82-a42479b1b10b | note | Standard / Specification - PS 16.19.2
9ae3f07c-9cef-56f9-9e35-0be8c98f5eb7 | note | Verifying Document - Datasheet
b168ac11-82bb-5eff-87ba-4deece75bc07 | note | Frequency - Prior to use
a42ef08f-bd84-56f4-9c1d-d71128b54418 | note | Verification Activity: Activity - R
e4c1b13e-6135-5c9a-a6e9-18ee890bded7 | note | Verification Activity: By - SE
09831387-a4cc-5e4e-840d-c5ebccc38528 | section | Stormwater Geogrid and Geofabric
4849c987-2e84-57e1-9a6b-b4241993f3ff | checkpoint | Geofabric
b275e6fe-d370-561a-a486-287f57ab5c25 | note | Acceptance / Conformance Criteria - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval at least two weeks before commencement of the works.
372a82a4-b690-5489-ba37-bcd2717026d7 | note | Standard / Specification - PS 16.29.2
fe04de85-cd76-5bda-b406-2bffeeec9ba5 | note | Verifying Document - Datasheet
53ce6a45-b4ec-54b6-b251-27b9a54b698d | note | Frequency - Prior to use
f39d7678-acb5-5cac-8de7-1d6168d5f8cc | note | Verification Activity: Activity - R
408f9185-f15d-5d1d-89be-b27d74f1dce8 | note | Verification Activity: By - SE
4d008daf-90df-5427-8a01-3090a3181775 | checkpoint | Biaxial Geogrid
4d00fdb1-e085-5f4e-9f49-4dece679ceee | note | Acceptance / Conformance Criteria - The biaxial geogrid shall be manufactured in accordance with a management system which complies with the requirements of BS EN ISO 9001, BS 14001. The Contractor shall submit the full details of the geogrid they propose to use for approval at least 2 weeks before commencement of the works.
28d9f1c9-2b4d-54fc-a6fe-41f477159503 | note | Standard / Specification - PS16.29.3
57ccaa8f-f9f2-54b6-9ed4-b41b9845924f | note | Verifying Document - Datasheet
7b59a1cd-a1b2-586c-88b7-afe2786de8b9 | note | Frequency - Prior to use
09d73cb0-81d7-5d60-a067-f6dafcb2daef | note | Verification Activity: Activity - HP
2fdb51cc-a059-5397-ab01-4e816364f50c | note | Verification Activity: By - ENG
9bcd6e55-d445-590a-9a49-3e5215e25fa6 | signoff | AUTHORITY HOLDPOINT
70aa3e3e-d978-53db-893b-635fe6b37eca | section | Bioretention Soil Media
a6fe90de-8122-5aac-8091-c7f6d31a4c2f | checkpoint | Bioretention Soil Media.
7bf8dce9-0e33-585e-aeec-b571e3a8697f | note | Acceptance / Conformance Criteria - Test results for soil filtration media material properties are submitted to the Engineer including ASTM F1815-06 test results, pH, clay content, organics content and material grading curve.
f844f8f3-39ce-5f95-a123-3e04896f6fab | note | Standard / Specification - PS 16.38
73a8aa46-83d3-5888-ab03-5840dc847679 | note | Verifying Document - Datasheet
961934c0-cf61-51b3-932c-ee01c47b9c53 | note | Frequency - Prior to installation
613940a0-29de-5ae4-974b-364396066fd7 | note | Verification Activity: Activity - W
b5032080-b748-5b6b-bc66-3c9ba5e469c1 | note | Verification Activity: By - ENG
3fe0cc32-d99f-5f2b-93a8-620d509a2134 | section | Directional Drill HDPE Pipe Materials
cacdf83a-614c-5d32-9faf-6296e114d74f | checkpoint | PE Pipe
39679f4e-7dfb-5ad4-83c0-79822a31931d | note | Acceptance / Conformance Criteria - PE pipe is required to comply with AS/NZS 4130 and be PE100 or PE80B plain wall with an SDR as shown on the drawings, but no greater than SDR17.
eeb5a2b5-be4b-56bd-be7c-8005927d3fc3 | note | Standard / Specification - PS 16.28.3
96b82146-7575-5c00-bf0d-9f2c69325289 | note | Verifying Document - Datasheet
a80ce8bd-ae96-59f3-b2bd-4b24cba04ea9 | note | Frequency - Prior to use
c5f49967-4607-5da5-8e7b-feaf6e3d2dbc | note | Verification Activity: Activity - R
4e4db892-3a3e-5937-9345-142faf0292a8 | note | Verification Activity: By - SE
b67a6e68-66bb-5ba8-a67c-4616567f8c09 | checkpoint | PE Fittings
634c9606-4835-5a0b-a69b-6f9f1dfe22c0 | note | Acceptance / Conformance Criteria - PE fittings must be manufactured in accordance with AS/NZS 4129 and be the same class and pipe material as the main pipe.
1770274a-64f3-59de-a8c3-90008cea6eed | note | Standard / Specification - PS 16.28.3
ebd3eb94-b20a-55bb-b72e-4918ae4e8449 | note | Verifying Document - Datasheet
a0ca16f6-d150-5ff8-aa3b-191b608fbdcb | note | Frequency - Prior to use
88109833-f150-51c1-bd1a-edbcc227cebc | note | Verification Activity: Activity - R
dc436d68-e22b-53f3-98f2-1bdc6e0030a0 | note | Verification Activity: By - SE
ecda0acd-0701-53f1-81f5-5475240ba7a8 | checkpoint | Electrofusion couplers
793a8885-21af-599a-92ed-b44c6c5803ed | note | Acceptance / Conformance Criteria - Electrofusion couplers must comply with AS/NZS 4129 and be minimum PN16 pressure rating.
5ffbf523-d656-5e9a-8369-13ddbcdb7705 | note | Standard / Specification - PS 16.28.3
8078c729-d7b3-5fd7-9df6-2a8860bf50cb | note | Verifying Document - Datasheet
0fba24ce-623c-5bba-b97f-03a84df39b63 | note | Frequency - Prior to use
352ad1be-2f40-5890-bffd-d3bd7ecb7e16 | note | Verification Activity: Activity - R
5b166374-e50e-5226-ab38-40d8882f0686 | note | Verification Activity: By - SE
ea551cc2-b425-5632-b8a3-f967077b9943 | checkpoint | PE Fitting Flanges
8d5aa6e4-0c67-53a4-93fc-9010fea31bd8 | note | Acceptance / Conformance Criteria - Flanged connections between PE pipe and metal fittings (e.g. cast or ductile iron flanges on valves, spools, bends, etc) are to be made using PE stub flanges, full face gaskets (Tessnit or Klinger or equivalent approved by the Engineer), 316 grade stainless steel backing rings, and 316 grade stainless steel bolts and nuts.
56a154c9-fd05-54d1-818e-a1d075993948 | note | Standard / Specification - T-EES: 04311 - 2.3
af5faea2-2724-59ff-89f8-b1040d7bfc5f | note | Verifying Document - Datasheet
4cc65cde-57df-5d1f-a88a-5a9541fad12e | note | Frequency - Prior to use
5a7c39d1-dcca-5603-a91e-53ff6d548d25 | note | Verification Activity: Activity - R
7f4bcd0a-5fc6-543d-9b1c-7ebdc0403dd0 | note | Verification Activity: By - SE
568ab51e-65f4-5f2c-9670-530a2b6c0f53 | checkpoint | Denso Tape
add57388-47de-5b9a-844b-15309927f18b | note | Acceptance / Conformance Criteria - Denso Tape (or equivalent) shall be used on buried flanged fittings
d637cd1f-e2e1-5771-9bbf-2a50bb20f322 | note | Standard / Specification - T-EES: 04311 - 2.3
0aa968a3-e835-5495-a89f-53c9cc324927 | note | Verifying Document - Datasheet
9d263955-1453-565f-978c-f4ce8d0dc974 | note | Frequency - Prior to use
bde816ea-0bb6-56ce-8ba0-8a1997be82ca | note | Verification Activity: Activity - R
31030de9-7237-5559-985f-c24efe4a15fb | note | Verification Activity: By - SE
3ee3b540-2ac5-5d3f-8448-e43b6aafde1f | checkpoint | Grout
24f72ef2-56ec-55db-8f2b-f6032dd8b34f | note | Acceptance / Conformance Criteria - Grout must be 1.5 MPa flowable concrete. The grout must be compatible with the pipe material and must have a service life matching the new pipe.
db69ac4f-3da7-5fb7-be30-1f0a0cb731c8 | note | Standard / Specification - PS 16.28.6
dde3488d-8cd0-5d7f-8e52-552863881847 | note | Verifying Document - Datasheet
d93bd7f5-27af-58b1-ab0d-5c5ba6917ce2 | note | Frequency - Prior to use
f21b6b56-4a4e-54ee-97bd-88572b30b414 | note | Verification Activity: Activity - R
d9ebbc34-79bd-5ce9-89bd-628fe8b6080d | note | Verification Activity: By - SE
965464e8-55fe-5772-afee-903a732b4671 | checkpoint | Welder Qualifications
a491fcbf-48e7-5f1c-ae1b-6d20dadf1e0b | note | Acceptance / Conformance Criteria - Evidence of welder certification is to be presented to the Engineer prior to starting welding.
5a90b187-f5bb-510d-8416-f4bc6f0a3e9e | note | Standard / Specification - T-EES: 04311 - 3.2.2
5ff5ffb4-fba1-528e-be13-a72dde3b6514 | note | Verifying Document - Welding Qualifications
25d5be36-96de-5efe-9077-e744646d05c1 | note | Frequency - Prior to starting welding.
4d5cbf62-42c6-59c2-928b-12e87012d715 | note | Verification Activity: Activity - R
5a62c1f7-998d-51b7-9138-553dfd19d278 | note | Verification Activity: By - SE
ec84861e-1312-5143-ad18-ff48f2acdb97 | section | 5.02 Stormwater Drainage
c61b86a7-85ed-5c4f-8d2b-7e80d2bf9443 | checkpoint | 5.02.01 - Obsolete Stormwater Structures
c9519e89-e59b-55f8-a5cb-4f9e471197a9 | note | Acceptance / Conformance Criteria - Obsolete catchpits, manholes, kerb and channel shall be demolished, uplifted and removed to an approved tip site.
ff3b3ee8-560b-5802-af81-84a6076b81a5 | note | Standard / Specification - PS 14.2.1
c0128abd-f895-5363-a753-e0fc001349cb | note | Verifying Document - Site Record
c3f6c8c0-cd00-5942-9f91-cbaa9001bd7f | note | Frequency - Each Obsolete Structures
fdb6cd60-4f04-5cad-a867-053e7b6a401a | note | Verification Activity: Activity - R
67c12850-b533-5170-9b61-af097c299c53 | note | Verification Activity: By - SE
d8ecb190-bc10-5edb-ac53-42eb0dc3bfcf | checkpoint | 5.02.02 - Cutting Existing Pipes
26f8a382-e4dd-50c0-8a22-fe0764ad83db | note | Acceptance / Conformance Criteria - Where the catchpit will be replaced by a new drainage structure and/or constructed in a new location the existing stormwater pipe shall be neatly cut perpendicular to the line of the pipe to allow it to be easily extended.
339b08d0-cc37-5ee3-bcad-df841b25bf9a | note | Standard / Specification - PS 14.2.2
f1f54999-e08d-5685-b0ed-b8093f3d86ac | note | Verifying Document - Site Record
af5c30d3-8622-5702-91f8-5e0e728ede81 | note | Frequency - Each Occurrence
4b4161b7-a2bf-503b-a38f-d8c00a6e7c15 | note | Verification Activity: Activity - R
393d39bc-8c5e-52fa-93cd-331d9f1bcd57 | note | Verification Activity: By - SE
422da152-7833-5472-8ab0-c6da502f6651 | checkpoint | 5.02.03 - Debris Removal and Void Filling
8fc70ee0-1d4b-5999-b8d0-2bc836434fdd | note | Acceptance / Conformance Criteria - All debris shall be removed to waste. The resulting void shall be backfilled with well compacted approved fill material.
bf248110-4546-5026-a8ca-f06abc88db59 | note | Standard / Specification - PS 14.2.3
5f938e82-acb0-5a57-8567-2d3a61d90d61 | note | Verifying Document - Site Record
be64ba83-b27e-5b05-b663-8900515f280d | note | Frequency - Each Occurrence
a6993403-5123-5df6-ae11-6e0887b5dcea | note | Verification Activity: Activity - R
1e2b3203-fe02-596d-b4a1-2e27b7d73ce0 | note | Verification Activity: By - SE
0a1bcd19-6d32-50b7-b9b5-cf1f5ba2d77f | checkpoint | 5.02.04 - Obsolete culverts
13eb4b48-758a-5402-918a-bf7560c15d83 | note | Acceptance / Conformance Criteria - Obsolete culverts shall be removed or may be left in place subject to the agreement of the Engineer. Abandoned culverts shall be plugged with concrete at each end or if the culvert is within 1.0m of the surface it shall be completely filled with a cement grout.
24a1f1af-a5b7-5aba-a6f1-8c50f4dcf6fa | note | Standard / Specification - PS 14.2.4
c25afc76-e311-50c0-b8a6-c7a12aad1687 | note | Verifying Document - Site Record
33599ab8-0632-5e0c-9a11-eed000b87d5a | note | Frequency - Each Occurrence
565389f9-e737-54bf-bed0-3ac2aa8e810a | note | Verification Activity: Activity - HP
ee1f8647-8313-5f83-9d78-b31308962dca | note | Verification Activity: By - ENG
b6c6a2d0-8dbc-5054-95f0-291dca3b6462 | signoff | AUTHORITY HOLDPOINT
d86dec03-b7f0-5833-a091-b52d1e5c378f | section | 7.01 Services
210f7528-7a9d-561d-832c-2d9cd77272d2 | checkpoint | 7.01.01 - Existing Services
9c0bbed2-f1f3-5109-990f-1abc48d3ecdb | note | Acceptance / Conformance Criteria - The Contractor is required to identify all known utility service crossings or encroachment, within 5m horizontally, of the proposed drainage alignments.
93ee85ee-6aa3-5a1b-b5e3-162d59068373 | note | Standard / Specification - PS 16.5.4
8647a48e-5ae2-50bb-99ff-54bd428fb23e | note | Verifying Document - Survey Records
d49ff898-5f37-5e3e-b817-5596591f4efc | note | Frequency - Prior to excavation
97923632-fca8-5db9-bcb1-1274ac77bfe1 | note | Verification Activity: Activity - R
752e8085-0229-52fa-a2c9-086bc89edc41 | note | Verification Activity: By - SE
b81866a1-713f-5217-a849-4f9b743945d5 | checkpoint | Service Support
e72525dc-79a7-5a60-a2aa-086f4f3e5903 | note | Acceptance / Conformance Criteria - The Contractor shall support all existing services affected by the works whether these services cross-or are located alongside the excavation.
19986c06-5d8d-5f00-828f-620d45b4b35a | note | Standard / Specification - PS 16.5.4
709a3cf6-1b86-5882-b73b-a62b2a66992f | note | Verifying Document - Site Records
1092e54b-981c-572a-ac65-f20681897409 | note | Frequency - Each Occurrence
c22480a8-ea53-5dcb-b876-360d84c63dec | note | Verification Activity: Activity - R
978f84f3-3ede-5a21-98b7-4276adfd37f6 | note | Verification Activity: By - SE
af6a7901-7702-51c8-ab45-cc4fd749f93c | checkpoint | Utility Operators Approval
90e88bb6-4662-5448-bfb7-2f3e26ad746e | note | Acceptance / Conformance Criteria - Prior to commencing with any construction, the Contractor shall Obtain written approval from the relevant Utility Operators for any construction activities within the vicinity of their service(s).
3beff479-50a8-5e9e-8929-fe8bd5043c8e | note | Standard / Specification - PS 16.5.4
280d715f-6095-54d6-9b11-921bcd69e9fb | note | Verifying Document - Written Approval
ca35d788-0d26-5fef-9190-a26a51723728 | note | Frequency - Prior to commencing with any construction
28ad1197-9641-531b-bc1a-2c6f73bc59b8 | note | Verification Activity: Activity - HP
43be137d-5720-50f5-b14a-a7a7f02ab622 | note | Verification Activity: By - ENG
fe7e76d7-8b6e-50c7-8517-2c37ab991ec2 | signoff | AUTHORITY HOLDPOINT
2340960a-f3a6-5805-9da4-8316b1795e7a | checkpoint | Utility Operators Requirements
39c7de44-ceaa-56f2-b4ef-c6d3005150a6 | note | Acceptance / Conformance Criteria - Prior to commencing with any construction, the Contractor shall Undertake the construction activities within the vicinity of the service in compliance with the with the relevant Utility Operator’s requirements.
88fab9e3-fdef-5960-9e7c-1bac1a35a847 | note | Standard / Specification - PS 16.5.4
f268193e-13cc-5386-92c1-b447be703f84 | note | Verifying Document - Site Records
f0b375ff-4ee3-5291-aead-4b9f39cd2b96 | note | Frequency - Prior to commencing with any construction
0719f026-30ef-5ecc-812b-6d52ada67a5b | note | Verification Activity: Activity - HP
1165af04-194f-5033-bd71-046cc6da6b38 | note | Verification Activity: By - ENG
5c055e4e-3a73-56db-a1ec-01c96b1547bd | signoff | AUTHORITY HOLDPOINT
ba4d0a34-4991-50f1-9410-46f75947312c | checkpoint | Protection of Pipelines / Structures During Construction
8b256576-dd83-5209-836c-51cdb41ef9d4 | note | Acceptance / Conformance Criteria - Where construction plant is required to be operated over pipelines Table B1 of AS/NZS 3725:2007 shall apply in determination of the minimum depth of fill (cover) required. A temporary embankment, extending not less than 15m on both sides of the pipe/culvert, shall be used to provide the necessary cover.
4f2b5d60-6a5f-559c-866d-0dc8a491e8e8 | note | Standard / Specification - PS 16.5.5
96cb4222-a5e4-5683-92d6-52e359a5cad0 | note | Verifying Document - Site Records
7f7cca92-2e3f-5b92-b9cd-83e8ebba3cb5 | note | Frequency - Each Occurrence
261f309e-aafb-54d9-be19-19097cd884bf | note | Verification Activity: Activity - R
998ee5da-6adf-55f2-bbc7-65c58571e261 | note | Verification Activity: By - SE
ac9cccb8-a4cb-5e1f-bbfb-2661d2b8a06f | section | 4.02 Stormwater General
73bd1a9d-3933-5c6d-a96c-ac286417bbbc | checkpoint | Setout
88e423dc-ecd2-571b-b44f-a9265e122b4c | note | Acceptance / Conformance Criteria - Prior to the commencement of any drainage works for a particular drainage line, the Contractor shall set out the line, level, and position of the proposed drainage line, including inlet and outlet positions and levels, and present it to the Engineer for their consideration. The Contractor shall provide at least 48 hours’ notice to the Engineer ahead of set-out and allow 48 hours for the Engineer to respond prior to commencing work.
88c8598f-748a-59d5-8438-6f88924dd2bf | note | Standard / Specification - PS 16.6.1
91cc06a2-296e-5830-af4a-5a1e49991444 | note | Verifying Document - Survey Records
f84fd96a-7286-5965-b1e2-3fb358b668b8 | note | Frequency - Prior to the commencement
be38a529-8ba5-5e68-bb6c-df557f03c974 | note | Verification Activity: Activity - HP
3f1cfd57-6796-5552-8717-3324b0510bd5 | note | Verification Activity: By - ENG
0494c03b-463e-5b26-8ef3-1e1af4ca4793 | signoff | AUTHORITY HOLDPOINT
a0ec803a-1845-5391-8cb4-1f796aea4d68 | checkpoint | Dealing with Water
9c9c6cf7-46ed-50f4-b45e-031073dad72b | note | Acceptance / Conformance Criteria - The Contractor shall maintain all trench inverts free from flowing or accumulated water. Water arising from, or draining into, the trench shall be drained or pumped. Any sumps required shall be refilled to formation level as directed by the Engineer.
74adf568-f9a8-5ec1-835d-6ed0ecac4ed6 | note | Standard / Specification - PS 16.7.1
0b1e03cb-4a05-5721-b1ad-3f2678e9f09a | note | Verifying Document - Site Records
0cc4b814-e149-59fe-b60f-66ec1e2b61d8 | note | Frequency - During Works
49c1c7f5-1305-5f6b-84e7-18ae1f9918a1 | note | Verification Activity: Activity - S
1635c430-5590-5500-9a71-cbecd972fa5a | note | Verification Activity: By - SE
8140ee38-799d-5b7b-a7f3-6a533e5bb08b | section | 4.02 Pipe Installation and Backfill
7ee02f03-4b52-553d-8de6-2a113bb4d8b2 | checkpoint | Open Trenches
85a54333-d011-5d05-9997-e8b5b8d392de | note | Acceptance / Conformance Criteria - All open trench excavations for pipelines shall be to a minimum depth of 100mm below the pipe external walls. Where excavating in natural ground or existing carriageways, no more than 100 metres of trench (per drain laying operation) shall remain open at any one time.
3c9ebbf2-2eef-55d0-89c9-2e8db371b4db | note | Standard / Specification - PS 16.9.2.10
c95b6a35-f7a6-594f-9d18-3b123d726162 | note | Verifying Document - Site Records
20a7c7df-0d35-58b7-aa70-7bc5e9e20426 | note | Frequency - During Works
2da2690a-c01c-5275-9d7a-2aa61ff8fb80 | note | Verification Activity: Activity - S
a606b4c1-1584-5085-988c-5a18f53ec8ce | note | Verification Activity: By - SE
050b7638-8546-5c40-98ca-2c370f9bbaf3 | checkpoint | Saw Cutting
1886856a-8a30-511f-a145-1faf77098a8c | note | Acceptance / Conformance Criteria - Where trenching through roads, prior to excavation, the surface shall be saw-cut a minimum of 100mm beyond the trench wall and parallel to the proposed alignment.
09f1c4d3-689e-5daf-b707-ebd9fdfadbfd | note | Standard / Specification - PS 16.9.2.10
8c1fd2ad-d29c-56ba-948d-5b9c63aa5fd6 | note | Verifying Document - Site Records
83686973-886d-5a2b-9808-1da53682eeac | note | Frequency - During Works
6b054d1e-2d91-5f51-9249-ac9645624f8e | note | Verification Activity: Activity - S
26915d98-c3de-5fe1-8401-dcd16563de12 | note | Verification Activity: By - SE
09dd1447-1272-5fee-9257-6aae4dfdd652 | checkpoint | Stability check
7eb87aab-75cb-5d60-b64c-be7b1d5af58a | note | Acceptance / Conformance Criteria - Where trenching is near new or existing structures (within 5m horizontally, or where the trench invert is below a plane projected downwards at 1(V) in 2(H) from the base of the structure), a stability check shall be undertaken to ensure undermining of the structure is avoided. The Contractor shall undertake a stability check in these situations.
548116c5-3651-54f3-9ed8-41da6761885e | note | Standard / Specification - PS 16.9.2.10
69a1014d-2430-564f-bf84-dd5a1bc28bd3 | note | Verifying Document - Site Records
7a56d487-5178-534d-a161-eda8f1c042e1 | note | Frequency - Each Occurrence
f96d6a24-5d3f-5a7f-91da-5efeab1f4ff9 | note | Verification Activity: Activity - S
d5e23f31-00ac-5050-b9ab-9f6ff1e7adb3 | note | Verification Activity: By - SE
addd9cc3-22da-5bc3-a8ff-2123a26d4d83 | checkpoint | Trench Width
071ab73e-cbc2-5c11-99da-e46fc21393f7 | note | Acceptance / Conformance Criteria - The minimum trench widths are as indicated on Drawing WD-0131 but not less than the external pipe diameter plus 600mm and not more than the external pipe diameter plus 1200mm.
95852d97-fe66-5784-8e13-c3750b77e5d8 | note | Standard / Specification - PS 16.9.2.10
960ec6e4-2f94-55b8-9aa1-21e0485e959e | note | Verifying Document - Site Records
b9463573-c4eb-5034-8340-4ec8dcc46561 | note | Frequency - Each Pipe
160b50a7-6ddd-5d74-9814-23ace3815cf8 | note | Verification Activity: Activity - S
9bd015b6-771e-5edd-8d1c-d6ed081ee5ca | note | Verification Activity: By - SE
54f1d1ba-7b14-565d-8bd5-f5dba161d268 | checkpoint | Unsuitable Material
55f7c25b-394f-5258-91b5-d109a17e15a7 | note | Acceptance / Conformance Criteria - All material deemed to be unsuitable shall be removed to a depth of 600mm or a greater depth as specified by the Engineer, until suitable material is reached.
4af1ebef-16c6-57d1-8390-52950017ad8c | note | Standard / Specification - PS 16.9.2.10
4bf01bcd-ea9b-5d5a-888a-8f1093564c4a | note | Verifying Document - Site Records
d8cdd0c4-0f02-5fcc-bf66-76b613abdfe3 | note | Frequency - Each Occurrence
4a988a2e-cc7d-5ebf-a861-974161fa72ba | note | Verification Activity: Activity - S
39f2027c-ec3f-53f3-80eb-e2f4c0bcb4d8 | note | Verification Activity: By - SE
60ba2855-6337-5f43-baee-a20b6a38cce0 | checkpoint | Trench invert subgrade inspection
c327e8b9-ace3-55e3-b86a-67bba06be72f | note | Acceptance / Conformance Criteria - The Engineer shall have the opportunity to complete a Visual Inspection to NZTA F/3:2010 on the trench subgrade each day on each pipeline during installation.
ed5ce385-2df0-5928-bde2-b5806f77441a | note | Standard / Specification - Suitability
a65f734b-66ed-551c-a1d1-f899ce9241cd | note | Verifying Document - Engineers Record
a01177dd-5077-515e-b561-f48f77e1d6bc | note | Frequency - Daily
03226ffd-8903-52c6-bf3b-133443c3a403 | note | Verification Activity: Activity - WP
6857ef3d-a8db-5466-bfd2-41bf7f5fbb6c | note | Verification Activity: By - ENG
2f9f725a-99b7-5507-8b86-0302c8567494 | checkpoint | Trench invert subgrade testing
49af6839-4608-5742-a54e-2fd2da1a6e73 | note | Acceptance / Conformance Criteria - The subgrade shall be tested for CBR>5 by Scala or shear vane. This test shall be undertaken at the design subgrade level and at a depth of 300mm below the design subgrade level.
202eb984-357c-5d06-a0b5-4e6a6e33987c | note | Standard / Specification - PS 16.9.1.3, PS 16.32.3
ba97a3e0-b45e-5d3c-8ea1-cd78f6d93c21 | note | Verifying Document - Scala or Shear Vane Report
f67f9a9e-3036-51a2-98f7-6fcdbdab3cff | note | Frequency - 1 per 15m trench length Minimum of 2 tests between pits/manholes
9787b1b7-adbc-5062-a870-523637491ebb | note | Verification Activity: Activity - I
062f3ae9-3bb7-53de-8287-72d58173782e | note | Verification Activity: By - SE
c83967ab-fb9b-5da3-a728-f0b3db5df37e | checkpoint | Subgrade Undercut and Replacement
54ab8068-6690-5fba-bf09-486a6fc09b40 | note | Acceptance / Conformance Criteria - The insitu trench base shall be tested and if CBR is less than 5, it shall be undercut and backfilled with AP65 compacted to compacted to lD=60% or correlated CIV.
b582ff75-33ad-5e22-986d-3988e087ef9e | note | Standard / Specification - PS 16.9.1.3
4abf8f1b-93b3-5eb7-9d42-9e2e9e350942 | note | Verifying Document - Site Records / NDM / Clegg Report
7b008d73-1410-54cf-b51c-daaed3cf0289 | note | Frequency - Each Occurrence
d1d18b44-596a-5e03-b501-918b7aaeaf82 | note | Verification Activity: Activity - S
c6b30dfa-8017-5145-bd11-fafdda0a8589 | note | Verification Activity: By - SE
ede858dd-9765-5d83-a5c5-09014bf14c02 | checkpoint | Pipe bedding and haunch zone inspection
d437c547-b309-5049-b7f7-a49fb2269aa5 | note | Acceptance / Conformance Criteria - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe bedding and haunch zone
8db3be70-34d4-55fb-88be-1f717609e454 | note | Standard / Specification - PS 16.32.3
bb437696-fc12-5174-a4a0-5ef025a73034 | note | Verifying Document - Engineers Record
e7898fe4-c146-5312-ace7-cbf361c932f1 | note | Frequency - 1 per trench length (Between Chambers)
cdf6333c-79c9-5205-b5fb-616a9114e421 | note | Verification Activity: Activity - HP
026bc135-b2e8-575d-80d6-1baa1f78ae7c | note | Verification Activity: By - ENG
0577727e-9c3b-5edc-9922-97b0780aff8f | signoff | AUTHORITY HOLDPOINT
098e00a4-6018-52ba-8e1e-a43f6d086206 | checkpoint | Pipe bedding and haunch zone Density Testing
b01dabb4-4ae8-5b44-b89d-0807a47812b9 | note | Acceptance / Conformance Criteria - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes. The pipe bedding and haunching zone shall be compacted to lD=60% or correlated CIV.
0a32f85c-231f-5932-9063-451368eb2bc8 | note | Standard / Specification - PS 16.32.3, PS 16.6
8dd086b7-6a4b-50ac-87e6-b98ae15bf6bb | note | Verifying Document - NDM / Clegg Report
8ff25fd7-31bc-5761-bc43-2deefbc731bb | note | Frequency - 1 per 15m trench length Minimum of 2 tests between pits/manholes
a74d5091-e771-540c-a1d0-8f9edf34220d | note | Verification Activity: Activity - I
71e65daa-6bef-5df5-8bb6-b5e0c3a7f9a8 | note | Verification Activity: By - SE
4673f583-ad7a-54fd-8ac0-030bec81871a | checkpoint | Backfilling of pipes and culverts with embankment fill - QA Acceptance
e0ac6397-9880-5d99-a382-40ae9e2a9cfa | note | Acceptance / Conformance Criteria - Prior to Backfilling of pipes and culverts with embankment fill the test results for bedding, haunching, side zone, and overlay zone material properties, grading curves and compaction tests are accepted by the Engineer.
7e325fef-a9c5-5355-a1c4-a2b5af31a216 | note | Standard / Specification - PS 16.37
088c4ae3-fb8c-5415-adf4-e9d5fe0b580b | note | Verifying Document - Engineers Acceptance
17f3e4b5-4fd5-5aa1-8433-95c5b26aa661 | note | Frequency - Prior to Backfilling of pipes and culverts with embankment fill
0aad2b78-55b6-5ed0-8179-fb75d8e36e80 | note | Verification Activity: Activity - HP
40eb933d-5887-5274-bd9c-0fd6f07e5246 | note | Verification Activity: By - ENG
de3d46c2-9972-53ff-b01a-021f386ffc9a | signoff | AUTHORITY HOLDPOINT
bfadab6c-08ba-5ab0-b31a-3461af4ee5e1 | checkpoint | Pipe laying in Embankments
cd873f3c-6d13-5a0d-b000-ba0fd9275857 | note | Acceptance / Conformance Criteria - The Contractor shall have each pipe checked for level as it is laid, by a competent technician using an Engineer’s level, pipe laser or other approved equipment. Pipes shall be laid on uniform gradients between successive designated manholes at the gradients specified on the Drawings.
7ef22651-6631-51b7-9d7b-ef862088a9c7 | note | Standard / Specification - PS 16.9.2.8
22009b50-fa3f-5cd2-be51-ed4110a46db7 | note | Verifying Document - Survey Records
e80e4897-2741-56f3-b8bc-d6fc5484666b | note | Frequency - Each Pipe
5fad18f3-10d7-579a-8b59-78df1595d762 | note | Verification Activity: Activity - I
cca0b73a-b456-5928-972d-2f65b4d13d4b | note | Verification Activity: By - SV
3bc2d285-1969-556e-a4ab-d324ab0e99a4 | checkpoint | Pipe Connections
f21907e1-5fa0-588d-b21f-e6c1da360797 | note | Acceptance / Conformance Criteria - A flexible joint shall be provided to the outside face of any structure (manholes, catchpits, catchpit manholes and headwalls) into which a pipe is built. The length of the next pipe (rocker pipe) join away from the structure shall be no more than 600mm for all concrete stormwater pipes and shall be constructed in accordance with Typical Details on the drawings.
5626af0e-bbe1-5573-aea6-9b7c07ac9e12 | note | Standard / Specification - PS 16.9.2.15
16464398-5a84-530f-8707-4cdbef83e690 | note | Verifying Document - Site Records
6f64234a-9447-5f75-9bae-e400df78d938 | note | Frequency - Each Structure
7a5dc16b-8d66-57ee-a784-22b8fe2fe5a2 | note | Verification Activity: Activity - I
256de5e8-fe4f-5f02-87fc-700f1471f9a8 | note | Verification Activity: By - SE
a66e2a16-b83b-5c59-8522-1ab16515eb12 | checkpoint | Cutting of Concrete Pipes
333c5fe5-8612-5235-a4cb-0967b8c1c36b | note | Acceptance / Conformance Criteria - Where it is necessary to cut a concrete pipe the pipe supplier should be informed of such requirement specifically where the dimensional tolerance for the pipe is deemed critical.
871669e7-3eac-57a7-92d7-9578d237a575 | note | Standard / Specification - PS 16.9.2.16
822ee59e-8b86-5e61-acd2-21b088dc0ede | note | Verifying Document - Supplier Approval
ba7ef296-5a1e-5da9-a240-62621473ecf6 | note | Frequency - Each Occurrence
cc8e92bb-d03d-5817-9ec4-04015ecde2f6 | note | Verification Activity: Activity - S
37a26aab-b4d4-5b84-9717-40162fb92be3 | note | Verification Activity: By - SE
2cc5b170-ba84-5d4b-a764-a1ea031fd2ee | checkpoint | Cut Pipe Sealing
d35d5cdd-5ac4-55e6-ba5e-6a4a1c1fc97b | note | Acceptance / Conformance Criteria - All cut surfaces, not encased within benching or other in-situ concrete, shall be coated with an epoxy resin mortar in accordance with the manufacturer/supplier recommendations, leaving no exposed reinforcement.
11db9469-5566-55f0-b60a-22fa0b5c1dec | note | Standard / Specification - PS 16.9.2.16
0c55b779-8e3e-5f0d-97a4-1f74278bc8be | note | Verifying Document - Site Records
1fe91ee6-2bf4-533a-bf5a-f1755cac4210 | note | Frequency - Each Occurrence
b22a77a8-aa00-5fed-83d5-b97692e04f75 | note | Verification Activity: Activity - S
07081433-530d-5ac8-99d3-f123e4bba6ed | note | Verification Activity: By - SE
7fc83344-d695-5fe9-9072-1ca6dc544f7d | checkpoint | Side zones Density Testing
4e741ad3-d978-53fd-8e44-126f6654bdb5 | note | Acceptance / Conformance Criteria - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes. The Side zones shall be compacted to lD=60% or correlated CIV.
2b82f52d-905f-55af-96a1-57339655fc0f | note | Standard / Specification - PS 16.32.3, PS 16.6
e9def231-79f7-56a2-a30b-58ed834be225 | note | Verifying Document - NDM / Clegg Report
9fde4f14-76fc-5a72-a807-f65c10ab16f9 | note | Frequency - 1 per backfill layer per 15m trench length. Minimum of 2 tests backfill layer per trench between pits/manholes
e4847710-50ae-5ec7-aefb-253fa5c88e59 | note | Verification Activity: Activity - I
72f85049-46ab-5dbe-aa6d-6c4ebac9f055 | note | Verification Activity: By - SE
2fca84de-0eee-5697-9759-48639b3c5d48 | checkpoint | Compaction above Pipe
2f1e7167-bec3-577a-b65a-80211ce3728e | note | Acceptance / Conformance Criteria - Only hand operated compaction tools shall be used until the backfill has achieved a depth of 300mm above the crown of the pipe.
82ae6884-0127-5123-99c4-72bdfe1142e2 | note | Standard / Specification - PS 16.32
123c33fa-bed2-5490-8d1a-a0e8b36016ce | note | Verifying Document - Site Records
0ebd2b0c-aec7-5992-8334-4a2a743144f5 | note | Frequency - During Works
c6ef089a-108b-5ce9-b210-3f4f71c94bcf | note | Verification Activity: Activity - S
e4e52f2f-4401-52f5-97ad-5a9ede32bc42 | note | Verification Activity: By - SE
bb9f33f0-36df-53e0-ad46-932d7a11e8b3 | checkpoint | Pipe overlay zone inspection
4003d7cf-3c05-52f2-8f33-5aa62a445791 | note | Acceptance / Conformance Criteria - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe overlay zone
303a798e-55dc-50ed-a5be-a37675ea7cca | note | Standard / Specification - PS 16.32.3
70298fe7-c403-5864-be0c-e77e8c2ac2aa | note | Verifying Document - Engineers Record
c61e204c-1dbd-550f-95ff-a89b31bab837 | note | Frequency - 1 per trench length (Between Chambers)
8518ba54-f494-5886-b0ea-eaae397f63bf | note | Verification Activity: Activity - HP
0922f834-d1b9-57d3-81fd-fd01ef158c42 | note | Verification Activity: By - ENG
dc4ad34c-55ed-5e5c-9c37-53afc29eabb9 | signoff | AUTHORITY HOLDPOINT
9e63ee02-c753-5552-8128-bed10766f3da | checkpoint | Pipe overlay zone Density Testing
9996120a-c901-5d1c-8e54-457aa8cdd915 | note | Acceptance / Conformance Criteria - Backfill material shall be built up in layers not exceeding 200mm. The Pipe overlay zone shall be compacted to lD=60% or correlated CIV.
00888154-43a2-5472-8668-5ea3dd27ad4a | note | Standard / Specification - PS 16.32.3, PS 16.6
fe05e8b8-34ee-55ce-a753-a56b534a27c5 | note | Verifying Document - NDM / Clegg Report
f5a5fff8-59a8-584d-af45-d184027c0045 | note | Frequency - 1 per 15m trench length Minimum of 2 tests between pits/manholes
712eaf73-b76f-592b-8e3f-59eb686dc2f5 | note | Verification Activity: Activity - I
5d4325d2-4efc-574a-9483-c00d02ee27be | note | Verification Activity: By - SE
4083d597-86b8-5c45-b66f-4e8b311c0f28 | checkpoint | Pipe invert levels/lid levels at all drainage structures
68501429-8653-5e2a-8a66-25eeadbe6c0b | note | Acceptance / Conformance Criteria - Pipes shall be installed within 20mm of stated invert level (vertical tolerance) and within 50mm or 5% of the pipe diameter of proposed horizontal alignment (whichever is greater). Catchpits and catchpit manholes shall be located to align with proposed kerb and channel (or dish channel) and finished to be flush with the finished road surface unless otherwise specified on the Drawings.
d0ec968f-4a93-53de-925f-37936892da8e | note | Standard / Specification - PS 16.34.2
ab46316f-2b5d-51be-88fb-f0a3b97e66cf | note | Verifying Document - Survey Records
7931d7a3-1893-5da6-a2a8-5ee865aad110 | note | Frequency - At the completion of each stormwater pipeline
27b98828-4e40-5604-be5d-cb46dafc9757 | note | Verification Activity: Activity - I
3705f2fe-4a17-521f-94f9-8af2fe54875a | note | Verification Activity: By - SV
cd8b1e1c-939d-53d8-a80d-27f2d234284b | section | 4.02 Subsoil Drain
058f1f15-c3ce-520b-872d-a12a41adc55e | checkpoint | Trench Grade
623c6f24-0aad-5f1d-aee7-736d1f58cb49 | note | Acceptance / Conformance Criteria - Unless otherwise specified trenches shall have: a minimum gradient of not less than 1 in 100; vertical sides from the trench bottom to a minimum of 300 mm above the top of the pipe; and a minimum depth that will ensure that, when the pipes are laid, the invert level shall be not less than one metre below finished subgrade level.
7054c937-efc5-5f08-8ee8-6f1387dc9f7d | note | Standard / Specification - NZTA F/5 PS 16.11.2
566db88a-9865-5293-876e-988afba55f37 | note | Verifying Document - Note only
92600ecf-3864-516f-b11f-0175807adbdf | note | Frequency - Each Pipe
c6c33483-7c67-5c8c-988c-4845c82ea0a0 | checkpoint | Bedding and Installation of Drainage Pipe
8ff5a013-d6f3-57ab-9e97-a6068bd24682 | note | Acceptance / Conformance Criteria - Prior to laying the drain pipes, the Constructor shall ensure that pipes do not become contaminated with clay or soil and that pipe slots are not blocked. Any such blockages shall be removed before pipes are laid.
d2368cbc-f93b-5b72-8371-0e0cbb80f2af | note | Standard / Specification - PS 16.11.3
453fabdc-8a85-5eb7-b118-32fab2eda204 | note | Verifying Document - Site Records
7a7f62ef-596c-5cda-91b2-bb3cb0040458 | note | Frequency - Each Pipe
fcfd341f-02ec-5b7d-b3c6-1564a705d376 | note | Verification Activity: Activity - S
2b5bf501-994b-5ca6-b89f-ce3a316f0ca9 | note | Verification Activity: By - SE
3583d04c-1195-565d-824e-0edfc327b937 | checkpoint | Bedding Placement
84f2203f-8e81-53ab-9ac2-363d1c867f09 | note | Acceptance / Conformance Criteria - The filter material shall be placed, and the drain pipe installed such that the pipe is at a uniform grade and is underlain by a minimum of 50 mm and overlaid by a minimum of 150mm of filter material which completely surrounds the drain pipe. The filter material shall be placed in a manner to achieve a generally uniform dense state.
a439c520-6123-53b9-8fdc-3ef76c18a62b | note | Standard / Specification - PS 16.11.3
e4371f75-5689-510f-b5f8-914a9d666da2 | note | Verifying Document - Site Records
6e588e44-39e7-527a-bffe-62f1d6106948 | note | Frequency - Each Pipe
d6d405b5-2513-5b6b-8a18-594c44923e5a | note | Verification Activity: Activity - S
93d04dd4-9e82-559b-bdb4-f62df1ff7a48 | note | Verification Activity: By - SE
f73366fd-bea9-5749-9c6d-d4bf16c3eb7b | checkpoint | Pipe Orientation
3b86f474-5869-5f0d-9ec7-2f54c01d3a15 | note | Acceptance / Conformance Criteria - Pipes should generally be laid so that the perforations are oriented as shown in accordance with the manufacturer’s recommendations for corrugated HDPE pipes.
ceccd876-07e4-5b58-bd25-2234261a3868 | note | Standard / Specification - PS 16.11.3
6972b955-28f4-53a0-afbc-1c216d13c188 | note | Verifying Document - Site Records
1b52b7f6-1c8a-51a2-b60c-81e22d9f34af | note | Frequency - Each Pipe
907a6846-9597-575e-9291-cb7b81dacbf9 | note | Verification Activity: Activity - S
3c874e98-6417-58c6-8a09-c65c9a8e4ca7 | note | Verification Activity: By - SE
7f7c97a1-280b-5baa-a0b4-2bf7a1cd5151 | checkpoint | Pipe Jointing
155e4274-bf07-5026-8ae4-ca6eea81fdf3 | note | Acceptance / Conformance Criteria - The drain pipe lengths shall be joined following the manufacturer’s instructions or as approved by the Engineer, with the pipe jointing carried out to leave a smooth flush internal surface. The top ends of the pipes shall be capped.
e9ead1bf-af81-5235-baf1-53331343103c | note | Standard / Specification - PS 16.11.3
2344b679-db77-58bf-809b-8e456e9730e0 | note | Verifying Document - Site Records
64652a70-8d66-506d-bac2-7945756ab194 | note | Frequency - Each Joint
667ad5eb-da55-5469-b283-e84ffb3149d6 | note | Verification Activity: Activity - S
61615215-bf93-5161-bf79-083192bc0b85 | note | Verification Activity: By - SE
99cbd9be-a0b3-50ef-969a-d7075dec3b62 | checkpoint | Pipe Installation Inspection
6f4ca1a8-2e9c-53ed-ae17-1eeefc57302c | note | Acceptance / Conformance Criteria - The drain pipe installation shall be inspected and approved by the Engineer before placing filter material and backfill.
34004ed8-2104-527a-a0d5-0f5e29c2580b | note | Standard / Specification - PS 16.11.3
be987d2a-0b1d-5455-a10f-7c250bd9dfc8 | note | Verifying Document - Engineers Acceptance
387c64ff-408d-558d-bb63-8e7feb38d026 | note | Frequency - Prior to backfilling
9902589a-9672-5938-8440-b3d5c5d709ac | note | Verification Activity: Activity - HP
791a850c-3cb4-531b-a39d-b747df1c426b | note | Verification Activity: By - ENG
20c643a8-92f0-5638-aa37-95627d7e163f | signoff | AUTHORITY HOLDPOINT
55f5e26a-05c9-5c66-8fff-4e298d2f285b | checkpoint | Lose Debris Removal
ea1e3447-dc89-5495-b430-3014e1b97f48 | note | Acceptance / Conformance Criteria - Prior to placing filter material and backfill, the base and sides of the trench shall be cleaned of loose debris so far as is practical.
336743bd-b0da-5578-97f6-82ad36934942 | note | Standard / Specification - PS 16.11.3
51d00809-1b68-5912-8f12-14168910e9ea | note | Verifying Document - Site Records
db7c6b99-92ce-56cf-a73e-b20f01dc2eaa | note | Frequency - Prior to backfilling
82d106bc-ab12-545b-a74e-6c9cf1b470c6 | note | Verification Activity: Activity - S
31fa4ccf-3575-5192-902d-461eef69ab81 | note | Verification Activity: By - SE
b4d57f5c-5f92-5817-b9e2-6ca40984f3bf | checkpoint | Subsoil Backfilling
d26231de-6274-53f2-bd78-5833ca8b030a | note | Acceptance / Conformance Criteria - The backfill shall be filter sand as detailed in clause 2.2 of this specification. The backfill material shall be placed in layers not exceeding 150 mm loose depth and shall be positively compacted around the sides of the pipe to provide support of not less than that of the adjacent material
c6915a51-958c-5ba4-a7f6-5b3163c0c718 | note | Standard / Specification - NZTA F/5 PS 16.11.2
aea027fe-40c0-5b75-92d7-1f9dd51e4644 | note | Verifying Document - Site Records
bf8af501-647a-5d28-ae3d-88c74a57109e | note | Frequency - Each Pipe
e22d997d-6f1e-5224-8492-9706f3a14f49 | note | Verification Activity: Activity - S
910d06e1-ccf9-5f86-9b97-b3e3c41ad595 | note | Verification Activity: By - SE
0c48cb3a-7790-5b0a-ab2a-f416bf860062 | checkpoint | Overlaying
317ff592-b972-51f4-81d4-15b38abb08ee | note | Acceptance / Conformance Criteria - The completed drains shall be backfilled with an overlying capping layer to prevent the ingress of surface water.
58e7cbf2-47a1-5a69-8b86-6dc8d9012d7f | note | Standard / Specification - PS 16.11.4
7afcdbd8-7194-5247-a828-5b3022c91e38 | note | Verifying Document - Site Records
f3236a2b-a7a2-5637-a89b-86f98ea23f81 | note | Frequency - On Completed Drains
6f43c493-8111-53ec-b147-09ecca167033 | note | Verification Activity: Activity - S
16c190ce-afd0-5a60-bdc1-9c53d8780cbe | note | Verification Activity: By - SE
ca5fc354-a9de-5db9-ab52-4704930f1b5d | section | 4.02 Stormwater Structures General
04fd4090-ed4e-5028-a1f7-55d7ccf3d6b0 | checkpoint | Stormwater Structures Subgrade
758a6232-7e02-567a-b3ac-069f876d2b26 | note | Acceptance / Conformance Criteria - A hand Auger Scala / Shear Vane up to 4m deep shall be completed in the base of the excavation and the results submitted to the Engineer. The subgrade shall be CBR>5.
9bbcc3ab-c449-5cb3-a3c3-be7dd3625936 | note | Standard / Specification - PS 16.32.3
b65ba87d-7432-5b73-9ea7-20ecba7ab3e4 | note | Verifying Document - Scala / Shear Vane Results
afd2c346-01d6-5fcc-843a-7be1c9cca032 | note | Frequency - 1 per structure
2ec1b89a-6e78-530f-96d0-4c18da416824 | note | Verification Activity: Activity - I
4fb2630d-dc5b-525d-b529-7f0a8644d61e | note | Verification Activity: By - SE
e133756c-cbbd-586f-865d-da800d003e83 | checkpoint | Stormwater Structures Bedding material
ae7e88fa-e726-5b6f-b3be-03a363bdd805 | note | Acceptance / Conformance Criteria - Stormwater Structures Bedding granular material shall be compacted to MDD of 95%.
6d2511d9-8a9f-5694-b322-a793db61c3c2 | note | Standard / Specification - PS 16.32.3
c6f7d5cd-c35f-5ccf-8d65-dca94d14abea | note | Verifying Document - NDM Results
db2b36be-883d-50b1-a807-9726099f2c2f | note | Frequency - 1 per structure
696f0e93-f8f2-5baf-9cf0-1f354bccd57c | note | Verification Activity: Activity - I
caf69c92-7c4f-5670-8a9b-8d419c5852d8 | note | Verification Activity: By - SE
85ef8f43-5fc5-5a34-bec8-eabeed209925 | checkpoint | Stormwater Structures Backfill
5caad188-f93e-5ff6-9199-85643ff2bfe0 | note | Acceptance / Conformance Criteria - Stormwater Structures Backfill granular material shall be compacted to MDD of 95%.
3e67bb80-810b-5cc7-a5fb-7bc9501fbacd | note | Standard / Specification - PS 16.32.3
74db1892-a85b-56f9-bbbf-7e7e44801eba | note | Verifying Document - NDM Results
4e942db4-a8a5-5b1e-bc55-37eb33f29bdb | note | Frequency - 1 per backfill layer per structure
a4a298d9-ecdd-54dd-998f-0ab91937bb40 | note | Verification Activity: Activity - I
10771e04-4ab8-5638-a861-63ccc1d6a95a | note | Verification Activity: By - SE
b5bdd5cc-584c-50e8-bc87-604cffae448f | checkpoint | Subgrade Clay
ed9d3bec-fd9a-5e25-8d00-191b20131c0e | note | Acceptance / Conformance Criteria - If clay is present at subgrade level, then this should be supplemented with soaked CBR laboratory testing.
f7ad5eed-7b2d-566e-9504-b00cd2cd7442 | note | Standard / Specification - PS 16.32.3
7f7db475-5669-5e15-b442-c3d108d349fc | note | Verifying Document - Soaked CBR
e31e3835-417b-5c80-a0e1-7ff9bfe1c976 | note | Frequency - Each Occurrence
1dff818f-f6db-56a4-978f-4aa28ffc86ff | note | Verification Activity: Activity - I
85487c2a-85e8-54cd-a41f-2813a1b305a5 | note | Verification Activity: By - SE
3f012aa4-23e1-5c5b-b7f2-6b0ae64bdc3b | checkpoint | Culvert CBR Approval
910c8bed-2828-5cb6-ae9e-966a8186e9f3 | note | Acceptance / Conformance Criteria - The contractor is to provide CBR testing of trench subgrade prior to placement of bedding and laying of culverts.
d8117810-1df1-5930-b85d-bed13da04f0a | note | Standard / Specification - PS 16.38
192b1607-56da-5b60-a3af-40da42c45c63 | note | Verifying Document - CBR
dfb7a8fc-7e9c-55e9-b260-b5f897727210 | note | Frequency - Each culvert prior to bedding
a7527c75-627c-5a36-a1c7-86aac66964f6 | note | Verification Activity: Activity - W
8ebe096a-cb35-5d16-8de1-b8d9302d4fec | note | Verification Activity: By - ENG
ebe808c3-7483-59c2-abae-da91d2c7d110 | checkpoint | Field Welding
0492a6fd-a08a-5aea-9f3d-02d65b3eafff | note | Acceptance / Conformance Criteria - Field welded joints shall be filed to remove rough surfaces and shall receive a protective coating of an approved zinc rich paint.
9d8090b4-51d1-5e7e-b0bb-811c75700d58 | note | Standard / Specification - PS 16.8.4.1
5eea9571-ad90-5af0-a046-868f0f5e3aa7 | note | Verifying Document - Site records
4c421a66-7742-5f14-aa48-3fe3e21a4e63 | note | Frequency - Each Weld
37a2b237-d047-592c-a2cb-cfea465c46bc | note | Verification Activity: Activity - R
e61abcb8-97f9-59db-856a-0c929338c3be | note | Verification Activity: By - SE
0ee9e16a-5700-5a2a-8ca7-43703534bbd1 | section | 4.02 Catchpits (Structure)
ce879b0e-567a-56c9-9816-5f5ec09518a8 | checkpoint | Catchpits Base
91451da5-4823-5156-a9c8-1c71fccd6f21 | note | Acceptance / Conformance Criteria - Catchpits shall be constructed on a compacted, 50mm blinding sand underlain by 150mm layer of AP65 granular material.
29b09a17-446e-5a72-8c66-3cb66058e5ec | note | Standard / Specification - PS 16.10.2
885fe284-61d4-5d67-a3fb-e4e813d5f2d2 | note | Verifying Document - Site Records
f616a0f7-1d19-57c9-9c94-84faad93fee4 | note | Frequency - Each Catchpit
e1d0b4cb-7c28-5efb-863b-1f324e7da3bd | note | Verification Activity: Activity - I
c2bf6404-9c16-5656-bedd-49c43e18f0e4 | note | Verification Activity: By - SE
207ffa27-8a0f-5f15-bd6c-3fd10cd4f51f | checkpoint | Precast Catchpit Sealant
cc1bfc1a-16c5-50e2-99b9-1e283361fec6 | note | Acceptance / Conformance Criteria - All joints between segments of precast catchpit risers shall be sealed with ‘Black Butyl Mastic Sealant – Hynds (MSR)’ or similar and approved.
8d4d3799-4de1-5353-a71c-6aab0fa73e93 | note | Standard / Specification - PS 16.10.2
2ead71c7-d8aa-5288-a26c-b095680596d7 | note | Verifying Document - Site Records
dd66a4ad-0ca6-50e2-baf4-4b207fdc5058 | note | Frequency - Each Catchpit
c60f3492-8c9b-5c73-975d-dcf9e1009616 | note | Verification Activity: Activity - I
4e504112-6ff7-55cb-8be6-3381dea54c2e | note | Verification Activity: By - SE
5231bfcb-24c5-52fd-b1ad-16502b883171 | checkpoint | Catchpits Grates
db42fee5-1f9b-5538-9679-ef2f7dbd4434 | note | Acceptance / Conformance Criteria - Cast-iron grates and frames shall be set no more than 30mm lower than, but parallel to the cross fall and grade of the surrounding, finished pavement surface level. All grates and frames shall be haunched to lids.
20d9fe26-a2ef-51b3-a9eb-a38a0f943654 | note | Standard / Specification - PS 16.10.2
340538aa-09ed-5276-9c86-55b19703ec55 | note | Verifying Document - Site Records
4d898ada-3d56-58e0-a471-279ffa8d3e69 | note | Frequency - Each Catchpit
763f38c7-ad2b-530b-95c6-10353c0904b7 | note | Verification Activity: Activity - I
892457cd-679a-53f7-9cda-8c802cab4af6 | note | Verification Activity: By - SE
249d4406-f70c-5ad2-a9bc-125599601216 | checkpoint | Catchpits Sumps
a9557bc1-415c-5321-9be1-8f99e9d934fe | note | Acceptance / Conformance Criteria - Catchpits must have sumps at least 450mm deep (below the invert of the outlet pipe level)
547becef-617d-5951-bd5e-82df9d8db534 | note | Standard / Specification - PS 16.10
14f6973a-d453-5236-8856-de35f0accb31 | note | Verifying Document - Site Records
70e25b73-2e4f-5867-ba7c-5b58acd7ebd8 | note | Frequency - Each Catchpit
513de8e0-7eee-59dd-a76e-2747c8b38c97 | note | Verification Activity: Activity - I
88d69b3a-3584-5753-a013-a69a2a9e00f2 | note | Verification Activity: By - SE
0ccd0730-e4bc-5580-b55a-327899f68751 | checkpoint | Catchpits Inlets
215fc192-79fb-5955-b47c-6ea5b30729e0 | note | Acceptance / Conformance Criteria - All catchpits receiving stormwater from the highway shall be constructed with a back-entry inlet.
f21a17d7-6ee3-5d1f-98af-1eaa9e3789cc | note | Standard / Specification - PS 16.10
602a3ece-e3f1-5591-81a4-c6b6f46a42f1 | note | Verifying Document - Site Records
349121df-322b-556a-922d-481a41c6fe0b | note | Frequency - Each Catchpit
476ed926-eae7-5ad2-9f0d-5247fb96c4d7 | note | Verification Activity: Activity - I
0205cf67-ee93-590a-8844-6de792106559 | note | Verification Activity: By - SE
a793a8ad-c4d0-5d47-b468-a40e41e1d39d | section | 4.02 Manholes (Including Catchpit Manholes)
57decfc4-22f3-5029-91f2-d41fdc7c71c6 | checkpoint | Manholes Base
3e3f65c4-ac26-54a4-9479-925241b021c9 | note | Acceptance / Conformance Criteria - Manholes shall be constructed on top of a 150mm layer of compacted AP65 or GAP100 granular material
cba8c7c4-652a-5821-a4fe-f1246dea6d56 | note | Standard / Specification - PS 16.15.2
83d130da-2c4b-537f-9b49-3d6ba92de6bc | note | Verifying Document - Site Records
085968bb-4378-5fc5-9385-55bbb79ef966 | note | Frequency - Each Manhole
9cfa8895-e9ea-5494-b0ab-74aa22779dcd | note | Verification Activity: Activity - I
34d7b838-041a-536b-a90e-ecd01f5f5a8b | note | Verification Activity: By - SE
1e9370f2-6eaa-5f91-9eed-b69b0e82ab59 | checkpoint | Manholes Sealant
494c53e9-9bb6-5a97-a70d-13b9d49f5ad0 | note | Acceptance / Conformance Criteria - All joints between ring segments of precast manholes and chambers shall be sealed with ‘Grey Butyl Manhole Sealant – Hynds (SM9020)’ or similar and approved.
73557a9a-4c1d-5817-a9d4-a7527e9904fa | note | Standard / Specification - PS 16.15.2
6d5b8a26-9e33-5a52-943f-4248d4965e6c | note | Verifying Document - Site Records
f2fec96b-fee9-5fee-9370-de0db739df91 | note | Frequency - Each Catchpit
031cf630-81f0-5af3-949b-bf95e8b29317 | note | Verification Activity: Activity - I
68e90003-c01f-5415-9f9e-a119e1854ec9 | note | Verification Activity: By - SE
869ecf33-5409-5f27-9707-37311f3c5727 | checkpoint | Benching
bc59a1b4-3578-5d6e-b1f2-07cdf0e00b8a | note | Acceptance / Conformance Criteria - Benching is required in all manhole structures unless noted otherwise on Drawings. Benching shall be 20MPa concrete and to a F4 finish. Manhole benching shall accommodate pavement subsoil drain connections where required.
3c775f97-4007-5742-9271-b1b1f65f8480 | note | Standard / Specification - PS 16.15.2
c8bfb107-8454-5769-a0fa-71e23dd50167 | note | Verifying Document - Site Records
efc0b834-99e9-5637-ad22-c24cfad273d1 | note | Frequency - Each Catchpit
bf71753b-6f08-5e10-9fa8-bba84faa3401 | note | Verification Activity: Activity - I
98277e3f-167b-5505-9508-4415132f351b | note | Verification Activity: By - SE
c8c3277e-08f4-542e-a006-120a808c21cc | checkpoint | Benching Fall
9238b141-7512-54e1-b372-25ea9565ab3a | note | Acceptance / Conformance Criteria - All side benching shall be formed with a fall towards the channel unless otherwise stated.
fa0dad55-98d3-5b7e-9c7a-2408d3b58241 | note | Standard / Specification - PS 16.15.2
2dd19203-f9cf-552f-be34-9856ac80b7df | note | Verifying Document - Site Records
4a6dd8dd-2b8d-5a38-8707-2cfa32d9e3c2 | note | Frequency - Each Manhole
59930903-0387-5330-861b-606e4e054b44 | note | Verification Activity: Activity - I
73197103-0320-567b-9aa9-2ee569aa7857 | note | Verification Activity: By - SE
b392a0da-024a-537b-9dd6-a076c03687ad | checkpoint | Sealant
efa129d3-e028-5f33-902d-9b337f4a61ad | note | Acceptance / Conformance Criteria - All pipe work penetrations through manhole walls shall be sealed using Epoxy Mortar or an approved equivalent type of permanent sealant.
91565d88-af91-5c2a-bc44-4d66a085e0c9 | note | Standard / Specification - PS 16.15.2
5d906ba4-b24f-59b6-80b5-20ee61c8bff5 | note | Verifying Document - Site Records
dad8f851-1286-5309-a028-b5fe0d926b73 | note | Frequency - Each Manhole
5e7775da-9288-5faf-a203-c7b08d538273 | note | Verification Activity: Activity - I
102fc87f-010e-5bc4-af86-27331dbf1c2d | note | Verification Activity: By - SE
d197f6d4-9636-51d0-beeb-7ffbb972dfeb | checkpoint | Lids
50f8c1da-aa4d-555e-9f37-953e1a14f829 | note | Acceptance / Conformance Criteria - All solid cast-iron covers and frames shall be set flush with the cross fall and grade of the surrounding finished surfaces. All grates and frames shall be haunched to lids.
db83f25e-53cd-5887-80d8-96d8555350c5 | note | Standard / Specification - PS 16.15.2
103b195b-273b-5a2b-8df3-8d57e11317ca | note | Verifying Document - Site Records
670c6463-fbc2-54be-ab30-2530665fb362 | note | Frequency - Each Manhole
565173a0-9a5b-5617-9bd8-b1eaf8006dd3 | note | Verification Activity: Activity - I
c82822e7-2d51-50c7-a971-0349a987e60a | note | Verification Activity: By - SE
2021e082-feb8-597e-bf7b-37ffea0005c6 | checkpoint | Raised cover levels
070a5ede-2b2d-5082-9be1-3d43915d1f93 | note | Acceptance / Conformance Criteria - For new or existing manholes with raised cover levels, the height of the manhole access shaft (throat) shall be no greater than 600mm where access is required (all non-catchpit manholes).
bf8c25ff-8163-53ab-81f2-039f29c933b9 | note | ○ The shaft and any subsequent extensions to the shaft shall be constructed using either:
f2ef9b07-088e-59fa-8437-f55bd5847602 | note | Standard / Specification - PS 16.15.2
f991fffd-770c-5608-b542-b9b3fccad7f0 | note | Verifying Document - Site Records
2942d467-d679-55ea-a39f-d17109ab076d | note | Frequency - Each Manhole
c7e664b4-997d-5bcd-8913-1f8c8e119c3d | note | Verification Activity: Activity - I
f29396f4-f2c1-5845-a908-f00fbc05305e | note | Verification Activity: By - SE
6745195e-1ee1-5657-a325-cb919982a609 | checkpoint | Adjust Manhole Service Lid Covers
f8663452-20c1-5bb9-97ee-5ea7bc113292 | note | Acceptance / Conformance Criteria - Following adjustment, the service cover shall be firmly held in place and shall not be 5mm higher or 0mm lower than the adjoining surface. The item shall cover adjustments + or – 300mm from the original height. Any adjustments exceeding these measurements shall be treated as a variation.
fbb983b6-7b0c-52e8-9c97-e843cf080e03 | note | Standard / Specification - PS 16.12.1
af481a1a-da23-522b-bde4-5f8fd06b219b | note | Verifying Document - Site Records
cd90577b-7396-5f21-bf7d-6a5b99704d08 | note | Frequency - Each Lid
77159fbe-d8d3-5c8c-953f-c2862e830892 | note | Verification Activity: Activity - I
e4506001-c756-569e-a5a0-44bf924d0a0f | note | Verification Activity: By - SE
980bd207-6d69-55ac-9946-689cf86e1eed | checkpoint | Visual inspection of all Manholes
20cd507a-4067-5855-81c7-0ba4cc709c22 | note | Acceptance / Conformance Criteria - 3-6 months following construction, Each manhole shall be inspected. No evidence of identifiable flow infiltration, settlement and riser displacement or cracking shall be present
04ec00a8-4f1b-5400-864a-34b4a048cc7c | note | Standard / Specification - PS 16.34
ca7f50c2-ec7b-5c7f-b980-ac4f907e2039 | note | Verifying Document - Inspection Record
1fb897bb-f1b7-5f79-a22c-ea17b6f9e89d | note | Frequency - Each Manhole 3-6 months after Construction
dd630042-8ad3-5da4-86f5-ea4757046c33 | note | Verification Activity: Activity - W
bbe5bdae-8aae-5301-a287-fcc19ad04de6 | note | Verification Activity: By - ENG
692f9242-5d40-5839-9058-e786ce140608 | section | 4.02 Headwalls and Wingwalls (Structure)
931829a5-4dc0-58fa-999e-63f198870e0b | checkpoint | Headwall Bedding
d6e8fd5b-7c84-5439-8b75-65c7718d40e1 | note | Acceptance / Conformance Criteria - Headwall aprons shall be constructed on a compacted, 75mm bedding sand underlay by 150mm layer of AP65 (or similar material as approved by the Engineer) granular material and compacted to a MDD of 95%.
df19c1d4-e3e6-52fb-b57f-67eb0daeb35e | note | Standard / Specification - PS 16.13.2
6c069bb7-ec99-5d94-a94d-afdf5e348b66 | note | Verifying Document - NDM Results
88538583-650c-593b-9fa3-e4a04c63afdc | note | Frequency - Every Unit
65a96f82-4f4d-5589-b246-4ff6457857fc | note | Verification Activity: Activity - I
b2499e15-8a61-5b04-8bdf-b572bdd91048 | note | Verification Activity: By - SE
8be6e9f8-b058-5e72-80bf-b20134e32b6b | note | Comments / Closeout Details - 1 per Apron
a8ddf9cb-2bd9-57e4-83f0-b5320f27c50b | checkpoint | Precast and Cast in-situ Headwall and Wingwall tolerance
e35759d5-a08b-5133-ac97-ab5a64f468f7 | note | Acceptance / Conformance Criteria - +/- 10mm variance to vertical design set-out
4917959d-980c-5e8b-9f37-0f4bd860673f | note | ○ +/- 10mm variance to horizontal design set-out (values in accordance with NZS 3109: 1997)
f24e243d-7b27-5ed0-926c-31504047afba | note | Standard / Specification - PS 16.34
1c98bc6a-fb15-5fb3-b623-f4f03c89fefb | note | Verifying Document - Survey Records
b1116892-6aed-5597-b466-3fcadd3a2279 | note | Frequency - Every Unit
ab4591aa-728a-5751-ba74-1b4557ed805c | note | Verification Activity: Activity - I
1c23eab1-ff2b-5427-875c-03d136c8ade5 | note | Verification Activity: By - SV
a158ed91-6672-5f07-aa5d-9c1bfd58b3d6 | section | 5.01 Stormwater Insitu Concrete Pour
6154b303-86b3-54cd-aa11-e28461a03423 | checkpoint | Construction Joint Locations
03272a5b-3994-591e-9963-6054a6617160 | note | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
2fc050e1-4e34-58a1-905b-c83b65e8f789 | note | Standard / Specification - Downer
cc075955-10bd-5e0b-9955-79587acb6e75 | note | Verifying Document - Approval
951c08b8-5cac-5954-8b4b-322046f4f1b3 | note | Frequency - Prior to Pour
1316a56b-9ce2-508b-ba28-048a728ab5a5 | note | Verification Activity: Activity - HP
588bd909-478c-554e-9acf-4c9d92d45aa7 | note | Verification Activity: By - ENG
66d4c0ed-648a-5ea8-ac2a-ac66c182b587 | signoff | AUTHORITY HOLDPOINT
b89621c0-d6ba-5e0b-8113-6f0faa1f67ef | checkpoint | Dry Pack Mortar
f9dfda64-7e36-500e-903b-e8ddeb3dc48f | note | Acceptance / Conformance Criteria - Dry pack mortar where specified on the drawings shall be places as per the manufactures instructions.
120abff6-478f-5d8e-9b7c-b62834e0f463 | note | Standard / Specification - Downer
48fafdda-80df-5c3d-8606-9cdf8c87f9fb | note | Verifying Document - Pre pour
afcdefba-0990-5529-89fc-67377e37e2b4 | note | Frequency - Before Works
ffbafc1b-8fe3-5328-8c8e-f50b1c47f1a3 | note | Verification Activity: Activity - R
c74f6b66-6752-5374-bffd-f3566221d1fb | note | Verification Activity: By - PE
ae866a02-00df-5788-9f05-048029cdb1ad | checkpoint | Reinforcement Pre Pour Inspection
e37ae9d7-e89c-58c9-ab6f-dfdd03948d8e | note | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
a4a7a487-aa5c-5f15-832d-b2df276da3b4 | note | Standard / Specification - Downer
69d4187c-4be5-5a18-92cc-5f83125be6d5 | note | Verifying Document - Pre pour
ba67afbe-5538-59bc-b3bc-c82bbb462d71 | note | Frequency - Each Pour
61bc1f71-0504-5746-a3b0-ee6d3278e4a9 | note | Verification Activity: Activity - R
2796a920-7736-5f69-ab96-80869115dec5 | note | Verification Activity: By - PE
ae12e61b-14bf-52e1-8712-95421eadb4d8 | checkpoint | Pre-Pour Inspection
bcdbd1bc-eced-5465-9001-0f9101186b78 | note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
7ac72b16-4611-54a3-8926-a837ebfc9b6c | note | Standard / Specification - Downer
6a12d5ec-be44-5573-b7a0-42ee27e865db | note | Verifying Document - Signed Pre-Pour
2755fad5-8481-59f5-bdbb-74d1dde99b42 | note | Frequency - 48 Hours Notice Prior to Each Occurrence
d1f4e329-8e39-5ca7-b816-739eb32d4fd1 | note | Verification Activity: Activity - HP
b0ce7d8e-225d-5567-9da2-17deb23b9fa7 | note | Verification Activity: By - ENG
61f646ff-f717-5b42-8ace-5ab658a782c1 | signoff | AUTHORITY HOLDPOINT
adc9a3ef-8e00-5211-8f06-57a22d004a33 | checkpoint | Delivery Dockets
18164939-6962-5586-a55d-5ef058442ad4 | note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
b32e4137-6c16-555b-85e4-896ae4396220 | note | Standard / Specification - Downer
96b8ff0a-f7ab-5cd5-bbc9-5c414148b159 | note | Verifying Document - Dockets
93bd6e47-8e00-58a4-b5d1-a590185a073e | note | Frequency - Each Pour
e45e90eb-f359-59ea-87ad-9cda915a9433 | note | Verification Activity: Activity - R
715b8808-5c6b-5431-b696-590db25441fe | note | Verification Activity: By - PE
c5e24299-b40e-5d11-9f84-a756b4e0595c | checkpoint | Slump Testing
50983e9d-0930-539c-882d-35871822d0cb | note | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
1ab3ed77-c623-5145-8dbb-06119cb4b605 | note | Standard / Specification - Downer
9c5dda47-65d2-53eb-97b9-da26404e2109 | note | Verifying Document - Pre Pour
bfd3575e-90b7-5c5a-94b8-8d6c197ede45 | note | Frequency - Each Pour
c909c0cd-e428-5b71-a1bf-8617fbf6be7f | note | Verification Activity: Activity - R
ea4e9ccb-860f-52c7-83a3-413f935b20ec | note | Verification Activity: By - PE
dc05037a-b2b7-5a07-bc91-49798fdf8318 | section | 5.02 Stormwater Insitu Concrete Post Pour
88ad4a7f-f270-5172-a9a6-605ce7079125 | checkpoint | Post Pour Inspection
10a16dc4-1593-5da1-8444-ef7215d9f983 | note | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
ba33dcad-e04a-5ab7-ab6e-2bb448942f56 | note | Standard / Specification - Downer
54c1fd82-1912-5065-bc52-6a02e14ff2f7 | note | Verifying Document - Post Pour
44106101-7697-5c12-96a0-b4a5f18452c9 | note | Frequency - Each Pour
a10cd423-9f3d-5c00-894e-fc06c97503e3 | note | Verification Activity: Activity - R
8289c616-6820-558a-bff8-28e72ac13c2d | note | Verification Activity: By - PE
b751d3da-acb9-5b40-b4cc-b71a773e9688 | checkpoint | Construction joints
c0ca9e31-596d-5008-b48b-dbcca85bc2cb | note | Acceptance / Conformance Criteria - Construction joints shall be placed as per the drawings / agreement.
e6f39b73-37b8-51ed-82c7-6aef73ed304f | note | Standard / Specification - Downer
079e1943-a765-56a2-8df5-e3bd2bf7f889 | note | Verifying Document - Post Pour
a3f6b1aa-1015-5dd2-ad54-6412569eadcf | note | Frequency - Each Pour
442ded53-f85d-556d-9f50-82e86fdc4296 | note | Verification Activity: Activity - R
2dba0a49-7fc8-5657-9f72-48278434ee98 | note | Verification Activity: By - PE
b82492f6-ec62-561c-9684-dd5fe2d7e966 | checkpoint | Defective Concrete Finishes
7137c47d-1047-5eaa-bc8b-edd044ba5216 | note | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
b5316bf6-f3a0-540b-b3dc-851f8290f49e | note | Standard / Specification - NZS 3114
6dcc4b0e-5625-50bd-9a2f-9e7786d1d88d | note | Verifying Document - NCR
560a3dcb-a49c-51bf-ab25-25c382cc4443 | note | Frequency - Prior to non Minor Repair
1f84c50c-e50b-5288-b05d-1c95bd6115fe | note | Verification Activity: Activity - V
e6c1f36b-be2a-52ac-9700-f8b106f42b05 | note | Verification Activity: By - SE
e0ceb118-cf93-5ebf-8799-db37dbe1b4cc | section | 4.02 Soakage Pits and Infiltration Trench
56da3b35-e977-5098-869b-68846db1f6fe | checkpoint | Soakage Pit Sealing
f19a3897-0998-55f9-b69e-07de75c9e3db | note | Acceptance / Conformance Criteria - All pipe work penetrations through manhole walls shall be sealed using Epoxy Mortar or an approved equivalent type of permanent sealant.
240ac6fd-0908-54b2-9440-46987ce3543c | note | Standard / Specification - PS 16.12.2.2
58e4ec0a-138e-5e17-ab82-9787efdfe970 | note | Verifying Document - Site Records
6c6f806a-9eac-5b87-b302-63e6942c6172 | note | Frequency - Each Hole
6deee2d6-03db-5312-bd8d-27cf3eae4851 | note | Verification Activity: Activity - S
0a00ed48-8f8b-54c8-b621-88679bf73458 | note | Verification Activity: By - SE
a014b34e-2844-5368-86c7-cb4629d86371 | checkpoint | Soakage Pit Benching
bc0e0430-564a-537f-8fc9-c3f072479b15 | note | Acceptance / Conformance Criteria - All side benching shall be formed with a fall towards the channel unless otherwise stated.
986c937f-65e8-5125-a5e5-984e6800acc8 | note | Standard / Specification - PS 16.12.2.2
0dc2dbee-2aad-549e-97c7-1d9be162ebe8 | note | Verifying Document - Site Records
04a64432-635c-58f7-b176-2f39413235dc | note | Frequency - Each Occurrence
a4e0c236-9451-5406-8333-968730e71a33 | note | Verification Activity: Activity - S
a737a79e-562b-5b2c-8b49-6d1a7779c49a | note | Verification Activity: By - SE
8cf7174f-0bb5-548b-95f8-8a7f421ea96f | checkpoint | Soakage Pit Lids
e0c9d442-22f3-5353-ac3a-35d6adad8767 | note | Acceptance / Conformance Criteria - All solid cast-iron covers and frames shall be set flush with the cross fall and grade of the surrounding finished surfaces. All grates and frames shall be haunched to lids.
c674f390-4c1e-5817-9c53-a6ce8058239c | note | Standard / Specification - PS 16.12.2.2
7b0506d1-007b-5d7a-a41b-e66778ebc316 | note | Verifying Document - Site Records
273e8c34-6c92-5f05-860e-329637367619 | note | Frequency - Each Occurrence
0f3b2fbc-1c63-5bec-b0a7-8ea15a9a166b | note | Verification Activity: Activity - S
f6ba389c-80f9-5866-ba37-edf67537f7ab | note | Verification Activity: By - SE
90473d89-6a25-5b98-8346-30103561caf6 | checkpoint | Infiltration Trench Excavation
28dc59d8-c851-5f48-800d-99207ac4df71 | note | Acceptance / Conformance Criteria - The trench/excavation shall be free of roots and projections or obstructions. Where over excavation has occurred, the bottom shall be brought back to grade using excavated material which is only lightly compacted in position to the same extent as the undisturbed surrounding soil. No loose soil shall be left in the excavation after restoration to finished grade.
54c52924-627e-5f41-9731-16a0aac30f75 | note | Standard / Specification - PS 16.12.3.1
34777817-f24d-5241-9fa0-54162740f875 | note | Verifying Document - Site Records
adc502c6-7f92-58d9-8e2c-a7ec8c2f0a4c | note | Frequency - Each Trench
ad3c3740-9612-5b44-849d-5c744c2f8c50 | note | Verification Activity: Activity - S
b1e4f5a4-9108-5a02-aee2-ea12cfbc5122 | note | Verification Activity: By - SE
61eb9303-9958-5eda-9af6-66d7c29dad85 | checkpoint | Trench Inspection
91397fb8-2f58-501f-bfb1-5dd61830d53b | note | Acceptance / Conformance Criteria - All trenches in existing ground shall be inspected by the Engineer prior to commencement of laying filter cloth. Any unsuitable foundation material shall be removed at the Engineers direction.
98252f8b-39f0-56bd-9c84-e57564da0e76 | note | Standard / Specification - PS 16.12.3.1
20fd9b71-01bd-5dc0-9505-8688091ff9c0 | note | Verifying Document - Engineers Approval
5c46e0d4-3756-5480-910c-6f8f6ce4408f | note | Frequency - Prior to commencement of laying filter cloth
803be5a0-e0ba-5483-b4b6-0642b205354c | note | Verification Activity: Activity - HP
60a78816-8e22-5eaf-9e3d-0f414f4e6371 | note | Verification Activity: By - ENG
0bfb2850-b44a-5f80-8428-539e15c33ea3 | signoff | AUTHORITY HOLDPOINT
1eb6aa80-25e1-5a22-b805-7f5e985078e7 | checkpoint | Groundwater
bcbef807-f9d9-5a7e-9571-cac57e09ade2 | note | Acceptance / Conformance Criteria - If groundwater is encountered in the trench/excavation the Contractor shall seek instructions from the Engineer on how to proceed.
a0a914d7-14bf-596c-904a-9550b9301207 | note | Standard / Specification - PS 16.12.3.1
57549735-c03e-5583-9f50-6967674c552c | note | Verifying Document - Site Records
bf67a56b-804d-500a-a4cb-80881d00665b | note | Frequency - Each Occurrence
cca2877e-d691-5684-ba6a-285a0112c762 | note | Verification Activity: Activity - S
eb9e8934-e35a-5407-b1ee-67b3a0b2f87f | note | Verification Activity: By - SE
f512cfbf-e342-577e-bb22-255c49acfb23 | section | 4.02 Drainage Media
16a8526f-f1e5-55df-b58d-f5d462706ab5 | checkpoint | Placement of Drainage Media
5c81fd44-0443-5e48-9de0-fb4edf3a0bf8 | note | Acceptance / Conformance Criteria - The drainage media (100-150mm rock) shall be carefully placed in the clean, excavated area after the excavated material has been removed and the excavation site cleared of potentially contaminating material and the excavation lined with filter cloth. The drainage media shall be lightly and uniformly compacted. No mechanical compaction equipment shall be used. The drainage media shall not be placed or lightly compacted if the excavation is flooded or the in-situ soils saturated.
55341c3a-d015-5915-a20f-baa4cf5e52a4 | note | Standard / Specification - PS 16.12.3.3
b30b18af-bac7-5ebc-9a63-b66c44569ffa | note | Verifying Document - Site Records
8f8fe2c0-debd-5ea8-9348-caa5854b814b | note | Frequency - Each Area
c2be408b-076f-5377-838c-b5199a61c1b1 | note | Verification Activity: Activity - S
96cd4a28-de3f-5148-a343-deb372841c14 | note | Verification Activity: By - SE
c042aad8-5619-5c0a-a456-04535ddcb656 | section | 4.02 Place D50 250mm Rip Rap
4c9484f2-61b4-5b4b-865b-b4cb9ae1e88e | checkpoint | Rip Rap Placement
22853bc5-0753-5053-8c33-b9466d7ee3c7 | note | Acceptance / Conformance Criteria - The Contractor shall place D50 = 250mm size rock rip rap in areas shown on the contract drawings and as instructed by the Engineer. The rock shall be placed to ensure rock is tightly knit with no movement.
e46a71ae-ecb4-5f9d-97ee-c06397b40849 | note | Standard / Specification - PS 16.14.2
6e3f78c2-f1b6-5e08-a0a3-2701c258e5e1 | note | Verifying Document - Site Records
9fb4ce5d-ffd3-5f2b-8422-6bf81421bfe6 | note | Frequency - Each Area
f70ab0e3-62d8-5ef0-99bd-f95784295c60 | note | Verification Activity: Activity - S
e537a9a5-5849-56e8-b0f3-6ea03be34dd0 | note | Verification Activity: By - SE
d572ac21-c4d7-5544-a1f4-c02d02caa3e9 | section | 4.02 Rip Rap Rock Flumes
9b8345d2-3cff-4475-a536-fcd7cb14f966 | checkpoint | Rip Rap Placement
bc2f5ba9-1d9e-5eac-8912-dbb98a299746 | note | Acceptance / Conformance Criteria - The Contractor shall place D50 rock rip rap in areas shown on the contract drawings and as instructed by the Engineer. The rock shall be placed to ensure rock is tightly knit with no movement.
651e3d11-773b-5226-a4a7-9a27f16dd06b | note | Standard / Specification - PS 16.17.2
5eca0f93-6b6e-5e2f-90fc-8117ed6cf1c9 | note | Verifying Document - Site Records
9d1ca5ce-7fa5-5baa-8874-c937c5e43244 | note | Frequency - Each Area
6ed2f43c-5b07-5f52-983a-385f6803293f | note | Verification Activity: Activity - S
4443f3e4-499b-57e2-8311-f6bb24d43222 | note | Verification Activity: By - SE
933915f5-84dd-55ac-8f31-94e0724761c5 | checkpoint | Geotextile Protection
d86c9a05-a2b4-5cbb-9e54-8ea396cc96e3 | note | Acceptance / Conformance Criteria - The contractor shall minimise the height from which rock is placed on order to reduce the risk of damage to the filter fabric layer. Rock shall not be dropped from >0.5m height.
f46e091d-234a-53c0-a0bb-a735b507f88f | note | Standard / Specification - PS 16.17.2
300b4c85-2e37-5047-bbdc-be4da0087496 | note | Verifying Document - Site Records
16123acf-b19a-51c9-b58a-1183899be92d | note | Frequency - Each Area
42e783ef-cfd7-5549-aca8-169816c04b68 | note | Verification Activity: Activity - S
fdcada70-18b0-59a1-bd27-1c4dc9a46588 | note | Verification Activity: By - SE
5ae76e3f-ad0c-5b17-acdd-38cf495e6d63 | checkpoint | Face Alignment
98f89134-4d3c-5b88-bbd9-26f2b72c2cae | note | Acceptance / Conformance Criteria - The face of the rock rip rap shall be placed at the gradient shown on the drawings and the termination at each end against existing slopes is to be keyed into and to approximately match the adjacent slope and placed in general accordance with ‘Section 10 Filling’ of TNZ F/1:1997 to achieve a compact mass with minimal voids and good interlock of rock fragments.
76c92f01-b839-53c1-b80c-5935c294115c | note | Standard / Specification - PS 16.17.2
9f3d8cdc-5118-5d35-bbf8-f9114d509a8a | note | Verifying Document - Survey Records
bb4aca4a-6248-5079-a1e0-c068707111d7 | note | Frequency - Each Area
03f7bb56-4982-5c96-8785-a224fb1d6850 | note | Verification Activity: Activity - S
307c6950-1d78-57c0-9e91-31b576b33287 | note | Verification Activity: By - SE
66492d75-daa6-54e0-b4f9-2284f4b3e385 | section | 4.02 Geofabric
8fbdc2a5-80fc-5f9b-b15a-82adfd429a2c | checkpoint | Geotextile Filter Fabric Protection
4cf579a4-2a05-56a7-81ec-b364ade89574 | note | Acceptance / Conformance Criteria - Construction plant shall not travel over exposed fabric. A minimum cover of 200mm of fill material shall be in place before construction plant is operated above the fabric.
7b71b768-d966-5512-bef1-a433f3ff7c47 | note | Standard / Specification - PS 16.18.1, PS 16.12.3.2
30911133-9df5-5b7f-bf87-2acf74d0b25e | note | Verifying Document - Site Records
ed26b16f-63a4-5096-a35c-c600397ddbdd | note | Frequency - Before Trafficking
993e692a-90b3-5247-a472-90e3632c5d45 | note | Verification Activity: Activity - S
8dfb6967-7c56-5bbc-a690-40d0804d7a69 | note | Verification Activity: By - SE
8405fec7-77b3-562e-ba2f-debcd2d7317c | checkpoint | Geotextile Filter Fabric Lab
122bc352-ec1f-5337-b3c4-7a6c55757851 | note | Acceptance / Conformance Criteria - Geotextile filter fabric shall have a minimum overlap of 500mm at any joins.
96937be9-371a-59f7-866e-f5037f929c70 | note | Standard / Specification - PS 16.18.1, PS 16.12.3.2
f46ae553-2f4e-5af9-bbd7-577f2166fc71 | note | Verifying Document - Site Records
58247961-654f-556a-afab-a8baf23aabc4 | note | Frequency - Each Joint
214b306a-90e5-5a0f-8739-5592fa1607e6 | note | Verification Activity: Activity - R
d3afa148-98b5-55c5-960d-c2558ed861b7 | note | Verification Activity: By - SE
5649ca93-ff44-5e6f-b8b6-c96d7135571d | section | 4.02 GeoGrid
1e09a67c-513f-5bc4-a4f6-717a666a4fd5 | checkpoint | GeoGrid Installation Approval
22d8eada-7d12-5d3f-a79a-5747323033a9 | note | Acceptance / Conformance Criteria - The installation of biaxial geogrid shall not commence until the Engineer has inspected the proposed geogrid on site and confirmed that the correct types of geogrid have been supplied and that the foundation soils meet with those assumed in the detailed design calculations.
8149176d-da0c-5cc0-afd9-4a3e73fdf3ae | note | Standard / Specification - PS16.29.3
83a6e3c7-825b-530e-8253-9ef839533932 | note | Verifying Document - Engineers Approval
aac8d7e8-db3c-5f15-abc7-819c4bb23bbb | note | Frequency - Prior to installation
9487c39e-e641-58b0-8c71-8d4be62b6830 | note | Verification Activity: Activity - HP
9300e67c-4440-5a4a-966d-61f947899486 | note | Verification Activity: By - ENG
0e9c7c5c-012f-530b-a6e8-e661bfe46465 | signoff | AUTHORITY HOLDPOINT
5bf9209f-4eed-584b-9f4a-c59c0f229810 | checkpoint | Biaxial Geogrid Placement
cf0de219-93be-5aa4-8937-7ebec28e3cc0 | note | Acceptance / Conformance Criteria - Geogrid is to be placed in accordance with the Manufacturer’s instructions, to the lines and levels shown on the drawings. Geogrid shall have a minimum overlap of 1000mm at any joins. The geogrid shall be placed perpendicular to the road orientation and shall run in a continuous unbroken length from one side to the other.
29c48110-8ec2-5333-8ade-02a505ffc306 | note | Standard / Specification - PS 16.29.3
c55e502f-d726-511a-984a-a76312bf6f58 | note | Verifying Document - Site Records
8235d6bb-d43b-52a0-a490-7fabc5234df1 | note | Frequency - Each Joint
246bb60c-0074-5404-889d-8dabfa4c390d | note | Verification Activity: Activity - S
999206c4-db50-5dbe-88aa-16801a1ead0d | note | Verification Activity: By - SE
c5d1ba0c-5f6b-5e7f-85d0-77e1b9f01425 | checkpoint | Biaxial Geogrid Backfilling
3fee1f42-4bf7-5f17-91dc-eda7a0c2b9d3 | note | Acceptance / Conformance Criteria - At no time shall more reinforcing geogrid be laid than cant be covered in the same day. Each run of geogrid shall be firmly secured in place to maintain the grid in position and ensure that the geogrid is taut over the face. Care shall be taken to ensure that the geogrid is not damaged during fill placement. Construction plant shall not travel over exposed geogrid. A minimum cover of 150mm of fill material shall be in place before construction plant is operated above the geogrid.
08439b4f-0a4e-588a-b526-e1fca1e1c6b8 | note | Standard / Specification - PS 16.29.3
e71b3ac4-47f3-5fca-9b07-b23d3fa8a848 | note | Verifying Document - Site Records
aedf6afc-28a3-5899-a072-64d805c08a13 | note | Frequency - Daily
02125582-4a06-5a27-babb-d73193100feb | note | Verification Activity: Activity - S
dfead6d0-2cc1-5c17-bb54-a60874e5ac92 | note | Verification Activity: By - SE
0ec66c2a-c9a1-58a8-ac75-4a7224586083 | section | 4.02 Bioretention Soil Media
104dfbf0-a859-591e-aeaa-ea3f4aa9d30a | checkpoint | Exclusion Zones (Bioretention and Infiltration Devices)
0d81736a-eb72-51db-9cbd-cff336c2a8a2 | note | Acceptance / Conformance Criteria - The contractor is to establish fenced-off exclusion zones at the start of the works to avoid plant / machinery tracking and over-compacting bioretention and infiltration device formations such that the hydraulic conductivity of the existing ground is not compromised. The exclusion zone shall at a minimum cover the extent of the device base area.
ed15f851-64ed-5c28-b220-b89d3a4be542 | note | Standard / Specification - PS 16.39.1
8a1a0eb5-a919-58a8-ae91-f54e25c29ea0 | note | Verifying Document - Site Records
581b4183-1141-5220-85b0-534d56547521 | note | Frequency - At the start of the works
53c0dd84-b6cb-565c-abda-0d8b3aac3846 | note | Verification Activity: Activity - R
1f349e6e-5d2d-57aa-b2b7-91d245bf18d2 | note | Verification Activity: By - SE
e838acb5-a243-5aee-b134-0368c63ca89b | checkpoint | Interface Finish
4db93a4d-29d9-5210-bdc9-010d1feb6980 | note | Acceptance / Conformance Criteria - Bioretention devices operation as it provides a poor interface with the media. A rough finish such as that achieved with a toothed digger bucket is preferred.
29c29eef-c746-50b0-9da4-2f237d3c8edd | note | Standard / Specification - PS 16.21
5f199cd1-a152-58d5-aca9-1d791420f495 | note | Verifying Document - Site Records
4469be41-6da2-581d-a95c-ee6d1f61c436 | note | Frequency - Each Device
e9df8289-fa4c-521c-b85f-cd0e902c519b | note | Verification Activity: Activity - R
6481b49b-9bd2-5c22-af4b-477fac0ca73b | note | Verification Activity: By - SE
68a70d58-a064-59d5-9cd1-5cb48a512fbe | checkpoint | Suitability of existing soil for infiltration and bioretention areas.
1ec53b8f-0670-5987-b147-f8677cd76213 | note | Acceptance / Conformance Criteria - Bioretention device and infiltration device formations are to be inspected by the Engineer prior to laying of bioretention or filtration media to confirm the suitability of the existing ground.
11363c58-23de-5433-a35f-4045bbbd450e | note | Standard / Specification - PS 16.38
9df65bf8-12cf-5cb2-a9ed-6c6685c394a6 | note | Verifying Document - Site Records
e1e9a62d-7b52-50c6-9826-2d0ddeb6afce | note | Frequency - prior to laying of bioretention or filtration media
cfa7446b-7740-5fe4-a867-cf0dd5ec346b | note | Verification Activity: Activity - W
7de82b65-dd64-5793-9333-8075fbf1f041 | note | Verification Activity: By - ENG
400709eb-385d-519c-9839-a4753cf58ed9 | checkpoint | Bioretention Soil Media placement
f1a571d4-30a5-500c-bb20-d6254407c571 | note | Acceptance / Conformance Criteria - The soil media layer is required to line the invert of all bioretention devices and placed in a single lift to 50 mm above the finished level. The finished surface shall be reasonably smooth, uniform and free of obvious hollows and humps. Care shall be taken to avoid overhandling the soi
12416c74-9d61-523f-b779-3d778f99719a | note | Standard / Specification - PS 16.21.1
1ae2f2c6-d4c0-5f13-aba6-86b5b047b1de | note | Verifying Document - Site Records
b7074a3b-480e-5055-9135-c025a99e2666 | note | Frequency - Each Device
c1504bcf-2fe6-5a11-b49d-b50ee1febd2e | note | Verification Activity: Activity - R
2feaab38-9471-504d-bc9a-df4656f8f492 | note | Verification Activity: By - SE
83d11636-2c9e-52b1-8eef-5d144d45c471 | checkpoint | Compaction
7d3f6bd9-fda6-5006-bf31-39315051a361 | note | Acceptance / Conformance Criteria - The soil media shall be raked without any form of mechanical compaction.
c5649570-c279-5f89-89c5-96b55e6d5eb4 | note | Standard / Specification - PS 16.21
8348b57a-f6c7-5a05-add9-6112fa0b22d9 | note | Verifying Document - Site Records
47bfa947-5611-51e6-adef-dc19492ee8c4 | note | Frequency - Each Device
4256f0d6-2ca2-5382-ae0c-112269f5b30b | note | Verification Activity: Activity - R
e7a1a21e-71ea-5830-8c34-2a513964ae19 | note | Verification Activity: By - SE
e07dc8a8-0872-5e05-bd99-2d5224567429 | checkpoint | Infiltration testing
351c5980-f602-5b0a-bba6-624b814a0979 | note | Acceptance / Conformance Criteria - Once the bioretention devices have been completed, it shall be tested by double-ring infiltrometer for permeability. The rate shall be >50 mm/hr and not exceed 500 mm/hr. Alternative testing means must be approved by the Engineer.
fdd26f94-76d8-59f6-b7f7-5eb4fde2dab7 | note | Standard / Specification - PS 16.21.1
c5369bce-d2e9-5697-b2cd-25b7d4f01e73 | note | Verifying Document - Site Records
7cb61bb4-a3ea-516a-a7aa-e3fda159eec7 | note | Frequency - Each Device upon completion
0877c65c-5d77-5615-b113-4c1c9f5c2102 | note | Verification Activity: Activity - i
30e6bd0f-3520-5fab-9554-df2d49f0a071 | note | Verification Activity: By - SE
a5d7291c-6637-5c57-a02c-5b67bc1a58a7 | checkpoint | Landscaping Approval
75a467a6-f1d2-5a5f-8092-a6ba7eb698b6 | note | Acceptance / Conformance Criteria - Once the media is placed the Contractor shall notify the Engineer. If the Engineer is satisfied with the soil placement, they will advise the Contractor that landscaping can commence. Stabilisation with grass seed shall be carried out within seven days once approval is obtained from the Engineer.
f25e94a5-57f8-51de-a985-a13dd6c3e0d7 | note | Standard / Specification - PS 16.21
533ff0f4-2785-52e9-8c1b-d08dba18e301 | note | Verifying Document - Engineers Approval
c0870aa2-d2b0-55d9-8830-10690bd5f3fb | note | Frequency - Prior to Landscaping
9a296181-344f-58d6-b48e-67c29cc31607 | note | Verification Activity: Activity - HP
7779c4c6-56fc-551e-9261-8f6e358a552a | note | Verification Activity: By - ENG
ce74b3ac-ecd6-59dd-a56e-48782c6f9e5d | signoff | AUTHORITY HOLDPOINT
ff4c6cce-29c9-5715-9a71-8af215dfd828 | section | 4.02 Wetland and Bioretention Access Track
a6eba942-9657-575e-8b6f-4d1e7017a0f8 | checkpoint | Access Track Subgrade
f06e5221-b70d-549b-8bd9-626dbd5b573f | note | Acceptance / Conformance Criteria - The access track for the wetland and bioretention device 01 shall have a Compact Subgrade (minimum CBR 5).
bcaf2d44-71ed-57c1-b32f-5eb1f5498ca0 | note | Standard / Specification - PS 16.22.1
40505522-0620-54d1-a129-9bb19992a4b4 | note | Verifying Document - Scala Results
02b7fad5-28d3-500c-bb98-e648fdc19e92 | note | Frequency - TBC
f5d14694-3937-5a36-871e-693a5c110c60 | note | Verification Activity: Activity - R
e85c85ef-e9cd-575c-9601-119c29cf5c45 | note | Verification Activity: By - SE
535cf887-d805-5a19-93ef-e335e7440575 | note | Comments / Closeout Details - Frequency TBC
a1d86325-4b51-55d5-a4da-7b4dc7557832 | checkpoint | Access Track Subbase
47946a38-8f3a-58a7-99a7-ba6373c296cb | note | Acceptance / Conformance Criteria - The access track for the wetland and bioretention device 01 shall be formed as a 3m wide all-weather access track constructed with a 150mm GAP 65 Subbase.
e584151a-75a0-516d-9715-1de006e66d31 | note | Standard / Specification - PS 16.22.1
27b9b4b2-6363-550a-a4f9-7399da5794f6 | note | Verification Activity: Activity - R
c2b45e42-0290-5ba4-b359-99ccc2dee79b | note | Verification Activity: By - SE
5fa1d8d9-8540-57dc-8a10-86e6d89c789f | note | Comments / Closeout Details - Frequency and testing TBC
676ccda9-a477-5ace-a1fa-4c0dfdd6aa85 | checkpoint | Access Track Basecourse
5135c4a3-41ed-5682-8ee5-6df7f413c8e4 | note | Acceptance / Conformance Criteria - The access track for the wetland and bioretention device 01 shall be formed as a 3m wide all-weather access track constructed with a 50mm GAP 20 Basecourse (Gravel Road Spec)
bddfa7db-d6cc-5540-b855-bb75330546e3 | note | Standard / Specification - PS 16.22.1
e4573664-f832-5776-8e75-5046cfc217ee | note | Verification Activity: Activity - R
f9da32d5-cfa4-5ec3-b56e-3eeab55159c8 | note | Verification Activity: By - SE
ec197585-abcf-5f27-bbef-3285eb5331ab | note | Comments / Closeout Details - Frequency and testing TBC
115e4ffb-3697-5533-8ed9-37c13e0dfc0a | section | 4.02 Design and Construct Outfall Access Track
bbe3a9c0-92d3-5c9d-8b38-740adf8da7de | checkpoint | Outfall Access Track Design
882baa3c-2302-5b7e-9659-2c133e4daada | note | Acceptance / Conformance Criteria - The design including producer statements are to be submitted to the Engineer for approval. The Engineer will have 5 working days to review the design and provide approval or feedback (this is not a design review).
87191696-f913-52c9-b1f4-7f8a012f757d | note | Standard / Specification - PS 16.23.6
a093c227-3a73-5c5d-a8f2-099dc8529809 | note | Verifying Document - Approved Design
8810ad38-ec30-520e-adb7-78172504750d | note | Frequency - Prior to Works
4f9b5ea9-c346-54e4-b92f-49a5f486afd6 | note | Verification Activity: Activity - HP
61c8fc29-1af5-58a7-b9df-b5829414aefd | note | Verification Activity: By - ENG
e9a77ccd-ebaf-5bdd-826e-44f5c9b13004 | signoff | AUTHORITY HOLDPOINT
099a0434-7840-54fe-a0c4-e9442077ae37 | section | 4.02 Construct Wetlands
99a18b6b-9e98-57d9-90e6-ef6b9ac627f6 | checkpoint | Geotextile fabric installation
7847a402-3065-5f4d-9104-980c981d735f | note | Acceptance / Conformance Criteria - Geotextile fabric shall be laid directly on the existing ground to protect the liner from damage due to punctures. It is assumed that the existing ground will be sand from the existing geotechnical information provided. If this is not the case the Engineer must be notified to allow for remedial treatment prior to the placement of the geofabric.
1706d692-a762-58e7-8c23-58b59142daa8 | note | Standard / Specification - PS 16.24.6
7dcb761b-8999-5c69-97c7-b05da47ef324 | note | Verifying Document - Site Records
14305fb2-3d73-51bd-9ac4-537c4e5a6551 | note | Frequency - During Placement
fd0b286b-1a8c-5662-83ad-bbb776495b2a | note | Verification Activity: Activity - R
ef6067c2-551d-59b1-8121-07b1caa7cf6c | note | Verification Activity: By - SE
7eadd61e-9bed-512b-8d0c-fc30072bf454 | checkpoint | Impermeable liner installation
9236f205-24cd-5e16-a5d2-3659008fdc1c | note | Acceptance / Conformance Criteria - An impermeable liner is required to line the entire wetland base and batters to avoid ground stability issues near the gully embankment. Particular care should be taken to ensure water tightness around inlet and outlet structures as per the Drawing details.
02562567-35a9-50fa-bfa0-929526b5d6c2 | note | Standard / Specification - PS 16.24.5
0925ec77-8e6b-564e-a0cf-959f53a8ccc5 | note | Verifying Document - Site Records
a4c607bc-ca88-58c3-a11c-9583c29ce7ce | note | Frequency - During Placement
25368655-3226-51bf-9314-54cbc3b0a140 | note | Verification Activity: Activity - R
ba49fe1c-cbf6-5103-a265-b0437b4b66a3 | note | Verification Activity: By - SE
4d221194-b13f-578b-b4d4-a9b59fc5e186 | section | 4.02 Rock Riprap for Erosion Protection
09688126-8303-52c1-af1b-515803060192 | checkpoint | Organic Material Removal
82226598-a7a3-5dc6-a713-c995ad1aadeb | note | Acceptance / Conformance Criteria - Prior to placement of rock riprap, all organic material is to be removed, followed by the placement and anchorage of a Class E geotextile (in accordance with TNZ Specification F/7 Geotextile).
e7343a51-bbb6-58b6-8575-4d95ee87f02b | note | Standard / Specification - PS 16.25.1
0032fb53-1ec7-502e-ba0f-0768b6168ec9 | note | Verifying Document - Site Records
ab13743e-59e1-5732-9948-20fe239e0a1e | note | Frequency - Prior to placement of rock riprap
0e192123-2755-5088-9c4e-1f71cf77050e | note | Verification Activity: Activity - R
e61f7242-84e7-5664-9b26-ae57bf9d000d | note | Verification Activity: By - SE
d4e82767-aa07-552e-ad48-f220fc1cdc4a | section | 4.02 Void Filled Riprap
4aaaa41d-919b-5fbe-b490-6e752134928f | checkpoint | Rip Rap Mixing
1dc6996d-b22d-58d6-ba5c-4df6b0446c3b | note | Acceptance / Conformance Criteria - Mix the material thoroughly using additional moisture and control procedures that ensure a homogenous mixture where the fines fill the inherent voids in the riprap without displacing riprap.
f747012f-3d3f-5813-9689-30ddffa9a5a5 | note | Standard / Specification - PS 16.26.3
f2fd59f3-c015-5bd9-b6a6-556e29d90d6e | note | Verifying Document - Site Records
77d14f6d-975e-5ccd-a5f2-bd28ff94f416 | note | Frequency - Prior to Placement
f286c1bd-3936-5ecd-a29b-846cc0545fd3 | note | Verification Activity: Activity - R
f323441a-33df-554a-8c22-f69405db6bcf | note | Verification Activity: By - SE
d0c8dde0-be67-498e-9ec9-67448a7600c0 | checkpoint | Rip Rap Placement
1c5f7d0f-66a2-5cc9-ac55-4ded78226988 | note | Acceptance / Conformance Criteria - Place the blended mixture of approximate 2 x D50 thickness, minimising segregation of material. Some additional mixing may be required after the initial placement where there is segregation or areas that consist of smaller void fill materials.
95a6d5a5-026b-563c-b498-cc52ce39008a | note | Standard / Specification - PS 16.26.4
8c070f73-ed1f-51a4-a10c-a7e9e2445b0b | note | Verifying Document - Site Records
9f897055-7389-5e03-b44a-c3f2e35ef8ca | note | Frequency - During Placement
03e217b8-9ebc-5566-9004-bc1042940841 | note | Verification Activity: Activity - R
a229b293-a524-5524-b48e-72b25bc48c0f | note | Verification Activity: By - SE
af53a5db-ec9f-521b-90c9-eea3fb0c7f5d | checkpoint | Rip Rap Compaction
9995bf72-39d2-5083-9592-a56cdb4feec7 | note | Acceptance / Conformance Criteria - The mixture shall be consolidated by driving over it with a loader or tamping with an excavator bucket to create a tight, dense interlocking mass.
698baef5-c343-577d-9299-a65e16074ad1 | note | Standard / Specification - PS 16.26.5
ee39f4e1-3b8b-52f4-a9cb-33bc90f9b3fc | note | Verifying Document - Site Records
e957a414-4c74-531c-b56c-57f551b56d90 | note | Frequency - During Placement
90fe8e1e-a375-5b1a-a334-ad422b263912 | note | Verification Activity: Activity - R
b539b9ff-a596-585e-a806-26516d17d768 | note | Verification Activity: By - SE
da71f76b-bd7c-5c17-89cd-9727680225b5 | checkpoint | Rip Rap Surface
5f1e2b0d-e565-5efd-a110-952359c99eba | note | Acceptance / Conformance Criteria - Where a surface layer of topsoil is specified, moist topsoil shall be placed over the void filled riprap and compacted to a dense stable state. Prior to placement of topsoil, the riprap placement must be reviewed by the Engineer. Additional topsoil shall be added to any areas that settle.
9398a935-a9f3-5a5f-80f0-724e0860d0b2 | note | Standard / Specification - PS 16.26.9
25b8101c-8806-5440-b28a-cc3c1d4ed0cc | note | Verifying Document - Engineers Approval
1b347d91-2c9c-51a3-83f4-bf61332cb462 | note | Frequency - Prior to placement of topsoil
e4201375-9c05-5a6e-816d-34de73fd873f | note | Verification Activity: Activity - HP
e140971c-ddfb-562d-982d-9310b2a9f581 | note | Verification Activity: By - ENG
304c231e-79f8-5178-b4d8-5bdce6fee5e3 | signoff | AUTHORITY HOLDPOINT
6d8ceccf-7904-55f5-b7d3-d14357d7fe95 | section | 4.02 Establish and Reinstatement of the Temporary Access Track
16795991-583a-5f1d-94f5-87cb4d8c880e | checkpoint | Access Track Design
7fbb9616-dd08-51a2-a1a2-45e885be065a | note | Acceptance / Conformance Criteria - The Contractor shall submit a design of the access track which shall include consideration of runoff, erosion and sediment control measures, health and safety risk assessment to the Engineer a minimum 20 days prior to the work commencing.
b1693b24-fdce-53ad-bdf6-649b944bb45f | note | Standard / Specification - PS 16.27.1
2b18a42e-e6bb-5627-ac49-10b7db186091 | note | Verifying Document - Design
88f39580-4af6-5e94-9820-4f9394791baf | note | Frequency - 20 days prior to the work commencing
bcb1a10a-9699-576f-99c3-02aedec14617 | note | Verification Activity: Activity - HP
13d4c151-3963-5a2b-8df3-d0137e3f0f7d | note | Verification Activity: By - ENG
f8898f0d-a8c4-59c7-bb0e-d99fda5a40a1 | signoff | AUTHORITY HOLDPOINT
193d44b1-49f0-50fd-ac4d-cfa0fdc3a759 | checkpoint | Topsoil Installation
55077c0d-6643-51a5-8540-41549646a546 | note | Acceptance / Conformance Criteria - Topsoil shall be spread uniformly over the areas as defined to a depth noted on the drawings
f940e232-6cc9-5950-902c-04d267b92c88 | note | Standard / Specification - PS 16.27.2.1
d29f04b9-b3b1-583f-9324-8a7cfaab5bb2 | note | Verifying Document - Photos
ccc64612-ab59-5779-991c-4ef2420cab8f | note | Frequency - During installation
405ca296-06d5-5fe4-a089-f4f583ebc7b5 | note | Verification Activity: Activity - D
c60ebc4a-59f9-54d8-ae09-7891f4720ec9 | note | Verification Activity: By - SE
f6b8922e-b6e1-532d-88a2-e657324d53af | checkpoint | Fertilisers
64bf12e2-b108-5ca4-9c93-a2c0344da104 | note | Acceptance / Conformance Criteria - Fertilisers shall be lightly arrowed into the topsoil, 2-3 days prior to seed sowing, at the following rates at 200kg/ha.
bd2cd79c-c6be-5487-8664-3978066f7a72 | note | Standard / Specification - PS 16.27.2.2
ae69b6b6-9892-5473-8589-1ba6429dea67 | note | Verifying Document - Site Records
fc3750c0-478d-5e76-a3b1-aac4b9c621c6 | note | Frequency - Each Sown Area
165115b5-184f-5c36-9042-b8b92e9d61dd | note | Verification Activity: Activity - R
5b0a7c5d-a85c-57b0-a09c-70366dd62d10 | note | Verification Activity: By - SE
248eb036-60b7-52ba-9c8a-4c1ffa1f5ec1 | checkpoint | Grass sowing
9a18c4ca-efd9-5e8a-bf79-12e8818b5f9c | note | Acceptance / Conformance Criteria - The seed mixture shall be an industry standard quality. On large areas the seed shall be “check” sown in at least two directions and surface rolled with suitable flat roller. On small areas the grass seed shall be evenly applied and raked into the soil.
d26ee503-d5b2-56ce-8c87-b07bea3dd59c | note | Standard / Specification - PS 16.27.2.2
d365642f-fa95-5d9f-9366-369f511ed6b3 | note | Verifying Document - Site Records
f7a8fe8c-a89f-5460-b776-52e79dc3816c | note | Frequency - Each Sown Area
fec78116-cf5d-572a-9ab4-c8e0ba4e2878 | note | Verification Activity: Activity - R
6671f776-2f7e-5db9-959d-b41ee6220c5f | note | Verification Activity: By - SE
0052136b-b06c-592b-8996-4770e11c0f01 | checkpoint | Establishment of sown areas
7931ce43-8ee0-5e0b-8375-fbd925c7935a | note | Acceptance / Conformance Criteria - Newly established grass shall be protected from damage by pedestrian and vehicular traffic until grass has reached a self-sustaining state. Grassed areas shall be watered as required to achieve an efficient germination of the seed. Newly grassed areas shall be maintained with regular mowing (90mm-30mm) ensuring that all clippings are removed from adjacent hard surfaces.
068d19c5-48b3-5aff-acc3-e0b3b40222a2 | note | Standard / Specification - PS 16.27.2.2
67cd6c41-a455-57e6-8913-065554992a66 | note | Verifying Document - Site Records
badf1d24-56a8-5d78-95d4-b2c7e26b2eaf | note | Frequency - Each Sown Area
5f3be49a-0fbf-53b8-96b0-13196dcd003a | note | Verification Activity: Activity - R
ad026666-7317-520e-8ed9-40f45fddd4d3 | note | Verification Activity: By - SE
b1606534-eb0d-5f99-8455-683dcea5ac0f | checkpoint | Grassed areas adjacent hardscape
1e7829c9-6b40-5489-aa14-92a8257da9cf | note | Acceptance / Conformance Criteria - All grassed areas adjacent hardscape - such as paths, kerbs, hardstand areas – to ensure base of grass is flush with adjacent path. If base of grass level is 30mm lower or more than adjacent hardstand, grass will need to be removed min 1m back from path, soil put back in, levelled and re-consolidated to spec and grass re-sown to correct level. If less than 30mm top dressing at 10mm each time, over time will be acceptable until the correct level is achieved.
2ccb5f57-f8ca-5012-9ecd-90b5806bb7df | note | Standard / Specification - PS 16.27.2.2
3ad4c87d-991a-5cfa-90b6-fd4092670bc1 | note | Verifying Document - Site Records
dae962da-301a-5401-9fdd-9edce7efad11 | note | Frequency - Each Occurrence
0783823f-80a0-5d26-b72e-ad61f8786da9 | note | Verification Activity: Activity - R
39caa455-f072-5878-888c-89fbb3df86df | note | Verification Activity: By - SE
2a2bc01b-3b96-538d-8ae8-5a096ed1a968 | checkpoint | Slope Area Preparation
c15a7c76-d434-5bdf-8fa8-a2bda025422c | note | Acceptance / Conformance Criteria - In all sites, except natural gully systems, where the slope gradient is steeper than 1:3 (one metre high by three metres long), it is preferable that the embankment is either scarified or grooved on an angle to a depth of 200mm, from the top of the bank to the base. This assists topsoil adhesion and prevents separation of the top 150mm topsoil from the base material due to gravity and/or glazed/planning of base material.
476c655f-2a61-56b8-a12e-2dabfc2d93b1 | note | Standard / Specification - PS 16.27.2.2
4c6c57a7-e08f-57b0-bbb9-4950714390a7 | note | Verifying Document - Site Records
0f8c0a5a-eeaf-5393-b745-bd4c06b61b90 | note | Frequency - Each Occurrence
bc7d4b0a-24aa-5c30-9d22-9cdd6d7145d9 | note | Verification Activity: Activity - R
9e0b454a-7951-5dba-a87a-077d50dfdd41 | note | Verification Activity: By - SE
9de879fd-4193-5e0d-a8a1-ea2d71db4c3e | section | 4.02 Directional Drill HDPE Pipe
d086fda2-3686-5097-a3aa-373176e7b186 | checkpoint | Methodology Statement
a48f8260-00f1-559f-88c7-5f2219bd14e4 | note | Acceptance / Conformance Criteria - The Contractor is required to submit to the Engineer a Methodology Statement that addresses the requirements of the process covered by this Standard Technical Specification.
e834a856-bc0e-5293-8bd2-3d731ac3925a | note | Standard / Specification - T-EES: 04311 - 3.3 PS 16.28.4
e8b7e0d3-c5cb-535e-869e-b1e46d67d80e | note | Verifying Document - Approved Method Statement
d87242a7-7e1f-5bca-bce3-ab23dc442bd3 | note | Frequency - Prior to Works
692df271-7a2a-55ab-a372-e140aa8ec015 | note | Verification Activity: Activity - HP
e0c9bde5-3032-5890-a82a-8917fa1061be | note | Verification Activity: By - ENG
3aadb200-b802-5da6-b21e-743e0d56f5f1 | signoff | AUTHORITY HOLDPOINT
bfefc48c-e917-5f52-8f75-8dac1364f9c5 | checkpoint | Ground Investigation
f3468348-a5ba-56e2-b82d-d0f36be3d1a1 | note | Acceptance / Conformance Criteria - Carry out additional ground investigation as necessary to confirm the feasibility of the trenchless method proposed for installation.
abf824d8-f3c4-55e1-8b1d-9075c5e4f028 | note | Standard / Specification - PS 16.28.5
e3a2625a-5f79-539f-90a9-aeadb2181e46 | note | Verifying Document - Report
32e48347-b3b9-5e6d-a99a-67036c2fe778 | note | Frequency - Prior to Works
28f7eb63-275c-5dcb-8970-8afcc7e38377 | note | Verification Activity: Activity - HP
098c7399-c558-5ab4-8807-eae9afc01f7e | note | Verification Activity: By - ENG
119e165d-5071-5386-84cd-edc660281e33 | signoff | AUTHORITY HOLDPOINT
d60a83e4-576a-4a52-88ad-a1003be603b7 | checkpoint | Pipe Jointing
acbd0f20-ef41-5edf-b908-a34f15130f3e | note | Acceptance / Conformance Criteria - Join PE pipe sections by butt fusion welding, in compliance with Section 3.2.2 of T-EES 04311. Remove all external and internal welding beads. Clean dirt and loose material from the pipe and examine it for any damage to the surface before drawing it into the reamed hole.
18f32434-3631-5b40-a4ca-d7f782014bda | note | Standard / Specification - PS 16.28.6 T-EES: 04311 - 3.2.2
04cd9ace-a35b-535b-991f-d6880e5e3e51 | note | Verifying Document - Welding Records
3bc1ba1f-e087-5d32-a112-c22ecdbc6cef | note | Frequency - Each Weld
b47ab1f5-9153-51f0-8b0b-f120e2d7c46a | note | Verification Activity: Activity - R
35d2e19d-6c3f-556c-b32e-b37be74d926d | note | Verification Activity: By - SE
8b7ea74c-84c7-54f7-82c1-2a3b516259ea | note | Comments / Closeout Details - Review if Internal beads need to be removed
2311c517-d5bb-5111-8f33-9216695a3c7c | checkpoint | Pipe String Inspection
45c79602-d7df-55a7-a1a8-b2266b2cbd2c | note | Acceptance / Conformance Criteria - Prior to being drawn into the back-reamed hole PE pipes are to be welded together to form a continuous “string” using a butt welding process. The pipe string to be installed is to be fully assembled and inspected by the Engineer prior to commencing the installation.
d42b4621-f81c-5715-92c3-482897e6662f | note | Standard / Specification - T-EES: 04311 - 3.2.2
b2b48af0-cc77-5c7f-9fd4-8ce9f44c6aa5 | note | Verifying Document - Engineers Approval
c1640d4c-bd44-5d13-bb21-7ff1ae7d3988 | note | Frequency - Each String
77fa212c-b3bf-510e-9a26-87e401d6d718 | note | Verification Activity: Activity - HP
73acedf1-a6d0-507e-a7bd-51317961ea23 | note | Verification Activity: By - ENG
2cfadaff-5425-5cf2-9f3d-d5b0598bf910 | signoff | AUTHORITY HOLDPOINT
b4fffcb9-d7e1-503f-a50d-4a62f28f044b | checkpoint | Weld Identification
daa2d026-066d-5d90-9450-19f207441f03 | note | Acceptance / Conformance Criteria - Each weld is to be positively and uniquely identified (including the welding operators code) and the printout generated by the welding machine cross referenced and retained. The location of each weld is to be recorded so that its installed position can be identified.
3f4c1cb1-4da0-5f76-807a-6ff4ed8ddeb0 | note | Standard / Specification - T-EES: 04311 - 3.2.2
cd3bf394-c462-55a1-9d3a-f843ff5fe864 | note | Verifying Document - Weld Records
b7496382-d67a-584a-9def-056f69769899 | note | Frequency - Each Weld
e6a629ee-c832-53f2-821e-02bdd17d24fc | note | Verification Activity: Activity - R
3777a7c3-8e04-5229-baa9-3ade0dba89df | note | Verification Activity: By - SE
1a050a0c-9bdb-58e8-ab42-3f65c9ec4308 | checkpoint | Weld Testing Pre-construction Welds
994f2e24-a71c-50f9-b5a5-3e0fb62c36ea | note | Acceptance / Conformance Criteria - The Contractor is required to perform specimen welds observed by the Engineer. At least 2 complying welds are to be completed for each pipe size. These welded joints are to be tested prior to commencing drilling and installation of the pipelines.
c55bcd44-90f8-5f5c-93b7-3e4b07751c42 | note | Standard / Specification - T-EES: 04311 - 3.4.1
f563db49-d504-536f-a22f-1473a47c587f | note | Verifying Document - Weld Reports
1d350f05-3d32-55a8-9962-389a62b5bdbd | note | Frequency - 2 welds per pipe size prior to works.
44474f30-017f-5274-86d2-0fbe2f6d0375 | note | Verification Activity: Activity - I
9ce580ac-f038-5947-9395-4d01952718c5 | note | Verification Activity: By - SE
a516ee9e-d6ef-54e3-9f33-6fe6ccc4e9d9 | checkpoint | Weld Testing Production Welds
45e32826-9120-531d-a78c-ab32adf0089c | note | Acceptance / Conformance Criteria - The Contractor is required to perform specimen welds observed by the Engineer. Further weld tests are required at the rate of 1 % of welds completed on each size of pipe.
e307c95b-d16e-5c35-afa0-a924217db28c | note | Standard / Specification - T-EES: 04311 - 3.4.1
142bee60-c616-5a22-a0b1-f5172aeb271b | note | Verifying Document - Weld Reports
d7836efa-ac8d-55ba-982e-d5e7ae3ad180 | note | Frequency - Every 1 in 100 welds for each pipe size.
75bf1276-553b-5507-8462-77caad3d4956 | note | Verification Activity: Activity - I
2913594e-fecb-509e-b0e0-fde010eeabd0 | note | Verification Activity: By - SE
c8cf5f6a-b5ae-5019-a847-85c20074f259 | checkpoint | Pipe Damage Inspection
cd547f3a-5930-5988-a41b-1e5c6215d25a | note | Acceptance / Conformance Criteria - Check each pipe for notching and gouging. The maximum gouge depth is 10% of the pipe wall thickness.
87a5ce04-f126-5a05-8052-87852b315d81 | note | Standard / Specification - PS 16.28.6
c8236799-ab0e-5521-883e-d52b1c327c8f | note | Verifying Document - Site Records
0ce145e2-f2ab-520c-b52b-4d08f9533c87 | note | Frequency - Each Occurrence
7f795884-c563-51cd-bcf5-3aa5af7c8c41 | note | Verification Activity: Activity - I
27df8d00-d2e0-5ba6-8a54-78c9160ccf54 | note | Verification Activity: By - SE
d2f45598-31be-513f-8c5c-532fbdccb7a8 | checkpoint | Bolt Torquing
b07f5e38-af42-5f4d-91ce-8149a331417e | note | Acceptance / Conformance Criteria - The bolts are to be inserted and tightened following an appropriate methodology.
a911b2ad-3795-517d-9367-f0e3d4e5d130 | note | Standard / Specification - T-EES: 04311 - 2.3
b9d8a2df-d287-54fb-bb4d-b65a665e9420 | note | Verifying Document - Torque Sheet
b7ceaffb-8aeb-522d-9058-f7b3bfb5c91a | note | Frequency - Each Flange
b5f02eb1-1675-5731-964f-b106b5d89660 | note | Verification Activity: Activity - I
f912b38f-7ddb-5242-8d16-7e2b2503bbf3 | note | Verification Activity: By - SE
3bdb746d-3678-5622-853d-b095118a9d8e | checkpoint | Denso Wrapping Joints
f6990fb9-fca7-5a8d-9a94-9b8c5385ca5d | note | Acceptance / Conformance Criteria - Where the flanged connection is to be buried the completed connection is to be wrapped in Denso Tape before backfilling.
8faf269c-bb85-5303-9203-0c8d5c45469c | note | Standard / Specification - T-EES: 04311 - 2.3
173744c7-b63a-54ab-9242-15e9b93eaf99 | note | Verifying Document - Site Records
b372dd24-ecb2-58b1-a9ef-29848e62c851 | note | Frequency - Each Buried Fitting
e9167a22-3c1c-5abf-90f1-e8e2e7f31a8b | note | Verification Activity: Activity - I
d1b7616b-3dcc-5743-a188-3270d0e9e476 | note | Verification Activity: By - SE
dc1fdd4f-9bc8-5c62-bbc8-d56dd23fb5dc | checkpoint | Grouting
8dc53b3c-606d-50cd-b370-be00269007ef | note | Acceptance / Conformance Criteria - Seal the reamed annulus around the pipe with grout for a minimum distance of 500 mm from the outside face of the launch and reception pits.
c6c12c55-81f6-5a09-910c-e4a3a4574c1a | note | Standard / Specification - PS 16.28.6
9ed58e51-0f02-5383-a55c-1525e27e8fe0 | note | Verifying Document - Site Records
bb077ad1-194f-5c83-9b50-2e719a992e97 | note | Frequency - Each Occurrence
a5beb13a-0604-5f72-826b-cda11a869183 | note | Verification Activity: Activity - I
530c8d80-0a77-521d-ba4b-50b7dabc01a5 | note | Verification Activity: By - SE
cefa2f0c-0f24-58f6-a2b1-05d6a5a5908d | checkpoint | Post-Installation Inspections
6c7b8a12-6191-55eb-8937-4a6b2e7c80de | note | Acceptance / Conformance Criteria - The Contractor is required to cause inspection of the pipeline after installation and measure the ovality of the pipe. Deviation from circular greater than 7% of the nominal diameter of the pipe is unacceptable. The Contractor is required to inspect the interior of the installed pipeline using CCTV. CCTV Inspection Reports are to record the location of all laterals to an accuracy of +/-0.1m.
4c867859-ae8c-5fc9-acf9-52d7137f1e5d | note | Standard / Specification - T-EES: 04311 - 3.4.2
5e4d3e69-278f-5312-8fb1-bb9b5d69a978 | note | Verifying Document - CCTV Video and Report
c9261406-4268-532c-ac61-a5f9d352a50b | note | Frequency - Each Pipeline
50e4c336-eb70-57d4-96a1-56cc680ee1a1 | note | Verification Activity: Activity - I
4ca824e0-326a-5096-be22-04d464001b80 | note | Verification Activity: By - SE
1bfbe8f2-b0c3-572e-b37f-155333c26424 | checkpoint | As Built Records
ec695000-04cd-55b6-9eac-8eb0f4a5cc38 | note | Acceptance / Conformance Criteria - Prior to acceptance as-built records of completed sections of installed pipeline shall be submitted to the Engineer. The format of the as-built records shall comply with specific requirements of the Contract Specification.
c1af57d7-ad67-52e8-aafa-eae8fb1780a7 | note | Standard / Specification - T-EES: 04311 - 3.4.4
53764de8-7e0c-54eb-a73d-2e130584bed0 | note | Verifying Document - Survey Records
06d0524e-e752-5f67-b80a-ab5b564e3681 | note | Frequency - Each Pipeline
6af55e44-d99c-5724-b89b-e9bbf9ce37b6 | note | Verification Activity: Activity - I
28e68d6f-a7d4-51a2-82ad-fa9fb7c43a7b | note | Verification Activity: By - SV
d77e77ee-702a-5428-9219-e59cb5dcc629 | checkpoint | Pressure Test: M5 Water Loss Method
c3bedec0-f167-5018-a159-b58140dc9c05 | note | Acceptance / Conformance Criteria - Pressure testing of mains 355PE and larger to be M5 Water Loss Method. The final tests are to be witnessed by Council prior to the pipe being connected to the ‘live’ network. No further connections will be permitted after this stage.
5e041584-abcd-5504-a227-71246c53c72f | note | Standard / Specification - ASNZS: 2566.2 T-EES: 04311 - 3.5
cfc7b15d-c977-51dc-a2d0-a3f0e81dd1de | note | Verifying Document - Test Report
6b5b34e2-37b0-58b2-aee6-2d7a1ff54f6d | note | Frequency - Prior to livening of new main
77578056-8adb-5a7a-9879-eb1fe7d062ae | note | Verification Activity: Activity - HP
e15df05a-5678-560c-a56e-052db7ec995c | note | Verification Activity: By - ENG
0be03369-e888-53c0-94f2-7149a1ff9fd6 | note | Comments / Closeout Details - Do we need to pressure test gravity lines?
d3d0d53e-a3e5-5672-a164-ff5e92c2911e | signoff | AUTHORITY HOLDPOINT
ec6ed3a5-6407-59be-9bf0-f6c5d627702d | section | 4.02 Swales
ea1e09eb-ee7d-57c9-80c9-7d9343a2f15e | checkpoint | Swale invert
b47f3cfa-3dcc-52b2-ae0c-297f22438958 | note | Acceptance / Conformance Criteria - Swale invert shall have a uniform gradient and the line and level at any point shall not vary by more than ±20mm from the vertical set-out position and ±50mm for the horizontal set-out position
34c33a74-91da-5522-8ac6-40cc1852c612 | note | Standard / Specification - 16.34.4
7a408ab7-397b-5778-937a-5afd4807ed9a | note | Verifying Document - Survey
bec33a4d-7469-534a-8552-e23bc791b95c | note | Frequency - Each Swale
b9a8d66a-f5fc-50fd-b2a7-e7b4903440f0 | note | Verification Activity: Activity - I
d4e6dc14-2b32-5b53-a665-9ed80c407b8d | note | Verification Activity: By - SV
df086965-0a15-5163-aa28-88f5195b0d26 | checkpoint | Swale batters
647ace2b-4c30-56fe-8748-66a462df6cb5 | note | Acceptance / Conformance Criteria - Swale batters shall be uniform slope and the line and level of the top of the batter shall uniform slope and not vary by more than ±50mm from the vertical set-out position and ±50mm for the horizontal set-out position.
d7b9f932-c24d-5c48-964b-9bb51f623666 | note | Standard / Specification - 16.34.4
09507e9d-0631-5054-b30c-51cba6ec0769 | note | Verifying Document - Survey
b287c8d2-2de9-52ab-af08-39a65797a436 | note | Frequency - Each Swale
11b6a12f-167f-59f7-a311-8ea5ed1e19e0 | note | Verification Activity: Activity - I
dd91b875-e855-5f20-89fc-aa35f8452ad0 | note | Verification Activity: By - SV
be4660c4-c5bb-5f02-b5cf-7b023833b53f | checkpoint | Grated Trench Drain
ad9b10b0-fa5a-55b7-b4e7-429605fe5eef | note | Acceptance / Conformance Criteria - Grated Trench Drains shall be installed as per Manufacturers specifications
55c5cdb7-ac10-5881-98f9-8de7bdfcaec9 | note | Standard / Specification - PS 16.34
ed58d2bb-9777-5e12-83d2-f88e0e9d537e | note | Verifying Document - Site Records
00da04c0-88be-5898-ae6f-e826e0cc80ea | note | Frequency - As per manufacturers specifications
f8a634b8-a4fd-5f3e-a6e2-5677b951f6d8 | note | Verification Activity: Activity - R
ab91de1f-af8c-55ef-8bcc-57c0af554f76 | note | Verification Activity: By - SE
8de3213b-19c1-5c4d-8b80-96d3eb2c434f | section | 4.02 16.35 CCTV Inspections
4cd04adc-e1de-589c-8883-919f2a404e4c | checkpoint | CCTV stormwater pipe
c04f3331-f93a-5a01-8eb6-6cf3802ff895 | note | Acceptance / Conformance Criteria - Every stormwater pipeline 300mm and greater shall be inspected by means of CCTV camera at the completion of each pipe trench backfill and compaction and at the completion of Earthworks operations (or at a time otherwise agreed with the Engineer).
693453fb-d2c1-56a6-bafe-182d9d2e48d6 | note | Standard / Specification - PS 16.34, PS 16.35.1
5e83ce3d-9965-5bc3-ba48-a63788203396 | note | Verifying Document - CCTV Video and Report
f7cc6427-0691-5b80-b996-8f6ccd759681 | note | Frequency - At completion of pipes laying, backfilling but prior to final surfacing (Pavements, etc.)
74bd3db3-2ccb-5542-a122-f862a9bbfa40 | note | Verification Activity: Activity - I
ccb52201-0d84-5d5b-816c-fdb76a1a4276 | note | Verification Activity: By - PE
769721ef-252d-554f-ba83-68ab6229b47c | checkpoint | Pavement Construction CCTV Review
13f8dd7c-d32a-55e4-87c7-e6cceffc30ac | note | Acceptance / Conformance Criteria - Prior to pavement construction, The Contractor shall submit the pipe condition inspection report to the Engineer for acceptance. The pipe condition inspection report is to be based on CCTV for all pipes upon completion of backfilling the trench.
60d84bd0-e2d3-54ad-8034-bf93d0c1781c | note | Standard / Specification - PS 16.37
45a9de80-2469-5d54-8b82-11f135111826 | note | Verifying Document - Engineers Acceptance
ec06197e-1058-56c0-87d1-5fc069c47ce2 | note | Frequency - Prior to pavement construction above Stormwater pipelines
87ae84e8-7caf-5af7-a64d-c5734e6e8593 | note | Verification Activity: Activity - HP
3f1ed2b1-3f91-561e-80be-6806fff96b7d | note | Verification Activity: By - ENG
159177bb-b619-5419-b76c-f49bb808cf1e | signoff | AUTHORITY HOLDPOINT
8e5eed1a-d752-55a8-99a4-75b5937fac3f | section | 4.02 As Built Records
929e3bd0-176f-5e9a-8dcf-79b0ae77e2ef | checkpoint | Survey Requirements - Stormwater Systems - Underground:
81ccc27d-bd03-5875-800a-b25b40bd4777 | note | Acceptance / Conformance Criteria - The following items shall be recorded for asbuilt drawings.: Trench invert. Pipe/structure bedding and backfill compaction. Pipe/structure size, class, alignment, and level. Manhole and catchpit position, levels (lid and inverts). Outlet structures including position, levels, erosion provisions and fish passages.
a9f688c4-0d9d-5032-9905-25669c41d4d8 | note | Standard / Specification - PS 16.33
96231d52-634a-51f4-b980-ab099d6baa31 | note | Verifying Document - Survey
f9b19b78-0fc7-5dfc-ab39-320c38775bdd | note | Frequency - All underground Stormwater Systems
12cfdf16-64ce-52e6-a712-fe2ddfe8ec04 | note | Verification Activity: Activity - I
d46f3a40-e9da-58ff-b482-3197a2b88140 | note | Verification Activity: By - SV
9a0cb30a-21fa-5ad1-a02a-88a16caa0c7f | checkpoint | Survey Requirements - Stormwater Systems – Above ground:
101e59c8-8481-568a-b243-0240c168674a | note | Acceptance / Conformance Criteria - The following items shall be recorded for asbuilt drawings: Treatment swales, wetlands, basin’s location, profile and grade. Diversion Drain location, profile, and grade. Trench excavation and invert. Line, levels and grade of kerb and channels. Rodding eye locations.
1339ec29-d717-5bf6-bc8a-eed52f696a39 | note | Standard / Specification - PS 16.33
c536036a-eaeb-55dc-8251-cacc831cbdcf | note | Verifying Document - Survey
1d3e1f01-020f-5086-acd7-ae27b15dd3fa | note | Frequency - All above ground Stormwater Systems
fd22d94c-8f7a-5a55-b87f-f7bc8e1058f4 | note | Verification Activity: Activity - I
daf4400c-725e-5f8d-8f00-d8b9ddf23710 | note | Verification Activity: By - SV
c97cdc40-e806-4931-8e06-fa5aec13708d | checklist | ITP - Stormwater (Infrastructure) - 203 - Rev B | itp | ITP - Stormwater (Infrastructure) - 203 - Rev B
01481da8-fe46-46c6-b6f1-c7a504fd241f | section | 1.01 Stormwater Rip Rap Materials
b0080958-183a-49b8-a359-6c77e8f3d81d | checkpoint | 1.01.1 - Rip Rap Rock Source Properties
ed51c520-efd0-5f23-b1b4-3b02d1c4d22c | note | Acceptance / Conformance Criteria - The Riprap Source shall be tested for Point Load Strength, UCS Rock, Weathering Index, Crushing Resistance, and Solid Density.
69968595-06e7-598e-b9f2-665fdb3ac983 | note | Standard / Specification - PS 16.8.3
461ffacf-96c2-59b6-91df-a67b56e2ee6d | note | Verifying Document - IANZ Lab Reports
11fc442a-b136-59c9-a806-744496c34e9c | note | Frequency - 1 per 1000m3
7c06af41-028b-5caf-b9a7-2f9a2e2ab8fb | note | Verification Activity: Activity - HP
8280b98b-c4f0-5ae4-a1c2-bc041daccfdd | note | Verification Activity: By - ENG
6bf49825-1a92-4f93-a4ff-d0560e658a05 | signoff | AUTHORITY HOLDPOINT
9e7b69ff-ae61-487b-9174-93aeaed2a9db | checkpoint | 1.01.2 - D50=150mm RipRap - Grading
49e3caaa-4bb8-5a5a-9cb5-785c054978c9 | note | Acceptance / Conformance Criteria - The D50=150mm RipRap grading for the drainage design shall be in general accordance with Auckland Council Technical Report TR2013/018
61a58a57-2ca9-526b-b672-c89973310d9f | note | Standard / Specification - PS 16.8.3
934af831-c489-560f-bcd7-4431640cfd53 | note | Verifying Document - IANZ Lab Reports
92aad84e-6604-57be-9537-7fa055d304e1 | note | Frequency - 1 per 1000m3
960d05c6-0dac-5195-b2bc-bc6a2682ae10 | note | Verification Activity: Activity - HP
8be0ce6a-3702-524c-befa-c9cd7a8873d8 | note | Verification Activity: By - ENG
0a0ac000-571f-4010-9547-4441cb8a2bed | signoff | AUTHORITY HOLDPOINT
8414e82c-a52d-44ce-ad3a-004b0b6b507b | checkpoint | 1.01.3 - D50=250mm RipRap - Grading
938c8c63-8368-5530-844b-42ed9009cf45 | note | Acceptance / Conformance Criteria - The D50=250mm RipRap grading for the drainage design shall be in general accordance with Auckland Council Technical Report TR2013/018
ce99ee5e-e318-57b7-9361-3b6ab206b67a | note | Standard / Specification - PS 16.8.3
83345cdf-dd77-5530-ae0c-5443b055e6f1 | note | Verifying Document - IANZ Lab Reports
6a74d5cf-54df-5f08-9607-46defc30e290 | note | Frequency - 1 per 1000m3
56d0f4f6-f362-5a12-bf2b-62e30d651ee2 | note | Verification Activity: Activity - HP
7b2652a1-860c-54b9-b435-435734d42b3e | note | Verification Activity: By - ENG
20975d45-040b-4743-8c7c-970580eea056 | signoff | AUTHORITY HOLDPOINT
904ea5a9-dfec-40ea-91e2-c2cd488dfaae | section | 1.02 Subsoil Drainage Materials
1be206e8-0832-4215-9f45-e256275171c4 | checkpoint | 1.02.1 - Subsoil Drainage Pipe
e329b63c-1a81-585b-b910-6a746319a8dd | note | Acceptance / Conformance Criteria - Pipes shall be high density polyethylene (HDPE) smooth bore perforated corrugated plastic pipe as shown on the Drawings and shall comply with the requirements of NZTA F/5.
af2760b4-a0e4-5564-8426-3fa2de9b5328 | note | Standard / Specification - PS 16.11.1
df6dd9ad-bd89-5880-8545-c4c9fa68d2a2 | note | Verifying Document - Datasheet
84b7f776-bfc1-52d5-bd63-14c8526c6a26 | note | Frequency - Prior to use
1486c484-2ee4-5425-946c-c25c43b5fd6c | note | Verification Activity: Activity - R
4c2e6c5e-fcdd-55fd-a235-08bc46e47856 | note | Verification Activity: By - SE
334a27e1-2dbd-4c2f-9341-382c0b745f1a | checkpoint | 1.02.2 - Filter Material
8fec64a0-0167-577e-b08a-4243b2fcd83d | note | Acceptance / Conformance Criteria - Filter material shall be placed around drainage pipe as shown on the Drawings and shall comprise no fines AP20/AP40 material.
1bde53aa-20a1-5350-ab67-2d21f9250675 | note | Standard / Specification - PS 16.11.1
9fc309e7-01cd-5cdb-8b31-4cfbcd7c7958 | note | Verifying Document - Datasheet
d32c2d74-9f54-5b21-858d-b9f855629953 | note | Frequency - Prior to use
e7a6b74b-0c95-5bf2-bd7c-ed7a45ddf5b9 | note | Verification Activity: Activity - R
87542a28-6fd1-52bb-8229-36dac650de5e | note | Verification Activity: By - SE
a5045a29-f993-40f4-a604-4f5c4399a88e | section | 1.04 Stormwater Geogrid and Geofabric
fe35b0c2-4fdf-4cef-bacf-cc050800991b | checkpoint | 1.04.1 - Geofabric
64bacd62-db26-5e45-bc4d-7a320152a0fe | note | Acceptance / Conformance Criteria - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval at least two weeks before commencement of the works.
9f94f8b0-3c43-5d0c-b0f1-7cdac66c26fa | note | Standard / Specification - PS 16.29.2
46f20516-fb72-5952-8826-9aa17bdcd48e | note | Verifying Document - Datasheet
65e57ff7-1909-5ca7-acd1-a134a9f75bb0 | note | Frequency - Prior to use
9344cbe3-c963-5953-a421-85176c5cd731 | note | Verification Activity: Activity - R
9bc5ea42-7ed3-5228-936e-a8c962e1bd3f | note | Verification Activity: By - SE
bc1fabf2-8958-47e5-93f6-8a52f65079e9 | checkpoint | 1.04.2 - Biaxial Geogrid
abdecd59-daf1-5540-af0b-43ff6b2cab6c | note | Acceptance / Conformance Criteria - The biaxial geogrid shall be manufactured in accordance with a management system which complies with the requirements of BS EN ISO 9001, BS 14001. The Contractor shall submit the full details of the geogrid they propose to use for approval at least 2 weeks before commencement of the works.
9caa7e88-2243-5514-8413-49d5e3f220be | note | Standard / Specification - PS16.29.3
d5f92006-a169-5c0c-889d-cca87ad1d6b5 | note | Verifying Document - Datasheet
3544734c-e7b3-5ec2-a23a-49f61d26bfa2 | note | Frequency - Prior to use
4dd3472a-ac68-56ce-bfb1-dd5b460dd04b | note | Verification Activity: Activity - HP
922a7503-415d-5399-afe2-62e78aefadd7 | note | Verification Activity: By - ENG
0a634b94-a8b1-423e-afad-ad964255e67b | signoff | AUTHORITY HOLDPOINT
779e5a60-40a7-48ca-a7e3-ef83a1dbf1ce | section | 1.05 Bioretention Soil Media
1791e0ed-67ca-4055-ac43-c11778f1cd96 | checkpoint | 1.05.1 - Bioretention Soil Media.
1ee2d439-a201-565e-a6ed-ddaad5429063 | note | Acceptance / Conformance Criteria - Test results for soil filtration media material properties are submitted to the Engineer including ASTM F1815-06 test results, pH, clay content, organics content and material grading curve.
02725417-dfc9-54cf-babf-a175005c2274 | note | Standard / Specification - PS 16.38
f61d712f-7654-5403-9198-c5cd00cc4906 | note | Verifying Document - Datasheet
9684a641-c1b7-56eb-bb84-22e8a785e407 | note | Frequency - Prior to installation
d3db63fe-ef58-543b-8911-b23e83542b15 | note | Verification Activity: Activity - W
161435cf-49ec-567c-b315-a46cf32217ba | note | Verification Activity: By - ENG
13fc025e-b0f1-4791-91d2-13ba77eab723 | section | 2.01 Services
178c31a9-0cdc-4e09-90f4-c6e4beeb3178 | checkpoint | 2.01.1 - Existing Services
66d0f0cd-29df-5906-be66-8e3abbf86711 | note | Acceptance / Conformance Criteria - The Contractor is required to identify all known utility service crossings or encroachment, within 5m horizontally, of the proposed drainage alignments.
fbcf4875-fc7f-5e58-a154-977595759c15 | note | Standard / Specification - PS 16.5.4
6e82df01-79ba-5e45-b235-ac57b869d035 | note | Verifying Document - Survey Records
16f4b699-d83c-5bf6-83c7-05ae54252d0e | note | Frequency - Prior to excavation
87c87f35-1947-5d02-8a53-58e03b68a85a | note | Verification Activity: Activity - R
61861e83-e38f-5f1f-b0d9-b52f452f2032 | note | Verification Activity: By - SE
9d376dc2-ff54-4bf2-aa7c-3b510572a23d | checkpoint | 2.01.2 - Service Support
801b1901-bd66-506d-b1bd-4352be056f53 | note | Acceptance / Conformance Criteria - The Contractor shall support all existing services affected by the works whether these services cross-or are located alongside the excavation.
3a608ab2-f424-569f-a74b-26a01a878439 | note | Standard / Specification - PS 16.5.4
6292847d-15dd-50c7-be04-e7096244a3bc | note | Verifying Document - Site Records
05e96bea-b5af-5c89-9138-5a8c95edf34b | note | Frequency - Each Occurrence
0f12c3d6-1f05-5e14-aa94-b0a6634fa2c6 | note | Verification Activity: Activity - R
cb4af978-483a-55af-9ab9-b1a0ec31fedc | note | Verification Activity: By - SE
8c810b6d-b76a-44e0-9d88-0912c7ba7acd | checkpoint | 2.01.3 - Utility Operators Approval
16e785e7-7a2e-5969-a0d3-090445d9f025 | note | Acceptance / Conformance Criteria - Prior to commencing with any construction, the Contractor shall Obtain written approval from the relevant Utility Operators for any construction activities within the vicinity of their service(s).
8a0e4fed-4502-5e61-a815-4345a7c8bc05 | note | Standard / Specification - PS 16.5.4
9fa401fc-fd0d-589d-9918-a7a3792f3e1d | note | Verifying Document - Written Approval
37360898-8217-5a1c-bbd8-694634cad343 | note | Frequency - Prior to commencing with any construction
6cbacad2-7c41-5d82-a198-ab99289fff94 | note | Verification Activity: Activity - HP
0ca93492-e25f-5559-8259-81100788d664 | note | Verification Activity: By - ENG
5640f115-2505-466f-b489-e04bd02499c5 | signoff | AUTHORITY HOLDPOINT
eac1dc0f-07ab-4666-b424-b9444ef40156 | checkpoint | 2.01.4 - Utility Operators Requirements
958f4b4d-9f44-56be-a6ff-ce1887eba5d9 | note | Acceptance / Conformance Criteria - Prior to commencing with any construction, the Contractor shall Undertake the construction activities within the vicinity of the service in compliance with the with the relevant Utility Operator’s requirements.
a557dbb3-92dd-5f85-b72a-a29c6a2ddfb8 | note | Standard / Specification - PS 16.5.4
433320ab-d892-5470-becd-8453655bea7a | note | Verifying Document - Site Records
8fca1b9a-bbef-5df3-98be-cd502bbb20db | note | Frequency - Prior to commencing with any construction
403494d8-14ba-5d63-8a96-7540106c25b6 | note | Verification Activity: Activity - HP
e34f5205-8239-5ea7-a30c-b33ddf6e6089 | note | Verification Activity: By - ENG
72ade9f0-d5e9-4557-b242-1f113d1b6e5b | signoff | AUTHORITY HOLDPOINT
449c844d-c065-4ab6-874c-e5eed127370d | checkpoint | 2.01.5 - Protection of Pipelines / Structures During Construction
8ecad00b-3292-5653-b7da-1ac2b50a52ac | note | Acceptance / Conformance Criteria - Where construction plant is required to be operated over pipelines Table B1 of AS/NZS 3725:2007 shall apply in determination of the minimum depth of fill (cover) required. A temporary embankment, extending not less than 15m on both sides of the pipe/culvert, shall be used to provide the necessary cover.
391e6af5-6965-5702-8f4e-60133425aaab | note | Standard / Specification - PS 16.5.5
fe128e4b-6036-56be-b7df-9cc1aa735319 | note | Verifying Document - Site Records
461e579d-0724-53a9-8dc2-8bd2a298e6ee | note | Frequency - Each Occurrence
9b72a4b4-0af2-58b6-9721-6df27a9b6a9b | note | Verification Activity: Activity - R
c0e28a5b-5bd8-514a-86fc-e31026d5b438 | note | Verification Activity: By - SE
1def7eac-8bbc-47c1-b9e4-19ed6917863f | section | 2.02 Stormwater General
794e6f21-80d0-4eac-945c-e6dba29f7195 | checkpoint | 2.02.1 - Setout
1bf4a666-9999-5ff6-b922-a5aa744642d5 | note | Acceptance / Conformance Criteria - Prior to the commencement of any drainage works for a particular drainage line, the Contractor shall set out the line, level, and position of the proposed drainage line, including inlet and outlet positions and levels, and present it to the Engineer for their consideration. The Contractor shall provide at least 48 hours’ notice to the Engineer ahead of set-out and allow 48 hours for the Engineer to respond prior to commencing work.
12079106-17a6-5de0-a60b-eb9e54dca9ba | note | Standard / Specification - PS 16.6.1
be379d62-8674-5319-ade0-9e4a6c2dafd5 | note | Verifying Document - Survey Records
84240b8a-fd91-5e5c-ba91-64c248aed718 | note | Frequency - Prior to the commencement
c4d18165-5b58-578b-a4d2-f1a4443fa780 | note | Verification Activity: Activity - HP
34ecccbf-d525-503e-bfae-ccff1f837fc9 | note | Verification Activity: By - ENG
44d35b7e-3d7b-4cbb-8b42-c7750d95ac73 | signoff | AUTHORITY HOLDPOINT
65198a05-3cba-4762-a837-0d99b781db8b | checkpoint | 2.02.2 - Dealing with Water
e9fc66f2-04e2-511f-b49a-b20ffbaf4f7d | note | Acceptance / Conformance Criteria - The Contractor shall maintain all trench inverts free from flowing or accumulated water. Water arising from, or draining into, the trench shall be drained or pumped. Any sumps required shall be refilled to formation level as directed by the Engineer.
91b0dcc5-a393-51e6-8482-49fd75fb95be | note | Standard / Specification - PS 16.7.1
11dc4e4d-1498-5880-9279-23a3d293ce97 | note | Verifying Document - Site Records
b8b9eaa3-ea61-5a24-9611-06aa477a090b | note | Frequency - During Works
478d13df-d3f6-5d97-b61d-ace7d35cd77d | note | Verification Activity: Activity - S
ac42600f-f1f1-5a5b-8f6a-4fa25f5c937e | note | Verification Activity: By - SE
ae0e151b-1061-436d-a497-49d3a300dfa6 | section | 2.03 Soakage Pits and Infiltration Trench
1a5e1723-510e-43b5-9e97-0f917d28cd1e | checkpoint | 2.03.1 - Soakage Pit Sealing
00683922-e8a5-537b-b46c-8cc474d86268 | note | Acceptance / Conformance Criteria - All pipe work penetrations through manhole walls shall be sealed using Epoxy Mortar or an approved equivalent type of permanent sealant.
2609c121-2edb-55b0-bcc0-3d10812526a9 | note | Standard / Specification - PS 16.12.2.2
070334da-4e91-513e-95f1-cb4f0fcd73d5 | note | Verifying Document - Site Records
dd4acbb2-8a0e-5c37-8193-250b82ef080c | note | Frequency - Each Hole
845c8737-8539-5fac-8bd5-a93b861e50e7 | note | Verification Activity: Activity - S
95901f18-3f58-5ea2-8fcc-6b0ff0d13b8f | note | Verification Activity: By - SE
34d9a40c-05a0-4ad2-92cb-39c5d4ce2e14 | checkpoint | 2.03.3 - Soakage Pit Lids
bdf1849d-6051-54de-9052-8e549d5c0e67 | note | Acceptance / Conformance Criteria - All solid cast-iron covers and frames shall be set flush with the cross fall and grade of the surrounding finished surfaces. All grates and frames shall be haunched to lids.
849e2fad-cab1-5a1e-a747-af81594a0a12 | note | Standard / Specification - PS 16.12.2.2
3c49321a-5d3d-5305-8a56-e0f0c1bc63d1 | note | Verifying Document - Site Records
246d81d3-194d-5b4c-8761-2923b5dd7bcb | note | Frequency - Each Occurrence
b0712beb-3ef8-5da7-af62-f07cfb1285be | note | Verification Activity: Activity - S
cd55e1de-3442-5e63-b951-12de650428f2 | note | Verification Activity: By - SE
96e8a663-083c-4143-ba79-486390b38cba | checkpoint | 2.03.4 - Infiltration Trench Excavation
25fc4eee-9ec9-54db-b231-d8a258f07698 | note | Acceptance / Conformance Criteria - The trench/excavation shall be free of roots and projections or obstructions. Where over excavation has occurred, the bottom shall be brought back to grade using excavated material which is only lightly compacted in position to the same extent as the undisturbed surrounding soil. No loose soil shall be left in the excavation after restoration to finished grade.
d731cafe-bcd7-59e4-b88a-468dd5911cdf | note | Standard / Specification - PS 16.12.3.1
edf87acf-3430-5f15-8b0f-898142f59df3 | note | Verifying Document - Site Records
4a7df12e-500e-5a5a-8384-beab695f9cb4 | note | Frequency - Each Trench
f3dcde60-a34a-51af-937b-cf05642817ce | note | Verification Activity: Activity - S
9637d3fd-ad3d-59f8-a5dd-69c6c81984e4 | note | Verification Activity: By - SE
0582c6aa-0b3e-4a44-8653-e497093401c9 | checkpoint | 2.03.5 - Trench Inspection
22f13e6c-e93a-5c48-8b73-bfb68373eb01 | note | Acceptance / Conformance Criteria - All trenches in existing ground shall be inspected by the Engineer prior to commencement of laying filter cloth. Any unsuitable foundation material shall be removed at the Engineers direction.
798f196a-462e-515c-ad36-1ef6a15eabf3 | note | Standard / Specification - PS 16.12.3.1
949d74a6-8fed-59bc-91a9-275b4227e8ef | note | Verifying Document - Engineers Approval
f2a16ac2-1314-58e4-964d-9f1e7b0eeee9 | note | Frequency - Prior to commencement of laying filter cloth
54358963-ffa4-57fb-996a-e80edb8bcd7c | note | Verification Activity: Activity - HP
cdd7bad0-1f7b-5bc9-9457-513a725a0cdc | note | Verification Activity: By - ENG
ff507959-ca21-49a6-a45d-4968c15e3512 | signoff | AUTHORITY HOLDPOINT
8f408c7e-e5b0-44e0-ab5a-b9e546adbf72 | checkpoint | 2.03.6 - Groundwater
6e6a8626-602e-5034-a03c-89f42aaa8291 | note | Acceptance / Conformance Criteria - If groundwater is encountered in the trench/excavation the Contractor shall seek instructions from the Engineer on how to proceed.
8b80298c-d5b0-564f-8226-ec9c8fdc3405 | note | Standard / Specification - PS 16.12.3.1
bd244ebf-a8e9-53b5-bce4-12e0523512a2 | note | Verifying Document - Site Records
258355a4-8526-542b-a70a-4089dd418a7b | note | Frequency - Each Occurrence
44d84eca-9097-56f4-8aa9-6dc2eec4b78b | note | Verification Activity: Activity - S
5405e9ad-2cab-5988-bb7f-eea54c684ac5 | note | Verification Activity: By - SE
730e999c-a36e-4815-aeae-40be2bdb93e2 | section | 2.04 Drainage Media
72cbb0eb-cbec-4530-8075-3364acc7013c | checkpoint | 2.04.1 - Placement of Drainage Media
2acd3876-2814-5294-b4cb-780afb184c79 | note | Acceptance / Conformance Criteria - The drainage media (100-150mm rock) shall be carefully placed in the clean, excavated area after the excavated material has been removed and the excavation site cleared of potentially contaminating material and the excavation lined with filter cloth. The drainage media shall be lightly and uniformly compacted. No mechanical compaction equipment shall be used. The drainage media shall not be placed or lightly compacted if the excavation is flooded or the in-situ soils saturated.
c6852124-32da-59c0-a9f5-463d63a240ab | note | Standard / Specification - PS 16.12.3.3
71b80ea7-f056-5667-b2b9-15c4595b007f | note | Verifying Document - Site Records
5b9d840c-5703-5234-8952-dc94660f1c51 | note | Frequency - Each Area
285c0cb7-d40c-5c76-b99b-b552388573e8 | note | Verification Activity: Activity - S
eb705c9f-64a7-597b-9bb0-796129711ef4 | note | Verification Activity: By - SE
b9cdce42-195d-4b29-a1b0-241493a776cc | section | 2.05 Place D50 250mm Rip Rap
22d8c033-c0d2-4c69-9fe0-f8f01c46ee75 | checkpoint | 2.05.1 - Rip Rap Placement
5768c424-c468-59c2-b62e-e6faeb7c5209 | note | Acceptance / Conformance Criteria - The Contractor shall place D50 = 250mm size rock rip rap in areas shown on the contract drawings and as instructed by the Engineer. The rock shall be placed to ensure rock is tightly knit with no movement.
b48ae758-b97d-56cf-bc8f-fc50f86fa695 | note | Standard / Specification - PS 16.14.2
1bc46f34-4307-5584-8b96-d8f0366f71d9 | note | Verifying Document - Site Records
455f1d20-892d-545d-815d-c2d5c27d6e83 | note | Frequency - Each Area
a1576b3c-8bea-587f-adf1-f8bd8780a144 | note | Verification Activity: Activity - S
98be39bf-ce0d-534e-ba21-6284bbbf801f | note | Verification Activity: By - SE
f4d1aaa8-4c5e-46ea-b4a7-f5c57cf437b2 | section | 2.06 Rip Rap Rock Flumes
e33807d6-da9d-461b-9e64-1b3c1b4b67f5 | checkpoint | 2.06.1 - Rip Rap Placement
301e7606-6281-53da-9821-d00c0a388d17 | note | Acceptance / Conformance Criteria - The Contractor shall place D50 rock rip rap in areas shown on the contract drawings and as instructed by the Engineer. The rock shall be placed to ensure rock is tightly knit with no movement.
0b05b2c2-b1ed-5f4b-9d62-9bb5a7b66d11 | note | Standard / Specification - PS 16.17.2
95b544d6-b499-5aa9-a5b6-ece304c4054b | note | Verifying Document - Site Records
0c4008f0-48d4-5017-bc69-cbf0bebbb5d2 | note | Frequency - Each Area
4517c380-b179-5d66-911b-061ec7a235ce | note | Verification Activity: Activity - S
ba4d4a10-b8be-522a-bd14-8939622b461f | note | Verification Activity: By - SE
502d3200-acb9-49ae-8866-279a798ce736 | checkpoint | 2.06.2 - Geotextile Protection
e681a4bc-1905-551b-9e88-c6f2e5084c1e | note | Acceptance / Conformance Criteria - The contractor shall minimise the height from which rock is placed on order to reduce the risk of damage to the filter fabric layer. Rock shall not be dropped from >0.5m height.
ccd48b56-c766-578b-b820-104b4784af76 | note | Standard / Specification - PS 16.17.2
0b4420af-739b-5d2f-8ae1-2c4db4fb8bee | note | Verifying Document - Site Records
1541100d-4b39-541e-b02f-cbde5b2895da | note | Frequency - Each Area
869c4c25-3f99-5a23-ac99-d9ec198bfb03 | note | Verification Activity: Activity - S
7b2f9106-7935-5100-b94a-910016a92add | note | Verification Activity: By - SE
6bc56b2d-880b-4c8e-b305-877b470980de | checkpoint | 2.06.3 - Face Alignment
49998aa8-b9b3-5a3d-b358-a9a80483cde7 | note | Acceptance / Conformance Criteria - The face of the rock rip rap shall be placed at the gradient shown on the drawings and the termination at each end against existing slopes is to be keyed into and to approximately match the adjacent slope and placed in general accordance with ‘Section 10 Filling’ of TNZ F/1:1997 to achieve a compact mass with minimal voids and good interlock of rock fragments.
d764adbc-a917-5234-b720-73b6edc6dc2b | note | Standard / Specification - PS 16.17.2
33677346-2031-55e0-82b7-6e2c6a42e71d | note | Verifying Document - Survey Records
5fd88c47-4326-5637-b994-c2cf9343180c | note | Frequency - Each Area
83e9594f-d9c5-5f93-bba9-de272ecd86d8 | note | Verification Activity: Activity - S
40341b07-7389-5d4f-96da-53dbfe298ea7 | note | Verification Activity: By - SE
3712abd4-fd03-46a4-bc4e-8277bbf13690 | section | 2.07 Geofabric
84876bf2-1413-44b8-a7a9-61a7f767ef5a | checkpoint | 2.07.1 - Geotextile Filter Fabric Protection
1cf91409-3025-56f8-bb96-b78b48b48834 | note | Acceptance / Conformance Criteria - Construction plant shall not travel over exposed fabric. A minimum cover of 200mm of fill material shall be in place before construction plant is operated above the fabric.
03142beb-318f-5331-b339-b0ae0ca312ff | note | Standard / Specification - PS 16.18.1, PS 16.12.3.2
2713b17e-915f-589b-b87a-e5463d4dce8a | note | Verifying Document - Site Records
ac926be4-8fb9-5e4d-a78f-a34d82588562 | note | Frequency - Before Trafficking
819217b2-6a6f-517d-adef-51f55f95a8fb | note | Verification Activity: Activity - S
987adb1e-b9ee-51a9-868d-cc7ffd0c3bdd | note | Verification Activity: By - SE
d9f2c955-bc0c-41f9-b3e5-89ccf72d367e | checkpoint | 2.07.2 - Geotextile Filter Fabric Lab
f4a008a1-c5ea-59c1-9970-51383ea40069 | note | Acceptance / Conformance Criteria - Geotextile filter fabric shall have a minimum overlap of 500mm at any joins.
7120d9c4-61df-5d4b-a6f3-62987ffaf026 | note | Standard / Specification - PS 16.18.1, PS 16.12.3.2
5f4b56ee-9ec0-5e9f-987e-8df6f50683a2 | note | Verifying Document - Site Records
150f2ee7-e629-58c4-81ca-49bd555c820c | note | Frequency - Each Joint
473f2d6f-73a0-5cb6-9f0b-a68accad246f | note | Verification Activity: Activity - R
eb0630a4-3d65-5877-b10a-734584e11cfa | note | Verification Activity: By - SE
d0b02502-dc5c-4ccc-a184-f9a382da60d0 | section | 2.09 Bioretention Soil Media
b159f758-fd30-49e8-84c0-1a729bc78faa | checkpoint | 2.09.1 - Exclusion Zones (Bioretention and Infiltration Devices)
ea79dbbb-ed04-569c-88c7-a049025ed63c | note | Acceptance / Conformance Criteria - The contractor is to establish fenced-off exclusion zones at the start of the works to avoid plant / machinery tracking and over-compacting bioretention and infiltration device formations such that the hydraulic conductivity of the existing ground is not compromised. The exclusion zone shall at a minimum cover the extent of the device base area.
e8bfbd96-b782-5af4-a671-fec37809e630 | note | Standard / Specification - PS 16.39.1
dd73aa6b-a178-55dd-b8d3-f995192074c7 | note | Verifying Document - Site Records
0b023dcf-fd21-59d0-8b9c-c900bfb4beb4 | note | Frequency - At the start of the works
469776d4-5f7f-534b-9f3d-a54c35ad97fa | note | Verification Activity: Activity - R
cc639aec-651d-5fba-b472-f651ff0ab7d9 | note | Verification Activity: By - SE
075b37ac-3bef-4a57-855a-4e9796253e92 | checkpoint | 2.09.2 - Interface Finish
2915d957-1ede-5dcb-acb8-354e86ef7b62 | note | Acceptance / Conformance Criteria - Bioretention devices operation as it provides a poor interface with the media. A rough finish such as that achieved with a toothed digger bucket is preferred.
b5261bab-fe0d-5304-b197-c4e1c0827ab3 | note | Standard / Specification - PS 16.21
9c78fcd3-a935-56a2-9a74-07a330a1294a | note | Verifying Document - Site Records
6b865f49-b1d1-5379-84c9-8402f5da1fa5 | note | Frequency - Each Device
8ee066f0-602f-535b-9628-1033af3d7905 | note | Verification Activity: Activity - R
594d2c13-f2ea-58cd-ac75-d8a469d93fee | note | Verification Activity: By - SE
01ac164c-942d-4702-8122-ec95db7a123f | checkpoint | 2.09.3 - Suitability of existing soil for infiltration and bioretention areas.
3202869c-357e-50a0-9ea2-e3c4af57c48a | note | Acceptance / Conformance Criteria - Bioretention device and infiltration device formations are to be inspected by the Engineer prior to laying of bioretention or filtration media to confirm the suitability of the existing ground.
4883304a-3b1c-537f-a23f-dc3c68d97f8d | note | Standard / Specification - PS 16.38
b6ac6d71-d89c-58b0-875c-b6b15961618c | note | Verifying Document - Site Records
07e3bb87-796a-5978-8755-5c1368f70b0f | note | Frequency - prior to laying of bioretention or filtration media
e3686de0-2ad7-5efb-92f2-7df1a2b33a5d | note | Verification Activity: Activity - W
0dad7320-670e-51f0-a7a9-be3e448b595e | note | Verification Activity: By - ENG
259135e2-6ae3-4f66-aa59-cb86c3327259 | checkpoint | 2.09.4 - Bioretention Soil Media placement
6322a205-97fe-558c-99a5-498b65a47d5d | note | Acceptance / Conformance Criteria - The soil media layer is required to line the invert of all bioretention devices and placed in a single lift to 50 mm above the finished level. The finished surface shall be reasonably smooth, uniform and free of obvious hollows and humps. Care shall be taken to avoid overhandling the soi
1024781f-a243-5690-8f7e-5160ab736855 | note | Standard / Specification - PS 16.21.1
2d2cdec0-5cd3-5e6e-b691-82e209b85273 | note | Verifying Document - Site Records
86006bf1-bc38-5202-a9fa-d97f8500fbba | note | Frequency - Each Device
6c8b11f3-efaa-50a7-aee9-79e24b92eba9 | note | Verification Activity: Activity - R
13ac8479-46b2-50fb-b520-f6965f9dc46b | note | Verification Activity: By - SE
739913d5-fe38-4c3d-962b-668b1d43fa48 | checkpoint | 2.09.5 - Compaction
82858d27-f26b-5a9f-9b52-84f1c3aede5b | note | Acceptance / Conformance Criteria - The soil media shall be raked without any form of mechanical compaction.
1231bccf-6cfa-5869-b20b-bbb04f2fac87 | note | Standard / Specification - PS 16.21
1cf5299a-d6da-5570-979b-2cfd3a2461ee | note | Verifying Document - Site Records
5f91f41b-02e0-510d-a08b-1b7d46cdaaf9 | note | Frequency - Each Device
4ccd23b3-7b4b-5090-acc4-0fe319def5d9 | note | Verification Activity: Activity - R
8a6e14f0-507d-55e9-bdbf-8c32c8b9a4a6 | note | Verification Activity: By - SE
09e2a9cd-5a5a-4d99-8936-49e0ff56d921 | checkpoint | 2.09.6 - Infiltration testing
2de5f8c9-57ad-500e-bd9d-76abcd0d3070 | note | Acceptance / Conformance Criteria - Once the bioretention devices have been completed, it shall be tested by double-ring infiltrometer for permeability. The rate shall be >50 mm/hr and not exceed 500 mm/hr. Alternative testing means must be approved by the Engineer.
b44e51c0-cc2e-59db-bdcc-fdfc23528ebc | note | Standard / Specification - PS 16.21.1
c6aefa10-d21d-58c9-905b-4502fa069ed4 | note | Verifying Document - Site Records
b1e8af01-930f-5218-ba88-081bd2a36f1f | note | Frequency - Each Device upon completion
b87bf458-2245-5f7d-a602-8a168d60fcce | note | Verification Activity: Activity - I
24d9dc81-20a7-5b42-b62c-2a01d7691403 | note | Verification Activity: By - SE
1ab3f34c-710a-4ea5-b587-aad9ff1c3369 | checkpoint | 2.09.7 - Landscaping Approval
0c21bcd8-386b-5e58-84b8-0da669b2031a | note | Acceptance / Conformance Criteria - Once the media is placed the Contractor shall notify the Engineer. If the Engineer is satisfied with the soil placement, they will advise the Contractor that landscaping can commence. Stabilisation with grass seed shall be carried out within seven days once approval is obtained from the Engineer.
ebb79dd7-e602-5ea0-b3ae-19ba491e8b68 | note | Standard / Specification - PS 16.21
ea56d376-07a3-5441-9870-74010c4c2cf9 | note | Verifying Document - Engineers Approval
6cfb9749-fe8d-521d-831b-4b5844507e1d | note | Frequency - Prior to Landscaping
271201fd-676d-595d-b2e6-166a905f5481 | note | Verification Activity: Activity - HP
41c04bcd-7853-5dae-bdd3-6bce805227f8 | note | Verification Activity: By - ENG
4cccbeb5-8b51-4b30-bfa7-c65ba6827520 | signoff | AUTHORITY HOLDPOINT
80459239-fc8f-4b28-be48-f1f46684725f | section | 2.12 Rock Riprap for Erosion Protection
8a4f4103-6afc-484e-aec6-bc3dd2e7d003 | checkpoint | 2.12.1 - Geotextile fabric installation
291fb202-9852-54e8-b41b-c232517433f8 | note | Acceptance / Conformance Criteria - Geotextile fabric shall be laid directly on the existing ground to protect the liner from damage due to punctures. It is assumed that the existing ground will be sand from the existing geotechnical information provided. If this is not the case the Engineer must be notified to allow for remedial treatment prior to the placement of the geofabric.
682fc2e6-003a-5147-824f-9b747e49f694 | note | Standard / Specification - PS 16.24.6
625821e3-a2c3-5047-bae1-e0f73916972a | note | Verifying Document - Site Records
a3a17cb4-b70b-571e-9621-12d92b36463b | note | Frequency - During Placement
d61a0454-4e80-5212-9ccd-b3337a9452d4 | note | Verification Activity: Activity - R
99a17e33-9554-5f99-8e20-64ccfad25722 | note | Verification Activity: By - SE
95770dbc-e51c-498e-b1ac-59972e9c4515 | checkpoint | 2.12.2 - Impermeable liner installation
a6ad1db3-fe69-5aa3-83b0-a9079f75bf4f | note | Acceptance / Conformance Criteria - An impermeable liner is required to line the entire wetland base and batters to avoid ground stability issues near the gully embankment. Particular care should be taken to ensure water tightness around inlet and outlet structures as per the Drawing details.
4217d30e-0825-505c-9133-826d182bd685 | note | Standard / Specification - PS 16.24.5
f6b61cff-f5db-5f80-b83a-e1ba6e3bd0c4 | note | Verifying Document - Site Records
7dcf4b41-a4ed-5f25-922c-ba3da3d1d2d7 | note | Frequency - During Placement
7f9c4e22-d973-508e-9f52-eb7cc104dc59 | note | Verification Activity: Activity - R
f69ad299-3732-55e5-aae2-e4e1400572b5 | note | Verification Activity: By - SE
d86b24bb-bf5d-4f42-9baf-4ce68c497b4b | section | 2.13 Rock Riprap for Erosion Protection
c7464100-f686-42b7-a5d3-d8d993743a52 | checkpoint | 2.13.1 - Organic Material Removal
bd5f0230-d354-5689-86b3-6f2ff8cc5a6d | note | Acceptance / Conformance Criteria - Prior to placement of rock riprap, all organic material is to be removed, followed by the placement and anchorage of a Class E geotextile (in accordance with TNZ Specification F/7 Geotextile).
d1917709-b988-5fde-9426-7b3ca8e111cc | note | Standard / Specification - PS 16.25.1
9d9c7ee5-0b05-53cb-b86e-0bfbe3d04419 | note | Verifying Document - Site Records
8d87c2e8-25a5-5d5e-9270-9bc2853f475d | note | Frequency - Prior to placement of rock riprap
63f60576-dcb5-5b6f-9b21-1a6d76d93ba2 | note | Verification Activity: Activity - R
d7b7777b-23d3-53d1-92c2-9aa6066d012f | note | Verification Activity: By - SE
4ead4ed0-d695-4381-b3da-bf7d7fe7e2fd | section | 2.17 Swales
6543a3c5-db5c-4840-81f7-a101308ee1d6 | checkpoint | 2.17.1 - Swale invert
1e111f86-2812-5cf0-9705-573043e7a52b | note | Acceptance / Conformance Criteria - Swale invert shall have a uniform gradient and the line and level at any point shall not vary by more than ±20mm from the vertical set-out position and ±50mm for the horizontal set-out position
a9906f95-9b3c-58ca-98d1-46a2c0ea3d3b | note | Standard / Specification - 16.34.4
23a9d150-d78f-5f40-b13a-c477cd7850bf | note | Verifying Document - Survey
229506b9-eca3-5d50-9845-1b396476a60f | note | Frequency - Each Swale
2b0712c0-8c16-5497-acf7-391495473164 | note | Verification Activity: Activity - I
3255ead1-db2e-57cc-a751-ece462a8cef5 | note | Verification Activity: By - SV
5513e339-746c-4707-8da8-63b68a018e80 | checkpoint | 2.17.2 - Swale batters
ff71df35-12dc-5a60-8fa0-58f0c157ea3b | note | Acceptance / Conformance Criteria - Swale batters shall be uniform slope and the line and level of the top of the batter shall uniform slope and not vary by more than ±50mm from the vertical set-out position and ±50mm for the horizontal set-out position.
f0a7d388-a5e0-578f-b009-d1dd568d34c7 | note | Standard / Specification - 16.34.4
95a89954-80c9-54de-8325-36ab8317dd91 | note | Verifying Document - Survey
950c6f2a-726d-5e3c-85f5-1fd1da50002e | note | Frequency - Each Swale
23f2c3e6-f5ea-5985-b250-a37143e52f3d | note | Verification Activity: Activity - I
fff74a16-e8c8-54b8-87a7-b4d0ff24da66 | note | Verification Activity: By - SV
0f3987b4-0210-4b82-9b3c-58617f991014 | checkpoint | 2.17.3 - Grated Trench Drain
502a5a13-a457-567d-9992-22fdae8b2b19 | note | Acceptance / Conformance Criteria - Grated Trench Drains shall be installed as per Manufacturers specifications
d62df253-0272-5bfd-9ffc-b5029c2461a7 | note | Standard / Specification - PS 16.34
382762ac-21f3-5ddd-975d-b14dc1d69a8d | note | Verifying Document - Site Records
11f2d96b-76f3-5a42-beca-8b2a2f2a266f | note | Frequency - As per manufacturers specifications
781fd2d6-aaa3-5370-92dd-984cee2d91fb | note | Verification Activity: Activity - R
33aa6d8b-4c9e-5fe1-86c2-0c5f3776bedd | note | Verification Activity: By - SE
4004f9c3-1027-48f4-b64b-0decca7dfec9 | section | 2.18 As Built Records
bfe697e1-ecc1-4be6-8dbf-4285c277d29e | checkpoint | 2.18.1 - Survey Requirements - Stormwater Systems – Above ground:
9005e554-bee3-5850-a85b-af9739cce380 | note | Acceptance / Conformance Criteria - The following items shall be recorded for asbuilt drawings: Treatment swales, wetlands, basin’s location, profile and grade. Diversion Drain location, profile, and grade. Trench excavation and invert. Line, levels and grade of kerb and channels. Rodding eye locations.
44efda96-6b2e-5997-bf9a-b74b8558cc96 | note | Standard / Specification - PS 16.33
a153d555-427f-529d-91da-788956120d6b | note | Verifying Document - Survey
a6a1ff4e-f306-5ea7-b03f-c9617fcfd0c1 | note | Frequency - All above ground Stormwater Systems
01154725-3044-531c-abb5-abeb4a81ad74 | note | Verification Activity: Activity - I
cd5bc385-5095-5866-b3af-e9525bf5da98 | note | Verification Activity: By - SV
d8a3a7e5-b0c0-523d-bb90-a7701d6a761e | checklist | ITP - Stormwater (Structures) - 202 - Rev B | itp | ITP - Stormwater (Structures) - 202 - Rev B
e48adf96-a921-5393-9ab6-5ff61a725470 | section | 1.01 Stormwater Aggregate Materials
a95ca035-74c8-594b-8085-a1d9aa423a24 | checkpoint | 1.01.1 - Controlled Low Strength Materials - CLSM
b9cb59d3-622b-5902-82ee-48040e0dc331 | note | Acceptance / Conformance Criteria - The use of CLSM by the Contractor will require approval from the Engineer on a case-by-case basis.
d554de1a-f0a4-5766-9fab-bcabe212688d | note | Standard / Specification - PS 16.8.1, PS 16.37
fd9db4d6-b13f-578c-8a31-3a884af41cc9 | note | Verifying Document - Engineers Approval
293ada82-74e5-50ff-abe1-0c3759c6dfc0 | note | Frequency - An application submitted to the Engineer for approval, to use CLSM.
a0d796f0-ae9b-550b-83fb-f5fb3235c7bc | note | Verification Activity: Activity - HP
d9065f6e-0e33-5678-b156-92376f309262 | note | Verification Activity: By - ENG
cb3b8a82-5309-5c00-9c64-feba92dfeae8 | signoff | AUTHORITY HOLDPOINT
25ba88a4-4910-5004-8d64-eec2b2d9f977 | checkpoint | 1.01.2 - AP65 Aggregate
af80170f-9aed-5408-bec8-4a356e26bf00 | note | Acceptance / Conformance Criteria - AP 65 Aggregate is to be a crushed product with a maximum granule size of 65mm and be a graded, clean durable aggregate which meets Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities requirements
bee0afb1-20d8-5697-b6a2-6c782b16c71a | note | Standard / Specification - PS 16.8.2.1, PS 16.9.1.2, PS 16.6, PS 16.37
c4a66042-2771-5b74-a492-ca79dea11dba | note | Verifying Document - IANZ Lab Reports
13ea5eba-d119-5ef1-b17c-3554240289eb | note | Frequency - Submitted to Engineer for approval
cd7d29b9-6f4c-5665-b93d-90316e17cf36 | note | Verification Activity: Activity - HP
d7fdc9ce-90a5-5e16-b637-b1f83456885d | note | Verification Activity: By - ENG
d104ba0f-f41a-5817-8d54-5b844a37c26a | signoff | AUTHORITY HOLDPOINT
6dd2f2ca-856f-5198-a519-10cfd10b5e41 | checkpoint | 1.01.3 - AP40 Aggregate
0d99e137-981e-585d-900b-c0c4ba5ebe81 | note | Acceptance / Conformance Criteria - AP 40 aggregate is to be a crushed product with a maximum granule size of 40mm and be a graded, clean, durable aggregate and which meets Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities requitements
47ee1303-2574-50ae-b3c6-beb51f336151 | note | Standard / Specification - PS 16.8.2.2, PS 16.9.1.2, PS 16.6, PS 16.37
6e63f27c-18db-5df0-9168-7215f6097c85 | note | Verifying Document - IANZ Lab Reports
71d6a36c-6da9-5b27-ad80-11fc671a8e9f | note | Frequency - Submitted to Engineer for approval
94a9d1bf-48a9-59d5-9052-be3d45e3b182 | note | Verification Activity: Activity - HP
d1d25752-f92f-530a-ab79-2acc8f9d8256 | note | Verification Activity: By - ENG
c5c5034d-17c0-530a-a8db-4f8cf9313412 | signoff | AUTHORITY HOLDPOINT
60b51c6d-53b8-52b8-86b9-6f6cb8e7a404 | checkpoint | 1.01.4 - AP20 Aggregate
8752c5af-e588-5e11-b8bc-3ac23a4c8173 | note | Acceptance / Conformance Criteria - AP 20 aggregate is to be a crushed product with a maximum granule size of 20mm and be a graded, clean, durable aggregate and which meets Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities requirements
852076c2-b933-5c7d-9cb6-66271e63669f | note | Standard / Specification - PS 16.8.2.3, PS 16.9.1.2, PS 16.6, PS 16.37
b360cd9b-409d-59ba-9154-d674c6997095 | note | Verifying Document - IANZ Lab Reports
c6b0b3a7-6dcf-50c1-9752-a9b5e6c216f4 | note | Frequency - Submitted to Engineer for approval
84aee3af-5288-58df-8681-3745321c5d83 | note | Verification Activity: Activity - HP
36d91c27-e601-58f0-bfc9-7e77fbbbba59 | note | Verification Activity: By - ENG
c815d7ea-eda2-5e1b-92bd-9dc6bba41adc | signoff | AUTHORITY HOLDPOINT
218c5f06-0ccd-560e-b6b0-c9b027b59a28 | checkpoint | 1.01.6 - Alternative Bedding
a85001ed-6c8b-5551-9216-b5b9ec0d7a89 | note | Acceptance / Conformance Criteria - If the Contractor wishes to propose a different material from that specified in this section, the Contractor shall submit to the Engineer
cdd195da-360a-5eb0-9f67-da0bb290ce41 | note | Standard / Specification - PS 16.9.2.1, PS 16.9.1.2, PS 16.37
094abc90-e93f-59f2-8f58-4a3416f1fec3 | note | Verifying Document - Statement from the concrete pipe supplier
2a6a8f95-5476-5bd0-909d-f9d7bc293854 | note | Frequency - Submitted to Engineer for approval
7853bd94-b417-5dfe-865f-db7f733661b9 | note | Verification Activity: Activity - HP
f0e0455f-bafc-5c44-9fdb-2cfb183fee07 | note | Verification Activity: By - ENG
fa2dd314-75f8-5cd2-8157-2cf844b50ad4 | signoff | AUTHORITY HOLDPOINT
878ad85c-37ec-5b05-aa55-b8b309cd8376 | checkpoint | 1.01.7 - Overlay Zone Material (for concrete pipes)
73d0dffb-72de-5c06-abf2-f02ee29527da | note | Acceptance / Conformance Criteria - Materials for the overlay zone GAP 20 shall be used which has been tested for Grading, Weathering Index, Crushing Index
c1fc6083-d497-512b-899f-211d02bc7bb0 | note | Standard / Specification - PS 16.9.2.2, PS 16.37
78c23021-09c1-50ce-b93d-a1424387d6c7 | note | Verifying Document - IANZ Lab Reports
4b9eaaa1-c003-502f-a6c4-adc0743d8a8e | note | Frequency - Submitted to Engineer for approval
eb0d75c9-c21d-52e8-837d-9d2632d925b0 | note | Verification Activity: Activity - HP
674ddbf1-b044-5339-b386-a5448fe068f7 | note | Verification Activity: By - ENG
f8091fef-c776-5fa2-af04-7a9b6e0462dc | signoff | AUTHORITY HOLDPOINT
4a4e4a8a-7cb6-582c-93dc-909ff02072ba | section | 1.02 Stormwater Pipe Materials
69e09f41-d841-56ba-b5dd-cc6933a78e4f | checkpoint | 1.02.2 - Steel Work
7983486e-24cd-50d5-a88a-077d77907780 | note | Acceptance / Conformance Criteria - Unless otherwise specified, all steel work shall be fabricated from mild steel conforming to the requirements of AS/NZS 3679.1:2010 and AS/NZS 4680:2006. All cut surfaces shall be protected with a corrosion protection coating i.e., zinc rich paint.
096536d9-25d7-5385-a9ab-7329e68ac748 | note | Standard / Specification - PS 16.8.1, PS 16.8.4
a67baf84-4f4e-5af7-9f49-3d508d370eb0 | note | Verifying Document - Datasheet
8e8f3895-996a-571f-8a07-9807f33a4bf9 | note | Frequency - Prior to use
259e532f-e49b-52fa-a769-9900f1bcbbce | note | Verification Activity: Activity - R
c6d0f086-4e55-5120-9b06-7082f5a74ce6 | note | Verification Activity: By - SE
60ecbba7-61f7-5ae0-85a1-a18bef3de7c5 | checkpoint | 1.02.4 - Steel Fitting Corrosion Protection
01185b10-0157-5713-b427-207939b2ade7 | note | Acceptance / Conformance Criteria - Steel fittings shall be shop assembled as large as practicable before hot dip galvanising or zinc metal spray to AS/NZS 2312.2:2014 and AS/NZS 4680:2006, to minimise the number of field welds and bolted joints required.
25ea048e-44e9-5283-8d13-d016e3882bcc | note | Standard / Specification - PS 16.8.4.1
baa12f3d-f909-5cfb-8bf9-7107d00dcbe0 | note | Verifying Document - Datasheet
3b0dd7b1-6557-5e42-b3be-12318e43d8f1 | note | Frequency - Prior to use
35ab5a0f-10e0-5d1b-8df2-6eadfb534c2a | note | Verification Activity: Activity - R
2a194199-2148-53af-9e58-783ccc2f0809 | note | Verification Activity: By - SE
64f50980-c6f3-5fcc-9255-86d784630f99 | checkpoint | 1.02.5 - Hot Dip Galvanised
b513d5d2-10aa-5f60-89c6-58c9d7e3abda | note | Acceptance / Conformance Criteria - All ferrous metalwork except standard galvanised pipe shall be hot dip galvanised to HDG900 unless otherwise specified.
5d82e457-0b21-59b4-9eba-46c2b85cc2a0 | note | Standard / Specification - PS 16.8.4.1
1a0913ce-7898-56e3-892a-ed544fffcb61 | note | Verifying Document - Datasheet / Cert
b7fa39ed-7c9f-533f-a6b4-0b740b67c96b | note | Frequency - Prior to use
a9c395dc-0d70-5ef4-85ae-4190b4c6b5dd | note | Verification Activity: Activity - R
f08d80a0-bb58-5b29-bd7c-ee503311a19c | note | Verification Activity: By - SE
2fc23d9c-901d-57bc-b711-629672507c09 | checkpoint | 1.02.6 - Fastenings
1b59b4f3-9733-5b2b-a421-64721b8a2f98 | note | Acceptance / Conformance Criteria - All fastenings associated with manholes or drainage structures shall be either hot dipped galvanised or stainless steel. Zinc Plated fastenings shall not be permitted
8fbbe4db-f8ac-5d54-8095-fd3bd975af7c | note | Standard / Specification - PS 16.8.4.2
05cafc36-f9b1-58d4-95d1-2579f2dea1b3 | note | Verifying Document - Datasheet
3df46a37-58ed-533e-b9e5-00d053f7dddb | note | Frequency - Prior to use
d14e8d20-e9f8-5d12-b4c3-5bc088c6d24c | note | Verification Activity: Activity - R
6c9ac783-c583-5a72-911d-15db94b028e5 | note | Verification Activity: By - SE
35d72f2d-cc19-5c7a-90cc-ec774c712f02 | checkpoint | 1.02.7 - Concrete pipes and fittings
bd5c47f4-cf1f-50dc-8976-169e73db3ae0 | note | Acceptance / Conformance Criteria - Concrete pipes and fittings shall comply with the requirements of AS/NZS 4058:2007 for concrete pipes
1731c56c-d3a6-5dad-aca8-69a3ba67f45f | note | Standard / Specification - PS 16.9.1.1, PS 16.37
775f9007-c66b-5956-8a36-44d03630cc33 | note | Verifying Document - Datasheets
66c80b3d-245b-5bf8-a54f-fd82cf27bf23 | note | Frequency - Prior to use
eb064c25-c76c-5ed0-affe-481bf3ed01b1 | note | Verification Activity: Activity - W
386e7a4c-f276-54f6-92f6-7be2b7ac52f1 | note | Verification Activity: By - ENG
f5e951c8-6f34-5e62-aa3c-51bb1cf65da1 | checkpoint | 1.02.8 - Quality of Pipe and Precast Units
645f8a5c-6968-5a6e-9c36-2decea5a5c54 | note | Acceptance / Conformance Criteria - IANZ Accredited Manufacturers certificate to NZTA F/3 (refer to Appendix F)
effdac09-57ab-5c96-9fa7-9c71b362880a | note | Standard / Specification - PS 16.34
340eb304-3e6a-5a2c-b3f2-e90da12f49de | note | Frequency - For every pipeline delivered (as soon as they are delivered)
e84e9ff3-3308-5e82-b5e6-74a8c9354723 | section | 1.03 Stormwater Structure Materials
91fce285-1472-507c-b6a3-7c424a6057d7 | checkpoint | 1.03.1 - Precast Catchpits
e407ffbd-9200-5da7-8e25-bd5b9f3d1b32 | note | Acceptance / Conformance Criteria - All catchpits shall be precast concrete suitable for HN-HO-72 traffic loading.
87577e7f-5f3f-57fe-ba74-a703edcfd570 | note | Standard / Specification - PS 16.10.1
8ceb1190-a1de-51bb-88c4-3d29675f7809 | note | Verifying Document - Datasheet
ca0b164a-0c34-5e15-b97a-2254b55e46c8 | note | Frequency - Prior to use
7894f69f-6143-5628-a852-3155e5566e76 | note | Verification Activity: Activity - R
c902d63f-8497-5ec0-a66e-4f94fb56a84c | note | Verification Activity: By - SE
56cb0cef-ffb7-59aa-8cfc-680a0a3fe297 | checkpoint | 1.03.2 - Catchpit Lids
e6170961-e3f3-502c-9fa2-e7510f1f4cae | note | Acceptance / Conformance Criteria - Non-Rock 510mm Class D Heavy Duty type lids or similarly approved shall be used unless otherwise specified on the drawings. Heavy Duty type lids to be suitable for HN-HO-72 traffic loadings that are cycle friendly.
bd39b4d6-1ae8-5971-8291-8e90c4274f69 | note | Standard / Specification - PS 16.10.2
5e113349-3b70-5825-8b06-060f2df94543 | note | Verifying Document - Datasheet
d909513c-266a-59da-a468-cc109b3621ff | note | Frequency - Prior to use
8b226bac-b2e0-5a85-943a-14307bb421ad | note | Verification Activity: Activity - R
12c18111-0bd8-55c3-a804-82722e87321e | note | Verification Activity: By - SE
130a6f97-8fb9-504e-bcea-a3dfe8267d7c | checkpoint | 1.03.3 - Precast concrete manhole
634be762-717c-515c-a554-d8979387f70c | note | Acceptance / Conformance Criteria - All precast concrete manholes shall be manufactured in accordance with NZS 3109:1997. All manholes shall be suitable for HN-HO-72 traffic loading.
ca8a9af4-798e-50fd-9e4c-3b5ec7898656 | note | Standard / Specification - 16.15.1
420f8c7e-04f9-59fb-ab74-7fc35388c82a | note | Verifying Document - Datasheet
b1584ed3-02ad-5e48-9c73-8390b3407f96 | note | Frequency - Prior to use
227984e3-99ed-57ad-95cc-c3048e175ddf | note | Verification Activity: Activity - R
c063324e-399e-58e1-b115-43ed816dab2f | note | Verification Activity: By - SE
3000c124-dd41-5f1e-9807-ca9596c2438a | checkpoint | 1.03.4 - Catchpit Grates and Frames
7453bb2e-b4ad-51dd-9022-e5680ffe2cd4 | note | Acceptance / Conformance Criteria - Catchpits grates and frames shall be grey cast iron suitable for HN-HO-72 traffic loadings.
33d34d62-d9ad-5330-b2b5-b6de920f060f | note | Standard / Specification - PS 16.10.1
380387b8-ed28-5375-a13c-4823092ea855 | note | Verifying Document - Datasheet
29e240df-4bbb-5c0d-9430-412f7612a924 | note | Frequency - Prior to use
fd3c952a-02b6-5538-8278-9f9afdd806ac | note | Verification Activity: Activity - R
f6f94745-3ea0-5aa9-95a9-ecdd44c3b113 | note | Verification Activity: By - SE
14e1a3a3-be4a-5b23-8bcf-99effdb4e476 | checkpoint | 1.03.5 - Scruffy domes lids
4723b51d-d9f5-53fa-99d6-78bd334e89d7 | note | Acceptance / Conformance Criteria - Scruffy domes lids shall be galvanised steel Hynds Type 2 scruffy domes (unless noted otherwise in the drawings), or similar approved.
4e4d8c5e-c79d-5145-b794-2d0297d94056 | note | Standard / Specification - PS 16.16.2
93555c26-b70e-51b5-a4f5-21678789eb95 | note | Verifying Document - Datasheet
25a85b6d-506c-59a5-be45-0512b40f6556 | note | Frequency - Prior to use
fe1d8a9b-ab9d-503e-a92d-fb29067fb9de | note | Verification Activity: Activity - R
cac01b62-8654-5dd6-9bb0-1bb924597fea | note | Verification Activity: By - SE
cf286ccb-3176-5052-9aa2-4d85340f725f | checkpoint | 1.03.6 - Cement Mortar
7cc40a29-dfc7-5c71-bb96-d455b3dfbcfe | note | Acceptance / Conformance Criteria - Cement mortar shall be Durability Class M4 in accordance with NZS 4210:2001, with a minimum compressive strength of 12.5MPa.
3bec60e2-bed1-5d40-87da-604172d29ee4 | note | Standard / Specification - PS 16.8.1
48a9e6b5-f12f-5ebb-8a40-aa28c96b3a3e | note | Verifying Document - Datasheet
b8172244-144e-56dc-ada3-fe04a0d79433 | note | Frequency - Prior to use
63fa2a58-3fa3-59d6-81a3-1a7e80f98de3 | note | Verification Activity: Activity - R
d22fba64-a915-50fb-8599-28b0232fa4de | note | Verification Activity: By - SE
254f5570-ad69-595d-a595-909b315f255c | checkpoint | 1.03.7 - Epoxy Mortar
f2d4d949-c995-5eb8-b960-03edc644762e | note | Acceptance / Conformance Criteria - Epoxy mortar for use in manhole riser joining or repairing of damaged or cut concrete (to provide cover to reinforcing due to cutting of precast units) shall be Hynds (MSR) or Humes Hume bond (or similar approved), applied in accordance with the manufacturer’s recommendations.
71d12180-4709-548f-b9fd-e42220292653 | note | Standard / Specification - PS 16.8.1
ac466c57-262c-593d-865b-8e021eafb278 | note | Verifying Document - Datasheet
d5ae3c63-f547-5786-9da6-99bcaa04f4cb | note | Frequency - Prior to use
d384304a-0ceb-5f2d-888a-0af115e6cd57 | note | Verification Activity: Activity - R
9dc04b08-af9e-5e8d-a29f-397601fe007d | note | Verification Activity: By - SE
b290cd34-1606-50fd-995d-df90428ff8a7 | checkpoint | 1.03.8 - Precast Headwalls and Wingwalls
2aea9831-44c8-502d-9cb4-31bfea24869e | note | Acceptance / Conformance Criteria - Precast concrete headwalls or wingwall units shall be manufactured in accordance with NZS 3109:1997.
b466059e-18fa-56e3-b8cf-ddeef46ef999 | note | Standard / Specification - PS 16.13.1
48868a3c-d614-5565-a13b-3b8f5032cb2e | note | Verifying Document - Datasheet
f4edb9cc-17ef-573d-9611-0b663f37b336 | note | Frequency - Prior to use
88a8147e-3ae8-586e-bc5a-79c822b94136 | note | Verification Activity: Activity - R
972e5ea3-2701-56c8-8ea7-03dc2399cec3 | note | Verification Activity: By - SE
6d0f6d8c-7ec1-5e25-8613-a36245635455 | checkpoint | 1.03.9 - Erosion protection matting
8eb1e8c5-c77a-5966-adaa-594f0a07fcbc | note | Acceptance / Conformance Criteria - Erosion protection matting (coir Blanket or similar approved) is to be 100% biodegradable.
c6b9dac9-8519-5998-9374-3b2b45d725c4 | note | Standard / Specification - PS 16.13.1
29ecd1a9-bd78-5f4a-a647-f5557c620ca5 | note | Verifying Document - Datasheet
3d8ed03f-0f2e-5d3c-8f31-577b8d129216 | note | Frequency - Prior to use
5f1a4837-9a24-52cd-8f2c-b3337d7cc032 | note | Verification Activity: Activity - R
b118e925-1b38-51f6-9362-5aef40b69302 | note | Verification Activity: By - SE
0a061ecb-47c1-5451-be12-856fee80de39 | checkpoint | 1.03.10 - Precast Soakage Pit
649e01bd-8154-573f-a3cd-3a6bf4c78811 | note | Acceptance / Conformance Criteria - All precast concrete Soakage Pit manholes shall be manufactured in accordance with NZS 3109:1997.
da94e9ba-3fa9-5a42-a147-241634ca73f7 | note | Standard / Specification - PS 16.12.2.1
343f10c2-efa2-5d81-957c-64c8e8bdb937 | note | Verifying Document - Datasheet
9800ac4e-fc96-5395-950d-8f5d97f3c838 | note | Frequency - Prior to use
d7130151-50ad-5933-8505-02ac8efcc1fd | note | Verification Activity: Activity - R
9a83194e-2fcc-5fd2-829a-4671ef5e4184 | note | Verification Activity: By - SE
10e6e077-15d2-56b2-ae1c-2a0894025b52 | checkpoint | 1.03.12 - Manhole Sealant
b1fba66c-fa51-5ab6-81a5-9257673353b1 | note | Acceptance / Conformance Criteria - All joints between ring segments of precast manholes and chambers shall be sealed with ‘Grey Butyl Manhole Sealant – Hynds (SM9020)’ or similar and approved.
caf60dd5-2587-512e-bbdd-38748f7b581a | note | Standard / Specification - PS 16.12.2.2
5ec3bfd4-4b89-5406-ab56-a51192d66787 | note | Verifying Document - Datasheet
f7f757c0-2fc8-5eda-9eef-951f1d89f780 | note | Frequency - Prior to use
c0d00499-e831-54eb-9b2e-23ab7d09c556 | note | Verification Activity: Activity - R
4e5d5d68-8c05-5b42-8538-4830a13ae01f | note | Verification Activity: By - SE
a0739509-7e17-5960-a813-ae432cb4ebad | checkpoint | 1.03.13 - Head and Wing wall Insitu Concrete
11245d58-c1be-5a1a-8561-10399a85f634 | note | Acceptance / Conformance Criteria - Headwall and wingwall insitu reinforcing shall be steel grade 500E.
83fd79c8-c568-5f06-b17b-fa3bfd3e896d | note | Standard / Specification - PS 16.13.2
ca6591b6-ef01-56bd-a720-fd5ada9551f6 | note | Verifying Document - Mill Certs
b8d16d43-5094-524b-a9b2-ca92ec2bacc3 | note | Frequency - Prior to use
d1f6fdc0-3c1e-57a9-9054-59c64e60d928 | note | Verification Activity: Activity - R
c16fa753-e1b4-54ed-a760-2245d5fd5043 | note | Verification Activity: By - SE
de604162-2266-58c3-bfef-680800f0396a | checkpoint | 1.03.14 - Head and Wing wall Reinforcing
847b76a9-15d5-55c4-b19c-eb2c5a847275 | note | Acceptance / Conformance Criteria - The headwall and wingwall cast in-situ concrete shall be 40MPa
d9d7a9b3-c50c-5307-a76a-28e05a25bf40 | note | Standard / Specification - PS 16.13.2
dd353d74-2cb8-56cb-8460-a70faefad9b6 | note | Verifying Document - Mix Design
7ca5b1a0-d31f-58f7-93ac-dbaaf779d679 | note | Frequency - Prior to use
14f6f916-9c9c-5212-9cec-e45904c012ad | note | Verification Activity: Activity - R
32984417-a5f4-58d6-99d3-db5e7d3b819e | note | Verification Activity: By - SE
0e382e0a-0547-590f-bae7-3624e64784f6 | checkpoint | 1.03.16 - Benching Concrete
928c057a-d29f-5ffd-9593-552cb38134d0 | note | Acceptance / Conformance Criteria - Benching shall be 20MPa concrete
9df84dda-e75c-5d87-93b0-1a1ccc670043 | note | Standard / Specification - PS 16.15.2
04317dcd-5b01-5c4b-9300-a09ab978053d | note | Verifying Document - Mix Design
05b8be1e-8ffd-5b62-b63d-ccce3b85adfa | note | Frequency - Prior to use
c1838719-7c4e-5bad-8f7a-ffd337adbe42 | note | Verification Activity: Activity - R
b0282277-0faf-5295-93be-7133bab0b29d | note | Verification Activity: By - SE
3f8a50a6-974f-54d2-989e-817719c48b96 | section | 2.01 Stormwater Drainage (Existing Assets)
9e4cc768-b88c-500f-afbb-8755a862e601 | checkpoint | 2.01.1 - Obsolete Stormwater Structures
2c3d3a9c-b156-5097-ba15-7a0782b26fa6 | note | Acceptance / Conformance Criteria - Obsolete catchpits, manholes, kerb and channel shall be demolished, uplifted and removed to an approved tip site.
31173915-c7cd-5f74-9e62-c25e15a35923 | note | Standard / Specification - PS 14.2.1
0e6c9191-8281-5d8e-bdec-7784bbdf645f | note | Verifying Document - Site Record
504dcb0e-f3f8-56a6-981a-a8725478c73a | note | Frequency - Each Obsolete Structures
00a8535f-eec8-5fab-ab44-c16900a827ac | note | Verification Activity: Activity - R
6f3ca366-5b19-5a6c-b489-12eabf0934d2 | note | Verification Activity: By - SE
c7f50f69-b0f9-5fdc-8f19-342f12ec544b | checkpoint | 2.01.2 - Cutting Existing Pipes
747c8d6f-5003-5245-8865-225a4eae1ad0 | note | Acceptance / Conformance Criteria - Where the catchpit will be replaced by a new drainage structure and/or constructed in a new location the existing stormwater pipe shall be neatly cut perpendicular to the line of the pipe to allow it to be easily extended.
043b091e-ccd0-5604-b95c-01ec23a83c89 | note | Standard / Specification - PS 14.2.2
70cd7d22-0581-5e3b-9735-36bdd4a03618 | note | Verifying Document - Site Record
dc9b9aeb-7227-58a1-b53a-b0365ca89b19 | note | Frequency - Each Occurrence
4ab71c05-9078-50f8-8dfd-bac50912375d | note | Verification Activity: Activity - R
f5bffa36-df23-5049-8e3e-f04aa5756571 | note | Verification Activity: By - SE
4825206e-1201-5e97-939a-dd7bb149a61d | checkpoint | 2.01.3 - Debris Removal and Void Filling
00ae3615-b5f8-5515-94bb-cc4af1790b3b | note | Acceptance / Conformance Criteria - All debris shall be removed to waste. The resulting void shall be backfilled with well compacted approved fill material.
91a12ac3-25c7-566b-abb0-fefe6dfa0cca | note | Standard / Specification - PS 14.2.3
59b99207-5c92-5b0f-a4c1-38b1f9762fa8 | note | Verifying Document - Site Record
b3dd4f55-1940-51f5-b8a9-d5b14a8c3cc6 | note | Frequency - Each Occurrence
4c9006bc-ce0a-54e5-93ea-32a656e3b7b9 | note | Verification Activity: Activity - R
2f04c4ac-fc2c-5b19-8eea-b4af3bf524f2 | note | Verification Activity: By - SE
7d731da0-9d36-5dc2-bbaa-36fd489fe260 | checkpoint | 2.01.4 - Obsolete culverts
64a008ec-0d3d-565f-a7e7-15e9e3229bec | note | Acceptance / Conformance Criteria - Obsolete culverts shall be removed or may be left in place subject to the agreement of the Engineer. Abandoned culverts shall be plugged with concrete at each end or if the culvert is within 1.0m of the surface it shall be completely filled with a cement grout.
43d90bc1-c134-5f6c-aa7a-a4cb1dce5bbb | note | Standard / Specification - PS 14.2.4
1a18f3e3-6c2e-5f7e-8b12-ff9be1c34d9b | note | Verifying Document - Site Record
17297358-32fe-5c3e-892b-c9de06eef71f | note | Frequency - Each Occurrence
0f0f5c08-98a1-5108-b306-bd9adf7ac08f | note | Verification Activity: Activity - HP
bb150a45-ee07-55a1-9ca5-6948c1428315 | note | Verification Activity: By - ENG
07db67e3-cab4-5ae7-ac32-126b928f841a | signoff | AUTHORITY HOLDPOINT
fafc21ec-637c-525a-8389-661e2d0e99f5 | section | 3.01 Stormwater General
a210fb2a-8fbf-5a1e-b274-262fc5b0bdb3 | checkpoint | 3.01.1 - Setout
885e5323-57d8-5a8e-8c9c-69f94e63bfc0 | note | Acceptance / Conformance Criteria - Prior to the commencement of any drainage works for a particular drainage line, the Contractor shall set out the line, level, and position of the proposed drainage line, including inlet and outlet positions and levels, and present it to the Engineer for their consideration. The Contractor shall provide at least 48 hours’ notice to the Engineer ahead of set-out and allow 48 hours for the Engineer to respond prior to commencing work.
a1a93af7-9b43-51ef-bc2a-c6ab37b27930 | note | Standard / Specification - PS 16.6.1
da135260-1772-5a7f-b957-b57a6f72a4b6 | note | Verifying Document - Survey Records
6463a494-9a7f-549e-b734-fca2b7301daf | note | Frequency - Prior to the commencement
c3f2d9fe-1cf3-5d58-8d66-3279709c13ef | note | Verification Activity: Activity - HP
0fbb3873-7a54-56b0-8c33-adb06319ad03 | note | Verification Activity: By - ENG
1de8f978-8a84-5ff3-a1fb-37a4c0083aee | signoff | AUTHORITY HOLDPOINT
654daa1a-e7a3-569d-81c4-4329920ea593 | checkpoint | 3.01.2 - Dealing with Water
e37040ee-67a4-5058-bddd-36d0b3da0335 | note | Acceptance / Conformance Criteria - The Contractor shall maintain all trench inverts free from flowing or accumulated water. Water arising from, or draining into, the trench shall be drained or pumped. Any sumps required shall be refilled to formation level as directed by the Engineer.
de17876a-efdd-5ba7-9620-afee920b2a56 | note | Standard / Specification - PS 16.7.1
ceacfe1a-148e-5994-9711-e757a9db3c38 | note | Verifying Document - Site Records
c22ecdcc-0b52-5ca0-a9b6-402c2b0a5cd4 | note | Frequency - During Works
852d3cca-741a-5c6b-bae5-c08aab69d59d | note | Verification Activity: Activity - S
83d23992-8d12-589d-bac6-5768b9173ac3 | note | Verification Activity: By - SE
4f09ae7c-2a93-5390-810b-532208062fd7 | section | 3.02 Pipe Installation and Backfill
4783c80c-dbfc-527d-b81d-044fdec625f6 | checkpoint | 3.02.1 - Open Trenches
09aa8ea3-d78c-5998-a238-4b3026117470 | note | Acceptance / Conformance Criteria - All open trench excavations for pipelines shall be to a minimum depth of 100mm below the pipe external walls. Where excavating in natural ground or existing carriageways, no more than 100 metres of trench (per drain laying operation) shall remain open at any one time.
88a69342-365e-5e42-a7e8-e3c6c51fca3f | note | Standard / Specification - PS 16.9.2.10
902b85a7-4238-5c3d-806d-1ecd05255206 | note | Verifying Document - Site Records
4c1d8f7d-813a-521e-a636-9694c762f276 | note | Frequency - During Works
da90614b-9307-53fd-b41d-fe6c6505e67b | note | Verification Activity: Activity - S
125dce34-a0b8-5c8e-9aa3-89d65eeb7792 | note | Verification Activity: By - SE
79d789f7-cd98-5db7-b2f4-1f8fdbbb5348 | checkpoint | 3.02.2 - Saw Cutting
7083baa1-f4ba-576a-9369-c64c5cd7ce85 | note | Acceptance / Conformance Criteria - Where trenching through roads, prior to excavation, the surface shall be saw-cut a minimum of 100mm beyond the trench wall and parallel to the proposed alignment.
a0c13b34-28e9-56eb-8a82-c6e5b95af9ac | note | Standard / Specification - PS 16.9.2.10
cf928557-7adc-596e-904a-56ec05e0b42f | note | Verifying Document - Site Records
4104cdb9-cc9b-500b-871f-c0111fa2e36d | note | Frequency - During Works
d86780b1-d4c5-5e9d-abf9-5e44c4bdd0cf | note | Verification Activity: Activity - S
00ba596c-9795-5d07-8837-a5a71c95e0cb | note | Verification Activity: By - SE
6afb86e1-05de-5ae2-af76-09e9e705fa80 | checkpoint | 3.02.3 - Stability check
47b6fbab-02d3-5836-97ee-8511a70f8f3b | note | Acceptance / Conformance Criteria - Where trenching is near new or existing structures (within 5m horizontally, or where the trench invert is below a plane projected downwards at 1(V) in 2(H) from the base of the structure), a stability check shall be undertaken to ensure undermining of the structure is avoided. The Contractor shall undertake a stability check in these situations.
65869707-4fe2-58ed-b155-b3d7f914ca95 | note | Standard / Specification - PS 16.9.2.10
24b41d81-4dbb-5068-b0b2-ab34686eb8f3 | note | Verifying Document - Site Records
421bc9e6-cc7a-5ae7-9b74-578305ddcb58 | note | Frequency - Each Occurrence
c41ed935-4c7a-5e88-a959-ecb8e593f2cb | note | Verification Activity: Activity - S
7c04dfdc-5014-552b-bdb3-c3c5864e58fa | note | Verification Activity: By - SE
e9ca101b-c573-5a5a-8cd3-20d24be499e4 | checkpoint | 3.02.4 - Trench Width
1382f0b1-e246-5e57-b1b5-bbf95fbb4846 | note | Acceptance / Conformance Criteria - The minimum trench widths are as indicated on Drawing WD-0131 but not less than the external pipe diameter plus 600mm and not more than the external pipe diameter plus 1200mm.
89af5cbd-572b-5da8-bbfe-fa831f19db81 | note | Standard / Specification - PS 16.9.2.10
6fb17de3-604d-5920-99ed-204096c22c36 | note | Verifying Document - Site Records
aed67127-c926-57b1-8a8a-9a6f3d561375 | note | Frequency - Each Pipe
101b3e87-da0a-5028-91fc-d6aaab781a46 | note | Verification Activity: Activity - S
98913d78-758c-5c78-992c-291397a970db | note | Verification Activity: By - SE
58a4d71f-6dbc-5a10-a296-7ed58b085508 | checkpoint | 3.02.5 - Unsuitable Material
c6296427-fd57-57c3-b04f-ea539a1fe192 | note | Acceptance / Conformance Criteria - All material deemed to be unsuitable shall be removed to a depth of 600mm or a greater depth as specified by the Engineer, until suitable material is reached.
c8cac576-c80e-519a-999d-fbe4ecb38f6d | note | Standard / Specification - PS 16.9.2.10
0d96338e-1a5a-56c4-9c36-899cb10f1543 | note | Verifying Document - Site Records
45547264-56db-57ea-8512-83b968e480f2 | note | Frequency - Each Occurrence
d8af951d-38ea-5c47-aec6-e9bc9dd3268a | note | Verification Activity: Activity - S
20405893-728a-5401-a025-cda48715762b | note | Verification Activity: By - SE
ea7ad893-3773-5813-936f-69f88f144761 | checkpoint | 3.02.6 - Trench invert subgrade inspection
bace89a8-4114-5657-81a1-40b92186c5df | note | Acceptance / Conformance Criteria - The Engineer shall have the opportunity to complete a Visual Inspection to NZTA F/3:2010 on the trench subgrade each day on each pipeline during installation.
00ea6f44-a237-5f33-aab0-a38ae488e46d | note | Standard / Specification - Suitability
20479204-28f3-5202-92fd-1ae43a431474 | note | Verifying Document - Engineers Record
c73433d7-959b-5a93-a184-87741fdb7a61 | note | Frequency - Daily
728831df-b427-54c1-a8a4-4f4bd16296c2 | note | Verification Activity: Activity - WP
2c263ad2-49c7-5642-84b3-8f731b614797 | note | Verification Activity: By - ENG
d818a004-d73b-5d9a-b27c-6159bea11363 | checkpoint | 3.02.7 - Trench invert subgrade testing
8b34e583-94dc-5dfb-b119-bd27d6f83fff | note | Acceptance / Conformance Criteria - The subgrade shall be tested for CBR>5 by Scala or shear vane. This test shall be undertaken at the design subgrade level and at a depth of 300mm below the design subgrade level.
08fcbbae-abb7-5e65-b1b2-c4fe011ef492 | note | Standard / Specification - PS 16.9.1.3, PS 16.32.3
95b337db-a279-5b5a-a0c7-27a2721b36bd | note | Verifying Document - Scala or Shear Vane Report
437ab222-615b-5929-9da8-43c25d6a192d | note | Frequency - 1 per 15m trench length Minimum of 2 tests between pits/manholes
5a2fadf0-aebc-5245-bc96-3eafea8e905a | note | Verification Activity: Activity - I
dca8baf3-bc11-5d22-84ab-f82af75330a5 | note | Verification Activity: By - SE
270c1a1e-7412-5580-a7d8-4802dc5d53ca | checkpoint | 3.02.8 - Subgrade Undercut and Replacement
4676078b-2efe-5dc6-81cb-0e0a70c92c55 | note | Acceptance / Conformance Criteria - The insitu trench base shall be tested and if CBR is less than 5, it shall be undercut and backfilled with AP65 compacted to compacted to a MDD of 90%
a668908e-2871-52bc-a3c7-42391c06b4b7 | note | Standard / Specification - PS 16.9.1.3
6e6c8c2c-9779-5dc9-bd5a-27df674a3f76 | note | Verifying Document - Site Records / NDM / Clegg Report
378e22fe-6714-51fa-976a-92b94c3fc07b | note | Frequency - Each Occurrence
ee1a250d-8642-5b6d-ac2b-1416d50fd965 | note | Verification Activity: Activity - S
625d8e04-1d03-5fe5-a673-aecd649281f2 | note | Verification Activity: By - SE
81f73ef2-bdc8-5939-aa6d-cff64bb295e5 | checkpoint | 3.02.9 - Pipe bedding and haunch zone inspection
80afe4fd-6f35-59f9-aae3-29e56c3792c0 | note | Acceptance / Conformance Criteria - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe bedding and haunch zone
8f0b796f-53c8-50ac-9132-c77a670c3d03 | note | Standard / Specification - PS 16.32.3
60b5717d-85de-5442-b8a9-bef95f12d06d | note | Verifying Document - Engineers Record
dae45631-30e1-5857-ad4d-6a92517ebf2e | note | Frequency - 1 per trench length (Between Chambers)
bde049dc-34cb-5219-bb69-b986c7ef030a | note | Verification Activity: Activity - HP
3ff31980-c7e1-5278-91d2-473bdcff7c1b | note | Verification Activity: By - ENG
5cf170fc-8df5-5e2c-b092-708051a3742b | signoff | AUTHORITY HOLDPOINT
5814668f-ccd5-5d72-badb-415127e4c7e4 | checkpoint | 3.02.10 - Pipe bedding and haunch zone Density Testing
7780f82b-4990-59fe-a8bc-884f232a201f | note | Acceptance / Conformance Criteria - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes. The pipe bedding and haunching zone shall be compacted to a MDD of 90%
6cccbd2f-65ba-5ea9-b97a-8c4bb86632a0 | note | Standard / Specification - PS 16.32.3, PS 16.6
2eb44e5d-5e21-5d11-86b9-6530b43ab9b2 | note | Verifying Document - NDM / Clegg Report
641ea46d-f966-5b91-abc5-a0ffcf8610fd | note | Frequency - 1 per 15m trench length Minimum of 2 tests between pits/manholes
56dadca6-874d-5d2f-b167-2a5a6ce18b08 | note | Verification Activity: Activity - I
c5d6fc74-488c-57b1-af27-39ac3a5333f6 | note | Verification Activity: By - SE
c03d2694-c46a-5d17-84c5-81dfdcdc396f | checkpoint | 3.02.11 - Backfilling of pipes and culverts with embankment fill - QA Acceptance
54c8cf14-a7e5-56f3-b2a5-031afc96d58b | note | Acceptance / Conformance Criteria - Prior to Backfilling of pipes and culverts with embankment fill the test results for bedding, haunching, side zone, and overlay zone material properties, grading curves and compaction tests are accepted by the Engineer.
556bb476-5c8b-5e81-9d97-402026fc5cfa | note | Standard / Specification - PS 16.37
6f63a7f2-ad23-523a-9aa8-8c354adb37e8 | note | Verifying Document - Engineers Acceptance
163a2091-7069-560a-aeae-aea14f580ae8 | note | Frequency - Prior to Backfilling of pipes and culverts with embankment fill
e3b88e8c-a85b-55ce-8e53-66de6475b952 | note | Verification Activity: Activity - HP
e5489cde-3c63-5f55-816c-9c60ec1bc44a | note | Verification Activity: By - ENG
19a18f40-a4da-5db3-aeba-1eabda497cc4 | signoff | AUTHORITY HOLDPOINT
f8a5db8b-7b9c-5b42-9bdd-2aee0aee659b | checkpoint | 3.02.12 - Pipe laying in Embankments
9333aaaa-bb90-5a92-8fc4-21b56f24ee09 | note | Acceptance / Conformance Criteria - The Contractor shall have each pipe checked for level as it is laid, by a competent technician using an Engineer’s level, pipe laser or other approved equipment. Pipes shall be laid on uniform gradients between successive designated manholes at the gradients specified on the Drawings.
de949b47-e5bb-596e-9340-959a6b481c11 | note | Standard / Specification - PS 16.9.2.8
81d88739-b339-5b45-af6b-cd0cd37dddc1 | note | Verifying Document - Survey Records
7967b6ad-cc3e-50c1-bac5-90d180ab9963 | note | Frequency - Each Pipe
ae552d7c-6f4e-5bd3-92a6-85659f422a67 | note | Verification Activity: Activity - I
50ae43b8-b7f8-58a1-8966-b0ac0ff3fd4c | note | Verification Activity: By - SV
f9ac2429-13b8-58d3-8851-eab84a3fd0e7 | checkpoint | 3.02.14 - Cutting of Concrete Pipes
30041ea1-5673-5c52-a5cd-006cccb974ee | note | Acceptance / Conformance Criteria - Where it is necessary to cut a concrete pipe the pipe supplier should be informed of such requirement specifically where the dimensional tolerance for the pipe is deemed critical.
dfb00597-946b-5992-96c2-1bdbabaf4b18 | note | Standard / Specification - PS 16.9.2.16
acdcf809-4c9d-56c3-aaaa-d8ac32594b5a | note | Verifying Document - Suppler Approval
212d01d3-4f70-56eb-be43-3cc662da4072 | note | Frequency - Each Occurrence
c40e6911-bdab-5cfe-abbe-45ef70d12450 | note | Verification Activity: Activity - S
3835eda0-ea57-5160-b112-c942f617dbdc | note | Verification Activity: By - SE
035129dc-7d0e-5a42-b6fe-5dee75371088 | checkpoint | 3.02.15 - Cut Pipe Sealing
e65c9d26-4d1c-5d84-aa1d-8dfc0f16d611 | note | Acceptance / Conformance Criteria - All cut surfaces, not encased within benching or other in-situ concrete, shall be coated with an epoxy resin mortar in accordance with the manufacturer/supplier recommendations, leaving no exposed reinforcement.
aec9e4ca-b54d-53bb-9102-878cdc4379f9 | note | Standard / Specification - PS 16.9.2.16
99d2b016-c059-5f7e-9ac0-71ba4c2ddadc | note | Verifying Document - Site Records
f55294a3-ad52-5c4f-a1bf-68db916a46b1 | note | Frequency - Each Occurrence
e4b52e80-c90e-578b-9ac0-b43990ecba07 | note | Verification Activity: Activity - S
afd4d60d-0ac2-5818-a90f-71bad8ab5770 | note | Verification Activity: By - SE
e4c33cd6-d38e-587d-aa5c-a623c74935ed | checkpoint | 3.02.16 - Side zones Density Testing
7777ec8b-3bbc-5f47-a3c1-fb31188bf4ba | note | Acceptance / Conformance Criteria - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes. The Side zones shall be compacted to a MDD of 90%
5309e99a-d68c-5d9d-99b5-c598629cd3ab | note | Standard / Specification - PS 16.32.3, PS 16.6
e428b8f0-4950-5176-9b15-a16d4dccc3da | note | Verifying Document - NDM / Clegg Report
aa408326-72d2-5db2-9779-1f9780278be5 | note | Frequency - 1 per backfill layer per 15m trench length. Minimum of 2 tests backfill layer per trench between pits/manholes
55baa83d-214f-55d4-a515-b2b744d467da | note | Verification Activity: Activity - I
1565a9de-acd7-55a7-bee4-ab67d56d629a | note | Verification Activity: By - SE
3382e817-6a28-577d-8653-2be0f10dfb15 | checkpoint | 3.02.17 - Compaction above Pipe
0f621c95-2add-5163-9e74-674f0236295a | note | Acceptance / Conformance Criteria - Only hand operated compaction tools shall be used until the backfill has achieved a depth of 300mm above the crown of the pipe.
cb8dbe72-2c7e-5a2a-8e84-ac948c72432b | note | Standard / Specification - PS 16.32
5e993aac-af3d-5c0e-b7ba-f7f7d54f8028 | note | Verifying Document - Site Records
68b95351-d29b-59e3-97b6-2cd5e950a0ce | note | Frequency - During Works
ac98194b-42f1-503f-b174-bde1d7e887ca | note | Verification Activity: Activity - S
6cdf8e68-eeac-52a3-b3fd-e8cf26a5a558 | note | Verification Activity: By - SE
51eb3361-8108-503c-8a25-987fd585578d | checkpoint | 3.02.18 - Pipe overlay zone inspection
d759fc60-4644-58f5-bd79-b55b5bd1fb89 | note | Acceptance / Conformance Criteria - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe overlay zone
41f61bb4-c281-5e16-92d2-15f1fa5eab78 | note | Standard / Specification - PS 16.32.3
53c317a1-55ba-55c1-82e1-8fc0cdfe0a82 | note | Verifying Document - Engineers Record
f299943b-7879-52a3-a141-0d281743d90b | note | Frequency - 1 per trench length (Between Chambers)
bd215c41-c17d-5954-9ec4-b311106ae3ba | note | Verification Activity: Activity - HP
cc936f89-e555-5592-a1c5-7752671b456a | note | Verification Activity: By - ENG
bd74d56a-352f-5342-982f-d30a401d4e76 | signoff | AUTHORITY HOLDPOINT
35acfe1b-9d28-5cb4-9eb1-8f3050ddfbcf | checkpoint | 3.02.19 - Pipe Overlay Zone Density Testing
ea4a7c21-2cd6-51ba-89f9-65f4083ee4cd | note | Acceptance / Conformance Criteria - Backfill material shall be built up in layers not exceeding 200mm. The Pipe overlay zone shall be compacted to a MDD of 90%
a786b17d-34ea-57ec-8ba3-7fef24b9424a | note | Standard / Specification - PS 16.32.3, PS 16.6
4b32e01c-ad41-5413-ac29-af993bd155bb | note | Verifying Document - NDM / Clegg Report
9f21ec6a-04d0-5ba8-96f3-1eb9421522e9 | note | Frequency - 1 per 15m trench length Minimum of 2 tests between pits/manholes
d93c0d3c-1206-53b2-8982-bb08eccc3924 | note | Verification Activity: Activity - I
50a17376-53cd-53d0-8940-c74e1ab03a05 | note | Verification Activity: By - SE
91558f9b-dbd3-5b49-8a78-7e78124ef5d3 | checkpoint | 3.02.20 - Pipe invert levels/lid levels at all drainage structures
aa555522-51f3-5980-b9d1-c3ab7c1e70fe | note | Acceptance / Conformance Criteria - Pipes shall be installed within 20mm of stated invert level (vertical tolerance) and within 50mm or 5% of the pipe diameter of proposed horizontal alignment (whichever is greater). Catchpits and catchpit manholes shall be located to align with proposed kerb and channel (or dish channel) and finished to be flush with the finished road surface unless otherwise specified on the Drawings.
aad2186f-af8e-5603-95b3-75a2c89579d4 | note | Standard / Specification - PS 16.34.2
a74d5719-acf4-58a9-9d3a-f363807a7440 | note | Verifying Document - Survey Records
0fa9e2a2-80d6-5268-9740-1a0c21764355 | note | Frequency - At the completion of each stormwater pipeline
3147a91c-0253-5526-a0a9-708fe114c933 | note | Verification Activity: Activity - I
03cc8ce8-f6f6-5939-a085-971d4562b8c9 | note | Verification Activity: By - SV
3cbaefad-09bf-5980-99ae-9f82d36421b2 | section | 3.04 Stormwater Structures General
55e0db49-0d55-5fcb-a32c-d06f9e360544 | checkpoint | 3.04.1 - Stormwater Structures Subgrade
7ccab956-c555-5c92-a515-ccd3161b2fa6 | note | Acceptance / Conformance Criteria - A hand Auger Scala / Shear Vane up to 4m deep shall be completed in the base of the excavation and the results submitted to the Engineer. The subgrade shall be CBR>5.
d1c3a282-502d-5571-9cb0-2708c6831439 | note | Standard / Specification - PS 16.32.3
7fb8daab-73b9-517e-9d03-e50aa11e5642 | note | Verifying Document - Scala / Shear Vane Results
37c7858f-1d66-55e1-95e2-8ba4a1fec8a3 | note | Frequency - 1 per structure
ab9c59e4-05af-515e-b1c4-49227fe82f7d | note | Verification Activity: Activity - I
3629fb0c-7009-5d28-a077-787874d9e25d | note | Verification Activity: By - SE
11df0ca5-2244-56ff-87cf-6389bd9bd635 | checkpoint | 3.04.2 - Stormwater Structures Bedding material
48bc291a-2a29-5bc3-906f-3cdac2399e31 | note | Acceptance / Conformance Criteria - Stormwater Structures Bedding granular material shall be compacted to MDD of 95%.
c46f0835-2b13-58d9-99e7-d82b75d1a056 | note | Standard / Specification - PS 16.32.3
b42f32fc-9bfa-5fb2-be62-057e44830231 | note | Verifying Document - NDM Results
29fd4438-97bd-5577-b172-a518d3a3a8bd | note | Frequency - 1 per structure
c62da838-5b40-56be-8866-a002ab4b97fa | note | Verification Activity: Activity - I
720c64e6-0ca3-59a3-8768-96eb4f76fe64 | note | Verification Activity: By - SE
edf4ceda-4a42-5d83-8430-f5df17c20e6e | checkpoint | 3.04.3 - Stormwater Structures Backfill
b34f1f7f-0938-5b21-a47f-6db328924c17 | note | Acceptance / Conformance Criteria - Stormwater Structures Backfill granular material shall be compacted to MDD of 95%.
d1c7cb98-8641-5341-994b-ea4470308fdd | note | Standard / Specification - PS 16.32.3
75e64ac6-029b-5e7e-ab2f-6d62438d5624 | note | Verifying Document - NDM Results
6f6b8403-ddb8-5d40-adf1-d4cc9f2ef858 | note | Frequency - 1 per backfill layer per structure
296e6018-bc51-5a85-a578-f14fc5cc21f8 | note | Verification Activity: Activity - I
15cce95e-fa47-5c7b-9032-921bd70bd231 | note | Verification Activity: By - SE
c39c3e78-c1aa-5dca-a3f5-3c587c96df60 | checkpoint | 3.04.4 - Subgrade Clay
ae0091af-8c0c-52cc-b75d-a35fa3f76837 | note | Acceptance / Conformance Criteria - If clay is present at subgrade level, then this should be supplemented with soaked CBR laboratory testing.
1db22515-8d3a-56b7-9dd8-77f0a46019d5 | note | Standard / Specification - PS 16.32.3
77029148-a510-56dc-88d6-c28059422f6b | note | Verifying Document - Soaked CBR
36143a61-3eec-534e-99a7-55ac2d9cbd59 | note | Frequency - Each Occurrence
eb3dbda9-3677-5a19-b28d-7e491ed5f611 | note | Verification Activity: Activity - I
a881e587-2b20-553b-9123-49e3bdebae1b | note | Verification Activity: By - SE
772516f7-046e-5c6f-aac8-fb5becb92a72 | checkpoint | 3.04.5 - Culvert CBR Approval
3c258f69-f678-52f7-9913-42fb49154f2e | note | Acceptance / Conformance Criteria - The contractor is to provide CBR testing of trench subgrade prior to placement of bedding and laying of culverts.
0c978519-93f2-565e-aad6-832f7c252596 | note | Standard / Specification - PS 16.38
f26024b5-c24c-542e-9adc-b46f6a06d840 | note | Verifying Document - CBR
414b1fad-73e1-5bc8-9d59-9cbde223fa67 | note | Frequency - Each culvert prior to bedding
8a7c2686-1478-51dd-8a5f-b6ead3cfc667 | note | Verification Activity: Activity - W
b311b341-d8a7-57cf-9f2a-03a65b60768f | note | Verification Activity: By - ENG
2b11378f-fb1e-5ce9-90ee-5cf3efd04f03 | section | 3.05 Catchpits (Structure)
31ff3eb2-aa65-5635-a88d-3fd640cbd3bf | checkpoint | 3.05.1 - Catchpits Base
7c12f643-54cd-5642-b419-a60cb10f0a3d | note | Acceptance / Conformance Criteria - Catchpits shall be constructed on a compacted, on top of a 150mm layer of compacted AP65 or GAP100 granular material.
4d7a6880-94e2-5dd5-87c5-acf5d37d6788 | note | Standard / Specification - PS 16.10.2
cfd7a3fa-c030-5be5-902f-e19786facbfe | note | Verifying Document - Site Records
3b50728b-9859-55b4-a133-214b3d0fd973 | note | Frequency - Each Catchpit
eb439e00-b472-5d4e-b1b9-909647a050e9 | note | Verification Activity: Activity - I
b97ed336-e7f3-586a-b7a9-76d5e23c013a | note | Verification Activity: By - SE
ec26eee7-2ffc-5274-9a64-37128cd44b24 | checkpoint | 3.05.2 - Precast Catchpit Sealant
caca2619-e854-52de-8466-ceb7c1b17f08 | note | Acceptance / Conformance Criteria - All joints between segments of precast catchpit risers shall be sealed with ‘Black Butyl Mastic Sealant – Hynds (MSR)’ or similar and approved.
5662f1dc-68c0-57c4-96a2-ab8b3cf29981 | note | Standard / Specification - PS 16.10.2
e3491805-ebf4-5a7d-9d6a-768e20f967dc | note | Verifying Document - Site Records
c1b760af-fdbc-54d1-ac9d-473503e15ed1 | note | Frequency - Each Catchpit
74fda00c-9175-57e9-9e72-c326c6f42529 | note | Verification Activity: Activity - I
5b4fd898-b0e4-573a-8f1c-5faacd3f59fd | note | Verification Activity: By - SE
feb0a3cc-ec88-5255-a059-11b948c8cfc2 | checkpoint | 3.05.3 - Catchpits Grates
f3063c57-e226-5f54-b6f3-63ee891fca10 | note | Acceptance / Conformance Criteria - Cast-iron grates and frames shall be set no more than 30mm lower than, but parallel to the cross fall and grade of the surrounding, finished pavement surface level. All grates and frames shall be haunched to lids.
afa108f9-36ee-549b-bee0-84858cac3fcb | note | Standard / Specification - PS 16.10.2
b9715cd7-3ddd-56a3-84b7-03434604bcda | note | Verifying Document - Site Records
db7af4b0-2966-5b17-8edb-d0fce08bab3b | note | Frequency - Each Catchpit
833ad2d4-0f3d-5158-98a3-cef60fb2b875 | note | Verification Activity: Activity - I
2a0daae5-4037-56fd-bb23-56fb57cd2535 | note | Verification Activity: By - SE
20499adb-cd8d-52ad-9503-f7ac36d5126e | checkpoint | 3.05.4 - Catchpits Sumps
82783ac0-0a33-54c7-926b-fb0accf22531 | note | Acceptance / Conformance Criteria - Catchpits must have sumps at least 450mm deep (below the invert of the outlet pipe level)
f07874f5-809f-5857-9ca1-dde377bad4d0 | note | Standard / Specification - PS 16.10
9811e13a-60c2-55cf-a626-05c28b8da90c | note | Verifying Document - Site Records
ba27d4c4-4877-5b94-adc6-c5dec1860b9e | note | Frequency - Each Catchpit
1cb8192a-31f2-5be6-afba-3ce6e4f421b0 | note | Verification Activity: Activity - I
09a245a3-b6ff-5b78-92c9-f795fb912fe6 | note | Verification Activity: By - SE
38a69e92-eb03-5781-babf-63bafa6f0463 | checkpoint | 3.05.5 - Catchpits Inlets
8fc438ca-6594-5b52-84ee-1bbf3c7d5221 | note | Acceptance / Conformance Criteria - All catchpits receiving stormwater from the highway shall be constructed with a back-entry inlet.
19206e38-5252-55d9-b766-ed46b3f4d212 | note | Standard / Specification - PS 16.10
617f5fe4-08cd-56a5-a9ed-2e6d64437fc2 | note | Verifying Document - Site Records
60babfde-8a7b-5821-876e-365eb6628c75 | note | Frequency - Each Catchpit
e16b2f58-8955-55e7-b3f8-a0bf1c481028 | note | Verification Activity: Activity - I
783f76e9-2b93-5db0-845f-1e21c8d64c5c | note | Verification Activity: By - SE
fbfd030e-e726-5b00-b683-815353d7d8ec | section | 3.06 Manholes (Including Catchpit Manholes)
4ea6a7a4-33ae-5695-82f6-c7b9a7aa7caf | checkpoint | 3.06.1 - Manholes Base
3a9e6f0e-79b8-5d80-afa4-286e1327281d | note | Acceptance / Conformance Criteria - Manholes shall be constructed on a compacted, on top of a 150mm layer of compacted AP65 or GAP100 granular material
f493d2b6-4b01-51c7-b4bd-b7b5abee8966 | note | Standard / Specification - PS 16.15.2
dec3f19d-bd7b-5bc5-98a6-18340d74e6bb | note | Verifying Document - Site Records
8c10f297-d8b6-58b1-b0cc-b291908bb792 | note | Frequency - Each Manhole
4e07cb12-774d-5d74-a75c-a7a17318ca90 | note | Verification Activity: Activity - I
acae7bce-bc0e-5278-b5d3-4c2c81856ed9 | note | Verification Activity: By - SE
830ba5c3-5241-5f8c-9d26-aee2aa04121a | checkpoint | 3.06.2 - Manholes Sealant
1d507ef0-acca-5a43-88c4-d1acd676ce68 | note | Acceptance / Conformance Criteria - All joints between ring segments of precast manholes and chambers shall be sealed with ‘Grey Butyl Manhole Sealant – Hynds (SM9020)’ or similar and approved.
4e2dce2e-e2b4-5031-8fb5-21ac1c0128fa | note | Standard / Specification - PS 16.15.2
c412922a-19eb-5c79-8071-400b7df951fd | note | Verifying Document - Site Records
c51f6de7-834a-56e4-aa11-a45cf597f87d | note | Frequency - Each Catchpit
89e41216-5fc5-5a4d-ac7b-b6e80627fabe | note | Verification Activity: Activity - I
fc8b90cb-5fbb-5cad-8ac4-af7ffe5f9e7b | note | Verification Activity: By - SE
65a61540-a274-5c95-993e-1bca70d687a4 | checkpoint | 3.06.3 - Benching
f95c7681-49b8-5df2-b050-183c6406024a | note | Acceptance / Conformance Criteria - Benching is required in all manhole structures unless noted otherwise on Drawings. Benching shall be 20MPa concrete and to a F4 finish. Manhole benching shall accommodate pavement subsoil drain connections where required.
1d794a62-7c5d-58c5-9714-015fe298b28c | note | Standard / Specification - PS 16.15.2
3347e862-c03a-52ab-9d9c-2a79228848a4 | note | Verifying Document - Site Records
f42162ea-77b6-5c48-9a5b-721d72594dc3 | note | Frequency - Each Catchpit
f2fe82f9-8dbd-5b31-ab79-7f8fb6e8871b | note | Verification Activity: Activity - I
f60e390e-e985-5b3e-8d40-dac7c9c4ecff | note | Verification Activity: By - SE
1b2b7647-ea00-550b-94b6-c3eb86c1e5af | checkpoint | 3.06.4 - Benching Fall
0cac811e-75f9-532a-b09c-a44cad9229f8 | note | Acceptance / Conformance Criteria - All side benching shall be formed with a fall towards the channel unless otherwise stated.
1097b43a-3ffe-57df-8568-ead8070fa6a4 | note | Standard / Specification - PS 16.15.2
74262943-c30c-56a4-bafb-64db4aae0de9 | note | Verifying Document - Site Records
b34fb4dc-ca10-5c46-a515-a7a0d16dec8e | note | Frequency - Each Manhole
f813fdc6-8eaf-51ae-b92e-d3902ff8bcf9 | note | Verification Activity: Activity - I
0360d584-5bab-5633-8f8f-c65954b27c4b | note | Verification Activity: By - SE
e2634fcd-64bd-5c88-986a-591133456f83 | checkpoint | 3.06.5 - Sealant
21cb44f5-1153-5b62-90ee-b4948ae6730a | note | Acceptance / Conformance Criteria - All pipe work penetrations through manhole walls shall be sealed using Epoxy Mortar or an approved equivalent type of permanent sealant.
3cc3eb22-7813-530f-8aa5-6ae338830655 | note | Standard / Specification - PS 16.15.2
59ebae16-ebd8-56f7-aa02-b87e2ef8cba1 | note | Verifying Document - Site Records
58e9733d-3a89-5204-ae3f-36a29763d73e | note | Frequency - Each Manhole
7e94f9b2-5165-5c4a-9957-f9bb127a161b | note | Verification Activity: Activity - I
7a9c04a4-d06b-559d-97ec-c27fb6692cc1 | note | Verification Activity: By - SE
011d016c-aafb-54b9-b1eb-bc32a59107a7 | checkpoint | 3.06.6 - Lids
7aa78c8f-122b-5ccc-917d-ff44c192c11c | note | Acceptance / Conformance Criteria - All solid cast-iron covers and frames shall be set flush with the cross fall and grade of the surrounding finished surfaces. All grates and frames shall be haunched to lids.
46ea94c0-a704-5d95-8387-8698484f51c9 | note | Standard / Specification - PS 16.15.2
1f3bc0d6-5be8-5873-a9e9-c6544a416ebe | note | Verifying Document - Site Records
f608c04d-9e1c-5bfc-a52c-999da51bef95 | note | Frequency - Each Manhole
7aa68f92-8526-588d-ab62-c690abfab4e3 | note | Verification Activity: Activity - I
f5d7d1b6-2b8d-579b-933c-8545e4c06196 | note | Verification Activity: By - SE
f97987d2-2d57-5b5c-a4fd-287d395bce0e | checkpoint | 3.06.7 - raised cover levels
df0a6082-b5e9-573c-a1eb-4417756b2a91 | note | Acceptance / Conformance Criteria - For new or existing manholes with raised cover levels, the height of the manhole access shaft (throat) shall be no greater than 600mm where access is required (all non-catchpit manholes). The shaft and any subsequent extensions to the shaft shall be constructed using either:
ef266951-f763-5fac-9123-b81939b21d05 | note | Standard / Specification - PS 16.15.2
82e191ee-3427-5ad3-a704-000251cc0625 | note | Verifying Document - Site Records
1cd684fd-7259-59b4-a745-bc1f6cf2f01f | note | Frequency - Each Manhole
ff52b000-0775-509f-9955-80514ffdb205 | note | Verification Activity: Activity - I
64c3f6d9-b360-539d-9a0f-8f406ab46004 | note | Verification Activity: By - SE
137e9184-dbbb-5055-85de-4e13f31d3b5e | checkpoint | 3.06.8 - Adjust Manhole Service Lid Covers
391775e4-fd9b-56c6-9f3f-159ce096b096 | note | Acceptance / Conformance Criteria - Following adjustment, the service cover shall be firmly held in place and shall not be 5mm higher or 0mm lower than the adjoining surface. The item shall cover adjustments + or – 300mm from the original height. Any adjustments exceeding these measurements shall be treated as a variation.
04334fc2-b281-51f3-8aa9-0a76cf293552 | note | Standard / Specification - PS 16.12.1
57287e33-c31e-55c1-a5d0-8ae74216966d | note | Verifying Document - Site Records
f5b7ab8b-269a-54a7-bfc3-75ff06b220c5 | note | Frequency - Each Lid
ccc852a1-41d3-5d1b-90e4-f782f972d478 | note | Verification Activity: Activity - I
963627e5-207a-51ad-9868-852410b6cc08 | note | Verification Activity: By - SE
2a566367-4568-59ef-8af5-b33af6cd82fd | checkpoint | 3.06.9 - Visual inspection of all Manholes
3e9bb3c2-f553-5292-961f-29cdcd544bae | note | Acceptance / Conformance Criteria - 3-6 months following construction, Each manhole shall be inspected. No evidence of identifiable flow infiltration, settlement and riser displacement or cracking shall be present
867b6da2-0105-570c-9e45-1e84db38098a | note | Standard / Specification - PS 16.34
c7293857-6920-5d24-95cc-56b8befaa828 | note | Verifying Document - Inspection Record
a0f5bb33-714b-5902-87e6-be5fdf9607a1 | note | Frequency - Each Manhole 3-6 months after Construction
d8c8ada0-1f73-5c3b-ad64-707803459d6d | note | Verification Activity: Activity - W
505eb47b-c74b-5bcb-985d-8f81b9bac215 | note | Verification Activity: By - ENG
27774e0c-99d7-5289-8467-16e09dd355ec | section | 3.07 Headwalls and Wingwalls (Structure)
a282b859-9ba8-5309-ac5f-cce9472c84c2 | checkpoint | 3.07.1 - Headwall Bedding
2bab5ccb-3cbf-57f6-8710-b2459902c1f5 | note | Acceptance / Conformance Criteria - Headwall aprons shall be constructed on a compacted, 75mm bedding sand underlay by 150mm layer of AP65 (or similar material as approved by the Engineer) granular material and compacted to a MDD of 95%.
91063004-0b29-50ff-b05e-821158bec0e8 | note | Standard / Specification - PS 16.13.2
82b3bf69-61dc-5cf6-bca7-7e387c6379ff | note | Verifying Document - NDM Results
b73fe472-3c42-5813-8fba-89f17bab39ba | note | Frequency - 1 Per Apron
8881594f-1fb1-5b9f-afa7-d37ce5091875 | note | Verification Activity: Activity - I
94340d61-1416-52e1-b978-f8650ee0935b | note | Verification Activity: By - SE
07fc3567-164c-5618-a44d-5368bfd158b2 | checkpoint | 3.07.2 - Precast and Cast in-situ Headwall and Wingwall tolerance
21f8fae2-c3f3-5adf-86e0-7393a663a12e | note | Acceptance / Conformance Criteria - +/- 10mm variance to vertical design set-out
5a5687cc-6e9a-5bce-93d6-38d9dd154e4f | note | ○ +/- 10mm variance to horizontal design set-out (values in accordance with NZS 3109: 1997)
86b8dbec-1541-5da5-8190-ed28920688b4 | note | Standard / Specification - PS 16.34
208c6c08-ec71-5a1d-9d54-701f09fcccae | note | Verifying Document - Survey Records
dc7f4cf0-5888-52fd-b014-035b78fea0ba | note | Frequency - Every Unit
e0a4a3b7-1c85-546d-80f0-d3d5193a7762 | note | Verification Activity: Activity - I
0f5c6158-e8c4-56c2-ada6-733e98d3831c | note | Verification Activity: By - SV
8068364e-520f-5fd0-991b-16023b2271ec | section | 3.08 Stormwater Concrete Capping (Pre Pour)
bd69386d-659e-5519-93df-1bd1697fd818 | checkpoint | 3.08.1 - Construction Joint Locations
5f47460c-17f6-5a16-82a0-d5da69d96d71 | note | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
bcdb9380-87ba-5b77-b134-cff7009c664a | note | Standard / Specification - Downer
7fcaf1be-2e8f-59fa-94fc-5a7bc498d040 | note | Verifying Document - Approval
f2cbab80-916f-5bf8-8fcd-14e744ff2e5e | note | Frequency - Prior to Pour
592d2188-3269-5697-a6c3-acbbf70737b1 | note | Verification Activity: Activity - HP
8b4c3044-7670-510a-9877-2fb346213beb | note | Verification Activity: By - ENG
1885b19b-fd69-523f-9265-6ecd08f19429 | signoff | AUTHORITY HOLDPOINT
f50d5944-adee-5c53-805f-e43deb1cbcd6 | checkpoint | 3.08.2 - Dry Pack Mortar
bc415a1b-696b-5a55-8143-ab5c161a66d0 | note | Acceptance / Conformance Criteria - Dry pack mortar where specified on the drawings shall be places as per the manufactures instructions.
3497142d-f243-5a8d-9be2-ce7568b448bc | note | Standard / Specification - Downer
f99c52e3-5888-5a4b-9bce-7354556879ec | note | Verifying Document - Pre pour
4c63d7de-d2f6-5dcd-a6c9-650d45058db5 | note | Frequency - Before Works
0a914d3b-42c3-54b9-9825-3359f3ae4990 | note | Verification Activity: Activity - R
53ee03dd-1ade-5cad-b017-c44bc5b48127 | note | Verification Activity: By - PE
7ddf1616-1eae-54b1-afaf-a7dbaf19d051 | checkpoint | 3.08.3 - Reinforcement Pre Pour Inspection
42a17dd3-d295-5d6b-b380-447c658db28e | note | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
2af99b23-dbfe-5ed0-87c8-ce749b036717 | note | Standard / Specification - Downer
9affa3d5-1486-542b-a9d2-ee8d51017ec7 | note | Verifying Document - Pre pour
3e50e346-575b-5748-b476-67754d8ebc63 | note | Frequency - Each Pour
0a3b6477-fa0a-57c6-9aa7-d4438541a7ae | note | Verification Activity: Activity - R
2384d2d0-d928-537a-bf85-fd5f2a402d49 | note | Verification Activity: By - PE
49afaa9c-fcb3-541e-a838-fe0a90e77ca3 | checkpoint | 3.08.4 - Pre-Pour Inspection
0c8f35e6-f474-5ea8-aed5-1ded1a659a16 | note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
070abcb2-7bf3-5d84-9c6f-33dcd92c65fb | note | Standard / Specification - Downer
66acced7-8b9f-5989-9f56-a0091a8b6302 | note | Verifying Document - Signed Pre-Pour
7b32fc0c-01de-5596-9243-19fd69a3df18 | note | Frequency - 48 Hours Notice Prior to Each Occurrence
e788a677-e575-56ea-983a-c85f93bb281d | note | Verification Activity: Activity - HP
43366cc7-9dd2-5ad0-9fe0-3fca307e02b1 | note | Verification Activity: By - ENG
bc0f02e9-b1ca-53bc-ac57-244188125592 | signoff | AUTHORITY HOLDPOINT
bbd94df5-4b0f-53f6-ae1b-aa72bd251ca6 | checkpoint | 3.08.5 - Delivery Dockets
02b4606a-efbc-5629-abaa-968be95213fb | note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
631c12cb-2d6f-508e-ad19-e9a7ce9788ae | note | Standard / Specification - Downer
3b998771-c19d-5c84-8f0b-40cc49fe060a | note | Verifying Document - Dockets
7fb6e36c-ba86-57a3-bf57-d0765b07e8eb | note | Frequency - Each Pour
4395b7f3-7ead-58ed-82e6-d5fb8519306b | note | Verification Activity: Activity - R
425eee7d-b0ef-505b-8ff7-088d243ed20b | note | Verification Activity: By - PE
4279327e-59cf-5451-83b7-3515969e2984 | section | 3.09 Stormwater Concrete Capping (Post Pour)
033f68b5-19da-576d-ab6c-0e1322ff0d66 | checkpoint | 3.09.1 - Post Pour Inspection
40c46004-a0d2-55b3-a8b8-8c3b33037ae3 | note | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
411daf79-3c25-57cf-ae76-78628629977e | note | Standard / Specification - Downer
a3e75254-9229-55f5-9653-09df3c558c89 | note | Verifying Document - Post Pour
78ab019f-3d34-52c5-b593-b4913cf5aa03 | note | Frequency - Each Pour
fb8ec1e5-57ab-53d6-b80e-f7c853b534f4 | note | Verification Activity: Activity - R
ed99a297-8f95-516f-8e5f-18f02a31ff66 | note | Verification Activity: By - PE
4f83fc6d-7c13-5e0c-8101-fc7d013048d1 | checkpoint | 3.09.2 - Construction joints
3eef2fc6-cb15-5b10-8ec5-92adcf30affc | note | Acceptance / Conformance Criteria - Construction joints shall be placed as per the drawings / agreement.
c4fe7329-89d1-5b92-97fb-946425b4de35 | note | Standard / Specification - Downer
8c200ebd-8252-5998-a899-76c41ab70a2e | note | Verifying Document - Post Pour
7109bee6-d043-51e5-9868-872c9082099d | note | Frequency - Each Pour
bbcc0d1b-9163-541c-8742-77a41ffea878 | note | Verification Activity: Activity - R
0e00c0a9-2e62-57ed-90f3-3b3db0efe016 | note | Verification Activity: By - PE
7bf1ae95-4187-5f9c-ad6a-07e234d10d2b | checkpoint | 3.09.3 - Defective Concrete Finishes
a826d68e-d3e9-5374-b462-7f774e9b20f6 | note | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
79d88ba9-d28a-5aa0-8420-589301486a67 | note | Standard / Specification - NZS 3114
51411ba0-df15-5afa-9058-69a514ce4bff | note | Verifying Document - NCR
5178402c-3803-58ae-9609-e3477c92a417 | note | Frequency - Prior to non Minor Repair
0c46167d-50f4-5af7-81da-627189c701b5 | note | Verification Activity: Activity - V
fab78af2-0726-52ba-b6d3-5e0ca7dceb51 | note | Verification Activity: By - SE
9677155b-1567-5603-9058-10b8155b0cfb | section | 3.10 16.35 CCTV Inspections
148112e0-6cfb-504e-8565-c9c49eeea73b | checkpoint | 3.10.1 - CCTV stormwater pipe
9b110b3d-b14a-500b-9f70-6bfee2d47466 | note | Acceptance / Conformance Criteria - Every stormwater pipeline 300mm and greater shall be inspected by means of CCTV camera at the completion of each pipe trench backfill and compaction and at the completion of Earthworks operations (or at a time otherwise agreed with the Engineer).
33ba4a54-0d0b-549a-803e-2113e2b980a5 | note | Standard / Specification - PS 16.34, PS 16.35.1
a10ba199-9940-51e5-bd48-fcffc08e0e56 | note | Verifying Document - CCTV Video and Report
e7ec6065-f0ef-5743-8684-aa5761cd04e3 | note | Frequency - At completion of pipes laying, backfilling but prior to final surfacing (Pavements, etc.)
c4d739e9-d404-5135-9f86-101444ebec1c | note | Verification Activity: Activity - I
6da0e0e0-2b67-5a23-be2f-a5acbdabd9f5 | note | Verification Activity: By - PE
1bb8f0ef-71a1-5083-bde8-eddaaedae0da | checkpoint | 3.10.2 - Pavement Construction CCTV Review
856f1831-3c20-5a03-ade3-5bb0c01dbeba | note | Acceptance / Conformance Criteria - Prior to pavement construction, The Contractor shall submit the pipe condition inspection report to the Engineer for acceptance. The pipe condition inspection report is to be based on CCTV for all pipes upon completion of backfilling the trench.
29ebfdb2-81c5-5080-8628-ddd2129a1380 | note | Standard / Specification - PS 16.37
b096192c-aecf-5fcf-9c3b-abf79330ef6c | note | Verifying Document - Engineers Acceptance
227d49f2-89ee-5142-aed3-b693f5bc28e4 | note | Frequency - Prior to pavement construction above Stormwater pipelines
da035812-d13b-5178-b416-e457d43c05cc | note | Verification Activity: Activity - HP
587f0ad7-ea70-570a-b2ad-7682d65e9ec1 | note | Verification Activity: By - ENG
c99c9d00-0420-58fe-b549-3dcfcc6d3958 | signoff | AUTHORITY HOLDPOINT
d25444e5-96eb-541b-becc-59f2adbdde88 | section | 3.11 As Built Records
2424709a-58b3-5a56-8303-6a65e7fc6226 | checkpoint | 3.11.1 - Survey Requirements - Stormwater Systems - Underground:
c597a341-c1b0-5fb6-bd9b-1b8e6bc1c3d0 | note | Acceptance / Conformance Criteria - The following items shall be recorded for asbuilt drawings.: Trench invert. Pipe/structure bedding and backfill compaction. Pipe/structure size, class, alignment, and level. Manhole and catchpit position, levels (lid and inverts). Outlet structures including position, levels, erosion provisions and fish passages.
178957d6-1815-56b9-8eec-b2ed2bbe4cff | note | Standard / Specification - PS 16.33
a470446c-240f-5e87-a0bc-9a7dfe0076f2 | note | Verifying Document - Survey
85b7f2fc-fca9-5599-954d-88a20587b9a6 | note | Frequency - All underground Stormwater Systems
297aa355-398b-5be0-87c3-36edee67c577 | note | Verification Activity: Activity - I
c1bef070-6ad4-58dc-b8ed-62f707bf1462 | note | Verification Activity: By - SV
d9c444fd-5ffe-5265-81e4-16abd7347357 | checkpoint | 3.11.2 - Survey Requirements - Stormwater Systems – Above ground:
54850b2d-ac5d-5b3b-8ff5-cfa01879fe43 | note | Acceptance / Conformance Criteria - The following items shall be recorded for asbuilt drawings: Treatment swales, wetlands, basin’s location, profile and grade. Diversion Drain location, profile, and grade. Trench excavation and invert. Line, levels and grade of kerb and channels. Rodding eye locations.
cf027f9f-d387-570b-80d6-c9c7a1996470 | note | Standard / Specification - PS 16.33
ce1e0489-3673-55e7-ab1c-47486e9ecb0c | note | Verifying Document - Survey
bba38cb5-4871-5fa6-829b-1af2c5118f4f | note | Frequency - All above ground Stormwater Systems
4f3331d3-fc36-58e6-aefb-4483ee8174ec | note | Verification Activity: Activity - I
d6f5d537-2878-5e6a-be62-f8c7ba769148 | note | Verification Activity: By - SV
f14b70a6-c1eb-4cdb-9441-b03840fd034c | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
2835c71d-8bb9-585e-96e7-b6bd7b4f2f91 | textbox | Contractor's Rep Name:
31b6c8be-6c3f-543f-80de-4272ca4fb71a | textbox | Engineer's Rep. Name:
1e54d08d-0f41-56ff-bace-40115249cbd7 | date | Date:
99df5f2e-a715-4415-84fa-7fb0f6aaf40d | signoff | Add Signature
b4760a82-9f3b-556c-af6f-76a939004fcd | checklist | ITP - Streetlighting - 105 - Rev A | itp | ITP - Streetlighting - 105 - Rev A
ac5ee1ee-5139-57b0-9c55-3196b7da263c | section | 3.01 General
4b182364-c9b8-5807-85b4-26cb6c506fc7 | checkpoint | 3.01.01 - Precondition Surveys
14944127-20df-5ef9-b360-3ea45cb6f3de | note | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
52c546e2-3803-58dd-9fde-4554a9e3c039 | note | Standard / Specification - PS 2.13
5f2013dc-6b69-5c5f-b9f2-5642377083d7 | note | Verifying Document - Precondition Survey
c2903486-276a-52f6-bd72-f4b3ed92d440 | note | Frequency - Prior to the Contractor taking possession of the Site.
921400a3-6509-529f-adf0-20885b798bbe | note | Verification Activity: Activity - H
ec20b5b2-fe9e-5f26-9c94-4dfa24c66824 | note | Verification Activity: By - PM
918efc9b-ead6-529b-8735-39e583dd468a | section | 15.01 Streetlighting Quality Assurance plan
a977b9b6-126d-57dc-b111-e2f82786b52c | checkpoint | Streetlighting Quality Assurance plan
5ec6f0dd-f086-5edc-92c9-da808a68edfb | note | Acceptance / Conformance Criteria - Provide a Quality Assurance plan to propose, establish, maintain, monitor and document a quality assurance system covering all aspects of the procurement, fabrication, installation and completion of the works.
50fe28c4-5c79-53bf-9114-3b0c3377624b | note | Standard / Specification - PS 22.4.6
590e6490-e368-586a-af70-83ff2b9484ee | note | Verifying Document - Streetlighting QA Plan
4af6bd41-1cf3-5c73-8fca-3a60c2345a36 | note | Frequency - Prior to Streetlighting
a2659496-1c51-540d-8b88-7f0842e6bea1 | note | Verification Activity: Activity - HP
d16ba403-b5a9-56d2-8257-acec463bf81c | note | Verification Activity: By - ENG
857c8f02-1c4b-5ce7-bd16-7c9671fc1c35 | signoff | AUTHORITY HOLDPOINT
bf765646-c79e-56cd-962c-be28ceb626ac | checklist | ITP - Streetlighting - 903 - Rev B | itp | ITP - Streetlighting - 903 - Rev B
e1dfdf0d-f448-5d40-9931-65785ee79785 | section | 3.1. - Safety in Design Analysis
307d39ee-3231-5ad3-8fc2-3b45fe9cec6e | checkpoint | 3.1.01 - Safety in Design Analysis
8b89d99c-65eb-56a3-ae8c-dd7d2113a126 | note | Acceptance / Conformance Criteria - Conduct a detailed safety in design analysis. Ensure the installation is compliant with the Site’s safety in design proposal including all regulatory requirements.
74abf515-409a-507e-bb6b-3d83c3de6f06 | note | Standard / Specification - PS 22.1.15& 22.3.2
feab34c1-79a0-5eda-a842-91be5a1cff09 | note | Verifying Document - Design Analysis report
5d37eb63-cd7e-546b-a5e3-c87a365f2db5 | note | Frequency - Prior to Construction
a4cc6791-5c49-5fc8-aa05-9ac4d234f3a2 | note | Verification Activity: Activity - H
88026bdb-a71f-571f-bb40-fc89771884af | note | Verification Activity: By - PE
5bb3dde5-d5d9-5773-a2e1-891fc2a76792 | section | 3.2. - Streetlighting Quality Assurance plan
6de94bce-091e-511a-ba32-9ffc116d33a3 | checkpoint | 3.2.01 - Streetlighting Quality Assurance plan
95105840-acfb-5454-b42b-7f314ff7e234 | note | Acceptance / Conformance Criteria - Sub-Contractor to provide a Quality Assurance plan to propose, establish, maintain, monitor and document a quality assurance system covering all aspects of the procurement, fabrication, installation and completion of the works.
2d0fafc2-db04-587f-a9b0-a6a5bad9a1b3 | note | Standard / Specification - PS 22.4.6
cbd8e3eb-c76c-525e-96cc-1f405289bc11 | note | Verifying Document - Streetlighting QA Plan
88d22070-e1ff-575d-88cd-35fdec5d7756 | note | Frequency - Prior to Construction
79829e46-2208-5ad4-ac69-8bdc57f1d9de | note | Verification Activity: Activity - HP
165400ce-66b7-5e8e-a48e-d2d3c54bfcdb | note | Verification Activity: By - ENG
b8b2db8a-d454-5204-9612-317adf33519b | signoff | AUTHORITY HOLDPOINT
28886096-4e36-5957-a5d6-583eed42eb49 | section | 3.3. - Montrose Box (MSB-NMB)
7be3f3af-0a81-57eb-a64b-d431b39718a3 | checkpoint | 3.3.01 - (MSB-NMB)
dad3b660-68ad-51f0-ab2d-622c09a61c51 | note | Acceptance / Conformance Criteria - Provide MSB-NMB shop drawings complete with wiring schematics for review and approval by the Engineer prior to construction.
56a8bfa7-e110-5742-96e8-d706d02ea192 | note | Standard / Specification - PS 22.1.7
e467846b-f967-5fe1-a3b1-5dc91020491e | note | Verifying Document - Shop Drawings
d040bd67-b35a-5a8c-9c9f-40d686400b56 | note | Frequency - Prior to Installation
15eb5684-5e83-5394-b8ab-8ad2f9cc0771 | note | Verification Activity: Activity - HP
65243919-c5a3-593e-a71e-036c2f54b416 | note | Verification Activity: By - ENG
e0c2fe71-5150-51a9-ae3b-29eb38828ebe | signoff | AUTHORITY HOLDPOINT
8bbfe05b-747a-5ad4-9b36-3f74b577dd9a | checkpoint | 3.3.02 - Hasp and Staple
09babadd-dc07-5e97-91e3-568b857a3fc8 | note | Acceptance / Conformance Criteria - MSB-NMB shall be fitted with a Stainless-Steel hasp and staple to allow for Waka Kotahi to fit their own padlock onto it. MSB-NMB shall be sourced directly from Montrose Foundry, Mt. Wellington, Auckland.
18689d8d-40a1-5e2b-adb5-9907c34bd143 | note | Standard / Specification - PS 22.1.7
44bec1af-e465-5b85-92d9-1df473571878 | note | Verifying Document - Datasheet and dockets
9ffabcbe-7bf3-5a19-9f60-16398967f671 | note | Frequency - Prior to Installation
7c05d107-ee0f-5ff6-a94c-707f01302685 | note | Verification Activity: Activity - I
336a4ef6-cb42-5800-87b3-36687b3577a3 | note | Verification Activity: By - PE
68c6b2b3-1b9d-58ad-9940-e1ae1c2eaaaf | checkpoint | 3.3.03 - Metering
23991eb9-362e-5044-a726-eb24d236c4a7 | note | Acceptance / Conformance Criteria - Liaise with the client’s electricity retailer for the installation of their three-phase meter within the metering compartment of the new Montrose Box.
ac3bb863-f70c-52f5-8e26-0e3372e7de53 | note | Standard / Specification - PS 22.1.9
179ba631-9cf1-5b01-8c15-0cc3916d9138 | note | Verifying Document - Comms
b8df60e9-ecef-5471-9e73-54232fe06c6e | note | Frequency - Prior to Installation
1141fecb-b923-577e-81a5-29b07fccc368 | note | Verification Activity: Activity - I
0bfd854f-cb3b-5356-9435-6d7aebaf1c70 | note | Verification Activity: By - PE
3be29dcc-1dba-5024-a259-181202824d12 | checkpoint | 3.3.04 - CCTV Compartment
47635e1a-b0fa-5532-b6b9-774e55e28ccf | note | Acceptance / Conformance Criteria - Allow for a CCTV Compartment withing the Montrose Box. Provide a 10A double power outlet within this compartment for future use of CCTV equipment. CCTV Compartment to meet NZTA requirements.
2a7ed634-183d-5033-a7bb-9817fa2bca1d | note | Standard / Specification - PS 22.1.10
d3b0839c-cdce-53aa-9a5c-51dfe6e692ff | note | Verifying Document - Datasheet
25f74cf7-3f05-50e4-8264-713bbd8be4b4 | note | Frequency - Prior to Installation
651ea506-19f8-5613-a655-839d293bef5c | note | Verification Activity: Activity - I
1b7ab34b-9e25-52ce-a64a-22fc0b4ff6ec | note | Verification Activity: By - PE
a8ef432e-2dc2-5f98-a193-6b5daa8afe46 | checkpoint | 3.3.05 - Earthing, Bonding & Surge Protection
832b3628-7d30-535c-bb7d-202622e9385d | note | Acceptance / Conformance Criteria - Install an earth electrode in accordance with the in AS/NZS 3000. Install new Earth Bar and Neutral Bar c/w MEN link.
735e8656-9d0c-5008-b0f7-166f3703b548 | note | Standard / Specification - PS 22.1.11 & 22.6.10
067c2fe0-3d3f-5636-a767-8d2832549f1e | note | Verifying Document - Site Record
e31e4f59-b8df-54e1-a7f7-d14ec10faa84 | note | Frequency - Prior to Installation
cf28b61d-da40-5ece-be49-cd236766e210 | note | Verification Activity: Activity - I
e46aba8c-ae47-5b57-9814-5d36eadc5bfd | note | Verification Activity: By - PE
2a97f45d-145b-5d8a-bb12-9fc7157a95fd | section | 3.4. - Lighting Equipment
5c9fa16a-9d46-5e99-962f-7f1385f3c8c8 | checkpoint | 3.4.01 - Design Drawings
095e00e4-0eb1-5e7b-a177-9638afe418b6 | note | Acceptance / Conformance Criteria - Provide drawings of luminaire design and pole locations for review and approval by the Engineer prior to construction.
f398f91f-dbaf-5661-aabf-6cff8e542511 | note | Standard / Specification - PS 22.1.14
8b2c29f6-e84c-501c-92d3-c872fb1de3a6 | note | Verifying Document - Drawings
a61d6787-3f16-51bf-84db-9d884c2b7887 | note | Frequency - Prior to Construction
205d27fa-40c3-576a-a33f-718c99148d12 | note | Verification Activity: Activity - HP
c517acb5-dd2e-5ded-aeac-5a674fd604f1 | note | Verification Activity: By - ENG
dc556589-b616-5074-861d-602ea49fb4af | signoff | AUTHORITY HOLDPOINT
c68f167a-4012-5f24-bab6-be7d64678b18 | section | 3.5. - Welding
04342a2a-887d-584d-980a-a3c44105e569 | checkpoint | 3.5.01 - Welding
6488d3db-9bca-5042-b6ea-4c74a26336a5 | note | Acceptance / Conformance Criteria - All welding shall be performed by qualified and experienced tradesmen in accordance with relevant New Zealand or Australian Standards, with the engineer having the right to request certification and welding experience, and, if concerns arise about welding quality, to request at no additional cost X-ray and/or ultrasonic testing of up to 10% of all welds selected by the engineer, with any failures potentially requiring additional testing.
5362db31-ed7e-516c-beb7-3034226d19a2 | note | ○ All welding is to be completed before any corrosion protection treatment is applied.
352072c9-ab26-5d7e-b336-910de2d37d23 | note | Standard / Specification - PS 22.6.6 & 22.7.1
d43a34cd-ac62-5681-a572-8b6bb6df11e2 | note | Verifying Document - Welding Certificates
e7dfff8d-662c-551c-bcc2-fee072282dd4 | note | Frequency - Prior to Construction
a9ff8a00-11fd-5b67-b12a-8ccc43aceb5c | note | Verification Activity: Activity - R
89f2fda0-5d9e-5b0a-92f6-205abd142839 | note | Verification Activity: By - PE
840d33b8-3b32-592a-bc42-0ead8942733f | section | 3.6. - Corrosion Protection
aa45e653-8dfd-56b9-90d5-392a09ffe5a4 | checkpoint | 3.6.01 - General
72896e6b-1496-553e-9ca1-917c3faf53d3 | note | Acceptance / Conformance Criteria - Notwithstanding anything to the contrary in this specification, where possible all items of plant, equipment and materials shall be manufactured or supplied in materials that will not suffer corrosion. Appropriate materials include galvanised steel, aluminium, fibreglass, stainless steel, etc. All support steelwork, fixings and other galvanised steel shall be hot dip galvanised. The use of electro plated fastenings for external works is not acceptable. All welding is to be completed before any corrosion protection treatment is applied.
0bbb8b27-14a2-58b5-9f7e-d94f70b472bf | note | Standard / Specification - PS 22.7.1
9e754e4f-a430-568c-b84e-ae36fffee793 | note | Verifying Document - Datasheet
1d04f223-a0c0-5ea1-946b-11b1600982f9 | note | Frequency - Prior to Construction
ae758830-b599-51f1-a8fa-fa2ab6e7b087 | note | Verification Activity: Activity - I
08f19036-1e09-59d1-aeea-66a8e3d5f8bf | note | Verification Activity: By - PE
56ae953b-82cf-54a9-aa9d-11fd0888f179 | section | 3.7. - Painting, Protection and Identification
16b29004-1be5-5d55-8c4f-cf49624e165c | checkpoint | 3.7.01 - Environmental
3c158550-9ad7-5f9d-8e25-b380eb9b22c0 | note | Acceptance / Conformance Criteria - Select painting and finishes in accordance with the area environmental conditions.
344b6e04-c920-51bd-89db-e058b62aa80e | note | Standard / Specification - PS 22.8.1
c6f21874-db27-55a8-91ce-42db563646ce | note | Verifying Document - Datasheet
335abc26-4098-5add-887e-77be938380ac | note | Frequency - Prior to Painting
900e38da-f633-5753-9305-815674e43b71 | note | Verification Activity: Activity - I
93e7e26b-d80c-5d7b-8e5f-f0d91f2b146c | note | Verification Activity: By - PE
8aba94e4-1df7-5958-b829-2d64584b485a | checkpoint | 3.7.02 - Compliance Review
14f5f3a9-967f-5cff-b65b-7e3e7797ea9f | note | Acceptance / Conformance Criteria - Review the risk assessment and statutory and authority requirements completed as part of the system testing, commissioning and handover requirements and provide labelling and signage as determined.
38c3bcd1-1973-574e-b073-b2bee52972d9 | note | Standard / Specification - PS 22.8.1
f604e0d0-097a-5f09-866c-71863841e911 | note | Verifying Document - Datasheet
8b57db79-c936-55b6-8d02-940c3da87244 | note | Frequency - Prior to Painting
1bbcc248-a321-5d14-92ce-3e6402bc7068 | note | Verification Activity: Activity - R
dfca0a15-69c6-5c6c-9ed8-eb6f30f51a40 | note | Verification Activity: By - PE
e409c28e-e2ee-583d-89c3-cef6ad2ef3c7 | checkpoint | 3.7.03 - Colours
b0f652aa-80be-5403-bfd1-7ff206147c07 | note | Acceptance / Conformance Criteria - Paint colours nominated are to be in accordance with NZS 5807
e32987fb-2ce5-52e1-887f-355eb36055e1 | note | Standard / Specification - PS 22.8.6 NZS 5807
34e93b68-df2b-572c-b599-d2067ad6d004 | note | Verifying Document - Datasheet
a2885161-7868-53bc-940e-7762d71df3de | note | Frequency - Prior to Painting
f2bad3a8-dbf0-5bfd-af8a-75c8df9c4b78 | note | Verification Activity: Activity - I
c8bf7c47-493b-5bb1-a6f6-f57f73ee30cf | note | Verification Activity: By - PE
a5fe9d65-9ded-5735-934e-03824ce957c8 | section | 3.8. - Underground Services
a0c84950-dcb1-5746-aff4-c432748d2ad3 | checkpoint | 3.8.01 - Ducting
7bb32db7-84db-5798-9076-3512d047123d | note | Acceptance / Conformance Criteria - Unless shown otherwise all buried ducts shall be the sizes and quantities as indicated on the layout plan. (DIA. 50mm) (DIA. 100mm)
8ca05f73-8158-513a-aeb1-f91c292975bf | note | a) Use heavy duty HD PVC conduit for underground services. Use best practice PVC where possible.
e8e28d47-5ffe-5004-8f3f-1873a43c3d96 | note | b) Colour: Orange for all conduits containing consumer mains, sub-mains or final sub-circuits cabling.
a4a30cf0-4308-5612-b766-267006f0bd61 | note | Standard / Specification - Road Lighting Ducting Layout, PS 22.12.8
2e0069fe-705d-5810-9009-da57592c3352 | note | Verifying Document - Datasheet
05311528-4b4d-5ee6-a869-84f005065342 | note | Frequency - Prior to Installation
4940d2af-8c84-554c-94b0-9640e9051461 | note | Verification Activity: Activity - I
d13afd3d-d64e-5504-a7c7-3f4217c34afa | note | Verification Activity: By - PE
34541f8d-12d1-52a7-abe3-b7172bf428a1 | checkpoint | 3.8.02 - Warning Tape
a12b791c-4680-55d2-b61d-02e06d05db52 | note | Acceptance / Conformance Criteria - Provide orange marker tape complying with AS/NZS 2648.1
a2f457ae-2d1d-577d-a20d-604a11b626e6 | note | Standard / Specification - PS 22.12.9, AS/NZS 2648.1
5505f0cd-d55a-5e0e-bd9f-a6daca7cbd79 | note | Verifying Document - Datasheet
dec8fc02-4681-5363-97ea-f719ef27f005 | note | Frequency - Prior to Installation
f3997441-4a44-5eea-a073-19f4818cf4bf | note | Verification Activity: Activity - I
421c0cde-7ff5-56f7-b958-da2a98943d6d | note | Verification Activity: By - PE
e004ab01-acbe-5443-92f8-c0bd596d1087 | section | 4.1. - Existing Underground Services
f5d6fa37-4c51-58b6-92b2-37a2da9c36e0 | checkpoint | 4.1.01 - Existing Underground Services
edd9c07f-3d36-5ed0-955f-af4f58f6da74 | note | Acceptance / Conformance Criteria - The contractor shall undertake a comprehensive services identification program prior to beginning site works. This would include as a minimum, review of all service providers maps and drawings, a site scan, and if necessary, a scan using GPR (ground penetrating radar).
59fc6ca4-811f-5488-a610-668b9af5def4 | note | Standard / Specification - PS 22.6.4
99433fd1-5cf0-5acd-8c7d-1ac4008d80fa | note | Verifying Document - Site Record/Survey Record
237d1b1b-3e44-5718-a84a-f0859d4a676f | note | Frequency - Prior to Construction
f9d067a0-3bc8-599f-8116-7fd0112c18d5 | note | Verification Activity: Activity - R
9e4c2f51-5d9f-5c9e-be76-9207939bad99 | note | Verification Activity: By - PE
a3b6c300-8b48-52e1-a2b8-51c633d791cb | section | 4.2. - Survey
9e75368d-d900-5b2f-8522-74f3dca84b15 | checkpoint | 4.2.01 - Set-out
5aff5e02-f558-5b34-a90a-a225c65e87ac | note | Acceptance / Conformance Criteria - Light columns set out as per design locations.
ccc35a7b-a2cc-5df1-93dd-d873f8104d81 | note | Standard / Specification - IBEX Lighting Plan
b1b39f66-5987-5a33-adc9-954b1eb0803b | note | Verifying Document - Survey Record
cc4863bc-f61c-57bc-b086-b9bf61de0023 | note | Frequency - Prior to Construction
f64f3fe5-743c-5f38-8de0-cce9f6649d27 | note | Verification Activity: Activity - R
eabbb61b-d648-58c1-9fa6-2362bc75440c | note | Verification Activity: By - SV
0e97a9d8-b5d5-5b47-8e12-15aefb8b302b | section | 4.3. - Underground Services
00bfa1b1-fbbc-58c6-8228-8fd6c651f347 | checkpoint | 4.3.01 - Trench Excavation
fa2d72e4-f435-54ba-bcbd-33a4eb03fb03 | note | Acceptance / Conformance Criteria - Excavate trench and lay 50mm sand bedding and free from obstraction
a945b395-ba89-58d0-bc26-1fc58dc00dd6 | note | Standard / Specification - PS 22.12.8
f235ea5d-218b-50a8-a812-69c441a64bd4 | note | Verifying Document - Site Record
78273b1c-af7d-5698-84e9-2e35b881121b | note | Frequency - Where Required
21d500ca-1cd4-5195-a8ae-4401a22dc4c1 | note | Verification Activity: Activity - I
00915434-e861-58ea-babe-7a039339a9cc | note | Verification Activity: By - SE
0254eb66-8bd1-5f65-a204-face5086c97d | checkpoint | 4.3.02 - Ducting/Conduit
095a241b-a557-5419-b8c0-7d5209354dfb | note | Acceptance / Conformance Criteria - (a)Separation from LV conduits: Minimum separation between conduits shall be no less than 50mm from other conduits and no less than 100mm from boundary of the trench. Sandy loam is required for building and separation.
508227a1-95e0-57f8-8d76-f8ea779a5133 | note | b) Depth: Conduits shall be buried in trench at a depth no less than that nominated in AS 3000 for the method of installation, with all bends being slow radius bends.
849a8ee7-d3cc-5d21-8d99-094fe1801138 | note | c) Separation from other services: Maintain separation from other services running in parallel and crossing electrical installation as nominated by relevant standard (e.g. AS/NZS 3500 for water services, AS/ACIF S009 for telecommunications, AS 5061 for gas services, etc.).
7248f09f-0ec9-5394-8fdc-64c759a604c0 | note | Standard / Specification - Road Lighting Ducting Layout, PS 22.12.8
e8f82c0b-fbab-535b-b022-15c13e38c55e | note | Verifying Document - Site Record
ef12903f-4a7c-5a08-bfc9-0f1e03ec81ef | note | Frequency - Where Required
29363c44-079e-542a-a3f4-54bce3a8b002 | note | Verification Activity: Activity - I
658f5fb9-e203-5723-9eca-ba0b277b03e0 | note | Verification Activity: By - SE
6933ca64-6484-59cf-a90e-f0f3f84582e9 | checkpoint | 4.3.03 - Survey As-Built
fac666bb-03f2-5e18-be39-dd675b96135a | note | Acceptance / Conformance Criteria - Accurately record the routes of underground cables before backfilling
3554c3ac-5f6f-50d2-855a-8415e47095aa | note | Standard / Specification - PS 22.12.9
05b08c1f-dfb8-5aa8-8335-a9b47cda6d63 | note | Verifying Document - Survey Record
17da8a6a-715d-57d8-b7c1-166e7eb624d4 | note | Frequency - After ducts are Installed
553fbbe3-2a90-506e-b988-a0b755e92322 | note | Verification Activity: Activity - H
84a1197d-7118-5d7e-bc8b-475f5554d89b | note | Verification Activity: By - PE
685f02ad-1fcb-5dd0-a3be-2efdfeb2a119 | checkpoint | 4.3.04 - Backfill
14875e7d-acb8-5380-bf57-338109bdfdf4 | note | Acceptance / Conformance Criteria - Backfill trenches with sand as soon as possible after approval of laid and bedded service to a height of 300mm. Place the sand in layers < 150mm thick and compact to the density which applies to the location of the trenches to minimize settlement,
495c4aff-5d3b-5cbd-b525-981138171dd7 | note | Standard / Specification - PS 22.12.8
157b6ccd-1a65-50d3-836b-0178c3a1b2dd | note | Verifying Document - Site Record
f3f24ba3-0093-59a4-b1a3-dbc7cf2bfdb3 | note | Frequency - Where Required
31e820eb-44c3-5dee-9048-b850d0a70fab | note | Verification Activity: Activity - I
3061a857-32ff-58d6-be22-96049effd190 | note | Verification Activity: By - SE
f8975094-aa7f-53e3-aae2-ba8fc3031a52 | checkpoint | 4.3.05 - Warning Tape
28de7278-04f9-5ec2-b639-d02c5f1de581 | note | Acceptance / Conformance Criteria - Install orange marker tape complying to AS/NZS 2648.1. Install marker tape at 150mm or 50% of the depth of burial, whichever is greater, below finished ground level.
4dac0845-87a9-5445-91c5-0a8c322d0983 | note | Standard / Specification - PS 22.12.9
aba50031-fa91-5017-9ddd-1d5694a17664 | note | Verifying Document - Site Record
d9b12438-43e9-5e90-8eb0-ae6cc7282c59 | note | Frequency - Where Required
e154251a-fea2-5971-a19b-944b4f7c1879 | note | Verification Activity: Activity - I
3595378b-4d11-5ad8-a61d-2f59d160c405 | note | Verification Activity: By - SE
841b1835-8c8e-5ca5-bd70-970a10e99ee3 | section | 4.4. - Lighting
759a044d-e973-5a7b-81c0-ef9baae5afcf | checkpoint | 4.4.01 - Shear Base
5d00bfb7-19ca-5150-a5d3-a14e8860baa5 | note | Acceptance / Conformance Criteria - Ensure the shear base is installed as per the NZTA M26 specification and in the correct location as per the latest IFC drawing.
2d87b1dc-9215-5d99-aea6-ecc2b2032f30 | note | Standard / Specification - NZTA M26, IBEX Lighting Plan
54826512-bd73-5160-a0e0-065694be0604 | note | Verifying Document - Site Record
c9ca5705-7790-553d-8571-5fbfd5328f26 | note | Frequency - Where Required
057c784a-80a1-5198-9077-ce36c112f05c | note | Verification Activity: Activity - I
e818e6f6-b8d2-5855-a97a-a0de1bfc4118 | note | Verification Activity: By - SE
8c9c1497-1356-5c5c-8bba-9169c8079575 | checkpoint | 4.4.02 - Column Installation
193c0d7e-c568-50a0-82d9-e0d9d9172ef2 | note | Acceptance / Conformance Criteria - Columns shall be positioned 1.0m behind the kerb unless stated otherwise or advised.
4316c88e-7d07-5035-9acf-4a994f200894 | note | Allowable tolerances of the column location are:
c16acce1-868c-5200-b5b2-0a06d1094293 | note | A) 0.5m Parrallel to the carriageway
045be0c0-acd4-5d84-a08f-32a3a318571a | note | B) 0.2m Perpendicular to the carriageway
f1411082-f884-581b-918e-37c29ae9ee9c | note | C) 0.2m Vertically
ce3f2aff-7ca7-5d55-a9d7-bfdc13d3943b | note | ○ Ensure columns are oriented correctly and have the correct outreach arm lengths.
a1441cca-e6b5-5104-976c-89001fcf9a86 | note | Standard / Specification - IBEX Lighting Plan
f84550e6-30eb-5220-9ffa-cce115b8698a | note | Verifying Document - Site Record
7e90effe-782b-5e02-994c-c36246f87cf1 | note | Frequency - Each Column
dca78346-fe48-5162-90f2-dd66cc507d67 | note | Verification Activity: Activity - I
54d49b35-ca36-5663-aa6a-526ce413c8b4 | note | Verification Activity: By - SE
5ce24536-c4f7-5611-8fc1-534057409fcb | checkpoint | 4.4.03 - Luminaire
54f9b4e3-11af-59b2-a6d7-ea9965ff3cfc | note | Acceptance / Conformance Criteria - Ensure the correct luminaire type and tilt angle is installed as per the latest IFC drawings
b13ab339-0818-5e70-9027-e718949dae57 | note | Standard / Specification - IBEX Lighting Plan
2858aa6f-de34-5b2a-91a3-a3bf268c7a4a | note | Verifying Document - Site Record
c536b2e2-e0d9-5479-9870-9a2b35d27892 | note | Frequency - Each Luminaire
56a70913-a79b-5bcf-951c-6c1a71c22887 | note | Verification Activity: Activity - I
d641e2ae-e550-5ed8-8757-7f100ca7eab6 | note | Verification Activity: By - SE
1f68b460-fa11-57a1-8c3d-83197fa2bc20 | section | 4.5. - Montrose Box (MSB-NMB)
bbdaa859-f270-50b2-8358-320181da1ca0 | checkpoint | 4.5.01 - Montrose Box (MSB-NMB)
c2706842-0e75-53e6-8c40-9d0f5bc0bf52 | note | Acceptance / Conformance Criteria - Install MSB-NMB as per project specification, Installation and commisioning ITP and the Electrical Services drawings.
a6fe6af2-ce22-5d83-86dc-fdd328156983 | note | Standard / Specification - PS 22.1.7
13fc4f40-8de2-5b9d-b81e-db4612315488 | note | Verifying Document - Site Record
54fa19f6-c108-5ab9-9705-70c0a5216999 | note | Frequency - Once
4e83d3f9-3deb-5f20-9eb2-4127efdfcec7 | note | Verification Activity: Activity - I
94798367-0492-5851-b943-21cbc53f2585 | note | Verification Activity: By - SE
2da89b60-997f-58e1-98c5-8f176291076a | section | 4.6. - Painting and Protection
20799dd2-22c2-5db7-86e7-6e9a3b547e09 | checkpoint | 4.6.01 - Preparation of Surfaces
70cb1f7c-c61e-5a09-b2d7-bd29f186da98 | note | Acceptance / Conformance Criteria - Preparation: all surfaces shall be prepared by thorough cleaning of all dirt, grease, scale, welding flux and corrosion in accordance with AS/NZS 2312.1. For galvanised surfaces that have been subsequently cut or welded, prime the affected area with organic zinc rich coating for protection of steel to AS/NZS2312.1, two pack or accepted alternative
c4bb5395-dd8e-5e31-a959-d414d675ed54 | note | ○ Prime/undercoat all surfaces. Galvanised and non-ferrous surfaces must be etch primed.
4726106a-445b-5c89-a4a8-9dba4f09b6b9 | note | Standard / Specification - PS 22.8.3
e7200ea7-cc4a-5493-ba4a-046fb798de7b | note | Verifying Document - Datasheet
252c1a8d-71ff-594b-a820-126fab373f83 | note | Frequency - Prior to Painting
257e4b5e-df81-5c90-b9ca-6f29692d4fdf | note | Verification Activity: Activity - I
c7fc7563-697f-5876-a29a-59496277e2d8 | note | Verification Activity: By - PE
6b68f108-dd75-5c86-a9f3-3b79d2553e0a | checkpoint | 4.6.02 - Application
60572689-2d18-50a3-8026-e18e96b9a358 | note | Acceptance / Conformance Criteria - Apply the first coat immediately after substrate preparation and before contamination, and follow all paint system applications strictly according to the manufacturer's recommendations.
aa2b40a7-e392-5a72-bc2f-53c0e099f0b2 | note | Standard / Specification - PS 22.8.4
85d86c0c-8af6-5256-910f-aacdf412f059 | note | Verifying Document - Site Record
1adef6e9-b0f1-585c-9620-abef599a032e | note | Frequency - After surface preparation
66ff874a-c744-5df7-acae-353d07613d5a | note | Verification Activity: Activity - I
bc7cebc5-21b7-5ffc-9176-8d0c65ad4451 | note | Verification Activity: By - SE
166360d1-9388-54e5-a005-0d9fc1903196 | checkpoint | 4.6.03 - Finishing
314eaee6-88cf-5840-9235-844f22d958f4 | note | Acceptance / Conformance Criteria - Concrete Bases: 2 coats synthetic emulsion paint
8c561367-1880-582e-b2b8-ad1ffb0df841 | note | ○ Equipment Panels/Switchboards: 2 final coats full gloss enamel (c) Equipment: Factory spray application
a928d6c3-0200-5619-973c-00f1c7e1fde3 | note | ○ Other surfaces: 2 final coats full gloss enamel.
26580671-2fe3-5e00-b4d3-49806eb65dc4 | note | Standard / Specification - PS 22.8.5
bce47e6d-0566-52b4-ba30-1527cdf1ecfa | note | Verifying Document - Streetlighting QA Plan
03699c68-2e94-54e7-8050-d6bfe978e37f | note | Frequency - Prior to Construction
6787d926-bc45-5eb1-89e0-11af8a1cbc18 | note | Verification Activity: Activity - I
1b1c35a1-cd49-5aad-b152-1a4ae4035b50 | note | Verification Activity: By - PE
d4e69d02-1d12-57ca-b96a-a503419d380f | section | 5.1. - Survey
814085ad-2345-5b57-8339-0c8209d82ce1 | checkpoint | 5.1.01 - As-Built Drawings
ae8cc8bd-75f3-50da-8234-fa89d15a911f | note | Acceptance / Conformance Criteria - As-builts reviewed and submitted showing final location of all poles.
e3c43e59-b183-57ef-bd57-a1eccce2898b | note | Standard / Specification - PS 22.9.4
d5f9104a-c07f-5aa7-be60-a1c7547f0390 | note | Verifying Document - Survey Record
1ff52c34-db84-5c78-ad06-f5dd381f1eb4 | note | Frequency - Post Works Completion
15fd6dec-fb47-53c9-99f8-cdaef6fc1074 | note | Verification Activity: Activity - R
dc106640-fa84-577c-b007-a1964dd24ed8 | note | Verification Activity: By - SV
eb2c1484-6cf5-51ee-a6de-325bc1f6071c | section | 5.2. - Testing
598b708d-aa9f-517d-afb4-938cd4d042d3 | checkpoint | 5.2.01 - Electrical Certificate of Compliance (CoC)
7dbd875c-2acc-56d4-be23-5b8c8ea7edcc | note | Acceptance / Conformance Criteria - The contractor shall provide a CoC for the electrical installation. The certificate shall record all test results including insulation resistances, earth continuity and earth resistance. Detail to be included on the CoC is the measured prospective short circuit current for each outlet, switchboards and termination point,
696ba1e3-9362-595f-8255-b73939a9de9f | note | Standard / Specification - PS 22.6.11
0a540a84-1c2e-5c17-ae14-23c57f1d342b | note | Verifying Document - CoC
ad1e12f4-c781-5c3c-afdf-d39130486bba | note | Frequency - Post Works Completion
34d603a5-a2a5-5499-b192-c8f04b247c42 | note | Verification Activity: Activity - R
68684866-1bbe-5786-9d3e-bdef99319628 | note | Verification Activity: By - PE
190d70fc-2ff8-57a9-9daa-1db829a83db8 | checkpoint | 5.2.02 - Twelve-month warranty period
8582cfcd-cab4-570c-9c30-7614cb62d4fd | note | Acceptance / Conformance Criteria - Provide twelve (12) months statutory testing, servicing, maintenance, remediation of defects and warranty of all services systems and equipment installed under this contract from the date of Practical Completion
76f97a3e-ef81-5eb5-8659-4316ed86934a | note | Standard / Specification - PS 22.1.15
691f161c-5e5f-50d6-907d-f4b1a252f2c7 | note | Verifying Document - Warranty
aa762e9d-b73f-53a6-8122-b0f666842e14 | note | Frequency - Datasheets
fa0f5cde-154e-5288-9c78-56b2c4b6b7b9 | note | Verification Activity: Activity - R
0ae7b1f2-9990-592e-8756-d3acb81ffc57 | note | Verification Activity: By - PE
1f64854c-1c63-5f27-8b5e-120ca1d8d479 | section | 5.3. - Certification
e4fd88be-fac7-5e2e-a95c-f793a3077ff6 | checkpoint | 5.3.01 - Final Certification
ec4fbb18-4044-5a09-8f6d-a756fea8ec45 | note | Acceptance / Conformance Criteria - Obtain final certification of the installed systems by an independent electrical inspector approved by the Electricity Workers Registration Board.
9484c330-8fc5-5e0a-8040-d338120737d8 | note | Standard / Specification - PS 22.1.15
48666ff7-66f1-5159-8dbb-1804d6025159 | note | Verifying Document - Final Certificate
ec5e90a4-e3da-5ee5-94c3-f804d568ac19 | note | Frequency - Post Works Completion
e78dd76b-18aa-5142-b968-b51c64ca2967 | note | Verification Activity: Activity - R
7fd320d7-a1b0-5bb2-8e3b-889ea404cd35 | note | Verification Activity: By - PE
2b2e2dff-a8a9-5c1c-9c14-796d058cd9a4 | section | 5.4. - Guarantee
64e7a9c1-80f4-52cc-bd0b-cd984c328b37 | checkpoint | 5.4.01 - Guarantee
a200de05-2cfa-5ed2-9d76-3fa634872f64 | note | Acceptance / Conformance Criteria - Provide guarantees for all equipment including 10-year minimum guarantees for external luminaires and poles.
671c744a-9171-5e3d-9905-a7cfd293a34b | note | Standard / Specification - PS 22.1.15, IBEX Lighting Plan
9b9f8758-4daa-5091-86fc-2835f5eb6832 | note | Verifying Document - Guarantee
f2be27fc-36f5-5208-b732-7010f873cb63 | note | Frequency - Post Works Completion
1247f784-f112-58a0-b204-8165f32d4be7 | note | Verification Activity: Activity - R
38cd6709-c4cd-5392-93d7-9c72dcc65780 | note | Verification Activity: By - PE
27e4209f-2cd7-58d0-9eea-49905ed399ec | section | 5.5. - Spare Parts Schedule
d51c4b12-6e9e-544d-9b8e-c16f9ab836dc | checkpoint | 5.5.01 - Spare Parts Schedule
2cc937e0-2c01-57bd-8bba-88fbc0b2e6f5 | note | Acceptance / Conformance Criteria - Provide a comprehensive schedule of maintenance spare parts, detailing recommended quantities, manufacturer prices including packaging and delivery to site, marking and numbering procedures, referencing equipment schedules, and preventive measures such as painting and greasing to avoid deterioration during storage.
3b63edda-6e26-520b-808e-a6c8ac9dd4ba | note | Standard / Specification - PS 22.9.7
8fd5f8af-a6ae-5f20-a250-15dc125447ab | note | Verifying Document - Spare Parts Schedule
bfbd5332-d4ca-56f2-86ba-18f7d960246b | note | Frequency - At least 8 weeks prior to Practical Completion
9fb1f5fe-d0da-52f2-8acd-681efe4d50db | note | Verification Activity: Activity - R
50c1cd1f-4d75-54df-80ef-d1439d8dc1ef | note | Verification Activity: By - PE
e3058f1d-bbaa-5675-95ad-7399d577b17a | section | 5.6. - Required Operating Instructions
e2e13f46-3951-5993-99d5-cf57643b4ec0 | checkpoint | 5.6.01 - Required Operating Instructions
6ada5fe4-e1f6-5c1c-97f4-d4f22fad9c4e | note | Acceptance / Conformance Criteria - Provide operating instructions and schematic diagrams mounted alongside equipment to meet statutory requirements, e.g., Fire Brigade. Diagrams to be colour-coded, colour-fast, laminated and mounted.
705527d4-8c71-5418-a690-7d30d9eef5a5 | note | Standard / Specification - PS 22.9.7
53cdf0a2-82a9-598d-885c-dd8d490bfeb5 | note | Verifying Document - Site Records
f0381975-1b90-5f26-a575-4df121cb99a2 | note | Frequency - Post Works Completion
2a197893-bf92-5cc9-a429-029a980ba90a | note | Verification Activity: Activity - R
29a98e64-baee-5847-beb4-4b60b492f514 | note | Verification Activity: By - PE
26c60b94-06b2-588e-a88e-73eeceb9f301 | section | 5.7. - Operating and Maintenance Manuals
5f66f82a-d175-5ce4-b601-7611a60cf164 | checkpoint | 5.7.01 - Operating and Maintenance Manuals
5bab8eaa-60db-5395-87f7-9ab853782e5f | note | Acceptance / Conformance Criteria - Provide a comprehensive Operating and Maintenance documentation to cover all installations to provide a detailed understanding of the plant and its operation, an aid for training of operators, a reference for fault diagnosis and a framework for preventative and breakdown maintenance.
2b7d29ee-7127-5a17-8b3e-18fc010b1e8d | note | ○ Submit manuals in two stages. Stage 1 include all the sections (generally sections 1-5) of manuals excluding final testing and commissioning records and As Built drawings. This manual shall be submitted well in advance of the Practical Completion and should be signed off by the Engineer at least 4-6 weeks before programme Practical Completion Date.
a7d74c87-a1e3-562c-bf7a-f7f76e035926 | note | ○ A first draft manual should be submitted 8-10 weeks before the practical completion date for review. Subsequently, submit a completed second draft incorporating comments for further review. Finally, include all remaining sections, incorporate all changes and resubmit until all comments are addressed to the satisfaction of the Engineer
780e0df4-63ee-50a7-8d62-529d86f68745 | note | Standard / Specification - PS 22.9.6
221c7536-aaf0-50d4-88d3-505a2fd5bf20 | note | Verifying Document - O&MM
53f3213c-ddf8-5a89-a3d5-f83be3cd0d72 | note | Frequency - 4-6 weeks before programme Practical Completion Date
5f9b7440-34bc-5845-abe6-6d1bfbab4ce2 | note | Verification Activity: Activity - HP
2e524ba2-c124-53ab-921f-77f1ca5bb0f0 | note | Verification Activity: By - ENG
50719d87-199c-5ecb-bce8-f7f0a1c75028 | signoff | AUTHORITY HOLDPOINT
dcc180a6-bfb1-5f1e-b060-8226615a96ba | checkpoint | 5.7.02 - Inspection and Test Plan
853da2df-0652-5075-a812-639c9f427f12 | note | Acceptance / Conformance Criteria - Installation and commisioning Inspection and Testing Plans to be provided to the satisfaction of the Engineer
01978bc1-2425-5e30-ad75-d9998bcdce4d | note | Standard / Specification - PS 22.9.6, PS 22.9.4
3258e8e0-55f7-5e8f-8ad3-7f0c70ceda7e | note | Verifying Document - ITP
a6f48de1-3d0d-5ab7-a12e-eaff9bae67f3 | note | Frequency - Prior to Installation
44337a02-7d42-5d89-9247-2c4843e9911d | note | Verification Activity: Activity - HP
36ae7990-ff08-5ec4-bbb6-2db4d40aeffe | note | Verification Activity: By - ENG
35700bd3-37bc-5e31-8882-5ccec9abf52f | signoff | AUTHORITY HOLDPOINT
ee1ca210-f15b-56d4-9ecd-ea58a157be55 | checkpoint | 5.7.03 - Final Copies Stage 1 & 2
9457221a-8975-54ea-8d84-f14d02122f86 | note | Acceptance / Conformance Criteria - Submit 3 sets of final volumes within 2 weeks after practical completion. Incorporate feedback from review and from training of Principal’s staff, including preparation and insertion of additional data. Include a section containing commissioning test reports.
68d56e7d-bc36-57db-b057-e3679c0c6686 | note | Standard / Specification - PS 22.9.6
471dd93d-4fd6-5669-9d3e-182432289634 | note | Verifying Document - O&MM
2b81b194-386c-565a-b8c9-b940762ebad5 | note | Frequency - Within 2 weeks after practical completion
bc001c2d-e93d-501b-a1df-42a6dd0964d6 | note | Verification Activity: Activity - R
596f928f-81c0-55cf-b72f-ec8b0a9f0305 | note | Verification Activity: By - PE
0a525513-f4d1-508c-8026-31b897b6b5a1 | section | 5.8. - Final Contract and Hand-Over Documentation
e889cfad-7438-57f0-9030-574799ece21b | checkpoint | 5.8.01 - Final Hand-Over
e299142d-642f-5081-9944-206253217d2e | note | Acceptance / Conformance Criteria - Documentation is required in electronic and hard copy format. Electronic documentation shall be supplied on the latest Microsoft and Autodesk Software versions at the time of Practical Completion.
c6b12f70-7f8a-5031-b25b-62e21a4904f2 | note | Operating and Maintenance Manuals (including Final Commissioning Data):
c9149671-11a3-5142-907f-f18e1f2102f8 | note | ○ Electronic format installed on BMS File Server: 1 set
0e0b32cb-2710-5335-950e-51c4bcf28753 | note | ○ PDF format on USB storage device: 3 sets
0d712266-7649-515e-8d67-ab969d71db3e | note | ○ Hardcopy: 3 sets
c6e4110a-e6c8-539e-a65e-fc98e49f65a6 | note | As-Built Drawings:
6326ea8c-4c44-5dba-9e99-e328af8ecdc9 | note | ○ AutoCAD format on USB storage device: 3 sets
25361ced-8e9f-56c5-932d-6693336b557f | note | ○ Hardcopy full-size with hanging strips: 1 set
0e43eae1-0405-5898-be31-9e312c374ce2 | note | ○ A3 size (included in O&M Manual): 2 sets
d982cc7e-8656-53b3-8696-8ad2fe6b7f34 | note | Revit Model:
b456118c-daba-50e4-b589-e9a3c12e9f75 | note | ○ Refer to the requirements set out in the project BEP (BIM Execution Plan)
dff34ba4-293a-5efe-81a5-b9729e4e94d9 | note | Control Software:
81e063a3-db7f-5d5d-88bc-6648f09157e4 | note | ○ USB storage device: 1 set
2e280229-6736-5169-a58e-2ac2df02d613 | note | OH&S Safety Signage:
783ecc73-8424-537f-8dcf-30d4f548a776 | note | ○ Permanent: 1 set
f212cc3e-f056-56ab-9102-db2258ed9cbb | note | Standard / Specification - PS 22.9.7
42e83937-3bd2-54b2-bce8-8571dae2a67e | note | Verifying Document - Site Records
a1b54ee0-a17d-5191-80a7-f462a0afb6ad | note | Frequency - Post Works Completion
621a68ee-6c39-5710-895d-66f78f03c39e | note | Verification Activity: Activity - R
1a27656e-0961-5097-a305-1f064117de50 | note | Verification Activity: By - PE
e85e9ecc-3421-57a0-bf7b-f45069e6b84c | checklist | ITP - Traffic Services ITP - 105 - Rev B | itp | ITP - Traffic Services ITP - 105 - Rev B
cbb694b5-9a79-5eff-82e8-792fdfcecb63 | section | 16.01 Signs
0e4e7528-b117-573c-bedf-a3265d509aa1 | checkpoint | Redundant Signs
fc652128-0b9b-5889-9f84-c44a7466ca8d | note | Acceptance / Conformance Criteria - All redundant sign equipment shall be offered to the New Zealand Transport Agency to be uplifted for possible future use. All redundant equipment not required by New Zealand Transport Agency, shall be uplifted, removed completely off site, and disposed of in an appropriate manner.
7d07ea0e-24d3-52ea-a3ee-469c31dfa8ce | note | Standard / Specification - PS 23.2.2
1639787e-f88a-562e-94fe-2f1f28688bc9 | note | Verifying Document - Site Records
148b159e-c20d-54ee-8449-7fd712ebf23b | note | Frequency - Where Required
572ef37a-c91d-54e2-bb2b-f9596f112ead | note | Verification Activity: Activity - R
24517924-8f84-5a1d-8e15-394d41e81b7a | note | Verification Activity: By - SE
d95fbd5b-ce62-57ff-a566-dd0d774b22db | checkpoint | Relocated Signs
e446e723-3b92-552d-a602-3b78cc90a82c | note | Acceptance / Conformance Criteria - All relocated signs shall be Firmly installed in a vertical position and securely attached to posts where appropriate. Fixed to posts with appropriate fixing brackets. Signs shall not be fixed to posts by bolting through the sign unless specifically approved by the Engineer.
94bbbc65-7c4b-5c47-9fac-4a9d74f8fdb8 | note | Standard / Specification - PS 23.2.3
25b647c1-1c54-5c81-b265-d6c4d5710bc5 | note | Verifying Document - Site Records
afb46a6d-0e7d-5e4f-8a5d-d66a13119c9c | note | Frequency - Each Sign
0a7cc22e-e010-57dc-8e46-cc3d3515f8c2 | note | Verification Activity: Activity - R
16b1af2c-b10e-571c-9abe-e4603b2c7658 | note | Verification Activity: By - SE
63e60a80-2389-587b-8d02-bcee3658aea1 | checkpoint | Posts and poles
a0ff9fa1-3b5d-57f2-bf74-10aea886e486 | note | Acceptance / Conformance Criteria - The Contractor shall maintain construction records for each sign that clearly shows that all post, poles and foundation details comply with the requirements of this Specification. The design of foundations should, where required, consider the very close proximity of services and not subject these services to any dead or live loadings from the sign support structures.
e293e5b4-bdd3-5a71-adfc-4c7faf8e6169 | note | Standard / Specification - PS 23.2.17 PS 23.2.18 PS 23.2.24
0bdb7a0b-9899-5a69-8953-a9ee74118990 | note | Verifying Document - Checksheet
03a97a80-bb7c-5851-b6db-a111a1e485c1 | note | Frequency - Each Sign
828a02c7-fa0e-5162-850a-0d43cc77ba41 | note | Verification Activity: Activity - I
0a5fbbde-b7a5-54b5-9c1c-4646cfdba6e5 | note | Verification Activity: By - SE
d7ccad97-0972-5c41-9395-f8b1f3223072 | checkpoint | Ground Mounted Signs
433691a6-d99a-5ea7-b6c9-d980c1edab59 | note | Acceptance / Conformance Criteria - All ground mounted signs shall be orientated such that they are turned about five degrees away from the driver’s line of sight or the normal to-the-road centreline as detailed in Clause 1.10 ‘Orientation’ of the Waka Kotahi NZ Transport Agency Manual of Pavement Markings and Signs Part 1.
cf12d1ca-e75a-5493-a5d9-f4bb8f05255f | note | Standard / Specification - PS 23.2.27
56606c29-2f1e-57ee-85e1-778c3a924f06 | note | Verifying Document - Site Records
b2ecc68d-77be-508f-81f5-8ec27963cf17 | note | Frequency - Each Ground Mounted Sign
4c92a8fa-e501-5c9e-94fa-af4ed67d2c5c | note | Verification Activity: Activity - V
490fafcb-8774-56bd-a190-109873203a23 | note | Verification Activity: By - SE
ea2b689c-b2a4-5570-aa94-6d1d1ab86c7c | section | 16.02 Pavement Markings
37d73ff5-7875-592e-bb65-845271c4deab | checkpoint | Surplus Chip Removal
f3d75540-33a1-557c-abc0-84cb0221aa60 | note | Acceptance / Conformance Criteria - Accumulations of surplus chip and other coarse material shall be removed prior to road marking.
4b900777-f199-5f8c-a1a9-0fef82285885 | note | Standard / Specification - PS 23.3.2
e697fffc-8b2c-51f5-878d-595c029ae8d2 | note | Verifying Document - Site Records
97fd5d51-2e06-51f1-bafb-98573ccdfff9 | note | Frequency - Prior to Marking
f0952784-cf2f-5b0d-b658-a5b83ac7ca7a | note | Verification Activity: Activity - V
e73c5472-f2ea-5da5-a6bc-5b6ab72a2580 | note | Verification Activity: By - SE
7cc3473e-9ccd-5e6c-bf8d-16fc32a74903 | checkpoint | High Performance Marking
57a1fbc9-1891-5ff8-a20e-866e6b6759f5 | note | Acceptance / Conformance Criteria - All road marking installed is to be high performance textured pavement markings in accordance with NZTA P30 High Performance Road markings unless otherwise specified.
6aca3ef2-fb65-505d-971e-9559e6c3b8c2 | note | Standard / Specification - PS 23.3.1
60f27952-3784-5a74-ba11-0db600b5c626 | note | Verifying Document - Site Records
a71becad-6961-53a3-a5c9-4360153c052e | note | Frequency - Each Marking
92ada486-d843-5e60-ac1e-1d3e6ce2b944 | note | Verification Activity: Activity - V
c3302b85-2e6c-5e24-bfaa-1a9827ac2423 | note | Verification Activity: By - SE
a631979e-2c25-5df5-bcfb-e8fb3bc69b5b | checkpoint | Roadmarking Removal
f53357af-e335-5829-90b8-e4c6127587b1 | note | Acceptance / Conformance Criteria - All road markings that are to be permanently removed must be either by water blasting or milling off in line with the NZRF line removal guide. The removal of all redundant pavement marking shall be such that The shape of the marking cannot be distinguished, The final surface texture is like the surrounding pavement; and No evidence of the paint remains.
5f961253-c6c1-5857-b36f-63e00b29b075 | note | Standard / Specification - PS 23.3.2
3aba31d3-f6c8-5e8a-bb2b-e6104a8689ff | note | Verifying Document - Site Records
9042e646-695f-5034-8e3a-161d6e2c68f0 | note | Frequency - Each Removed marking
89d07754-36d2-5820-8ca8-26027fb0dcbc | note | Verification Activity: Activity - V
0ca0ceb1-5666-5cfe-88e4-39dfe828a076 | note | Verification Activity: By - SE
4f67c6ff-9945-532a-87fc-d6a73512f2ec | checkpoint | Raised Pavement Markers
a4dfb383-b16d-5883-a240-b09a33717caa | note | Acceptance / Conformance Criteria - These shall be located as detailed on the Drawings and installed in accordance with the requirements of TNZ P/14. The applicator shall ensure that the placement surface is dry and free of all foreign material and loose chip, which would hinder the correct installation of the raised pavement markers.
7d9ce684-58f3-5bce-8ca4-889f9dea71a3 | note | Standard / Specification - PS 23.3.2
c55645d3-3cb9-56c3-b3c3-836531e7ae1b | note | Verifying Document - Site Records
67404876-f53e-5ab3-914d-ad2783139553 | note | Frequency - Each Marking
4359ebed-c8a0-5623-9fba-9f0887e41775 | note | Verification Activity: Activity - V
2a44a8cc-4498-583e-b8f9-d35a0b033a6d | note | Verification Activity: By - SE
b8086ecc-f696-5e17-95b8-844cc78efc6a | checkpoint | Edge Marker Posts:
2edb267b-dfb7-5e5f-acf0-d7532c142a02 | note | Acceptance / Conformance Criteria - Edge marker posts shall be installed in accordance with the requirements of NZTA M14. Setting out shall be in accordance with the latest amendment of the Manual of Traffic Signs and Markings and the Drawings.
aaff5d05-11e3-5ad9-ab72-7c1672b76a6b | note | Standard / Specification - PS 23.3.2
db5ea000-6319-5ab7-a8ec-35f68e7c87f7 | note | Verifying Document - Site Records
75eaf30b-75ff-5253-b367-23140a2c49b1 | note | Frequency - Each Marking
a7b1cd52-5a24-57b5-b872-cc37c268e5ea | note | Verification Activity: Activity - V
f1864724-2e91-5352-aa4f-ec1fab52a61f | note | Verification Activity: By - SE
e220e36c-c5b4-56e1-99a1-aa71ea3dcc81 | checkpoint | Coloured Surfacing
cc9bba5c-7425-54fd-aef5-d3aa9a42b4f3 | note | Acceptance / Conformance Criteria - Coloured surfacing shall be laid in accordance with the requirements of NZTA P33.
233c1f17-38d3-55f8-ad54-f3068921fcc5 | note | Standard / Specification - PS 23.3.2, PS 23.4
e8ec9b0a-9101-56ee-ac04-1f340ffbb1ad | note | Verifying Document - Site Records
8eb7a64b-c4d9-5fbb-bf54-c8c762275ea3 | note | Frequency - Each Application
825d26d0-57b6-5836-9764-0b1bd37db22c | note | Verification Activity: Activity - V
379dc95d-2f24-5c63-8232-293318aedcdb | note | Verification Activity: By - SE
5a9b8dd9-0399-50f6-9500-2df0acaf5af9 | section | 16.03 Long-life Road Markings
35cc9dea-af9f-518b-9a20-708d74708ef1 | checkpoint | Mark out the Contract Works with Engineer
0c33102b-efdb-5d37-9a0e-10a3274de6d4 | note | Acceptance / Conformance Criteria - The Contractor is required to mark out the contract works with the Engineer in accordance with the NZTA Traffic Control Devices Manual Part 5 before any installation commences. The application shall be in accordance with the Land Transport Rule: Traffic Control Devices 2004. The Contractor must give the Engineer 5 Working Day notice of the proposed date the Contractor intents to mark out the extent of the contract works on site.
d2c59fa7-fa0a-5a9c-9c40-7f6c7541cf46 | note | Standard / Specification - PS 23.5.9
7721a508-a4b1-5ed1-bd6e-bc6cef1fa3cc | note | Verifying Document - Markout Records
32bd25dd-729f-5821-832a-c48560fbefde | note | Frequency - 5 Working Day notice prior to mark out
1c94914f-3c33-59e8-939f-3c0f9741396e | note | Verification Activity: Activity - HP
1fb540b4-8e94-5161-9d50-050f2162b95b | note | Verification Activity: By - ENG
ada6a83f-dae7-5844-b51a-a84e3e8b7844 | signoff | AUTHORITY HOLDPOINT
515d37f4-4ec9-507b-8176-afec39742d6b | checkpoint | Applicator, Marking System, Marking Format and Applicator Crew Trial
6700fb3c-cd42-5882-b30e-cfad2bac4b6d | note | Acceptance / Conformance Criteria - The trial shall be completed using the applicator(s), marking system(s), marking format and crew approved for the contract works. The Contractor shall give the Engineer 5 Working Day notice of the date for the trial(s). Installation shall commence only if the Engineer is satisfied with the trial result(s). Verbal acceptance will be given to the Contractor immediately after the trial with written confirmation to follow.
d8c30e13-298e-578d-a704-33819d9f0665 | note | Standard / Specification - PS 23.5.11
a6be0360-e986-52ef-9bde-50a05719ca4e | note | Verifying Document - Trail Results
4c3f5044-9639-5c89-b428-e1213e557283 | note | Frequency - Prior to Installation
40e0bd42-1e38-5817-940e-4ecbadaa2fba | note | Verification Activity: Activity - HP
fe86147b-36e7-5849-9824-86b689753cf9 | note | Verification Activity: By - ENG
cced6d0d-ca6b-557b-9ff4-09d74853cf42 | signoff | AUTHORITY HOLDPOINT
84221197-005e-50f0-9e01-324fdbcb4a38 | checkpoint | Inspection and Measuring During Installation
ab37c16d-293c-56a7-a8d9-27d0d154d1f5 | note | Acceptance / Conformance Criteria - The Contractor shall inspect the long-life road marking against dimensional and installation tolerances as installation progresses. The Contractor shall on a daily frequency complete a Daily Quality Assurance Form (Thermoplastic and CAP respectively). The form records the material data, environmental conditions, etc.
52bdea2e-e9e8-5b90-9e37-7bb76a71b15c | note | Standard / Specification - PS 23.5.13, PS 23.5.15
c3483788-333b-5a2f-8b41-14f9df41ae49 | note | Verifying Document - Daily Quality Assurance Form
77a8bb25-4cbf-55a6-a3be-7c1c7a41773c | note | Frequency - During installation
a84353cb-2add-5e23-8278-2111961551f5 | note | Verification Activity: Activity - V
fcb24cc4-d125-51ec-9be3-448214c80bf6 | note | Verification Activity: By - SE
593543f2-b853-579e-922b-41949d6ffb5c | checkpoint | Inspection Post Installation
a7ecc87c-3c3b-5ce2-8fa3-66bd611f8a0c | note | Acceptance / Conformance Criteria - Formal visual drive over inspections. The visual inspection shall include An initial night inspection followed by a day inspection shall be carried out by the Engineer and Contractor of the first 25 to 50km per type of roadmarking installed (approximately 5 to 7 days of installation). The inspection shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event. Subsequent visual inspections by the Engineer and the Contractor shall be jointly carried out of a sample of the contract works.
36818422-5312-5b30-8915-f6eebbefdda5 | note | Standard / Specification - PS 23.5.16
bd776027-565b-5ce7-90f0-d84f558a7af9 | note | Verifying Document - Report
5d19d78f-d9bc-5336-b3e2-bdef61de023d | note | Frequency - Minimum of 20% of the total contract works will be inspected per type of roadmarking
c206c266-7a30-51c4-a696-7e0dc3b56666 | note | Verification Activity: Activity - V
0befd2f0-b085-5032-8a76-d7c6bd3d4b1c | note | Verification Activity: By - SE
b2fb75c1-603e-5892-be9a-c01064ccabea | checkpoint | Monitoring Post Installation
fd49bb47-eb67-53a0-a380-1c2f8d225a02 | note | Acceptance / Conformance Criteria - The Engineer and the Contractor shall agree on representative sites for ongoing monitoring. Monitoring sites shall be 2 per 100km of edge-line per roadmarking type. Three sets of monitoring shall be carried out First monitoring following installation of all contract works. The monitoring shall be carried out 2 to 4 weeks post installation to allow for trafficking and a rainfall event. Second monitoring approximately six months after the first monitoring. The Engineer may waive the monitoring if they are satisfied with the performance of the markings based on the first monitoring. Third monitoring prior the issue of Final Completion Certificate.
888bcbda-554f-5c90-9d65-9a4435c51368 | note | Standard / Specification - PS 23.5.17
7d22f5c1-b411-5c51-8d1b-5be9ed8ba22e | note | Verifying Document - Report
8c91126d-0d0b-5bc3-8c3f-e909c4f32a91 | note | Frequency - 2 per 100km of edge-line per roadmarking type
e9e8ba65-e11b-5ba4-ba95-20940b332d90 | note | Verification Activity: Activity - HP
905666d8-19a1-5771-9b8c-4bc948bd3879 | note | Verification Activity: By - ENG
1331ca8b-8a6e-545b-81ed-6a3977b122c1 | signoff | AUTHORITY HOLDPOINT
a8523497-008f-5d14-abaa-0d6ae1ea132d | section | 16.04 Safety Barriers
fb660e6b-cff0-5921-901c-34d6f0da2710 | checkpoint | Ground profile
c4efcc04-1317-5b89-ab39-592f5b4570f8 | note | Acceptance / Conformance Criteria - The finished ground profile from the edge of the pavement to the guardrail and for at least 600mm behind the guardrail shall be a maximum crossfall of + or -1 in 10.
beb3a0cb-74bc-5201-8574-baf9e9789042 | note | Standard / Specification - PS 23.6 M23
b4553607-8238-57c5-b251-452edb5f206f | note | Verifying Document - Site Records
c9bc83db-0123-5893-949c-9f36cc9c06a2 | note | Frequency - Prior to post installation
9efd250c-3a55-55e1-a0f5-af5ec201ed39 | note | Verification Activity: Activity - V
627fb330-10c0-5d6d-8c84-64ede17e9b25 | note | Verification Activity: By - SE
8884d2a2-559c-52f4-925b-e3a5f67ae036 | checkpoint | Installation Notice
d0a861cc-4875-51e9-80ce-2ecd28f4046c | note | Acceptance / Conformance Criteria - The Engineer shall be notified and given opportunity to inspect the set-out for the guardrail at least 24 hours prior to construction.
50dda0c6-7bb6-573a-81c0-f0fd17ebe5fc | note | Standard / Specification - PS 23.6 M23
114a4f12-7e1e-5da2-96f6-8a06f060ae11 | note | Verifying Document - Notice
a5781f25-9d10-501b-9117-566a282932df | note | Frequency - Prior to Guardrail Construction
ac9cf37e-5226-5d82-8111-cb3dba07093e | note | Verification Activity: Activity - HP
8344221b-dd7b-5772-b788-0525b09b6d48 | note | Verification Activity: By - ENG
8f3a56f4-54f1-5e2a-93a6-b8538ebb393a | signoff | AUTHORITY HOLDPOINT
c575770a-0da0-51f4-8fe7-39613551fc90 | checkpoint | Guardrail Alignment Visual Inspection
b70906a5-a409-5635-9c76-e199b3937ab6 | note | Acceptance / Conformance Criteria - The horizontal alignment of the barrier shall not deviate more than ± 10 mm from the specified positions and levels. When erected but before posts are permanently fixed the completed guardrail alignment shall be visually acceptable.
3e81e72b-2fda-5b2f-9a58-6dcc91d9537a | note | Standard / Specification - PS 23.6 M23
2fb7498d-0483-5820-a77f-a3e7738857c8 | note | Verifying Document - Site Records
76ec074e-21b9-5c53-9562-f5f2af9af603 | note | Frequency - When erected but before posts are permanently fixed
4f46e91a-7745-5f65-816e-252be54ec5de | note | Verification Activity: Activity - V
d865b97f-f06f-5677-99de-6bc3fd5a2591 | note | Verification Activity: By - SE
5891dd1d-d957-538d-9837-de207c510e13 | checkpoint | Guard Rail and End Post Installation Checksheets
956af5c2-5da1-58cc-bd36-7f9a09ef7900 | note | Acceptance / Conformance Criteria - The Contractor shall submit a completed and signed installation check sheet for each terminal and guardrail section installed to the Engineer for acceptance
73dc39c6-7918-52f6-ad87-c9031f2e54dd | note | Standard / Specification - PS 23.6 M23
72c6c1eb-69a0-5619-ae79-90dc372069ff | note | Verifying Document - Checksheets
a565cda2-3064-5c84-98ea-5c437494e4cc | note | Frequency - Upon completion of the Guardrail Construction
ad949362-5162-58c3-8b99-16afd9af5e7c | note | Verification Activity: Activity - HP
4aee2243-32a7-50bf-b528-4a1c164faa15 | note | Verification Activity: By - ENG
bf4cc9ec-2e9c-5ead-92f4-16850b08e11b | signoff | AUTHORITY HOLDPOINT
9a210f72-c819-596c-bd99-c7ddad210861 | checkpoint | Galvanising Repair
ed6b1db2-6d13-5b2d-9217-0ecf9bb9ca64 | note | Acceptance / Conformance Criteria - After assembly, any areas of the galvanised coating that have been damaged or show signs of deterioration shall be wire brushed and washed to thoroughly clean down to fresh zinc or parent metal. They shall then be spot painted with two brush coats of un-thinned approved zinc rich paint the first coat being applied to a dry surface immediately after cleaning.
af2eb423-0bd7-5394-b0a2-1ddebc64b9ed | note | Standard / Specification - PS 23.6 M23
43367e46-e477-5720-9e0c-0d9f53aaf0a1 | note | Verifying Document - Site Records
84fcd489-7141-55ad-904d-be7079124680 | note | Frequency - Where Required
b56e0445-95a4-5231-acec-46d30e7f8202 | note | Verification Activity: Activity - S
ca0103dc-ef04-5882-bfb4-76372d2b521c | note | Verification Activity: By - SE
3b6e694e-ea22-5cf7-9c8c-f50551b48a0a | section | 16.05 Safe Lane Delineators
1893069f-b24e-5962-ab5b-4023fa145f92 | checkpoint | Safe Lane Delineator Installation
078f1647-87b1-5bda-8a9c-8e1b7d605de7 | note | Acceptance / Conformance Criteria - The safe lane delineators are to be installed in accordance with the manufacturer’s specification unless otherwise directed in the Contract Drawings.
b722e735-37db-5f93-a68b-edcf668644e5 | note | Standard / Specification - PS 23.7
d1630399-f55d-5291-a6aa-515441c20118 | note | Verifying Document - Site Records
f084265d-3f5b-5860-8d5d-48706d2497d6 | note | Frequency - Post Installation
3407f6d5-5570-5976-b047-f0a5efbc17ff | note | Verification Activity: Activity - S
7c7bb3e3-c9ec-53af-850e-9dc6af8ee371 | note | Verification Activity: By - SE
a4bb45e6-00c3-5ec9-83ca-06454e70db00 | checkpoint | Chemset Safe Lane Delineator
6978f879-b6e4-5ddd-b6fc-1ebe23e6c604 | note | Acceptance / Conformance Criteria - Where detailed in the Contract Drawings the Contractor shall excavate a 300mm x 300mm diameter hole and ensure all loose debris is removed from the hole. The hole shall be back filled with 20MPa concrete and the safe lane delineator is to be chemset in place. The concrete shall be level with the existing surfacing around the hole and water shall drain away from the delineator.
b24168a3-7a61-5419-a411-7c4277668a10 | note | Standard / Specification - PS 23.7
c18d7f2c-f9a3-5752-bedb-01b14ce7e257 | note | Verifying Document - Site Records
ae674a60-f90b-5421-b042-13c78184eedc | note | Frequency - Each Post
3dd80a83-900f-5e2f-b056-368f195cbe2d | note | Verification Activity: Activity - S
39ae7e2b-04bf-5322-9965-2928d5fd654f | note | Verification Activity: By - SE
573ff2f4-823b-57a7-9287-d7227b010f4c | checklist | ITP - Underpass Construction - 103 - Rev D | itp | ITP - Underpass Construction - 103 - Rev D
b75e124d-fe66-55c9-a631-94fb56471ab8 | section | 3.03 Subsoil Drain
7936ef09-4ba2-52a3-8d41-c9fbcfa54b56 | checkpoint | 3.03.1 - Trench Grade
5a825b5a-a81e-5763-a66f-a3c4ab9c07aa | note | Acceptance / Conformance Criteria - Unless otherwise specified trenches shall have: a minimum gradient of not less than 1 in 100; vertical sides from the trench bottom to a minimum of 300 mm above the top of the pipe; and a minimum depth that will ensure that, when the pipes are laid, the invert level shall be not less than one metre below finished subgrade level.
59574125-fa0e-51a5-b0b1-305fc8c48fc0 | note | Standard / Specification - NZTA F/5 PS 16.11.2
a34ecc5c-a8a9-5471-8641-078cc46e395f | note | Verifying Document - Note only
e3ebcf79-48e9-5d4d-a489-f797dd8e07c7 | note | Frequency - Each Pipe
642f912f-eb4e-5693-915c-b1da3c7b0ae8 | note | Verification Activity: Activity -
1bdfbb34-22fc-5cac-badf-aa16b428f0fb | note | Verification Activity: By -
4fb79358-a052-5b54-a7da-8d33d0decaaf | checkpoint | 3.03.2 - Bedding and Installation of Drainage Pipe
0b9ec629-0e91-52c2-84a8-2312db9d6d4e | note | Acceptance / Conformance Criteria - Prior to laying the drain pipes, the Constructor shall ensure that pipes do not become contaminated with clay or soil and that pipe slots are not blocked. Any such blockages shall be removed before pipes are laid.
24c7d13e-d811-5526-a8b3-d4e5db24cb7d | note | Standard / Specification - PS 16.11.3
acdca211-7142-57e4-9733-55a2e313315a | note | Verifying Document - Site Records
95a8af9c-0114-52f3-86ad-22661cc7cb79 | note | Frequency - Each Pipe
dec02c4e-a6b1-5312-90ac-8e6590e96adc | note | Verification Activity: Activity - S
6a8ed684-f053-5001-8c22-b2d53cb2bdc7 | note | Verification Activity: By - SE
08f9a616-8e77-5407-a5e6-3c88a6e10fbd | checkpoint | 3.03.3 - Bedding Placement
638f4e29-af56-5a25-8c6e-4b1ed8411883 | note | Acceptance / Conformance Criteria - The filter material shall be placed, and the drain pipe installed such that the pipe is at a uniform grade and is underlain by a minimum of 50 mm and overlaid by a minimum of 150mm of filter material which completely surrounds the drain pipe. The filter material shall be placed in a manner to achieve a generally uniform dense state.
1cde5f44-36f4-5146-82ae-09ac30b33502 | note | Standard / Specification - PS 16.11.3
2df2edec-93ec-504a-8c3f-aef59704321c | note | Verifying Document - Site Records
1887868a-bd9b-58f2-8097-ff9c3d6e075f | note | Frequency - Each Pipe
95be1982-df6b-5548-8fdf-1794f1272a38 | note | Verification Activity: Activity - S
e2d71b85-aea0-5514-906a-894b68b85239 | note | Verification Activity: By - SE
05ce68f8-b4be-5cce-8474-bbb07ed45901 | checkpoint | 3.03.4 - Pipe Orientation
545e51c8-998d-5db4-ab11-ab655af9b089 | note | Acceptance / Conformance Criteria - Pipes should generally be laid so that the perforations are oriented as shown in accordance with the manufacturer’s recommendations for corrugated HDPE pipes.
e83dea8a-bb7d-530a-a507-1e3e935c3b15 | note | Standard / Specification - PS 16.11.3
386f9756-0252-5e91-961f-be0c39092910 | note | Verifying Document - Site Records
8e6012fe-5fa6-5645-ab36-85e2437c148b | note | Frequency - Each Pipe
7d7c5b81-c6d5-5666-9315-8e665aa790fe | note | Verification Activity: Activity - S
40acf20c-f89c-56a7-aac9-d3aab1360982 | note | Verification Activity: By - SE
ba976090-1b76-596c-bd7f-77d7d3b73ec5 | checkpoint | 3.03.5 - Pipe Jointing
6eabb8c3-b7cc-503f-a1bd-080fbd01b7c9 | note | Acceptance / Conformance Criteria - The drain pipe lengths shall be joined following the manufacturer’s instructions or as approved by the Engineer, with the pipe jointing carried out to leave a smooth flush internal surface. The top ends of the pipes shall be capped.
b7802ea9-fffb-5d0d-8d4e-a8511c63bb5c | note | Standard / Specification - PS 16.11.3
beb3303d-d6a6-5b0a-9def-894f21bd4a32 | note | Verifying Document - Site Records
f2e60124-0673-55b1-ac18-b95ea4948217 | note | Frequency - Each Joint
c4aa85c4-253f-51c8-8034-03eca82556b1 | note | Verification Activity: Activity - S
5c89fe7f-88fc-535f-b560-a91e60cca1d6 | note | Verification Activity: By - SE
4e27c6e6-5a37-57e4-a099-dcb7417191e0 | checkpoint | 3.03.6 - Pipe Installation Inspection
25f9dead-3803-5267-b4f2-b7fc85c343fb | note | Acceptance / Conformance Criteria - The drain pipe installation shall be inspected and approved by the Engineer before placing filter material and backfill.
cc19571e-22e3-549e-9f0b-ce04fb0758b1 | note | Standard / Specification - PS 16.11.3
8d10cb49-39e2-5fd3-9bb5-1eac253672ec | note | Verifying Document - Engineers Acceptance
b7a30e4e-2653-5f3d-a6b6-958ba21dc61a | note | Frequency - Prior to backfilling
787eaa1b-fa2d-5975-bffa-558bb9a0bcf8 | note | Verification Activity: Activity - HP
6a6f5f82-a7d4-5363-9f7d-38835f0f052e | note | Verification Activity: By - ENG
07e48991-e1d5-55f5-866c-b6f966a404a3 | signoff | AUTHORITY HOLDPOINT
964a0105-283d-577c-9761-88c8229fe022 | checkpoint | 3.03.7 - Lose Debris Removal
3b8aa6d8-54f0-57e6-bcfe-8c0920cc219f | note | Acceptance / Conformance Criteria - Prior to placing filter material and backfill, the base and sides of the trench shall be cleaned of loose debris so far as is practical.
18c0edce-89e4-5835-b3ee-55d6114ca807 | note | Standard / Specification - PS 16.11.3
b6e5ea96-2fea-5f01-974c-87c28f740317 | note | Verifying Document - Site Records
8d61ce2f-a264-5064-bfbd-71b3dc71b4ca | note | Frequency - Prior to backfilling
c1682f1c-97d3-5006-96ba-8aaebf7faa3d | note | Verification Activity: Activity - S
6b40297e-5bcb-59c4-9d15-1ae7de0a7646 | note | Verification Activity: By - SE
5dfa7e2e-ce9b-55bb-8c98-a7f45d62276a | checkpoint | 3.03.8 - Subsoil Backfilling
a99f44b1-d645-51f9-a00e-2a05d15871d4 | note | Acceptance / Conformance Criteria - The backfill shall be filter sand as detailed in clause 2.2 of this specification. The backfill material shall be placed in layers not exceeding 150 mm loose depth and shall be positively compacted around the sides of the pipe to provide support of not less than that of the adjacent material
53345917-6def-5d2f-bbe5-49fc142886bb | note | Standard / Specification - NZTA F/5 PS 16.11.2
52f9ed58-0dd9-553d-b223-7df02e175438 | note | Verifying Document - Site Records
1af5364c-98d0-5ebf-b88d-7651311e29c5 | note | Frequency - Each Pipe
5f912046-e498-55c2-9660-0578ef4a8569 | note | Verification Activity: Activity - S
1e6866a2-9bf2-554a-bd79-9d3d28360cd9 | note | Verification Activity: By - SE
18ddc1ae-3926-5357-8ed5-e358e11d3d78 | checkpoint | 3.03.9 - Overlaying
3dc029ca-01fe-5d18-bbd3-94aa04526572 | note | Acceptance / Conformance Criteria - The completed drains shall be backfilled with an overlying capping layer to prevent the ingress of surface water.
7e09bae0-802f-5e66-bb65-4940f7cb9b27 | note | Standard / Specification - PS 16.11.4
f5a28aa2-6f19-5b71-bea8-68f5c6041393 | note | Verifying Document - Site Records
4493885d-6915-57fe-9d1a-23d75a3ce6ae | note | Frequency - On Completed Drains
7adc524f-00b4-58ba-9c69-79f6f9411a2a | note | Verification Activity: Activity - S
5fc751ca-743c-55d3-8a70-7fd4e6d7c3fe | note | Verification Activity: By - SE
96bce2aa-39c9-51ad-b916-3ecb5c5fd9df | section | 4.21 Underpass Materials
e0b3f528-ff2a-5e28-88ad-3bd75d383107 | checkpoint | 4.21.01 - Concrete Plant
5a825b5a-a81e-5763-a66f-a3c4ab9c07aa | note | Acceptance / Conformance Criteria - All plants supplying concrete to the project shall hold and maintain a current quality Certificate of Audit in accordance with NZS 3104 throughout the duration of their supply of concrete for the contract. A copy of each plant’s current Certificate of Audit shall be submitted to the Engineer prior to their initial supply of concrete.
59574125-fa0e-51a5-b0b1-305fc8c48fc0 | note | Standard / Specification - PS 19.7.1
a34ecc5c-a8a9-5471-8641-078cc46e395f | note | Verifying Document - Audit Cert
e3ebcf79-48e9-5d4d-a489-f797dd8e07c7 | note | Frequency - Prior to their initial supply of concrete
642f912f-eb4e-5693-915c-b1da3c7b0ae8 | note | Verification Activity: Activity - HP
1bdfbb34-22fc-5cac-badf-aa16b428f0fb | note | Verification Activity: By - ENG
b8384fc2-03a0-5160-831c-e5865c63514a | signoff | AUTHORITY HOLDPOINT
dffc3c4c-2cfd-525c-a09a-fb49cbcec42b | checkpoint | 4.21.02 - Blinding Concrete
0b9ec629-0e91-52c2-84a8-2312db9d6d4e | note | Acceptance / Conformance Criteria - Blinding concrete shall have a minimum 28 days compression strength of 10 MPa and comply with the requirements for Prescribed Mix concrete specified by NZS 3104.
24c7d13e-d811-5526-a8b3-d4e5db24cb7d | note | Standard / Specification - PS 19.5.1, PS 19.7.10
acdca211-7142-57e4-9733-55a2e313315a | note | Verifying Document - Approved Mix Design
95a8af9c-0114-52f3-86ad-22661cc7cb79 | note | Frequency - Submitted to and approved by the Engineer prior to concreting
dec02c4e-a6b1-5312-90ac-8e6590e96adc | note | Verification Activity: Activity - HP
6a8ed684-f053-5001-8c22-b2d53cb2bdc7 | note | Verification Activity: By - ENG
9da81b7a-de1d-517f-b7d7-918eb85f955a | signoff | AUTHORITY HOLDPOINT
edf8e519-1f31-581a-b5b0-d9853d6a7eae | checkpoint | 4.21.03 - Underpass Entrances Concrete
638f4e29-af56-5a25-8c6e-4b1ed8411883 | note | Acceptance / Conformance Criteria - The Underpass Entrances (insitu) concrete shall be a Normal 40MPA 19mm Mix.
1cde5f44-36f4-5146-82ae-09ac30b33502 | note | Standard / Specification - PS 19.6.1, PS 19.7.9
2df2edec-93ec-504a-8c3f-aef59704321c | note | Verifying Document - Approved Mix Design
1887868a-bd9b-58f2-8097-ff9c3d6e075f | note | Frequency - Submitted to and approved by the Engineer prior to concreting
95be1982-df6b-5548-8fdf-1794f1272a38 | note | Verification Activity: Activity - HP
e2d71b85-aea0-5514-906a-894b68b85239 | note | Verification Activity: By - ENG
d6f30363-6fc1-5066-a243-d3eed523f674 | signoff | AUTHORITY HOLDPOINT
1111f606-130a-5570-82ad-467c19fd12aa | checkpoint | 4.21.04 - Precast Mild steel fixings
545e51c8-998d-5db4-ab11-ab655af9b089 | note | Acceptance / Conformance Criteria - All mild steel fixings including bolts, nuts, inserts, washers, cleats and brackets shall be hot dip galvanised after fabrication.
e83dea8a-bb7d-530a-a507-1e3e935c3b15 | note | Standard / Specification - PS 19.15.6
386f9756-0252-5e91-961f-be0c39092910 | note | Verifying Document - Datasheet / Mill Certs
8e6012fe-5fa6-5645-ab36-85e2437c148b | note | Frequency - Prior to use
7d7c5b81-c6d5-5666-9315-8e665aa790fe | note | Verification Activity: Activity - R
40acf20c-f89c-56a7-aac9-d3aab1360982 | note | Verification Activity: By - SE
da46fb56-3e14-522a-b1e7-aed67309ec4b | checkpoint | 4.21.05 - Precast Stainless steel
6eabb8c3-b7cc-503f-a1bd-080fbd01b7c9 | note | Acceptance / Conformance Criteria - Stainless steel shall be type 316 unless otherwise specified.
b7802ea9-fffb-5d0d-8d4e-a8511c63bb5c | note | Standard / Specification - PS 19.15.7
beb3303d-d6a6-5b0a-9def-894f21bd4a32 | note | Verifying Document - Datasheet / Mill Certs
f2e60124-0673-55b1-ac18-b95ea4948217 | note | Frequency - Prior to use
c4aa85c4-253f-51c8-8034-03eca82556b1 | note | Verification Activity: Activity - R
5c89fe7f-88fc-535f-b560-a91e60cca1d6 | note | Verification Activity: By - SE
2df7f4c0-191f-57ac-b0f0-8222b88f5810 | checkpoint | 4.21.06 - Reinforcement cover spacer blocks
25f9dead-3803-5267-b4f2-b7fc85c343fb | note | Acceptance / Conformance Criteria - Reinforcement cover spacer blocks shall be either Concrete spacer blocks made from concrete containing 8% Microsilica and with a specified strength at least 10MPa stronger than the surrounding concrete or Plastic spacer blocks are in general undesirable in corrosive environments but may be acceptable in specific areas.
cc19571e-22e3-549e-9f0b-ce04fb0758b1 | note | Standard / Specification - PS 19.7.8
8d10cb49-39e2-5fd3-9bb5-1eac253672ec | note | Verifying Document - Datasheets
b7a30e4e-2653-5f3d-a6b6-958ba21dc61a | note | Frequency - Prior to use
787eaa1b-fa2d-5975-bffa-558bb9a0bcf8 | note | Verification Activity: Activity - R
6a6f5f82-a7d4-5363-9f7d-38835f0f052e | note | Verification Activity: By - SE
d027755f-c801-51e4-97ab-766e0e456545 | section | 4.22 Underpass Materials – Associated Works
6e241f13-080a-54f3-91a9-3f63a5538f62 | checkpoint | 4.22.01 - uPVC Pipe
58f48794-78c3-5ce8-99ac-d37e605b1df8 | note | Acceptance / Conformance Criteria - Pipes and fittings shall comply with the requirements of AS/NZS 1254:2010 for uPVC pipes
26a72867-eb08-5843-b7ad-5541570c7d65 | note | Standard / Specification - PS 19.27
c81c7cb5-7ccd-551d-8d39-70dd73cfc5ef | note | Verifying Document - Datasheets
51204c4f-7bc5-54bc-8d6d-dca676b57ad5 | note | Frequency - Prior to use
559b7457-9230-5915-b77d-afb55d2d7e42 | note | Verification Activity: Activity - R
9b279fb8-aa65-55b4-a993-bd63b0b974c7 | note | Verification Activity: By - SE
bb0e75dc-1a51-5fad-b17b-a8746b4bb728 | checkpoint | 4.22.02 - Anti-Graffiti Product
ed1a3651-466d-5660-9109-bca5d1059484 | note | Acceptance / Conformance Criteria - Permanent (not sacrificial) anti-graffiti coatings shall be applied to the exposed faces of all concrete surfaces including wingwalls. The coatings shall have a design life of not less than 10 years. The Contractor shall submit the proposed extent of application for authorisation by the Engineer.
548b5106-8ea7-51e6-af37-18da6cfedfd7 | note | Standard / Specification - PS 19.24.1, PS 19.24.2
07d6f0fe-95e2-54a0-9809-ac754836368a | note | Verifying Document - Details of prequalified Product
a7361187-0b65-5bb7-a912-e41336e4af3c | note | Frequency - Prior to Application
7ef4e30e-d2c6-59d5-a9e6-a5dc54812ae4 | note | Verification Activity: Activity - HP
20a8db01-e966-5932-b0fb-9c6cac10ab56 | note | Verification Activity: By - ENG
9567846c-86e7-5454-ac56-98fecc04f512 | signoff | AUTHORITY HOLDPOINT
3d41d29f-bfe3-5761-947c-2852f1080563 | checkpoint | 4.22.04 - Steelwork Fabrication Notice
43092ea8-2c44-5563-931e-f42c02583fe6 | note | Acceptance / Conformance Criteria - To allow for the provision of inspection and verification, the Contractor shall, in writing, notify the Engineer at least one weeks prior to commencement of the workshop fabrication work.
1f363a02-311e-5738-8a15-1cf7065bdf85 | note | Standard / Specification - PS 19.26.6
c351b5ba-0384-5f39-adc7-fc55d3d54458 | note | Verifying Document - Notice
16aac013-c8eb-56cd-a7d3-f71078b04d7e | note | Frequency - At least one weeks prior to fabrication
377d1077-20a8-5fed-98c3-1715cc9bb805 | note | Verification Activity: Activity - HP
7ba80646-ab1f-5b2a-8f75-339cd746a4ea | note | Verification Activity: By - ENG
8ab17f8f-b589-5fe1-b550-165d674a5e43 | signoff | AUTHORITY HOLDPOINT
9887edd4-a572-5477-af85-3e459867e16a | checkpoint | 4.22.05 - Steelwork Shop and Erection Drawings
22459906-5f11-50a1-9b2a-e0a0b125f719 | note | Acceptance / Conformance Criteria - The Contract Drawings show the design intent. The Contractor shall submit shop and erection drawings to the Engineer for approval a minimum of 10 days prior to fabrication.
7c2647c3-47c9-5832-bc71-1aecebc187a0 | note | Standard / Specification - PS 19.26.7
1ee22e0e-0ce2-5e61-8e05-c3c725c12d29 | note | Verifying Document - Drawings
8f2978f9-3860-5bf1-9aa9-1f7491f46758 | note | Frequency - 10 days prior to fabrication
d5a93200-74f8-5af4-8172-8f6c13b06f66 | note | Verification Activity: Activity - HP
a9416b2c-8158-5279-9d18-ea2265828bf1 | note | Verification Activity: By - ENG
cb6277a0-8e1b-5abe-983e-d2e4e943f079 | signoff | AUTHORITY HOLDPOINT
a08a068c-cb8c-544c-b872-dbbbdfaf4857 | checkpoint | 4.22.06 - Welding Plan
a5082915-36f2-5f7f-8314-af6727f8ac67 | note | Acceptance / Conformance Criteria - The Welding Plans shall comply with AS/NZS 5131, Section 7.
37f48751-a29d-59e5-a9c1-ad99b7e317e5 | note | Standard / Specification - PS 19.26.8
23ab5077-2f96-5fb2-8d08-94490f3bfa29 | note | Verifying Document - Welding Plan
a3a806e8-7c84-573a-ac02-17e10e8b7d47 | note | Frequency - Prior to Welding
a4d1b7d6-de9d-5cf1-8c2e-a2152d4ae192 | note | Verification Activity: Activity - R
062deea6-8de8-5057-b659-d02686b4f1bc | note | Verification Activity: By - SE
77a3eeaa-7d42-57a8-9949-440aa7dbc1e6 | checkpoint | 4.22.07 - Welder Qualiications
9b4968fd-9a57-5f47-8626-f79f5e0ce522 | note | Acceptance / Conformance Criteria - Welder Qualiications shall comply with AS/NZS 5131, Section 7.
7a3928dc-716a-58c1-ad8a-b895867f1b4e | note | Standard / Specification - PS 19.26.8
975a9e08-049c-52ba-a981-b58ada2f14f4 | note | Verifying Document - Qualifications
38929fc8-b89c-588f-983c-eb85b668d8d2 | note | Frequency - Prior to Welding
ef241d45-3c38-5108-b0a7-3a963d00f521 | note | Verification Activity: Activity - R
da6a157a-18fb-5210-b827-7d6f5aeff4f0 | note | Verification Activity: By - SE
196d8138-343d-53bd-9148-554125db4a5f | checkpoint | 4.22.08 - Supply of Non-slip Coating
c15ed590-5b65-5de0-a327-33e8a2dca326 | note | Acceptance / Conformance Criteria - The top of the underpass floor slab and bottom chamfers will have Sikafloor 91 or Sikafloor 150.
f8d5076e-38d6-5c4d-88dd-e45dcf58d475 | note | Standard / Specification - PS 19.23.1
bd257fb3-bf3e-587f-be54-35ee7f447de8 | note | Verifying Document - Datasheet
10c07705-8623-5fb7-a39d-172189c34fa8 | note | Frequency - Prior to use
12954c93-453d-5d29-9360-621fbdfee3e3 | note | Verification Activity: Activity - R
c1ed26ee-9aac-5119-90e8-f7a724022ffc | note | Verification Activity: By - SE
8b7ece77-1fec-5c32-9b46-f85b3727fb63 | checkpoint | 4.22.09 - Joint Sealing and Waterproofing Sealant
b63b998c-109b-5e1e-828a-c0e645e301ed | note | Acceptance / Conformance Criteria - Joints are to be sealed using a fuel resistant, multi-component polysulphide sealant designed for horizontal and vertical joints in concrete and is joint sealant pourable or gunning grade as appropriate.
f2084351-8dfc-5b2f-9ce1-ff488c39e696 | note | Standard / Specification - PS 19.22.1, PS 19.22.7
2e96da32-cafb-59d2-9834-d23e547b9602 | note | Verifying Document - Datasheet
6000cc61-582a-5db4-9bb0-307a99a797ce | note | Frequency - Prior to use
76d6171b-0cac-5867-a60f-17b20c07cc8a | note | Verification Activity: Activity - R
719b027f-c463-53b7-9b39-a1bd699b6258 | note | Verification Activity: By - SE
509f57c9-951f-524a-a813-237822099452 | checkpoint | 4.22.10 - Debonding tape / Backing Rod
c8e61dee-3614-5fc5-981d-25549fb79c4a | note | Acceptance / Conformance Criteria - A polyethylene bond breaker tape, or a closed cell, polyethylene backing rod shall be used in movement joints unless joint sealant is natureally bond breaking.
c39ce643-08a6-53b9-9edb-d4f9a39bb454 | note | Standard / Specification - PS 19.22.3
3c9c9ddb-f577-51cd-b28f-4b082f18aac6 | note | Verifying Document - Datasheet
21d29b28-202b-5c2c-abd4-b717485fbb57 | note | Frequency - Prior to use
f745acf0-69fc-5171-85ca-442c0ad09852 | note | Verification Activity: Activity - R
e5abab30-2e8f-574a-878f-8118d07046b2 | note | Verification Activity: By - SE
716c18c8-b218-5a52-b884-d30c5f9c7fd2 | checkpoint | 4.22.11 - Compressible filler board
7d64cda1-ea26-59c2-b7f1-03c2b217dca6 | note | Acceptance / Conformance Criteria - Details of the Compressible filler board proposed to be used shall submitted to the Engineer for acceptance at least 1 week prior to installation.
6f41f44d-a3dc-5d56-b29b-c40534b6f4d6 | note | Standard / Specification - PS 19.22.6
9416ce14-15b7-5cd2-b6c6-19ffd2f0451d | note | Verifying Document - Datasheet
7d6be9ac-2323-54b0-a2e0-47a23a2ee968 | note | Frequency - prior to installation.
b6a63abf-1952-5214-81fe-03883fb7a5bb | note | Verification Activity: Activity - HP
17764c61-2575-5ec5-83ce-0f632a8864cd | note | Verification Activity: By - ENG
63ef02f2-9bee-5161-82f3-fab62a00a088 | signoff | AUTHORITY HOLDPOINT
b3c7639a-7ced-5f49-a911-333bd4864dfa | checkpoint | 4.22.12 - Reinforcement bars
04cc4d1a-878a-5266-9e1a-7b48ad8a3ec8 | note | Acceptance / Conformance Criteria - All Reinforcement bars shall be of New Zealand origin unless otherwise accepted, grade 500 ductility class E and shall be manufactured by the micro-alloy process. Quenched and tempered reinforcement shall not be permitted.
9a3b0fca-aa79-5d28-8192-e1d5266b6d6a | note | Standard / Specification - PS 19.16.12
b2c3fa86-8b48-51ac-89f8-ef2a66716b4e | note | Verifying Document - Mill Certs
11f87309-812d-5039-ae7f-946e42c0d52c | note | Frequency - Each Item
f38e71c6-a94b-55f3-896a-ee2600e35476 | note | Verification Activity: Activity - R
98ff664b-c0f2-59d6-87f8-e135a49e202e | note | Verification Activity: By - SE
b6d13b33-48f8-5267-87e0-2af4c71ad310 | checkpoint | 4.22.14 - Reinforcement Welding Approval
70874d40-097c-5e37-99dd-14fb4b658414 | note | Acceptance / Conformance Criteria - Steel reinforcement shall not be welded, except where specified on the Drawings or approved by the Engineer. In either case, welding of reinforcement shall comply with AS/NZS 1554.3.
f6acbd9f-0dae-5b04-8986-001dbb11014f | note | Standard / Specification - PS 19.16.15
f66e186a-7374-5b50-ab60-3659ae0a4718 | note | Verifying Document - Engineers Approval
0efc08b2-c886-5f07-b35d-601a49e23017 | note | Frequency - Before Welding
db825aec-1248-5a19-b18b-1a0065d0469b | note | Verification Activity: Activity - HP
2a06a9cc-9c6b-5791-b925-4bc7b5156787 | note | Verification Activity: By - ENG
25ea82a6-5d0f-516e-853c-22770674301f | signoff | AUTHORITY HOLDPOINT
36bf2169-cd8e-53ba-b367-d9b9d17d5f58 | checkpoint | 4.22.15 - Welding TPI Inspections
7f82326a-8edd-51d4-88c3-7bdbcdf83a64 | note | Acceptance / Conformance Criteria - The welding shall be inspected by the Contractor’s Third Part Inspector who shall meet the “Qualifications of Inspectors” requirements of AS/NZS 1554.3 Clause 10.2. Inspections of the welding shall be in accordance with AS/NZS 1554.3 with the following additional requirements: All welding shall undergo visual scanning. Welding shall be non-destructively tested to the extent and standards of acceptance of AS/NZS 1554.1 Appendix F, for SP welds. All welds shall be visually scanned by the steel fabricator. 30% of the welds shall undergo visual examination in accordance with Table 6.2.2 and 5% of the welds shall be subjected to radiography or ultrasonic testing in accordance with Table 6.2.1 of AS/NZS 1554.1.
1c33f483-2b92-5364-b919-ab5a3300a09f | note | Standard / Specification - PS 19.16.16
49b84990-322a-5024-a2b6-4914a6223e4a | note | Verifying Document - TPI Report
63db3569-b627-523f-bce2-646bced6f606 | note | Frequency - 100% Visual Scanning
b2bf14cd-6933-51c7-a13c-5787d5157472 | note | ○ 30% Visual Examination
75b83f6c-e2a7-5ebb-88c6-b097a6e94867 | note | ○ 5% Radiography / Ultrasonic Tesing
3c313b1c-cf49-5111-816b-93508b83c983 | note | Verification Activity: Activity - R
d8897d61-b29c-5514-b5f7-f81ce87a2253 | note | Verification Activity: By - SE
20daaa14-ea0e-54ef-b89c-4fed1c1a1889 | checkpoint | 4.22.16 - Bar Schedule
40e00c5c-3cb9-5e62-ba32-15418e4621d0 | note | Acceptance / Conformance Criteria - The Contractor shall prepare reinforcing bar schedules in accordance with BS 8666 with due allowance for bending tolerance and associated drawings, two copies of which shall be supplied progressively to the Engineer for comment at least 14 days before the start of placing the corresponding reinforcing bars.
7de681e3-d7b7-5ba9-bbe5-714ecbc05a3f | note | Standard / Specification - PS19.16.20
84d78042-6bba-5fbc-9623-b5b56a2d1008 | note | Verifying Document - Bar Schedule
00647474-21d5-5d55-9f1d-940b4db1419b | note | Frequency - At least 14 days before the start of placing
ef6d4512-2d98-5ef0-b95f-ab5d2c703182 | note | Verification Activity: Activity - HP
31449ce5-2071-5f5b-ac29-aa6431bb15cc | note | Verification Activity: By - ENG
32aff0ff-0a4a-51c3-ab26-0add07ab217c | signoff | AUTHORITY HOLDPOINT
185b1965-31fd-51ec-aa63-ac7a7967f669 | checkpoint | 4.22.17 - Reinforcing Mill Certs
582f89fe-3ac9-5333-86c7-189089b4dd8e | note | Acceptance / Conformance Criteria - Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of ay work incorporating these materials. Test certificates shall be traceable to the batch of material supplied to the work.
b2a97371-eadc-5ba3-b517-44d8c26cc50b | note | Standard / Specification - PS19.16.23
97f67526-d692-5dc9-8293-6d0643ecfec2 | note | Verifying Document - Mill Certs
14b8a9a7-2b07-5753-a8b4-7a5a07c9ad7c | note | Frequency - At least one week before the programmed commencement of ay work incorporating these materials
54bb79d0-7600-510e-8a5a-ea61ce8319ed | note | Verification Activity: Activity - HP
54cdf5ea-1370-50bd-aa08-2e67d1397671 | note | Verification Activity: By - ENG
a013c0bd-4609-5101-b527-449b3a18d076 | signoff | AUTHORITY HOLDPOINT
050b4a48-1add-5f49-b3c4-b4dd0acb32a5 | checkpoint | 4.22.18 - Corrosion Protection
e88658cc-1e1f-550a-a8db-ee7b5ff01a95 | note | Acceptance / Conformance Criteria - Unless otherwise shown on drawings, all steel members, bolts, nuts and washers, excluding any stainless-steel components shall be hot dip galvanized after fabrication in accordance with AS/NZS4680.
13cd2968-d064-5243-b0c0-39155c349dc4 | note | Standard / Specification - PS 19.17.1
fb5c3ebd-944b-5de1-9e47-ab5ebb6094cd | note | Verifying Document - Datasheet
515270ed-8429-556b-bf5e-0fd9e02f0b92 | note | Frequency - Each Item
615bae90-b4a5-50ae-a00d-9ee3c24ef18b | note | Verification Activity: Activity - R
17e94463-6e83-555e-97f9-9e7e1d868557 | note | Verification Activity: By - SE
29cce257-d047-560d-a0bb-5aec8f55d114 | section | 10.01 Concrete Pours
ddf5def9-40da-5e8f-a30a-5101fbd9bcce | checkpoint | 10.01.1 - Construction Joint Locations
b2225819-4841-5515-b5b0-8c24efd4cb81 | note | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
73ead49a-f787-5bcd-9b66-1ed27dd9f62b | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
4f101d28-ea29-5b60-a79e-1514bbbe4711 | note | Verifying Document - Approval
e24b9822-6c43-5391-b22e-4c88b50da725 | note | Frequency - Prior to Pour
ffb0b7de-5fc6-5874-88ac-a23169c4acc6 | note | Verification Activity: Activity - HP
05202aee-2f0f-5b50-90ee-06d7e708bdc3 | note | Verification Activity: By - ENG
4ff4caf5-29c0-5bda-a708-87e499624d43 | signoff | AUTHORITY HOLDPOINT
bf3d4714-e5d5-5509-a42b-66bea38f0b8a | checkpoint | 10.01.2 - Dry Pack Mortar
4e2d023e-df97-5274-ae42-6338c9d54ad2 | note | Acceptance / Conformance Criteria - Dry pack mortar where specified on the drawings shall be places as per the manufactures instructions.
28c69cf1-5c3b-5376-b7cc-bc14706517ff | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
830cce76-3026-5938-b5b8-81548c21f972 | note | Verifying Document - Pre pour
3718fa3e-bde5-54f7-b0ef-58c637068d27 | note | Frequency - Before Works
0d0d2aa1-6d02-5899-bfc2-0340295de738 | note | Verification Activity: Activity - R
5cb8fc78-a74c-5396-8f16-0cd4be1a158d | note | Verification Activity: By - PE
12c26443-934d-5a44-88b6-8603ac4805ba | checkpoint | 10.01.3 - Blinding Concrete Subgrade Inspection
a6e89354-7048-583f-881a-c5a8f729a377 | note | Acceptance / Conformance Criteria - A subgrade inspection is required by the Engineer prior to the pouring of the blinding concrete layer.
02cb5d0a-7c74-5fbc-8978-c0789f515fa0 | note | Standard / Specification - PS 19.5.1
c440ffa9-0779-5312-8bf0-0c9ddafe2d81 | note | Verifying Document - Pre Pour Checksheet
d30b91af-1e25-5d96-b0f9-17744238915a | note | Frequency - Prior to Pour
d8bc78ee-e062-5251-b6e1-0bbf96cbbb48 | note | Verification Activity: Activity - HP
4b7f307f-830e-5ac2-8332-c105100a78f0 | note | Verification Activity: By - ENG
b1ac62b9-1d13-5f6d-a1d2-bf98e64f904d | signoff | AUTHORITY HOLDPOINT
69b1846b-7ca9-52e4-a5a4-109c63f26b5f | checkpoint | 10.01.4 - Reinforcement Pre Pour Inspection
19c5ad9e-084c-5a5b-969d-cf4824c2bb95 | note | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
5fab8b27-45db-549e-8a8f-a891509ea9d4 | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
4de9420c-a6cb-5fc0-a316-e0bd5aa3d51e | note | Verifying Document - Pre pour
a77612fb-2ee3-5e61-9f81-127619d51353 | note | Frequency - Each Pour
3b7b791f-78ee-5502-b3aa-6fe543024602 | note | Verification Activity: Activity - R
cd527bba-3d28-556c-9c50-0e74fa3bbb42 | note | Verification Activity: By - PE
980d9547-e4b1-5810-a07d-68159afd4ef2 | checkpoint | 10.01.5 - Pre-Pour Inspection
75d143b2-2584-5745-a1b8-53cb25b41a81 | note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
d6e9d056-5ebf-5bb2-a840-02716632a204 | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
30216ff3-540d-5692-85d2-c325446cdabf | note | Verifying Document - Signed Pre-Pour
02161c7a-6dfd-5862-9c35-06c35e471e5d | note | Frequency - 48 Hours Notice Prior to Each Occurrence
6c39902c-2a24-582d-afc6-7a01e8721fc4 | note | Verification Activity: Activity - HP
ceedf489-2146-576b-b867-091e67d447ec | note | Verification Activity: By - ENG
29c75676-141e-5308-a17b-059832f7f1bc | signoff | AUTHORITY HOLDPOINT
545610bf-420b-5e5f-843d-88ccb744f5d0 | checkpoint | 10.01.6 - Delivery Dockets
25fe0a4e-d671-5480-bafb-dd3f99be288e | note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
c37ff86d-f8d7-550f-9d76-4c3d1d81a089 | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
5b0397aa-1671-5cc0-9db9-e0ffd58ed0a4 | note | Verifying Document - Dockets
014d92ba-75c9-5260-b160-7c274feafd7b | note | Frequency - Each Pour
8d8fa6a5-af4d-5af8-9cc5-afb968b6d2f6 | note | Verification Activity: Activity - R
71e1d5b6-fdc7-5c98-9dde-e46beec353ab | note | Verification Activity: By - PE
39572f77-0e68-5354-9c7e-c02b65ddbdea | checkpoint | 10.01.7 - Slump Testing
4be0e272-64ee-5795-9508-87cdef8ccef6 | note | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
9a02c1f5-f25d-5af9-bf0a-a60bc7d13efa | note | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
37426970-c98b-549e-af0a-b12a032ca573 | note | Verifying Document - Pre Pour
12c16151-de69-5da5-a308-016f37ec5db3 | note | Frequency - Each Pour
07a918d6-a30a-5651-ae95-43f9dbeb2537 | note | Verification Activity: Activity - R
8c94e8c6-8c60-5311-ad72-096191785281 | note | Verification Activity: By - PE
a68b74f2-5060-567d-be84-990c7f007dbd | checkpoint | 10.01.8 - Compression Testing Insutu Concrete
77c65b0f-0a85-5dba-bc63-1ddb276f5b1a | note | Acceptance / Conformance Criteria - The sampling of freshly mixed concrete shall be random, and the type of samples shall be representative. The frequency of compression testing shall be determined by the Engineer, but there shall be at least one set of test specimens taken daily. A set of test specimens shall consist of at least six field specimens made from one sample of concrete. Three shall be tested at 28 days after casting.
2aba5d30-13dd-5e2e-97fb-95f5bb88bc40 | note | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2, PS 19.8.7
9054545f-c754-54c7-a7c4-63863dbf53fc | note | Verifying Document - IANZ Test Results
90ecd10f-6d68-5890-b31b-74dfda657ee4 | note | Frequency - One Set Daily consist of at least six field specimens
09401163-4c9f-5e55-ac5c-8a76d5dfd521 | note | Verification Activity: Activity - R
7547f48f-d292-57bd-92c2-e2b2509a76bd | note | Verification Activity: By - PE
08e026e3-9ace-58ef-8d95-f212e891eaba | checkpoint | 10.01.9 - Compression Testing Precast Concrete
08028f69-6943-53ea-86e4-9ee591272ed5 | note | Acceptance / Conformance Criteria - For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28 days compressive strength in an approved laboratory.
8869d7fb-7329-541e-9e9e-91b81318c360 | note | ○ For repetitive small pours (e.g., precast concrete barrier pours) undertaken on a regular basis, three standard cylinders shall be made for each of the first five pours of any one type, and thereafter three standard cylinders shall be made for every fifth pour of that type for testing of 28 days compressive strength in an approved laboratory.
6dec6147-31cc-5995-9660-6ba7e6de709a | note | Standard / Specification - PS 19.8.7, PS 19.8.8, PS 19.8.9, PS 19.8.10, PS 19.8.11
bb6f54c1-fcb8-5682-b271-e2a46799d161 | note | Verifying Document - Plant Test Results
1816b98d-289c-514d-aa77-1fe2e47ae8f4 | note | Frequency - 1 set per 50m3 or part therefor of / First Five then every 5th
1a804d19-4630-57cc-a064-6fd260ebe80f | note | Verification Activity: Activity - R
0a70add6-acb4-54c2-9ab8-85377d5c183e | note | Verification Activity: By - PE
ada65559-9e0b-5d91-800f-942054472e78 | section | 10.02 Post Pours
4e22a134-60cc-588b-8f12-eaeb422f1a7c | checkpoint | 10.02.1 - Post Pour Inspection
ef616bfd-ca9d-5a6d-98d4-a8c772fb6e05 | note | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
22cf8016-1c26-50d9-8e00-d89060bf73d2 | note | Standard / Specification - PS 18.2, PS 19, PS 19.15
4a498a84-c0e8-58b9-a2bb-add3a815d9c4 | note | Verifying Document - Post Pour
71b83169-6721-504e-9879-6a9a37232e7b | note | Frequency - Each Pour
489909c1-e1de-5852-b917-19015021ef6e | note | Verification Activity: Activity - R
e7462f14-b203-5510-b1bb-0a70c0663655 | note | Verification Activity: By - PE
bb0e6aa4-62be-5996-b3b1-73c166e80309 | checkpoint | 10.02.2 - Construction joints
45612da8-c8b1-590f-8ce3-4f2ec1bef678 | note | Acceptance / Conformance Criteria - Construction joints shall be placed as per the drawings / agreement.
9e445051-818f-5bcf-9e9f-56f5b20daf0b | note | Standard / Specification - PS 18.2, PS 19, PS 19.15
361daf4a-ee44-5b7e-9694-eeb7fb685716 | note | Verifying Document - Post Pour
8164530f-30ef-5ede-9921-23ed54a87bef | note | Frequency - Each Pour
d2d35986-55f4-5f08-a422-a7a6a214bf91 | note | Verification Activity: Activity - R
7ecc7eb5-729f-5be3-9677-16e4c1389e87 | note | Verification Activity: By - PE
583a9a8f-3977-5799-863b-f43c473088a2 | checkpoint | 10.02.3 - Concrete Curing
7f2ae6b5-60e8-5fb2-b8ad-adc1212f1334 | note | Acceptance / Conformance Criteria - Concrete shall be cured for at least 7 days as per the drawings / specification.
a89b33bd-e872-5839-bdc1-cc4c6527d382 | note | Standard / Specification - PS 18.2, PS 19, PS 19.12
4dc2ba2b-036e-5993-913d-9f4653f23c8d | note | Verifying Document - Post Pour
183fbd73-7c91-5898-b6ce-e3c8ee8aed2f | note | Frequency - At least 7 days after pour
8100b68e-5c5c-5135-96c6-ef100345ce14 | note | Verification Activity: Activity - R
46cb6b6d-0a8d-5430-a020-efe33572e359 | note | Verification Activity: By - PE
8dfa5b69-676d-5f38-a9fb-4e13f3a8b18a | checkpoint | 10.02.4 - Stripping
d604b028-ad77-5560-8a9b-056eb63c5be1 | note | Acceptance / Conformance Criteria - No formwork shall be stripped until at least 3 days have elapsed from time of pouring concrete.
c23c71d1-ca3a-5fff-aa2c-5c867063bccf | note | Standard / Specification - PS 18.2, PS 19
3e3ed230-058d-539c-9cc7-3af3b6a95b74 | note | Verifying Document - Post Pour
0e46acfa-dfeb-57e8-97e2-fff14e835f30 | note | Frequency - At least 3 days after pour
fb50bd4e-f794-56bb-837a-01995173a024 | note | Verification Activity: Activity - R
25cab698-87f6-55f9-998b-be2f0160387b | note | Verification Activity: By - PE
38f0359e-a3cf-5c68-8d7d-a71754a24712 | checkpoint | 10.02.5 - Protection of Completed Works
3f1cd740-99ba-5dba-83c2-e1c7789037ce | note | Acceptance / Conformance Criteria - Protect the completed work from damage and from dropping other materials during the remainder of the construction period. Do not use the completed work as a building platform or for material storage.
c36a781d-ed0c-5bd0-a7b7-fb410ad4f686 | note | Standard / Specification - PS 18.2, PS 19
75d9f11d-8901-5dcb-9ddb-25a9d18b395a | note | Verifying Document - Post Pour
e208d638-af54-5601-98b4-4cc7c84259d4 | note | Frequency - During the remainder of the construction period
d9ac58cd-70da-50a7-9260-d67214476827 | note | Verification Activity: Activity - R
20b0923c-c870-5551-ba13-752ba14518be | note | Verification Activity: By - PE
3bf41fc9-dbeb-5a09-9b35-0de57ba98e79 | checkpoint | 10.02.6 - Defective Concrete Finishes
662a6a18-e4f1-56cc-88a5-4adcecd3b56e | note | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
06ed3d80-d320-54fa-925c-d71ae6aada41 | note | Standard / Specification - PS 18.2, PS 19, PS 19.13
5edf30ca-0440-5c10-8226-2136dbf8e4bc | note | Verifying Document - NCR
5fa2c48d-3f8b-58e9-8cd3-be43b590087a | note | Frequency - Prior to non Minor Repair
d61120b3-f98f-5a5f-b700-12348ccf1e73 | note | Verification Activity: Activity - V
306aecf1-15b6-5ac1-9384-0dc4da90ae31 | note | Verification Activity: By - SE
09d6770f-c9fd-55d6-a473-70cd1fa70a46 | section | 12.01 Undercut to Drying Site and Backfill with Compacted GAP65
d7cbace4-bb93-5f8e-94fc-3072a77f43ae | checkpoint | 12.01.01 - Excavations
97bb8cba-ad47-59cb-a150-e14d8a5870de | note | Acceptance / Conformance Criteria - All excavations/cuts shall be carried out in fully drained conditions with no free water on the working surface.
d042845d-1295-5eac-9921-4f3abd12f8c5 | note | Standard / Specification - PS 19.4.1
60dbd2cb-bb32-5f82-90da-fb1996b97701 | note | Verifying Document - Site Records
bf7b264f-a7c3-52dc-8eef-f9d4a7b09dd2 | note | Frequency - During Works
e14d8061-79f6-5ade-bf18-61099c055cc6 | note | Verification Activity: Activity - R
b96cbeef-c3c3-5813-9c35-10c551bf5f29 | note | Verification Activity: By - SE
0b423a17-f2f0-5007-a86c-b30cc9b57bc5 | checkpoint | 12.01.02 - Foundations
9f45efa3-a5d0-5290-8534-96f5788103f6 | note | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
3910bbba-ab24-5ca2-a13e-27c0080d96fe | note | Standard / Specification - Downer
e4bf5677-9ddd-5aeb-b38e-df64d42c7d2d | note | Verifying Document - Scala Report
c738c855-738e-5906-bb01-43af2eae8710 | note | Frequency - 10m
fd4eec4a-96ee-56e8-aae6-a16263047479 | note | Verification Activity: Activity - I
6bff1b69-3d2b-55f5-a12c-5f34f34250ca | note | Verification Activity: By - SE
808aa903-be80-556f-aca4-b05e2f914690 | checkpoint | 12.01.03 - GAP65
1f0fc1b4-2db1-53d9-b153-3f19e44db912 | note | Acceptance / Conformance Criteria - The imported granular Material shall be GAP65 with the grading envelope given in Table 15-3 and have the following geotechnical parameters after placement and compaction Angle of internal friction = 35° and Cohesion = 0kPa
15b25874-f432-57f4-adfb-7b1382d7e00f | note | Standard / Specification - PS 19.4.5.3
0b83bec7-2eb3-5f0e-9067-655d0938813f | note | Verifying Document - IANZ Test Reprots
b8f294b1-57bf-5cad-a88b-386128cfb153 | note | Frequency - Prior to use
a6cebb80-64c8-5d90-bdaa-b02a0ad6c4f0 | note | Verification Activity: Activity - R
a5b61f33-5f09-560e-820e-1cec1560a2c4 | note | Verification Activity: By - SE
b2d1bb69-5699-5738-92ec-2fe30d4b298e | checkpoint | 12.01.04 - GAP65 Layer Compaction
a89a954a-48b6-57bb-a349-a9841ee047a0 | note | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95
d5225379-432e-5413-af4f-d8e24a91882f | note | Standard / Specification - PS 19.4.5.4
4ef67507-19d8-5229-bc5e-223a60f72375 | note | Verifying Document - NDM Report
c0c5199b-bdbc-5507-a2ea-f388adf6038f | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
9325bd4c-f2df-54a1-ba06-6407cf35f6c4 | note | Verification Activity: Activity - HP
487e1de1-9dec-55af-a5f1-3eb409f2c60d | note | Verification Activity: By - ENG
8889cfbd-f68e-5d41-b749-24d6735f9c51 | signoff | AUTHORITY HOLDPOINT
5d138294-9a5c-5a64-9f56-5a9721a45049 | checkpoint | 12.01.05 - GAP65 Layer thickness.
bd0a60d6-eb75-5b89-9be8-9a7829488262 | note | Acceptance / Conformance Criteria - The Sub-basecourse shall be monitored for Layer thickness. The GAP65 layers shall be constructed in accordance with NZTA B/2. The maximum lift thickness shall be 200mm.
894ba11a-c6b0-5683-965d-08bcf90e9985 | note | Standard / Specification - PS 19.4.5.4
4fb6fdf7-a95f-5f9f-9a8a-857ab44a7fea | note | Verifying Document - Survey / Level Checks
d69114e3-7a1a-50bf-b8c7-5c713525dd71 | note | Frequency - 1 test per 20m
50fa3739-abbe-5bff-9c33-ade0c9ba32e4 | note | Verification Activity: Activity - R
ba754ba5-fced-5dba-a074-f6a43e12de9c | note | Verification Activity: By - SE
20cd3c6a-e8a4-5de2-866a-668c612edb1a | checkpoint | 12.01.06 - Proof Rolling
e29ddd50-0ad8-54b5-906d-0739cada8b26 | note | Acceptance / Conformance Criteria - The GAP65 layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass.
1bf66a4d-30cd-5ec9-a6d1-35d85b599731 | note | Standard / Specification - PS 19.4.5.5
54c4bd53-e48b-512c-b42b-826001c465f3 | note | Verifying Document - Site Records
476d2e5e-3cf9-5dbf-a6eb-bb56ba65c7e8 | note | Frequency - Prior to Concreting
871e6f36-9019-5a58-bbc1-67544bd1c016 | note | Verification Activity: Activity - W
cfb963e2-3f0a-50a2-a9bd-219af2836e71 | note | Verification Activity: By - SE
635f73eb-6089-58cd-8e44-f9b159b2d813 | section | 12.02 Concreting
c2c4f6c2-b7cf-5984-8a7e-3cae9c9ba574 | checkpoint | 12.02.02 - Insitu Concreting Methodology
be662ab7-82b0-561c-829c-7a3f164eebb3 | note | Acceptance / Conformance Criteria - The Contractor shall submit the proposed handling and placing methods, sequence and timing of pours and location on construction joints for the Engineer's consent before concrete placing commences. Where a placing diagram, construction joint location diagram or equivalent is included in the drawings, the requirements thereof shall be followed unless changes are specifically agreed by the Engineer in writing.
28f56793-5acd-5131-8c8f-a1a79badff34 | note | Standard / Specification - PS 19.9.1
a129302a-e12f-5b42-81b5-59750251cf68 | note | Verifying Document - Methodology
c3ddddc7-4c9a-570a-a4b1-1d8232eb170e | note | Frequency - Before concrete placing commences
efc4b4e0-0675-5bab-af8e-2ee1fb76a30d | note | Verification Activity: Activity - HP
186ae7e8-bce7-5221-9633-418607de404f | note | Verification Activity: By - ENG
741ebdb7-a413-5fb3-8f48-f9de8fd46de9 | signoff | AUTHORITY HOLDPOINT
4865e8a0-c8b9-5211-99b7-836829d56695 | section | 12.03 Precast Concrete
b38a7d23-b39d-5067-9778-043b52dee3ae | checkpoint | 12.03.01 - Precast Methodology
afaa02af-43fe-51a2-800b-bf552f580764 | note | Acceptance / Conformance Criteria - Details of the proposed method of casting, curing, storing, transportation, and erection shall be submitted to the Engineer before commencing manufacture of the mould and precast units.
97fe4a6c-51d0-587b-b73f-a614b56eafb6 | note | ○ The Engineer shall be informed 24 hours prior to the casting of any unit, to allow the Engineer to attend the pre-casting plant to inspect before and during production of the units.
727183a1-fdf9-5018-bad6-e68952b8fd59 | note | Standard / Specification - PS 19.15.1
b14f2400-82cf-510d-ad2c-130e7d028566 | note | Verifying Document - Methodology
6b5c28c0-dbf4-56bd-b617-68130a2c514d | note | Frequency - Before commencing manufacture of the mould and precast units.
7ef73f19-3af0-5ad0-ad37-2e97ab541dd0 | note | Verification Activity: Activity - HP
52e6224b-e171-5d59-8c56-4a70bf78dd15 | note | Verification Activity: By - ENG
5b00292b-bfe6-5963-a1fb-dd424e542cbe | signoff | AUTHORITY HOLDPOINT
97dc4747-cdf3-5557-aa09-2b6e02835df6 | checkpoint | 12.03.02 - Precast Shop Drawings
9468f1bc-09d3-5f09-9c72-1f144544efde | note | Acceptance / Conformance Criteria - The Contractor shall make available the shop drawings to the Engineer for review, at least 14 days prior to manufacture. Any variations between the Drawings and shop drawings shall be clearly identified and brought to the attention of the Engineer.
4a859762-4464-510c-befc-fa8522c97f6f | note | Standard / Specification - PS 19.15.16
d8fe157b-4adc-53a3-a251-332f3ce70939 | note | Verifying Document - Shop Drawings
98988191-4bff-5694-a4ff-c3e31b859018 | note | Frequency - At least 14 days prior to manufacture
f6aa56cf-0e4f-595a-99d7-8539f431baac | note | Verification Activity: Activity - HP
ecfa6b0c-d3e0-54a7-bdfb-4e88d6f309b6 | note | Verification Activity: By - ENG
25202b86-1f51-5c8c-a1bb-dd2accc2a529 | signoff | AUTHORITY HOLDPOINT
aa322b93-5630-5961-8051-afe33a5827e1 | section | 12.04 Installation and Bolt Tightening
9f64880d-ebaa-56a8-9c72-477d0d294c9a | checkpoint | 12.04.01 - Structural steelwork fixed to the concrete surfaces Dry Packing
d290ab33-cf1b-5ffe-a83c-060713ab7ae3 | note | Acceptance / Conformance Criteria - All structural steelwork fixed to the concrete surfaces shall be bedded against the concrete surfaces using a layer of dry pack mortar, plastic bedding mortar or grout with a minimum compressive strength at 28 days of at least the specified compressive strength of the element being bedded against.
7ec7b40d-11b5-57b4-a965-031789829838 | note | Standard / Specification - PS 19.18.1
ea9828b5-eb56-5049-8cb5-7bc2ce84ff91 | note | Verifying Document - Pre Pour
9b1b3976-3305-5d97-ae30-cd97249eab13 | note | Frequency - All structural steelwork fixed to the concrete surfaces
e48ab7bc-3982-5d23-a360-4cce15339a29 | note | Verification Activity: Activity - I
161ea7ad-c0d9-5f0d-b416-71506cffce84 | note | Verification Activity: By - SE
84b03552-8ae3-5bbe-939c-fe5ada6fac05 | checkpoint | 12.04.02 - Bolt, threaded rod, and stud connections
1f7d3a76-58c0-5b74-b096-276ef7771157 | note | Acceptance / Conformance Criteria - All bolt, threaded rod, and stud connections shall be installed in accordance with AS/NZS 5131 Section 8.2. Tightening shall be to the snug tight condition as specified in Section 8.3 of AS/NZS 5131 after the mortar packing or grout has hardened. Where shown on the drawings, lock nuts shall be fitted, and snug tightened against the nut.
4b8ad16c-5980-5583-a223-fdbe57ba0247 | note | Standard / Specification - PS 19.18.2
bc5b25ff-8cdd-594d-8f20-546ff97314fe | note | Verifying Document - Site Records
4df0902c-e5b2-589b-bfba-d846ccf99000 | note | Frequency - Each Bolt
fddfbb36-351f-5fa0-a25d-72d1ab1e689d | note | Verification Activity: Activity - I
689c2ac3-e38d-59eb-b88d-91fb4806a035 | note | Verification Activity: By - SE
a87d1c5d-d09e-5e42-843c-b496902d4b3b | section | 12.05 Underpass and Wingwall Backfill
53061aa9-dbfe-5d4e-830b-0868bebf18f7 | checkpoint | 12.05.01 - Polythene Sheet above Underpass
cee2b800-fc8b-57dd-b838-80fcb26926eb | note | Acceptance / Conformance Criteria - Two layers of polythene sheet shall be placed across the full width and length of all underpass precast concrete units. The polythene sheet shall have a nominal thickness of 0.25mm and comply with the requirements of the New Zealand Building Code.
14759f24-20d3-5890-8dbc-bcfa90816bab | note | ○ Polythene sheet shall be lapped by a minimum of 150mm at all joints.
76e6ed59-844a-5312-8d75-c002572f246d | note | Standard / Specification - PS 19.19.1
a38c0994-eb2a-5a6c-ab39-4a53a8e81a9e | note | Verifying Document - Site Records
bd3f1e5c-8ea4-545e-8c04-b031bf5f6775 | note | Frequency - Each Sheet
34fc454f-52de-58d1-894b-99d655d41cab | note | Verification Activity: Activity - I
d3dae103-ddd5-5454-9437-54bb140b64ea | note | Verification Activity: By - SE
ba3cb896-2d37-5125-a9a1-b8a2b71b0e6d | checkpoint | 12.05.02 - Minimum cover over Underpass
a264e1fd-1cf4-5b8f-ab23-e8a3917b2797 | note | Acceptance / Conformance Criteria - The minimum cover to the underpass within all traffic lanes is to be 600mm to the top of the pavement.
3390e8e9-4d33-5291-ba39-e4287b014b61 | note | Standard / Specification - PS 19.19.1
c1fbfe3f-fee1-5eec-95b0-c89fdf405439 | note | Verifying Document - Survey Records
a4ba4813-b6b1-5e0b-acd1-cb6cceffe578 | note | Frequency - During Backfilling
cd6268f8-87ce-5be1-9f81-6afa1041afa8 | note | Verification Activity: Activity - I
d2588c7f-c269-5707-b6f7-69fe494581f0 | note | Verification Activity: By - SV
c9ec4dff-4ff1-5b1f-8144-e55cc6743033 | checkpoint | 12.05.03 - AP40 Backfill alongside Underpass
f2694d03-faf5-5c49-b08b-c8148fd598ef | note | Acceptance / Conformance Criteria - Fill shall be spread in horizontal layers not exceeding 200mm loose depth. Backfill shall be compacted in accordance with TNZ B/2. The maximum lift thickness shall be 200mm. Backfill shall be carried out in unison on both sides of the box underpass such that the level of backfill on one side is not more than 500mm different from the other side, at all times. and testing shall be completed on each lift.
d89dd283-6f74-5b24-a6cf-3507d4962659 | note | Standard / Specification - PS 19.19.2
a5b7fa1e-6556-57fe-8e4b-d92b9d239b9a | note | Verifying Document - Site Records
d496f9a3-cb27-5fdd-8305-7b59db813e8b | note | Frequency - Each lift
f826854a-3410-54bf-8d9c-a6d53097b936 | note | Verification Activity: Activity - R
0eb3fc18-bab7-5c7d-b970-05915d331b9b | note | Verification Activity: By - SE
a5e9f1a5-1720-58b5-9041-e517564c2c45 | checkpoint | 12.05.04 - AP40 Backfill Compaction Testing
5add8675-3696-5e50-8095-af47c2ece2cc | note | Acceptance / Conformance Criteria - Clegg testing shall be carried out and recorded for each lift (200mm Maximum) to be carried out once per 10m length of the 300mm wide AP40 strip. A CIV value of 40 shall be achieved for each test.
77dad3c3-b723-5aa8-95ac-c1eca1cb44c2 | note | Standard / Specification - PS 19.19.2
556b299e-a559-5a72-bc99-db84fc2b4683 | note | Verifying Document - Clegg Results
68d1c079-bf0e-59bb-a7d6-b8c8d2083628 | note | Frequency - Each lift to be carried out once per 10m length of the 300mm wide AP40 strip
46eb9b5a-19e8-5b0a-9b4a-c092f3588e42 | note | Verification Activity: Activity - I
c8920217-b234-5595-b4de-75f2847d98cf | note | Verification Activity: By - SE
aba2e09b-1e5d-5df7-b8f5-4e2773650758 | checkpoint | 12.05.05 - Polythene sheet at Culvert
849ebf72-6cd2-59e1-b65e-8030fcda4478 | note | Acceptance / Conformance Criteria - The polythene sheet between the precast culvert and the structural fill, or site concrete layer. The polyethene sheet shall be a single continuous sheet with no joins. The sheet is to be laid flat with folds or wrinkles prior to the placement of material on top.
4f7f0bed-325b-5cbf-b4c0-75b92c352a2d | note | Standard / Specification - PS 19.20.2
3b167963-c3b3-55bb-bf9a-26c2d489b6ca | note | Verifying Document - Site Records
f0242803-c0fe-5c7d-b835-4f3e094b50be | note | Frequency - Each Culvert Entrance
73e45ea2-2aae-5e0f-a5b0-f092625b4b5b | note | Verification Activity: Activity - R
b74a0b64-c8dd-5d00-ade6-77a3835ef1c7 | note | Verification Activity: By - SE
b4e7e5fe-c530-558c-b051-926e772ea5ec | section | 12.06 Joint Sealing and Waterproofing
506e7714-f4ea-58a4-abfa-cd064c80c570 | checkpoint | 12.06.01 - Preparation
fb3b19db-8811-575b-bf45-f0960a55879a | note | Acceptance / Conformance Criteria - The joints surfaces should be accurately formed and must be thoroughly dry, clean, and free from frost. Remove all laitance, curing compounds, form release agents, loose material, and any contaminating foreign matter from joint faces by grinding, grit blasting or wire brushing. The prepared sealing slot should be blown out with dry, oil-free compressed air. The sealant may be applied in joints up to a maximum of 30mm wide. All moving joints should be designed to an optimal width to depth ratio of 2:1, with a minimum joint size of 12mm sealant depth.
414a62eb-768b-57b5-bde1-2631c9db51f8 | note | Standard / Specification - PS 19.22.2
887c5026-e94c-5134-9a44-0296d6eae49f | note | Verifying Document - Site Records
8e132dcd-7ae7-5c02-b66b-685edf51132c | note | Frequency - Each Joint
1cf46dae-6e46-5bc8-93fa-f60df98b9358 | note | Verification Activity: Activity - R
66a7f355-311b-5217-9384-fe7223c099c6 | note | Verification Activity: By - SE
cba9df5e-1840-510c-b3e6-9ee45b1732d9 | checkpoint | 12.06.02 - Movement joints
f3eb1f54-44d4-58fc-b314-fcbefd41eded | note | Acceptance / Conformance Criteria - In movement joints, the sealant must not be allowed to bond to the back face of the joint.
67f075c7-9174-5125-a365-82829b9613f3 | note | Standard / Specification - PS 19.22.3
df76e417-ecdc-5ff2-ac4a-58a53bc1675a | note | Verifying Document - Site Records
0985baed-c9fd-5389-bdce-b28a722a5639 | note | Frequency - Each Joint
79162b12-f8b1-5a6c-ad4d-669d1477365f | note | Verification Activity: Activity - R
cc04f2eb-9779-5bf4-bd25-9ae3ab06751f | note | Verification Activity: By - SE
657d9132-bd5a-562f-b479-70bcd42119b6 | checkpoint | 12.06.03 - Concrete Age
13b89807-9a4e-58c7-ac23-efa5285c7100 | note | Acceptance / Conformance Criteria - New concrete must be allowed to cure for a minimum of 28 days before sealant installation.
bab37d1e-371e-5eeb-bf4f-11704acdcc0b | note | Standard / Specification - PS 19.22.4
84ef6c23-b372-5721-a799-e5de1ab9c913 | note | Verifying Document - Site Records
02bbf6cf-1ec0-5afb-9a37-b10eeb6cfaff | note | Frequency - 28 days post pouring
a68c3715-3a4b-55e3-8b5c-fafa2f3cf24a | note | Verification Activity: Activity - R
6f7d7ead-1329-5a5d-8279-645cba251254 | note | Verification Activity: By - SE
fa894895-71d0-52ec-b7ef-6e8c9d0da791 | section | 12.07 Supply and Install of Non-slip Coating
a29779db-d9dc-5a4f-a7fc-c2d7bb96fe8a | checkpoint | 12.07.01 - Install of Non-slip Coating
04c30715-8c5c-5859-9672-996f5c51cda4 | note | Acceptance / Conformance Criteria - The top of the underpass floor slab and bottom chamfers will have Sikafloor 91 or Sikafloor 150 applied after the installation of the box culvert segments. The thickness of this is to be between 3 and 5mm. The application of the product must be done in accordance with the manufacturer’s specifications.
fb8e1f87-87f7-518a-b17a-cae412f5e895 | note | Standard / Specification - PS 19.23.2
7f4de997-193d-5b19-89ca-27246937b813 | note | Verifying Document - Site Records
937ec9b2-73ec-501c-ab26-52e485b47c1a | note | Frequency - Each Underpass
1f739448-5758-530b-9f84-24e95214d0d1 | note | Verification Activity: Activity - I
4d63cd5a-ba25-5c6f-adcd-920253522c3c | note | Verification Activity: By - SE
d3adefc2-67da-5698-9ca4-d2400ca3e896 | section | 12.08 Anti-Graffiti Finish
77be84ea-a9a2-57a2-970e-999b184ae026 | checkpoint | 12.08.01 - Anti-Graffiti Application
cda89512-8344-562a-b03b-56ee34edbb9d | note | Acceptance / Conformance Criteria - The anti-graffiti coatings shall be applied and maintained in accordance with the manufacturer's requirements.
54a0a2ca-85c6-5795-a3f8-f0ace541504f | note | Standard / Specification - PS 19.24.3
a7d0dbf6-4937-5649-9a2f-bfc22343be54 | note | Verifying Document - Site Records
c5ee8124-af2c-5dfe-a313-b0cdbff19e35 | note | Frequency - Each Application
a5a7ec8b-ae66-568a-bcdb-243fe6b2fe30 | note | Verification Activity: Activity - R
457a7204-3a90-5a8f-b029-b89e4ac6c428 | note | Verification Activity: By - SE
efacb135-16e5-55ca-a64a-5494421f2fce | section | 12.09 Steelwork Fabrication and Installation
72a3fc25-ec20-5289-8196-77d5b59e0577 | checkpoint | 12.09.01 - Welding
2415b9d2-f0a0-5ba9-b531-ace0b9d79442 | note | Acceptance / Conformance Criteria - Welding shall comply with AS/NZS 5131, Section 7.
d86d71df-6274-5cf8-87b1-743f9a463446 | note | Standard / Specification - PS 19.26.8
5650394d-4662-5fd2-a729-b44b2847ca49 | note | Verifying Document - Site Records
ef6fd828-8c5a-5bc7-ac4f-4a821f3f52f8 | note | Frequency - Each Weld
930948b8-100c-5138-bb85-7d9c9d4320a7 | note | Verification Activity: Activity - S
e0aa515c-9658-5a64-b6fd-6c3477d6af4c | note | Verification Activity: By - SE
88697b26-9511-5008-b735-86c64b81f050 | checkpoint | 12.09.02 - Holing
4f87bf26-68d1-556b-ae9b-c3c4fbe3da06 | note | Acceptance / Conformance Criteria - Holing shall comply with AS/NZS 5131, Section 6.7.
19dd755c-cf14-5e8d-a427-f3f5c10c9bf2 | note | Standard / Specification - PS 19.26.9
ca9493f9-f48d-5cd1-a028-c1757f5bfd2a | note | Verifying Document - Site Records
6d748a21-a145-5b0a-bcd8-c97717a557fa | note | Frequency - Each Hole
7d4c027d-322b-5e8d-8250-1e951276c660 | note | Verification Activity: Activity - S
e0c5ca18-71e8-559d-a3c6-2df7c1f3e02f | note | Verification Activity: By - SE
005199f0-55dc-51b6-a050-65a89216e346 | checkpoint | 12.09.03 - Installation
f4a3a584-07df-502d-a34d-3bf0cf89b450 | note | Acceptance / Conformance Criteria - Holing shall comply with AS/NZS 5131
8e6eb9aa-f1bd-5337-ad96-5e0eaea79f51 | note | Standard / Specification - PS 19.26
b0058667-828f-5b75-8ff7-1f7613c4477a | note | Verifying Document - Site Records
4bb6e719-7e34-5e7d-a92f-ff48a80e6262 | note | Frequency - Each Item
7b604d30-2666-5865-a68f-6dae94fad86f | note | Verification Activity: Activity - S
81511f79-be31-5cb3-9edb-ce3b31e17659 | note | Verification Activity: By - SE
32f26889-aec1-582e-aec7-39adc34c3a13 | section | 12.10 uPVC Pipe
71941ead-6a23-5072-b6db-602aa1b01232 | checkpoint | 12.10.01 - Plastic Pipe Trench Backfill
522b9f09-8aa4-503d-80c9-1872ca5bd165 | note | Acceptance / Conformance Criteria - Plastic Pipe Trench Backfill
6449c151-7fa2-54a9-b52b-91906ef62d4d | note | Standard / Specification - Except as shown otherwise on the drawings, or directed otherwise by the Engineer, support material shall be as per AS/NZS 2566.2.2002 “Buried flexible pipelines – installation” corresponding to the relevant pipe support type as detailed. All materials in bedding zones, side zones and haunching zones shall comply with the grading specification in the aforementioned AS/NZS 2566.2.2002.
fc5cf35b-12b1-5209-a19f-cf92cfe3eaf0 | note | Verifying Document - PS 19.27.4
dd976146-8876-4252-8a19-5d2bde46e4e2 | section | 12.11 Underpass Capping
7e3205cd-2fc4-47e5-b2ad-91a5bf1be13f | checkpoint | 12.11.02 - Pit Sand/Geotextile
7e188068-5590-588e-9d52-d4d3dbc4d843 | note | Acceptance / Conformance Criteria - 100mm min thickness Course (Pit) sand over the culvert and for 2.5m either side.
e1ef5b88-f445-5ce5-8b13-36794ed27576 | note | ○ The pit sand layer shall be wrapped in geotextile on all sides.
1963ee10-e02a-537e-994c-70edba575ba3 | note | ○ Pit sand to be compacted with lightweight plant (and water) and proof rolled for acceptance
0fcb4ae5-fd00-51c6-9728-c4534954aa6f | note | Standard / Specification - RFI-DN1208-DOW-GCO-0149
c28d1b00-09bf-5f2c-9ccf-25e7dc099c31 | note | Verifying Document - Site Records/Data Sheet
d285cd18-35d0-56b1-ac5f-860b699834ae | note | Frequency - Each Underpass
8a3230e1-9c1c-5239-bed4-b1ad4565f8d2 | note | Verification Activity: Activity - R
eb51d875-5aea-5f1c-803c-9e199a1450b1 | note | Verification Activity: By - PE
6d7588b6-3bd0-4426-a07c-d41a226898ba | checkpoint | 12.11.03 - Geogrid (Duragrid X 30/30)
f034b296-6aba-59ff-8183-afc0f8b75913 | note | Acceptance / Conformance Criteria - Geogrid to be placed above the pit sand for 10m above the last bench either side of the underpass
e5557635-4dc7-5df0-9db0-9aef081a3c55 | note | Standard / Specification - RFI-DN1208-DOW-GCO-0149
6fbeb31f-222b-5d7d-a970-4da584d6cbb1 | note | Verifying Document - Site Records
0cd4c863-787b-58a9-9556-2da54821a8dc | note | Frequency - Each Underpass
5f4e8d92-2637-55ea-ba38-80d36dcffca3 | note | Verification Activity: Activity - R
2ce4bb9f-3e26-53ab-926a-26508b598ea3 | note | Verification Activity: By - PE
3cb41a1f-3cee-4e02-b33c-7c0e932fbcf4 | checkpoint | 12.11.04 - AP40
dc88d514-1f53-57b8-804d-34ce2d9fdced | note | Acceptance / Conformance Criteria - Variable depth of AP40. Compacted in 100mm max. layer thickness. NDM testing to be conducted and to achieve MIN of 91 and AVE 95% of MDD
34ff8f2f-1ab8-5a05-aa08-2b1c4be32d4a | note | Standard / Specification - RFI-DN1208-DOW-GCO-0150
70a2f682-c65d-5671-aa3e-3d9e686c7bf3 | note | Verifying Document - NDM Field Sheets
c8493319-592d-5f51-9545-f9d7424811ef | note | Frequency - Each Underpass
9c53f98a-5a68-5cf5-8b89-1203278814d4 | note | Verification Activity: Activity - R
d20aad59-2b3f-5497-b455-1163fd5551b4 | note | Verification Activity: By - PE
16b607e7-d75f-45bd-ab18-a764c0ca3fbc | checkpoint | 12.11.05 - 10Mpa Concrete
21332432-2b00-55c7-811a-792e5a1b7e98 | note | Acceptance / Conformance Criteria - Replace Hilab 65 layer with 10MPa Concrete for 2.5m either side of underpass.
faf5c379-3673-5f8e-9925-0c2cc2c10835 | note | Standard / Specification - RFI-DN1208-DOW-GCO-0151
37a2fc34-46da-5814-8251-f6908806e9e6 | note | Verifying Document - Site Records/Data Sheet
a46e6b32-76f4-570e-95cb-905e0c16d35d | note | Frequency - Each Underpass
d9d7a052-c15b-58ec-ae94-f2f08bde7734 | note | Verification Activity: Activity - R
ad1cd557-ad09-5d84-9ca3-49c9a1367ce5 | note | Verification Activity: By - PE
457493dc-0bd2-467e-a671-4c4659fc3657 | checkpoint | 12.11.06 - Hatelite Asphalt Reinforcement
b6ea629f-1f2d-5a51-abd1-fc44143124a2 | note | Acceptance / Conformance Criteria - Hatelite to be installed on top of first layer of AC20 above underpass for 12.5m either side.
52920a3e-cdc9-5e90-b538-d045bbd13032 | note | Standard / Specification - RFI-DN1208-DOW-GCO-0151
238dab0c-b898-5f65-a576-fd1cc7255136 | note | Verifying Document - Site Records
ae7dfd92-1dd0-557b-8dba-97d3a389a101 | note | Frequency - Each Underpass
97f83136-52a0-5e62-a71d-65151ef22644 | note | Verification Activity: Activity - R
5b0c28fe-29ad-506f-ab1a-986a616cff05 | note | Verification Activity: By - PE
6a51a261-0438-5ca1-bcad-d0fa766c1843 | checklist | ITP - Utilities ITP - 105 - Rev B | itp | ITP - Utilities ITP - 105 - Rev B
6b75b985-ae5c-5a47-b89a-b1523ac6b3bb | section | 17.01 Services
91e264ed-3c61-51aa-8cbc-19f20861dbc7 | checkpoint | Existing Services
a7b82be6-5066-5e73-9ea4-5d49074cc5e9 | note | Acceptance / Conformance Criteria - The Contractor shall locate or arrange for the relevant service authority to locate existing services prior to commencing work in any area. Where a clash of services is identified the Contractor shall summit a proposal for overcoming the problem to the Engineer. The Contractor shall give service authorities reasonable notice when excavating within close proximity to their services.
38ef4909-88ea-54f1-82ed-b5f063781684 | note | Standard / Specification - PS 24.1.1
2a18cabf-b228-559d-96c3-23636ab69e52 | note | Verifying Document - Comms
fd9c301c-a802-5c92-9aab-bdf1cb59e2d9 | note | Frequency - Prior to commencing work
96511d44-7923-5d30-bc67-85d26e50c5d7 | note | Verification Activity: Activity - HP
153b5bf0-bbc3-5b6a-8ddd-6a5d685a2c99 | note | Verification Activity: By - ENG
42748784-238b-5b1a-8516-c27d7583e33a | signoff | AUTHORITY HOLDPOINT
93c04d03-af02-597f-bfa9-24cdae54c223 | checkpoint | Private Services
15e7e877-ff09-515e-860f-c59234954dbe | note | Acceptance / Conformance Criteria - Any private services such as domestic water and power supplies, rural mailboxes etc., damaged by the Contractor’s operations shall be repaired at the Contractor’s expense. The Contractor shall keep disruptions to individual landowners/occupiers to the minimum practicable. The Contractor shall consult with all affected landowners/occupiers to arrange for a mutually acceptable time for works that will interrupt availability of services and to identify any special requirements for continuity of supply. Where there is a requirement for continuity of supply the Contractor shall take all reasonable measures necessary to satisfy the affected party’s requirements. Where possible at least 10 Working Days’ notice should be given before shutdowns.
5db48652-420d-5454-a640-1fd54447bad0 | note | Standard / Specification - PS 24.1.2
caf34197-bcd3-58e7-9076-9250028e9427 | note | Verifying Document - Comms
901079fd-aa32-55c3-87a7-8b733cd396f9 | note | Frequency - 10 Working Days’ notice should be given before shutdowns.
78e52848-8532-5df4-85a4-1c0df5637ba3 | note | Verification Activity: Activity - R
cbb19cc2-1b68-5046-bf27-56cf796eff35 | note | Verification Activity: By - SE
59def15e-e138-5f9d-b93c-fe3b1d410957 | checkpoint | Service Connections
0ea143f7-d548-5856-807a-647a9ab68752 | note | Acceptance / Conformance Criteria - The Contractor shall liaise with the appropriate service provider to coordinate connection of the new service into the existing service.
ee2e0a1d-8bf5-50c7-aa7a-14056bc9fdd4 | note | Standard / Specification - PS 24.1.3
669377b7-56b2-5159-83d3-e568cd417e43 | note | Verifying Document - Comms
30fab273-2392-563c-92cb-281653217d73 | note | Frequency - Prior to connections
e65f53ab-09b3-5d4b-85e2-eb9557a8633b | note | Verification Activity: Activity - R
65341bfa-de94-594a-abc0-b18dd217eacc | note | Verification Activity: By - SE
7d29ee5f-c6d4-594f-a48a-3bb331fb5301 | section | 17.02 Locate and Pothole Services
2f3b42c9-909d-5429-bee7-4cf8a7147fa8 | checkpoint | Service Location
2cbee9ff-cd65-51ad-8f23-0388fb0e2036 | note | Acceptance / Conformance Criteria - All locations where connection to an existing pipe is proposed, the Contractor shall pothole and expose the pipe and level the crown. If an issue is identified from potholing, the Contractor shall notify the Engineer.
f9ea7ed0-d4f9-5356-ac72-69cd3e3dab30 | note | Standard / Specification - PS 24.2
46e0ce0e-0500-5741-8540-284af7eefa51 | note | Verifying Document - Potholing Record
cde8f58b-bbe1-58f5-b417-b023eb0d6551 | note | Frequency - Prior to Excavation
4bfb9e3d-1537-51ec-adfa-bec412c8c302 | note | Verification Activity: Activity - H
a11288f4-19b1-5b2e-98f6-3a7f8d765589 | note | Verification Activity: By - PE
108b1f07-ffeb-5cf0-806b-2efccb2f103d | checkpoint | Service Clashes
5fd77950-b3bd-5fe4-8436-479fc215016a | note | Acceptance / Conformance Criteria - The Contractor shall notify the Engineer immediately of any service clashes identified and the Engineer will advise on how to proceed.
52c6189f-3cf1-5fcb-82d1-19f40ad19337 | note | Standard / Specification - PS 24.2
a7d792e0-0334-5c65-ac10-3c9dfc22617c | note | Verifying Document - Notice
a0099c39-baa2-5ae6-a1e8-1201ddb8e56a | note | Frequency - Each Occurrence
f4faf304-1b91-5193-9535-6ee6f55500bd | note | Verification Activity: Activity - HP
16282b5a-eb47-563f-b652-9458c850c688 | note | Verification Activity: By - ENG
d4332a62-d978-5521-8b0a-c03b6e98d957 | signoff | AUTHORITY HOLDPOINT
b2036b55-32ee-5a9d-81e0-6994939494ab | checkpoint | Service Plans
fdecfde7-6967-54ab-946f-ed41e5a7db75 | note | Acceptance / Conformance Criteria - The Contractor shall be responsible for obtaining all service plans and identifying all existing services on site, including potholing where required to confirm the exact location and depth.
06bb3591-b021-5761-8809-1802c7eb13e5 | note | Standard / Specification - PS 24.2
95f10bc1-930b-54e9-b88c-668bfafa59c3 | note | Verifying Document - Service Plans
a78bbf8d-d6e5-5322-997d-a4c4120ab480 | note | Frequency - Prior to Excavation
e1136b17-085a-5224-80c8-05b626d2a51f | note | Verification Activity: Activity - H
5a7a1f9f-81f4-5af6-947f-bcbe0c60336e | note | Verification Activity: By - PE
9b81d9d6-fe6a-58b9-b026-b19a93b3559b | checklist | Ω (DEPRECATED) ITP - Concrete Pours - 305 - Rev B | itp | ITP - Concrete Pours - 305 - Rev B
29cce257-d047-560d-a0bb-5aec8f55d114 | section | 10.01 Concrete Pours
ddf5def9-40da-5e8f-a30a-5101fbd9bcce | checkpoint | 10.01.1 - Construction Joint Locations
77c3fee4-3014-56c6-8958-0d2d7a21c949 | note | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
6299b251-e253-5d7b-8616-e6d1bbed7943 | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
50bf4ba8-d836-5923-81e4-c26e161e1c9a | note | Verifying Document - Approval
05f5dfe5-3fe3-5f13-b20c-b50dc3ae4f02 | note | Frequency - Prior to Pour
58791a38-7c74-516f-9592-b9c501d97dde | note | Verification Activity: Activity - HP
af220b77-4659-5d55-bbdd-bd932a951939 | note | Verification Activity: By - ENG
4ff4caf5-29c0-5bda-a708-87e499624d43 | signoff | AUTHORITY HOLDPOINT
bf3d4714-e5d5-5509-a42b-66bea38f0b8a | checkpoint | 10.01.2 - Dry Pack Mortar
ab50827c-4169-56dc-bc37-97b6801b7c23 | note | Acceptance / Conformance Criteria - Dry pack mortar where specified on the drawings shall be places as per the manufactures instructions.
7d76b01f-021d-541d-87c6-6e0cfc1a23be | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
4e642898-e8f4-5e6e-b7e4-0be5d2cbbc37 | note | Verifying Document - Pre pour
18092f30-659a-50eb-bb1c-1341356f36c3 | note | Frequency - Before Works
03cef8c8-2bbb-5d8c-8af4-5cff17d157b9 | note | Verification Activity: Activity - R
88967d4c-4cb9-5844-a2d1-5ad02b659fd0 | note | Verification Activity: By - PE
12c26443-934d-5a44-88b6-8603ac4805ba | checkpoint | 10.01.3 - Blinding Concrete Subgrade Inspection
c27bb992-036f-58e6-a2bc-8dc864d5017c | note | Acceptance / Conformance Criteria - A subgrade inspection is required by the Engineer prior to the pouring of the blinding concrete layer.
f8224316-bb48-5c28-b1df-6d4ce286636d | note | Standard / Specification - PS 19.5.1
0657d05f-d3a2-5eee-89cb-bf76b2773c41 | note | Verifying Document - Pre Pour Checksheet
f9f6390f-ac06-5617-a6ac-1ff0ced3910c | note | Frequency - Prior to Pour
4b684efa-b574-5c3f-b1f9-774bb9e155cb | note | Verification Activity: Activity - HP
ae9f9c1a-49fd-5b3b-b7b9-03e0b1555f17 | note | Verification Activity: By - ENG
b1ac62b9-1d13-5f6d-a1d2-bf98e64f904d | signoff | AUTHORITY HOLDPOINT
69b1846b-7ca9-52e4-a5a4-109c63f26b5f | checkpoint | 10.01.4 - Reinforcement Pre Pour Inspection
216b0e83-62ef-52ac-af74-d6794062d74e | note | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
3da9c5cd-ed47-55a2-b596-7ef74d68b10c | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
de11a607-05ad-5602-85fd-9eef77824afe | note | Verifying Document - Pre pour
5c96772c-9d17-5174-b301-2ab930ac5395 | note | Frequency - Each Pour
2e28d195-174a-5fb5-83e7-4a90c3fcd018 | note | Verification Activity: Activity - R
2ae9c6f6-d823-5e84-b6c0-0aedb8a51d81 | note | Verification Activity: By - PE
980d9547-e4b1-5810-a07d-68159afd4ef2 | checkpoint | 10.01.5 - Pre-Pour Inspection
e1188bd7-cc46-5105-bfdb-d5350d5ff461 | note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
aeeffd21-0668-5cf1-8d4b-5601c15ee835 | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
73087163-48f0-5a5b-b952-d8685fe9b685 | note | Verifying Document - Signed Pre-Pour
f9fdd6cd-bafe-5618-b702-df89114ab36a | note | Frequency - 48 Hours Notice Prior to Each Occurrence
b1c9cd0e-fd05-5a18-8b07-935a95968af7 | note | Verification Activity: Activity - HP
ab527aeb-64a7-59e2-ac55-1624ec07938f | note | Verification Activity: By - ENG
29c75676-141e-5308-a17b-059832f7f1bc | signoff | AUTHORITY HOLDPOINT
545610bf-420b-5e5f-843d-88ccb744f5d0 | checkpoint | 10.01.6 - Delivery Dockets
34e8d0f8-5f3f-549a-a77e-38a16662f869 | note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
d15bdb02-9ce3-544a-8d0c-0c3219a7a6e5 | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
03f7f30a-6956-548b-b24b-8e234f7bc47c | note | Verifying Document - Dockets
9f333b98-7da3-5067-b90d-39fbed92f3f8 | note | Frequency - Each Pour
0e25c498-578f-5f20-9989-a086b9428134 | note | Verification Activity: Activity - R
16bfb57d-ab84-556e-bd07-1daeb5da06e3 | note | Verification Activity: By - PE
39572f77-0e68-5354-9c7e-c02b65ddbdea | checkpoint | 10.01.7 - Slump Testing
651b607c-4d94-5df9-97ef-609a228db4a7 | note | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
72bd8ce1-89f9-5b13-8e4b-df7548c6a14a | note | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
f1f6bea3-6dfd-59e2-8322-5c84efbe099b | note | Verifying Document - Pre Pour
052e3185-a0b9-52b2-9547-ad396b28fb3e | note | Frequency - Each Pour
baaef303-0d09-53ac-87ea-41a32b441645 | note | Verification Activity: Activity - R
cdce4799-a636-5b6a-b73d-ceef88b632b2 | note | Verification Activity: By - PE
a68b74f2-5060-567d-be84-990c7f007dbd | checkpoint | 10.01.8 - Compression Testing Insutu Concrete
abf0a42b-8816-5000-b618-2db993fbfae6 | note | Acceptance / Conformance Criteria - The sampling of freshly mixed concrete shall be random, and the type of samples shall be representative. The frequency of compression testing shall be determined by the Engineer, but there shall be at least one set of test specimens taken daily. A set of test specimens shall consist of at least six field specimens made from one sample of concrete. Three shall be tested at 28 days after casting.
6a74b721-efda-532c-b476-6bfba71717be | note | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2, PS 19.8.7
5d095a00-f6af-56dd-91e2-f8996967bb37 | note | Verifying Document - IANZ Test Results
d9eb6ebe-16df-5faa-8657-5c2ecc5c56ce | note | Frequency - One Set Daily consist of at least six field specimens
03fdcca1-9688-5095-a292-952a5b7e0bdf | note | Verification Activity: Activity - R
b5de1487-a723-51c5-a611-07d5b4bf5cfd | note | Verification Activity: By - PE
08e026e3-9ace-58ef-8d95-f212e891eaba | checkpoint | 10.01.9 - Compression Testing Precast Concrete
20f3bc5d-f827-554e-bf54-0d26b9f4fe89 | note | Acceptance / Conformance Criteria - For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28 days compressive strength in an approved laboratory.
66ac3f96-f3e2-5246-9916-942853821161 | note | ○ For repetitive small pours (e.g., precast concrete barrier pours) undertaken on a regular basis, three standard cylinders shall be made for each of the first five pours of any one type, and thereafter three standard cylinders shall be made for every fifth pour of that type for testing of 28 days compressive strength in an approved laboratory.
c7d1e12d-4a77-5562-8943-817544d4c727 | note | Standard / Specification - PS 19.8.7, PS 19.8.8, PS 19.8.9, PS 19.8.10, PS 19.8.11
425fe4c0-3998-54a6-9db8-d263bd46a41e | note | Verifying Document - Plant Test Results
8505799b-7ca7-5805-a4ee-c8f37ee8c946 | note | Frequency - 1 set per 50m3 or part therefor of / First Five then every 5th
2e7def74-19db-501b-83e4-f1cd772a2f0e | note | Verification Activity: Activity - R
446ec503-bb3b-5e52-8c6f-3e4135ad37af | note | Verification Activity: By - PE
ada65559-9e0b-5d91-800f-942054472e78 | section | 10.02 Post Pours
4e22a134-60cc-588b-8f12-eaeb422f1a7c | checkpoint | 10.02.1 - Post Pour Inspection
bb73d605-2d35-5658-8d71-f816cd27d198 | note | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
e0b99469-16c1-5899-9486-eba94ee8639c | note | Standard / Specification - PS 18.2, PS 19, PS 19.15
1a9a3066-00b1-5cdb-9045-523d177d9011 | note | Verifying Document - Post Pour
d69124ed-2c9a-571e-b980-f4472fb9b6c1 | note | Frequency - Each Pour
2c9b75b6-3ae5-5516-84f7-286b062ea42f | note | Verification Activity: Activity - R
a6c2f255-940e-59b9-a4cc-2264904b06da | note | Verification Activity: By - PE
bb0e6aa4-62be-5996-b3b1-73c166e80309 | checkpoint | 10.02.2 - Construction joints
34f04b18-ee80-5818-877f-db6024f366bd | note | Acceptance / Conformance Criteria - Construction joints shall be placed as per the drawings / agreement.
c3622fe1-5cc2-5751-8395-573d7c1f22df | note | Standard / Specification - PS 18.2, PS 19, PS 19.15
5cfb1266-1870-5e58-93f2-162495d47f5f | note | Verifying Document - Post Pour
4aa7e96c-7a36-5bc8-80c4-297767529f7d | note | Frequency - Each Pour
4d36cdc4-19cf-5ba3-8981-4e89a4cde94c | note | Verification Activity: Activity - R
3cf6fe6a-fd2f-5b98-973f-d9a12d7151d7 | note | Verification Activity: By - PE
583a9a8f-3977-5799-863b-f43c473088a2 | checkpoint | 10.02.3 - Concrete Curing
088b2548-38a5-5d7b-b847-2006507623db | note | Acceptance / Conformance Criteria - Concrete shall be cured for at least 7 days as per the drawings / specification.
3a296e1d-1d18-55ae-835f-4df4cab41907 | note | Standard / Specification - PS 18.2, PS 19, PS 19.12
82d6a528-31ea-504d-bac1-c4c1d6655dc8 | note | Verifying Document - Post Pour
740c48b2-402d-5e91-86e3-b86d7114416d | note | Frequency - At least 7 days after pour
5b6e6d37-e249-5c36-bdce-b545d1e37b88 | note | Verification Activity: Activity - R
6c8f0a8d-c100-5b7c-b97a-d68c713568b5 | note | Verification Activity: By - PE
8dfa5b69-676d-5f38-a9fb-4e13f3a8b18a | checkpoint | 10.02.4 - Stripping
33296847-d9c7-5203-83e4-0572e5713c35 | note | Acceptance / Conformance Criteria - No formwork shall be stripped until at least 3 days have elapsed from time of pouring concrete.
52deacb3-ef2c-5cb0-ae4b-435066cb833f | note | Standard / Specification - PS 18.2, PS 19
e0a48761-de40-5585-a079-f12fa1539d0c | note | Verifying Document - Post Pour
cb20615b-9fe3-57e3-b0c4-3937e018f4f5 | note | Frequency - At least 3 days after pour
221d0b33-5dd5-5e32-ba5b-53dbe02d7eed | note | Verification Activity: Activity - R
d1e75c53-a4d2-5f7b-9e34-42bb173834ca | note | Verification Activity: By - PE
38f0359e-a3cf-5c68-8d7d-a71754a24712 | checkpoint | 10.02.5 - Protection of Completed Works
f2d0fc54-a351-54f3-92d2-2d6781fe43e7 | note | Acceptance / Conformance Criteria - Protect the completed work from damage and from dropping other materials during the remainder of the construction period. Do not use the completed work as a building platform or for material storage.
c7daff67-593c-5040-b967-62f080cc6d57 | note | Standard / Specification - PS 18.2, PS 19
ded691a8-9762-5ef0-bbea-0036cd5bc84c | note | Verifying Document - Post Pour
4af66c1c-feae-570a-8fbb-2dc2be5082c7 | note | Frequency - During the remainder of the construction period
d248199b-b113-598a-8fb0-18d22822b007 | note | Verification Activity: Activity - R
0e58fe0e-f00d-5611-9373-bc80dca87f3c | note | Verification Activity: By - PE
3bf41fc9-dbeb-5a09-9b35-0de57ba98e79 | checkpoint | 10.02.6 - Defective Concrete Finishes
bd5e44b7-a215-5e63-ad70-3206a3ae6e4d | note | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
5fadb43e-0d37-57e4-84e1-1afde5844eb2 | note | Standard / Specification - PS 18.2, PS 19, PS 19.13
8bcc5cd6-e69d-5ed1-8ae6-be46264c2bd2 | note | Verifying Document - NCR
cc604e63-458a-5084-b33f-e825e4fb7b6e | note | Frequency - Prior to non Minor Repair
471ca773-ed4b-5c35-9040-94e8be6b70b2 | note | Verification Activity: Activity - V
b6d0af65-6a06-53bc-a406-7b3b165d5b95 | note | Verification Activity: By - SE
3e8189fd-6110-55c5-9308-a903d3688c93 | checklist | Ω (DEPRECATED) ITP - Earthworks - 101 - Rev 2 | itp | ITP - Earthworks - 101 - Rev 2
ac5ee1ee-5139-57b0-9c55-3196b7da263c | section | 3.01 General
4b182364-c9b8-5807-85b4-26cb6c506fc7 | checkpoint | 3.01.01 - Precondition Surveys
69cd2420-d366-54eb-958b-47ee6ba30c3b | note | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
8a300e3e-8b0d-50e1-92a8-acacc9470272 | note | Standard / Specification - PS 2.13
4012ae1e-5742-5bb3-bd88-9891dd0da569 | note | Verifying Document - Precondition Survey
5ee54bf7-4881-50be-9cbd-b6ca24fbed29 | note | Frequency - Prior to the Contractor taking possession of the Site.
4ee5ad50-8a49-5ef9-b2ce-6829404da63e | note | Verification Activity: Activity - H
042a86d8-9388-5bf2-bc39-fae98a19ea53 | note | Verification Activity: By - PM
2c4b8fd4-5150-5656-bda8-48bbc0f299cc | section | 4.01 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
eec51e33-e195-5fd4-8848-2a84896576bc | checkpoint | 4.01.01 - Source Property Tests and Sampling
c970b435-1a5a-5b52-9c63-6d3dc47a7b24 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, Los Angeles Abrasion, and Soaked CBR at least 2 weeks prior to importing to the site.
5fddf01b-636b-5c1b-9e0f-f9d479c784a9 | note | Standard / Specification - PS 15.7.3 Appendix XIII
c05f86e5-078b-56d0-a84d-743d12ed7c80 | note | Verifying Document - IANZ Lab Reports
0d61936a-619a-5486-b002-fd3bb8ecd191 | note | Frequency - 2 Test Per Material Per Source at least 2 weeks prior to importing to the site.
6c36e154-7375-5049-8d17-38c7ea3fb8aa | note | Verification Activity: Activity - HP
3ce79e68-2cd7-57fc-8b23-187278275664 | note | Verification Activity: By - ENG
943c57a3-9718-5eec-a0c4-4f254ca57b92 | signoff | AUTHORITY HOLDPOINT
e74ba8eb-c7ac-51ca-806d-ce6b2d151d6f | checkpoint | 4.01.02 - Testing for Layer Compaction - MDD
0eea5d39-c7a9-597e-95e8-2d3aa0eb79ce | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Heavy Compaction), Optimum Water Content, Air Voids, and Shear Vane Strength (Su) with Range of Moisture Contents.
3a7cfff1-f254-5419-911c-e86cf81791ad | note | Standard / Specification - PS 15.7.3 Appendix XIII PS 15.13
bac60110-709f-58ca-825f-eef1d568b6fe | note | Verifying Document - IANZ Lab Reports
28d0819b-7509-50e5-aaad-6484fe8c56af | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
93ed1431-f321-5f8b-8125-d991cf43a90b | note | Verification Activity: Activity - HP
5eecf011-989a-5420-a82b-eb0149a57904 | note | Verification Activity: By - ENG
1ad45696-b06f-57ba-991f-876ec2469f8a | signoff | AUTHORITY HOLDPOINT
cc28f368-5ec3-56d4-92e5-eeccc9eacb38 | checkpoint | 4.01.03 - Production Property Test Sampling
6c461bdf-e882-525f-a094-2bcc190ce2e7 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD).
4c2ef108-068a-59d0-b3de-60b2a95c6c7f | note | Standard / Specification - PS 15.7.3 Appendix XIII
6a814afb-0be7-53e5-8592-2862e1a765fd | note | Verifying Document - IANZ Lab Reports
efce84d9-b1b2-5d89-991c-9da04e5ba923 | note | Frequency - 0-400 M3 – 2 Tests
f89666dd-0f56-5b39-b7d2-2694b08c1b13 | note | ○ 400-1,500M3 – 3 Tests
ed92ad50-6f20-5df3-bdee-ddfd8f5eb73d | note | ○ 1,500-4,000M3 – 4 Tests
8473fabf-bde7-5cc9-8e93-e31e0d9d300b | note | ○ >4,000M3 - 1 Test For Each Additional 10,000M3
fd98181f-7bd9-5f53-8201-bb0c6813a688 | note | Verification Activity: Activity - H
29935793-de84-5fc9-9e9a-dc726b88856e | note | Verification Activity: By - PE
d3197014-3f06-5fe0-b1d9-aea439b97c54 | section | 4.04 Type A3 (Site Won Landscaping Fill)
bd572b98-794b-572a-b262-0d8895c651db | checkpoint | 4.04.01 - On Site track-able Testing
8fefcbaf-cb68-5917-9433-3d41137b8e4e | note | Acceptance / Conformance Criteria - Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it is ‘track-able’ by the contractor’s plant. This shall be determined before Sampling.
b4914206-8d0b-5414-9502-17ae4fad6e1c | note | Standard / Specification - PS 15.7.3
e51abaca-32b0-57d1-8544-f906b25a9fc0 | note | Verifying Document - Visual Site Record
aaf6e6a1-d9e9-5a27-86da-31e404a8a62d | note | Frequency - Prior to Sampling
d4f5a2c3-8d72-5a12-84a0-52e374ec9d02 | note | Verification Activity: Activity - W
21e39c46-937e-5756-bf3a-0fa20897c108 | note | Verification Activity: By - PE
bbfc5154-bf5f-5edf-b862-ca5b40d3d743 | checkpoint | 4.04.02 - Testing for Layer Compaction - MDD
da4431ef-f91b-5faf-a07f-ebe5b3ed0ce8 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Standard Compaction), Optimum Water Content, and Shear Vane Strength (Su) with Range of Moisture Contents.
75366e9f-f170-5da4-8e90-2ba29431f456 | note | Standard / Specification - PS 15.7.3, PS 15.13
01c254a6-d804-5850-b1b7-daee29774ece | note | Verifying Document - IANZ Lab Reports
cd00113d-ee85-5286-956b-580960ae86ae | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
9895d0dc-5a1e-556b-b3a4-f60bb935b694 | note | Verification Activity: Activity - HP
803e0adb-6908-539d-91c5-5f291f829291 | note | Verification Activity: By - ENG
787da1d7-76e7-5318-90fc-d7c5b66f0772 | signoff | AUTHORITY HOLDPOINT
1b403918-b691-5bde-88b7-f3ee9e087117 | checkpoint | 4.04.03 - Insitu Property Test Sampling
b2e3a0b7-200b-54bc-8753-e33bdade2178 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD) and inspected for deleterious materials such as boulder size fragments and organic materials.
da342694-bd84-565c-b303-933f704abeb3 | note | Standard / Specification - PS 15.7.3
3f8b0f56-e239-5878-82f3-25bd301b0188 | note | Verifying Document - IANZ Lab Reports
54187772-fb0a-5304-b22d-e6fef5571033 | note | Frequency - Prior to use
5f2c876f-b40e-5944-91db-1b5c4f101bfd | note | Verification Activity: Activity - HP
10ebcf48-ad4b-5c4f-ac90-4d24da87969d | note | Verification Activity: By - ENG
f4da45cc-ae32-586a-82a0-8191c8cf5c37 | signoff | AUTHORITY HOLDPOINT
540a5e70-44a2-557d-9a5c-b23f9eba4a3f | section | 4.05 Topsoil
20c79c91-2f0b-5e64-bc79-4fc755ec0ddc | checkpoint | 4.05.01 - Topsoil
c48a7814-415e-5bf0-90db-a1b8443b9fdd | note | Acceptance / Conformance Criteria - Topsoil is defined as the layer of material immediately below the ground surface comprising vegetation, tree roots, other non-decomposed organic matter, turf and humus. The Contractor is to stockpile and utilise site won topsoil for placement on the final batter slopes and for borrow site reinstatement as shown in the Contract Drawings.
e65a11a1-9f5f-5b9b-b31a-005bf9a0f5ad | note | Standard / Specification - PS 15.7.3
cf04a554-dfc6-58b4-9613-62ac16fdabb9 | note | Verifying Document - Site Record
ee11df60-1ce5-585b-8998-69594136d238 | note | Frequency - During Stripping
e137dc49-6b12-5bed-ab75-30d89abce352 | note | Verification Activity: Activity - I
11dd70c8-b8f1-5205-a62a-89a0d37a59b0 | note | Verification Activity: By - SE
d75e34e2-526e-508b-9139-1c41f905aee4 | section | 4.06 Geotextiles
94c5cd81-4c09-5866-a780-a6cb2b294715 | checkpoint | 4.06.01 - Geotextile on Undercut to Waste and Backfill
01a812e1-2a2b-5d7f-a9f9-4d80c94b831d | note | Acceptance / Conformance Criteria - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation.
c17089c8-cde6-5780-af0b-4d44cfe037e4 | note | Standard / Specification - PS 15.10.9
3752352a-df5a-53b2-8094-118f73546c7d | note | Verifying Document - Datasheet
8e7145b3-d717-57d4-8b68-f84837bcbada | note | Frequency - Prior to use
6f3350cc-a5e3-5922-90ec-ceba1cff1e25 | note | Verification Activity: Activity - R
ffc1a14f-5946-57d0-b15d-4eb1e2f5b1a3 | note | Verification Activity: By - SE
00122e61-34f7-53d5-a67f-e0c09f6146f3 | section | 5.01 Site Clearance
aa56f8f4-2f1d-53a7-90e0-bf9bff008cd2 | checkpoint | 5.01.01 - Site Clearance
76735cd9-4858-55a6-aa06-101f02518612 | note | Acceptance / Conformance Criteria - All trees, scrub, non-lawn vegetation and/or self-sown plants within the extent of the earthworks shall be removed to waste in accordance with Clause 3 and Clause 9.4 of TNZ F/1:1997 Specification for Earthworks Construction.
e2b43d2f-4215-5670-89ab-c3b1d39d5dd5 | note | Standard / Specification - PS 14.1.1 NZTA F/1 - 3
f35896e9-18bd-51fb-84bd-a516fea07908 | note | Verifying Document - Site Record
1c9aecd5-6527-5a3f-90f9-fb46fb1152c3 | note | Frequency - Prior to excavation
553d21dc-d656-5d11-a678-49e9091a7776 | note | Verification Activity: Activity - I
b8ac2dc9-f39d-5a4c-88d0-92ffc13d346b | note | Verification Activity: By - SE
0434188f-64e5-5961-b752-f68ed0678033 | checkpoint | 5.01.02 - Dump Site Approval
165908c4-435f-5b36-8fd9-df3fab4ecdd9 | note | Acceptance / Conformance Criteria - The locations of dump areas shall be agreed by the Engineer before use.
e22c6756-65e9-50b5-b8f9-e78161c44d04 | note | Standard / Specification - NZTA F/1 - 9.4
55d5c387-b48b-5e7f-9757-2749a36ece54 | note | Verifying Document - Site Record
f84ff3ba-d111-577e-814d-2f3b3ff0c62e | note | Frequency - Prior to Stockpiling
73737f8f-3ed5-5230-a5fa-7d12fd1ac08c | note | Verification Activity: Activity - HP
74ce0d35-f379-5262-b7f4-46543d42148d | note | Verification Activity: By - ENG
c082bbf0-64bb-5295-803d-efd5e36c07d2 | signoff | AUTHORITY HOLDPOINT
97e973d9-e87b-5abc-b883-a17a57730683 | checkpoint | 5.01.03 - Mulching
7c25105e-22ed-5c83-8240-5f58fa89da29 | note | Acceptance / Conformance Criteria - Where possible, cleared vegetation shall be mulched and stockpiled at a suitable site for future landscaping work.
39aa4f4e-e9d4-5b72-a53a-4a01c43363d6 | note | Standard / Specification - PS 14.1.1
54411dec-bc57-5533-afb7-0f38308d0bf6 | note | Verifying Document - Site Record
d3575c48-3185-5f98-b1fe-4784265e23ac | note | Frequency - During Clearing
449c8392-36d0-5a80-8ce1-30049ce1eaa6 | note | Verification Activity: Activity - R
07fddfa0-d1c0-5767-bf10-aa4ad5673f63 | note | Verification Activity: By - SE
4f7cfdbd-f8a4-5f17-a5dd-b36d0cb99ded | section | 6.01 General Earthworks
7b7266d6-ecf8-561a-b4ca-7b37880265fd | checkpoint | 6.01.01 - Earthworks Methodology
c228e36c-639a-5d64-84a6-17b814e6f41b | note | Acceptance / Conformance Criteria - The Contractor shall submit the construction and QA methodology for each element of Earthworks including construction, Haul roads, Site Access, dewatering, Wet weather, testing, inspection, and hold points for review and approval prior to works.
0b682de4-c8ae-51d1-9923-ecbfc85690dd | note | Standard / Specification - PS 15.13, PS 15.6.2, PS 15.10.13
b50a3242-4781-56d2-9c29-2bfa07bedacd | note | Verifying Document - Approved Methodology
9b77a527-c1c2-52d4-bf08-2baf8fe48a93 | note | Frequency - Prior to Earthworks
00c15935-b738-5367-8878-db856c582b87 | note | Verification Activity: Activity - HP
2e554e60-d952-5dd6-861b-a558370ee856 | note | Verification Activity: By - ENG
326a5f19-66e6-52e8-8259-accb86134d3f | signoff | AUTHORITY HOLDPOINT
ce70eb24-ffd6-534e-9bc3-84ccc496c6db | checkpoint | 6.01.02 - Temporary Excavation Approval
8b4c1814-1483-57a0-a93e-7cf0f5129205 | note | Acceptance / Conformance Criteria - The Contractor shall submit Temporary Excavations details to the engineer for approval prior to excavation.
33ca796d-57e5-58de-b34f-c32e6163735c | note | Standard / Specification - PS 15.13
c6d3b217-5879-5d04-b9ab-a032084546f6 | note | Verifying Document - Engineers Approval
de2c1bd3-ac7a-562d-817a-3f4a0bb05767 | note | Frequency - Prior to Excavation.
cd18a545-923b-5871-b92c-dee9402f4e29 | note | Verification Activity: Activity - HP
b2515f22-7df2-58c2-ac65-fe920a60c040 | note | Verification Activity: By - ENG
7f24d1ae-eaea-5164-a39d-b9602a701e03 | signoff | AUTHORITY HOLDPOINT
7be180f9-b731-51bf-aa2a-2646cc8a1c69 | checkpoint | 6.01.03 - Temporary Works Design
6bf13ae3-7a65-50e5-8ee5-356f37e5f99f | note | Acceptance / Conformance Criteria - The Contractor shall submit the temporary works design for Review and approval of prior to excavation.
34321cd1-593b-53a3-963f-41929191a96b | note | Standard / Specification - PS 15.13
725dbc6f-43b7-58dd-b840-2a9e1cc7a0a5 | note | Verifying Document - Approved Design
e4fec50b-b4eb-5cfa-bc23-b5a1182bdb5c | note | Frequency - Prior to Excavation.
2ac192cb-bf2e-52c2-b62a-50c4c4697492 | note | Verification Activity: Activity - HP
e421222d-e59e-5ba2-9fce-d91b87b2c1cd | note | Verification Activity: By - ENG
bd223daf-c7ae-5c7b-b6da-6f123e740f86 | signoff | AUTHORITY HOLDPOINT
55e3284f-9a58-588c-bbef-d9a461605980 | checkpoint | 6.01.04 - Temporary Stockpiles
baf815d3-1ef3-59b4-94ad-daf49ffc72eb | note | Acceptance / Conformance Criteria - Temporary stockpiles shall not be located within the footprint of the permanent works unless approved by the Engineer.
18b30793-18bf-5c62-9ab2-12c0e2ba5c49 | note | Standard / Specification - PS 15.6.5
cc98758a-ecad-5043-bcc8-3a0f6433d90f | note | Verifying Document - Engineers Approval
58eb1e17-79a1-52e1-b4e4-ff51e4c2a10c | note | Frequency - Prior to stockpiling
08cfbbd5-6e1b-5ca2-872e-ed4df362935a | note | Verification Activity: Activity - HP
8f11b887-eb69-534b-b326-59012efc3a5c | note | Verification Activity: By - ENG
a94c983f-b77c-5257-ba7c-2cf26f751c21 | signoff | AUTHORITY HOLDPOINT
9f916a51-531e-50f9-ab39-015b1c560d11 | checkpoint | 6.01.05 - Surplus Material
02f14ce9-3ef4-562b-b104-58d1241b50c7 | note | Acceptance / Conformance Criteria - Surplus or waste soils may be deposited outside the site boundaries with the written approval of the Engineer.
c85b74b4-9183-55a7-ae2f-345297038e49 | note | Standard / Specification - PS 15.1
ef2e0cf0-e7d5-51ba-8a6d-bbc82bdf9e2f | note | Verifying Document - Engineers Approval
a960256b-958b-5eb6-af8e-bc4d99728fb0 | note | Frequency - Each Occurrence
52fea67b-14ca-5826-8d8a-c11dc3466cf4 | note | Verification Activity: Activity - HP
4b1848f4-9510-5def-95f4-d24b7a6c808e | note | Verification Activity: By - ENG
291238e6-3d02-5ec2-b9a8-ab81fb7023ca | signoff | AUTHORITY HOLDPOINT
918a1145-c5ce-509f-bed1-f62ab59e0117 | checkpoint | 6.01.06 - As-Builts
db708295-8b31-57be-bec5-77dab4401720 | note | Acceptance / Conformance Criteria - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
a24bef18-ed19-5402-9911-8d0aa41611d7 | note | Standard / Specification - PS 15.11.7
44a3c1ca-2b3c-5bd8-bcd9-8166bc6a932f | note | Verifying Document - Survey Records
b240b2d4-ab96-5982-84a2-2fd25825db00 | note | Frequency - During Earthworks
f0563e63-58d2-5281-99f2-223329a109a7 | note | Verification Activity: Activity - D
0379ef52-f0a4-5de8-b838-16ad532332f7 | note | Verification Activity: By - SV
44d1c624-06c3-5e22-b6df-9c6af47c6102 | section | 6.02 Cutting and Subgrade
e2056d42-43d7-5262-8e7d-f3a1023524d6 | checkpoint | 6.02.01 - Cut slope inspections
f0c9e4d3-35fc-5484-b867-873378bcdcc6 | note | Acceptance / Conformance Criteria - Cut slope inspections will be required to allow inspection of the soils exposed and check for seepages. Inspection records are to include photographs, logged soils (to NZ Geotechnical Guidelines) and hand shear vane testing on fine grained soils. Results will be submitted to the Engineer.
a5050965-657c-5cb4-ba54-29f7a81a36c0 | note | Standard / Specification - PS 15.10.2, PS 15.13
0ca6644d-27bc-50cb-82c3-e9215beabdf8 | note | Verifying Document - Engineers Approval
ee095220-c54a-544f-8c85-d2e244c4a0fd | note | Frequency - Each Occurrence
6854b9e5-08d8-53bf-b4c4-25cc08b491a4 | note | Verification Activity: Activity - HP
3b8c7bd6-7173-5f1c-9873-a15adf5e3876 | note | Verification Activity: By - ENG
e91cf135-5c98-52a7-a54a-3c6af3be7601 | signoff | AUTHORITY HOLDPOINT
d2fbe478-ad1f-5048-8657-8f4e357aec4a | checkpoint | 6.02.02 - Dewatering
45ad7851-3863-514c-bd5d-d0013775f8f7 | note | Acceptance / Conformance Criteria - Trenches and excavations shall be dry at all times during construction works and a constant water level is to be maintained at 300mm below the base of the trench. No construction works may occur if there is any water in an excavation.
10bf3c53-35d3-54c6-aa6d-417ba63dc5da | note | Standard / Specification - PS 15.10.18
fbd2f8c6-64ab-5c47-af05-cb3418296a2c | note | Verifying Document - Site Records
bc3137ea-86db-5fc7-b231-fea3db637513 | note | Frequency - Ongoing
f642d9fb-44aa-5900-a964-19c664e82209 | note | Verification Activity: Activity - S
83904629-984d-510e-b1a8-050717dedc6a | note | Verification Activity: By - SE
0478f66f-1630-5596-ad8d-f38a4cc2b1c9 | checkpoint | 6.02.03 - Subgrade CBR Testing (Road and Embankment)
f3d10b4e-addd-5538-a957-2a37e0034faf | note | Acceptance / Conformance Criteria - The subgrade shall be tested for CBR via Shear Vane or Scala depending on site conditions. Testing to be undertaken to maximum 3m depth at 0.5m interval with hand auger holes required for test deeper than 900mm.
2ce0f2e8-1f40-5e35-8e0b-a78fd0b55a7b | note | This test shall be undertaken at the design subgrade level and at a depth of 300mm below the design subgrade level. Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material.
8b65a2ae-cac6-521a-a731-1c5b9ef6ea23 | note | ○ Shear Vane Average minimum su: > 60kpa
4ccae70e-9d5a-53e4-8f6b-a4e00f80f67e | note | ○ Shear Vane Single test minimum su: > 50kpa
3ff01897-8d7b-537a-9e0a-bdedcefe185a | note | ○ SCALA: Minimum 3 blows per 100mm penetration
630d469c-d4b6-528c-8e3d-4302c9510b53 | note | Standard / Specification - PS 15.10.4, PS 15.10.5 Appendix XIII
0c3bb1ce-aaf0-5272-9b8f-4d902e6bbc45 | note | Verifying Document - Shear Vane or Scala Report
85d3bae8-7bf8-56b3-9602-213fb78a5576 | note | Frequency - 4 test per 400M2
55a69f30-35b2-5c05-9282-92604524f101 | note | Verification Activity: Activity - I
8a1bfe00-8ce7-590a-a5cb-d9ae236fa6a6 | note | Verification Activity: By - SE
55b576e1-21ed-531a-aacd-d94250dc6129 | checkpoint | 6.02.04 - Undercut Subgrade Compaction
f841e758-4cd2-5891-b08c-751a3c88b535 | note | Acceptance / Conformance Criteria - The degree of compaction of each layer shall be such that when trimmed to a smooth surface, the resultant impression in the surface under a smooth wheel roller having a minimum loading of 6259kg per metre width of fill or equivalent as agreed by the Engineer, shall not be greater than 7 mm for bulk fill or 5mm for subgrade fill.
8fb02c88-5c79-5b58-a1dd-92a07552b833 | note | Standard / Specification - PS 15.10.4
a629293c-385f-5bce-b059-933f4c7d43dd | note | Verifying Document - Site Records
2a96cae7-3c6a-51cb-9454-6091224f2d6f | note | Frequency - Prior to Backfilling
4ff321f5-d0cb-5131-9bac-f2447b9cd5d8 | note | Verification Activity: Activity - S
9afabe93-cf7b-5ea2-9907-09925e3a24f2 | note | Verification Activity: By - SE
9bb70f82-94b7-566d-9ef1-4b61c37556a1 | checkpoint | 6.02.05 - Soft Road Subgrade Areas
6fd65fab-6193-5462-afeb-d69af1a8db96 | note | Acceptance / Conformance Criteria - Any soft area observed during rolling of the subgrade shall be referred to the Engineer.
d76e99d9-c656-55e3-acb1-1c1df46f6945 | note | Standard / Specification - PS 15.10.4
1be23212-e8df-5d9f-8313-9a5254ebe069 | note | Verifying Document - Notice
1c0d6418-f406-5f50-950c-5444425f50bf | note | Frequency - When Encountered
34656019-18b2-5fea-94d4-d598e2a8138a | note | Verification Activity: Activity - S
c035f040-40a1-576d-b193-c59e6a453dad | note | Verification Activity: By - SE
c3b7c71e-cfaa-5a96-a625-454bb0cc64fa | checkpoint | 6.02.07 - Finished Surfaces
9bec837e-b683-55ad-bd75-4a248c626262 | note | Acceptance / Conformance Criteria - The works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for Subgrade is 0 to -30mm before placing aggregate layers.
a6991efb-ab9a-5b99-bf23-cb2f8b77c50b | note | Standard / Specification - PS 15.6.8
be65fa83-a107-5342-9c6d-a54c8b435c69 | note | Verifying Document - Survey Records
887ad7d3-09f0-5edf-a3ba-45e2f89d1d67 | note | Frequency - Each Finished Surface
157d7177-0edf-5110-9131-f02c3d9f1433 | note | Verification Activity: Activity - D
1fe43a96-441d-52f3-9c61-b1ddff480ba2 | note | Verification Activity: By - SV
9149e6ff-1de8-5094-9b9f-ead6fee4ce61 | checkpoint | 6.02.08 - Subgrade Proof Roll and Foundation Inspection (Road and Embankment)
b64008e4-8e18-5171-b4ca-a72a0d91c282 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect the Foundation surface prior to Filling during the Proof Roll. No filling shall be undertaken until an inspection has been made and the Engineer has approved the cut and stripping of unsuitable materials. Visual Observation Across The Stripped Area Displacement < 15mm.
677d8b3a-9fe5-5e7f-9e11-0862609e0580 | note | Standard / Specification - Appendix XIII PS 15.13, PS 15.10.5
9841c2a6-be7e-500d-bcca-506f57b64c31 | note | Verifying Document - Engineers Approval
4e231911-13ab-5ecd-9b53-75b332d5bfb0 | note | Frequency - Prior to filling with 24h notice
c10bf413-07c4-5174-9e14-7c2fbcd9358d | note | Verification Activity: Activity - HP
950b4e24-66ad-5e1f-946a-4eebbe8609ed | note | Verification Activity: By - ENG
f05195d4-07ae-5bad-820d-5d958fa1f023 | signoff | AUTHORITY HOLDPOINT
cbfd5119-9511-5f05-a1a3-eb568e57c7a2 | section | 6.03 Filling General
6da130e7-ec1a-5eb6-b735-c0a7919ee1b0 | checkpoint | 6.03.01 - Compaction Trials
082af659-e5a1-5e55-bb14-86dcfa2c12cc | note | Acceptance / Conformance Criteria - The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (i.e. construction discs and scarifiers). The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements. The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial.
b932f253-0659-5483-8431-149e22a51f34 | note | Standard / Specification - PS 15.10.15
0ff16a2c-7e89-5fe7-97b9-0d0dc811e560 | note | Verifying Document - Trial Results
5fa74afb-d11f-58b9-9267-b51498af3937 | note | Frequency - During Works before placement of each material.
103d17fd-0df9-56e9-949a-dda4690eb715 | note | Verification Activity: Activity - R
66efe4f8-ef07-5b70-852c-a42dccaab6c1 | note | Verification Activity: By - PE
e6b0ff49-10c9-5967-b663-f2fc4e147aa3 | checkpoint | 6.03.04 - Geotextile on Undercut to Waste and Backfill
b66a3f7f-c101-55fc-a488-65023d32f225 | note | Acceptance / Conformance Criteria - Geotextile shall be laid across the undercut base and the sides and joints shall be overlapped to in accordance with the manufacturers specification to prevent squeezing of the underlying foundation.
39fe306a-53bb-58ff-84b4-d25744279b95 | note | Standard / Specification - PS 15.10.9
2215bfc9-484e-5f67-adce-6df3c540172a | note | Verifying Document - Site Records
2d33a3f7-a446-54bb-a02a-dbae2920cdbb | note | Frequency - Prior to Backfilling undercuts
8477f682-7f40-53b2-9c76-46de57fde771 | note | Verification Activity: Activity - R
f661c483-12d8-5268-8d41-625af8658963 | note | Verification Activity: By - SE
29370bd4-2ff3-5032-ac70-4629fb46ed01 | checkpoint | 6.03.06 - Weaving or Pumping
bd1991d0-5093-5804-aff8-c52b44e7385d | note | Acceptance / Conformance Criteria - Any weaving or pumping of the soil or subgrade during the compaction process is likely to indicate that either the water content is excessive or the material has been over-compacted. If weaving or pumping is observed, the Engineer should be contacted to advise the appropriate solution.
e605ba42-46c5-5a4e-888c-2477e598e0b8 | note | Standard / Specification - PS 15.10.16
d39f9c2c-ed77-5b28-9068-8d5502076351 | note | Verifying Document - Site Records
68e095e6-4a9f-530e-83a7-48b3803bce4c | note | Frequency - When encountered
27e7c1ea-82b6-5046-a56c-510159c3d998 | note | Verification Activity: Activity - S
ed838f5a-7bf1-5227-8006-76b8f7af37f3 | note | Verification Activity: By - SE
8121b3c2-5c62-5f8a-95d7-1511aca62833 | checkpoint | 6.03.07 - Finished Surfaces
3070b6ed-33d2-59d9-86fa-a87d75982015 | note | Acceptance / Conformance Criteria - The proposed works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for earthworks construction purposes shall be level +/25mm unless stated otherwise, Subgrade; 0 to -30mm before placing aggregate layers, Bulk fill ±100mm, Preload and surcharge ±100mm, Batter slope tolerance ±100mm
3c16fa38-3eaf-5ad1-9f22-07ba1a84a45f | note | Standard / Specification - PS 15.6.8
816b2da5-1e05-56ee-b0d4-f4dad76d85e7 | note | Verifying Document - Survey Records
41c5a73c-3d7a-5d08-99a6-a6c30a41296c | note | Frequency - Each Finished Surface
d8403246-e1a7-5f1e-a63f-c616a6f86317 | note | Verification Activity: Activity - D
6183135d-77a3-5020-94fc-7c8fb634a0f3 | note | Verification Activity: By - SV
28941e1a-7c86-5b6c-b4be-2bd9aa06435c | checkpoint | 6.03.08 - Final Trimmed Shape Inspection
929f9aa7-dcab-55ef-848e-e713dd5186b9 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect final trimmed shape prior to placing topsoil or track rolled fill.
a0d0e862-2504-55af-b439-f3f7356c1fcf | note | Standard / Specification - PS 15.13
51f6149e-c97b-5a09-af39-5267730b4dd8 | note | Verifying Document - Engineers Approval
1d64599f-c05f-5017-bfc2-421633c38bf0 | note | Frequency - Prior to placing topsoil or track rolled fill.
ec8638c9-6512-5db2-95d2-d6d3f35119b8 | note | Verification Activity: Activity - HP
72c74c91-2072-5a09-8013-ca846e10480a | note | Verification Activity: By - ENG
2fa4e556-dcd6-5d59-898c-5d69fcba5b07 | signoff | AUTHORITY HOLDPOINT
9009fa4f-63e9-5b9f-b8f5-3feccfd591cc | section | 6.04 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
25dd2c92-e278-54c8-aa60-59679d5bfb86 | checkpoint | 6.04.01 - Imported Structural Fill Layers
6878fdaf-0bcd-5db1-a513-1fc0df376bbf | note | Acceptance / Conformance Criteria - The material shall be placed and compacted in layers no greater than 300mm thick.
8b06cea0-2762-5a10-b343-8660f98e0189 | note | Standard / Specification - PS 15.10.14
1a89ef0a-9801-51bc-aee0-85e181a5627d | note | Verifying Document - Site Records
30797fec-d05d-5e1d-9407-2ca3ce812dbc | note | Frequency - Each Layer
e9f5e8d3-b7f2-5398-be87-1d5e695a0fb9 | note | Verification Activity: Activity - R
d72c325b-87d7-5b7a-abca-566cc22d1211 | note | Verification Activity: By - SE
7d79ea5d-74fb-5020-a7fc-15bc0d20fe88 | checkpoint | 6.04.03 - Structural Fill Zone - Strength – Clegg Impact Value (CIV)
33972346-eaf4-5b1b-adab-39ff4c57e4e4 | note | Acceptance / Conformance Criteria - A1 Imported Structural Fill Strength shall be tested by Clegg Hammer every 200m3 per area per day per lift
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Minimum CIV = 18
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Average CIV= 20
b21d6bc2-fa63-5bc1-8d96-b05121b299af | note | Standard / Specification - Appendix XIII
9e78cce7-cd0a-5ffe-b4f7-52f1a5f40ad1 | note | Verifying Document - Clegg Results
edfa4ec3-1fcc-5df9-ba9c-81716eabe644 | note | Frequency - 1 Set (5 Tests – 5x5m Square Grid) Per 200m3 Of Placed Per Area Worked Of Day Per Lift
c952f64f-f2ef-5aeb-b6b7-5b247ddc0cdb | note | Verification Activity: Activity - I
e91737f2-9daa-590c-ba83-c4825556312f | note | Verification Activity: By - SE
cff2e2af-607b-551c-bbeb-3ae8301207cb | note | Comments / Closeout Details - Are both NDMs and Clegg Required
e7febe44-92c4-5796-b0f2-b82320d4484e | checkpoint | 6.04.05 - Structural Fill Zone Insitu Density Insitu Compacted Dry Density Insitu Water Content
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - A1 Structural Fill Compaction shall be tested by NDM in Backscatter Mode every 200m3 per area per day per lift
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | ○ Average >95% Of In-Situ MDD
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | ○ Minimum >92% Of In-Situ MDD
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Standard / Specification - Appendix XIII
69d85f65-b61d-579d-940f-2b691894d755 | note | Verifying Document - NDM Results
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
e2147c12-4568-5322-b418-283ae63070af | note | Verification Activity: Activity - I
09a8aad4-3fc9-597d-b419-c865f36b4acc | note | Verification Activity: By - SE
e446d0a3-f492-586c-ab52-5751ac56d10a | note | Comments / Closeout Details - Are both NDMs and Clegg Required
b9a8462b-715b-5c2d-8c25-e4f73254a4ca | checkpoint | 6.04.06 - Solid Density
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - The Solid Density Of Aggregate Particles shall be tested by collecting 1 sample with every set of NDMS completed (1 Test Per 200m3 For That Material Type And Source). Test Results Provide Input To Acceptance Criteria For Insitu Compacted Dry Density Determined By Nuclear Moisture Density Gauge (NDM)
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - Appendix XIII
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Solid Density Lab Report
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - 1 Set (5 Tests) Per Material Type And Source Then 1 Test Per 200m3 For That Material Type And Source
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
5ec91113-ac87-53de-b900-bcb9253aa488 | note | Comments / Closeout Details - Are both NDMs and Clegg Required
504915a0-29d1-5b8a-891c-a7b613638c3c | checkpoint | 6.04.07 - Organic Content
f09d0ff0-01ec-50cb-9988-3a078371cb3d | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
5d4c6d19-d8fb-5765-9b80-10ed32dbffe9 | note | Standard / Specification - Appendix XIII
ea12d870-db9e-5048-94de-56f316678975 | note | Verifying Document - Site Records
4b4f2a35-1e50-5341-80c6-541a73664b53 | note | Frequency - Ongoing
f77c9bbc-fb8f-5e0f-86c9-c66a4643254e | note | Verification Activity: Activity - I
dbb35f07-7f2f-5414-a8b4-c69adbcef37c | note | Verification Activity: By - SE
f910ed7f-8370-57c8-b1bd-2fb721606286 | checkpoint | 6.04.08 - Completed Fill Approval
cb670aff-3430-5d2c-ac3e-1482548f09ee | note | Acceptance / Conformance Criteria - Prior to pavement construction the Engineer shall complete a Desktop review of all structural fill compaction testing for acceptance.
e3ea5880-55a7-54a4-9ee9-9323b972ab79 | note | Standard / Specification - PS 15.13
eb4e4dcc-9679-50a0-8275-a70670f63fd0 | note | Verifying Document - Engineer Approval
5b1465a0-9c5b-51b0-8b4b-9694e85f2324 | note | Frequency - Prior to Pavement Construction
a3b40c94-fe59-5b33-bcda-878d287d2995 | note | Verification Activity: Activity - HP
696e1611-579b-5ae6-b3d8-5701063db1b8 | note | Verification Activity: By - ENG
5e0c2555-3e93-5160-beb9-af9efce873aa | signoff | AUTHORITY HOLDPOINT
faf4f3a3-1299-5382-bb2c-73748ed0cb2e | section | 6.05 LANDSCAPE FILL
a57c22bd-882b-5e15-98f1-6cc1024a010c | checkpoint | 6.05.01 - Cohesive Fill Layers
c352122b-b969-515a-bd14-4ee2d6d77a2c | note | Acceptance / Conformance Criteria - Cohesive structural and non-structural fill material, shall generally be compacted in layers of less than 200mm thickness. All fill surfaces shall be sealed at the end of each day’s work with rubber tyre plant to reduce erosion and protect the fill.
eb2c9836-d46b-5735-a171-5b7c260a8373 | note | Standard / Specification - PS 15.10.16
16c87f21-2b6f-5a9e-950f-ce52726911a4 | note | Verifying Document - Site Records
f997564b-0a06-59cc-aaf8-0d04c169bb65 | note | Frequency - Each Layer
48daa9bc-dbe2-5457-aa35-ebb3d2f05eee | note | Verification Activity: Activity - R
a63751f3-0140-5d7c-80c1-864752f123ce | note | Verification Activity: By - SE
e9f6dd3e-48b2-53bf-8c70-05c59c2b86d9 | checkpoint | 6.05.03 - Non-Structural Fill - Air Voids
8e28b866-fa38-519b-918f-3d14bb22ecfb | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill compaction (Air Voids) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift.
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Average Maximum Air Voids < 8%
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Single Test Maximum Air Voids< 10%
b6a6dfee-f164-5998-9bdb-0af48b5f824e | note | Standard / Specification - Appendix XIII
bebdea1e-dece-5fe9-9b48-a107125b16b9 | note | Verifying Document - NDM Results
e003f7a2-352b-5d80-9fd5-e44eddfe06fe | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
3f5e0ef0-3697-5f92-8b8c-ec24df3f2e89 | note | Verification Activity: Activity - R
da65e1bd-770b-59ad-9793-ebeab9e626dd | note | Verification Activity: By - SE
cf7abc67-8aed-5d00-ac3a-cbae29efad1b | checkpoint | 6.05.04 - Non-structural fill Zone Strength – Shear Strength (SU)
8a655586-34a5-5a18-aef6-d6c0c46b2eca | note | Acceptance / Conformance Criteria - A2 Cohesive Non-Structural Fill Strength shall be tested by hand held Shear Vane or Scala every 500m3 per area per day per lift of fill placed.
c7bdbe91-5ef1-591f-a7d8-c0e38c48b32f | note | ○ Average Minimum Su > 60kPa
73c7904a-13cc-5564-872e-5dd2ec0ff2cf | note | ○ Single Test Minimum Su > 50kPa
6d410085-df0f-5e4e-aba8-430c7c78ff17 | note | ○ Scala: Minimum 2 Blow Per 100mm
1fb5184e-2a61-5ac4-9704-8af92d7bb87c | note | Standard / Specification - Appendix XIII
10e1325c-804d-5162-810d-a48453df0e42 | note | Verifying Document - Shear Vane or Scala Results
37a82803-7835-5700-8489-5432f89e46a3 | note | Frequency - 1 Set (5 Test) Per 500m3 Of Fill Placed Per Area Worked Per Day Per Lift
338c0f69-5352-5f07-a019-adfc9ad24162 | note | Verification Activity: Activity - I
6aa5aee6-bbbc-5074-9145-e9071c21bc5a | note | Verification Activity: By - SE
67d2cb19-a2ab-56fe-9362-2a11a6148fa9 | checkpoint | 6.05.05 - Non-Structural Fill - MDD
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - Non-Cohesive Non-Structural Fill compaction (Dry Density) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift. 90% Minimum Dry Density (MDD).
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | Standard / Specification - Appendix XIII
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | Verifying Document - NDM Results
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
69d85f65-b61d-579d-940f-2b691894d755 | note | Verification Activity: Activity - I
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Verification Activity: By - SE
940c74e2-d6b4-59ce-a549-e065a128c6e6 | checkpoint | 6.05.06 - Non-Structural Fill - Granular Mixed Materials
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - Mixed non-structural material requires proof roll to ensure compliance with the 7mm requirement. Proof roll to be done where soils cannot be penetrated via shear vanes or scala
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - TNZ F1 Section 10.5.1
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Site Records
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - Formation level
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
c83c1a95-6cc3-5b55-ac8c-57dd36cf1a2e | checkpoint | 6.05.07 - Organic Content
8e7ab7fa-96cb-549a-9853-95660876e381 | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
8198a028-f5d8-5206-b061-611b85274fdd | note | Standard / Specification - Appendix XIII
952eeb47-9e0c-50f4-864e-51dc8f1168e6 | note | Verifying Document - Site Records
e0771c83-af76-5822-8faf-087df801ca3e | note | Frequency - Ongoing
d1b036db-e4f5-5709-84c8-a981882122fa | note | Verification Activity: Activity - I
c2527edb-afb6-51e1-9d14-580ba94c551a | note | Verification Activity: By - SE
8a6e4423-2a66-5b93-af2a-67e156f07a85 | checkpoint | 6.05.08 - Water content
cb670aff-3430-5d2c-ac3e-1482548f09ee | note | Acceptance / Conformance Criteria - The water content shall be tested by collecting 1 sample with every individual NDM test.
e3ea5880-55a7-54a4-9ee9-9323b972ab79 | note | Standard / Specification - Appendix XIII
eb4e4dcc-9679-50a0-8275-a70670f63fd0 | note | Verifying Document - Water Report
5b1465a0-9c5b-51b0-8b4b-9694e85f2324 | note | Frequency - Every NDM
a3b40c94-fe59-5b33-bcda-878d287d2995 | note | Verification Activity: Activity - I
696e1611-579b-5ae6-b3d8-5701063db1b8 | note | Verification Activity: By - SE
94ecb72f-b511-5fef-99c9-b75caaae5292 | checkpoint | 6.05.09 - Bulk Density, Dry Density, Air Voids
5257c877-8603-5fa7-ae79-94eb9ad4ab20 | note | Acceptance / Conformance Criteria - The Bulk Density, Dry Density, Air Voids shall be tested by collecting 1 sample (Sample Tube) for every 10 NDM Sets completed.
2fe2c019-2b72-552f-a304-756bdc1f6860 | note | Standard / Specification - Appendix XIII
369e10f0-7e1b-5d5e-aa82-dcc934fc71fc | note | Verifying Document - Lab Report
d73d03d0-a4f9-5979-a6e3-170237792f12 | note | Frequency - 1 Test Performed For Every 10 NDM Test Results Provide
c22d180e-106e-518e-ab92-606ab548f934 | note | Verification Activity: Activity - I
e7a22350-c145-569f-b04c-38482bc1bfa7 | note | Verification Activity: By - SE
a3350b27-5c47-5b3b-ab57-f9e96424a1da | section | 6.06 Settlement Monitoring
5e695847-04f1-541c-9e60-5f3ce9021c7d | checkpoint | 6.06.01 - Settlement Monitoring Methodology
55cd879c-55fc-5cf6-ac3c-be63cb59295d | note | Acceptance / Conformance Criteria - The Contractor shall submit details of their proposed monitoring equipment and installation methodology within their Earthworks Management Plan for the Engineer’s Approval.
e81a1f0f-e781-525e-8c33-4e23315d1115 | note | Standard / Specification - PS 15.12.5
3d5ed6b8-8e4c-545a-9b90-7b60919dd913 | note | Verifying Document - Approved EMP
ef9455b2-30f0-545d-a18d-d1e03ec6a2d5 | note | Frequency - Prior to Works
bbd43815-e554-5e0c-8e5b-3ca67662ee30 | note | Verification Activity: Activity - HP
258d068c-dd4d-5efc-a8bb-531c5d1e9410 | note | Verification Activity: By - ENG
5d1819d4-2a89-5c6a-acb4-52c8ae9493b0 | signoff | AUTHORITY HOLDPOINT
1309e638-c7ad-5317-82c8-377f0218a22a | checkpoint | 6.06.02 - Supply, Install, Survey and Remove and Monitoring Equipment
f3fece7f-2a75-51d9-ab8c-3818abf85f3f | note | Acceptance / Conformance Criteria - The Contractor shall install geotechnical instrument systems in the positions shown in the Contract Drawings unless otherwise instructed by the Engineer.
f5b4da39-18a7-50fa-81bb-119512aa3245 | note | Standard / Specification - PS 15.12
f2f8a813-1fd2-5f2e-8fb2-868eac6068eb | note | Verifying Document - Site Records
51df963b-9897-5abb-94e9-92f9a247955d | note | Frequency - Prior to Construction
68391c45-455a-5051-9344-65d8f1c811eb | note | Verification Activity: Activity - I
160f22c6-6304-5fea-b1ab-230125cb63ef | note | Verification Activity: By - SV
0f533e6c-1bd1-57a4-a4c0-c28f362a9a0c | checkpoint | 6.06.03 - Instrument Reading Notice
6f87da36-7041-5714-aab1-a9d1a3d4eb69 | note | Acceptance / Conformance Criteria - The Contractor shall inform the Engineer two days in advance of planned instrument readings so that the Engineer may observe the work.
e3bc3f60-11df-5986-8e49-8f95bf3b526c | note | Standard / Specification - PS 15.12.5
d1a19be7-e1d3-5547-8909-138345432d0b | note | Verifying Document - Site Records
1f9dbbe2-04ff-5485-ae11-50ba7690ec6a | note | Frequency - Prior to Survey
fe3add51-08eb-5bf7-8e2f-9257106320fe | note | Verification Activity: Activity - HP
78d1467f-a870-5168-8aca-e0fc839d8ecc | note | Verification Activity: By - ENG
f2f84277-75de-5c7e-be35-eeeb68a3e8a9 | signoff | AUTHORITY HOLDPOINT
2517047e-845e-5644-ae2e-510b4502a782 | checkpoint | 6.06.04 - Base Readings, Responsibility and Ownership
26de447a-be80-5db7-9fed-a5598df339e2 | note | Acceptance / Conformance Criteria - Following installation, the Contractor shall undertake testing to demonstrate the instruments are working properly. The Contractor shall submit records of each of the instruments showing location, soil conditions encountered, installation details and initial readings. Construction will not be permitted until the Engineer is satisfied that the instruments are working correctly.
3dac7c57-2fd9-5583-b22e-1c9daad809d8 | note | Standard / Specification - PS 15.12.2
57fbadc8-856e-59ea-9c0b-6a4ad79abd98 | note | Verifying Document - Site Records
887d2697-0438-5748-9d92-50071d9dcfaf | note | Frequency - Prior to Construction
172ad8cb-f559-5105-bb7d-9fce0c280ca5 | note | Verification Activity: Activity - HP
e13218bd-7f4d-5ce9-9578-5fc34d2a157d | note | Verification Activity: By - ENG
b68c1eb5-b89f-5102-ab04-0d343f0c2bc8 | signoff | AUTHORITY HOLDPOINT
012ae06c-51f7-539e-99db-22dc8857a1af | checkpoint | 6.06.05 - Pin Protection
05377e32-4d4d-5ac9-85e7-88b011824a6c | note | Acceptance / Conformance Criteria - The Contractor shall ensure the Pins are protected and not disturbed in any way once constructed. The Contractor shall also install settlement survey stations at locations protected from Construction traffic and works.
5d18b3db-6402-5696-83e5-db181b003227 | note | Standard / Specification - PS 15.12.5
05cd1b8f-838a-5ded-9ab1-8a0bccdc8b88 | note | Verifying Document - Site Records
89614663-9ee1-5f54-80d8-09f62996a296 | note | Frequency - Ongoing
96cac559-a2d0-5e18-bd1c-8c5f91f83364 | note | Verification Activity: Activity - R
3f8e7bef-6f86-5244-b41d-7c1991bd3106 | note | Verification Activity: By - PE
d71f530d-3a2d-502a-85c4-0e6cfd071bfd | checkpoint | 6.06.06 - Monitoring
1d838e30-c9ec-58bc-8841-43d057802429 | note | Acceptance / Conformance Criteria - Following the active fill of the embankment, the Contractor shall read all monitoring pins bi weekly. Monitoring frequency may be reduced to weekly intervals when there is no active earthworks in that area, and while waiting for embankment to settle.
ab916766-b8ca-5614-a3be-61f3ef5ce0a5 | note | Standard / Specification - PS 15.12.5
5a8987e1-beb5-5285-9626-14c6d4b752e3 | note | Verifying Document - Survey Records
6fa587b6-07fd-53aa-b98e-c9e5af40fc7a | note | Frequency - Bi Weekly following Embankment Filling
a7929d20-4291-5176-920f-7926ba3c34af | note | Verification Activity: Activity - R
c2010ee4-fd12-508a-ae38-dccfae200836 | note | Verification Activity: By - SV
a623e6c5-b632-5bb4-bb24-cba69e701574 | checkpoint | 6.06.07 - Engineers Review
d77b11fc-070b-50e1-8629-958659ff4f44 | note | Acceptance / Conformance Criteria - The Engineer will review the results of the settlement monitoring to assess completion of the preconsolidation period. This period is anticipated to be less than 3 months.
cf3d110b-7081-5043-99cf-c1c5e1e82116 | note | Standard / Specification - PS 15.12.5
88313476-05c6-574c-be37-84b542b7c1ff | note | Verifying Document - Survey Records
aba9f8b6-25d1-5e33-9124-ff7cef034c4a | note | Frequency - Ongoing
53867a85-e95a-5618-87e7-f9eec85edf34 | note | Verification Activity: Activity - R
49b6db7c-780d-5c5a-b85b-ffd17e3d8432 | note | Verification Activity: By - SV
c0a27a5d-8b1f-50f5-b01d-a262601e207d | checkpoint | 6.06.08 - Pore Water Dissipation
75ceb013-f0cb-5b7e-af80-af6640b2d53d | note | Acceptance / Conformance Criteria - Review of settlement pins data to confirm sufficient pore water dissipation has occurred in the soft soil layer.
1e5ba5db-1e50-52e5-a141-a55015b8ec11 | note | Standard / Specification - PS 15.13
6d539e72-2e15-54ff-a874-531eefc30c8a | note | Verifying Document - Engineers Approval
bde27891-0f79-54b4-bce1-6e40158e43bd | note | Frequency - Prior to completing Monitoring
1f4973ca-c9c2-5289-b401-f542f7e282e3 | note | Verification Activity: Activity - HP
c3e2a4d3-85b0-50f8-aab3-5c691c2e24f6 | note | Verification Activity: By - ENG
2e34f781-af18-50d3-a840-a001fb34c51d | signoff | AUTHORITY HOLDPOINT
89b1bcee-a704-5892-9410-e9311d5e0992 | checkpoint | 6.06.09 - Settlement Monitoring Termination
f89d107c-7f62-5edf-ba7c-a0e330bfb041 | note | Acceptance / Conformance Criteria - The criteria for terminating the embankment preload are either: Three consecutive measurements indicating the t90 settlement value has been achieved, A rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed. The settlement readings shall be evaluated by the Engineer to assess the need to extend the monitoring.
2d0e1d42-bc4c-5ffc-a6ec-30a5d4d6670d | note | Standard / Specification - PS 15.12.7, PS 15.13
95432c0f-587e-557b-a06a-d2c1de6b3656 | note | Verifying Document - Engineers Approval
e1dd00fe-0aed-5bbc-9759-328a6cb6ca36 | note | Frequency - Prior to completing Monitoring
f1a09b53-7a5d-50a9-8933-50232be4a599 | note | Verification Activity: Activity - HP
adfba00d-f5d8-5f2d-a739-d023b0e4a01c | note | Verification Activity: By - ENG
de792686-1074-5b19-8609-1cce7f903454 | signoff | AUTHORITY HOLDPOINT
b28d4a9e-b7eb-4ad3-8001-1ddfdd89fb24 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
4e1802e6-4c8b-5a6c-8586-cdab8da021eb | textbox | Contractor's Rep Name:
890e5832-c342-5d4a-8e46-36364f3d6f9d | textbox | Engineer's Rep. Name:
e1aa43d4-df34-5b10-b422-99007969a4ff | date | Date:
9d278f96-54f2-4e0b-b7f9-edd2cb9dd539 | signoff | Add Signature
2b145170-2aa6-5494-aa28-972981668d1b | checklist | Ω (DEPRECATED) ITP - Earthworks - 101 - Rev 2 - v1 | itp | ITP - Earthworks - 101 - Rev 2
ac5ee1ee-5139-57b0-9c55-3196b7da263c | section | 3.01 General
4b182364-c9b8-5807-85b4-26cb6c506fc7 | checkpoint | 3.01.01 - Precondition Surveys
69cd2420-d366-54eb-958b-47ee6ba30c3b | note | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
8a300e3e-8b0d-50e1-92a8-acacc9470272 | note | Standard / Specification - PS 2.13
4012ae1e-5742-5bb3-bd88-9891dd0da569 | note | Verifying Document - Precondition Survey
5ee54bf7-4881-50be-9cbd-b6ca24fbed29 | note | Frequency - Prior to the Contractor taking possession of the Site.
4ee5ad50-8a49-5ef9-b2ce-6829404da63e | note | Verification Activity: Activity - H
042a86d8-9388-5bf2-bc39-fae98a19ea53 | note | Verification Activity: By - PM
2c4b8fd4-5150-5656-bda8-48bbc0f299cc | section | 4.01 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
eec51e33-e195-5fd4-8848-2a84896576bc | checkpoint | 4.01.01 - Source Property Tests and Sampling
c970b435-1a5a-5b52-9c63-6d3dc47a7b24 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, Los Angeles Abrasion, and Soaked CBR at least 2 weeks prior to importing to the site.
5fddf01b-636b-5c1b-9e0f-f9d479c784a9 | note | Standard / Specification - PS 15.7.3 Appendix XIII
c05f86e5-078b-56d0-a84d-743d12ed7c80 | note | Verifying Document - IANZ Lab Reports
0d61936a-619a-5486-b002-fd3bb8ecd191 | note | Frequency - 2 Test Per Material Per Source at least 2 weeks prior to importing to the site.
6c36e154-7375-5049-8d17-38c7ea3fb8aa | note | Verification Activity: Activity - HP
3ce79e68-2cd7-57fc-8b23-187278275664 | note | Verification Activity: By - ENG
943c57a3-9718-5eec-a0c4-4f254ca57b92 | signoff | AUTHORITY HOLDPOINT
e74ba8eb-c7ac-51ca-806d-ce6b2d151d6f | checkpoint | 4.01.02 - Testing for Layer Compaction - MDD
0eea5d39-c7a9-597e-95e8-2d3aa0eb79ce | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Heavy Compaction), Optimum Water Content, Air Voids, and Shear Vane Strength (Su) with Range of Moisture Contents.
3a7cfff1-f254-5419-911c-e86cf81791ad | note | Standard / Specification - PS 15.7.3 Appendix XIII PS 15.13
bac60110-709f-58ca-825f-eef1d568b6fe | note | Verifying Document - IANZ Lab Reports
28d0819b-7509-50e5-aaad-6484fe8c56af | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
93ed1431-f321-5f8b-8125-d991cf43a90b | note | Verification Activity: Activity - HP
5eecf011-989a-5420-a82b-eb0149a57904 | note | Verification Activity: By - ENG
2de69587-8bf8-5aa7-bee6-c425de611b49 | note | Comments / Closeout Details - MDD may need to be by Vibrating Hammer depending on Material
1ad45696-b06f-57ba-991f-876ec2469f8a | signoff | AUTHORITY HOLDPOINT
cc28f368-5ec3-56d4-92e5-eeccc9eacb38 | checkpoint | 4.01.03 - Production Property Test Sampling
6c461bdf-e882-525f-a094-2bcc190ce2e7 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD).
4c2ef108-068a-59d0-b3de-60b2a95c6c7f | note | Standard / Specification - PS 15.7.3 Appendix XIII
6a814afb-0be7-53e5-8592-2862e1a765fd | note | Verifying Document - IANZ Lab Reports
efce84d9-b1b2-5d89-991c-9da04e5ba923 | note | Frequency - 0-400 M3 – 2 Tests
f89666dd-0f56-5b39-b7d2-2694b08c1b13 | note | ○ 400-1,500M3 – 3 Tests
ed92ad50-6f20-5df3-bdee-ddfd8f5eb73d | note | ○ 1,500-4,000M3 – 4 Tests
8473fabf-bde7-5cc9-8e93-e31e0d9d300b | note | ○ >4,000M3 - 1 Test For Each Additional 10,000M3
fd98181f-7bd9-5f53-8201-bb0c6813a688 | note | Verification Activity: Activity - H
29935793-de84-5fc9-9e9a-dc726b88856e | note | Verification Activity: By - PE
d3197014-3f06-5fe0-b1d9-aea439b97c54 | section | 4.04 Type A3 (Site Won Landscaping Fill)
bd572b98-794b-572a-b262-0d8895c651db | checkpoint | 4.04.01 - On Site track-able Testing
8fefcbaf-cb68-5917-9433-3d41137b8e4e | note | Acceptance / Conformance Criteria - Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it is ‘track-able’ by the contractor’s plant. This shall be determined before Sampling.
b4914206-8d0b-5414-9502-17ae4fad6e1c | note | Standard / Specification - PS 15.7.3
e51abaca-32b0-57d1-8544-f906b25a9fc0 | note | Verifying Document - Visual Site Record
aaf6e6a1-d9e9-5a27-86da-31e404a8a62d | note | Frequency - Prior to Sampling
d4f5a2c3-8d72-5a12-84a0-52e374ec9d02 | note | Verification Activity: Activity - W
21e39c46-937e-5756-bf3a-0fa20897c108 | note | Verification Activity: By - PE
bbfc5154-bf5f-5edf-b862-ca5b40d3d743 | checkpoint | 4.04.02 - Testing for Layer Compaction - MDD
da4431ef-f91b-5faf-a07f-ebe5b3ed0ce8 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Standard Compaction), Optimum Water Content, and Shear Vane Strength (Su) with Range of Moisture Contents.
75366e9f-f170-5da4-8e90-2ba29431f456 | note | Standard / Specification - PS 15.7.3, PS 15.13
01c254a6-d804-5850-b1b7-daee29774ece | note | Verifying Document - IANZ Lab Reports
cd00113d-ee85-5286-956b-580960ae86ae | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
9895d0dc-5a1e-556b-b3a4-f60bb935b694 | note | Verification Activity: Activity - HP
803e0adb-6908-539d-91c5-5f291f829291 | note | Verification Activity: By - ENG
787da1d7-76e7-5318-90fc-d7c5b66f0772 | signoff | AUTHORITY HOLDPOINT
1b403918-b691-5bde-88b7-f3ee9e087117 | checkpoint | 4.04.03 - Insitu Property Test Sampling
b2e3a0b7-200b-54bc-8753-e33bdade2178 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD) and inspected for deleterious materials such as boulder size fragments and organic materials.
da342694-bd84-565c-b303-933f704abeb3 | note | Standard / Specification - PS 15.7.3
3f8b0f56-e239-5878-82f3-25bd301b0188 | note | Verifying Document - IANZ Lab Reports
54187772-fb0a-5304-b22d-e6fef5571033 | note | Frequency - Prior to use
5f2c876f-b40e-5944-91db-1b5c4f101bfd | note | Verification Activity: Activity - HP
10ebcf48-ad4b-5c4f-ac90-4d24da87969d | note | Verification Activity: By - ENG
f4da45cc-ae32-586a-82a0-8191c8cf5c37 | signoff | AUTHORITY HOLDPOINT
540a5e70-44a2-557d-9a5c-b23f9eba4a3f | section | 4.05 Topsoil
20c79c91-2f0b-5e64-bc79-4fc755ec0ddc | checkpoint | 4.05.01 - Topsoil
c48a7814-415e-5bf0-90db-a1b8443b9fdd | note | Acceptance / Conformance Criteria - Topsoil is defined as the layer of material immediately below the ground surface comprising vegetation, tree roots, other non-decomposed organic matter, turf and humus. The Contractor is to stockpile and utilise site won topsoil for placement on the final batter slopes and for borrow site reinstatement as shown in the Contract Drawings.
e65a11a1-9f5f-5b9b-b31a-005bf9a0f5ad | note | Standard / Specification - PS 15.7.3
cf04a554-dfc6-58b4-9613-62ac16fdabb9 | note | Verifying Document - Site Record
ee11df60-1ce5-585b-8998-69594136d238 | note | Frequency - During Stripping
e137dc49-6b12-5bed-ab75-30d89abce352 | note | Verification Activity: Activity - I
11dd70c8-b8f1-5205-a62a-89a0d37a59b0 | note | Verification Activity: By - SE
d75e34e2-526e-508b-9139-1c41f905aee4 | section | 4.06 Geotextiles
94c5cd81-4c09-5866-a780-a6cb2b294715 | checkpoint | 4.06.01 - Geotextile on Undercut to Waste and Backfill
01a812e1-2a2b-5d7f-a9f9-4d80c94b831d | note | Acceptance / Conformance Criteria - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation.
c17089c8-cde6-5780-af0b-4d44cfe037e4 | note | Standard / Specification - PS 15.10.9
3752352a-df5a-53b2-8094-118f73546c7d | note | Verifying Document - Datasheet
8e7145b3-d717-57d4-8b68-f84837bcbada | note | Frequency - Prior to use
6f3350cc-a5e3-5922-90ec-ceba1cff1e25 | note | Verification Activity: Activity - R
ffc1a14f-5946-57d0-b15d-4eb1e2f5b1a3 | note | Verification Activity: By - SE
00122e61-34f7-53d5-a67f-e0c09f6146f3 | section | 5.01 Site Clearance
aa56f8f4-2f1d-53a7-90e0-bf9bff008cd2 | checkpoint | 5.01.01 - Site Clearance
76735cd9-4858-55a6-aa06-101f02518612 | note | Acceptance / Conformance Criteria - All trees, scrub, non-lawn vegetation and/or self-sown plants within the extent of the earthworks shall be removed to waste in accordance with Clause 3 and Clause 9.4 of TNZ F/1:1997 Specification for Earthworks Construction.
e2b43d2f-4215-5670-89ab-c3b1d39d5dd5 | note | Standard / Specification - PS 14.1.1 NZTA F/1 - 3
f35896e9-18bd-51fb-84bd-a516fea07908 | note | Verifying Document - Site Record
1c9aecd5-6527-5a3f-90f9-fb46fb1152c3 | note | Frequency - Prior to excavation
553d21dc-d656-5d11-a678-49e9091a7776 | note | Verification Activity: Activity - I
b8ac2dc9-f39d-5a4c-88d0-92ffc13d346b | note | Verification Activity: By - SE
0434188f-64e5-5961-b752-f68ed0678033 | checkpoint | 5.01.02 - Dump Site Approval
165908c4-435f-5b36-8fd9-df3fab4ecdd9 | note | Acceptance / Conformance Criteria - The locations of dump areas shall be agreed by the Engineer before use.
e22c6756-65e9-50b5-b8f9-e78161c44d04 | note | Standard / Specification - NZTA F/1 - 9.4
55d5c387-b48b-5e7f-9757-2749a36ece54 | note | Verifying Document - Site Record
f84ff3ba-d111-577e-814d-2f3b3ff0c62e | note | Frequency - Prior to Stockpiling
73737f8f-3ed5-5230-a5fa-7d12fd1ac08c | note | Verification Activity: Activity - HP
74ce0d35-f379-5262-b7f4-46543d42148d | note | Verification Activity: By - ENG
c082bbf0-64bb-5295-803d-efd5e36c07d2 | signoff | AUTHORITY HOLDPOINT
97e973d9-e87b-5abc-b883-a17a57730683 | checkpoint | 5.01.03 - Mulching
7c25105e-22ed-5c83-8240-5f58fa89da29 | note | Acceptance / Conformance Criteria - Where possible, cleared vegetation shall be mulched and stockpiled at a suitable site for future landscaping work.
39aa4f4e-e9d4-5b72-a53a-4a01c43363d6 | note | Standard / Specification - PS 14.1.1
54411dec-bc57-5533-afb7-0f38308d0bf6 | note | Verifying Document - Site Record
d3575c48-3185-5f98-b1fe-4784265e23ac | note | Frequency - During Clearing
449c8392-36d0-5a80-8ce1-30049ce1eaa6 | note | Verification Activity: Activity - R
07fddfa0-d1c0-5767-bf10-aa4ad5673f63 | note | Verification Activity: By - SE
4f7cfdbd-f8a4-5f17-a5dd-b36d0cb99ded | section | 6.01 General Earthworks
7b7266d6-ecf8-561a-b4ca-7b37880265fd | checkpoint | 6.01.01 - Earthworks Methodology
c228e36c-639a-5d64-84a6-17b814e6f41b | note | Acceptance / Conformance Criteria - The Contractor shall submit the construction and QA methodology for each element of Earthworks including construction, Haul roads, Site Access, dewatering, Wet weather, testing, inspection, and hold points for review and approval prior to works.
0b682de4-c8ae-51d1-9923-ecbfc85690dd | note | Standard / Specification - PS 15.13, PS 15.6.2, PS 15.10.13
b50a3242-4781-56d2-9c29-2bfa07bedacd | note | Verifying Document - Approved Methodology
9b77a527-c1c2-52d4-bf08-2baf8fe48a93 | note | Frequency - Prior to Earthworks
00c15935-b738-5367-8878-db856c582b87 | note | Verification Activity: Activity - HP
2e554e60-d952-5dd6-861b-a558370ee856 | note | Verification Activity: By - ENG
326a5f19-66e6-52e8-8259-accb86134d3f | signoff | AUTHORITY HOLDPOINT
ce70eb24-ffd6-534e-9bc3-84ccc496c6db | checkpoint | 6.01.02 - Temporary Excavation Approval
8b4c1814-1483-57a0-a93e-7cf0f5129205 | note | Acceptance / Conformance Criteria - The Contractor shall submit Temporary Excavations details to the engineer for approval prior to excavation.
33ca796d-57e5-58de-b34f-c32e6163735c | note | Standard / Specification - PS 15.13
c6d3b217-5879-5d04-b9ab-a032084546f6 | note | Verifying Document - Engineers Approval
de2c1bd3-ac7a-562d-817a-3f4a0bb05767 | note | Frequency - Prior to Excavation.
cd18a545-923b-5871-b92c-dee9402f4e29 | note | Verification Activity: Activity - HP
b2515f22-7df2-58c2-ac65-fe920a60c040 | note | Verification Activity: By - ENG
7f24d1ae-eaea-5164-a39d-b9602a701e03 | signoff | AUTHORITY HOLDPOINT
7be180f9-b731-51bf-aa2a-2646cc8a1c69 | checkpoint | 6.01.03 - Temporary Works Design
6bf13ae3-7a65-50e5-8ee5-356f37e5f99f | note | Acceptance / Conformance Criteria - The Contractor shall submit the temporary works design for Review and approval of prior to excavation.
34321cd1-593b-53a3-963f-41929191a96b | note | Standard / Specification - PS 15.13
725dbc6f-43b7-58dd-b840-2a9e1cc7a0a5 | note | Verifying Document - Approved Design
e4fec50b-b4eb-5cfa-bc23-b5a1182bdb5c | note | Frequency - Prior to Excavation.
2ac192cb-bf2e-52c2-b62a-50c4c4697492 | note | Verification Activity: Activity - HP
e421222d-e59e-5ba2-9fce-d91b87b2c1cd | note | Verification Activity: By - ENG
bd223daf-c7ae-5c7b-b6da-6f123e740f86 | signoff | AUTHORITY HOLDPOINT
55e3284f-9a58-588c-bbef-d9a461605980 | checkpoint | 6.01.04 - Temporary Stockpiles
baf815d3-1ef3-59b4-94ad-daf49ffc72eb | note | Acceptance / Conformance Criteria - Temporary stockpiles shall not be located within the footprint of the permanent works unless approved by the Engineer.
18b30793-18bf-5c62-9ab2-12c0e2ba5c49 | note | Standard / Specification - PS 15.6.5
cc98758a-ecad-5043-bcc8-3a0f6433d90f | note | Verifying Document - Engineers Approval
58eb1e17-79a1-52e1-b4e4-ff51e4c2a10c | note | Frequency - Prior to stockpiling
08cfbbd5-6e1b-5ca2-872e-ed4df362935a | note | Verification Activity: Activity - HP
8f11b887-eb69-534b-b326-59012efc3a5c | note | Verification Activity: By - ENG
a94c983f-b77c-5257-ba7c-2cf26f751c21 | signoff | AUTHORITY HOLDPOINT
9f916a51-531e-50f9-ab39-015b1c560d11 | checkpoint | 6.01.05 - Surplus Material
02f14ce9-3ef4-562b-b104-58d1241b50c7 | note | Acceptance / Conformance Criteria - Surplus or waste soils may be deposited outside the site boundaries with the written approval of the Engineer.
c85b74b4-9183-55a7-ae2f-345297038e49 | note | Standard / Specification - PS 15.1
ef2e0cf0-e7d5-51ba-8a6d-bbc82bdf9e2f | note | Verifying Document - Engineers Approval
a960256b-958b-5eb6-af8e-bc4d99728fb0 | note | Frequency - Each Occurrence
52fea67b-14ca-5826-8d8a-c11dc3466cf4 | note | Verification Activity: Activity - HP
4b1848f4-9510-5def-95f4-d24b7a6c808e | note | Verification Activity: By - ENG
291238e6-3d02-5ec2-b9a8-ab81fb7023ca | signoff | AUTHORITY HOLDPOINT
918a1145-c5ce-509f-bed1-f62ab59e0117 | checkpoint | 6.01.06 - As-Builts
db708295-8b31-57be-bec5-77dab4401720 | note | Acceptance / Conformance Criteria - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
a24bef18-ed19-5402-9911-8d0aa41611d7 | note | Standard / Specification - PS 15.11.7
44a3c1ca-2b3c-5bd8-bcd9-8166bc6a932f | note | Verifying Document - Survey Records
b240b2d4-ab96-5982-84a2-2fd25825db00 | note | Frequency - During Earthworks
f0563e63-58d2-5281-99f2-223329a109a7 | note | Verification Activity: Activity - D
0379ef52-f0a4-5de8-b838-16ad532332f7 | note | Verification Activity: By - SV
44d1c624-06c3-5e22-b6df-9c6af47c6102 | section | 6.02 Cutting and Subgrade
e2056d42-43d7-5262-8e7d-f3a1023524d6 | checkpoint | 6.02.01 - Cut slope inspections
f0c9e4d3-35fc-5484-b867-873378bcdcc6 | note | Acceptance / Conformance Criteria - Cut slope inspections will be required to allow inspection of the soils exposed and check for seepages. Inspection records are to include photographs, logged soils (to NZ Geotechnical Guidelines) and hand shear vane testing on fine grained soils. Results will be submitted to the Engineer.
a5050965-657c-5cb4-ba54-29f7a81a36c0 | note | Standard / Specification - PS 15.10.2, PS 15.13
0ca6644d-27bc-50cb-82c3-e9215beabdf8 | note | Verifying Document - Engineers Approval
ee095220-c54a-544f-8c85-d2e244c4a0fd | note | Frequency - Each Occurrence
6854b9e5-08d8-53bf-b4c4-25cc08b491a4 | note | Verification Activity: Activity - HP
3b8c7bd6-7173-5f1c-9873-a15adf5e3876 | note | Verification Activity: By - ENG
e91cf135-5c98-52a7-a54a-3c6af3be7601 | signoff | AUTHORITY HOLDPOINT
d2fbe478-ad1f-5048-8657-8f4e357aec4a | checkpoint | 6.02.02 - Dewatering
45ad7851-3863-514c-bd5d-d0013775f8f7 | note | Acceptance / Conformance Criteria - Trenches and excavations shall be dry at all times during construction works and a constant water level is to be maintained at 300mm below the base of the trench. No construction works may occur if there is any water in an excavation.
10bf3c53-35d3-54c6-aa6d-417ba63dc5da | note | Standard / Specification - PS 15.10.18
fbd2f8c6-64ab-5c47-af05-cb3418296a2c | note | Verifying Document - Site Records
bc3137ea-86db-5fc7-b231-fea3db637513 | note | Frequency - Ongoing
f642d9fb-44aa-5900-a964-19c664e82209 | note | Verification Activity: Activity - S
83904629-984d-510e-b1a8-050717dedc6a | note | Verification Activity: By - SE
0478f66f-1630-5596-ad8d-f38a4cc2b1c9 | checkpoint | 6.02.03 - Subgrade CBR Testing (Road and Embankment)
f3d10b4e-addd-5538-a957-2a37e0034faf | note | Acceptance / Conformance Criteria - The subgrade shall be tested for CBR via Shear Vane or Scala depending on site conditions. Testing to be undertaken to maximum 3m depth at 0.5m interval with hand auger holes required for test deeper than 900mm.
2ce0f2e8-1f40-5e35-8e0b-a78fd0b55a7b | note | This test shall be undertaken at the design subgrade level and at a depth of 300mm below the design subgrade level. Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material.
8b65a2ae-cac6-521a-a731-1c5b9ef6ea23 | note | ○ Shear Vane Average minimum su: > 60kpa
4ccae70e-9d5a-53e4-8f6b-a4e00f80f67e | note | ○ Shear Vane Single test minimum su: > 50kpa
3ff01897-8d7b-537a-9e0a-bdedcefe185a | note | ○ SCALA: Minimum 3 blows per 100mm penetration
630d469c-d4b6-528c-8e3d-4302c9510b53 | note | Standard / Specification - PS 15.10.4, PS 15.10.5 Appendix XIII
0c3bb1ce-aaf0-5272-9b8f-4d902e6bbc45 | note | Verifying Document - Shear Vane or Scala Report
85d3bae8-7bf8-56b3-9602-213fb78a5576 | note | Frequency - 4 test per 400M2
55a69f30-35b2-5c05-9282-92604524f101 | note | Verification Activity: Activity - I
8a1bfe00-8ce7-590a-a5cb-d9ae236fa6a6 | note | Verification Activity: By - SE
55b576e1-21ed-531a-aacd-d94250dc6129 | checkpoint | 6.02.04 - Undercut Subgrade Compaction
f841e758-4cd2-5891-b08c-751a3c88b535 | note | Acceptance / Conformance Criteria - The degree of compaction of each layer shall be such that when trimmed to a smooth surface, the resultant impression in the surface under a smooth wheel roller having a minimum loading of 6259kg per metre width of fill or equivalent as agreed by the Engineer, shall not be greater than 7 mm for bulk fill or 5mm for subgrade fill.
8fb02c88-5c79-5b58-a1dd-92a07552b833 | note | Standard / Specification - PS 15.10.4
a629293c-385f-5bce-b059-933f4c7d43dd | note | Verifying Document - Site Records
2a96cae7-3c6a-51cb-9454-6091224f2d6f | note | Frequency - Prior to Backfilling
4ff321f5-d0cb-5131-9bac-f2447b9cd5d8 | note | Verification Activity: Activity - S
9afabe93-cf7b-5ea2-9907-09925e3a24f2 | note | Verification Activity: By - SE
9bb70f82-94b7-566d-9ef1-4b61c37556a1 | checkpoint | 6.02.05 - Soft Road Subgrade Areas
6fd65fab-6193-5462-afeb-d69af1a8db96 | note | Acceptance / Conformance Criteria - Any soft area observed during rolling of the subgrade shall be referred to the Engineer.
d76e99d9-c656-55e3-acb1-1c1df46f6945 | note | Standard / Specification - PS 15.10.4
1be23212-e8df-5d9f-8313-9a5254ebe069 | note | Verifying Document - Notice
1c0d6418-f406-5f50-950c-5444425f50bf | note | Frequency - When Encountered
34656019-18b2-5fea-94d4-d598e2a8138a | note | Verification Activity: Activity - S
c035f040-40a1-576d-b193-c59e6a453dad | note | Verification Activity: By - SE
c3b7c71e-cfaa-5a96-a625-454bb0cc64fa | checkpoint | 6.02.07 - Finished Surfaces
9bec837e-b683-55ad-bd75-4a248c626262 | note | Acceptance / Conformance Criteria - The works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for Subgrade is 0 to -30mm before placing aggregate layers.
a6991efb-ab9a-5b99-bf23-cb2f8b77c50b | note | Standard / Specification - PS 15.6.8
be65fa83-a107-5342-9c6d-a54c8b435c69 | note | Verifying Document - Survey Records
887ad7d3-09f0-5edf-a3ba-45e2f89d1d67 | note | Frequency - Each Finished Surface
157d7177-0edf-5110-9131-f02c3d9f1433 | note | Verification Activity: Activity - D
1fe43a96-441d-52f3-9c61-b1ddff480ba2 | note | Verification Activity: By - SV
9149e6ff-1de8-5094-9b9f-ead6fee4ce61 | checkpoint | 6.02.08 - Subgrade Proof Roll and Foundation Inspection (Road and Embankment)
b64008e4-8e18-5171-b4ca-a72a0d91c282 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect the Foundation surface prior to Filling during the Proof Roll. No filling shall be undertaken until an inspection has been made and the Engineer has approved the cut and stripping of unsuitable materials. Visual Observation Across The Stripped Area Displacement < 15mm.
677d8b3a-9fe5-5e7f-9e11-0862609e0580 | note | Standard / Specification - Appendix XIII PS 15.13, PS 15.10.5
9841c2a6-be7e-500d-bcca-506f57b64c31 | note | Verifying Document - Engineers Approval
4e231911-13ab-5ecd-9b53-75b332d5bfb0 | note | Frequency - Prior to filling with 24h notice
c10bf413-07c4-5174-9e14-7c2fbcd9358d | note | Verification Activity: Activity - HP
950b4e24-66ad-5e1f-946a-4eebbe8609ed | note | Verification Activity: By - ENG
f05195d4-07ae-5bad-820d-5d958fa1f023 | signoff | AUTHORITY HOLDPOINT
cbfd5119-9511-5f05-a1a3-eb568e57c7a2 | section | 6.03 Filling General
6da130e7-ec1a-5eb6-b735-c0a7919ee1b0 | checkpoint | 6.03.01 - Compaction Trials
082af659-e5a1-5e55-bb14-86dcfa2c12cc | note | Acceptance / Conformance Criteria - The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (i.e. construction discs and scarifiers). The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements. The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial.
b932f253-0659-5483-8431-149e22a51f34 | note | Standard / Specification - PS 15.10.15
0ff16a2c-7e89-5fe7-97b9-0d0dc811e560 | note | Verifying Document - Trial Results
5fa74afb-d11f-58b9-9267-b51498af3937 | note | Frequency - During Works before placement of each material.
103d17fd-0df9-56e9-949a-dda4690eb715 | note | Verification Activity: Activity - R
66efe4f8-ef07-5b70-852c-a42dccaab6c1 | note | Verification Activity: By - PE
e6b0ff49-10c9-5967-b663-f2fc4e147aa3 | checkpoint | 6.03.04 - Geotextile on Undercut to Waste and Backfill
b66a3f7f-c101-55fc-a488-65023d32f225 | note | Acceptance / Conformance Criteria - Geotextile shall be laid across the undercut base and the sides and joints shall be overlapped to in accordance with the manufacturers specification to prevent squeezing of the underlying foundation.
39fe306a-53bb-58ff-84b4-d25744279b95 | note | Standard / Specification - PS 15.10.9
2215bfc9-484e-5f67-adce-6df3c540172a | note | Verifying Document - Site Records
2d33a3f7-a446-54bb-a02a-dbae2920cdbb | note | Frequency - Prior to Backfilling undercuts
8477f682-7f40-53b2-9c76-46de57fde771 | note | Verification Activity: Activity - R
f661c483-12d8-5268-8d41-625af8658963 | note | Verification Activity: By - SE
29370bd4-2ff3-5032-ac70-4629fb46ed01 | checkpoint | 6.03.06 - Weaving or Pumping
bd1991d0-5093-5804-aff8-c52b44e7385d | note | Acceptance / Conformance Criteria - Any weaving or pumping of the soil or subgrade during the compaction process is likely to indicate that either the water content is excessive or the material has been over-compacted. If weaving or pumping is observed, the Engineer should be contacted to advise the appropriate solution.
e605ba42-46c5-5a4e-888c-2477e598e0b8 | note | Standard / Specification - PS 15.10.16
d39f9c2c-ed77-5b28-9068-8d5502076351 | note | Verifying Document - Site Records
68e095e6-4a9f-530e-83a7-48b3803bce4c | note | Frequency - When encountered
27e7c1ea-82b6-5046-a56c-510159c3d998 | note | Verification Activity: Activity - S
ed838f5a-7bf1-5227-8006-76b8f7af37f3 | note | Verification Activity: By - SE
8121b3c2-5c62-5f8a-95d7-1511aca62833 | checkpoint | 6.03.07 - Finished Surfaces
3070b6ed-33d2-59d9-86fa-a87d75982015 | note | Acceptance / Conformance Criteria - The proposed works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for earthworks construction purposes shall be level +/25mm unless stated otherwise, Subgrade; 0 to -30mm before placing aggregate layers, Bulk fill ±100mm, Preload and surcharge ±100mm, Batter slope tolerance ±100mm
3c16fa38-3eaf-5ad1-9f22-07ba1a84a45f | note | Standard / Specification - PS 15.6.8
816b2da5-1e05-56ee-b0d4-f4dad76d85e7 | note | Verifying Document - Survey Records
41c5a73c-3d7a-5d08-99a6-a6c30a41296c | note | Frequency - Each Finished Surface
d8403246-e1a7-5f1e-a63f-c616a6f86317 | note | Verification Activity: Activity - D
6183135d-77a3-5020-94fc-7c8fb634a0f3 | note | Verification Activity: By - SV
28941e1a-7c86-5b6c-b4be-2bd9aa06435c | checkpoint | 6.03.08 - Final Trimmed Shape Inspection
929f9aa7-dcab-55ef-848e-e713dd5186b9 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect final trimmed shape prior to placing topsoil or track rolled fill.
a0d0e862-2504-55af-b439-f3f7356c1fcf | note | Standard / Specification - PS 15.13
51f6149e-c97b-5a09-af39-5267730b4dd8 | note | Verifying Document - Engineers Approval
1d64599f-c05f-5017-bfc2-421633c38bf0 | note | Frequency - Prior to placing topsoil or track rolled fill.
ec8638c9-6512-5db2-95d2-d6d3f35119b8 | note | Verification Activity: Activity - HP
72c74c91-2072-5a09-8013-ca846e10480a | note | Verification Activity: By - ENG
2fa4e556-dcd6-5d59-898c-5d69fcba5b07 | signoff | AUTHORITY HOLDPOINT
9009fa4f-63e9-5b9f-b8f5-3feccfd591cc | section | 6.04 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
25dd2c92-e278-54c8-aa60-59679d5bfb86 | checkpoint | 6.04.01 - Imported Structural Fill Layers
6878fdaf-0bcd-5db1-a513-1fc0df376bbf | note | Acceptance / Conformance Criteria - The material shall be placed and compacted in layers no greater than 300mm thick.
8b06cea0-2762-5a10-b343-8660f98e0189 | note | Standard / Specification - PS 15.10.14
1a89ef0a-9801-51bc-aee0-85e181a5627d | note | Verifying Document - Site Records
30797fec-d05d-5e1d-9407-2ca3ce812dbc | note | Frequency - Each Layer
e9f5e8d3-b7f2-5398-be87-1d5e695a0fb9 | note | Verification Activity: Activity - R
d72c325b-87d7-5b7a-abca-566cc22d1211 | note | Verification Activity: By - SE
7d79ea5d-74fb-5020-a7fc-15bc0d20fe88 | checkpoint | 6.04.03 - Structural Fill Zone - Strength – Clegg Impact Value (CIV)
33972346-eaf4-5b1b-adab-39ff4c57e4e4 | note | Acceptance / Conformance Criteria - A1 Imported Structural Fill Strength shall be tested by Clegg Hammer every 200m3 per area per day per lift
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Minimum CIV = 18
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Average CIV= 20
b21d6bc2-fa63-5bc1-8d96-b05121b299af | note | Standard / Specification - Appendix XIII
9e78cce7-cd0a-5ffe-b4f7-52f1a5f40ad1 | note | Verifying Document - Clegg Results
edfa4ec3-1fcc-5df9-ba9c-81716eabe644 | note | Frequency - 1 Set (5 Tests – 5x5m Square Grid) Per 200m3 Of Placed Per Area Worked Of Day Per Lift
c952f64f-f2ef-5aeb-b6b7-5b247ddc0cdb | note | Verification Activity: Activity - I
e91737f2-9daa-590c-ba83-c4825556312f | note | Verification Activity: By - SE
cff2e2af-607b-551c-bbeb-3ae8301207cb | note | Comments / Closeout Details - Are both NDMs and Clegg Required
e7febe44-92c4-5796-b0f2-b82320d4484e | checkpoint | 6.04.05 - Structural Fill Zone Insitu Density Insitu Compacted Dry Density Insitu Water Content
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - A1 Structural Fill Compaction shall be tested by NDM in Backscatter Mode every 200m3 per area per day per lift
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | ○ Average >95% Of In-Situ MDD
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | ○ Minimum >92% Of In-Situ MDD
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Standard / Specification - Appendix XIII
69d85f65-b61d-579d-940f-2b691894d755 | note | Verifying Document - NDM Results
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
e2147c12-4568-5322-b418-283ae63070af | note | Verification Activity: Activity - I
09a8aad4-3fc9-597d-b419-c865f36b4acc | note | Verification Activity: By - SE
e446d0a3-f492-586c-ab52-5751ac56d10a | note | Comments / Closeout Details - Are both NDMs and Clegg Required
b9a8462b-715b-5c2d-8c25-e4f73254a4ca | checkpoint | 6.04.06 - Solid Density
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - The Solid Density Of Aggregate Particles shall be tested by collecting 1 sample with every set of NDMS completed (1 Test Per 200m3 For That Material Type And Source). Test Results Provide Input To Acceptance Criteria For Insitu Compacted Dry Density Determined By Nuclear Moisture Density Gauge (NDM)
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - Appendix XIII
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Solid Density Lab Report
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - 1 Set (5 Tests) Per Material Type And Source Then 1 Test Per 200m3 For That Material Type And Source
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
5ec91113-ac87-53de-b900-bcb9253aa488 | note | Comments / Closeout Details - Are both NDMs and Clegg Required
504915a0-29d1-5b8a-891c-a7b613638c3c | checkpoint | 6.04.07 - Organic Content
f09d0ff0-01ec-50cb-9988-3a078371cb3d | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
5d4c6d19-d8fb-5765-9b80-10ed32dbffe9 | note | Standard / Specification - Appendix XIII
ea12d870-db9e-5048-94de-56f316678975 | note | Verifying Document - Site Records
4b4f2a35-1e50-5341-80c6-541a73664b53 | note | Frequency - Ongoing
f77c9bbc-fb8f-5e0f-86c9-c66a4643254e | note | Verification Activity: Activity - I
dbb35f07-7f2f-5414-a8b4-c69adbcef37c | note | Verification Activity: By - SE
f910ed7f-8370-57c8-b1bd-2fb721606286 | checkpoint | 6.04.08 - Completed Fill Approval
cb670aff-3430-5d2c-ac3e-1482548f09ee | note | Acceptance / Conformance Criteria - Prior to pavement construction the Engineer shall complete a Desktop review of all structural fill compaction testing for acceptance.
e3ea5880-55a7-54a4-9ee9-9323b972ab79 | note | Standard / Specification - PS 15.13
eb4e4dcc-9679-50a0-8275-a70670f63fd0 | note | Verifying Document - Engineer Approval
5b1465a0-9c5b-51b0-8b4b-9694e85f2324 | note | Frequency - Prior to Pavement Construction
a3b40c94-fe59-5b33-bcda-878d287d2995 | note | Verification Activity: Activity - HP
696e1611-579b-5ae6-b3d8-5701063db1b8 | note | Verification Activity: By - ENG
5e0c2555-3e93-5160-beb9-af9efce873aa | signoff | AUTHORITY HOLDPOINT
faf4f3a3-1299-5382-bb2c-73748ed0cb2e | section | 6.05 LANDSCAPE FILL
a57c22bd-882b-5e15-98f1-6cc1024a010c | checkpoint | 6.05.01 - Cohesive Fill Layers
c352122b-b969-515a-bd14-4ee2d6d77a2c | note | Acceptance / Conformance Criteria - Cohesive structural and non-structural fill material, shall generally be compacted in layers of less than 200mm thickness. All fill surfaces shall be sealed at the end of each day’s work.
eb2c9836-d46b-5735-a171-5b7c260a8373 | note | Standard / Specification - PS 15.10.16
16c87f21-2b6f-5a9e-950f-ce52726911a4 | note | Verifying Document - Site Records
f997564b-0a06-59cc-aaf8-0d04c169bb65 | note | Frequency - Each Layer
48daa9bc-dbe2-5457-aa35-ebb3d2f05eee | note | Verification Activity: Activity - R
a63751f3-0140-5d7c-80c1-864752f123ce | note | Verification Activity: By - SE
91ea3ae5-4753-56e1-b28d-0d3a3fb40e12 | checkpoint | 6.05.02 - Fill surfaces Sealing
a578d34e-40e1-5c0c-b225-25282dfa3822 | note | Acceptance / Conformance Criteria - All fill surfaces shall be sealed at the end of each day’s work.
275dad26-4948-57bc-bc5d-25291c4dfe04 | note | Standard / Specification - PS 15.10.16
bf910f9a-c5f9-5501-bd00-480e205a15ef | note | Verifying Document - Site Records
cd655ab2-4234-580a-b1d2-e5f8d0f9c64b | note | Frequency - Each Day
5b4f0479-5692-504d-98b2-93cf71280de9 | note | Verification Activity: Activity - R
a00280e8-d9ac-5f5e-86c0-a351a10dc28a | note | Verification Activity: By - SE
e9f6dd3e-48b2-53bf-8c70-05c59c2b86d9 | checkpoint | 6.05.03 - Non-Structural Fill - Air Voids
8e28b866-fa38-519b-918f-3d14bb22ecfb | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill compaction (Air Voids) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift.
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Average Maximum Air Voids < 8%
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Single Test Maximum Air Voids< 10%
b6a6dfee-f164-5998-9bdb-0af48b5f824e | note | Standard / Specification - Appendix XIII
bebdea1e-dece-5fe9-9b48-a107125b16b9 | note | Verifying Document - NDM Results
e003f7a2-352b-5d80-9fd5-e44eddfe06fe | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
3f5e0ef0-3697-5f92-8b8c-ec24df3f2e89 | note | Verification Activity: Activity - R
da65e1bd-770b-59ad-9793-ebeab9e626dd | note | Verification Activity: By - SE
cf7abc67-8aed-5d00-ac3a-cbae29efad1b | checkpoint | 6.05.04 - Non-structural fill Zone Strength – Shear Strength (SU)
8a655586-34a5-5a18-aef6-d6c0c46b2eca | note | Acceptance / Conformance Criteria - A2 Cohesive Non-Structural Fill Strength shall be tested by hand held Shear Vane or Scala every 500m3 per area per day per lift of fill placed.
c7bdbe91-5ef1-591f-a7d8-c0e38c48b32f | note | ○ Average Minimum Su > 60kPa
73c7904a-13cc-5564-872e-5dd2ec0ff2cf | note | ○ Single Test Minimum Su > 50kPa
6d410085-df0f-5e4e-aba8-430c7c78ff17 | note | ○ Scala: Minimum 2 Blow Per 100mm
1fb5184e-2a61-5ac4-9704-8af92d7bb87c | note | Standard / Specification - Appendix XIII
10e1325c-804d-5162-810d-a48453df0e42 | note | Verifying Document - Shear Vane or Scala Results
37a82803-7835-5700-8489-5432f89e46a3 | note | Frequency - 1 Set (5 Test) Per 500m3 Of Fill Placed Per Area Worked Per Day Per Lift
338c0f69-5352-5f07-a019-adfc9ad24162 | note | Verification Activity: Activity - I
6aa5aee6-bbbc-5074-9145-e9071c21bc5a | note | Verification Activity: By - SE
67d2cb19-a2ab-56fe-9362-2a11a6148fa9 | checkpoint | 6.05.05 - Non-Structural Fill - MDD
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - Non-Cohesive Non-Structural Fill compaction (Dry Density) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift. 90% Minimum Dry Density (MDD).
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | Standard / Specification - Appendix XIII
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | Verifying Document - NDM Results
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
69d85f65-b61d-579d-940f-2b691894d755 | note | Verification Activity: Activity - I
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Verification Activity: By - SE
940c74e2-d6b4-59ce-a549-e065a128c6e6 | checkpoint | 6.05.06 - Non-Structural Fill - Granular Mixed Materials
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - Mixed non-structural material requires proof roll to ensure compliance with the 7mm requirement. Proof roll to be done where soils cannot be penetrated via shear vanes or scala
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - TNZ F1 Section 10.5.1
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Site Records
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - Formation level
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
c83c1a95-6cc3-5b55-ac8c-57dd36cf1a2e | checkpoint | 6.05.07 - Organic Content
8e7ab7fa-96cb-549a-9853-95660876e381 | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
8198a028-f5d8-5206-b061-611b85274fdd | note | Standard / Specification - Appendix XIII
952eeb47-9e0c-50f4-864e-51dc8f1168e6 | note | Verifying Document - Site Records
e0771c83-af76-5822-8faf-087df801ca3e | note | Frequency - Ongoing
d1b036db-e4f5-5709-84c8-a981882122fa | note | Verification Activity: Activity - I
c2527edb-afb6-51e1-9d14-580ba94c551a | note | Verification Activity: By - SE
8a6e4423-2a66-5b93-af2a-67e156f07a85 | checkpoint | 6.05.08 - Water content
9d39d25f-97ac-5ae3-970e-6abecd8c2228 | note | Acceptance / Conformance Criteria - The water content shall be tested by collecting 1 sample with every individual NDM test.
35a9571c-d251-519a-bf72-8bcb19c90ada | note | Standard / Specification - Appendix XIII
2f203e77-26b5-5030-9eb6-61930d4e3531 | note | Verifying Document - Water Report Report
548c00ec-7190-5439-bff7-d3a33919bc19 | note | Frequency - Every NDM
427069ab-8eaa-5f99-b292-086237aebe3e | note | Verification Activity: Activity - I
d48e35aa-39b8-5d10-900e-0bafb0b47fe7 | note | Verification Activity: By - SE
94ecb72f-b511-5fef-99c9-b75caaae5292 | checkpoint | 6.05.09 - Bulk Density, Dry Density, Air Voids
2ff13b7b-02c2-5a7b-8118-f41c41b17271 | note | Acceptance / Conformance Criteria - The Bulk Density, Dry Density, Air Voids shall be tested by collecting 1 sample (Sample Tube) for every 10 NDM Sets completed.
c39051d9-945b-528b-a585-33d79297aaee | note | Standard / Specification - Appendix XIII
dd793333-b4d3-5ea8-9644-25cf03ccc6e5 | note | Verifying Document - Lab Report
d69a3d8f-c798-532b-a15c-6f7e4df14e4c | note | Frequency - 1 Test Performed For Every 10 NDM Test Results Provide
2d5640eb-932b-5ba9-87eb-2c7ce14f8894 | note | Verification Activity: Activity - I
c9a19186-767d-535f-9741-6cc10a171f11 | note | Verification Activity: By - SE
a3350b27-5c47-5b3b-ab57-f9e96424a1da | section | 6.06 Settlement Monitoring
5e695847-04f1-541c-9e60-5f3ce9021c7d | checkpoint | 6.06.01 - Settlement Monitoring Methodology
55cd879c-55fc-5cf6-ac3c-be63cb59295d | note | Acceptance / Conformance Criteria - The Contractor shall submit details of their proposed monitoring equipment and installation methodology within their Earthworks Management Plan for the Engineer’s Approval.
e81a1f0f-e781-525e-8c33-4e23315d1115 | note | Standard / Specification - PS 15.12.5
3d5ed6b8-8e4c-545a-9b90-7b60919dd913 | note | Verifying Document - Approved EMP
ef9455b2-30f0-545d-a18d-d1e03ec6a2d5 | note | Frequency - Prior to Works
bbd43815-e554-5e0c-8e5b-3ca67662ee30 | note | Verification Activity: Activity - HP
258d068c-dd4d-5efc-a8bb-531c5d1e9410 | note | Verification Activity: By - ENG
5d1819d4-2a89-5c6a-acb4-52c8ae9493b0 | signoff | AUTHORITY HOLDPOINT
1309e638-c7ad-5317-82c8-377f0218a22a | checkpoint | 6.06.02 - Supply, Install, Survey and Remove and Monitoring Equipment
f3fece7f-2a75-51d9-ab8c-3818abf85f3f | note | Acceptance / Conformance Criteria - The Contractor shall install geotechnical instrument systems in the positions shown in the Contract Drawings unless otherwise instructed by the Engineer.
f5b4da39-18a7-50fa-81bb-119512aa3245 | note | Standard / Specification - PS 15.12
f2f8a813-1fd2-5f2e-8fb2-868eac6068eb | note | Verifying Document - Site Records
51df963b-9897-5abb-94e9-92f9a247955d | note | Frequency - Prior to Construction
68391c45-455a-5051-9344-65d8f1c811eb | note | Verification Activity: Activity - I
160f22c6-6304-5fea-b1ab-230125cb63ef | note | Verification Activity: By - SV
0f533e6c-1bd1-57a4-a4c0-c28f362a9a0c | checkpoint | 6.06.03 - Instrument Reading Notice
6f87da36-7041-5714-aab1-a9d1a3d4eb69 | note | Acceptance / Conformance Criteria - The Contractor shall inform the Engineer two days in advance of planned instrument readings so that the Engineer may observe the work.
e3bc3f60-11df-5986-8e49-8f95bf3b526c | note | Standard / Specification - PS 15.12.5
d1a19be7-e1d3-5547-8909-138345432d0b | note | Verifying Document - Site Records
1f9dbbe2-04ff-5485-ae11-50ba7690ec6a | note | Frequency - Prior to Survey
fe3add51-08eb-5bf7-8e2f-9257106320fe | note | Verification Activity: Activity - HP
78d1467f-a870-5168-8aca-e0fc839d8ecc | note | Verification Activity: By - ENG
f2f84277-75de-5c7e-be35-eeeb68a3e8a9 | signoff | AUTHORITY HOLDPOINT
2517047e-845e-5644-ae2e-510b4502a782 | checkpoint | 6.06.04 - Base Readings, Responsibility and Ownership
26de447a-be80-5db7-9fed-a5598df339e2 | note | Acceptance / Conformance Criteria - Following installation, the Contractor shall undertake testing to demonstrate the instruments are working properly. The Contractor shall submit records of each of the instruments showing location, soil conditions encountered, installation details and initial readings. Construction will not be permitted until the Engineer is satisfied that the instruments are working correctly.
3dac7c57-2fd9-5583-b22e-1c9daad809d8 | note | Standard / Specification - PS 15.12.2
57fbadc8-856e-59ea-9c0b-6a4ad79abd98 | note | Verifying Document - Site Records
887d2697-0438-5748-9d92-50071d9dcfaf | note | Frequency - Prior to Construction
172ad8cb-f559-5105-bb7d-9fce0c280ca5 | note | Verification Activity: Activity - HP
e13218bd-7f4d-5ce9-9578-5fc34d2a157d | note | Verification Activity: By - ENG
b68c1eb5-b89f-5102-ab04-0d343f0c2bc8 | signoff | AUTHORITY HOLDPOINT
012ae06c-51f7-539e-99db-22dc8857a1af | checkpoint | 6.06.05 - Pin Protection
05377e32-4d4d-5ac9-85e7-88b011824a6c | note | Acceptance / Conformance Criteria - The Contractor shall ensure the Pins are protected and not disturbed in any way once constructed. The Contractor shall also install settlement survey stations at locations protected from Construction traffic and works.
5d18b3db-6402-5696-83e5-db181b003227 | note | Standard / Specification - PS 15.12.5
05cd1b8f-838a-5ded-9ab1-8a0bccdc8b88 | note | Verifying Document - Site Records
89614663-9ee1-5f54-80d8-09f62996a296 | note | Frequency - Ongoing
96cac559-a2d0-5e18-bd1c-8c5f91f83364 | note | Verification Activity: Activity - R
3f8e7bef-6f86-5244-b41d-7c1991bd3106 | note | Verification Activity: By - PE
d71f530d-3a2d-502a-85c4-0e6cfd071bfd | checkpoint | 6.06.06 - Monitoring
1d838e30-c9ec-58bc-8841-43d057802429 | note | Acceptance / Conformance Criteria - Following the active fill of the embankment, the Contractor shall read all monitoring pins bi weekly. Monitoring frequency may be reduced to weekly intervals when there is no active earthworks in that area, and while waiting for embankment to settle.
ab916766-b8ca-5614-a3be-61f3ef5ce0a5 | note | Standard / Specification - PS 15.12.5
5a8987e1-beb5-5285-9626-14c6d4b752e3 | note | Verifying Document - Survey Records
6fa587b6-07fd-53aa-b98e-c9e5af40fc7a | note | Frequency - Bi Weekly following Embankment Filling
a7929d20-4291-5176-920f-7926ba3c34af | note | Verification Activity: Activity - R
c2010ee4-fd12-508a-ae38-dccfae200836 | note | Verification Activity: By - SV
a623e6c5-b632-5bb4-bb24-cba69e701574 | checkpoint | 6.06.07 - Engineers Review
d77b11fc-070b-50e1-8629-958659ff4f44 | note | Acceptance / Conformance Criteria - The Engineer will review the results of the settlement monitoring to assess completion of the preconsolidation period. This period is anticipated to be less than 3 months.
cf3d110b-7081-5043-99cf-c1c5e1e82116 | note | Standard / Specification - PS 15.12.5
88313476-05c6-574c-be37-84b542b7c1ff | note | Verifying Document - Survey Records
aba9f8b6-25d1-5e33-9124-ff7cef034c4a | note | Frequency - Ongoing
53867a85-e95a-5618-87e7-f9eec85edf34 | note | Verification Activity: Activity - R
49b6db7c-780d-5c5a-b85b-ffd17e3d8432 | note | Verification Activity: By - SV
c0a27a5d-8b1f-50f5-b01d-a262601e207d | checkpoint | 6.06.08 - Pore Water Dissipation
75ceb013-f0cb-5b7e-af80-af6640b2d53d | note | Acceptance / Conformance Criteria - Review of settlement pins data to confirm sufficient pore water dissipation has occurred in the soft soil layer.
1e5ba5db-1e50-52e5-a141-a55015b8ec11 | note | Standard / Specification - PS 15.13
6d539e72-2e15-54ff-a874-531eefc30c8a | note | Verifying Document - Engineers Approval
bde27891-0f79-54b4-bce1-6e40158e43bd | note | Frequency - Prior to completing Monitoring
1f4973ca-c9c2-5289-b401-f542f7e282e3 | note | Verification Activity: Activity - HP
c3e2a4d3-85b0-50f8-aab3-5c691c2e24f6 | note | Verification Activity: By - ENG
2e34f781-af18-50d3-a840-a001fb34c51d | signoff | AUTHORITY HOLDPOINT
89b1bcee-a704-5892-9410-e9311d5e0992 | checkpoint | 6.06.09 - Settlement Monitoring Termination
f89d107c-7f62-5edf-ba7c-a0e330bfb041 | note | Acceptance / Conformance Criteria - The criteria for terminating the embankment preload are either: Three consecutive measurements indicating the t90 settlement value has been achieved, A rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed. The settlement readings shall be evaluated by the Engineer to assess the need to extend the monitoring.
2d0e1d42-bc4c-5ffc-a6ec-30a5d4d6670d | note | Standard / Specification - PS 15.12.7, PS 15.13
95432c0f-587e-557b-a06a-d2c1de6b3656 | note | Verifying Document - Engineers Approval
e1dd00fe-0aed-5bbc-9759-328a6cb6ca36 | note | Frequency - Prior to completing Monitoring
f1a09b53-7a5d-50a9-8933-50232be4a599 | note | Verification Activity: Activity - HP
adfba00d-f5d8-5f2d-a739-d023b0e4a01c | note | Verification Activity: By - ENG
de792686-1074-5b19-8609-1cce7f903454 | signoff | AUTHORITY HOLDPOINT
18598be7-dc44-5e98-80cf-ec8682aefcf1 | checklist | Ω (DEPRECATED) ITP - Earthworks - 101 - Rev 2 - v2 | itp | ITP - Earthworks - 101 - Rev 2
ac5ee1ee-5139-57b0-9c55-3196b7da263c | section | 3.01 General
4b182364-c9b8-5807-85b4-26cb6c506fc7 | checkpoint | 3.01.01 - Precondition Surveys
69cd2420-d366-54eb-958b-47ee6ba30c3b | note | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
8a300e3e-8b0d-50e1-92a8-acacc9470272 | note | Standard / Specification - PS 2.13
4012ae1e-5742-5bb3-bd88-9891dd0da569 | note | Verifying Document - Precondition Survey
5ee54bf7-4881-50be-9cbd-b6ca24fbed29 | note | Frequency - Prior to the Contractor taking possession of the Site.
4ee5ad50-8a49-5ef9-b2ce-6829404da63e | note | Verification Activity: Activity - H
042a86d8-9388-5bf2-bc39-fae98a19ea53 | note | Verification Activity: By - PM
2c4b8fd4-5150-5656-bda8-48bbc0f299cc | section | 4.01 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
eec51e33-e195-5fd4-8848-2a84896576bc | checkpoint | 4.01.01 - Source Property Tests and Sampling
c970b435-1a5a-5b52-9c63-6d3dc47a7b24 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, Los Angeles Abrasion, and Soaked CBR at least 2 weeks prior to importing to the site.
5fddf01b-636b-5c1b-9e0f-f9d479c784a9 | note | Standard / Specification - PS 15.7.3 Appendix XIII
c05f86e5-078b-56d0-a84d-743d12ed7c80 | note | Verifying Document - IANZ Lab Reports
0d61936a-619a-5486-b002-fd3bb8ecd191 | note | Frequency - 2 Test Per Material Per Source at least 2 weeks prior to importing to the site.
6c36e154-7375-5049-8d17-38c7ea3fb8aa | note | Verification Activity: Activity - HP
3ce79e68-2cd7-57fc-8b23-187278275664 | note | Verification Activity: By - ENG
943c57a3-9718-5eec-a0c4-4f254ca57b92 | signoff | AUTHORITY HOLDPOINT
e74ba8eb-c7ac-51ca-806d-ce6b2d151d6f | checkpoint | 4.01.02 - Testing for Layer Compaction - MDD
0eea5d39-c7a9-597e-95e8-2d3aa0eb79ce | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Heavy Compaction), Optimum Water Content, Air Voids, and Shear Vane Strength (Su) with Range of Moisture Contents.
3a7cfff1-f254-5419-911c-e86cf81791ad | note | Standard / Specification - PS 15.7.3 Appendix XIII PS 15.13
bac60110-709f-58ca-825f-eef1d568b6fe | note | Verifying Document - IANZ Lab Reports
28d0819b-7509-50e5-aaad-6484fe8c56af | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
93ed1431-f321-5f8b-8125-d991cf43a90b | note | Verification Activity: Activity - HP
5eecf011-989a-5420-a82b-eb0149a57904 | note | Verification Activity: By - ENG
1ad45696-b06f-57ba-991f-876ec2469f8a | signoff | AUTHORITY HOLDPOINT
cc28f368-5ec3-56d4-92e5-eeccc9eacb38 | checkpoint | 4.01.03 - Production Property Test Sampling
6c461bdf-e882-525f-a094-2bcc190ce2e7 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD).
4c2ef108-068a-59d0-b3de-60b2a95c6c7f | note | Standard / Specification - PS 15.7.3 Appendix XIII
6a814afb-0be7-53e5-8592-2862e1a765fd | note | Verifying Document - IANZ Lab Reports
efce84d9-b1b2-5d89-991c-9da04e5ba923 | note | Frequency - 0-400 M3 – 2 Tests
f89666dd-0f56-5b39-b7d2-2694b08c1b13 | note | ○ 400-1,500M3 – 3 Tests
ed92ad50-6f20-5df3-bdee-ddfd8f5eb73d | note | ○ 1,500-4,000M3 – 4 Tests
8473fabf-bde7-5cc9-8e93-e31e0d9d300b | note | ○ >4,000M3 - 1 Test For Each Additional 10,000M3
fd98181f-7bd9-5f53-8201-bb0c6813a688 | note | Verification Activity: Activity - H
29935793-de84-5fc9-9e9a-dc726b88856e | note | Verification Activity: By - PE
d3197014-3f06-5fe0-b1d9-aea439b97c54 | section | 4.04 Type A3 (Site Won Landscaping Fill)
bd572b98-794b-572a-b262-0d8895c651db | checkpoint | 4.04.01 - On Site track-able Testing
8fefcbaf-cb68-5917-9433-3d41137b8e4e | note | Acceptance / Conformance Criteria - Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it is ‘track-able’ by the contractor’s plant. This shall be determined before Sampling.
b4914206-8d0b-5414-9502-17ae4fad6e1c | note | Standard / Specification - PS 15.7.3
e51abaca-32b0-57d1-8544-f906b25a9fc0 | note | Verifying Document - Visual Site Record
aaf6e6a1-d9e9-5a27-86da-31e404a8a62d | note | Frequency - Prior to Sampling
d4f5a2c3-8d72-5a12-84a0-52e374ec9d02 | note | Verification Activity: Activity - W
21e39c46-937e-5756-bf3a-0fa20897c108 | note | Verification Activity: By - PE
bbfc5154-bf5f-5edf-b862-ca5b40d3d743 | checkpoint | 4.04.02 - Testing for Layer Compaction - MDD
da4431ef-f91b-5faf-a07f-ebe5b3ed0ce8 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Standard Compaction), Optimum Water Content, and Shear Vane Strength (Su) with Range of Moisture Contents.
75366e9f-f170-5da4-8e90-2ba29431f456 | note | Standard / Specification - PS 15.7.3, PS 15.13
01c254a6-d804-5850-b1b7-daee29774ece | note | Verifying Document - IANZ Lab Reports
cd00113d-ee85-5286-956b-580960ae86ae | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
9895d0dc-5a1e-556b-b3a4-f60bb935b694 | note | Verification Activity: Activity - HP
803e0adb-6908-539d-91c5-5f291f829291 | note | Verification Activity: By - ENG
787da1d7-76e7-5318-90fc-d7c5b66f0772 | signoff | AUTHORITY HOLDPOINT
1b403918-b691-5bde-88b7-f3ee9e087117 | checkpoint | 4.04.03 - Insitu Property Test Sampling
b2e3a0b7-200b-54bc-8753-e33bdade2178 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD) and inspected for deleterious materials such as boulder size fragments and organic materials.
da342694-bd84-565c-b303-933f704abeb3 | note | Standard / Specification - PS 15.7.3
3f8b0f56-e239-5878-82f3-25bd301b0188 | note | Verifying Document - IANZ Lab Reports
54187772-fb0a-5304-b22d-e6fef5571033 | note | Frequency - Prior to use
5f2c876f-b40e-5944-91db-1b5c4f101bfd | note | Verification Activity: Activity - HP
10ebcf48-ad4b-5c4f-ac90-4d24da87969d | note | Verification Activity: By - ENG
f4da45cc-ae32-586a-82a0-8191c8cf5c37 | signoff | AUTHORITY HOLDPOINT
540a5e70-44a2-557d-9a5c-b23f9eba4a3f | section | 4.05 Topsoil
20c79c91-2f0b-5e64-bc79-4fc755ec0ddc | checkpoint | 4.05.01 - Topsoil
c48a7814-415e-5bf0-90db-a1b8443b9fdd | note | Acceptance / Conformance Criteria - Topsoil is defined as the layer of material immediately below the ground surface comprising vegetation, tree roots, other non-decomposed organic matter, turf and humus. The Contractor is to stockpile and utilise site won topsoil for placement on the final batter slopes and for borrow site reinstatement as shown in the Contract Drawings.
e65a11a1-9f5f-5b9b-b31a-005bf9a0f5ad | note | Standard / Specification - PS 15.7.3
cf04a554-dfc6-58b4-9613-62ac16fdabb9 | note | Verifying Document - Site Record
ee11df60-1ce5-585b-8998-69594136d238 | note | Frequency - During Stripping
e137dc49-6b12-5bed-ab75-30d89abce352 | note | Verification Activity: Activity - I
11dd70c8-b8f1-5205-a62a-89a0d37a59b0 | note | Verification Activity: By - SE
d75e34e2-526e-508b-9139-1c41f905aee4 | section | 4.06 Geotextiles
94c5cd81-4c09-5866-a780-a6cb2b294715 | checkpoint | 4.06.01 - Geotextile on Undercut to Waste and Backfill
01a812e1-2a2b-5d7f-a9f9-4d80c94b831d | note | Acceptance / Conformance Criteria - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation.
c17089c8-cde6-5780-af0b-4d44cfe037e4 | note | Standard / Specification - PS 15.10.9
3752352a-df5a-53b2-8094-118f73546c7d | note | Verifying Document - Datasheet
8e7145b3-d717-57d4-8b68-f84837bcbada | note | Frequency - Prior to use
6f3350cc-a5e3-5922-90ec-ceba1cff1e25 | note | Verification Activity: Activity - R
ffc1a14f-5946-57d0-b15d-4eb1e2f5b1a3 | note | Verification Activity: By - SE
00122e61-34f7-53d5-a67f-e0c09f6146f3 | section | 5.01 Site Clearance
aa56f8f4-2f1d-53a7-90e0-bf9bff008cd2 | checkpoint | 5.01.01 - Site Clearance
76735cd9-4858-55a6-aa06-101f02518612 | note | Acceptance / Conformance Criteria - All trees, scrub, non-lawn vegetation and/or self-sown plants within the extent of the earthworks shall be removed to waste in accordance with Clause 3 and Clause 9.4 of TNZ F/1:1997 Specification for Earthworks Construction.
e2b43d2f-4215-5670-89ab-c3b1d39d5dd5 | note | Standard / Specification - PS 14.1.1 NZTA F/1 - 3
f35896e9-18bd-51fb-84bd-a516fea07908 | note | Verifying Document - Site Record
1c9aecd5-6527-5a3f-90f9-fb46fb1152c3 | note | Frequency - Prior to excavation
553d21dc-d656-5d11-a678-49e9091a7776 | note | Verification Activity: Activity - I
b8ac2dc9-f39d-5a4c-88d0-92ffc13d346b | note | Verification Activity: By - SE
0434188f-64e5-5961-b752-f68ed0678033 | checkpoint | 5.01.02 - Dump Site Approval
165908c4-435f-5b36-8fd9-df3fab4ecdd9 | note | Acceptance / Conformance Criteria - The locations of dump areas shall be agreed by the Engineer before use.
e22c6756-65e9-50b5-b8f9-e78161c44d04 | note | Standard / Specification - NZTA F/1 - 9.4
55d5c387-b48b-5e7f-9757-2749a36ece54 | note | Verifying Document - Site Record
f84ff3ba-d111-577e-814d-2f3b3ff0c62e | note | Frequency - Prior to Stockpiling
73737f8f-3ed5-5230-a5fa-7d12fd1ac08c | note | Verification Activity: Activity - HP
74ce0d35-f379-5262-b7f4-46543d42148d | note | Verification Activity: By - ENG
c082bbf0-64bb-5295-803d-efd5e36c07d2 | signoff | AUTHORITY HOLDPOINT
97e973d9-e87b-5abc-b883-a17a57730683 | checkpoint | 5.01.03 - Mulching
7c25105e-22ed-5c83-8240-5f58fa89da29 | note | Acceptance / Conformance Criteria - Where possible, cleared vegetation shall be mulched and stockpiled at a suitable site for future landscaping work.
39aa4f4e-e9d4-5b72-a53a-4a01c43363d6 | note | Standard / Specification - PS 14.1.1
54411dec-bc57-5533-afb7-0f38308d0bf6 | note | Verifying Document - Site Record
d3575c48-3185-5f98-b1fe-4784265e23ac | note | Frequency - During Clearing
449c8392-36d0-5a80-8ce1-30049ce1eaa6 | note | Verification Activity: Activity - R
07fddfa0-d1c0-5767-bf10-aa4ad5673f63 | note | Verification Activity: By - SE
4f7cfdbd-f8a4-5f17-a5dd-b36d0cb99ded | section | 6.01 General Earthworks
7b7266d6-ecf8-561a-b4ca-7b37880265fd | checkpoint | 6.01.01 - Earthworks Methodology
c228e36c-639a-5d64-84a6-17b814e6f41b | note | Acceptance / Conformance Criteria - The Contractor shall submit the construction and QA methodology for each element of Earthworks including construction, Haul roads, Site Access, dewatering, Wet weather, testing, inspection, and hold points for review and approval prior to works.
0b682de4-c8ae-51d1-9923-ecbfc85690dd | note | Standard / Specification - PS 15.13, PS 15.6.2, PS 15.10.13
b50a3242-4781-56d2-9c29-2bfa07bedacd | note | Verifying Document - Approved Methodology
9b77a527-c1c2-52d4-bf08-2baf8fe48a93 | note | Frequency - Prior to Earthworks
00c15935-b738-5367-8878-db856c582b87 | note | Verification Activity: Activity - HP
2e554e60-d952-5dd6-861b-a558370ee856 | note | Verification Activity: By - ENG
326a5f19-66e6-52e8-8259-accb86134d3f | signoff | AUTHORITY HOLDPOINT
ce70eb24-ffd6-534e-9bc3-84ccc496c6db | checkpoint | 6.01.02 - Temporary Excavation Approval
8b4c1814-1483-57a0-a93e-7cf0f5129205 | note | Acceptance / Conformance Criteria - The Contractor shall submit Temporary Excavations details to the engineer for approval prior to excavation.
33ca796d-57e5-58de-b34f-c32e6163735c | note | Standard / Specification - PS 15.13
c6d3b217-5879-5d04-b9ab-a032084546f6 | note | Verifying Document - Engineers Approval
de2c1bd3-ac7a-562d-817a-3f4a0bb05767 | note | Frequency - Prior to Excavation.
cd18a545-923b-5871-b92c-dee9402f4e29 | note | Verification Activity: Activity - HP
b2515f22-7df2-58c2-ac65-fe920a60c040 | note | Verification Activity: By - ENG
7f24d1ae-eaea-5164-a39d-b9602a701e03 | signoff | AUTHORITY HOLDPOINT
7be180f9-b731-51bf-aa2a-2646cc8a1c69 | checkpoint | 6.01.03 - Temporary Works Design
6bf13ae3-7a65-50e5-8ee5-356f37e5f99f | note | Acceptance / Conformance Criteria - The Contractor shall submit the temporary works design for Review and approval of prior to excavation.
34321cd1-593b-53a3-963f-41929191a96b | note | Standard / Specification - PS 15.13
725dbc6f-43b7-58dd-b840-2a9e1cc7a0a5 | note | Verifying Document - Approved Design
e4fec50b-b4eb-5cfa-bc23-b5a1182bdb5c | note | Frequency - Prior to Excavation.
2ac192cb-bf2e-52c2-b62a-50c4c4697492 | note | Verification Activity: Activity - HP
e421222d-e59e-5ba2-9fce-d91b87b2c1cd | note | Verification Activity: By - ENG
bd223daf-c7ae-5c7b-b6da-6f123e740f86 | signoff | AUTHORITY HOLDPOINT
55e3284f-9a58-588c-bbef-d9a461605980 | checkpoint | 6.01.04 - Temporary Stockpiles
baf815d3-1ef3-59b4-94ad-daf49ffc72eb | note | Acceptance / Conformance Criteria - Temporary stockpiles shall not be located within the footprint of the permanent works unless approved by the Engineer.
18b30793-18bf-5c62-9ab2-12c0e2ba5c49 | note | Standard / Specification - PS 15.6.5
cc98758a-ecad-5043-bcc8-3a0f6433d90f | note | Verifying Document - Engineers Approval
58eb1e17-79a1-52e1-b4e4-ff51e4c2a10c | note | Frequency - Prior to stockpiling
08cfbbd5-6e1b-5ca2-872e-ed4df362935a | note | Verification Activity: Activity - HP
8f11b887-eb69-534b-b326-59012efc3a5c | note | Verification Activity: By - ENG
a94c983f-b77c-5257-ba7c-2cf26f751c21 | signoff | AUTHORITY HOLDPOINT
9f916a51-531e-50f9-ab39-015b1c560d11 | checkpoint | 6.01.05 - Surplus Material
02f14ce9-3ef4-562b-b104-58d1241b50c7 | note | Acceptance / Conformance Criteria - Surplus or waste soils may be deposited outside the site boundaries with the written approval of the Engineer.
c85b74b4-9183-55a7-ae2f-345297038e49 | note | Standard / Specification - PS 15.1
ef2e0cf0-e7d5-51ba-8a6d-bbc82bdf9e2f | note | Verifying Document - Engineers Approval
a960256b-958b-5eb6-af8e-bc4d99728fb0 | note | Frequency - Each Occurrence
52fea67b-14ca-5826-8d8a-c11dc3466cf4 | note | Verification Activity: Activity - HP
4b1848f4-9510-5def-95f4-d24b7a6c808e | note | Verification Activity: By - ENG
291238e6-3d02-5ec2-b9a8-ab81fb7023ca | signoff | AUTHORITY HOLDPOINT
918a1145-c5ce-509f-bed1-f62ab59e0117 | checkpoint | 6.01.06 - As-Builts
db708295-8b31-57be-bec5-77dab4401720 | note | Acceptance / Conformance Criteria - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
a24bef18-ed19-5402-9911-8d0aa41611d7 | note | Standard / Specification - PS 15.11.7
44a3c1ca-2b3c-5bd8-bcd9-8166bc6a932f | note | Verifying Document - Survey Records
b240b2d4-ab96-5982-84a2-2fd25825db00 | note | Frequency - During Earthworks
f0563e63-58d2-5281-99f2-223329a109a7 | note | Verification Activity: Activity - D
0379ef52-f0a4-5de8-b838-16ad532332f7 | note | Verification Activity: By - SV
44d1c624-06c3-5e22-b6df-9c6af47c6102 | section | 6.02 Cutting and Subgrade
e2056d42-43d7-5262-8e7d-f3a1023524d6 | checkpoint | 6.02.01 - Cut slope inspections
f0c9e4d3-35fc-5484-b867-873378bcdcc6 | note | Acceptance / Conformance Criteria - Cut slope inspections will be required to allow inspection of the soils exposed and check for seepages. Inspection records are to include photographs, logged soils (to NZ Geotechnical Guidelines) and hand shear vane testing on fine grained soils. Results will be submitted to the Engineer.
a5050965-657c-5cb4-ba54-29f7a81a36c0 | note | Standard / Specification - PS 15.10.2, PS 15.13
0ca6644d-27bc-50cb-82c3-e9215beabdf8 | note | Verifying Document - Engineers Approval
ee095220-c54a-544f-8c85-d2e244c4a0fd | note | Frequency - Each Occurrence
6854b9e5-08d8-53bf-b4c4-25cc08b491a4 | note | Verification Activity: Activity - HP
3b8c7bd6-7173-5f1c-9873-a15adf5e3876 | note | Verification Activity: By - ENG
e91cf135-5c98-52a7-a54a-3c6af3be7601 | signoff | AUTHORITY HOLDPOINT
d2fbe478-ad1f-5048-8657-8f4e357aec4a | checkpoint | 6.02.02 - Dewatering
45ad7851-3863-514c-bd5d-d0013775f8f7 | note | Acceptance / Conformance Criteria - Trenches and excavations shall be dry at all times during construction works and a constant water level is to be maintained at 300mm below the base of the trench. No construction works may occur if there is any water in an excavation.
10bf3c53-35d3-54c6-aa6d-417ba63dc5da | note | Standard / Specification - PS 15.10.18
fbd2f8c6-64ab-5c47-af05-cb3418296a2c | note | Verifying Document - Site Records
bc3137ea-86db-5fc7-b231-fea3db637513 | note | Frequency - Ongoing
f642d9fb-44aa-5900-a964-19c664e82209 | note | Verification Activity: Activity - S
83904629-984d-510e-b1a8-050717dedc6a | note | Verification Activity: By - SE
0478f66f-1630-5596-ad8d-f38a4cc2b1c9 | checkpoint | 6.02.03 - Subgrade CBR Testing (Road and Embankment)
f3d10b4e-addd-5538-a957-2a37e0034faf | note | Acceptance / Conformance Criteria - The subgrade shall be tested for CBR via Shear Vane or Scala depending on site conditions. Testing to be undertaken to maximum 3m depth at 0.5m interval with hand auger holes required for test deeper than 900mm.
2ce0f2e8-1f40-5e35-8e0b-a78fd0b55a7b | note | This test shall be undertaken at the design subgrade level and at a depth of 300mm below the design subgrade level. Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material.
8b65a2ae-cac6-521a-a731-1c5b9ef6ea23 | note | ○ Shear Vane Average minimum su: > 60kpa
4ccae70e-9d5a-53e4-8f6b-a4e00f80f67e | note | ○ Shear Vane Single test minimum su: > 50kpa
3ff01897-8d7b-537a-9e0a-bdedcefe185a | note | ○ SCALA: Minimum 3 blows per 100mm penetration
630d469c-d4b6-528c-8e3d-4302c9510b53 | note | Standard / Specification - PS 15.10.4, PS 15.10.5 Appendix XIII
0c3bb1ce-aaf0-5272-9b8f-4d902e6bbc45 | note | Verifying Document - Shear Vane or Scala Report
85d3bae8-7bf8-56b3-9602-213fb78a5576 | note | Frequency - 4 test per 400M2
55a69f30-35b2-5c05-9282-92604524f101 | note | Verification Activity: Activity - I
8a1bfe00-8ce7-590a-a5cb-d9ae236fa6a6 | note | Verification Activity: By - SE
55b576e1-21ed-531a-aacd-d94250dc6129 | checkpoint | 6.02.04 - Undercut Subgrade Compaction
f841e758-4cd2-5891-b08c-751a3c88b535 | note | Acceptance / Conformance Criteria - The degree of compaction of each layer shall be such that when trimmed to a smooth surface, the resultant impression in the surface under a smooth wheel roller having a minimum loading of 6259kg per metre width of fill or equivalent as agreed by the Engineer, shall not be greater than 7 mm for bulk fill or 5mm for subgrade fill.
8fb02c88-5c79-5b58-a1dd-92a07552b833 | note | Standard / Specification - PS 15.10.4
a629293c-385f-5bce-b059-933f4c7d43dd | note | Verifying Document - Site Records
2a96cae7-3c6a-51cb-9454-6091224f2d6f | note | Frequency - Prior to Backfilling
4ff321f5-d0cb-5131-9bac-f2447b9cd5d8 | note | Verification Activity: Activity - S
9afabe93-cf7b-5ea2-9907-09925e3a24f2 | note | Verification Activity: By - SE
9bb70f82-94b7-566d-9ef1-4b61c37556a1 | checkpoint | 6.02.05 - Soft Road Subgrade Areas
6fd65fab-6193-5462-afeb-d69af1a8db96 | note | Acceptance / Conformance Criteria - Any soft area observed during rolling of the subgrade shall be referred to the Engineer.
d76e99d9-c656-55e3-acb1-1c1df46f6945 | note | Standard / Specification - PS 15.10.4
1be23212-e8df-5d9f-8313-9a5254ebe069 | note | Verifying Document - Notice
1c0d6418-f406-5f50-950c-5444425f50bf | note | Frequency - When Encountered
34656019-18b2-5fea-94d4-d598e2a8138a | note | Verification Activity: Activity - S
c035f040-40a1-576d-b193-c59e6a453dad | note | Verification Activity: By - SE
c3b7c71e-cfaa-5a96-a625-454bb0cc64fa | checkpoint | 6.02.07 - Finished Surfaces
9bec837e-b683-55ad-bd75-4a248c626262 | note | Acceptance / Conformance Criteria - The works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for Subgrade is 0 to -30mm before placing aggregate layers.
a6991efb-ab9a-5b99-bf23-cb2f8b77c50b | note | Standard / Specification - PS 15.6.8
be65fa83-a107-5342-9c6d-a54c8b435c69 | note | Verifying Document - Survey Records
887ad7d3-09f0-5edf-a3ba-45e2f89d1d67 | note | Frequency - Each Finished Surface
157d7177-0edf-5110-9131-f02c3d9f1433 | note | Verification Activity: Activity - D
1fe43a96-441d-52f3-9c61-b1ddff480ba2 | note | Verification Activity: By - SV
9149e6ff-1de8-5094-9b9f-ead6fee4ce61 | checkpoint | 6.02.08 - Subgrade Proof Roll and Foundation Inspection (Road and Embankment)
b64008e4-8e18-5171-b4ca-a72a0d91c282 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect the Foundation surface prior to Filling during the Proof Roll. No filling shall be undertaken until an inspection has been made and the Engineer has approved the cut and stripping of unsuitable materials. Visual Observation Across The Stripped Area Displacement < 15mm.
677d8b3a-9fe5-5e7f-9e11-0862609e0580 | note | Standard / Specification - Appendix XIII PS 15.13, PS 15.10.5
9841c2a6-be7e-500d-bcca-506f57b64c31 | note | Verifying Document - Engineers Approval
4e231911-13ab-5ecd-9b53-75b332d5bfb0 | note | Frequency - Prior to filling with 24h notice
c10bf413-07c4-5174-9e14-7c2fbcd9358d | note | Verification Activity: Activity - HP
950b4e24-66ad-5e1f-946a-4eebbe8609ed | note | Verification Activity: By - ENG
f05195d4-07ae-5bad-820d-5d958fa1f023 | signoff | AUTHORITY HOLDPOINT
cbfd5119-9511-5f05-a1a3-eb568e57c7a2 | section | 6.03 Filling General
6da130e7-ec1a-5eb6-b735-c0a7919ee1b0 | checkpoint | 6.03.01 - Compaction Trials
082af659-e5a1-5e55-bb14-86dcfa2c12cc | note | Acceptance / Conformance Criteria - The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (i.e. construction discs and scarifiers). The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements. The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial.
b932f253-0659-5483-8431-149e22a51f34 | note | Standard / Specification - PS 15.10.15
0ff16a2c-7e89-5fe7-97b9-0d0dc811e560 | note | Verifying Document - Trial Results
5fa74afb-d11f-58b9-9267-b51498af3937 | note | Frequency - During Works before placement of each material.
103d17fd-0df9-56e9-949a-dda4690eb715 | note | Verification Activity: Activity - R
66efe4f8-ef07-5b70-852c-a42dccaab6c1 | note | Verification Activity: By - PE
e6b0ff49-10c9-5967-b663-f2fc4e147aa3 | checkpoint | 6.03.04 - Geotextile on Undercut to Waste and Backfill
b66a3f7f-c101-55fc-a488-65023d32f225 | note | Acceptance / Conformance Criteria - Geotextile shall be laid across the undercut base and the sides and joints shall be overlapped to in accordance with the manufacturers specification to prevent squeezing of the underlying foundation.
39fe306a-53bb-58ff-84b4-d25744279b95 | note | Standard / Specification - PS 15.10.9
2215bfc9-484e-5f67-adce-6df3c540172a | note | Verifying Document - Site Records
2d33a3f7-a446-54bb-a02a-dbae2920cdbb | note | Frequency - Prior to Backfilling undercuts
8477f682-7f40-53b2-9c76-46de57fde771 | note | Verification Activity: Activity - R
f661c483-12d8-5268-8d41-625af8658963 | note | Verification Activity: By - SE
29370bd4-2ff3-5032-ac70-4629fb46ed01 | checkpoint | 6.03.06 - Weaving or Pumping
bd1991d0-5093-5804-aff8-c52b44e7385d | note | Acceptance / Conformance Criteria - Any weaving or pumping of the soil or subgrade during the compaction process is likely to indicate that either the water content is excessive or the material has been over-compacted. If weaving or pumping is observed, the Engineer should be contacted to advise the appropriate solution.
e605ba42-46c5-5a4e-888c-2477e598e0b8 | note | Standard / Specification - PS 15.10.16
d39f9c2c-ed77-5b28-9068-8d5502076351 | note | Verifying Document - Site Records
68e095e6-4a9f-530e-83a7-48b3803bce4c | note | Frequency - When encountered
27e7c1ea-82b6-5046-a56c-510159c3d998 | note | Verification Activity: Activity - S
ed838f5a-7bf1-5227-8006-76b8f7af37f3 | note | Verification Activity: By - SE
8121b3c2-5c62-5f8a-95d7-1511aca62833 | checkpoint | 6.03.07 - Finished Surfaces
3070b6ed-33d2-59d9-86fa-a87d75982015 | note | Acceptance / Conformance Criteria - The proposed works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for earthworks construction purposes shall be level +/25mm unless stated otherwise, Subgrade; 0 to -30mm before placing aggregate layers, Bulk fill ±100mm, Preload and surcharge ±100mm, Batter slope tolerance ±100mm
3c16fa38-3eaf-5ad1-9f22-07ba1a84a45f | note | Standard / Specification - PS 15.6.8
816b2da5-1e05-56ee-b0d4-f4dad76d85e7 | note | Verifying Document - Survey Records
41c5a73c-3d7a-5d08-99a6-a6c30a41296c | note | Frequency - Each Finished Surface
d8403246-e1a7-5f1e-a63f-c616a6f86317 | note | Verification Activity: Activity - D
6183135d-77a3-5020-94fc-7c8fb634a0f3 | note | Verification Activity: By - SV
28941e1a-7c86-5b6c-b4be-2bd9aa06435c | checkpoint | 6.03.08 - Final Trimmed Shape Inspection
929f9aa7-dcab-55ef-848e-e713dd5186b9 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect final trimmed shape prior to placing topsoil or track rolled fill.
a0d0e862-2504-55af-b439-f3f7356c1fcf | note | Standard / Specification - PS 15.13
51f6149e-c97b-5a09-af39-5267730b4dd8 | note | Verifying Document - Engineers Approval
1d64599f-c05f-5017-bfc2-421633c38bf0 | note | Frequency - Prior to placing topsoil or track rolled fill.
ec8638c9-6512-5db2-95d2-d6d3f35119b8 | note | Verification Activity: Activity - HP
72c74c91-2072-5a09-8013-ca846e10480a | note | Verification Activity: By - ENG
2fa4e556-dcd6-5d59-898c-5d69fcba5b07 | signoff | AUTHORITY HOLDPOINT
9009fa4f-63e9-5b9f-b8f5-3feccfd591cc | section | 6.04 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
25dd2c92-e278-54c8-aa60-59679d5bfb86 | checkpoint | 6.04.01 - Imported Structural Fill Layers
6878fdaf-0bcd-5db1-a513-1fc0df376bbf | note | Acceptance / Conformance Criteria - The material shall be placed and compacted in layers no greater than 300mm thick.
8b06cea0-2762-5a10-b343-8660f98e0189 | note | Standard / Specification - PS 15.10.14
1a89ef0a-9801-51bc-aee0-85e181a5627d | note | Verifying Document - Site Records
30797fec-d05d-5e1d-9407-2ca3ce812dbc | note | Frequency - Each Layer
e9f5e8d3-b7f2-5398-be87-1d5e695a0fb9 | note | Verification Activity: Activity - R
d72c325b-87d7-5b7a-abca-566cc22d1211 | note | Verification Activity: By - SE
7d79ea5d-74fb-5020-a7fc-15bc0d20fe88 | checkpoint | 6.04.03 - Structural Fill Zone - Strength – Clegg Impact Value (CIV)
33972346-eaf4-5b1b-adab-39ff4c57e4e4 | note | Acceptance / Conformance Criteria - A1 Imported Structural Fill Strength shall be tested by Clegg Hammer every 200m3 per area per day per lift
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Minimum CIV = 18
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Average CIV= 20
b21d6bc2-fa63-5bc1-8d96-b05121b299af | note | Standard / Specification - Appendix XIII
9e78cce7-cd0a-5ffe-b4f7-52f1a5f40ad1 | note | Verifying Document - Clegg Results
edfa4ec3-1fcc-5df9-ba9c-81716eabe644 | note | Frequency - 1 Set (5 Tests – 5x5m Square Grid) Per 200m3 Of Placed Per Area Worked Of Day Per Lift
c952f64f-f2ef-5aeb-b6b7-5b247ddc0cdb | note | Verification Activity: Activity - I
e91737f2-9daa-590c-ba83-c4825556312f | note | Verification Activity: By - SE
cff2e2af-607b-551c-bbeb-3ae8301207cb | note | Comments / Closeout Details - Are both NDMs and Clegg Required
e7febe44-92c4-5796-b0f2-b82320d4484e | checkpoint | 6.04.05 - Structural Fill Zone Insitu Density Insitu Compacted Dry Density Insitu Water Content
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - A1 Structural Fill Compaction shall be tested by NDM in Backscatter Mode every 200m3 per area per day per lift
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | ○ Average >95% Of In-Situ MDD
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | ○ Minimum >92% Of In-Situ MDD
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Standard / Specification - Appendix XIII
69d85f65-b61d-579d-940f-2b691894d755 | note | Verifying Document - NDM Results
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
e2147c12-4568-5322-b418-283ae63070af | note | Verification Activity: Activity - I
09a8aad4-3fc9-597d-b419-c865f36b4acc | note | Verification Activity: By - SE
e446d0a3-f492-586c-ab52-5751ac56d10a | note | Comments / Closeout Details - Are both NDMs and Clegg Required
b9a8462b-715b-5c2d-8c25-e4f73254a4ca | checkpoint | 6.04.06 - Solid Density
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - The Solid Density Of Aggregate Particles shall be tested by collecting 1 sample with every set of NDMS completed (1 Test Per 200m3 For That Material Type And Source). Test Results Provide Input To Acceptance Criteria For Insitu Compacted Dry Density Determined By Nuclear Moisture Density Gauge (NDM)
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - Appendix XIII
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Solid Density Lab Report
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - 1 Set (5 Tests) Per Material Type And Source Then 1 Test Per 200m3 For That Material Type And Source
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
5ec91113-ac87-53de-b900-bcb9253aa488 | note | Comments / Closeout Details - Are both NDMs and Clegg Required
504915a0-29d1-5b8a-891c-a7b613638c3c | checkpoint | 6.04.07 - Organic Content
f09d0ff0-01ec-50cb-9988-3a078371cb3d | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
5d4c6d19-d8fb-5765-9b80-10ed32dbffe9 | note | Standard / Specification - Appendix XIII
ea12d870-db9e-5048-94de-56f316678975 | note | Verifying Document - Site Records
4b4f2a35-1e50-5341-80c6-541a73664b53 | note | Frequency - Ongoing
f77c9bbc-fb8f-5e0f-86c9-c66a4643254e | note | Verification Activity: Activity - I
dbb35f07-7f2f-5414-a8b4-c69adbcef37c | note | Verification Activity: By - SE
f910ed7f-8370-57c8-b1bd-2fb721606286 | checkpoint | 6.04.08 - Completed Fill Approval
cb670aff-3430-5d2c-ac3e-1482548f09ee | note | Acceptance / Conformance Criteria - Prior to pavement construction the Engineer shall complete a Desktop review of all structural fill compaction testing for acceptance.
e3ea5880-55a7-54a4-9ee9-9323b972ab79 | note | Standard / Specification - PS 15.13
eb4e4dcc-9679-50a0-8275-a70670f63fd0 | note | Verifying Document - Engineer Approval
5b1465a0-9c5b-51b0-8b4b-9694e85f2324 | note | Frequency - Prior to Pavement Construction
a3b40c94-fe59-5b33-bcda-878d287d2995 | note | Verification Activity: Activity - HP
696e1611-579b-5ae6-b3d8-5701063db1b8 | note | Verification Activity: By - ENG
5e0c2555-3e93-5160-beb9-af9efce873aa | signoff | AUTHORITY HOLDPOINT
faf4f3a3-1299-5382-bb2c-73748ed0cb2e | section | 6.05 LANDSCAPE FILL
a57c22bd-882b-5e15-98f1-6cc1024a010c | checkpoint | 6.05.01 - Cohesive Fill Layers
c352122b-b969-515a-bd14-4ee2d6d77a2c | note | Acceptance / Conformance Criteria - Cohesive structural and non-structural fill material, shall generally be compacted in layers of less than 200mm thickness. All fill surfaces shall be sealed at the end of each day’s work.
eb2c9836-d46b-5735-a171-5b7c260a8373 | note | Standard / Specification - PS 15.10.16
16c87f21-2b6f-5a9e-950f-ce52726911a4 | note | Verifying Document - Site Records
f997564b-0a06-59cc-aaf8-0d04c169bb65 | note | Frequency - Each Layer
48daa9bc-dbe2-5457-aa35-ebb3d2f05eee | note | Verification Activity: Activity - R
a63751f3-0140-5d7c-80c1-864752f123ce | note | Verification Activity: By - SE
91ea3ae5-4753-56e1-b28d-0d3a3fb40e12 | checkpoint | 6.05.02 - Fill surfaces Sealing
a578d34e-40e1-5c0c-b225-25282dfa3822 | note | Acceptance / Conformance Criteria - All fill surfaces shall be sealed at the end of each day’s work.
275dad26-4948-57bc-bc5d-25291c4dfe04 | note | Standard / Specification - PS 15.10.16
bf910f9a-c5f9-5501-bd00-480e205a15ef | note | Verifying Document - Site Records
cd655ab2-4234-580a-b1d2-e5f8d0f9c64b | note | Frequency - Each Day
5b4f0479-5692-504d-98b2-93cf71280de9 | note | Verification Activity: Activity - R
a00280e8-d9ac-5f5e-86c0-a351a10dc28a | note | Verification Activity: By - SE
e9f6dd3e-48b2-53bf-8c70-05c59c2b86d9 | checkpoint | 6.05.03 - Non-Structural Fill - Air Voids
8e28b866-fa38-519b-918f-3d14bb22ecfb | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill compaction (Air Voids) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift.
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Average Maximum Air Voids < 8%
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Single Test Maximum Air Voids< 10%
b6a6dfee-f164-5998-9bdb-0af48b5f824e | note | Standard / Specification - Appendix XIII
bebdea1e-dece-5fe9-9b48-a107125b16b9 | note | Verifying Document - NDM Results
e003f7a2-352b-5d80-9fd5-e44eddfe06fe | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
3f5e0ef0-3697-5f92-8b8c-ec24df3f2e89 | note | Verification Activity: Activity - R
da65e1bd-770b-59ad-9793-ebeab9e626dd | note | Verification Activity: By - SE
2254b6f8-ca87-5831-8381-537164057ab6 | checkpoint | 6.05.04 - Non-structural Fill – Shear Strength (SU)
9edd37d7-9376-551e-84f9-b888b8840c61 | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill Strength shall be tested by hand held Shear Vane or Scala every 500m3 per area per day per lift of fill placed.
5b2f902a-75e1-52ba-831a-286d435423d5 | note | ○ Average Minimum Su > 60kPa
0d47f6a9-9a9c-5830-a715-20e29444a71c | note | ○ Single Test Minimum Su > 50kPa
cd8cbc5d-5199-51fe-8b4d-b38294c9026a | note | ○ Scala: Minimum 2 Blow Per 100mm up to 1.0m deep
f92cde20-aba2-55da-8996-95fb4f00d9cf | note | ○ Shear vanes and scala's not applicable where cohesive soils are mixed with granular material
3987cf23-05e1-5604-91fa-7c85db88248f | note | Standard / Specification - Appendix XIII
7cd5ddd4-8c1e-52f1-aeba-5f314cce96f9 | note | Verifying Document - Shear Vane or Scala Results
6c04cc44-a270-5c2c-903f-8ca50b667f73 | note | Frequency - 1 Set (5 Test) Per 500m3 Of Fill Placed Per Area Worked Per Day Per Lift
031b41c8-0684-5bd5-9692-1238e6978165 | note | Verification Activity: Activity - I
2f45e865-55b9-5d5f-94f9-2cda2e27e330 | note | Verification Activity: By - SE
67d2cb19-a2ab-56fe-9362-2a11a6148fa9 | checkpoint | 6.05.05 - Non-Structural Fill - MDD
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - Non-Cohesive Non-Structural Fill compaction (Dry Density) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift. 90% Minimum Dry Density (MDD).
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | Standard / Specification - Appendix XIII
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | Verifying Document - NDM Results
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
69d85f65-b61d-579d-940f-2b691894d755 | note | Verification Activity: Activity - I
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Verification Activity: By - SE
940c74e2-d6b4-59ce-a549-e065a128c6e6 | checkpoint | 6.05.06 - Non-Structural Fill - Granular Mixed Materials
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - Mixed non-structural material requires proof roll to ensure compliance with the 7mm requirement. Proof roll to be done where soils cannot be penetrated via shear vanes or scala
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - TNZ F1 Section 10.5.1
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Site Records
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - Formation level
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
c83c1a95-6cc3-5b55-ac8c-57dd36cf1a2e | checkpoint | 6.05.07 - Organic Content
f09d0ff0-01ec-50cb-9988-3a078371cb3d | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
5d4c6d19-d8fb-5765-9b80-10ed32dbffe9 | note | Standard / Specification - Appendix XIII
ea12d870-db9e-5048-94de-56f316678975 | note | Verifying Document - Site Records
4b4f2a35-1e50-5341-80c6-541a73664b53 | note | Frequency - Ongoing
f77c9bbc-fb8f-5e0f-86c9-c66a4643254e | note | Verification Activity: Activity - I
dbb35f07-7f2f-5414-a8b4-c69adbcef37c | note | Verification Activity: By - SE
8a6e4423-2a66-5b93-af2a-67e156f07a85 | checkpoint | 6.05.08 - Water content
cb670aff-3430-5d2c-ac3e-1482548f09ee | note | Acceptance / Conformance Criteria - The water content shall be tested by collecting 1 sample with every individual NDM test.
e3ea5880-55a7-54a4-9ee9-9323b972ab79 | note | Standard / Specification - Appendix XIII
eb4e4dcc-9679-50a0-8275-a70670f63fd0 | note | Verifying Document - Water Report
5b1465a0-9c5b-51b0-8b4b-9694e85f2324 | note | Frequency - Every NDM
a3b40c94-fe59-5b33-bcda-878d287d2995 | note | Verification Activity: Activity - I
696e1611-579b-5ae6-b3d8-5701063db1b8 | note | Verification Activity: By - SE
94ecb72f-b511-5fef-99c9-b75caaae5292 | checkpoint | 6.05.09 - Bulk Density, Dry Density, Air Voids
2ff13b7b-02c2-5a7b-8118-f41c41b17271 | note | Acceptance / Conformance Criteria - The Bulk Density, Dry Density, Air Voids shall be tested by collecting 1 sample (Sample Tube) for every 10 NDM Sets completed.
c39051d9-945b-528b-a585-33d79297aaee | note | Standard / Specification - Appendix XIII
dd793333-b4d3-5ea8-9644-25cf03ccc6e5 | note | Verifying Document - Lab Report
d69a3d8f-c798-532b-a15c-6f7e4df14e4c | note | Frequency - 1 Test Performed For Every 10 NDM Test Results Provide
2d5640eb-932b-5ba9-87eb-2c7ce14f8894 | note | Verification Activity: Activity - I
c9a19186-767d-535f-9741-6cc10a171f11 | note | Verification Activity: By - SE
a3350b27-5c47-5b3b-ab57-f9e96424a1da | section | 6.06 Settlement Monitoring
5e695847-04f1-541c-9e60-5f3ce9021c7d | checkpoint | 6.06.01 - Settlement Monitoring Methodology
55cd879c-55fc-5cf6-ac3c-be63cb59295d | note | Acceptance / Conformance Criteria - The Contractor shall submit details of their proposed monitoring equipment and installation methodology within their Earthworks Management Plan for the Engineer’s Approval.
e81a1f0f-e781-525e-8c33-4e23315d1115 | note | Standard / Specification - PS 15.12.5
3d5ed6b8-8e4c-545a-9b90-7b60919dd913 | note | Verifying Document - Approved EMP
ef9455b2-30f0-545d-a18d-d1e03ec6a2d5 | note | Frequency - Prior to Works
bbd43815-e554-5e0c-8e5b-3ca67662ee30 | note | Verification Activity: Activity - HP
258d068c-dd4d-5efc-a8bb-531c5d1e9410 | note | Verification Activity: By - ENG
5d1819d4-2a89-5c6a-acb4-52c8ae9493b0 | signoff | AUTHORITY HOLDPOINT
1309e638-c7ad-5317-82c8-377f0218a22a | checkpoint | 6.06.02 - Supply, Install, Survey and Remove and Monitoring Equipment
f3fece7f-2a75-51d9-ab8c-3818abf85f3f | note | Acceptance / Conformance Criteria - The Contractor shall install geotechnical instrument systems in the positions shown in the Contract Drawings unless otherwise instructed by the Engineer.
f5b4da39-18a7-50fa-81bb-119512aa3245 | note | Standard / Specification - PS 15.12
f2f8a813-1fd2-5f2e-8fb2-868eac6068eb | note | Verifying Document - Site Records
51df963b-9897-5abb-94e9-92f9a247955d | note | Frequency - Prior to Construction
68391c45-455a-5051-9344-65d8f1c811eb | note | Verification Activity: Activity - I
160f22c6-6304-5fea-b1ab-230125cb63ef | note | Verification Activity: By - SV
0f533e6c-1bd1-57a4-a4c0-c28f362a9a0c | checkpoint | 6.06.03 - Instrument Reading Notice
6f87da36-7041-5714-aab1-a9d1a3d4eb69 | note | Acceptance / Conformance Criteria - The Contractor shall inform the Engineer two days in advance of planned instrument readings so that the Engineer may observe the work.
e3bc3f60-11df-5986-8e49-8f95bf3b526c | note | Standard / Specification - PS 15.12.5
d1a19be7-e1d3-5547-8909-138345432d0b | note | Verifying Document - Site Records
1f9dbbe2-04ff-5485-ae11-50ba7690ec6a | note | Frequency - Prior to Survey
fe3add51-08eb-5bf7-8e2f-9257106320fe | note | Verification Activity: Activity - HP
78d1467f-a870-5168-8aca-e0fc839d8ecc | note | Verification Activity: By - ENG
f2f84277-75de-5c7e-be35-eeeb68a3e8a9 | signoff | AUTHORITY HOLDPOINT
2517047e-845e-5644-ae2e-510b4502a782 | checkpoint | 6.06.04 - Base Readings, Responsibility and Ownership
26de447a-be80-5db7-9fed-a5598df339e2 | note | Acceptance / Conformance Criteria - Following installation, the Contractor shall undertake testing to demonstrate the instruments are working properly. The Contractor shall submit records of each of the instruments showing location, soil conditions encountered, installation details and initial readings. Construction will not be permitted until the Engineer is satisfied that the instruments are working correctly.
3dac7c57-2fd9-5583-b22e-1c9daad809d8 | note | Standard / Specification - PS 15.12.2
57fbadc8-856e-59ea-9c0b-6a4ad79abd98 | note | Verifying Document - Site Records
887d2697-0438-5748-9d92-50071d9dcfaf | note | Frequency - Prior to Construction
172ad8cb-f559-5105-bb7d-9fce0c280ca5 | note | Verification Activity: Activity - HP
e13218bd-7f4d-5ce9-9578-5fc34d2a157d | note | Verification Activity: By - ENG
b68c1eb5-b89f-5102-ab04-0d343f0c2bc8 | signoff | AUTHORITY HOLDPOINT
012ae06c-51f7-539e-99db-22dc8857a1af | checkpoint | 6.06.05 - Pin Protection
05377e32-4d4d-5ac9-85e7-88b011824a6c | note | Acceptance / Conformance Criteria - The Contractor shall ensure the Pins are protected and not disturbed in any way once constructed. The Contractor shall also install settlement survey stations at locations protected from Construction traffic and works.
5d18b3db-6402-5696-83e5-db181b003227 | note | Standard / Specification - PS 15.12.5
05cd1b8f-838a-5ded-9ab1-8a0bccdc8b88 | note | Verifying Document - Site Records
89614663-9ee1-5f54-80d8-09f62996a296 | note | Frequency - Ongoing
96cac559-a2d0-5e18-bd1c-8c5f91f83364 | note | Verification Activity: Activity - R
3f8e7bef-6f86-5244-b41d-7c1991bd3106 | note | Verification Activity: By - PE
d71f530d-3a2d-502a-85c4-0e6cfd071bfd | checkpoint | 6.06.06 - Monitoring
1d838e30-c9ec-58bc-8841-43d057802429 | note | Acceptance / Conformance Criteria - Following the active fill of the embankment, the Contractor shall read all monitoring pins bi weekly. Monitoring frequency may be reduced to weekly intervals when there is no active earthworks in that area, and while waiting for embankment to settle.
ab916766-b8ca-5614-a3be-61f3ef5ce0a5 | note | Standard / Specification - PS 15.12.5
5a8987e1-beb5-5285-9626-14c6d4b752e3 | note | Verifying Document - Survey Records
6fa587b6-07fd-53aa-b98e-c9e5af40fc7a | note | Frequency - Bi Weekly following Embankment Filling
a7929d20-4291-5176-920f-7926ba3c34af | note | Verification Activity: Activity - R
c2010ee4-fd12-508a-ae38-dccfae200836 | note | Verification Activity: By - SV
a623e6c5-b632-5bb4-bb24-cba69e701574 | checkpoint | 6.06.07 - Engineers Review
d77b11fc-070b-50e1-8629-958659ff4f44 | note | Acceptance / Conformance Criteria - The Engineer will review the results of the settlement monitoring to assess completion of the preconsolidation period. This period is anticipated to be less than 3 months.
cf3d110b-7081-5043-99cf-c1c5e1e82116 | note | Standard / Specification - PS 15.12.5
88313476-05c6-574c-be37-84b542b7c1ff | note | Verifying Document - Survey Records
aba9f8b6-25d1-5e33-9124-ff7cef034c4a | note | Frequency - Ongoing
53867a85-e95a-5618-87e7-f9eec85edf34 | note | Verification Activity: Activity - R
49b6db7c-780d-5c5a-b85b-ffd17e3d8432 | note | Verification Activity: By - SV
c0a27a5d-8b1f-50f5-b01d-a262601e207d | checkpoint | 6.06.08 - Pore Water Dissipation
75ceb013-f0cb-5b7e-af80-af6640b2d53d | note | Acceptance / Conformance Criteria - Review of settlement pins data to confirm sufficient pore water dissipation has occurred in the soft soil layer.
1e5ba5db-1e50-52e5-a141-a55015b8ec11 | note | Standard / Specification - PS 15.13
6d539e72-2e15-54ff-a874-531eefc30c8a | note | Verifying Document - Engineers Approval
bde27891-0f79-54b4-bce1-6e40158e43bd | note | Frequency - Prior to completing Monitoring
1f4973ca-c9c2-5289-b401-f542f7e282e3 | note | Verification Activity: Activity - HP
c3e2a4d3-85b0-50f8-aab3-5c691c2e24f6 | note | Verification Activity: By - ENG
2e34f781-af18-50d3-a840-a001fb34c51d | signoff | AUTHORITY HOLDPOINT
89b1bcee-a704-5892-9410-e9311d5e0992 | checkpoint | 6.06.09 - Settlement Monitoring Termination
f89d107c-7f62-5edf-ba7c-a0e330bfb041 | note | Acceptance / Conformance Criteria - The criteria for terminating the embankment preload are either: Three consecutive measurements indicating the t90 settlement value has been achieved, A rate of settlement less than 10% of the maximum rate measured immediately after the fill was completed. The settlement readings shall be evaluated by the Engineer to assess the need to extend the monitoring.
2d0e1d42-bc4c-5ffc-a6ec-30a5d4d6670d | note | Standard / Specification - PS 15.12.7, PS 15.13
95432c0f-587e-557b-a06a-d2c1de6b3656 | note | Verifying Document - Engineers Approval
e1dd00fe-0aed-5bbc-9759-328a6cb6ca36 | note | Frequency - Prior to completing Monitoring
f1a09b53-7a5d-50a9-8933-50232be4a599 | note | Verification Activity: Activity - HP
adfba00d-f5d8-5f2d-a739-d023b0e4a01c | note | Verification Activity: By - ENG
de792686-1074-5b19-8609-1cce7f903454 | signoff | AUTHORITY HOLDPOINT
997a50a6-df3e-5573-a989-a8a7b88ce2c5 | checklist | Ω (DEPRECATED) ITP - Earthworks - 101 - Rev 2 - v3 | itp | ITP - Earthworks - 101 - Rev 2
ac5ee1ee-5139-57b0-9c55-3196b7da263c | section | 3.01 General
4b182364-c9b8-5807-85b4-26cb6c506fc7 | checkpoint | 3.01.01 - Precondition Surveys
69cd2420-d366-54eb-958b-47ee6ba30c3b | note | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
8a300e3e-8b0d-50e1-92a8-acacc9470272 | note | Standard / Specification - PS 2.13
4012ae1e-5742-5bb3-bd88-9891dd0da569 | note | Verifying Document - Precondition Survey
5ee54bf7-4881-50be-9cbd-b6ca24fbed29 | note | Frequency - Prior to the Contractor taking possession of the Site.
4ee5ad50-8a49-5ef9-b2ce-6829404da63e | note | Verification Activity: Activity - H
042a86d8-9388-5bf2-bc39-fae98a19ea53 | note | Verification Activity: By - PM
2c4b8fd4-5150-5656-bda8-48bbc0f299cc | section | 4.01 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
eec51e33-e195-5fd4-8848-2a84896576bc | checkpoint | 4.01.01 - Source Property Tests and Sampling
c970b435-1a5a-5b52-9c63-6d3dc47a7b24 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, Los Angeles Abrasion, and Soaked CBR at least 2 weeks prior to importing to the site.
5fddf01b-636b-5c1b-9e0f-f9d479c784a9 | note | Standard / Specification - PS 15.7.3 Appendix XIII
c05f86e5-078b-56d0-a84d-743d12ed7c80 | note | Verifying Document - IANZ Lab Reports
0d61936a-619a-5486-b002-fd3bb8ecd191 | note | Frequency - 2 Test Per Material Per Source at least 2 weeks prior to importing to the site.
6c36e154-7375-5049-8d17-38c7ea3fb8aa | note | Verification Activity: Activity - HP
3ce79e68-2cd7-57fc-8b23-187278275664 | note | Verification Activity: By - ENG
943c57a3-9718-5eec-a0c4-4f254ca57b92 | signoff | AUTHORITY HOLDPOINT
e74ba8eb-c7ac-51ca-806d-ce6b2d151d6f | checkpoint | 4.01.02 - Testing for Layer Compaction - MDD
0eea5d39-c7a9-597e-95e8-2d3aa0eb79ce | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Heavy Compaction), Optimum Water Content, Air Voids, and Shear Vane Strength (Su) with Range of Moisture Contents.
3a7cfff1-f254-5419-911c-e86cf81791ad | note | Standard / Specification - PS 15.7.3 Appendix XIII PS 15.13
bac60110-709f-58ca-825f-eef1d568b6fe | note | Verifying Document - IANZ Lab Reports
28d0819b-7509-50e5-aaad-6484fe8c56af | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
93ed1431-f321-5f8b-8125-d991cf43a90b | note | Verification Activity: Activity - HP
5eecf011-989a-5420-a82b-eb0149a57904 | note | Verification Activity: By - ENG
1ad45696-b06f-57ba-991f-876ec2469f8a | signoff | AUTHORITY HOLDPOINT
cc28f368-5ec3-56d4-92e5-eeccc9eacb38 | checkpoint | 4.01.03 - Production Property Test Sampling
6c461bdf-e882-525f-a094-2bcc190ce2e7 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD).
4c2ef108-068a-59d0-b3de-60b2a95c6c7f | note | Standard / Specification - PS 15.7.3 Appendix XIII
6a814afb-0be7-53e5-8592-2862e1a765fd | note | Verifying Document - IANZ Lab Reports
efce84d9-b1b2-5d89-991c-9da04e5ba923 | note | Frequency - 0-400 M3 – 2 Tests
f89666dd-0f56-5b39-b7d2-2694b08c1b13 | note | ○ 400-1,500M3 – 3 Tests
ed92ad50-6f20-5df3-bdee-ddfd8f5eb73d | note | ○ 1,500-4,000M3 – 4 Tests
8473fabf-bde7-5cc9-8e93-e31e0d9d300b | note | ○ >4,000M3 - 1 Test For Each Additional 10,000M3
fd98181f-7bd9-5f53-8201-bb0c6813a688 | note | Verification Activity: Activity - H
29935793-de84-5fc9-9e9a-dc726b88856e | note | Verification Activity: By - PE
d3197014-3f06-5fe0-b1d9-aea439b97c54 | section | 4.04 Type A3 (Site Won Landscaping Fill)
bd572b98-794b-572a-b262-0d8895c651db | checkpoint | 4.04.01 - On Site track-able Testing
8fefcbaf-cb68-5917-9433-3d41137b8e4e | note | Acceptance / Conformance Criteria - Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it is ‘track-able’ by the contractor’s plant. This shall be determined before Sampling.
b4914206-8d0b-5414-9502-17ae4fad6e1c | note | Standard / Specification - PS 15.7.3
e51abaca-32b0-57d1-8544-f906b25a9fc0 | note | Verifying Document - Visual Site Record
aaf6e6a1-d9e9-5a27-86da-31e404a8a62d | note | Frequency - Prior to Sampling
d4f5a2c3-8d72-5a12-84a0-52e374ec9d02 | note | Verification Activity: Activity - W
21e39c46-937e-5756-bf3a-0fa20897c108 | note | Verification Activity: By - PE
bbfc5154-bf5f-5edf-b862-ca5b40d3d743 | checkpoint | 4.04.02 - Testing for Layer Compaction - MDD
da4431ef-f91b-5faf-a07f-ebe5b3ed0ce8 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Standard Compaction), Optimum Water Content, and Shear Vane Strength (Su) with Range of Moisture Contents.
75366e9f-f170-5da4-8e90-2ba29431f456 | note | Standard / Specification - PS 15.7.3, PS 15.13
01c254a6-d804-5850-b1b7-daee29774ece | note | Verifying Document - IANZ Lab Reports
cd00113d-ee85-5286-956b-580960ae86ae | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
9895d0dc-5a1e-556b-b3a4-f60bb935b694 | note | Verification Activity: Activity - HP
803e0adb-6908-539d-91c5-5f291f829291 | note | Verification Activity: By - ENG
787da1d7-76e7-5318-90fc-d7c5b66f0772 | signoff | AUTHORITY HOLDPOINT
1b403918-b691-5bde-88b7-f3ee9e087117 | checkpoint | 4.04.03 - Insitu Property Test Sampling
b2e3a0b7-200b-54bc-8753-e33bdade2178 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD) and inspected for deleterious materials such as boulder size fragments and organic materials.
da342694-bd84-565c-b303-933f704abeb3 | note | Standard / Specification - PS 15.7.3
3f8b0f56-e239-5878-82f3-25bd301b0188 | note | Verifying Document - IANZ Lab Reports
54187772-fb0a-5304-b22d-e6fef5571033 | note | Frequency - Prior to use
5f2c876f-b40e-5944-91db-1b5c4f101bfd | note | Verification Activity: Activity - HP
10ebcf48-ad4b-5c4f-ac90-4d24da87969d | note | Verification Activity: By - ENG
f4da45cc-ae32-586a-82a0-8191c8cf5c37 | signoff | AUTHORITY HOLDPOINT
540a5e70-44a2-557d-9a5c-b23f9eba4a3f | section | 4.05 Topsoil
20c79c91-2f0b-5e64-bc79-4fc755ec0ddc | checkpoint | 4.05.01 - Topsoil
c48a7814-415e-5bf0-90db-a1b8443b9fdd | note | Acceptance / Conformance Criteria - Topsoil is defined as the layer of material immediately below the ground surface comprising vegetation, tree roots, other non-decomposed organic matter, turf and humus. The Contractor is to stockpile and utilise site won topsoil for placement on the final batter slopes and for borrow site reinstatement as shown in the Contract Drawings.
e65a11a1-9f5f-5b9b-b31a-005bf9a0f5ad | note | Standard / Specification - PS 15.7.3
cf04a554-dfc6-58b4-9613-62ac16fdabb9 | note | Verifying Document - Site Record
ee11df60-1ce5-585b-8998-69594136d238 | note | Frequency - During Stripping
e137dc49-6b12-5bed-ab75-30d89abce352 | note | Verification Activity: Activity - I
11dd70c8-b8f1-5205-a62a-89a0d37a59b0 | note | Verification Activity: By - SE
d75e34e2-526e-508b-9139-1c41f905aee4 | section | 4.06 Geotextiles
94c5cd81-4c09-5866-a780-a6cb2b294715 | checkpoint | 4.06.01 - Geotextile on Undercut to Waste and Backfill
01a812e1-2a2b-5d7f-a9f9-4d80c94b831d | note | Acceptance / Conformance Criteria - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation.
c17089c8-cde6-5780-af0b-4d44cfe037e4 | note | Standard / Specification - PS 15.10.9
3752352a-df5a-53b2-8094-118f73546c7d | note | Verifying Document - Datasheet
8e7145b3-d717-57d4-8b68-f84837bcbada | note | Frequency - Prior to use
6f3350cc-a5e3-5922-90ec-ceba1cff1e25 | note | Verification Activity: Activity - R
ffc1a14f-5946-57d0-b15d-4eb1e2f5b1a3 | note | Verification Activity: By - SE
00122e61-34f7-53d5-a67f-e0c09f6146f3 | section | 5.01 Site Clearance
aa56f8f4-2f1d-53a7-90e0-bf9bff008cd2 | checkpoint | 5.01.01 - Site Clearance
76735cd9-4858-55a6-aa06-101f02518612 | note | Acceptance / Conformance Criteria - All trees, scrub, non-lawn vegetation and/or self-sown plants within the extent of the earthworks shall be removed to waste in accordance with Clause 3 and Clause 9.4 of TNZ F/1:1997 Specification for Earthworks Construction.
e2b43d2f-4215-5670-89ab-c3b1d39d5dd5 | note | Standard / Specification - PS 14.1.1 NZTA F/1 - 3
f35896e9-18bd-51fb-84bd-a516fea07908 | note | Verifying Document - Site Record
1c9aecd5-6527-5a3f-90f9-fb46fb1152c3 | note | Frequency - Prior to excavation
553d21dc-d656-5d11-a678-49e9091a7776 | note | Verification Activity: Activity - I
b8ac2dc9-f39d-5a4c-88d0-92ffc13d346b | note | Verification Activity: By - SE
0434188f-64e5-5961-b752-f68ed0678033 | checkpoint | 5.01.02 - Dump Site Approval
165908c4-435f-5b36-8fd9-df3fab4ecdd9 | note | Acceptance / Conformance Criteria - The locations of dump areas shall be agreed by the Engineer before use.
e22c6756-65e9-50b5-b8f9-e78161c44d04 | note | Standard / Specification - NZTA F/1 - 9.4
55d5c387-b48b-5e7f-9757-2749a36ece54 | note | Verifying Document - Site Record
f84ff3ba-d111-577e-814d-2f3b3ff0c62e | note | Frequency - Prior to Stockpiling
73737f8f-3ed5-5230-a5fa-7d12fd1ac08c | note | Verification Activity: Activity - HP
74ce0d35-f379-5262-b7f4-46543d42148d | note | Verification Activity: By - ENG
c082bbf0-64bb-5295-803d-efd5e36c07d2 | signoff | AUTHORITY HOLDPOINT
97e973d9-e87b-5abc-b883-a17a57730683 | checkpoint | 5.01.03 - Mulching
7c25105e-22ed-5c83-8240-5f58fa89da29 | note | Acceptance / Conformance Criteria - Where possible, cleared vegetation shall be mulched and stockpiled at a suitable site for future landscaping work.
39aa4f4e-e9d4-5b72-a53a-4a01c43363d6 | note | Standard / Specification - PS 14.1.1
54411dec-bc57-5533-afb7-0f38308d0bf6 | note | Verifying Document - Site Record
d3575c48-3185-5f98-b1fe-4784265e23ac | note | Frequency - During Clearing
449c8392-36d0-5a80-8ce1-30049ce1eaa6 | note | Verification Activity: Activity - R
07fddfa0-d1c0-5767-bf10-aa4ad5673f63 | note | Verification Activity: By - SE
4f7cfdbd-f8a4-5f17-a5dd-b36d0cb99ded | section | 6.01 General Earthworks
7b7266d6-ecf8-561a-b4ca-7b37880265fd | checkpoint | 6.01.01 - Earthworks Methodology
c228e36c-639a-5d64-84a6-17b814e6f41b | note | Acceptance / Conformance Criteria - The Contractor shall submit the construction and QA methodology for each element of Earthworks including construction, Haul roads, Site Access, dewatering, Wet weather, testing, inspection, and hold points for review and approval prior to works.
0b682de4-c8ae-51d1-9923-ecbfc85690dd | note | Standard / Specification - PS 15.13, PS 15.6.2, PS 15.10.13
b50a3242-4781-56d2-9c29-2bfa07bedacd | note | Verifying Document - Approved Methodology
9b77a527-c1c2-52d4-bf08-2baf8fe48a93 | note | Frequency - Prior to Earthworks
00c15935-b738-5367-8878-db856c582b87 | note | Verification Activity: Activity - HP
2e554e60-d952-5dd6-861b-a558370ee856 | note | Verification Activity: By - ENG
326a5f19-66e6-52e8-8259-accb86134d3f | signoff | AUTHORITY HOLDPOINT
ce70eb24-ffd6-534e-9bc3-84ccc496c6db | checkpoint | 6.01.02 - Temporary Excavation Approval
8b4c1814-1483-57a0-a93e-7cf0f5129205 | note | Acceptance / Conformance Criteria - The Contractor shall submit Temporary Excavations details to the engineer for approval prior to excavation.
33ca796d-57e5-58de-b34f-c32e6163735c | note | Standard / Specification - PS 15.13
c6d3b217-5879-5d04-b9ab-a032084546f6 | note | Verifying Document - Engineers Approval
de2c1bd3-ac7a-562d-817a-3f4a0bb05767 | note | Frequency - Prior to Excavation.
cd18a545-923b-5871-b92c-dee9402f4e29 | note | Verification Activity: Activity - HP
b2515f22-7df2-58c2-ac65-fe920a60c040 | note | Verification Activity: By - ENG
7f24d1ae-eaea-5164-a39d-b9602a701e03 | signoff | AUTHORITY HOLDPOINT
7be180f9-b731-51bf-aa2a-2646cc8a1c69 | checkpoint | 6.01.03 - Temporary Works Design
6bf13ae3-7a65-50e5-8ee5-356f37e5f99f | note | Acceptance / Conformance Criteria - The Contractor shall submit the temporary works design for Review and approval of prior to excavation.
34321cd1-593b-53a3-963f-41929191a96b | note | Standard / Specification - PS 15.13
725dbc6f-43b7-58dd-b840-2a9e1cc7a0a5 | note | Verifying Document - Approved Design
e4fec50b-b4eb-5cfa-bc23-b5a1182bdb5c | note | Frequency - Prior to Excavation.
2ac192cb-bf2e-52c2-b62a-50c4c4697492 | note | Verification Activity: Activity - HP
e421222d-e59e-5ba2-9fce-d91b87b2c1cd | note | Verification Activity: By - ENG
bd223daf-c7ae-5c7b-b6da-6f123e740f86 | signoff | AUTHORITY HOLDPOINT
55e3284f-9a58-588c-bbef-d9a461605980 | checkpoint | 6.01.04 - Temporary Stockpiles
baf815d3-1ef3-59b4-94ad-daf49ffc72eb | note | Acceptance / Conformance Criteria - Temporary stockpiles shall not be located within the footprint of the permanent works unless approved by the Engineer.
18b30793-18bf-5c62-9ab2-12c0e2ba5c49 | note | Standard / Specification - PS 15.6.5
cc98758a-ecad-5043-bcc8-3a0f6433d90f | note | Verifying Document - Engineers Approval
58eb1e17-79a1-52e1-b4e4-ff51e4c2a10c | note | Frequency - Prior to stockpiling
08cfbbd5-6e1b-5ca2-872e-ed4df362935a | note | Verification Activity: Activity - HP
8f11b887-eb69-534b-b326-59012efc3a5c | note | Verification Activity: By - ENG
a94c983f-b77c-5257-ba7c-2cf26f751c21 | signoff | AUTHORITY HOLDPOINT
9f916a51-531e-50f9-ab39-015b1c560d11 | checkpoint | 6.01.05 - Surplus Material
02f14ce9-3ef4-562b-b104-58d1241b50c7 | note | Acceptance / Conformance Criteria - Surplus or waste soils may be deposited outside the site boundaries with the written approval of the Engineer.
c85b74b4-9183-55a7-ae2f-345297038e49 | note | Standard / Specification - PS 15.1
ef2e0cf0-e7d5-51ba-8a6d-bbc82bdf9e2f | note | Verifying Document - Engineers Approval
a960256b-958b-5eb6-af8e-bc4d99728fb0 | note | Frequency - Each Occurrence
52fea67b-14ca-5826-8d8a-c11dc3466cf4 | note | Verification Activity: Activity - HP
4b1848f4-9510-5def-95f4-d24b7a6c808e | note | Verification Activity: By - ENG
291238e6-3d02-5ec2-b9a8-ab81fb7023ca | signoff | AUTHORITY HOLDPOINT
918a1145-c5ce-509f-bed1-f62ab59e0117 | checkpoint | 6.01.06 - As-Builts
db708295-8b31-57be-bec5-77dab4401720 | note | Acceptance / Conformance Criteria - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
a24bef18-ed19-5402-9911-8d0aa41611d7 | note | Standard / Specification - PS 15.11.7
44a3c1ca-2b3c-5bd8-bcd9-8166bc6a932f | note | Verifying Document - Survey Records
b240b2d4-ab96-5982-84a2-2fd25825db00 | note | Frequency - During Earthworks
f0563e63-58d2-5281-99f2-223329a109a7 | note | Verification Activity: Activity - D
0379ef52-f0a4-5de8-b838-16ad532332f7 | note | Verification Activity: By - SV
44d1c624-06c3-5e22-b6df-9c6af47c6102 | section | 6.02 Cutting and Subgrade
e2056d42-43d7-5262-8e7d-f3a1023524d6 | checkpoint | 6.02.01 - Cut slope inspections
f0c9e4d3-35fc-5484-b867-873378bcdcc6 | note | Acceptance / Conformance Criteria - Cut slope inspections will be required to allow inspection of the soils exposed and check for seepages. Inspection records are to include photographs, logged soils (to NZ Geotechnical Guidelines) and hand shear vane testing on fine grained soils. Results will be submitted to the Engineer.
a5050965-657c-5cb4-ba54-29f7a81a36c0 | note | Standard / Specification - PS 15.10.2, PS 15.13
0ca6644d-27bc-50cb-82c3-e9215beabdf8 | note | Verifying Document - Engineers Approval
ee095220-c54a-544f-8c85-d2e244c4a0fd | note | Frequency - Each Occurrence
6854b9e5-08d8-53bf-b4c4-25cc08b491a4 | note | Verification Activity: Activity - HP
3b8c7bd6-7173-5f1c-9873-a15adf5e3876 | note | Verification Activity: By - ENG
e91cf135-5c98-52a7-a54a-3c6af3be7601 | signoff | AUTHORITY HOLDPOINT
d2fbe478-ad1f-5048-8657-8f4e357aec4a | checkpoint | 6.02.02 - Dewatering
45ad7851-3863-514c-bd5d-d0013775f8f7 | note | Acceptance / Conformance Criteria - Trenches and excavations shall be dry at all times during construction works and a constant water level is to be maintained at 300mm below the base of the trench. No construction works may occur if there is any water in an excavation.
10bf3c53-35d3-54c6-aa6d-417ba63dc5da | note | Standard / Specification - PS 15.10.18
fbd2f8c6-64ab-5c47-af05-cb3418296a2c | note | Verifying Document - Site Records
bc3137ea-86db-5fc7-b231-fea3db637513 | note | Frequency - Ongoing
f642d9fb-44aa-5900-a964-19c664e82209 | note | Verification Activity: Activity - S
83904629-984d-510e-b1a8-050717dedc6a | note | Verification Activity: By - SE
0478f66f-1630-5596-ad8d-f38a4cc2b1c9 | checkpoint | 6.02.03 - Subgrade CBR Testing (Road and Embankment)
f3d10b4e-addd-5538-a957-2a37e0034faf | note | Acceptance / Conformance Criteria - The subgrade shall be tested for CBR via Shear Vane or Scala depending on site conditions. Testing to be undertaken to maximum 3m depth at 0.5m interval with hand auger holes required for test deeper than 900mm.
2ce0f2e8-1f40-5e35-8e0b-a78fd0b55a7b | note | This test shall be undertaken at the design subgrade level and at a depth of 300mm below the design subgrade level. Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material.
8b65a2ae-cac6-521a-a731-1c5b9ef6ea23 | note | ○ Shear Vane Average minimum su: > 60kpa
4ccae70e-9d5a-53e4-8f6b-a4e00f80f67e | note | ○ Shear Vane Single test minimum su: > 50kpa
3ff01897-8d7b-537a-9e0a-bdedcefe185a | note | ○ SCALA: Minimum 3 blows per 100mm penetration
630d469c-d4b6-528c-8e3d-4302c9510b53 | note | Standard / Specification - PS 15.10.4, PS 15.10.5 Appendix XIII
0c3bb1ce-aaf0-5272-9b8f-4d902e6bbc45 | note | Verifying Document - Shear Vane or Scala Report
85d3bae8-7bf8-56b3-9602-213fb78a5576 | note | Frequency - 4 test per 400M2
55a69f30-35b2-5c05-9282-92604524f101 | note | Verification Activity: Activity - I
8a1bfe00-8ce7-590a-a5cb-d9ae236fa6a6 | note | Verification Activity: By - SE
55b576e1-21ed-531a-aacd-d94250dc6129 | checkpoint | 6.02.04 - Undercut Subgrade Compaction
f841e758-4cd2-5891-b08c-751a3c88b535 | note | Acceptance / Conformance Criteria - The degree of compaction of each layer shall be such that when trimmed to a smooth surface, the resultant impression in the surface under a smooth wheel roller having a minimum loading of 6259kg per metre width of fill or equivalent as agreed by the Engineer, shall not be greater than 7 mm for bulk fill or 5mm for subgrade fill.
8fb02c88-5c79-5b58-a1dd-92a07552b833 | note | Standard / Specification - PS 15.10.4
a629293c-385f-5bce-b059-933f4c7d43dd | note | Verifying Document - Site Records
2a96cae7-3c6a-51cb-9454-6091224f2d6f | note | Frequency - Prior to Backfilling
4ff321f5-d0cb-5131-9bac-f2447b9cd5d8 | note | Verification Activity: Activity - S
9afabe93-cf7b-5ea2-9907-09925e3a24f2 | note | Verification Activity: By - SE
9bb70f82-94b7-566d-9ef1-4b61c37556a1 | checkpoint | 6.02.05 - Soft Road Subgrade Areas
6fd65fab-6193-5462-afeb-d69af1a8db96 | note | Acceptance / Conformance Criteria - Any soft area observed during rolling of the subgrade shall be referred to the Engineer.
d76e99d9-c656-55e3-acb1-1c1df46f6945 | note | Standard / Specification - PS 15.10.4
1be23212-e8df-5d9f-8313-9a5254ebe069 | note | Verifying Document - Notice
1c0d6418-f406-5f50-950c-5444425f50bf | note | Frequency - When Encountered
34656019-18b2-5fea-94d4-d598e2a8138a | note | Verification Activity: Activity - S
c035f040-40a1-576d-b193-c59e6a453dad | note | Verification Activity: By - SE
c3b7c71e-cfaa-5a96-a625-454bb0cc64fa | checkpoint | 6.02.07 - Finished Surfaces
9bec837e-b683-55ad-bd75-4a248c626262 | note | Acceptance / Conformance Criteria - The works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for Subgrade is 0 to -30mm before placing aggregate layers.
a6991efb-ab9a-5b99-bf23-cb2f8b77c50b | note | Standard / Specification - PS 15.6.8
be65fa83-a107-5342-9c6d-a54c8b435c69 | note | Verifying Document - Survey Records
887ad7d3-09f0-5edf-a3ba-45e2f89d1d67 | note | Frequency - Each Finished Surface
157d7177-0edf-5110-9131-f02c3d9f1433 | note | Verification Activity: Activity - D
1fe43a96-441d-52f3-9c61-b1ddff480ba2 | note | Verification Activity: By - SV
9149e6ff-1de8-5094-9b9f-ead6fee4ce61 | checkpoint | 6.02.08 - Subgrade Proof Roll and Foundation Inspection (Road and Embankment)
b64008e4-8e18-5171-b4ca-a72a0d91c282 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect the Foundation surface prior to Filling during the Proof Roll. No filling shall be undertaken until an inspection has been made and the Engineer has approved the cut and stripping of unsuitable materials. Visual Observation Across The Stripped Area Displacement < 15mm.
677d8b3a-9fe5-5e7f-9e11-0862609e0580 | note | Standard / Specification - Appendix XIII PS 15.13, PS 15.10.5
9841c2a6-be7e-500d-bcca-506f57b64c31 | note | Verifying Document - Engineers Approval
4e231911-13ab-5ecd-9b53-75b332d5bfb0 | note | Frequency - Prior to filling with 24h notice
c10bf413-07c4-5174-9e14-7c2fbcd9358d | note | Verification Activity: Activity - HP
950b4e24-66ad-5e1f-946a-4eebbe8609ed | note | Verification Activity: By - ENG
f05195d4-07ae-5bad-820d-5d958fa1f023 | signoff | AUTHORITY HOLDPOINT
cbfd5119-9511-5f05-a1a3-eb568e57c7a2 | section | 6.03 Filling General
6da130e7-ec1a-5eb6-b735-c0a7919ee1b0 | checkpoint | 6.03.01 - Compaction Trials
082af659-e5a1-5e55-bb14-86dcfa2c12cc | note | Acceptance / Conformance Criteria - The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (i.e. construction discs and scarifiers). The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements. The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial.
b932f253-0659-5483-8431-149e22a51f34 | note | Standard / Specification - PS 15.10.15
0ff16a2c-7e89-5fe7-97b9-0d0dc811e560 | note | Verifying Document - Trial Results
5fa74afb-d11f-58b9-9267-b51498af3937 | note | Frequency - During Works before placement of each material.
103d17fd-0df9-56e9-949a-dda4690eb715 | note | Verification Activity: Activity - R
66efe4f8-ef07-5b70-852c-a42dccaab6c1 | note | Verification Activity: By - PE
29370bd4-2ff3-5032-ac70-4629fb46ed01 | checkpoint | 6.03.06 - Weaving or Pumping
bd1991d0-5093-5804-aff8-c52b44e7385d | note | Acceptance / Conformance Criteria - Any weaving or pumping of the soil or subgrade during the compaction process is likely to indicate that either the water content is excessive or the material has been over-compacted. If weaving or pumping is observed, the Engineer should be contacted to advise the appropriate solution.
e605ba42-46c5-5a4e-888c-2477e598e0b8 | note | Standard / Specification - PS 15.10.16
d39f9c2c-ed77-5b28-9068-8d5502076351 | note | Verifying Document - Site Records
68e095e6-4a9f-530e-83a7-48b3803bce4c | note | Frequency - When encountered
27e7c1ea-82b6-5046-a56c-510159c3d998 | note | Verification Activity: Activity - S
ed838f5a-7bf1-5227-8006-76b8f7af37f3 | note | Verification Activity: By - SE
8121b3c2-5c62-5f8a-95d7-1511aca62833 | checkpoint | 6.03.07 - Finished Surfaces
3070b6ed-33d2-59d9-86fa-a87d75982015 | note | Acceptance / Conformance Criteria - The proposed works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for earthworks construction purposes shall be level +/25mm unless stated otherwise, Subgrade; 0 to -30mm before placing aggregate layers, Bulk fill ±100mm, Preload and surcharge ±100mm, Batter slope tolerance ±100mm
3c16fa38-3eaf-5ad1-9f22-07ba1a84a45f | note | Standard / Specification - PS 15.6.8
816b2da5-1e05-56ee-b0d4-f4dad76d85e7 | note | Verifying Document - Survey Records
41c5a73c-3d7a-5d08-99a6-a6c30a41296c | note | Frequency - Each Finished Surface
d8403246-e1a7-5f1e-a63f-c616a6f86317 | note | Verification Activity: Activity - D
6183135d-77a3-5020-94fc-7c8fb634a0f3 | note | Verification Activity: By - SV
28941e1a-7c86-5b6c-b4be-2bd9aa06435c | checkpoint | 6.03.08 - Final Trimmed Shape Inspection
929f9aa7-dcab-55ef-848e-e713dd5186b9 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect final trimmed shape prior to placing topsoil or track rolled fill.
a0d0e862-2504-55af-b439-f3f7356c1fcf | note | Standard / Specification - PS 15.13
51f6149e-c97b-5a09-af39-5267730b4dd8 | note | Verifying Document - Engineers Approval
1d64599f-c05f-5017-bfc2-421633c38bf0 | note | Frequency - Prior to placing topsoil or track rolled fill.
ec8638c9-6512-5db2-95d2-d6d3f35119b8 | note | Verification Activity: Activity - HP
72c74c91-2072-5a09-8013-ca846e10480a | note | Verification Activity: By - ENG
2fa4e556-dcd6-5d59-898c-5d69fcba5b07 | signoff | AUTHORITY HOLDPOINT
9009fa4f-63e9-5b9f-b8f5-3feccfd591cc | section | 6.04 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
25dd2c92-e278-54c8-aa60-59679d5bfb86 | checkpoint | 6.04.01 - Imported Structural Fill Layers
6878fdaf-0bcd-5db1-a513-1fc0df376bbf | note | Acceptance / Conformance Criteria - The material shall be placed and compacted in layers no greater than 300mm thick.
8b06cea0-2762-5a10-b343-8660f98e0189 | note | Standard / Specification - PS 15.10.14
1a89ef0a-9801-51bc-aee0-85e181a5627d | note | Verifying Document - Site Records
30797fec-d05d-5e1d-9407-2ca3ce812dbc | note | Frequency - Each Layer
e9f5e8d3-b7f2-5398-be87-1d5e695a0fb9 | note | Verification Activity: Activity - R
d72c325b-87d7-5b7a-abca-566cc22d1211 | note | Verification Activity: By - SE
7d79ea5d-74fb-5020-a7fc-15bc0d20fe88 | checkpoint | 6.04.03 - Structural Fill Zone - Strength – Clegg Impact Value (CIV)
33972346-eaf4-5b1b-adab-39ff4c57e4e4 | note | Acceptance / Conformance Criteria - A1 Imported Structural Fill Strength shall be tested by Clegg Hammer every 200m3 per area per day per lift
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Minimum CIV = 18
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Average CIV= 20
b21d6bc2-fa63-5bc1-8d96-b05121b299af | note | Standard / Specification - Appendix XIII
9e78cce7-cd0a-5ffe-b4f7-52f1a5f40ad1 | note | Verifying Document - Clegg Results
edfa4ec3-1fcc-5df9-ba9c-81716eabe644 | note | Frequency - 1 Set (5 Tests – 5x5m Square Grid) Per 200m3 Of Placed Per Area Worked Of Day Per Lift
c952f64f-f2ef-5aeb-b6b7-5b247ddc0cdb | note | Verification Activity: Activity - I
e91737f2-9daa-590c-ba83-c4825556312f | note | Verification Activity: By - SE
cff2e2af-607b-551c-bbeb-3ae8301207cb | note | Comments / Closeout Details - Are both NDMs and Clegg Required
e7febe44-92c4-5796-b0f2-b82320d4484e | checkpoint | 6.04.05 - Structural Fill Zone Insitu Density Insitu Compacted Dry Density Insitu Water Content
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - A1 Structural Fill Compaction shall be tested by NDM in Backscatter Mode every 200m3 per area per day per lift
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | ○ Average >95% Of In-Situ MDD
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | ○ Minimum >92% Of In-Situ MDD
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Standard / Specification - Appendix XIII
69d85f65-b61d-579d-940f-2b691894d755 | note | Verifying Document - NDM Results
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
e2147c12-4568-5322-b418-283ae63070af | note | Verification Activity: Activity - I
09a8aad4-3fc9-597d-b419-c865f36b4acc | note | Verification Activity: By - SE
e446d0a3-f492-586c-ab52-5751ac56d10a | note | Comments / Closeout Details - Are both NDMs and Clegg Required
b9a8462b-715b-5c2d-8c25-e4f73254a4ca | checkpoint | 6.04.06 - Solid Density
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - The Solid Density Of Aggregate Particles shall be tested by collecting 1 sample with every set of NDMS completed (1 Test Per 200m3 For That Material Type And Source). Test Results Provide Input To Acceptance Criteria For Insitu Compacted Dry Density Determined By Nuclear Moisture Density Gauge (NDM)
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - Appendix XIII
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Solid Density Lab Report
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - 1 Set (5 Tests) Per Material Type And Source Then 1 Test Per 200m3 For That Material Type And Source
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
5ec91113-ac87-53de-b900-bcb9253aa488 | note | Comments / Closeout Details - Are both NDMs and Clegg Required
504915a0-29d1-5b8a-891c-a7b613638c3c | checkpoint | 6.04.07 - Organic Content
f09d0ff0-01ec-50cb-9988-3a078371cb3d | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
5d4c6d19-d8fb-5765-9b80-10ed32dbffe9 | note | Standard / Specification - Appendix XIII
ea12d870-db9e-5048-94de-56f316678975 | note | Verifying Document - Site Records
4b4f2a35-1e50-5341-80c6-541a73664b53 | note | Frequency - Ongoing
f77c9bbc-fb8f-5e0f-86c9-c66a4643254e | note | Verification Activity: Activity - I
dbb35f07-7f2f-5414-a8b4-c69adbcef37c | note | Verification Activity: By - SE
f910ed7f-8370-57c8-b1bd-2fb721606286 | checkpoint | 6.04.08 - Completed Fill Approval
cb670aff-3430-5d2c-ac3e-1482548f09ee | note | Acceptance / Conformance Criteria - Prior to pavement construction the Engineer shall complete a Desktop review of all structural fill compaction testing for acceptance.
e3ea5880-55a7-54a4-9ee9-9323b972ab79 | note | Standard / Specification - PS 15.13
eb4e4dcc-9679-50a0-8275-a70670f63fd0 | note | Verifying Document - Engineer Approval
5b1465a0-9c5b-51b0-8b4b-9694e85f2324 | note | Frequency - Prior to Pavement Construction
a3b40c94-fe59-5b33-bcda-878d287d2995 | note | Verification Activity: Activity - HP
696e1611-579b-5ae6-b3d8-5701063db1b8 | note | Verification Activity: By - ENG
5e0c2555-3e93-5160-beb9-af9efce873aa | signoff | AUTHORITY HOLDPOINT
faf4f3a3-1299-5382-bb2c-73748ed0cb2e | section | 6.05 LANDSCAPE FILL
a57c22bd-882b-5e15-98f1-6cc1024a010c | checkpoint | 6.05.01 - Cohesive Fill Layers
c352122b-b969-515a-bd14-4ee2d6d77a2c | note | Acceptance / Conformance Criteria - Cohesive structural and non-structural fill material, shall generally be compacted in layers of less than 200mm thickness. All fill surfaces shall be sealed at the end of each day’s work.
eb2c9836-d46b-5735-a171-5b7c260a8373 | note | Standard / Specification - PS 15.10.16
16c87f21-2b6f-5a9e-950f-ce52726911a4 | note | Verifying Document - Site Records
f997564b-0a06-59cc-aaf8-0d04c169bb65 | note | Frequency - Each Layer
48daa9bc-dbe2-5457-aa35-ebb3d2f05eee | note | Verification Activity: Activity - R
a63751f3-0140-5d7c-80c1-864752f123ce | note | Verification Activity: By - SE
91ea3ae5-4753-56e1-b28d-0d3a3fb40e12 | checkpoint | 6.05.02 - Fill surfaces Sealing
a578d34e-40e1-5c0c-b225-25282dfa3822 | note | Acceptance / Conformance Criteria - All fill surfaces shall be sealed at the end of each day’s work.
275dad26-4948-57bc-bc5d-25291c4dfe04 | note | Standard / Specification - PS 15.10.16
bf910f9a-c5f9-5501-bd00-480e205a15ef | note | Verifying Document - Site Records
cd655ab2-4234-580a-b1d2-e5f8d0f9c64b | note | Frequency - Each Day
5b4f0479-5692-504d-98b2-93cf71280de9 | note | Verification Activity: Activity - R
a00280e8-d9ac-5f5e-86c0-a351a10dc28a | note | Verification Activity: By - SE
e9f6dd3e-48b2-53bf-8c70-05c59c2b86d9 | checkpoint | 6.05.03 - Non-Structural Fill - Air Voids
8e28b866-fa38-519b-918f-3d14bb22ecfb | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill compaction (Air Voids) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift.
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Average Maximum Air Voids < 8%
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Single Test Maximum Air Voids< 10%
b6a6dfee-f164-5998-9bdb-0af48b5f824e | note | Standard / Specification - Appendix XIII
bebdea1e-dece-5fe9-9b48-a107125b16b9 | note | Verifying Document - NDM Results
e003f7a2-352b-5d80-9fd5-e44eddfe06fe | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
3f5e0ef0-3697-5f92-8b8c-ec24df3f2e89 | note | Verification Activity: Activity - R
da65e1bd-770b-59ad-9793-ebeab9e626dd | note | Verification Activity: By - SE
2254b6f8-ca87-5831-8381-537164057ab6 | checkpoint | 6.05.04 - Non-structural Fill – Shear Strength (SU)
9edd37d7-9376-551e-84f9-b888b8840c61 | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill Strength shall be tested by hand held Shear Vane or Scala every 500m3 per area per day per lift of fill placed.
5b2f902a-75e1-52ba-831a-286d435423d5 | note | ○ Average Minimum Su > 60kPa
0d47f6a9-9a9c-5830-a715-20e29444a71c | note | ○ Single Test Minimum Su > 50kPa
cd8cbc5d-5199-51fe-8b4d-b38294c9026a | note | ○ Scala: Minimum 2 Blow Per 100mm up to 1.0m deep
f92cde20-aba2-55da-8996-95fb4f00d9cf | note | ○ Shear vanes and scala's not applicable where cohesive soils are mixed with granular material
3987cf23-05e1-5604-91fa-7c85db88248f | note | Standard / Specification - Appendix XIII
7cd5ddd4-8c1e-52f1-aeba-5f314cce96f9 | note | Verifying Document - Shear Vane or Scala Results
6c04cc44-a270-5c2c-903f-8ca50b667f73 | note | Frequency - 1 Set (5 Test) Per 500m3 Of Fill Placed Per Area Worked Per Day Per Lift
031b41c8-0684-5bd5-9692-1238e6978165 | note | Verification Activity: Activity - I
2f45e865-55b9-5d5f-94f9-2cda2e27e330 | note | Verification Activity: By - SE
67d2cb19-a2ab-56fe-9362-2a11a6148fa9 | checkpoint | 6.05.05 - Non-Structural Fill - MDD
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - Non-Cohesive Non-Structural Fill compaction (Dry Density) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift. 90% Minimum Dry Density (MDD).
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | Standard / Specification - Appendix XIII
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | Verifying Document - NDM Results
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
69d85f65-b61d-579d-940f-2b691894d755 | note | Verification Activity: Activity - I
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Verification Activity: By - SE
940c74e2-d6b4-59ce-a549-e065a128c6e6 | checkpoint | 6.05.06 - Non-Structural Fill - Granular Mixed Materials
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - Mixed non-structural material requires proof roll to ensure compliance with the 7mm requirement. Proof roll to be done where soils cannot be penetrated via shear vanes or scala
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - TNZ F1 Section 10.5.1
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Site Records
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - Formation level
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
c83c1a95-6cc3-5b55-ac8c-57dd36cf1a2e | checkpoint | 6.05.07 - Organic Content
f09d0ff0-01ec-50cb-9988-3a078371cb3d | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
5d4c6d19-d8fb-5765-9b80-10ed32dbffe9 | note | Standard / Specification - Appendix XIII
ea12d870-db9e-5048-94de-56f316678975 | note | Verifying Document - Site Records
4b4f2a35-1e50-5341-80c6-541a73664b53 | note | Frequency - Ongoing
f77c9bbc-fb8f-5e0f-86c9-c66a4643254e | note | Verification Activity: Activity - I
dbb35f07-7f2f-5414-a8b4-c69adbcef37c | note | Verification Activity: By - SE
8a6e4423-2a66-5b93-af2a-67e156f07a85 | checkpoint | 6.05.08 - Water content
cb670aff-3430-5d2c-ac3e-1482548f09ee | note | Acceptance / Conformance Criteria - The water content shall be tested by collecting 1 sample with every individual NDM test.
e3ea5880-55a7-54a4-9ee9-9323b972ab79 | note | Standard / Specification - Appendix XIII
eb4e4dcc-9679-50a0-8275-a70670f63fd0 | note | Verifying Document - Water Report
5b1465a0-9c5b-51b0-8b4b-9694e85f2324 | note | Frequency - Every NDM
a3b40c94-fe59-5b33-bcda-878d287d2995 | note | Verification Activity: Activity - I
696e1611-579b-5ae6-b3d8-5701063db1b8 | note | Verification Activity: By - SE
94ecb72f-b511-5fef-99c9-b75caaae5292 | checkpoint | 6.05.09 - Bulk Density, Dry Density, Air Voids
2ff13b7b-02c2-5a7b-8118-f41c41b17271 | note | Acceptance / Conformance Criteria - The Bulk Density, Dry Density, Air Voids shall be tested by collecting 1 sample (Sample Tube) for every 10 NDM Sets completed.
c39051d9-945b-528b-a585-33d79297aaee | note | Standard / Specification - Appendix XIII
dd793333-b4d3-5ea8-9644-25cf03ccc6e5 | note | Verifying Document - Lab Report
d69a3d8f-c798-532b-a15c-6f7e4df14e4c | note | Frequency - 1 Test Performed For Every 10 NDM Test Results Provide
2d5640eb-932b-5ba9-87eb-2c7ce14f8894 | note | Verification Activity: Activity - I
c9a19186-767d-535f-9741-6cc10a171f11 | note | Verification Activity: By - SE
fc2a90ef-55da-5ce7-be30-c6a3f87b303a | checklist | Ω (DEPRECATED) ITP - Retaining Wall Construction - 303 - Rev B | itp | ITP - Retaining Wall Construction - 303 - Rev B
5f850b57-682f-5bf5-bfdd-24ea3138edf6 | section | 4.19 Retaining Wall Materials
823b7a6d-757d-5b08-ba55-1880b2f49030 | checkpoint | 4.19.2 - Retaining Wall Concrete
fd7d10eb-4d58-56ab-82dd-7d5f62b1961b | note | Acceptance / Conformance Criteria - All concrete shall have a minimum 28-day compressive strength of 30 MPa for both piles and the capping beam. The contractor shall submit the proposed concrete mix including slump to the Engineer before the commencement of works
247c9885-b7c2-5a8a-9aaf-131a2f4c7fd2 | note | Standard / Specification - PS 18.2.5, PS 18.5.1
c2581b5a-6ff0-5885-aed1-e088cf70f62d | note | Verifying Document - Mix Design
70a49a1f-af9f-5c8b-b10d-2a1e9a9408cc | note | Frequency - before the commencement of works
02782cad-a71c-5be8-a784-1a241ce4af52 | note | Verification Activity: Activity - HP
b9fc96d4-1470-5d12-b52f-4bce30ed0f54 | note | Verification Activity: By - ENG
6e053514-b450-5ead-b46c-9e3a7252129c | signoff | AUTHORITY HOLDPOINT
88862f50-7b93-5208-b920-9b8b5cfc22b5 | checkpoint | 4.19.3 - Hot-dip Galvanising
a535afa0-5314-57b9-9840-17809daf505f | note | Acceptance / Conformance Criteria - Steel sections, and all associated fittings shall be hot dip galvanised, in accordance with AS/NZS 4680. All alterations to fittings shall be hot dip galvanised following fabrication.
2f55f061-b59e-5c17-b0f2-cd9da764f123 | note | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
cfd6895d-768e-5a52-9e06-7227141d6167 | note | Verifying Document - Datasheet
f7fc6ac8-9f72-570f-b2b6-f524eac78771 | note | Frequency - Prior to Works
58d8f645-cc20-5228-9e80-6d22725ee1a8 | note | Verification Activity: Activity - R
6a4f9452-18e4-5243-a71d-0ff612ae75e3 | note | Verification Activity: By - SE
bd7ccd3a-00b6-58b5-887e-c0490a2460dd | checkpoint | 4.19.5 - Welding Procedures
9b0357c0-a0f5-5b30-88ef-eb3d7aa327fe | note | Acceptance / Conformance Criteria - All welds shall be weld category GP in accordance with NZS 3404. All welding procedures shall be in accordance with AS/NZS 1554. The Contractor shall submit full details of the proposed welding procedures and electrodes, with drawings and schedules as required.
2be8899c-0996-5d55-b4ed-6dcec53a9b08 | note | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
485df183-811b-5237-9ade-12839a3f7d17 | note | Verifying Document - Welding Procedures
20d8738d-b67d-5dc0-afc9-eb6f5c4a42ad | note | Frequency - Prior to Works
dadef6d8-b550-5b92-8729-cd7bd856aff6 | note | Verification Activity: Activity - R
feda6f3c-de8e-5727-ace8-7eb10a498ef2 | note | Verification Activity: By - SE
0c6bcdba-391c-53c4-8464-48cde0cd386f | checkpoint | 4.19.6 - Welders Qualifications
5f29b780-4f38-502b-90a3-7273c025c4a7 | note | Acceptance / Conformance Criteria - Only welders qualified to AS/NZS 1554, or equivalent standard shall be employed on the works. Proof of welder’s proficiency and qualification shall be made available to the Engineer on request.
30e50192-78f7-5c6d-b629-a31dece44f90 | note | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
cd3b8b21-d534-521c-8e37-c905f441245d | note | Verifying Document - Qualification
5e2fac0d-e411-545e-9736-ce5def1f70cb | note | Frequency - Prior to Works
d624ba05-61af-5d9c-990d-03f394014184 | note | Verification Activity: Activity - R
5bba7bd5-9693-5986-8e5c-e62c166a6305 | note | Verification Activity: By - SE
ab662094-35d2-56b9-b623-a71ee833a695 | checkpoint | 4.19.7 - Steel Piles
18dd4bc1-b853-50ab-9d87-cdabb6de70ab | note | Acceptance / Conformance Criteria - Steel piles shall be 310 UC137, mild steel Grade 300, complying with NZS 3404 and galvanised in accordance with AS/NZS 4680. Only new steel pile section to be used. All piles and production certificates shall be made available for inspection by the Engineer at any time.
deeca1dd-0a34-51dd-9d67-377c6cffe1d7 | note | Standard / Specification - PS 18.2.4, PS 18.2.1, PS 18.2.2
75e7e067-907b-559d-8741-10990e862076 | note | Verifying Document - Mill Certs
8b5e9adc-944b-5227-a470-c429a76abe5d | note | Frequency - Prior to Works
fda27e5f-d826-5d5e-a42f-e9283d70056c | note | Verification Activity: Activity - R
83caf265-5827-582c-b9eb-4ee3127febe0 | note | Verification Activity: By - SE
334896d8-6e51-5f7a-8838-0c19ac0b8736 | checkpoint | 4.19.8 - Steel Reinforcement Compliance
879b0597-75bd-5eea-9ade-577a26abb4ea | note | Acceptance / Conformance Criteria - Conformin Steel Reinforcement Mill Certs conforming to AS/NZS 4671 shall be supplied.
48b36206-7cc5-58ab-aad0-6cb84cff9dce | note | Standard / Specification - AS/NZS4671 & NZS3109
347b8c86-1864-5462-9ec5-abebb27d348d | note | Verifying Document - Detail Sheets and Mill Certificates
7fac28c2-f78d-57aa-9517-cc83b322b4aa | note | Frequency - Prior to ordering steel
44b215cc-ad9b-50e8-81ab-65d2bf7f568f | note | Verification Activity: Activity - W
1d25b649-961b-5061-ae11-c5e40c79de6c | note | Verification Activity: By - SE
78070aeb-3f32-5c15-811a-945eb61fc4e1 | checkpoint | 4.19.9 - Reinforcing Welding Qualifications
159a5beb-388c-57fd-853f-0c527b7787fd | note | Acceptance / Conformance Criteria - Welders and Procedures are to be qualified to AS/NZS 1554.3, reviewed by TPI for conformance and submitted to the Engineer for Acceptance.
0130fc4c-1555-5375-a031-524742c060a7 | note | Standard / Specification - Drawings
fd764006-32e4-5a57-bf81-1fce359f60b5 | note | Verifying Document - TPI Report
c5cac918-2354-5264-9aac-ced0e5c842db | note | Frequency - Prior to Welding
955e27ee-db09-5220-924b-bf1fa6a233b0 | note | Verification Activity: Activity - HP
b2b116b5-4fea-50a7-a524-5e004d109f55 | note | Verification Activity: By - ENG
2f341b64-078c-51ff-8e80-91200e656c4d | signoff | AUTHORITY HOLDPOINT
4ba54622-a112-5b2c-9945-626512be4482 | checkpoint | 4.19.10 - Reinforcing Welding
606272de-2f75-5698-9565-3f5c1352b710 | note | Acceptance / Conformance Criteria - All welded reinforcing shall be completed as per AS/NZS 1554.3 and be 100% Visually NDT inspected by an independent and approved Third Party Inspector (TPI).
6036b58e-91b3-5599-8825-f707a8052091 | note | Standard / Specification - Drawings
58202a09-ab61-5aa3-a164-37e8e600f65a | note | Verifying Document - TPI Report
d8434764-ad65-5092-98d7-72d193c97fca | note | Frequency - Prior to concrete pour
a294423d-d178-5868-98c8-6c05a5431f1b | note | Verification Activity: Activity - R
63756ca6-9f96-559b-b3da-3dd8c9935b00 | note | Verification Activity: By - PE
7bcbb701-97bd-5390-8daf-03a2f59fca10 | checkpoint | 4.19.11 - Pile Concrete Mix Design / Tremmie Mix Design
9b1cff69-9845-59e4-8e2e-d0ad3ccb3359 | note | Acceptance / Conformance Criteria - Mix design compiling with the requirements of the contract to be approved by the Engineer.
10552595-2d17-5a0c-8c78-4bcc2d8c536c | note | Standard / Specification - Drawings
359aad3b-4058-5737-8c99-8c9b13aa0f34 | note | Verifying Document - Approved Mix Design
925dfb04-79a1-5b48-8442-100731f5048e | note | Frequency - Submitted to and approved by the Engineer prior to concreting
76c93829-eedd-544f-898f-050341430448 | note | Verification Activity: Activity - HP
8a22686d-4065-56fd-af55-5c15c178577d | note | Verification Activity: By - ENG
ad4324e6-7735-5b3c-baed-be9b1a956d4b | signoff | AUTHORITY HOLDPOINT
06a65faf-3a0a-5309-818c-70ee82c3f447 | checkpoint | 4.19.12 - Concrete Aggergate
2f50e19e-d978-564d-97ce-31502faaa1d7 | note | Acceptance / Conformance Criteria - Aggregates for concrete shall be selected from a single source, which shall be used for all concrete that will form part of the permanent works. Nominal maximum coarse aggregate size shall be 15mm.
df012fe7-1c00-5734-9456-cf33516df067 | note | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
22b5f118-7dd8-5823-a70d-0aa2d934dabf | note | Verifying Document - Mix Design
c2c2f4d4-6a3c-5f37-bec1-1e97a3870dcc | note | Frequency - Prior to Works
53c79150-8020-5c94-b7d2-b002f0a27ab4 | note | Verification Activity: Activity - R
c7aef61d-a503-5351-9eed-72fe68bebcc0 | note | Verification Activity: By - SE
40233808-3583-5439-92d1-e262364bffdf | checkpoint | 4.19.13 - Concrete Capping Concrete
de6b130d-ceb4-543d-8f73-75302714c34a | note | Acceptance / Conformance Criteria - All concrete shall have a minimum 28-day compressive strength of 30 MPa.
c6b035c2-379c-55c3-a8be-7520cc5850b8 | note | Standard / Specification - PS 18.5.1
9e371064-c33b-5e98-be64-a9cfb8ee2618 | note | Verifying Document - Approved Mix Design
2af95af4-df98-510c-b194-328a27825024 | note | Frequency - Submitted to and approved by the Engineer prior to concreting
9a2f3a38-f523-534d-98bd-c10c8a2e6dc9 | note | Verification Activity: Activity - HP
98928dc9-48d5-51ce-af6a-1977f5e73e90 | note | Verification Activity: By - ENG
aaa0e176-fc25-5d9d-954f-220387b4b6ef | signoff | AUTHORITY HOLDPOINT
a73a94b5-0329-50cb-a9f8-e12641ebc5ca | checkpoint | 4.19.14 - Capping Steelwork
83645f87-5e5a-54cb-897d-5141eb0e13c7 | note | Acceptance / Conformance Criteria - All grade 500E (MA) reinforcement shall comply with AS/NZS 4671 and be manufactured using micro alloy Process. Quench and tempered is not permitted.
b3bc1302-2c6d-5c1f-b08a-aa28b654912a | note | Standard / Specification - PS 18.5.2, PS 18.1.2
5886aa0d-febf-5753-97b2-83463bf83bd7 | note | Verifying Document - Detail Sheets and Mill Certificates
27d98f83-7b51-5f10-8278-75ec2cc670a8 | note | Frequency - Prior to ordering steel
e2332c23-cf1a-505c-9e22-73eaa98b1d9a | note | Verification Activity: Activity - R
33536bc2-e496-557c-b201-512e5c939ffd | note | Verification Activity: By - SE
ed0b672c-6a4f-5379-93af-6b7a183be96d | checkpoint | 4.19.15 - PFC & UC Steelwork
800c6266-15eb-54c2-b31c-26d75f224a0b | note | Acceptance / Conformance Criteria - Sections shall be grade 300 unless noted otherwise. All PFC & UC's to be grade 350 unless indicated otherwise All structural steel welding to comply with AS/NZS 1554 Class G.P. All welds to be 6mm minimum continuous fillet welds, unless noted otherwise.
b56cecf7-d913-54e7-8c0f-9adc2af0d499 | note | Standard / Specification - PS 18.5.2, PS 18.1.2
d8fd0022-5094-5552-9860-cd935463a3e2 | note | Verifying Document - Detail Sheets and Mill Certificates
831f8d2b-fefb-5f3b-ab03-a821dcae559a | note | Frequency - Prior to ordering steel
0ca3209c-f1b7-591f-9319-f55f2ddce451 | note | Verification Activity: Activity - R
5933185a-d863-567f-8515-5a224167f3b2 | note | Verification Activity: By - SE
5f6bc327-f18c-5355-89c2-a555de727393 | checkpoint | 4.19.16 - Precast Mild steel fixings
f016d70a-1ed0-520f-86fe-721f9d1443e1 | note | Acceptance / Conformance Criteria - All mild steel fixings including bolts, nuts, inserts, washers, cleats and brackets shall be hot dip galvanised after fabrication.
5c64a8e3-c710-572d-ade9-16a6edda3ae7 | note | Standard / Specification - PS 19.15.6
f342cb13-a72c-5af3-9631-1d051b28a7b9 | note | Verifying Document - Datasheet / Mill Certs
c5784e70-f325-50ab-88d4-2eccc540b366 | note | Frequency - Prior to use
84ab87c4-ade5-55c0-81ca-b3f40e72d7f8 | note | Verification Activity: Activity - R
bbe73770-8a70-5d0f-890c-6972641a6ee8 | note | Verification Activity: By - SE
ee1b0786-3e33-52cc-9fa7-891464122490 | checkpoint | 4.19.17 - Precast Stainless steel
ed9302cd-0cd5-57c6-9091-1d8ee67b8153 | note | Acceptance / Conformance Criteria - Stainless steel shall be type 316 unless otherwise specified.
bcb2ae09-961a-5dba-97e0-bc88b7215aea | note | Standard / Specification - PS 19.15.7
bcfedee1-7415-5999-bb1d-b28505d89478 | note | Verifying Document - Datasheet / Mill Certs
49c7954d-74aa-51c6-b80a-43cad102aca8 | note | Frequency - Prior to use
2bee71bc-aa6f-5cdf-84f6-b952883e66f5 | note | Verification Activity: Activity - R
cafbc81e-a1d4-5d55-a974-049894bb9348 | note | Verification Activity: By - SE
7eecf414-bc7d-59c2-af29-2bbd962bf031 | checkpoint | 4.19.18 - Reinforcement cover spacer blocks
3294dbfa-5322-57cf-94a0-6ab09dc62e10 | note | Acceptance / Conformance Criteria - Reinforcement cover spacer blocks shall be either Concrete spacer blocks made from concrete containing 8% Microsilica and with a specified strength at least 10MPa stronger than the surrounding concrete or Plastic spacer blocks are in general undesirable in corrosive environments but may be acceptable in specific areas.
227d0ba4-18ed-52dd-9ab2-25333232bd0e | note | Standard / Specification - PS 19.7.8
844fba81-3404-5445-ab26-f1c3b915236f | note | Verifying Document - Datasheets
143b7435-d60f-5818-827a-d1175b1505cf | note | Frequency - Prior to use
50243e8b-ce3a-5188-aed5-66d1f693da3c | note | Verification Activity: Activity - R
ba1d5f2a-72a5-5b79-b3d2-68730d6842a0 | note | Verification Activity: By - SE
2d383db2-fdd0-5396-bc9b-76afb271d457 | section | 9.01 Pile Construction
e7767916-d781-592b-8dee-ab4b0fa64485 | checkpoint | 9.01.1 - Contractor’s Methodology for Pile Construction
c92706a3-0b20-5fd7-8aa6-f1eaf2b0e146 | note | Acceptance / Conformance Criteria - The Contractor shall submit to the Engineer for acceptance his methodology for the construction of the steel soldier piles at least two weeks prior to commencement of the works.
852309fc-d8c5-50a1-95ba-5ef1529b8c85 | note | Standard / Specification - PS 18.3.1, PS 18.1.2
1e8b9629-82fb-5b5c-9463-926556b3a6ad | note | Verifying Document - Approved Methodology
5b66d40c-3751-569f-8113-1e7271836a71 | note | Frequency - At least two weeks prior to commencement of the works.
7e223e9a-c9ef-5668-82ae-82154a0f29d5 | note | Verification Activity: Activity - HP
18c41bd0-2abf-5d5e-9bda-1fe2ff9635bf | note | Verification Activity: By - ENG
1d090c1d-4749-579f-8faf-c6f98e51f333 | signoff | AUTHORITY HOLDPOINT
d99fc7c2-9e10-5e34-8f77-0b7125a2949c | checkpoint | 9.01.3 - Setting Out
b528dfb0-8ca5-5b4d-9931-f6c194f014bd | note | Acceptance / Conformance Criteria - The Contractor shall be responsible for the correct setting out of all works, including set out of the position of the piles and anchors correctly to reflect the requirements of the specification and drawings.
836b0891-e188-5d9d-a148-b8bdd12dd5b7 | note | Standard / Specification - PS 18.4.2
2f0c27a9-caf2-554d-84ad-7e14e9a901f4 | note | Verifying Document - Survey Records
9e612da5-ccf3-547a-8d71-a6c388416268 | note | Frequency - Each Pile
6f47cfa7-fc11-5f38-ac1e-9d798a7e8aef | note | Verification Activity: Activity - S
a5088bbf-cc0a-5b1e-b5a4-3a3170b11bfc | note | Verification Activity: By - SE
194c7c26-eb14-5b15-b6a4-72853a03d60f | checkpoint | 9.01.4 - Setout Approval
a3771e83-d23b-584c-9bae-b29308ff12eb | note | Acceptance / Conformance Criteria - On completion of the set out of the wall, the Contractor shall immediately advise the Engineer for the purposes of checking the set out. No other works shall be carried out until this has been checked and approved by the Engineer.
50fbb343-f9a9-570b-bc7d-ac64cfde3fef | note | Standard / Specification - PS 18.4.2
94f352bc-44e9-5a1f-8f30-ea8b3cfe5d1b | note | Verifying Document - Engineers Approval
c63eb805-2beb-56a1-99d9-4bc30adfb985 | note | Frequency - Each Pile beofre excavation
704a3b81-4440-5759-a189-758a8127f930 | note | Verification Activity: Activity - HP
aed46970-f869-5ab0-a9dc-8c7917c48c9f | note | Verification Activity: By - ENG
cfdeb7bd-3796-5a61-9b7e-83287579ac2f | signoff | AUTHORITY HOLDPOINT
29108c2c-17f9-520c-9c8d-a3fdc06a8cfb | checkpoint | 9.01.5 - Depth of Foundation
6c6feda5-07e0-553b-b1bb-81c0f3c8f38d | note | Acceptance / Conformance Criteria - The Engineer will advise the depth of founding for each cylinder based on the driller’s ground description log, examination of the material from the excavation and samples at no more than 0.5 m intervals.
df290685-4622-5b05-abeb-e9c7bae10d6d | note | Standard / Specification - PS 18.3.2
6b77ada5-26fd-5141-9ed7-93678a9cf9a8 | note | Verifying Document - Engineers Approval
b6af329c-086c-57de-abcf-ad210d5726f1 | note | Frequency - Each Pile Before Survey and Concrete
7bf94bea-7aa0-52e7-a046-23de1e83ecbc | note | Verification Activity: Activity - HP
fb9802e7-7e7b-5d83-90da-4f01be793702 | note | Verification Activity: By - ENG
f3c3ab87-eab2-573d-9cfa-a3c9ccdee41b | signoff | AUTHORITY HOLDPOINT
fe312ac7-4d6a-54f6-9dfc-1e3c6bf8f88c | checkpoint | 9.01.6 - Pilling Records
a0da90b1-0e87-5c2d-8d39-ab8f6d63073d | note | Acceptance / Conformance Criteria - The pile driller shall maintain a daily record of the progress of the piling with time recorded, and details of drilling equipment used, casing installed, groundwater levels and ground conditions recorded. The daily records from the driller shall be submitted no later than noon the following day.
3a0eab19-f96e-58c5-b6ad-ce9f381a6596 | note | Standard / Specification - PS 18.3.2
eaf72935-f93d-50bc-a983-3b3e94792746 | note | Verifying Document - Pilling Records
5849502e-ec74-553a-8d50-fdf42e34ebda | note | Frequency - Daily
4c26b8e7-af49-5708-a6e4-1103549bc907 | note | Verification Activity: Activity - I
f5cdcbbc-5dba-5f43-92ea-89e0f5a14c23 | note | Verification Activity: By - SE
46670991-b14f-55ce-80a7-4d4b522a8e5f | checkpoint | 9.01.7 - Pilling Timming
8b37b9ee-0e78-5eeb-950c-e65b1afec961 | note | Acceptance / Conformance Criteria - During pile construction, none of the pile holes shall be kept open for more than 48 hours and no more than 4 piles under construction at one time.
4497220d-c673-5e7b-8277-95e8eaeb0b8f | note | Standard / Specification - PS 18.3.2
24e62ca8-3c0d-5d12-bacb-5fe8085c0b6c | note | Verifying Document - Survey Records
d6b86a50-ec52-5ed4-a143-c89948b5f588 | note | Frequency - Each Pile
f3af4e38-9a60-5764-93b5-b52875b46abd | note | Verification Activity: Activity - S
00b061e1-0ff6-51ea-bc24-2cd48990ad5d | note | Verification Activity: By - SE
bda30306-22bb-5574-9201-3cbffcf58491 | checkpoint | 9.01.8 - Pile Excavation Survey
75d9df69-a74f-5cf9-a35b-b12573408ecc | note | Acceptance / Conformance Criteria - On completion of excavation, the Contractor shall survey the final reduced level of founding for each cylinder, measured to the nearest 0.01 m, and submit the surveyed final reduced levels for approval to the Engineer, prior to placing reinforcement and concrete.”
063c1dfa-7ef3-5656-94f8-c9e7ddf4e45e | note | Standard / Specification - PS 18.3.2
bd59a373-3c39-5b7a-8407-456522facb37 | note | Verifying Document - Survey Records
e7c032ea-f91a-5725-84b2-5b9a0f88e911 | note | Frequency - Each Pile before concrete
aef11be8-bd78-53a5-8df1-143c92b5b47e | note | Verification Activity: Activity - HP
692a34bb-ab97-5647-ba5f-e33e78632b3d | note | Verification Activity: By - ENG
b1014a04-a31f-516f-ba8e-9a61a2f20bbc | signoff | AUTHORITY HOLDPOINT
68265185-64f4-5272-9b05-24cb2606362e | checkpoint | 9.01.9 - Construction Tolerances for Piles
a07bcdc0-c353-5877-9671-f2697a540e28 | note | Acceptance / Conformance Criteria - The allowable positional tolerances of the concrete piles shall be ± 50 mm. The completed pile shall be plumb to within 1% of vertical, as determined by the angle from the vertical.
c93b6388-dd44-5efe-9afd-a72c32a1e551 | note | Standard / Specification - PS 18.3.3
a188ec44-37ec-5b0f-9a96-f2ea6515b552 | note | Verifying Document - Survey Records
401f776a-c22e-525a-a9bf-fdf0bfe591b2 | note | Frequency - Each Pile
0c88bf16-27a6-5749-ac68-b01fb3c0948b | note | Verification Activity: Activity - I
f5356446-3523-5c78-857d-1b3773023c47 | note | Verification Activity: By - SV
e7ccaa04-b029-5aee-9b5e-148785528c85 | checkpoint | 9.01.10 - Remedial Painting
a430cf01-9158-51a9-b34e-9208ccd3d24b | note | Acceptance / Conformance Criteria - Damaged galvanizing shall be coated / repaired in accordance with Appendix E of AS/NZS 4680, e.g., painted with 2 coats of an approved zinc rich paint, such as Resene AmorZinc110.
93052f21-9a92-5693-8396-284bef29d748 | note | Standard / Specification - PS 18.2.3, PS 18.2.1, PS 18.2.2
fc4415db-92a4-55ac-8d4b-0e6e25a96741 | note | Verifying Document - Site Records
2ececa43-b21f-5608-962d-3fc12384d9c8 | note | Frequency - Each Occurance
72d643a1-ac3f-5e02-a681-976acd416ab3 | note | Verification Activity: Activity - S
a4d65f50-b196-55c8-90ce-d8f97ca0ed1c | note | Verification Activity: By - SE
6d84a5a0-7520-57aa-82ee-ef4795e600e1 | section | 9.02 Monitoring Points and Survey
76a4b818-9153-529a-98b6-e3149cf8e43a | checkpoint | 9.02.1 - Monitoring Surveys / Deformation Surveys
c300a3d3-d349-5468-a0bf-6c721b677914 | note | Acceptance / Conformance Criteria - Monitoring / Deformation Surveys shall be completed on all Structures as agreed with the engineer using installed monitoring pins or fix location on structures.
652d7972-ffde-559c-b8f2-01ea6b7223fd | note | Standard / Specification - PS 18.7.1
d73cab2f-6b66-5fb6-86df-cd38f9f39906 | note | Verifying Document - Survey Records
61956925-b70f-5130-87a8-d9905e43b624 | note | Frequency - As Required
77f9d864-fcf2-5c04-9588-fd3db4c95e9d | note | Verification Activity: Activity - I
f7e6927a-f1e2-53ff-b9e7-c60258f45e33 | note | Verification Activity: By - SV
0f87aceb-230c-445c-bce9-472d50eb0dd7 | checklist | Ω (DEPRECATED) ITP - Stormwater (Structures) - 202 - (alternate Rev B) | itp | ITP - Stormwater (Structures) - 202 - Rev B
e48adf96-a921-5393-9ab6-5ff61a725470 | section | 1.01 Stormwater Aggregate Materials
a95ca035-74c8-594b-8085-a1d9aa423a24 | checkpoint | 1.01.1 - Controlled Low Strength Materials - CLSM
b9cb59d3-622b-5902-82ee-48040e0dc331 | note | Acceptance / Conformance Criteria - The use of CLSM by the Contractor will require approval from the Engineer on a case-by-case basis.
d554de1a-f0a4-5766-9fab-bcabe212688d | note | Standard / Specification - PS 16.8.1, PS 16.37
fd9db4d6-b13f-578c-8a31-3a884af41cc9 | note | Verifying Document - Engineers Approval
293ada82-74e5-50ff-abe1-0c3759c6dfc0 | note | Frequency - An application submitted to the Engineer for approval, to use CLSM.
a0d796f0-ae9b-550b-83fb-f5fb3235c7bc | note | Verification Activity: Activity - HP
d9065f6e-0e33-5678-b156-92376f309262 | note | Verification Activity: By - ENG
cb3b8a82-5309-5c00-9c64-feba92dfeae8 | signoff | AUTHORITY HOLDPOINT
25ba88a4-4910-5004-8d64-eec2b2d9f977 | checkpoint | 1.01.2 - AP65 Aggregate
af80170f-9aed-5408-bec8-4a356e26bf00 | note | Acceptance / Conformance Criteria - AP 65 Aggregate is to be a crushed product with a maximum granule size of 65mm and be a graded, clean durable aggregate which meets Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities requirements
bee0afb1-20d8-5697-b6a2-6c782b16c71a | note | Standard / Specification - PS 16.8.2.1, PS 16.9.1.2, PS 16.6, PS 16.37
c4a66042-2771-5b74-a492-ca79dea11dba | note | Verifying Document - IANZ Lab Reports
13ea5eba-d119-5ef1-b17c-3554240289eb | note | Frequency - Submitted to Engineer for approval
cd7d29b9-6f4c-5665-b93d-90316e17cf36 | note | Verification Activity: Activity - HP
d7fdc9ce-90a5-5e16-b637-b1f83456885d | note | Verification Activity: By - ENG
d104ba0f-f41a-5817-8d54-5b844a37c26a | signoff | AUTHORITY HOLDPOINT
6dd2f2ca-856f-5198-a519-10cfd10b5e41 | checkpoint | 1.01.3 - AP40 Aggregate
0d99e137-981e-585d-900b-c0c4ba5ebe81 | note | Acceptance / Conformance Criteria - AP 40 aggregate is to be a crushed product with a maximum granule size of 40mm and be a graded, clean, durable aggregate and which meets Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities requitements
47ee1303-2574-50ae-b3c6-beb51f336151 | note | Standard / Specification - PS 16.8.2.2, PS 16.9.1.2, PS 16.6, PS 16.37
6e63f27c-18db-5df0-9168-7215f6097c85 | note | Verifying Document - IANZ Lab Reports
71d6a36c-6da9-5b27-ad80-11fc671a8e9f | note | Frequency - Submitted to Engineer for approval
94a9d1bf-48a9-59d5-9052-be3d45e3b182 | note | Verification Activity: Activity - HP
d1d25752-f92f-530a-ab79-2acc8f9d8256 | note | Verification Activity: By - ENG
c5c5034d-17c0-530a-a8db-4f8cf9313412 | signoff | AUTHORITY HOLDPOINT
60b51c6d-53b8-52b8-86b9-6f6cb8e7a404 | checkpoint | 1.01.4 - AP20 Aggregate
8752c5af-e588-5e11-b8bc-3ac23a4c8173 | note | Acceptance / Conformance Criteria - AP 20 aggregate is to be a crushed product with a maximum granule size of 20mm and be a graded, clean, durable aggregate and which meets Grading, Linear Shrinkage, Weathering Index, Crushing resistance, Maximum and Minimum Dry Densities requirements
852076c2-b933-5c7d-9cb6-66271e63669f | note | Standard / Specification - PS 16.8.2.3, PS 16.9.1.2, PS 16.6, PS 16.37
b360cd9b-409d-59ba-9154-d674c6997095 | note | Verifying Document - IANZ Lab Reports
c6b0b3a7-6dcf-50c1-9752-a9b5e6c216f4 | note | Frequency - Submitted to Engineer for approval
84aee3af-5288-58df-8681-3745321c5d83 | note | Verification Activity: Activity - HP
36d91c27-e601-58f0-bfc9-7e77fbbbba59 | note | Verification Activity: By - ENG
c815d7ea-eda2-5e1b-92bd-9dc6bba41adc | signoff | AUTHORITY HOLDPOINT
218c5f06-0ccd-560e-b6b0-c9b027b59a28 | checkpoint | 1.01.6 - Alternative Bedding
a85001ed-6c8b-5551-9216-b5b9ec0d7a89 | note | Acceptance / Conformance Criteria - If the Contractor wishes to propose a different material from that specified in this section, the Contractor shall submit to the Engineer
cdd195da-360a-5eb0-9f67-da0bb290ce41 | note | Standard / Specification - PS 16.9.2.1, PS 16.9.1.2, PS 16.37
094abc90-e93f-59f2-8f58-4a3416f1fec3 | note | Verifying Document - Statement from the concrete pipe supplier
2a6a8f95-5476-5bd0-909d-f9d7bc293854 | note | Frequency - Submitted to Engineer for approval
7853bd94-b417-5dfe-865f-db7f733661b9 | note | Verification Activity: Activity - HP
f0e0455f-bafc-5c44-9fdb-2cfb183fee07 | note | Verification Activity: By - ENG
fa2dd314-75f8-5cd2-8157-2cf844b50ad4 | signoff | AUTHORITY HOLDPOINT
878ad85c-37ec-5b05-aa55-b8b309cd8376 | checkpoint | 1.01.7 - Overlay Zone Material (for concrete pipes)
73d0dffb-72de-5c06-abf2-f02ee29527da | note | Acceptance / Conformance Criteria - Materials for the overlay zone GAP 20 shall be used which has been tested for Grading, Weathering Index, Crushing Index
c1fc6083-d497-512b-899f-211d02bc7bb0 | note | Standard / Specification - PS 16.9.2.2, PS 16.37
78c23021-09c1-50ce-b93d-a1424387d6c7 | note | Verifying Document - IANZ Lab Reports
4b9eaaa1-c003-502f-a6c4-adc0743d8a8e | note | Frequency - Submitted to Engineer for approval
eb0d75c9-c21d-52e8-837d-9d2632d925b0 | note | Verification Activity: Activity - HP
674ddbf1-b044-5339-b386-a5448fe068f7 | note | Verification Activity: By - ENG
f8091fef-c776-5fa2-af04-7a9b6e0462dc | signoff | AUTHORITY HOLDPOINT
4a4e4a8a-7cb6-582c-93dc-909ff02072ba | section | 1.02 Stormwater Pipe Materials
69e09f41-d841-56ba-b5dd-cc6933a78e4f | checkpoint | 1.02.2 - Steel Work
7983486e-24cd-50d5-a88a-077d77907780 | note | Acceptance / Conformance Criteria - Unless otherwise specified, all steel work shall be fabricated from mild steel conforming to the requirements of AS/NZS 3679.1:2010 and AS/NZS 4680:2006. All cut surfaces shall be protected with a corrosion protection coating i.e., zinc rich paint.
096536d9-25d7-5385-a9ab-7329e68ac748 | note | Standard / Specification - PS 16.8.1, PS 16.8.4
a67baf84-4f4e-5af7-9f49-3d508d370eb0 | note | Verifying Document - Datasheet
8e8f3895-996a-571f-8a07-9807f33a4bf9 | note | Frequency - Prior to use
259e532f-e49b-52fa-a769-9900f1bcbbce | note | Verification Activity: Activity - R
c6d0f086-4e55-5120-9b06-7082f5a74ce6 | note | Verification Activity: By - SE
60ecbba7-61f7-5ae0-85a1-a18bef3de7c5 | checkpoint | 1.02.4 - Steel Fitting Corrosion Protection
01185b10-0157-5713-b427-207939b2ade7 | note | Acceptance / Conformance Criteria - Steel fittings shall be shop assembled as large as practicable before hot dip galvanising or zinc metal spray to AS/NZS 2312.2:2014 and AS/NZS 4680:2006, to minimise the number of field welds and bolted joints required.
25ea048e-44e9-5283-8d13-d016e3882bcc | note | Standard / Specification - PS 16.8.4.1
baa12f3d-f909-5cfb-8bf9-7107d00dcbe0 | note | Verifying Document - Datasheet
3b0dd7b1-6557-5e42-b3be-12318e43d8f1 | note | Frequency - Prior to use
35ab5a0f-10e0-5d1b-8df2-6eadfb534c2a | note | Verification Activity: Activity - R
2a194199-2148-53af-9e58-783ccc2f0809 | note | Verification Activity: By - SE
64f50980-c6f3-5fcc-9255-86d784630f99 | checkpoint | 1.02.5 - Hot Dip Galvanised
b513d5d2-10aa-5f60-89c6-58c9d7e3abda | note | Acceptance / Conformance Criteria - All ferrous metalwork except standard galvanised pipe shall be hot dip galvanised to HDG900 unless otherwise specified.
5d82e457-0b21-59b4-9eba-46c2b85cc2a0 | note | Standard / Specification - PS 16.8.4.1
1a0913ce-7898-56e3-892a-ed544fffcb61 | note | Verifying Document - Datasheet / Cert
b7fa39ed-7c9f-533f-a6b4-0b740b67c96b | note | Frequency - Prior to use
a9c395dc-0d70-5ef4-85ae-4190b4c6b5dd | note | Verification Activity: Activity - R
f08d80a0-bb58-5b29-bd7c-ee503311a19c | note | Verification Activity: By - SE
2fc23d9c-901d-57bc-b711-629672507c09 | checkpoint | 1.02.6 - Fastenings
1b59b4f3-9733-5b2b-a421-64721b8a2f98 | note | Acceptance / Conformance Criteria - All fastenings associated with manholes or drainage structures shall be either hot dipped galvanised or stainless steel. Zinc Plated fastenings shall not be permitted
8fbbe4db-f8ac-5d54-8095-fd3bd975af7c | note | Standard / Specification - PS 16.8.4.2
05cafc36-f9b1-58d4-95d1-2579f2dea1b3 | note | Verifying Document - Datasheet
3df46a37-58ed-533e-b9e5-00d053f7dddb | note | Frequency - Prior to use
d14e8d20-e9f8-5d12-b4c3-5bc088c6d24c | note | Verification Activity: Activity - R
6c9ac783-c583-5a72-911d-15db94b028e5 | note | Verification Activity: By - SE
35d72f2d-cc19-5c7a-90cc-ec774c712f02 | checkpoint | 1.02.7 - Concrete pipes and fittings
bd5c47f4-cf1f-50dc-8976-169e73db3ae0 | note | Acceptance / Conformance Criteria - Concrete pipes and fittings shall comply with the requirements of AS/NZS 4058:2007 for concrete pipes
1731c56c-d3a6-5dad-aca8-69a3ba67f45f | note | Standard / Specification - PS 16.9.1.1, PS 16.37
775f9007-c66b-5956-8a36-44d03630cc33 | note | Verifying Document - Datasheets
66c80b3d-245b-5bf8-a54f-fd82cf27bf23 | note | Frequency - Prior to use
eb064c25-c76c-5ed0-affe-481bf3ed01b1 | note | Verification Activity: Activity - W
386e7a4c-f276-54f6-92f6-7be2b7ac52f1 | note | Verification Activity: By - ENG
f5e951c8-6f34-5e62-aa3c-51bb1cf65da1 | checkpoint | 1.02.8 - Quality of Pipe and Precast Units
645f8a5c-6968-5a6e-9c36-2decea5a5c54 | note | Acceptance / Conformance Criteria - IANZ Accredited Manufacturers certificate to NZTA F/3 (refer to Appendix F)
effdac09-57ab-5c96-9fa7-9c71b362880a | note | Standard / Specification - PS 16.34
340eb304-3e6a-5a2c-b3f2-e90da12f49de | note | Frequency - For every pipeline delivered (as soon as they are delivered)
e84e9ff3-3308-5e82-b5e6-74a8c9354723 | section | 1.03 Stormwater Structure Materials
91fce285-1472-507c-b6a3-7c424a6057d7 | checkpoint | 1.03.1 - Precast Catchpits
e407ffbd-9200-5da7-8e25-bd5b9f3d1b32 | note | Acceptance / Conformance Criteria - All catchpits shall be precast concrete suitable for HN-HO-72 traffic loading.
87577e7f-5f3f-57fe-ba74-a703edcfd570 | note | Standard / Specification - PS 16.10.1
8ceb1190-a1de-51bb-88c4-3d29675f7809 | note | Verifying Document - Datasheet
ca0b164a-0c34-5e15-b97a-2254b55e46c8 | note | Frequency - Prior to use
7894f69f-6143-5628-a852-3155e5566e76 | note | Verification Activity: Activity - R
c902d63f-8497-5ec0-a66e-4f94fb56a84c | note | Verification Activity: By - SE
56cb0cef-ffb7-59aa-8cfc-680a0a3fe297 | checkpoint | 1.03.2 - Catchpit Lids
e6170961-e3f3-502c-9fa2-e7510f1f4cae | note | Acceptance / Conformance Criteria - Non-Rock 510mm Class D Heavy Duty type lids or similarly approved shall be used unless otherwise specified on the drawings. Heavy Duty type lids to be suitable for HN-HO-72 traffic loadings that are cycle friendly.
bd39b4d6-1ae8-5971-8291-8e90c4274f69 | note | Standard / Specification - PS 16.10.2
5e113349-3b70-5825-8b06-060f2df94543 | note | Verifying Document - Datasheet
d909513c-266a-59da-a468-cc109b3621ff | note | Frequency - Prior to use
8b226bac-b2e0-5a85-943a-14307bb421ad | note | Verification Activity: Activity - R
12c18111-0bd8-55c3-a804-82722e87321e | note | Verification Activity: By - SE
130a6f97-8fb9-504e-bcea-a3dfe8267d7c | checkpoint | 1.03.3 - Precast concrete manhole
634be762-717c-515c-a554-d8979387f70c | note | Acceptance / Conformance Criteria - All precast concrete manholes shall be manufactured in accordance with NZS 3109:1997. All manholes shall be suitable for HN-HO-72 traffic loading.
ca8a9af4-798e-50fd-9e4c-3b5ec7898656 | note | Standard / Specification - 16.15.1
420f8c7e-04f9-59fb-ab74-7fc35388c82a | note | Verifying Document - Datasheet
b1584ed3-02ad-5e48-9c73-8390b3407f96 | note | Frequency - Prior to use
227984e3-99ed-57ad-95cc-c3048e175ddf | note | Verification Activity: Activity - R
c063324e-399e-58e1-b115-43ed816dab2f | note | Verification Activity: By - SE
3000c124-dd41-5f1e-9807-ca9596c2438a | checkpoint | 1.03.4 - Catchpit Grates and Frames
7453bb2e-b4ad-51dd-9022-e5680ffe2cd4 | note | Acceptance / Conformance Criteria - Catchpits grates and frames shall be grey cast iron suitable for HN-HO-72 traffic loadings.
33d34d62-d9ad-5330-b2b5-b6de920f060f | note | Standard / Specification - PS 16.10.1
380387b8-ed28-5375-a13c-4823092ea855 | note | Verifying Document - Datasheet
29e240df-4bbb-5c0d-9430-412f7612a924 | note | Frequency - Prior to use
fd3c952a-02b6-5538-8278-9f9afdd806ac | note | Verification Activity: Activity - R
f6f94745-3ea0-5aa9-95a9-ecdd44c3b113 | note | Verification Activity: By - SE
14e1a3a3-be4a-5b23-8bcf-99effdb4e476 | checkpoint | 1.03.5 - Scruffy domes lids
4723b51d-d9f5-53fa-99d6-78bd334e89d7 | note | Acceptance / Conformance Criteria - Scruffy domes lids shall be galvanised steel Hynds Type 2 scruffy domes (unless noted otherwise in the drawings), or similar approved.
4e4d8c5e-c79d-5145-b794-2d0297d94056 | note | Standard / Specification - PS 16.16.2
93555c26-b70e-51b5-a4f5-21678789eb95 | note | Verifying Document - Datasheet
25a85b6d-506c-59a5-be45-0512b40f6556 | note | Frequency - Prior to use
fe1d8a9b-ab9d-503e-a92d-fb29067fb9de | note | Verification Activity: Activity - R
cac01b62-8654-5dd6-9bb0-1bb924597fea | note | Verification Activity: By - SE
cf286ccb-3176-5052-9aa2-4d85340f725f | checkpoint | 1.03.6 - Cement Mortar
7cc40a29-dfc7-5c71-bb96-d455b3dfbcfe | note | Acceptance / Conformance Criteria - Cement mortar shall be Durability Class M4 in accordance with NZS 4210:2001, with a minimum compressive strength of 12.5MPa.
3bec60e2-bed1-5d40-87da-604172d29ee4 | note | Standard / Specification - PS 16.8.1
48a9e6b5-f12f-5ebb-8a40-aa28c96b3a3e | note | Verifying Document - Datasheet
b8172244-144e-56dc-ada3-fe04a0d79433 | note | Frequency - Prior to use
63fa2a58-3fa3-59d6-81a3-1a7e80f98de3 | note | Verification Activity: Activity - R
d22fba64-a915-50fb-8599-28b0232fa4de | note | Verification Activity: By - SE
254f5570-ad69-595d-a595-909b315f255c | checkpoint | 1.03.7 - Epoxy Mortar
f2d4d949-c995-5eb8-b960-03edc644762e | note | Acceptance / Conformance Criteria - Epoxy mortar for use in manhole riser joining or repairing of damaged or cut concrete (to provide cover to reinforcing due to cutting of precast units) shall be Hynds (MSR) or Humes Hume bond (or similar approved), applied in accordance with the manufacturer’s recommendations.
71d12180-4709-548f-b9fd-e42220292653 | note | Standard / Specification - PS 16.8.1
ac466c57-262c-593d-865b-8e021eafb278 | note | Verifying Document - Datasheet
d5ae3c63-f547-5786-9da6-99bcaa04f4cb | note | Frequency - Prior to use
d384304a-0ceb-5f2d-888a-0af115e6cd57 | note | Verification Activity: Activity - R
9dc04b08-af9e-5e8d-a29f-397601fe007d | note | Verification Activity: By - SE
b290cd34-1606-50fd-995d-df90428ff8a7 | checkpoint | 1.03.8 - Precast Headwalls and Wingwalls
2aea9831-44c8-502d-9cb4-31bfea24869e | note | Acceptance / Conformance Criteria - Precast concrete headwalls or wingwall units shall be manufactured in accordance with NZS 3109:1997.
b466059e-18fa-56e3-b8cf-ddeef46ef999 | note | Standard / Specification - PS 16.13.1
48868a3c-d614-5565-a13b-3b8f5032cb2e | note | Verifying Document - Datasheet
f4edb9cc-17ef-573d-9611-0b663f37b336 | note | Frequency - Prior to use
88a8147e-3ae8-586e-bc5a-79c822b94136 | note | Verification Activity: Activity - R
972e5ea3-2701-56c8-8ea7-03dc2399cec3 | note | Verification Activity: By - SE
6d0f6d8c-7ec1-5e25-8613-a36245635455 | checkpoint | 1.03.9 - Erosion protection matting
8eb1e8c5-c77a-5966-adaa-594f0a07fcbc | note | Acceptance / Conformance Criteria - Erosion protection matting (coir Blanket or similar approved) is to be 100% biodegradable.
c6b9dac9-8519-5998-9374-3b2b45d725c4 | note | Standard / Specification - PS 16.13.1
29ecd1a9-bd78-5f4a-a647-f5557c620ca5 | note | Verifying Document - Datasheet
3d8ed03f-0f2e-5d3c-8f31-577b8d129216 | note | Frequency - Prior to use
5f1a4837-9a24-52cd-8f2c-b3337d7cc032 | note | Verification Activity: Activity - R
b118e925-1b38-51f6-9362-5aef40b69302 | note | Verification Activity: By - SE
0a061ecb-47c1-5451-be12-856fee80de39 | checkpoint | 1.03.10 - Precast Soakage Pit
649e01bd-8154-573f-a3cd-3a6bf4c78811 | note | Acceptance / Conformance Criteria - All precast concrete Soakage Pit manholes shall be manufactured in accordance with NZS 3109:1997.
da94e9ba-3fa9-5a42-a147-241634ca73f7 | note | Standard / Specification - PS 16.12.2.1
343f10c2-efa2-5d81-957c-64c8e8bdb937 | note | Verifying Document - Datasheet
9800ac4e-fc96-5395-950d-8f5d97f3c838 | note | Frequency - Prior to use
d7130151-50ad-5933-8505-02ac8efcc1fd | note | Verification Activity: Activity - R
9a83194e-2fcc-5fd2-829a-4671ef5e4184 | note | Verification Activity: By - SE
10e6e077-15d2-56b2-ae1c-2a0894025b52 | checkpoint | 1.03.12 - Manhole Sealant
b1fba66c-fa51-5ab6-81a5-9257673353b1 | note | Acceptance / Conformance Criteria - All joints between ring segments of precast manholes and chambers shall be sealed with ‘Grey Butyl Manhole Sealant – Hynds (SM9020)’ or similar and approved.
caf60dd5-2587-512e-bbdd-38748f7b581a | note | Standard / Specification - PS 16.12.2.2
5ec3bfd4-4b89-5406-ab56-a51192d66787 | note | Verifying Document - Datasheet
f7f757c0-2fc8-5eda-9eef-951f1d89f780 | note | Frequency - Prior to use
c0d00499-e831-54eb-9b2e-23ab7d09c556 | note | Verification Activity: Activity - R
4e5d5d68-8c05-5b42-8538-4830a13ae01f | note | Verification Activity: By - SE
a0739509-7e17-5960-a813-ae432cb4ebad | checkpoint | 1.03.13 - Head and Wing wall Insitu Concrete
11245d58-c1be-5a1a-8561-10399a85f634 | note | Acceptance / Conformance Criteria - Headwall and wingwall insitu reinforcing shall be steel grade 500E.
83fd79c8-c568-5f06-b17b-fa3bfd3e896d | note | Standard / Specification - PS 16.13.2
ca6591b6-ef01-56bd-a720-fd5ada9551f6 | note | Verifying Document - Mill Certs
b8d16d43-5094-524b-a9b2-ca92ec2bacc3 | note | Frequency - Prior to use
d1f6fdc0-3c1e-57a9-9054-59c64e60d928 | note | Verification Activity: Activity - R
c16fa753-e1b4-54ed-a760-2245d5fd5043 | note | Verification Activity: By - SE
de604162-2266-58c3-bfef-680800f0396a | checkpoint | 1.03.14 - Head and Wing wall Reinforcing
847b76a9-15d5-55c4-b19c-eb2c5a847275 | note | Acceptance / Conformance Criteria - The headwall and wingwall cast in-situ concrete shall be 40MPa
d9d7a9b3-c50c-5307-a76a-28e05a25bf40 | note | Standard / Specification - PS 16.13.2
dd353d74-2cb8-56cb-8460-a70faefad9b6 | note | Verifying Document - Mix Design
7ca5b1a0-d31f-58f7-93ac-dbaaf779d679 | note | Frequency - Prior to use
14f6f916-9c9c-5212-9cec-e45904c012ad | note | Verification Activity: Activity - R
32984417-a5f4-58d6-99d3-db5e7d3b819e | note | Verification Activity: By - SE
0e382e0a-0547-590f-bae7-3624e64784f6 | checkpoint | 1.03.16 - Benching Concrete
928c057a-d29f-5ffd-9593-552cb38134d0 | note | Acceptance / Conformance Criteria - Benching shall be 20MPa concrete
9df84dda-e75c-5d87-93b0-1a1ccc670043 | note | Standard / Specification - PS 16.15.2
04317dcd-5b01-5c4b-9300-a09ab978053d | note | Verifying Document - Mix Design
05b8be1e-8ffd-5b62-b63d-ccce3b85adfa | note | Frequency - Prior to use
c1838719-7c4e-5bad-8f7a-ffd337adbe42 | note | Verification Activity: Activity - R
b0282277-0faf-5295-93be-7133bab0b29d | note | Verification Activity: By - SE
3f8a50a6-974f-54d2-989e-817719c48b96 | section | 2.01 Stormwater Drainage (Existing Assets)
9e4cc768-b88c-500f-afbb-8755a862e601 | checkpoint | 2.01.1 - Obsolete Stormwater Structures
2c3d3a9c-b156-5097-ba15-7a0782b26fa6 | note | Acceptance / Conformance Criteria - Obsolete catchpits, manholes, kerb and channel shall be demolished, uplifted and removed to an approved tip site.
31173915-c7cd-5f74-9e62-c25e15a35923 | note | Standard / Specification - PS 14.2.1
0e6c9191-8281-5d8e-bdec-7784bbdf645f | note | Verifying Document - Site Record
504dcb0e-f3f8-56a6-981a-a8725478c73a | note | Frequency - Each Obsolete Structures
00a8535f-eec8-5fab-ab44-c16900a827ac | note | Verification Activity: Activity - R
6f3ca366-5b19-5a6c-b489-12eabf0934d2 | note | Verification Activity: By - SE
c7f50f69-b0f9-5fdc-8f19-342f12ec544b | checkpoint | 2.01.2 - Cutting Existing Pipes
747c8d6f-5003-5245-8865-225a4eae1ad0 | note | Acceptance / Conformance Criteria - Where the catchpit will be replaced by a new drainage structure and/or constructed in a new location the existing stormwater pipe shall be neatly cut perpendicular to the line of the pipe to allow it to be easily extended.
043b091e-ccd0-5604-b95c-01ec23a83c89 | note | Standard / Specification - PS 14.2.2
70cd7d22-0581-5e3b-9735-36bdd4a03618 | note | Verifying Document - Site Record
dc9b9aeb-7227-58a1-b53a-b0365ca89b19 | note | Frequency - Each Occurrence
4ab71c05-9078-50f8-8dfd-bac50912375d | note | Verification Activity: Activity - R
f5bffa36-df23-5049-8e3e-f04aa5756571 | note | Verification Activity: By - SE
4825206e-1201-5e97-939a-dd7bb149a61d | checkpoint | 2.01.3 - Debris Removal and Void Filling
00ae3615-b5f8-5515-94bb-cc4af1790b3b | note | Acceptance / Conformance Criteria - All debris shall be removed to waste. The resulting void shall be backfilled with well compacted approved fill material.
91a12ac3-25c7-566b-abb0-fefe6dfa0cca | note | Standard / Specification - PS 14.2.3
59b99207-5c92-5b0f-a4c1-38b1f9762fa8 | note | Verifying Document - Site Record
b3dd4f55-1940-51f5-b8a9-d5b14a8c3cc6 | note | Frequency - Each Occurrence
4c9006bc-ce0a-54e5-93ea-32a656e3b7b9 | note | Verification Activity: Activity - R
2f04c4ac-fc2c-5b19-8eea-b4af3bf524f2 | note | Verification Activity: By - SE
7d731da0-9d36-5dc2-bbaa-36fd489fe260 | checkpoint | 2.01.4 - Obsolete culverts
64a008ec-0d3d-565f-a7e7-15e9e3229bec | note | Acceptance / Conformance Criteria - Obsolete culverts shall be removed or may be left in place subject to the agreement of the Engineer. Abandoned culverts shall be plugged with concrete at each end or if the culvert is within 1.0m of the surface it shall be completely filled with a cement grout.
43d90bc1-c134-5f6c-aa7a-a4cb1dce5bbb | note | Standard / Specification - PS 14.2.4
1a18f3e3-6c2e-5f7e-8b12-ff9be1c34d9b | note | Verifying Document - Site Record
17297358-32fe-5c3e-892b-c9de06eef71f | note | Frequency - Each Occurrence
0f0f5c08-98a1-5108-b306-bd9adf7ac08f | note | Verification Activity: Activity - HP
bb150a45-ee07-55a1-9ca5-6948c1428315 | note | Verification Activity: By - ENG
07db67e3-cab4-5ae7-ac32-126b928f841a | signoff | AUTHORITY HOLDPOINT
fafc21ec-637c-525a-8389-661e2d0e99f5 | section | 3.01 Stormwater General
a210fb2a-8fbf-5a1e-b274-262fc5b0bdb3 | checkpoint | 3.01.1 - Setout
885e5323-57d8-5a8e-8c9c-69f94e63bfc0 | note | Acceptance / Conformance Criteria - Prior to the commencement of any drainage works for a particular drainage line, the Contractor shall set out the line, level, and position of the proposed drainage line, including inlet and outlet positions and levels, and present it to the Engineer for their consideration. The Contractor shall provide at least 48 hours’ notice to the Engineer ahead of set-out and allow 48 hours for the Engineer to respond prior to commencing work.
a1a93af7-9b43-51ef-bc2a-c6ab37b27930 | note | Standard / Specification - PS 16.6.1
da135260-1772-5a7f-b957-b57a6f72a4b6 | note | Verifying Document - Survey Records
6463a494-9a7f-549e-b734-fca2b7301daf | note | Frequency - Prior to the commencement
c3f2d9fe-1cf3-5d58-8d66-3279709c13ef | note | Verification Activity: Activity - HP
0fbb3873-7a54-56b0-8c33-adb06319ad03 | note | Verification Activity: By - ENG
1de8f978-8a84-5ff3-a1fb-37a4c0083aee | signoff | AUTHORITY HOLDPOINT
654daa1a-e7a3-569d-81c4-4329920ea593 | checkpoint | 3.01.2 - Dealing with Water
e37040ee-67a4-5058-bddd-36d0b3da0335 | note | Acceptance / Conformance Criteria - The Contractor shall maintain all trench inverts free from flowing or accumulated water. Water arising from, or draining into, the trench shall be drained or pumped. Any sumps required shall be refilled to formation level as directed by the Engineer.
de17876a-efdd-5ba7-9620-afee920b2a56 | note | Standard / Specification - PS 16.7.1
ceacfe1a-148e-5994-9711-e757a9db3c38 | note | Verifying Document - Site Records
c22ecdcc-0b52-5ca0-a9b6-402c2b0a5cd4 | note | Frequency - During Works
852d3cca-741a-5c6b-bae5-c08aab69d59d | note | Verification Activity: Activity - S
83d23992-8d12-589d-bac6-5768b9173ac3 | note | Verification Activity: By - SE
4f09ae7c-2a93-5390-810b-532208062fd7 | section | 3.02 Pipe Installation and Backfill
4783c80c-dbfc-527d-b81d-044fdec625f6 | checkpoint | 3.02.1 - Open Trenches
09aa8ea3-d78c-5998-a238-4b3026117470 | note | Acceptance / Conformance Criteria - All open trench excavations for pipelines shall be to a minimum depth of 100mm below the pipe external walls. Where excavating in natural ground or existing carriageways, no more than 100 metres of trench (per drain laying operation) shall remain open at any one time.
88a69342-365e-5e42-a7e8-e3c6c51fca3f | note | Standard / Specification - PS 16.9.2.10
902b85a7-4238-5c3d-806d-1ecd05255206 | note | Verifying Document - Site Records
4c1d8f7d-813a-521e-a636-9694c762f276 | note | Frequency - During Works
da90614b-9307-53fd-b41d-fe6c6505e67b | note | Verification Activity: Activity - S
125dce34-a0b8-5c8e-9aa3-89d65eeb7792 | note | Verification Activity: By - SE
79d789f7-cd98-5db7-b2f4-1f8fdbbb5348 | checkpoint | 3.02.2 - Saw Cutting
7083baa1-f4ba-576a-9369-c64c5cd7ce85 | note | Acceptance / Conformance Criteria - Where trenching through roads, prior to excavation, the surface shall be saw-cut a minimum of 100mm beyond the trench wall and parallel to the proposed alignment.
a0c13b34-28e9-56eb-8a82-c6e5b95af9ac | note | Standard / Specification - PS 16.9.2.10
cf928557-7adc-596e-904a-56ec05e0b42f | note | Verifying Document - Site Records
4104cdb9-cc9b-500b-871f-c0111fa2e36d | note | Frequency - During Works
d86780b1-d4c5-5e9d-abf9-5e44c4bdd0cf | note | Verification Activity: Activity - S
00ba596c-9795-5d07-8837-a5a71c95e0cb | note | Verification Activity: By - SE
6afb86e1-05de-5ae2-af76-09e9e705fa80 | checkpoint | 3.02.3 - Stability check
47b6fbab-02d3-5836-97ee-8511a70f8f3b | note | Acceptance / Conformance Criteria - Where trenching is near new or existing structures (within 5m horizontally, or where the trench invert is below a plane projected downwards at 1(V) in 2(H) from the base of the structure), a stability check shall be undertaken to ensure undermining of the structure is avoided. The Contractor shall undertake a stability check in these situations.
65869707-4fe2-58ed-b155-b3d7f914ca95 | note | Standard / Specification - PS 16.9.2.10
24b41d81-4dbb-5068-b0b2-ab34686eb8f3 | note | Verifying Document - Site Records
421bc9e6-cc7a-5ae7-9b74-578305ddcb58 | note | Frequency - Each Occurrence
c41ed935-4c7a-5e88-a959-ecb8e593f2cb | note | Verification Activity: Activity - S
7c04dfdc-5014-552b-bdb3-c3c5864e58fa | note | Verification Activity: By - SE
e9ca101b-c573-5a5a-8cd3-20d24be499e4 | checkpoint | 3.02.4 - Trench Width
1382f0b1-e246-5e57-b1b5-bbf95fbb4846 | note | Acceptance / Conformance Criteria - The minimum trench widths are as indicated on Drawing WD-0131 but not less than the external pipe diameter plus 600mm and not more than the external pipe diameter plus 1200mm.
89af5cbd-572b-5da8-bbfe-fa831f19db81 | note | Standard / Specification - PS 16.9.2.10
6fb17de3-604d-5920-99ed-204096c22c36 | note | Verifying Document - Site Records
aed67127-c926-57b1-8a8a-9a6f3d561375 | note | Frequency - Each Pipe
101b3e87-da0a-5028-91fc-d6aaab781a46 | note | Verification Activity: Activity - S
98913d78-758c-5c78-992c-291397a970db | note | Verification Activity: By - SE
58a4d71f-6dbc-5a10-a296-7ed58b085508 | checkpoint | 3.02.5 - Unsuitable Material
c6296427-fd57-57c3-b04f-ea539a1fe192 | note | Acceptance / Conformance Criteria - All material deemed to be unsuitable shall be removed to a depth of 600mm or a greater depth as specified by the Engineer, until suitable material is reached.
c8cac576-c80e-519a-999d-fbe4ecb38f6d | note | Standard / Specification - PS 16.9.2.10
0d96338e-1a5a-56c4-9c36-899cb10f1543 | note | Verifying Document - Site Records
45547264-56db-57ea-8512-83b968e480f2 | note | Frequency - Each Occurrence
d8af951d-38ea-5c47-aec6-e9bc9dd3268a | note | Verification Activity: Activity - S
20405893-728a-5401-a025-cda48715762b | note | Verification Activity: By - SE
ea7ad893-3773-5813-936f-69f88f144761 | checkpoint | 3.02.6 - Trench invert subgrade inspection
bace89a8-4114-5657-81a1-40b92186c5df | note | Acceptance / Conformance Criteria - The Engineer shall have the opportunity to complete a Visual Inspection to NZTA F/3:2010 on the trench subgrade each day on each pipeline during installation.
00ea6f44-a237-5f33-aab0-a38ae488e46d | note | Standard / Specification - Suitability
20479204-28f3-5202-92fd-1ae43a431474 | note | Verifying Document - Engineers Record
c73433d7-959b-5a93-a184-87741fdb7a61 | note | Frequency - Daily
728831df-b427-54c1-a8a4-4f4bd16296c2 | note | Verification Activity: Activity - WP
2c263ad2-49c7-5642-84b3-8f731b614797 | note | Verification Activity: By - ENG
d818a004-d73b-5d9a-b27c-6159bea11363 | checkpoint | 3.02.7 - Trench invert subgrade testing
8b34e583-94dc-5dfb-b119-bd27d6f83fff | note | Acceptance / Conformance Criteria - The subgrade shall be tested for CBR>5 by Scala or shear vane. This test shall be undertaken at the design subgrade level and at a depth of 300mm below the design subgrade level.
08fcbbae-abb7-5e65-b1b2-c4fe011ef492 | note | Standard / Specification - PS 16.9.1.3, PS 16.32.3
95b337db-a279-5b5a-a0c7-27a2721b36bd | note | Verifying Document - Scala or Shear Vane Report
437ab222-615b-5929-9da8-43c25d6a192d | note | Frequency - 1 per 15m trench length Minimum of 2 tests between pits/manholes
5a2fadf0-aebc-5245-bc96-3eafea8e905a | note | Verification Activity: Activity - I
dca8baf3-bc11-5d22-84ab-f82af75330a5 | note | Verification Activity: By - SE
270c1a1e-7412-5580-a7d8-4802dc5d53ca | checkpoint | 3.02.8 - Subgrade Undercut and Replacement
4676078b-2efe-5dc6-81cb-0e0a70c92c55 | note | Acceptance / Conformance Criteria - The insitu trench base shall be tested and if CBR is less than 5, it shall be undercut and backfilled with AP65 compacted to compacted to a MDD of 90%
a668908e-2871-52bc-a3c7-42391c06b4b7 | note | Standard / Specification - PS 16.9.1.3
6e6c8c2c-9779-5dc9-bd5a-27df674a3f76 | note | Verifying Document - Site Records / NDM / Clegg Report
378e22fe-6714-51fa-976a-92b94c3fc07b | note | Frequency - Each Occurrence
ee1a250d-8642-5b6d-ac2b-1416d50fd965 | note | Verification Activity: Activity - S
625d8e04-1d03-5fe5-a673-aecd649281f2 | note | Verification Activity: By - SE
81f73ef2-bdc8-5939-aa6d-cff64bb295e5 | checkpoint | 3.02.9 - Pipe bedding and haunch zone inspection
80afe4fd-6f35-59f9-aae3-29e56c3792c0 | note | Acceptance / Conformance Criteria - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe bedding and haunch zone
8f0b796f-53c8-50ac-9132-c77a670c3d03 | note | Standard / Specification - PS 16.32.3
60b5717d-85de-5442-b8a9-bef95f12d06d | note | Verifying Document - Engineers Record
dae45631-30e1-5857-ad4d-6a92517ebf2e | note | Frequency - 1 per trench length (Between Chambers)
bde049dc-34cb-5219-bb69-b986c7ef030a | note | Verification Activity: Activity - HP
3ff31980-c7e1-5278-91d2-473bdcff7c1b | note | Verification Activity: By - ENG
5cf170fc-8df5-5e2c-b092-708051a3742b | signoff | AUTHORITY HOLDPOINT
5814668f-ccd5-5d72-badb-415127e4c7e4 | checkpoint | 3.02.10 - Pipe bedding and haunch zone Density Testing
7780f82b-4990-59fe-a8bc-884f232a201f | note | Acceptance / Conformance Criteria - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes. The pipe bedding and haunching zone shall be compacted to a MDD of 90%
6cccbd2f-65ba-5ea9-b97a-8c4bb86632a0 | note | Standard / Specification - PS 16.32.3, PS 16.6
2eb44e5d-5e21-5d11-86b9-6530b43ab9b2 | note | Verifying Document - NDM / Clegg Report
641ea46d-f966-5b91-abc5-a0ffcf8610fd | note | Frequency - 1 per 15m trench length Minimum of 2 tests between pits/manholes
56dadca6-874d-5d2f-b167-2a5a6ce18b08 | note | Verification Activity: Activity - I
c5d6fc74-488c-57b1-af27-39ac3a5333f6 | note | Verification Activity: By - SE
c03d2694-c46a-5d17-84c5-81dfdcdc396f | checkpoint | 3.02.11 - Backfilling of pipes and culverts with embankment fill - QA Acceptance
54c8cf14-a7e5-56f3-b2a5-031afc96d58b | note | Acceptance / Conformance Criteria - Prior to Backfilling of pipes and culverts with embankment fill the test results for bedding, haunching, side zone, and overlay zone material properties, grading curves and compaction tests are accepted by the Engineer.
556bb476-5c8b-5e81-9d97-402026fc5cfa | note | Standard / Specification - PS 16.37
6f63a7f2-ad23-523a-9aa8-8c354adb37e8 | note | Verifying Document - Engineers Acceptance
163a2091-7069-560a-aeae-aea14f580ae8 | note | Frequency - Prior to Backfilling of pipes and culverts with embankment fill
e3b88e8c-a85b-55ce-8e53-66de6475b952 | note | Verification Activity: Activity - HP
e5489cde-3c63-5f55-816c-9c60ec1bc44a | note | Verification Activity: By - ENG
19a18f40-a4da-5db3-aeba-1eabda497cc4 | signoff | AUTHORITY HOLDPOINT
f8a5db8b-7b9c-5b42-9bdd-2aee0aee659b | checkpoint | 3.02.12 - Pipe laying in Embankments
9333aaaa-bb90-5a92-8fc4-21b56f24ee09 | note | Acceptance / Conformance Criteria - The Contractor shall have each pipe checked for level as it is laid, by a competent technician using an Engineer’s level, pipe laser or other approved equipment. Pipes shall be laid on uniform gradients between successive designated manholes at the gradients specified on the Drawings.
de949b47-e5bb-596e-9340-959a6b481c11 | note | Standard / Specification - PS 16.9.2.8
81d88739-b339-5b45-af6b-cd0cd37dddc1 | note | Verifying Document - Survey Records
7967b6ad-cc3e-50c1-bac5-90d180ab9963 | note | Frequency - Each Pipe
ae552d7c-6f4e-5bd3-92a6-85659f422a67 | note | Verification Activity: Activity - I
50ae43b8-b7f8-58a1-8966-b0ac0ff3fd4c | note | Verification Activity: By - SV
f9ac2429-13b8-58d3-8851-eab84a3fd0e7 | checkpoint | 3.02.14 - Cutting of Concrete Pipes
30041ea1-5673-5c52-a5cd-006cccb974ee | note | Acceptance / Conformance Criteria - Where it is necessary to cut a concrete pipe the pipe supplier should be informed of such requirement specifically where the dimensional tolerance for the pipe is deemed critical.
dfb00597-946b-5992-96c2-1bdbabaf4b18 | note | Standard / Specification - PS 16.9.2.16
acdcf809-4c9d-56c3-aaaa-d8ac32594b5a | note | Verifying Document - Suppler Approval
212d01d3-4f70-56eb-be43-3cc662da4072 | note | Frequency - Each Occurrence
c40e6911-bdab-5cfe-abbe-45ef70d12450 | note | Verification Activity: Activity - S
3835eda0-ea57-5160-b112-c942f617dbdc | note | Verification Activity: By - SE
035129dc-7d0e-5a42-b6fe-5dee75371088 | checkpoint | 3.02.15 - Cut Pipe Sealing
e65c9d26-4d1c-5d84-aa1d-8dfc0f16d611 | note | Acceptance / Conformance Criteria - All cut surfaces, not encased within benching or other in-situ concrete, shall be coated with an epoxy resin mortar in accordance with the manufacturer/supplier recommendations, leaving no exposed reinforcement.
aec9e4ca-b54d-53bb-9102-878cdc4379f9 | note | Standard / Specification - PS 16.9.2.16
99d2b016-c059-5f7e-9ac0-71ba4c2ddadc | note | Verifying Document - Site Records
f55294a3-ad52-5c4f-a1bf-68db916a46b1 | note | Frequency - Each Occurrence
e4b52e80-c90e-578b-9ac0-b43990ecba07 | note | Verification Activity: Activity - S
afd4d60d-0ac2-5818-a90f-71bad8ab5770 | note | Verification Activity: By - SE
e4c33cd6-d38e-587d-aa5c-a623c74935ed | checkpoint | 3.02.16 - Side zones Density Testing
7777ec8b-3bbc-5f47-a3c1-fb31188bf4ba | note | Acceptance / Conformance Criteria - Pipe surround material shall be placed and compacted over the full width of the trench to a finished minimum thickness of 150mm above the crown of the pipes. The Side zones shall be compacted to a MDD of 90%
5309e99a-d68c-5d9d-99b5-c598629cd3ab | note | Standard / Specification - PS 16.32.3, PS 16.6
e428b8f0-4950-5176-9b15-a16d4dccc3da | note | Verifying Document - NDM / Clegg Report
aa408326-72d2-5db2-9779-1f9780278be5 | note | Frequency - 1 per backfill layer per 15m trench length. Minimum of 2 tests backfill layer per trench between pits/manholes
55baa83d-214f-55d4-a515-b2b744d467da | note | Verification Activity: Activity - I
1565a9de-acd7-55a7-bee4-ab67d56d629a | note | Verification Activity: By - SE
3382e817-6a28-577d-8653-2be0f10dfb15 | checkpoint | 3.02.17 - Compaction above Pipe
0f621c95-2add-5163-9e74-674f0236295a | note | Acceptance / Conformance Criteria - Only hand operated compaction tools shall be used until the backfill has achieved a depth of 300mm above the crown of the pipe.
cb8dbe72-2c7e-5a2a-8e84-ac948c72432b | note | Standard / Specification - PS 16.32
5e993aac-af3d-5c0e-b7ba-f7f7d54f8028 | note | Verifying Document - Site Records
68b95351-d29b-59e3-97b6-2cd5e950a0ce | note | Frequency - During Works
ac98194b-42f1-503f-b174-bde1d7e887ca | note | Verification Activity: Activity - S
6cdf8e68-eeac-52a3-b3fd-e8cf26a5a558 | note | Verification Activity: By - SE
51eb3361-8108-503c-8a25-987fd585578d | checkpoint | 3.02.18 - Pipe overlay zone inspection
d759fc60-4644-58f5-bd79-b55b5bd1fb89 | note | Acceptance / Conformance Criteria - The Engineer shall complete a Visual Inspection to NZTA F/3: 2010 each strength length on Pipe overlay zone
41f61bb4-c281-5e16-92d2-15f1fa5eab78 | note | Standard / Specification - PS 16.32.3
53c317a1-55ba-55c1-82e1-8fc0cdfe0a82 | note | Verifying Document - Engineers Record
f299943b-7879-52a3-a141-0d281743d90b | note | Frequency - 1 per trench length (Between Chambers)
bd215c41-c17d-5954-9ec4-b311106ae3ba | note | Verification Activity: Activity - HP
cc936f89-e555-5592-a1c5-7752671b456a | note | Verification Activity: By - ENG
bd74d56a-352f-5342-982f-d30a401d4e76 | signoff | AUTHORITY HOLDPOINT
35acfe1b-9d28-5cb4-9eb1-8f3050ddfbcf | checkpoint | 3.02.19 - Pipe Overlay Zone Density Testing
ea4a7c21-2cd6-51ba-89f9-65f4083ee4cd | note | Acceptance / Conformance Criteria - Backfill material shall be built up in layers not exceeding 200mm. The Pipe overlay zone shall be compacted to a MDD of 90%
a786b17d-34ea-57ec-8ba3-7fef24b9424a | note | Standard / Specification - PS 16.32.3, PS 16.6
4b32e01c-ad41-5413-ac29-af993bd155bb | note | Verifying Document - NDM / Clegg Report
9f21ec6a-04d0-5ba8-96f3-1eb9421522e9 | note | Frequency - 1 per 15m trench length Minimum of 2 tests between pits/manholes
d93c0d3c-1206-53b2-8982-bb08eccc3924 | note | Verification Activity: Activity - I
50a17376-53cd-53d0-8940-c74e1ab03a05 | note | Verification Activity: By - SE
91558f9b-dbd3-5b49-8a78-7e78124ef5d3 | checkpoint | 3.02.20 - Pipe invert levels/lid levels at all drainage structures
aa555522-51f3-5980-b9d1-c3ab7c1e70fe | note | Acceptance / Conformance Criteria - Pipes shall be installed within 20mm of stated invert level (vertical tolerance) and within 50mm or 5% of the pipe diameter of proposed horizontal alignment (whichever is greater). Catchpits and catchpit manholes shall be located to align with proposed kerb and channel (or dish channel) and finished to be flush with the finished road surface unless otherwise specified on the Drawings.
aad2186f-af8e-5603-95b3-75a2c89579d4 | note | Standard / Specification - PS 16.34.2
a74d5719-acf4-58a9-9d3a-f363807a7440 | note | Verifying Document - Survey Records
0fa9e2a2-80d6-5268-9740-1a0c21764355 | note | Frequency - At the completion of each stormwater pipeline
3147a91c-0253-5526-a0a9-708fe114c933 | note | Verification Activity: Activity - I
03cc8ce8-f6f6-5939-a085-971d4562b8c9 | note | Verification Activity: By - SV
3cbaefad-09bf-5980-99ae-9f82d36421b2 | section | 3.04 Stormwater Structures General
55e0db49-0d55-5fcb-a32c-d06f9e360544 | checkpoint | 3.04.1 - Stormwater Structures Subgrade
7ccab956-c555-5c92-a515-ccd3161b2fa6 | note | Acceptance / Conformance Criteria - A hand Auger Scala / Shear Vane up to 4m deep shall be completed in the base of the excavation and the results submitted to the Engineer. The subgrade shall be CBR>5.
d1c3a282-502d-5571-9cb0-2708c6831439 | note | Standard / Specification - PS 16.32.3
7fb8daab-73b9-517e-9d03-e50aa11e5642 | note | Verifying Document - Scala / Shear Vane Results
37c7858f-1d66-55e1-95e2-8ba4a1fec8a3 | note | Frequency - 1 per structure
ab9c59e4-05af-515e-b1c4-49227fe82f7d | note | Verification Activity: Activity - I
3629fb0c-7009-5d28-a077-787874d9e25d | note | Verification Activity: By - SE
11df0ca5-2244-56ff-87cf-6389bd9bd635 | checkpoint | 3.04.2 - Stormwater Structures Bedding material
48bc291a-2a29-5bc3-906f-3cdac2399e31 | note | Acceptance / Conformance Criteria - Stormwater Structures Bedding granular material shall be compacted to MDD of 95%.
c46f0835-2b13-58d9-99e7-d82b75d1a056 | note | Standard / Specification - PS 16.32.3
b42f32fc-9bfa-5fb2-be62-057e44830231 | note | Verifying Document - NDM Results
29fd4438-97bd-5577-b172-a518d3a3a8bd | note | Frequency - 1 per structure
c62da838-5b40-56be-8866-a002ab4b97fa | note | Verification Activity: Activity - I
720c64e6-0ca3-59a3-8768-96eb4f76fe64 | note | Verification Activity: By - SE
edf4ceda-4a42-5d83-8430-f5df17c20e6e | checkpoint | 3.04.3 - Stormwater Structures Backfill
b34f1f7f-0938-5b21-a47f-6db328924c17 | note | Acceptance / Conformance Criteria - Stormwater Structures Backfill granular material shall be compacted to MDD of 95%.
d1c7cb98-8641-5341-994b-ea4470308fdd | note | Standard / Specification - PS 16.32.3
75e64ac6-029b-5e7e-ab2f-6d62438d5624 | note | Verifying Document - NDM Results
6f6b8403-ddb8-5d40-adf1-d4cc9f2ef858 | note | Frequency - 1 per backfill layer per structure
296e6018-bc51-5a85-a578-f14fc5cc21f8 | note | Verification Activity: Activity - I
15cce95e-fa47-5c7b-9032-921bd70bd231 | note | Verification Activity: By - SE
c39c3e78-c1aa-5dca-a3f5-3c587c96df60 | checkpoint | 3.04.4 - Subgrade Clay
ae0091af-8c0c-52cc-b75d-a35fa3f76837 | note | Acceptance / Conformance Criteria - If clay is present at subgrade level, then this should be supplemented with soaked CBR laboratory testing.
1db22515-8d3a-56b7-9dd8-77f0a46019d5 | note | Standard / Specification - PS 16.32.3
77029148-a510-56dc-88d6-c28059422f6b | note | Verifying Document - Soaked CBR
36143a61-3eec-534e-99a7-55ac2d9cbd59 | note | Frequency - Each Occurrence
eb3dbda9-3677-5a19-b28d-7e491ed5f611 | note | Verification Activity: Activity - I
a881e587-2b20-553b-9123-49e3bdebae1b | note | Verification Activity: By - SE
772516f7-046e-5c6f-aac8-fb5becb92a72 | checkpoint | 3.04.5 - Culvert CBR Approval
3c258f69-f678-52f7-9913-42fb49154f2e | note | Acceptance / Conformance Criteria - The contractor is to provide CBR testing of trench subgrade prior to placement of bedding and laying of culverts.
0c978519-93f2-565e-aad6-832f7c252596 | note | Standard / Specification - PS 16.38
f26024b5-c24c-542e-9adc-b46f6a06d840 | note | Verifying Document - CBR
414b1fad-73e1-5bc8-9d59-9cbde223fa67 | note | Frequency - Each culvert prior to bedding
8a7c2686-1478-51dd-8a5f-b6ead3cfc667 | note | Verification Activity: Activity - W
b311b341-d8a7-57cf-9f2a-03a65b60768f | note | Verification Activity: By - ENG
2b11378f-fb1e-5ce9-90ee-5cf3efd04f03 | section | 3.05 Catchpits (Structure)
31ff3eb2-aa65-5635-a88d-3fd640cbd3bf | checkpoint | 3.05.1 - Catchpits Base
7c12f643-54cd-5642-b419-a60cb10f0a3d | note | Acceptance / Conformance Criteria - Catchpits shall be constructed on a compacted, on top of a 150mm layer of compacted AP65 or GAP100 granular material.
4d7a6880-94e2-5dd5-87c5-acf5d37d6788 | note | Standard / Specification - PS 16.10.2
cfd7a3fa-c030-5be5-902f-e19786facbfe | note | Verifying Document - Site Records
3b50728b-9859-55b4-a133-214b3d0fd973 | note | Frequency - Each Catchpit
eb439e00-b472-5d4e-b1b9-909647a050e9 | note | Verification Activity: Activity - I
b97ed336-e7f3-586a-b7a9-76d5e23c013a | note | Verification Activity: By - SE
ec26eee7-2ffc-5274-9a64-37128cd44b24 | checkpoint | 3.05.2 - Precast Catchpit Sealant
caca2619-e854-52de-8466-ceb7c1b17f08 | note | Acceptance / Conformance Criteria - All joints between segments of precast catchpit risers shall be sealed with ‘Black Butyl Mastic Sealant – Hynds (MSR)’ or similar and approved.
5662f1dc-68c0-57c4-96a2-ab8b3cf29981 | note | Standard / Specification - PS 16.10.2
e3491805-ebf4-5a7d-9d6a-768e20f967dc | note | Verifying Document - Site Records
c1b760af-fdbc-54d1-ac9d-473503e15ed1 | note | Frequency - Each Catchpit
74fda00c-9175-57e9-9e72-c326c6f42529 | note | Verification Activity: Activity - I
5b4fd898-b0e4-573a-8f1c-5faacd3f59fd | note | Verification Activity: By - SE
feb0a3cc-ec88-5255-a059-11b948c8cfc2 | checkpoint | 3.05.3 - Catchpits Grates
f3063c57-e226-5f54-b6f3-63ee891fca10 | note | Acceptance / Conformance Criteria - Cast-iron grates and frames shall be set no more than 30mm lower than, but parallel to the cross fall and grade of the surrounding, finished pavement surface level. All grates and frames shall be haunched to lids.
afa108f9-36ee-549b-bee0-84858cac3fcb | note | Standard / Specification - PS 16.10.2
b9715cd7-3ddd-56a3-84b7-03434604bcda | note | Verifying Document - Site Records
db7af4b0-2966-5b17-8edb-d0fce08bab3b | note | Frequency - Each Catchpit
833ad2d4-0f3d-5158-98a3-cef60fb2b875 | note | Verification Activity: Activity - I
2a0daae5-4037-56fd-bb23-56fb57cd2535 | note | Verification Activity: By - SE
20499adb-cd8d-52ad-9503-f7ac36d5126e | checkpoint | 3.05.4 - Catchpits Sumps
82783ac0-0a33-54c7-926b-fb0accf22531 | note | Acceptance / Conformance Criteria - Catchpits must have sumps at least 450mm deep (below the invert of the outlet pipe level)
f07874f5-809f-5857-9ca1-dde377bad4d0 | note | Standard / Specification - PS 16.10
9811e13a-60c2-55cf-a626-05c28b8da90c | note | Verifying Document - Site Records
ba27d4c4-4877-5b94-adc6-c5dec1860b9e | note | Frequency - Each Catchpit
1cb8192a-31f2-5be6-afba-3ce6e4f421b0 | note | Verification Activity: Activity - I
09a245a3-b6ff-5b78-92c9-f795fb912fe6 | note | Verification Activity: By - SE
38a69e92-eb03-5781-babf-63bafa6f0463 | checkpoint | 3.05.5 - Catchpits Inlets
8fc438ca-6594-5b52-84ee-1bbf3c7d5221 | note | Acceptance / Conformance Criteria - All catchpits receiving stormwater from the highway shall be constructed with a back-entry inlet.
19206e38-5252-55d9-b766-ed46b3f4d212 | note | Standard / Specification - PS 16.10
617f5fe4-08cd-56a5-a9ed-2e6d64437fc2 | note | Verifying Document - Site Records
60babfde-8a7b-5821-876e-365eb6628c75 | note | Frequency - Each Catchpit
e16b2f58-8955-55e7-b3f8-a0bf1c481028 | note | Verification Activity: Activity - I
783f76e9-2b93-5db0-845f-1e21c8d64c5c | note | Verification Activity: By - SE
fbfd030e-e726-5b00-b683-815353d7d8ec | section | 3.06 Manholes (Including Catchpit Manholes)
4ea6a7a4-33ae-5695-82f6-c7b9a7aa7caf | checkpoint | 3.06.1 - Manholes Base
3a9e6f0e-79b8-5d80-afa4-286e1327281d | note | Acceptance / Conformance Criteria - Manholes shall be constructed on a compacted, on top of a 150mm layer of compacted AP65 or GAP100 granular material
f493d2b6-4b01-51c7-b4bd-b7b5abee8966 | note | Standard / Specification - PS 16.15.2
dec3f19d-bd7b-5bc5-98a6-18340d74e6bb | note | Verifying Document - Site Records
8c10f297-d8b6-58b1-b0cc-b291908bb792 | note | Frequency - Each Manhole
4e07cb12-774d-5d74-a75c-a7a17318ca90 | note | Verification Activity: Activity - I
acae7bce-bc0e-5278-b5d3-4c2c81856ed9 | note | Verification Activity: By - SE
830ba5c3-5241-5f8c-9d26-aee2aa04121a | checkpoint | 3.06.2 - Manholes Sealant
1d507ef0-acca-5a43-88c4-d1acd676ce68 | note | Acceptance / Conformance Criteria - All joints between ring segments of precast manholes and chambers shall be sealed with ‘Grey Butyl Manhole Sealant – Hynds (SM9020)’ or similar and approved.
4e2dce2e-e2b4-5031-8fb5-21ac1c0128fa | note | Standard / Specification - PS 16.15.2
c412922a-19eb-5c79-8071-400b7df951fd | note | Verifying Document - Site Records
c51f6de7-834a-56e4-aa11-a45cf597f87d | note | Frequency - Each Catchpit
89e41216-5fc5-5a4d-ac7b-b6e80627fabe | note | Verification Activity: Activity - I
fc8b90cb-5fbb-5cad-8ac4-af7ffe5f9e7b | note | Verification Activity: By - SE
65a61540-a274-5c95-993e-1bca70d687a4 | checkpoint | 3.06.3 - Benching
f95c7681-49b8-5df2-b050-183c6406024a | note | Acceptance / Conformance Criteria - Benching is required in all manhole structures unless noted otherwise on Drawings. Benching shall be 20MPa concrete and to a F4 finish. Manhole benching shall accommodate pavement subsoil drain connections where required.
1d794a62-7c5d-58c5-9714-015fe298b28c | note | Standard / Specification - PS 16.15.2
3347e862-c03a-52ab-9d9c-2a79228848a4 | note | Verifying Document - Site Records
f42162ea-77b6-5c48-9a5b-721d72594dc3 | note | Frequency - Each Catchpit
f2fe82f9-8dbd-5b31-ab79-7f8fb6e8871b | note | Verification Activity: Activity - I
f60e390e-e985-5b3e-8d40-dac7c9c4ecff | note | Verification Activity: By - SE
1b2b7647-ea00-550b-94b6-c3eb86c1e5af | checkpoint | 3.06.4 - Benching Fall
0cac811e-75f9-532a-b09c-a44cad9229f8 | note | Acceptance / Conformance Criteria - All side benching shall be formed with a fall towards the channel unless otherwise stated.
1097b43a-3ffe-57df-8568-ead8070fa6a4 | note | Standard / Specification - PS 16.15.2
74262943-c30c-56a4-bafb-64db4aae0de9 | note | Verifying Document - Site Records
b34fb4dc-ca10-5c46-a515-a7a0d16dec8e | note | Frequency - Each Manhole
f813fdc6-8eaf-51ae-b92e-d3902ff8bcf9 | note | Verification Activity: Activity - I
0360d584-5bab-5633-8f8f-c65954b27c4b | note | Verification Activity: By - SE
e2634fcd-64bd-5c88-986a-591133456f83 | checkpoint | 3.06.5 - Sealant
21cb44f5-1153-5b62-90ee-b4948ae6730a | note | Acceptance / Conformance Criteria - All pipe work penetrations through manhole walls shall be sealed using Epoxy Mortar or an approved equivalent type of permanent sealant.
3cc3eb22-7813-530f-8aa5-6ae338830655 | note | Standard / Specification - PS 16.15.2
59ebae16-ebd8-56f7-aa02-b87e2ef8cba1 | note | Verifying Document - Site Records
58e9733d-3a89-5204-ae3f-36a29763d73e | note | Frequency - Each Manhole
7e94f9b2-5165-5c4a-9957-f9bb127a161b | note | Verification Activity: Activity - I
7a9c04a4-d06b-559d-97ec-c27fb6692cc1 | note | Verification Activity: By - SE
011d016c-aafb-54b9-b1eb-bc32a59107a7 | checkpoint | 3.06.6 - Lids
7aa78c8f-122b-5ccc-917d-ff44c192c11c | note | Acceptance / Conformance Criteria - All solid cast-iron covers and frames shall be set flush with the cross fall and grade of the surrounding finished surfaces. All grates and frames shall be haunched to lids.
46ea94c0-a704-5d95-8387-8698484f51c9 | note | Standard / Specification - PS 16.15.2
1f3bc0d6-5be8-5873-a9e9-c6544a416ebe | note | Verifying Document - Site Records
f608c04d-9e1c-5bfc-a52c-999da51bef95 | note | Frequency - Each Manhole
7aa68f92-8526-588d-ab62-c690abfab4e3 | note | Verification Activity: Activity - I
f5d7d1b6-2b8d-579b-933c-8545e4c06196 | note | Verification Activity: By - SE
f97987d2-2d57-5b5c-a4fd-287d395bce0e | checkpoint | 3.06.7 - raised cover levels
df0a6082-b5e9-573c-a1eb-4417756b2a91 | note | Acceptance / Conformance Criteria - For new or existing manholes with raised cover levels, the height of the manhole access shaft (throat) shall be no greater than 600mm where access is required (all non-catchpit manholes). The shaft and any subsequent extensions to the shaft shall be constructed using either:
ef266951-f763-5fac-9123-b81939b21d05 | note | Standard / Specification - PS 16.15.2
82e191ee-3427-5ad3-a704-000251cc0625 | note | Verifying Document - Site Records
1cd684fd-7259-59b4-a745-bc1f6cf2f01f | note | Frequency - Each Manhole
ff52b000-0775-509f-9955-80514ffdb205 | note | Verification Activity: Activity - I
64c3f6d9-b360-539d-9a0f-8f406ab46004 | note | Verification Activity: By - SE
137e9184-dbbb-5055-85de-4e13f31d3b5e | checkpoint | 3.06.8 - Adjust Manhole Service Lid Covers
391775e4-fd9b-56c6-9f3f-159ce096b096 | note | Acceptance / Conformance Criteria - Following adjustment, the service cover shall be firmly held in place and shall not be 5mm higher or 0mm lower than the adjoining surface. The item shall cover adjustments + or – 300mm from the original height. Any adjustments exceeding these measurements shall be treated as a variation.
04334fc2-b281-51f3-8aa9-0a76cf293552 | note | Standard / Specification - PS 16.12.1
57287e33-c31e-55c1-a5d0-8ae74216966d | note | Verifying Document - Site Records
f5b7ab8b-269a-54a7-bfc3-75ff06b220c5 | note | Frequency - Each Lid
ccc852a1-41d3-5d1b-90e4-f782f972d478 | note | Verification Activity: Activity - I
963627e5-207a-51ad-9868-852410b6cc08 | note | Verification Activity: By - SE
2a566367-4568-59ef-8af5-b33af6cd82fd | checkpoint | 3.06.9 - Visual inspection of all Manholes
3e9bb3c2-f553-5292-961f-29cdcd544bae | note | Acceptance / Conformance Criteria - 3-6 months following construction, Each manhole shall be inspected. No evidence of identifiable flow infiltration, settlement and riser displacement or cracking shall be present
867b6da2-0105-570c-9e45-1e84db38098a | note | Standard / Specification - PS 16.34
c7293857-6920-5d24-95cc-56b8befaa828 | note | Verifying Document - Inspection Record
a0f5bb33-714b-5902-87e6-be5fdf9607a1 | note | Frequency - Each Manhole 3-6 months after Construction
d8c8ada0-1f73-5c3b-ad64-707803459d6d | note | Verification Activity: Activity - W
505eb47b-c74b-5bcb-985d-8f81b9bac215 | note | Verification Activity: By - ENG
27774e0c-99d7-5289-8467-16e09dd355ec | section | 3.07 Headwalls and Wingwalls (Structure)
a282b859-9ba8-5309-ac5f-cce9472c84c2 | checkpoint | 3.07.1 - Headwall Bedding
2bab5ccb-3cbf-57f6-8710-b2459902c1f5 | note | Acceptance / Conformance Criteria - Headwall aprons shall be constructed on a compacted, 75mm bedding sand underlay by 150mm layer of AP65 (or similar material as approved by the Engineer) granular material and compacted to a MDD of 95%.
91063004-0b29-50ff-b05e-821158bec0e8 | note | Standard / Specification - PS 16.13.2
82b3bf69-61dc-5cf6-bca7-7e387c6379ff | note | Verifying Document - NDM Results
b73fe472-3c42-5813-8fba-89f17bab39ba | note | Frequency - 1 Per Apron
8881594f-1fb1-5b9f-afa7-d37ce5091875 | note | Verification Activity: Activity - I
94340d61-1416-52e1-b978-f8650ee0935b | note | Verification Activity: By - SE
07fc3567-164c-5618-a44d-5368bfd158b2 | checkpoint | 3.07.2 - Precast and Cast in-situ Headwall and Wingwall tolerance
21f8fae2-c3f3-5adf-86e0-7393a663a12e | note | Acceptance / Conformance Criteria - +/- 10mm variance to vertical design set-out
5a5687cc-6e9a-5bce-93d6-38d9dd154e4f | note | ○ +/- 10mm variance to horizontal design set-out (values in accordance with NZS 3109: 1997)
86b8dbec-1541-5da5-8190-ed28920688b4 | note | Standard / Specification - PS 16.34
208c6c08-ec71-5a1d-9d54-701f09fcccae | note | Verifying Document - Survey Records
dc7f4cf0-5888-52fd-b014-035b78fea0ba | note | Frequency - Every Unit
e0a4a3b7-1c85-546d-80f0-d3d5193a7762 | note | Verification Activity: Activity - I
0f5c6158-e8c4-56c2-ada6-733e98d3831c | note | Verification Activity: By - SV
8068364e-520f-5fd0-991b-16023b2271ec | section | 3.08 Stormwater Concrete Capping (Pre Pour)
bd69386d-659e-5519-93df-1bd1697fd818 | checkpoint | 3.08.1 - Construction Joint Locations
5f47460c-17f6-5a16-82a0-d5da69d96d71 | note | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
bcdb9380-87ba-5b77-b134-cff7009c664a | note | Standard / Specification - Downer
7fcaf1be-2e8f-59fa-94fc-5a7bc498d040 | note | Verifying Document - Approval
f2cbab80-916f-5bf8-8fcd-14e744ff2e5e | note | Frequency - Prior to Pour
592d2188-3269-5697-a6c3-acbbf70737b1 | note | Verification Activity: Activity - HP
8b4c3044-7670-510a-9877-2fb346213beb | note | Verification Activity: By - ENG
1885b19b-fd69-523f-9265-6ecd08f19429 | signoff | AUTHORITY HOLDPOINT
f50d5944-adee-5c53-805f-e43deb1cbcd6 | checkpoint | 3.08.2 - Dry Pack Mortar
bc415a1b-696b-5a55-8143-ab5c161a66d0 | note | Acceptance / Conformance Criteria - Dry pack mortar where specified on the drawings shall be places as per the manufactures instructions.
3497142d-f243-5a8d-9be2-ce7568b448bc | note | Standard / Specification - Downer
f99c52e3-5888-5a4b-9bce-7354556879ec | note | Verifying Document - Pre pour
4c63d7de-d2f6-5dcd-a6c9-650d45058db5 | note | Frequency - Before Works
0a914d3b-42c3-54b9-9825-3359f3ae4990 | note | Verification Activity: Activity - R
53ee03dd-1ade-5cad-b017-c44bc5b48127 | note | Verification Activity: By - PE
7ddf1616-1eae-54b1-afaf-a7dbaf19d051 | checkpoint | 3.08.3 - Reinforcement Pre Pour Inspection
42a17dd3-d295-5d6b-b380-447c658db28e | note | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
2af99b23-dbfe-5ed0-87c8-ce749b036717 | note | Standard / Specification - Downer
9affa3d5-1486-542b-a9d2-ee8d51017ec7 | note | Verifying Document - Pre pour
3e50e346-575b-5748-b476-67754d8ebc63 | note | Frequency - Each Pour
0a3b6477-fa0a-57c6-9aa7-d4438541a7ae | note | Verification Activity: Activity - R
2384d2d0-d928-537a-bf85-fd5f2a402d49 | note | Verification Activity: By - PE
49afaa9c-fcb3-541e-a838-fe0a90e77ca3 | checkpoint | 3.08.4 - Pre-Pour Inspection
0c8f35e6-f474-5ea8-aed5-1ded1a659a16 | note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
070abcb2-7bf3-5d84-9c6f-33dcd92c65fb | note | Standard / Specification - Downer
66acced7-8b9f-5989-9f56-a0091a8b6302 | note | Verifying Document - Signed Pre-Pour
7b32fc0c-01de-5596-9243-19fd69a3df18 | note | Frequency - 48 Hours Notice Prior to Each Occurrence
e788a677-e575-56ea-983a-c85f93bb281d | note | Verification Activity: Activity - HP
43366cc7-9dd2-5ad0-9fe0-3fca307e02b1 | note | Verification Activity: By - ENG
bc0f02e9-b1ca-53bc-ac57-244188125592 | signoff | AUTHORITY HOLDPOINT
bbd94df5-4b0f-53f6-ae1b-aa72bd251ca6 | checkpoint | 3.08.5 - Delivery Dockets
02b4606a-efbc-5629-abaa-968be95213fb | note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
631c12cb-2d6f-508e-ad19-e9a7ce9788ae | note | Standard / Specification - Downer
3b998771-c19d-5c84-8f0b-40cc49fe060a | note | Verifying Document - Dockets
7fb6e36c-ba86-57a3-bf57-d0765b07e8eb | note | Frequency - Each Pour
4395b7f3-7ead-58ed-82e6-d5fb8519306b | note | Verification Activity: Activity - R
425eee7d-b0ef-505b-8ff7-088d243ed20b | note | Verification Activity: By - PE
4279327e-59cf-5451-83b7-3515969e2984 | section | 3.09 Stormwater Concrete Capping (Post Pour)
033f68b5-19da-576d-ab6c-0e1322ff0d66 | checkpoint | 3.09.1 - Post Pour Inspection
40c46004-a0d2-55b3-a8b8-8c3b33037ae3 | note | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
411daf79-3c25-57cf-ae76-78628629977e | note | Standard / Specification - Downer
a3e75254-9229-55f5-9653-09df3c558c89 | note | Verifying Document - Post Pour
78ab019f-3d34-52c5-b593-b4913cf5aa03 | note | Frequency - Each Pour
fb8ec1e5-57ab-53d6-b80e-f7c853b534f4 | note | Verification Activity: Activity - R
ed99a297-8f95-516f-8e5f-18f02a31ff66 | note | Verification Activity: By - PE
4f83fc6d-7c13-5e0c-8101-fc7d013048d1 | checkpoint | 3.09.2 - Construction joints
3eef2fc6-cb15-5b10-8ec5-92adcf30affc | note | Acceptance / Conformance Criteria - Construction joints shall be placed as per the drawings / agreement.
c4fe7329-89d1-5b92-97fb-946425b4de35 | note | Standard / Specification - Downer
8c200ebd-8252-5998-a899-76c41ab70a2e | note | Verifying Document - Post Pour
7109bee6-d043-51e5-9868-872c9082099d | note | Frequency - Each Pour
bbcc0d1b-9163-541c-8742-77a41ffea878 | note | Verification Activity: Activity - R
0e00c0a9-2e62-57ed-90f3-3b3db0efe016 | note | Verification Activity: By - PE
7bf1ae95-4187-5f9c-ad6a-07e234d10d2b | checkpoint | 3.09.3 - Defective Concrete Finishes
a826d68e-d3e9-5374-b462-7f774e9b20f6 | note | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
79d88ba9-d28a-5aa0-8420-589301486a67 | note | Standard / Specification - NZS 3114
51411ba0-df15-5afa-9058-69a514ce4bff | note | Verifying Document - NCR
5178402c-3803-58ae-9609-e3477c92a417 | note | Frequency - Prior to non Minor Repair
0c46167d-50f4-5af7-81da-627189c701b5 | note | Verification Activity: Activity - V
fab78af2-0726-52ba-b6d3-5e0ca7dceb51 | note | Verification Activity: By - SE
9677155b-1567-5603-9058-10b8155b0cfb | section | 3.10 16.35 CCTV Inspections
148112e0-6cfb-504e-8565-c9c49eeea73b | checkpoint | 3.10.1 - CCTV stormwater pipe
9b110b3d-b14a-500b-9f70-6bfee2d47466 | note | Acceptance / Conformance Criteria - Every stormwater pipeline 300mm and greater shall be inspected by means of CCTV camera at the completion of each pipe trench backfill and compaction and at the completion of Earthworks operations (or at a time otherwise agreed with the Engineer).
33ba4a54-0d0b-549a-803e-2113e2b980a5 | note | Standard / Specification - PS 16.34, PS 16.35.1
a10ba199-9940-51e5-bd48-fcffc08e0e56 | note | Verifying Document - CCTV Video and Report
e7ec6065-f0ef-5743-8684-aa5761cd04e3 | note | Frequency - At completion of pipes laying, backfilling but prior to final surfacing (Pavements, etc.)
c4d739e9-d404-5135-9f86-101444ebec1c | note | Verification Activity: Activity - I
6da0e0e0-2b67-5a23-be2f-a5acbdabd9f5 | note | Verification Activity: By - PE
1bb8f0ef-71a1-5083-bde8-eddaaedae0da | checkpoint | 3.10.2 - Pavement Construction CCTV Review
856f1831-3c20-5a03-ade3-5bb0c01dbeba | note | Acceptance / Conformance Criteria - Prior to pavement construction, The Contractor shall submit the pipe condition inspection report to the Engineer for acceptance. The pipe condition inspection report is to be based on CCTV for all pipes upon completion of backfilling the trench.
29ebfdb2-81c5-5080-8628-ddd2129a1380 | note | Standard / Specification - PS 16.37
b096192c-aecf-5fcf-9c3b-abf79330ef6c | note | Verifying Document - Engineers Acceptance
227d49f2-89ee-5142-aed3-b693f5bc28e4 | note | Frequency - Prior to pavement construction above Stormwater pipelines
da035812-d13b-5178-b416-e457d43c05cc | note | Verification Activity: Activity - HP
587f0ad7-ea70-570a-b2ad-7682d65e9ec1 | note | Verification Activity: By - ENG
c99c9d00-0420-58fe-b549-3dcfcc6d3958 | signoff | AUTHORITY HOLDPOINT
d25444e5-96eb-541b-becc-59f2adbdde88 | section | 3.11 As Built Records
2424709a-58b3-5a56-8303-6a65e7fc6226 | checkpoint | 3.11.1 - Survey Requirements - Stormwater Systems - Underground:
c597a341-c1b0-5fb6-bd9b-1b8e6bc1c3d0 | note | Acceptance / Conformance Criteria - The following items shall be recorded for asbuilt drawings.: Trench invert. Pipe/structure bedding and backfill compaction. Pipe/structure size, class, alignment, and level. Manhole and catchpit position, levels (lid and inverts). Outlet structures including position, levels, erosion provisions and fish passages.
178957d6-1815-56b9-8eec-b2ed2bbe4cff | note | Standard / Specification - PS 16.33
a470446c-240f-5e87-a0bc-9a7dfe0076f2 | note | Verifying Document - Survey
85b7f2fc-fca9-5599-954d-88a20587b9a6 | note | Frequency - All underground Stormwater Systems
297aa355-398b-5be0-87c3-36edee67c577 | note | Verification Activity: Activity - I
c1bef070-6ad4-58dc-b8ed-62f707bf1462 | note | Verification Activity: By - SV
d9c444fd-5ffe-5265-81e4-16abd7347357 | checkpoint | 3.11.2 - Survey Requirements - Stormwater Systems – Above ground:
54850b2d-ac5d-5b3b-8ff5-cfa01879fe43 | note | Acceptance / Conformance Criteria - The following items shall be recorded for asbuilt drawings: Treatment swales, wetlands, basin’s location, profile and grade. Diversion Drain location, profile, and grade. Trench excavation and invert. Line, levels and grade of kerb and channels. Rodding eye locations.
cf027f9f-d387-570b-80d6-c9c7a1996470 | note | Standard / Specification - PS 16.33
ce1e0489-3673-55e7-ab1c-47486e9ecb0c | note | Verifying Document - Survey
bba38cb5-4871-5fa6-829b-1af2c5118f4f | note | Frequency - All above ground Stormwater Systems
4f3331d3-fc36-58e6-aefb-4483ee8174ec | note | Verification Activity: Activity - I
d6f5d537-2878-5e6a-be62-f8c7ba769148 | note | Verification Activity: By - SV
20e6bebd-4ed2-4b81-839d-21280f9a0ea7 | section | 3.12 HDPE Pipe Materials
dda286d8-7d29-4296-a053-3ae99972251b | checkpoint | 3.12.01 - PE Pipe
48142e24-955e-5812-a7d4-eeba26ac1609 | note | Acceptance / Conformance Criteria - PE pipe is required to comply with AS/NZS 4130 and be PE100 or PE80B plain wall with an SDR as shown on the drawings, but no greater than SDR17.
72ebd30c-71c8-512a-a2f7-f8c2d6d975e7 | note | Standard / Specification - PS 16.28.3
85bbb74f-7654-5b39-b167-ed4e1d06eb61 | note | Verifying Document - Datasheet
77cd10b7-8a31-55d4-937e-711721f69800 | note | Frequency - Prior to use
f45a456f-a9c2-53eb-a690-6f2c0c6a7353 | note | Verification Activity: Activity - R
0559749c-9d09-5af2-9995-8fcdffa7541c | note | Verification Activity: By - SE
5d2c3207-3642-4da4-9d6a-b2c967e76321 | checkpoint | 3.12.02 - PE Fittings
9cd725b5-dffe-5131-b899-b1d34846c103 | note | Acceptance / Conformance Criteria - PE fittings must be manufactured in accordance with AS/NZS 4129 and be the same class and pipe material as the main pipe.
3e8bbb5a-274e-5d58-b2e4-bccf1a22e578 | note | Standard / Specification - PS 16.28.3
ce1f4f2e-1743-5406-bd33-1382fd3a8f7c | note | Verifying Document - Datasheet
d2635d51-6322-5ed5-9615-ee57affc6e84 | note | Frequency - Prior to use
43ba9033-0ed1-591e-8c28-b3ff6641dd04 | note | Verification Activity: Activity - R
7446ddbf-bb49-5564-a85a-ffad3eea2bb5 | note | Verification Activity: By - SE
6c0461bc-535e-4384-b6f0-939a6ee680f6 | checkpoint | 3.12.03 - Electrofusion Couplers
fc3dd1b2-8f15-5a51-94d0-470efad07c7b | note | Acceptance / Conformance Criteria - Electrofusion couplers must comply with AS/NZS 4129 and be minimum PN16 pressure rating.
add93445-f15b-5893-bf4b-6663950f7f03 | note | Standard / Specification - PS 16.28.3
c56d4a20-c3df-543a-b97c-c58384c5d5fb | note | Verifying Document - Datasheet
8cec3378-88b4-5520-bfbf-e98030ff5b08 | note | Frequency - Prior to use
8a31ed8d-ef47-5777-98e0-d935d8ae2d44 | note | Verification Activity: Activity - R
63bd3cc5-1d76-5c72-9daa-3e37efb173b4 | note | Verification Activity: By - SE
16690a25-3ea7-4f53-8077-a2095f402ffb | checkpoint | 3.12.04 - PE Fitting Flanges
924b351f-0f4f-5dbd-9179-75ed300f6661 | note | Acceptance / Conformance Criteria - Flanged connections between PE pipe and metal fittings (e.g. cast or ductile iron flanges on valves, spools, bends, etc) are to be made using PE stub flanges, full face gaskets (Tessnit or Klinger or equivalent approved by the Engineer), 316 grade stainless steel backing rings, and 316 grade stainless steel bolts and nuts.
753344c4-4b5f-59ef-8c60-0059e6066394 | note | Standard / Specification - T-EES: 04311 - 2.3
b7dbc142-beb3-5c15-b20d-395d1cca4b0f | note | Verifying Document - Datasheet
af08fc65-73c2-5832-8be3-412c1dfebd8f | note | Frequency - Prior to use
7a54005b-8250-5c9b-89eb-5fadcd759254 | note | Verification Activity: Activity - R
3a3e6a00-7ec4-57f3-862b-5a6c06454fba | note | Verification Activity: By - SE
31cecad0-628d-4eaa-ac6d-e5bf9f9c1b3e | checkpoint | 3.12.05 - Denso Tape
ffb98532-3fa2-5553-88e8-cd667b267637 | note | Acceptance / Conformance Criteria - Denso Tape (or equivalent) shall be used on buried flanged fittings
10980ff2-89ea-5340-9546-ac73c8b54bc2 | note | Standard / Specification - T-EES: 04311 - 2.3
d2f4c04e-b723-54b0-9c44-ad5a93896402 | note | Verifying Document - Datasheet
2df8d43b-b30b-5a0d-bbd7-7a9dcc4b4dd1 | note | Frequency - Prior to use
3c56dac3-444a-5f8d-b98a-bcd358f81e10 | note | Verification Activity: Activity - R
c922ed41-2417-5ab3-82a0-77b90e861f66 | note | Verification Activity: By - SE
4dadab66-1c4e-4122-bcbd-c216b0fc14eb | checkpoint | 3.12.06 - Grout
354c0029-dd0a-5540-8571-d643b013402e | note | Acceptance / Conformance Criteria - Grout must be 1.5 MPa flowable concrete. The grout must be compatible with the pipe material and must have a service life matching the new pipe.
21ce0b5b-a0b5-5563-926d-a5b663c43bf1 | note | Standard / Specification - PS 16.28.6
6452e849-5730-5a05-b88a-00898c8eb6e5 | note | Verifying Document - Datasheet
7a11676a-9d0c-5f20-bb5d-711364675e3b | note | Frequency - Prior to use
6fd48873-1f73-56ca-8733-813d24658667 | note | Verification Activity: Activity - R
b2831d4c-433d-5574-882a-4d4f3b316bfd | note | Verification Activity: By - SE
ad056676-d1f5-414e-a498-a52f99ada406 | checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
73f4b1f1-504f-56ef-9019-c043a8801d39 | textbox | Contractor's Rep Name:
5d0a416c-c4be-5a77-9499-b5f659c6b17b | textbox | Engineer's Rep. Name:
79f35bc8-27fa-5034-9030-fd4de24a3e7f | date | Date:
b1b9a132-2a74-4433-b020-982622f17d87 | signoff | Add Signature
a131da22-074b-5453-8279-a9db1f38d155 | checklist | Ω (DEPRECATED) ITP - Underpass Construction - 103 - (alternate Rev D) | itp | ITP - Underpass Construction - 103 - Rev D
b75e124d-fe66-55c9-a631-94fb56471ab8 | section | 3.03 Subsoil Drain
7936ef09-4ba2-52a3-8d41-c9fbcfa54b56 | checkpoint | 3.03.1 - Trench Grade
5a825b5a-a81e-5763-a66f-a3c4ab9c07aa | note | Acceptance / Conformance Criteria - Unless otherwise specified trenches shall have: a minimum gradient of not less than 1 in 100; vertical sides from the trench bottom to a minimum of 300 mm above the top of the pipe; and a minimum depth that will ensure that, when the pipes are laid, the invert level shall be not less than one metre below finished subgrade level.
59574125-fa0e-51a5-b0b1-305fc8c48fc0 | note | Standard / Specification - NZTA F/5 PS 16.11.2
a34ecc5c-a8a9-5471-8641-078cc46e395f | note | Verifying Document - Note only
e3ebcf79-48e9-5d4d-a489-f797dd8e07c7 | note | Frequency - Each Pipe
642f912f-eb4e-5693-915c-b1da3c7b0ae8 | note | Verification Activity: Activity -
1bdfbb34-22fc-5cac-badf-aa16b428f0fb | note | Verification Activity: By -
4fb79358-a052-5b54-a7da-8d33d0decaaf | checkpoint | 3.03.2 - Bedding and Installation of Drainage Pipe
0b9ec629-0e91-52c2-84a8-2312db9d6d4e | note | Acceptance / Conformance Criteria - Prior to laying the drain pipes, the Constructor shall ensure that pipes do not become contaminated with clay or soil and that pipe slots are not blocked. Any such blockages shall be removed before pipes are laid.
24c7d13e-d811-5526-a8b3-d4e5db24cb7d | note | Standard / Specification - PS 16.11.3
acdca211-7142-57e4-9733-55a2e313315a | note | Verifying Document - Site Records
95a8af9c-0114-52f3-86ad-22661cc7cb79 | note | Frequency - Each Pipe
dec02c4e-a6b1-5312-90ac-8e6590e96adc | note | Verification Activity: Activity - S
6a8ed684-f053-5001-8c22-b2d53cb2bdc7 | note | Verification Activity: By - SE
08f9a616-8e77-5407-a5e6-3c88a6e10fbd | checkpoint | 3.03.3 - Bedding Placement
638f4e29-af56-5a25-8c6e-4b1ed8411883 | note | Acceptance / Conformance Criteria - The filter material shall be placed, and the drain pipe installed such that the pipe is at a uniform grade and is underlain by a minimum of 50 mm and overlaid by a minimum of 150mm of filter material which completely surrounds the drain pipe. The filter material shall be placed in a manner to achieve a generally uniform dense state.
1cde5f44-36f4-5146-82ae-09ac30b33502 | note | Standard / Specification - PS 16.11.3
2df2edec-93ec-504a-8c3f-aef59704321c | note | Verifying Document - Site Records
1887868a-bd9b-58f2-8097-ff9c3d6e075f | note | Frequency - Each Pipe
95be1982-df6b-5548-8fdf-1794f1272a38 | note | Verification Activity: Activity - S
e2d71b85-aea0-5514-906a-894b68b85239 | note | Verification Activity: By - SE
05ce68f8-b4be-5cce-8474-bbb07ed45901 | checkpoint | 3.03.4 - Pipe Orientation
545e51c8-998d-5db4-ab11-ab655af9b089 | note | Acceptance / Conformance Criteria - Pipes should generally be laid so that the perforations are oriented as shown in accordance with the manufacturer’s recommendations for corrugated HDPE pipes.
e83dea8a-bb7d-530a-a507-1e3e935c3b15 | note | Standard / Specification - PS 16.11.3
386f9756-0252-5e91-961f-be0c39092910 | note | Verifying Document - Site Records
8e6012fe-5fa6-5645-ab36-85e2437c148b | note | Frequency - Each Pipe
7d7c5b81-c6d5-5666-9315-8e665aa790fe | note | Verification Activity: Activity - S
40acf20c-f89c-56a7-aac9-d3aab1360982 | note | Verification Activity: By - SE
ba976090-1b76-596c-bd7f-77d7d3b73ec5 | checkpoint | 3.03.5 - Pipe Jointing
6eabb8c3-b7cc-503f-a1bd-080fbd01b7c9 | note | Acceptance / Conformance Criteria - The drain pipe lengths shall be joined following the manufacturer’s instructions or as approved by the Engineer, with the pipe jointing carried out to leave a smooth flush internal surface. The top ends of the pipes shall be capped.
b7802ea9-fffb-5d0d-8d4e-a8511c63bb5c | note | Standard / Specification - PS 16.11.3
beb3303d-d6a6-5b0a-9def-894f21bd4a32 | note | Verifying Document - Site Records
f2e60124-0673-55b1-ac18-b95ea4948217 | note | Frequency - Each Joint
c4aa85c4-253f-51c8-8034-03eca82556b1 | note | Verification Activity: Activity - S
5c89fe7f-88fc-535f-b560-a91e60cca1d6 | note | Verification Activity: By - SE
4e27c6e6-5a37-57e4-a099-dcb7417191e0 | checkpoint | 3.03.6 - Pipe Installation Inspection
25f9dead-3803-5267-b4f2-b7fc85c343fb | note | Acceptance / Conformance Criteria - The drain pipe installation shall be inspected and approved by the Engineer before placing filter material and backfill.
cc19571e-22e3-549e-9f0b-ce04fb0758b1 | note | Standard / Specification - PS 16.11.3
8d10cb49-39e2-5fd3-9bb5-1eac253672ec | note | Verifying Document - Engineers Acceptance
b7a30e4e-2653-5f3d-a6b6-958ba21dc61a | note | Frequency - Prior to backfilling
787eaa1b-fa2d-5975-bffa-558bb9a0bcf8 | note | Verification Activity: Activity - HP
6a6f5f82-a7d4-5363-9f7d-38835f0f052e | note | Verification Activity: By - ENG
07e48991-e1d5-55f5-866c-b6f966a404a3 | signoff | AUTHORITY HOLDPOINT
964a0105-283d-577c-9761-88c8229fe022 | checkpoint | 3.03.7 - Lose Debris Removal
3b8aa6d8-54f0-57e6-bcfe-8c0920cc219f | note | Acceptance / Conformance Criteria - Prior to placing filter material and backfill, the base and sides of the trench shall be cleaned of loose debris so far as is practical.
18c0edce-89e4-5835-b3ee-55d6114ca807 | note | Standard / Specification - PS 16.11.3
b6e5ea96-2fea-5f01-974c-87c28f740317 | note | Verifying Document - Site Records
8d61ce2f-a264-5064-bfbd-71b3dc71b4ca | note | Frequency - Prior to backfilling
c1682f1c-97d3-5006-96ba-8aaebf7faa3d | note | Verification Activity: Activity - S
6b40297e-5bcb-59c4-9d15-1ae7de0a7646 | note | Verification Activity: By - SE
5dfa7e2e-ce9b-55bb-8c98-a7f45d62276a | checkpoint | 3.03.8 - Subsoil Backfilling
a99f44b1-d645-51f9-a00e-2a05d15871d4 | note | Acceptance / Conformance Criteria - The backfill shall be filter sand as detailed in clause 2.2 of this specification. The backfill material shall be placed in layers not exceeding 150 mm loose depth and shall be positively compacted around the sides of the pipe to provide support of not less than that of the adjacent material
53345917-6def-5d2f-bbe5-49fc142886bb | note | Standard / Specification - NZTA F/5 PS 16.11.2
52f9ed58-0dd9-553d-b223-7df02e175438 | note | Verifying Document - Site Records
1af5364c-98d0-5ebf-b88d-7651311e29c5 | note | Frequency - Each Pipe
5f912046-e498-55c2-9660-0578ef4a8569 | note | Verification Activity: Activity - S
1e6866a2-9bf2-554a-bd79-9d3d28360cd9 | note | Verification Activity: By - SE
18ddc1ae-3926-5357-8ed5-e358e11d3d78 | checkpoint | 3.03.9 - Overlaying
3dc029ca-01fe-5d18-bbd3-94aa04526572 | note | Acceptance / Conformance Criteria - The completed drains shall be backfilled with an overlying capping layer to prevent the ingress of surface water.
7e09bae0-802f-5e66-bb65-4940f7cb9b27 | note | Standard / Specification - PS 16.11.4
f5a28aa2-6f19-5b71-bea8-68f5c6041393 | note | Verifying Document - Site Records
4493885d-6915-57fe-9d1a-23d75a3ce6ae | note | Frequency - On Completed Drains
7adc524f-00b4-58ba-9c69-79f6f9411a2a | note | Verification Activity: Activity - S
5fc751ca-743c-55d3-8a70-7fd4e6d7c3fe | note | Verification Activity: By - SE
96bce2aa-39c9-51ad-b916-3ecb5c5fd9df | section | 4.21 Underpass Materials
e0b3f528-ff2a-5e28-88ad-3bd75d383107 | checkpoint | 4.21.01 - Concrete Plant
ab4e816b-dd78-518b-9a72-efc2d4244db1 | note | Acceptance / Conformance Criteria - All plants supplying concrete to the project shall hold and maintain a current quality Certificate of Audit in accordance with NZS 3104 throughout the duration of their supply of concrete for the contract. A copy of each plant’s current Certificate of Audit shall be submitted to the Engineer prior to their initial supply of concrete.
50891815-9127-5d05-848b-ec925b07f08a | note | Standard / Specification - PS 19.7.1
a17fec7c-3b13-500e-9b73-557c32e19f8b | note | Verifying Document - Audit Cert
9c99f9e6-ad95-5fa7-87dd-0945a9f87e6b | note | Frequency - Prior to their initial supply of concrete
b3054aed-00be-55ac-8fbb-1a9a301f2470 | note | Verification Activity: Activity - HP
cd9294ab-4cb7-5f1a-a0ca-33d25c671c38 | note | Verification Activity: By - ENG
b8384fc2-03a0-5160-831c-e5865c63514a | signoff | AUTHORITY HOLDPOINT
dffc3c4c-2cfd-525c-a09a-fb49cbcec42b | checkpoint | 4.21.02 - Blinding Concrete
e58bfdf0-28df-517a-bcb3-fc8d2254f3dc | note | Acceptance / Conformance Criteria - Blinding concrete shall have a minimum 28 days compression strength of 10 MPa and comply with the requirements for Prescribed Mix concrete specified by NZS 3104.
1768c0eb-9004-59b2-a4f5-546abbeab3ab | note | Standard / Specification - PS 19.5.1, PS 19.7.10
88d67771-21cd-5e67-bce9-f39ca81aac7a | note | Verifying Document - Approved Mix Design
55cb3a7e-9326-5bdb-aea7-41862f126096 | note | Frequency - Submitted to and approved by the Engineer prior to concreting
31c7a234-9443-59b8-9b27-5a3dd795b3ca | note | Verification Activity: Activity - HP
19395abf-34c5-5d4d-94a2-c3cc6c93861b | note | Verification Activity: By - ENG
9da81b7a-de1d-517f-b7d7-918eb85f955a | signoff | AUTHORITY HOLDPOINT
edf8e519-1f31-581a-b5b0-d9853d6a7eae | checkpoint | 4.21.03 - Underpass Entrances Concrete
21647618-bf25-5fe9-946b-bd84b5f3096e | note | Acceptance / Conformance Criteria - The Underpass Entrances (insitu) concrete shall be a Normal 40MPA 19mm Mix.
55eab315-e9d0-533b-844a-4cea89e6d407 | note | Standard / Specification - PS 19.6.1, PS 19.7.9
53d50bc9-d22d-5a96-a248-c1a4bc6485b4 | note | Verifying Document - Approved Mix Design
4f3b7b40-9245-51c0-903d-f98b33de7aa1 | note | Frequency - Submitted to and approved by the Engineer prior to concreting
0f861b53-0336-5abf-9fb1-8654802e2975 | note | Verification Activity: Activity - HP
49588221-f006-56ff-98da-aab867aa5e2b | note | Verification Activity: By - ENG
d6f30363-6fc1-5066-a243-d3eed523f674 | signoff | AUTHORITY HOLDPOINT
1111f606-130a-5570-82ad-467c19fd12aa | checkpoint | 4.21.04 - Precast Mild steel fixings
6b9ad874-da03-5eb2-a493-eaa3b5795238 | note | Acceptance / Conformance Criteria - All mild steel fixings including bolts, nuts, inserts, washers, cleats and brackets shall be hot dip galvanised after fabrication.
2872f20b-81bd-51d8-b831-68141754bae5 | note | Standard / Specification - PS 19.15.6
bac2d439-e0ad-54d6-b1bc-7f66f5992dea | note | Verifying Document - Datasheet / Mill Certs
177a3925-a6a6-5831-a814-d904c83041c2 | note | Frequency - Prior to use
ad107b81-573c-5dbe-bdf0-92ade971848e | note | Verification Activity: Activity - R
95aa8398-9a54-52ee-ae59-c0d022ed59e5 | note | Verification Activity: By - SE
da46fb56-3e14-522a-b1e7-aed67309ec4b | checkpoint | 4.21.05 - Precast Stainless steel
95aaca8e-d24d-56b0-8084-c2bc1013e9ac | note | Acceptance / Conformance Criteria - Stainless steel shall be type 316 unless otherwise specified.
c2f854f7-9478-5643-80f7-81e3a31336e2 | note | Standard / Specification - PS 19.15.7
12cf738f-e8fd-5e35-ab9b-fa2bbfdc5e93 | note | Verifying Document - Datasheet / Mill Certs
ba5e0f7d-5b16-5b14-860c-0071a41a3d36 | note | Frequency - Prior to use
7c0d4981-fffc-5acc-aaf5-c8efc60b0f08 | note | Verification Activity: Activity - R
7c29d879-0f53-5e0c-bc00-79d5f6b9fb45 | note | Verification Activity: By - SE
2df7f4c0-191f-57ac-b0f0-8222b88f5810 | checkpoint | 4.21.06 - Reinforcement cover spacer blocks
24e559ba-8770-581e-8a28-1ffdc8befcc0 | note | Acceptance / Conformance Criteria - Reinforcement cover spacer blocks shall be either Concrete spacer blocks made from concrete containing 8% Microsilica and with a specified strength at least 10MPa stronger than the surrounding concrete or Plastic spacer blocks are in general undesirable in corrosive environments but may be acceptable in specific areas.
d2c2d1bb-9d97-566e-921e-50e9b9c89592 | note | Standard / Specification - PS 19.7.8
cbe48102-af68-5110-8e42-310f15a1c9a1 | note | Verifying Document - Datasheets
db3eec8f-a1cf-5175-9df8-a404cb0fe2c9 | note | Frequency - Prior to use
3dc87d9d-da26-5b84-8446-4db02939b10d | note | Verification Activity: Activity - R
5c96b7f2-3726-5bf2-a5a8-97df24073580 | note | Verification Activity: By - SE
d027755f-c801-51e4-97ab-766e0e456545 | section | 4.22 Underpass Materials – Associated Works
6e241f13-080a-54f3-91a9-3f63a5538f62 | checkpoint | 4.22.01 - uPVC Pipe
799ce4c3-b444-5bf0-a4c7-8a81a038944a | note | Acceptance / Conformance Criteria - Pipes and fittings shall comply with the requirements of AS/NZS 1254:2010 for uPVC pipes
fb3090ed-524c-5e9e-8be9-ebb7f72f38a9 | note | Standard / Specification - PS 19.27
47c409fc-ca36-5466-a6c7-34ab591a4ecf | note | Verifying Document - Datasheets
1bdf0a2e-145c-56ed-b5cf-b11ff5ea2a0d | note | Frequency - Prior to use
40e1d2f3-924f-577b-a3d2-032b1011fd54 | note | Verification Activity: Activity - R
8aac147d-0275-5bc1-8054-b2d32e4f9a28 | note | Verification Activity: By - SE
bb0e75dc-1a51-5fad-b17b-a8746b4bb728 | checkpoint | 4.22.02 - Anti-Graffiti Product
5218e77b-9617-51a4-b87d-c1b5cbd6a6f0 | note | Acceptance / Conformance Criteria - Permanent (not sacrificial) anti-graffiti coatings shall be applied to the exposed faces of all concrete surfaces including wingwalls. The coatings shall have a design life of not less than 10 years. The Contractor shall submit the proposed extent of application for authorisation by the Engineer.
c0d998c0-439e-5f77-a1dd-d0419f1b864a | note | Standard / Specification - PS 19.24.1, PS 19.24.2
952900f5-f511-5977-a464-5e6b3ea6a7fb | note | Verifying Document - Details of prequalified Product
89c8e6b0-04a5-545d-bd99-a3d6235cacda | note | Frequency - Prior to Application
02440b62-18bf-5f43-8d34-cf6119d66475 | note | Verification Activity: Activity - HP
4075fef5-1bc0-5e73-bf7f-a9c113b3eb3c | note | Verification Activity: By - ENG
9567846c-86e7-5454-ac56-98fecc04f512 | signoff | AUTHORITY HOLDPOINT
d1b39a32-9130-500f-a04e-ccb9280990c3 | checkpoint | 4.22.03 - Anti-Graffiti Label
9eaffd7a-e78a-5508-bff7-b6efdc0a3b7b | note | Acceptance / Conformance Criteria - At least two weeks prior to the applicable works, the Contractor shall submit details of the label to the Engineer for authorisation.
568eb9a0-bae2-59fb-8913-b0450b38dcff | note | Standard / Specification - PS 19.24.4
763f1198-2558-577e-9562-a0a521aa9053 | note | Verifying Document - Label Details
add72d71-4ddb-54c2-8263-0e9767af2cac | note | Frequency - At least two weeks prior to the applicable works
c3bcff99-f892-51e5-80d1-e6b03fa7d0bb | note | Verification Activity: Activity - HP
1b7b76a2-f61e-51d4-90e0-ede539098d83 | note | Verification Activity: By - ENG
cbf031ee-83b6-5793-8803-136577e376a1 | signoff | AUTHORITY HOLDPOINT
3d41d29f-bfe3-5761-947c-2852f1080563 | checkpoint | 4.22.04 - Steelwork Fabrication Notice
03e9c430-3d7e-532e-b8cd-b3a1ef60d24c | note | Acceptance / Conformance Criteria - To allow for the provision of inspection and verification, the Contractor shall, in writing, notify the Engineer at least one weeks prior to commencement of the workshop fabrication work.
e7a47829-5ce2-5afb-b244-4e67d5890c79 | note | Standard / Specification - PS 19.26.6
e2beb952-2724-5cd3-8986-8c874b6d3c17 | note | Verifying Document - Notice
aa01aa31-5b36-5d6a-bfca-0aef6ae2e25c | note | Frequency - At least one weeks prior to fabrication
9a9c1366-9c5f-5d40-bfc9-82cdec8c29bc | note | Verification Activity: Activity - HP
8045cccf-7e33-55bc-9a10-5e89a52ff29c | note | Verification Activity: By - ENG
8ab17f8f-b589-5fe1-b550-165d674a5e43 | signoff | AUTHORITY HOLDPOINT
9887edd4-a572-5477-af85-3e459867e16a | checkpoint | 4.22.05 - Steelwork Shop and Erection Drawings
16ba96e5-aa3e-5f2a-9605-6e06f51b3492 | note | Acceptance / Conformance Criteria - The Contract Drawings show the design intent. The Contractor shall submit shop and erection drawings to the Engineer for approval a minimum of 10 days prior to fabrication.
020d7935-ff27-5daf-a513-00aee0baa989 | note | Standard / Specification - PS 19.26.7
28754ddd-8306-5795-b8fb-d323cf9ca003 | note | Verifying Document - Drawings
ef6ffb8c-6eab-51f6-9f18-d13ddd3cf96c | note | Frequency - 10 days prior to fabrication
2955f702-fd50-52b6-9680-e14e34cdade4 | note | Verification Activity: Activity - HP
a8f5c4de-d8e9-5fbc-8d37-5cfd723ff004 | note | Verification Activity: By - ENG
cb6277a0-8e1b-5abe-983e-d2e4e943f079 | signoff | AUTHORITY HOLDPOINT
a08a068c-cb8c-544c-b872-dbbbdfaf4857 | checkpoint | 4.22.06 - Welding Plan
d5e45c8a-bcf6-5134-b85a-5c97931323d7 | note | Acceptance / Conformance Criteria - The Welding Plans shall comply with AS/NZS 5131, Section 7.
3f757683-1d04-5266-8f05-a027b05765ba | note | Standard / Specification - PS 19.26.8
a5af26f1-e267-5b53-a262-16aa67697145 | note | Verifying Document - Welding Plan
10972df7-83f3-5a56-98b7-38cf8b02be1b | note | Frequency - Prior to Welding
47e75c00-9012-505c-b426-923b76fb29da | note | Verification Activity: Activity - R
bfe8f15f-9afb-51be-bc14-8e4602877f2f | note | Verification Activity: By - SE
77a3eeaa-7d42-57a8-9949-440aa7dbc1e6 | checkpoint | 4.22.07 - Welder Qualiications
e0a73912-be6f-5fa7-93b5-9027c6f145dd | note | Acceptance / Conformance Criteria - Welder Qualiications shall comply with AS/NZS 5131, Section 7.
a1bc81b4-f70e-5848-a867-a0e90119cf90 | note | Standard / Specification - PS 19.26.8
054b66e8-4899-5c88-8f65-0f4fb94b4822 | note | Verifying Document - Qualifications
40e2d8cd-da35-5805-b0a3-a862bf6c04c9 | note | Frequency - Prior to Welding
b6f572b1-8d43-51ce-942a-4d753847c773 | note | Verification Activity: Activity - R
04171d3b-085f-5d7c-8f14-dc4e98d48d75 | note | Verification Activity: By - SE
196d8138-343d-53bd-9148-554125db4a5f | checkpoint | 4.22.08 - Supply of Non-slip Coating
322a9559-4d62-5e22-a223-4051fd4c9a3c | note | Acceptance / Conformance Criteria - The top of the underpass floor slab and bottom chamfers will have Sikafloor 91 or Sikafloor 150.
da60b5e5-b1a2-50a1-9e5d-0e7a2e0608c6 | note | Standard / Specification - PS 19.23.1
d085adb4-b494-51c9-88ed-fff6df0c512e | note | Verifying Document - Datasheet
2e19d3ac-3238-5768-9a51-7a7f5500a1cd | note | Frequency - Prior to use
096efca7-24ec-570e-9c18-d85822c8931e | note | Verification Activity: Activity - R
d8ab53ac-567d-5c19-a34b-753f435b5d36 | note | Verification Activity: By - SE
8b7ece77-1fec-5c32-9b46-f85b3727fb63 | checkpoint | 4.22.09 - Joint Sealing and Waterproofing Sealant
2a963364-86aa-56d0-b050-3a0cdf7fd2cf | note | Acceptance / Conformance Criteria - Joints are to be sealed using a fuel resistant, multi-component polysulphide sealant designed for horizontal and vertical joints in concrete and is joint sealant pourable or gunning grade as appropriate.
c0485a71-7662-5578-a384-41cfada12ef3 | note | Standard / Specification - PS 19.22.1, PS 19.22.7
58ed961a-51a6-5ea4-934a-59d3cbb005c4 | note | Verifying Document - Datasheet
af729257-5818-5af8-bbda-6c27cb4b53de | note | Frequency - Prior to use
7c7a34c9-cd8b-5512-bbe9-76ab8daf417b | note | Verification Activity: Activity - R
fe3dd2e7-693c-5e6d-8cf3-921ba850856f | note | Verification Activity: By - SE
509f57c9-951f-524a-a813-237822099452 | checkpoint | 4.22.10 - Debonding tape / Backing Rod
c8d19d9c-4304-5947-b606-694b94fa679f | note | Acceptance / Conformance Criteria - A polyethylene bond breaker tape, or a closed cell, polyethylene backing rod shall be used in movement joints unless joint sealant is natureally bond breaking.
9f0347a3-d8b2-5cfd-8df8-306bf6785c3f | note | Standard / Specification - PS 19.22.3
fc3e1642-371d-5fbe-8859-306994ce4b5c | note | Verifying Document - Datasheet
162f94c9-aff9-5bc4-bcfd-e088edb9dd70 | note | Frequency - Prior to use
1970323b-b36e-509f-a98e-c751c4e8e176 | note | Verification Activity: Activity - R
5f389c13-0f3d-5609-bbb7-022ab97955c0 | note | Verification Activity: By - SE
716c18c8-b218-5a52-b884-d30c5f9c7fd2 | checkpoint | 4.22.11 - Compressible filler board
c9323f49-11fa-5536-888d-840c99c80ea6 | note | Acceptance / Conformance Criteria - Details of the Compressible filler board proposed to be used shall submitted to the Engineer for acceptance at least 1 week prior to installation.
9f297b92-1710-5b4c-a7f7-bfa57ad20cc2 | note | Standard / Specification - PS 19.22.6
a4a0c796-3f37-5eb2-9ec0-d333b5063c9d | note | Verifying Document - Datasheet
5080b222-f814-55eb-aaee-2c1df13f977f | note | Frequency - prior to installation.
6d9b56a0-3a9e-508f-9659-98c5292d6810 | note | Verification Activity: Activity - HP
5ec94610-2fb4-5559-a06f-b176b3ea1179 | note | Verification Activity: By - ENG
63ef02f2-9bee-5161-82f3-fab62a00a088 | signoff | AUTHORITY HOLDPOINT
b3c7639a-7ced-5f49-a911-333bd4864dfa | checkpoint | 4.22.12 - Reinforcement bars
04527bb9-f004-5b53-9c9e-e2bd28e40059 | note | Acceptance / Conformance Criteria - All Reinforcement bars shall be of New Zealand origin unless otherwise accepted, grade 500 ductility class E and shall be manufactured by the micro-alloy process. Quenched and tempered reinforcement shall not be permitted.
595f57bd-32e9-58aa-a56d-578247a7a30c | note | Standard / Specification - PS 19.16.12
887d9567-f080-55bb-9196-ebfaf371478e | note | Verifying Document - Mill Certs
1c90a3a9-fbf4-59a9-a205-bcbe9514d7ff | note | Frequency - Each Item
5cbd602e-263d-5361-8e89-14aa301586f1 | note | Verification Activity: Activity - R
9ba49534-0104-534d-8095-7b402a304a92 | note | Verification Activity: By - SE
b6d13b33-48f8-5267-87e0-2af4c71ad310 | checkpoint | 4.22.14 - Reinforcement Welding Approval
43cd3715-5181-53ef-831f-94989cbc8718 | note | Acceptance / Conformance Criteria - Steel reinforcement shall not be welded, except where specified on the Drawings or approved by the Engineer. In either case, welding of reinforcement shall comply with AS/NZS 1554.3.
fec3a366-227c-5726-b040-0e5ab4b281b0 | note | Standard / Specification - PS 19.16.15
8b731a0b-2d5a-5be2-a43f-f50e1c74cda8 | note | Verifying Document - Engineers Approval
87e75b92-11c0-5748-9286-5e3163066ff5 | note | Frequency - Before Welding
c21bd829-c45d-52d8-a576-e041f4a6d69a | note | Verification Activity: Activity - HP
2693438c-6271-52f1-aef7-cc9d5b4caef8 | note | Verification Activity: By - ENG
25ea82a6-5d0f-516e-853c-22770674301f | signoff | AUTHORITY HOLDPOINT
36bf2169-cd8e-53ba-b367-d9b9d17d5f58 | checkpoint | 4.22.15 - Welding TPI Inspections
253f77b6-7398-5cc9-a82c-3027d79ff389 | note | Acceptance / Conformance Criteria - The welding shall be inspected by the Contractor’s Third Part Inspector who shall meet the “Qualifications of Inspectors” requirements of AS/NZS 1554.3 Clause 10.2. Inspections of the welding shall be in accordance with AS/NZS 1554.3 with the following additional requirements: All welding shall undergo visual scanning. Welding shall be non-destructively tested to the extent and standards of acceptance of AS/NZS 1554.1 Appendix F, for SP welds. All welds shall be visually scanned by the steel fabricator. 30% of the welds shall undergo visual examination in accordance with Table 6.2.2 and 5% of the welds shall be subjected to radiography or ultrasonic testing in accordance with Table 6.2.1 of AS/NZS 1554.1.
3003d15b-f726-5c30-a26e-30a65aa058ca | note | Standard / Specification - PS 19.16.16
28d1061d-43d7-5fca-bd12-12b20497b5ca | note | Verifying Document - TPI Report
57dd28c5-1305-5107-83ba-76c6da428155 | note | Frequency - 100% Visual Scanning
3ae22829-0d0b-5ded-9644-1b8685de51f6 | note | ○ 30% Visual Examination
38dab23c-4988-5a54-a431-895330cf20ad | note | ○ 5% Radiography / Ultrasonic Tesing
9bb66c09-0645-50f0-bfae-c1bddd362c65 | note | Verification Activity: Activity - R
5d5a33cc-fedf-5b61-961e-7035a0a6df01 | note | Verification Activity: By - SE
20daaa14-ea0e-54ef-b89c-4fed1c1a1889 | checkpoint | 4.22.16 - Bar Schedule
c63c6ab9-a3cd-57a8-8382-3471038bb837 | note | Acceptance / Conformance Criteria - The Contractor shall prepare reinforcing bar schedules in accordance with BS 8666 with due allowance for bending tolerance and associated drawings, two copies of which shall be supplied progressively to the Engineer for comment at least 14 days before the start of placing the corresponding reinforcing bars.
9f9397fb-618b-5a07-a928-8ab202431383 | note | Standard / Specification - PS19.16.20
899dbddf-f474-5c5e-a0a4-1b2feeb7a68c | note | Verifying Document - Bar Schedule
b8f34fcd-0721-576c-99d9-a183a21971b3 | note | Frequency - At least 14 days before the start of placing
adc40734-084b-5ca1-ba8c-629a90bed9a5 | note | Verification Activity: Activity - HP
90c4a386-be5b-5b49-a0dd-2c033842d7e1 | note | Verification Activity: By - ENG
32aff0ff-0a4a-51c3-ab26-0add07ab217c | signoff | AUTHORITY HOLDPOINT
185b1965-31fd-51ec-aa63-ac7a7967f669 | checkpoint | 4.22.17 - Reinforcing Mill Certs
28c2e918-3e64-571e-9ca4-af748b8ca269 | note | Acceptance / Conformance Criteria - Test certificates shall be obtained from the manufacturer for all strand, cable and bar to be used in the work and copies shall be forwarded to the Engineer at least one week before the programmed commencement of ay work incorporating these materials. Test certificates shall be traceable to the batch of material supplied to the work.
36aedbff-416c-510c-bc17-f1f8ee493e07 | note | Standard / Specification - PS19.16.23
c430ef4e-35c0-5395-9dab-e6021ee7005e | note | Verifying Document - Mill Certs
b0b883b8-c64b-54db-96be-127bb91451e4 | note | Frequency - At least one week before the programmed commencement of ay work incorporating these materials
1bf0c0ce-8f08-5a4b-aaff-af7dd7e950f3 | note | Verification Activity: Activity - HP
e2046c4a-13f0-5f29-b4b3-5e4b058431be | note | Verification Activity: By - ENG
a013c0bd-4609-5101-b527-449b3a18d076 | signoff | AUTHORITY HOLDPOINT
050b4a48-1add-5f49-b3c4-b4dd0acb32a5 | checkpoint | 4.22.18 - Corrosion Protection
1de69983-966f-5af5-b935-b2de741decf6 | note | Acceptance / Conformance Criteria - Unless otherwise shown on drawings, all steel members, bolts, nuts and washers, excluding any stainless-steel components shall be hot dip galvanized after fabrication in accordance with AS/NZS4680.
bc8fb971-f2f4-5e06-b40c-4b6f39a3bbfe | note | Standard / Specification - PS 19.17.1
d9891bb3-e83c-5d9e-ac3a-f03921838555 | note | Verifying Document - Datasheet
c9ce270b-31d0-5f80-9658-b972a5195c3a | note | Frequency - Each Item
e9a603f8-f378-5fe3-95fe-434384471942 | note | Verification Activity: Activity - R
f42d3ee1-712a-5bae-9cb1-b9ed2a98f558 | note | Verification Activity: By - SE
29cce257-d047-560d-a0bb-5aec8f55d114 | section | 10.01 Concrete Pours
ddf5def9-40da-5e8f-a30a-5101fbd9bcce | checkpoint | 10.01.1 - Construction Joint Locations
b2225819-4841-5515-b5b0-8c24efd4cb81 | note | Acceptance / Conformance Criteria - Proposed location of construction joints to be submitted to the engineer for review prior to concrete pour.
73ead49a-f787-5bcd-9b66-1ed27dd9f62b | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
4f101d28-ea29-5b60-a79e-1514bbbe4711 | note | Verifying Document - Approval
e24b9822-6c43-5391-b22e-4c88b50da725 | note | Frequency - Prior to Pour
ffb0b7de-5fc6-5874-88ac-a23169c4acc6 | note | Verification Activity: Activity - HP
05202aee-2f0f-5b50-90ee-06d7e708bdc3 | note | Verification Activity: By - ENG
4ff4caf5-29c0-5bda-a708-87e499624d43 | signoff | AUTHORITY HOLDPOINT
bf3d4714-e5d5-5509-a42b-66bea38f0b8a | checkpoint | 10.01.2 - Dry Pack Mortar
4e2d023e-df97-5274-ae42-6338c9d54ad2 | note | Acceptance / Conformance Criteria - Dry pack mortar where specified on the drawings shall be places as per the manufactures instructions.
28c69cf1-5c3b-5376-b7cc-bc14706517ff | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
830cce76-3026-5938-b5b8-81548c21f972 | note | Verifying Document - Pre pour
3718fa3e-bde5-54f7-b0ef-58c637068d27 | note | Frequency - Before Works
0d0d2aa1-6d02-5899-bfc2-0340295de738 | note | Verification Activity: Activity - R
5cb8fc78-a74c-5396-8f16-0cd4be1a158d | note | Verification Activity: By - PE
12c26443-934d-5a44-88b6-8603ac4805ba | checkpoint | 10.01.3 - Blinding Concrete Subgrade Inspection
a6e89354-7048-583f-881a-c5a8f729a377 | note | Acceptance / Conformance Criteria - A subgrade inspection is required by the Engineer prior to the pouring of the blinding concrete layer.
02cb5d0a-7c74-5fbc-8978-c0789f515fa0 | note | Standard / Specification - PS 19.5.1
c440ffa9-0779-5312-8bf0-0c9ddafe2d81 | note | Verifying Document - Pre Pour Checksheet
d30b91af-1e25-5d96-b0f9-17744238915a | note | Frequency - Prior to Pour
d8bc78ee-e062-5251-b6e1-0bbf96cbbb48 | note | Verification Activity: Activity - HP
4b7f307f-830e-5ac2-8332-c105100a78f0 | note | Verification Activity: By - ENG
b1ac62b9-1d13-5f6d-a1d2-bf98e64f904d | signoff | AUTHORITY HOLDPOINT
69b1846b-7ca9-52e4-a5a4-109c63f26b5f | checkpoint | 10.01.4 - Reinforcement Pre Pour Inspection
19c5ad9e-084c-5a5b-969d-cf4824c2bb95 | note | Acceptance / Conformance Criteria - Handling, Fabrication, Placing and Fixing shall be inspected prior to pouring concrete.
5fab8b27-45db-549e-8a8f-a891509ea9d4 | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
4de9420c-a6cb-5fc0-a316-e0bd5aa3d51e | note | Verifying Document - Pre pour
a77612fb-2ee3-5e61-9f81-127619d51353 | note | Frequency - Each Pour
3b7b791f-78ee-5502-b3aa-6fe543024602 | note | Verification Activity: Activity - R
cd527bba-3d28-556c-9c50-0e74fa3bbb42 | note | Verification Activity: By - PE
980d9547-e4b1-5810-a07d-68159afd4ef2 | checkpoint | 10.01.5 - Pre-Pour Inspection
75d143b2-2584-5745-a1b8-53cb25b41a81 | note | Acceptance / Conformance Criteria - Pouring of any concrete must be inspected by the Engineer prior to further work being carried out in the area.
d6e9d056-5ebf-5bb2-a840-02716632a204 | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
30216ff3-540d-5692-85d2-c325446cdabf | note | Verifying Document - Signed Pre-Pour
02161c7a-6dfd-5862-9c35-06c35e471e5d | note | Frequency - 48 Hours Notice Prior to Each Occurrence
6c39902c-2a24-582d-afc6-7a01e8721fc4 | note | Verification Activity: Activity - HP
ceedf489-2146-576b-b867-091e67d447ec | note | Verification Activity: By - ENG
29c75676-141e-5308-a17b-059832f7f1bc | signoff | AUTHORITY HOLDPOINT
545610bf-420b-5e5f-843d-88ccb744f5d0 | checkpoint | 10.01.6 - Delivery Dockets
25fe0a4e-d671-5480-bafb-dd3f99be288e | note | Acceptance / Conformance Criteria - The delivery docket of each batch delivered certifying the mix designation, cement type, specified strength, slump, date, mixing time, water added during batching and maximum aggregate size.
c37ff86d-f8d7-550f-9d76-4c3d1d81a089 | note | Standard / Specification - PS 18.2, PS 19.9, PS 19
5b0397aa-1671-5cc0-9db9-e0ffd58ed0a4 | note | Verifying Document - Dockets
014d92ba-75c9-5260-b160-7c274feafd7b | note | Frequency - Each Pour
8d8fa6a5-af4d-5af8-9cc5-afb968b6d2f6 | note | Verification Activity: Activity - R
71e1d5b6-fdc7-5c98-9dde-e46beec353ab | note | Verification Activity: By - PE
39572f77-0e68-5354-9c7e-c02b65ddbdea | checkpoint | 10.01.7 - Slump Testing
4be0e272-64ee-5795-9508-87cdef8ccef6 | note | Acceptance / Conformance Criteria - Slump tests shall be taken for each delivery of concrete and the results recorded by the Contractor.
9a02c1f5-f25d-5af9-bf0a-a60bc7d13efa | note | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2
37426970-c98b-549e-af0a-b12a032ca573 | note | Verifying Document - Pre Pour
12c16151-de69-5da5-a308-016f37ec5db3 | note | Frequency - Each Pour
07a918d6-a30a-5651-ae95-43f9dbeb2537 | note | Verification Activity: Activity - R
8c94e8c6-8c60-5311-ad72-096191785281 | note | Verification Activity: By - PE
a68b74f2-5060-567d-be84-990c7f007dbd | checkpoint | 10.01.8 - Compression Testing Insutu Concrete
77c65b0f-0a85-5dba-bc63-1ddb276f5b1a | note | Acceptance / Conformance Criteria - The sampling of freshly mixed concrete shall be random, and the type of samples shall be representative. The frequency of compression testing shall be determined by the Engineer, but there shall be at least one set of test specimens taken daily. A set of test specimens shall consist of at least six field specimens made from one sample of concrete. Three shall be tested at 28 days after casting.
2aba5d30-13dd-5e2e-97fb-95f5bb88bc40 | note | Standard / Specification - PS 18.2.5, PS 18.2.1, PS 18.2.2, PS 19.8.7
9054545f-c754-54c7-a7c4-63863dbf53fc | note | Verifying Document - IANZ Test Results
90ecd10f-6d68-5890-b31b-74dfda657ee4 | note | Frequency - One Set Daily consist of at least six field specimens
09401163-4c9f-5e55-ac5c-8a76d5dfd521 | note | Verification Activity: Activity - R
7547f48f-d292-57bd-92c2-e2b2509a76bd | note | Verification Activity: By - PE
08e026e3-9ace-58ef-8d95-f212e891eaba | checkpoint | 10.01.9 - Compression Testing Precast Concrete
08028f69-6943-53ea-86e4-9ee591272ed5 | note | Acceptance / Conformance Criteria - For pours under 150m³: three standard cylinders shall be made for each 50m³ of concrete placed, or part thereof, for testing of 28 days compressive strength in an approved laboratory.
8869d7fb-7329-541e-9e9e-91b81318c360 | note | ○ For repetitive small pours (e.g., precast concrete barrier pours) undertaken on a regular basis, three standard cylinders shall be made for each of the first five pours of any one type, and thereafter three standard cylinders shall be made for every fifth pour of that type for testing of 28 days compressive strength in an approved laboratory.
6dec6147-31cc-5995-9660-6ba7e6de709a | note | Standard / Specification - PS 19.8.7, PS 19.8.8, PS 19.8.9, PS 19.8.10, PS 19.8.11
bb6f54c1-fcb8-5682-b271-e2a46799d161 | note | Verifying Document - Plant Test Results
1816b98d-289c-514d-aa77-1fe2e47ae8f4 | note | Frequency - 1 set per 50m3 or part therefor of / First Five then every 5th
1a804d19-4630-57cc-a064-6fd260ebe80f | note | Verification Activity: Activity - R
0a70add6-acb4-54c2-9ab8-85377d5c183e | note | Verification Activity: By - PE
ada65559-9e0b-5d91-800f-942054472e78 | section | 10.02 Post Pours
4e22a134-60cc-588b-8f12-eaeb422f1a7c | checkpoint | 10.02.1 - Post Pour Inspection
ef616bfd-ca9d-5a6d-98d4-a8c772fb6e05 | note | Acceptance / Conformance Criteria - Following the concrete pour, the concrete shall be inspected for Size, Shape, Features, inserts, reliefs, and Finish against the drawings.
22cf8016-1c26-50d9-8e00-d89060bf73d2 | note | Standard / Specification - PS 18.2, PS 19, PS 19.15
4a498a84-c0e8-58b9-a2bb-add3a815d9c4 | note | Verifying Document - Post Pour
71b83169-6721-504e-9879-6a9a37232e7b | note | Frequency - Each Pour
489909c1-e1de-5852-b917-19015021ef6e | note | Verification Activity: Activity - R
e7462f14-b203-5510-b1bb-0a70c0663655 | note | Verification Activity: By - PE
bb0e6aa4-62be-5996-b3b1-73c166e80309 | checkpoint | 10.02.2 - Construction joints
45612da8-c8b1-590f-8ce3-4f2ec1bef678 | note | Acceptance / Conformance Criteria - Construction joints shall be placed as per the drawings / agreement.
9e445051-818f-5bcf-9e9f-56f5b20daf0b | note | Standard / Specification - PS 18.2, PS 19, PS 19.15
361daf4a-ee44-5b7e-9694-eeb7fb685716 | note | Verifying Document - Post Pour
8164530f-30ef-5ede-9921-23ed54a87bef | note | Frequency - Each Pour
d2d35986-55f4-5f08-a422-a7a6a214bf91 | note | Verification Activity: Activity - R
7ecc7eb5-729f-5be3-9677-16e4c1389e87 | note | Verification Activity: By - PE
583a9a8f-3977-5799-863b-f43c473088a2 | checkpoint | 10.02.3 - Concrete Curing
7f2ae6b5-60e8-5fb2-b8ad-adc1212f1334 | note | Acceptance / Conformance Criteria - Concrete shall be cured for at least 7 days as per the drawings / specification.
a89b33bd-e872-5839-bdc1-cc4c6527d382 | note | Standard / Specification - PS 18.2, PS 19, PS 19.12
4dc2ba2b-036e-5993-913d-9f4653f23c8d | note | Verifying Document - Post Pour
183fbd73-7c91-5898-b6ce-e3c8ee8aed2f | note | Frequency - At least 7 days after pour
8100b68e-5c5c-5135-96c6-ef100345ce14 | note | Verification Activity: Activity - R
46cb6b6d-0a8d-5430-a020-efe33572e359 | note | Verification Activity: By - PE
8dfa5b69-676d-5f38-a9fb-4e13f3a8b18a | checkpoint | 10.02.4 - Stripping
d604b028-ad77-5560-8a9b-056eb63c5be1 | note | Acceptance / Conformance Criteria - No formwork shall be stripped until at least 3 days have elapsed from time of pouring concrete.
c23c71d1-ca3a-5fff-aa2c-5c867063bccf | note | Standard / Specification - PS 18.2, PS 19
3e3ed230-058d-539c-9cc7-3af3b6a95b74 | note | Verifying Document - Post Pour
0e46acfa-dfeb-57e8-97e2-fff14e835f30 | note | Frequency - At least 3 days after pour
fb50bd4e-f794-56bb-837a-01995173a024 | note | Verification Activity: Activity - R
25cab698-87f6-55f9-998b-be2f0160387b | note | Verification Activity: By - PE
38f0359e-a3cf-5c68-8d7d-a71754a24712 | checkpoint | 10.02.5 - Protection of Completed Works
3f1cd740-99ba-5dba-83c2-e1c7789037ce | note | Acceptance / Conformance Criteria - Protect the completed work from damage and from dropping other materials during the remainder of the construction period. Do not use the completed work as a building platform or for material storage.
c36a781d-ed0c-5bd0-a7b7-fb410ad4f686 | note | Standard / Specification - PS 18.2, PS 19
75d9f11d-8901-5dcb-9ddb-25a9d18b395a | note | Verifying Document - Post Pour
e208d638-af54-5601-98b4-4cc7c84259d4 | note | Frequency - During the remainder of the construction period
d9ac58cd-70da-50a7-9260-d67214476827 | note | Verification Activity: Activity - R
20b0923c-c870-5551-ba13-752ba14518be | note | Verification Activity: By - PE
3bf41fc9-dbeb-5a09-9b35-0de57ba98e79 | checkpoint | 10.02.6 - Defective Concrete Finishes
662a6a18-e4f1-56cc-88a5-4adcecd3b56e | note | Acceptance / Conformance Criteria - Repair of defective concrete finish other than that due to minor porosity of the surface shall be carried out only when approved by the Engineer.
06ed3d80-d320-54fa-925c-d71ae6aada41 | note | Standard / Specification - PS 18.2, PS 19, PS 19.13
5edf30ca-0440-5c10-8226-2136dbf8e4bc | note | Verifying Document - NCR
5fa2c48d-3f8b-58e9-8cd3-be43b590087a | note | Frequency - Prior to non Minor Repair
d61120b3-f98f-5a5f-b700-12348ccf1e73 | note | Verification Activity: Activity - V
306aecf1-15b6-5ac1-9384-0dc4da90ae31 | note | Verification Activity: By - SE
09d6770f-c9fd-55d6-a473-70cd1fa70a46 | section | 12.01 Undercut to Drying Site and Backfill with Compacted GAP65
d7cbace4-bb93-5f8e-94fc-3072a77f43ae | checkpoint | 12.01.01 - Excavations
6df90cfc-0dc5-58b3-a005-63755c7150ab | note | Acceptance / Conformance Criteria - All excavations/cuts shall be carried out in fully drained conditions with no free water on the working surface.
1d036e38-1c92-5eb8-98e4-670a5a796323 | note | Standard / Specification - PS 19.4.1
1c9f2829-2f25-5657-981c-2b56a8c9f44e | note | Verifying Document - Site Records
4e18c53c-c918-5a26-9bb3-69cd6e307b19 | note | Frequency - During Works
29676c31-8c86-5bcf-9940-f3f44cc24c74 | note | Verification Activity: Activity - R
2529606b-9b78-5c1e-a72f-054361639454 | note | Verification Activity: By - SE
0b423a17-f2f0-5007-a86c-b30cc9b57bc5 | checkpoint | 12.01.02 - Foundations
46d15275-3f55-5558-95b0-b8a63c9aea1c | note | Acceptance / Conformance Criteria - The Contractor is to confirm that the subgrade achieves the design CBR prior to pouring of concrete.
7cd645d4-76c3-572f-b0c1-455157d0a1a0 | note | Standard / Specification - Downer
98981051-a13f-5dc5-9655-a531c4ee6d02 | note | Verifying Document - Scala Report
c5f90a0e-8e52-5485-866b-e601a5bfea55 | note | Frequency - 10m
40fa4d82-1b01-58bf-927c-840b7256261c | note | Verification Activity: Activity - I
10e78b51-99c9-5c2d-8dbf-c98c393448a5 | note | Verification Activity: By - SE
808aa903-be80-556f-aca4-b05e2f914690 | checkpoint | 12.01.03 - GAP65
a163247f-a2f3-5bae-947e-771512bf8ce1 | note | Acceptance / Conformance Criteria - The imported granular Material shall be GAP65 with the grading envelope given in Table 15-3 and have the following geotechnical parameters after placement and compaction Angle of internal friction = 35° and Cohesion = 0kPa
8062ba42-b12a-5f7f-9d8f-d283016007de | note | Standard / Specification - PS 19.4.5.3
7b1b1215-6208-5895-baa9-c948b4af9a16 | note | Verifying Document - IANZ Test Reprots
79bf1971-b4da-56ab-9164-77192a1b88b8 | note | Frequency - Prior to use
2e634f66-2753-5219-af13-a9eef91e2fee | note | Verification Activity: Activity - R
7f44b236-b2f7-5123-a90e-34c36335f0aa | note | Verification Activity: By - SE
b2d1bb69-5699-5738-92ec-2fe30d4b298e | checkpoint | 12.01.04 - GAP65 Layer Compaction
7642f5c1-0731-58e4-b29a-d63eacb12169 | note | Acceptance / Conformance Criteria - Mean Value ≥ 98 Minimum Value ≥ 95
a6cd85d6-a513-53fb-842d-cb547ad2168f | note | Standard / Specification - PS 19.4.5.4
752fb57c-4ee6-580f-b764-4b00fce433f9 | note | Verifying Document - NDM Report
507bbfcc-2ac9-54aa-937b-2ba7d7f41d07 | note | Frequency - Min 5 Tests per lot 1000m2 max lot size
36bf93bf-b2fb-59d0-b505-30352157d1d6 | note | Verification Activity: Activity - HP
ad0aedeb-39bd-5fb2-aa90-b95b71b79f9d | note | Verification Activity: By - ENG
8889cfbd-f68e-5d41-b749-24d6735f9c51 | signoff | AUTHORITY HOLDPOINT
5d138294-9a5c-5a64-9f56-5a9721a45049 | checkpoint | 12.01.05 - GAP65 Layer thickness.
c6b9c8cf-c98e-5b50-93dd-241e48ed6716 | note | Acceptance / Conformance Criteria - The Sub-basecourse shall be monitored for Layer thickness. The GAP65 layers shall be constructed in accordance with NZTA B/2. The maximum lift thickness shall be 200mm.
58911f8b-36cd-516f-8300-ce16bd3e37bb | note | Standard / Specification - PS 19.4.5.4
07360822-5623-5b43-a620-c66304ea8476 | note | Verifying Document - Survey / Level Checks
45a1e36b-72bc-51a2-96c2-8fe7fb84651f | note | Frequency - 1 test per 20m
bd0fad53-5a29-512b-87aa-92e4757a61ab | note | Verification Activity: Activity - R
ba233f72-6f4e-5724-860b-0e5cef2352d1 | note | Verification Activity: By - SE
20cd3c6a-e8a4-5de2-866a-668c612edb1a | checkpoint | 12.01.06 - Proof Rolling
f8f98e72-b661-5781-95ff-7a656cc3181c | note | Acceptance / Conformance Criteria - The GAP65 layers shall be proof rolled with a minimum 10 Tonne static weight smooth drum roller, or a heavy pneumatic tyred roller (PTR) to identify any soft spots. The criteria for acceptance of the sub-base proof rolling shall be a settlement under the tyre not exceeding 5mm for one pass.
f7d3442c-6173-5708-a0b3-872c17d2a3c2 | note | Standard / Specification - PS 19.4.5.5
eca4538e-0f3e-5fea-8415-02227195b9a9 | note | Verifying Document - Site Records
0783ab1c-abb6-55d3-9edb-aae578fc0711 | note | Frequency - Prior to Concreting
14feb447-d2a9-5592-92e4-325350c3c2a5 | note | Verification Activity: Activity - W
fad05f75-f385-5ba6-919f-b567685450af | note | Verification Activity: By - SE
635f73eb-6089-58cd-8e44-f9b159b2d813 | section | 12.02 Concreting
c2c4f6c2-b7cf-5984-8a7e-3cae9c9ba574 | checkpoint | 12.02.02 - Insitu Concreting Methodology
dde2db87-e8ae-5900-aab6-b230bd96b860 | note | Acceptance / Conformance Criteria - The Contractor shall submit the proposed handling and placing methods, sequence and timing of pours and location on construction joints for the Engineer's consent before concrete placing commences. Where a placing diagram, construction joint location diagram or equivalent is included in the drawings, the requirements thereof shall be followed unless changes are specifically agreed by the Engineer in writing.
90924b7c-a970-5ac7-a755-6dccea2df495 | note | Standard / Specification - PS 19.9.1
4acb80bb-14a0-5923-9ef6-3b242f502bb1 | note | Verifying Document - Methodology
eaf1083b-d726-5add-aec0-eb36e8d61e41 | note | Frequency - Before concrete placing commences
950c61b4-a7ce-53f5-a5f2-e8015c3f88ec | note | Verification Activity: Activity - HP
58f17207-8b34-5f90-9ca9-e8f099036ded | note | Verification Activity: By - ENG
741ebdb7-a413-5fb3-8f48-f9de8fd46de9 | signoff | AUTHORITY HOLDPOINT
4865e8a0-c8b9-5211-99b7-836829d56695 | section | 12.03 Precast Concrete
b38a7d23-b39d-5067-9778-043b52dee3ae | checkpoint | 12.03.01 - Precast Methodology
26de8f15-8d4a-56d0-a5e7-8302a4dfee56 | note | Acceptance / Conformance Criteria - Details of the proposed method of casting, curing, storing, transportation, and erection shall be submitted to the Engineer before commencing manufacture of the mould and precast units.
87a3f730-935b-5ec2-9fd8-3e1772fe6632 | note | ○ The Engineer shall be informed 24 hours prior to the casting of any unit, to allow the Engineer to attend the pre-casting plant to inspect before and during production of the units.
963ba485-0625-5d7e-8b89-2f0e51c2f166 | note | Standard / Specification - PS 19.15.1
2afcf252-4c39-5d99-8cbb-fbb2f09bee03 | note | Verifying Document - Methodology
bd4b7bcb-4f0e-5541-bddb-48df18a42357 | note | Frequency - Before commencing manufacture of the mould and precast units.
721eafbb-fe5d-508b-ad9f-8d9800f7f4ab | note | Verification Activity: Activity - HP
521a6e6d-6c0e-5098-b625-3fff371b5738 | note | Verification Activity: By - ENG
5b00292b-bfe6-5963-a1fb-dd424e542cbe | signoff | AUTHORITY HOLDPOINT
97dc4747-cdf3-5557-aa09-2b6e02835df6 | checkpoint | 12.03.02 - Precast Shop Drawings
7e03ec5c-9086-5bdd-bc91-8017c9262e20 | note | Acceptance / Conformance Criteria - The Contractor shall make available the shop drawings to the Engineer for review, at least 14 days prior to manufacture. Any variations between the Drawings and shop drawings shall be clearly identified and brought to the attention of the Engineer.
5a78e657-6d92-532a-ab35-9d2b6c0b49f2 | note | Standard / Specification - PS 19.15.16
f547b892-be2f-51a3-8572-f54b3cfbb6a2 | note | Verifying Document - Shop Drawings
c2e0c515-9bcf-5192-a461-530af21cea78 | note | Frequency - At least 14 days prior to manufacture
77407f63-4d62-5c7c-ac6b-13cd3649e3c4 | note | Verification Activity: Activity - HP
f616bc72-3f60-55aa-946b-eb1c61c7989f | note | Verification Activity: By - ENG
25202b86-1f51-5c8c-a1bb-dd2accc2a529 | signoff | AUTHORITY HOLDPOINT
aa322b93-5630-5961-8051-afe33a5827e1 | section | 12.04 Installation and Bolt Tightening
9f64880d-ebaa-56a8-9c72-477d0d294c9a | checkpoint | 12.04.01 - Structural steelwork fixed to the concrete surfaces Dry Packing
f17af1e0-0899-5312-a9dd-3ec672361d72 | note | Acceptance / Conformance Criteria - All structural steelwork fixed to the concrete surfaces shall be bedded against the concrete surfaces using a layer of dry pack mortar, plastic bedding mortar or grout with a minimum compressive strength at 28 days of at least the specified compressive strength of the element being bedded against.
0c7c1421-a931-55f5-bd5b-e399b26c2a7b | note | Standard / Specification - PS 19.18.1
a2dbc8a3-8645-5284-a4c5-d9ee32cec077 | note | Verifying Document - Pre Pour
35c36870-2911-51bc-94b2-58382cd3b97c | note | Frequency - All structural steelwork fixed to the concrete surfaces
0f7d9af1-e73a-5483-99b1-50d39fa8334f | note | Verification Activity: Activity - I
90f4dc98-a969-5ee9-afd8-fa2a50c19bec | note | Verification Activity: By - SE
84b03552-8ae3-5bbe-939c-fe5ada6fac05 | checkpoint | 12.04.02 - Bolt, threaded rod, and stud connections
8178c018-006e-5128-80d7-4044bda86a7f | note | Acceptance / Conformance Criteria - All bolt, threaded rod, and stud connections shall be installed in accordance with AS/NZS 5131 Section 8.2. Tightening shall be to the snug tight condition as specified in Section 8.3 of AS/NZS 5131 after the mortar packing or grout has hardened. Where shown on the drawings, lock nuts shall be fitted, and snug tightened against the nut.
cf43cd2c-1631-5288-a7bc-fcaaf42467fc | note | Standard / Specification - PS 19.18.2
826d429c-cc7a-5331-8149-599eafa69a6b | note | Verifying Document - Site Records
75cfcdf4-3fa1-5412-9057-4cdd5e1dcc62 | note | Frequency - Each Bolt
362b08da-5c88-57f0-aecf-3f6a5893b475 | note | Verification Activity: Activity - I
432b78dd-5368-5c7e-8a86-c1b5dddb47eb | note | Verification Activity: By - SE
a87d1c5d-d09e-5e42-843c-b496902d4b3b | section | 12.05 Underpass and Wingwall Backfill
53061aa9-dbfe-5d4e-830b-0868bebf18f7 | checkpoint | 12.05.01 - Polythene Sheet above Underpass
9beff21a-2768-55d0-bdf7-56131f847884 | note | Acceptance / Conformance Criteria - Two layers of polythene sheet shall be placed across the full width and length of all underpass precast concrete units. The polythene sheet shall have a nominal thickness of 0.25mm and comply with the requirements of the New Zealand Building Code.
f0a609ee-c5f1-5c10-8b01-b75410c103e4 | note | ○ Polythene sheet shall be lapped by a minimum of 150mm at all joints.
fb560bd7-1b00-5ea1-8e57-432a9bc20166 | note | Standard / Specification - PS 19.19.1
db15791d-b33e-5081-bcce-6c72543e696e | note | Verifying Document - Site Records
d222be80-0eed-5cc7-a77d-f658b83c7196 | note | Frequency - Each Sheet
9afd286d-10ac-5fe5-b48e-506e991fc472 | note | Verification Activity: Activity - I
fe1f5882-18d1-567a-a5f8-0c689a63411c | note | Verification Activity: By - SE
ba3cb896-2d37-5125-a9a1-b8a2b71b0e6d | checkpoint | 12.05.02 - Minimum cover over Underpass
45a2a8e7-58bb-596c-908a-9049b0a773cd | note | Acceptance / Conformance Criteria - The minimum cover to the underpass within all traffic lanes is to be 600mm to the top of the pavement.
0aab7c17-100e-50fb-ba0a-21a5ef18a50e | note | Standard / Specification - PS 19.19.1
ab98d092-45ba-55b9-b787-85aa7ebb5a16 | note | Verifying Document - Survey Records
a7092e4e-bc86-5202-a9cb-0ccbffef1945 | note | Frequency - During Backfilling
b1c9cbe3-fd5a-53c6-95f4-eb5254315573 | note | Verification Activity: Activity - I
27d8c1c6-a370-53bd-8aee-ec741a222cec | note | Verification Activity: By - SV
c9ec4dff-4ff1-5b1f-8144-e55cc6743033 | checkpoint | 12.05.03 - AP40 Backfill alongside Underpass
d06faf53-16db-5498-a8e5-12b2d9fd32f7 | note | Acceptance / Conformance Criteria - Fill shall be spread in horizontal layers not exceeding 200mm loose depth. Backfill shall be compacted in accordance with TNZ B/2. The maximum lift thickness shall be 200mm. Backfill shall be carried out in unison on both sides of the box underpass such that the level of backfill on one side is not more than 500mm different from the other side, at all times. and testing shall be completed on each lift.
ca3a74b1-7915-505c-8b67-6084f2c0b372 | note | Standard / Specification - PS 19.19.2
4d450d51-07ba-57eb-8b46-6469b070d0b2 | note | Verifying Document - Site Records
2c0ec8a5-6b43-5f48-911c-87b9ba6d2fb7 | note | Frequency - Each lift
c7753ca0-f12a-573b-a278-50a1e4027b67 | note | Verification Activity: Activity - R
85bc4e9c-fb63-57dd-a8ce-4a29e0a5a12b | note | Verification Activity: By - SE
a5e9f1a5-1720-58b5-9041-e517564c2c45 | checkpoint | 12.05.04 - AP40 Backfill Compaction Testing
1a550b5f-2033-5bd4-847f-143cf2588400 | note | Acceptance / Conformance Criteria - Clegg testing shall be carried out and recorded for each lift (200mm Maximum) to be carried out once per 10m length of the 300mm wide AP40 strip. A CIV value of 40 shall be achieved for each test.
d65abb1d-2e5e-5987-a5b7-320e52ea4e9b | note | Standard / Specification - PS 19.19.2
3bf61641-dc70-5df9-9e31-dfdc1bf802ec | note | Verifying Document - Clegg Results
604648eb-9cc6-5504-b348-64a0f65bc136 | note | Frequency - Each lift to be carried out once per 10m length of the 300mm wide AP40 strip
04c7c987-66aa-5b95-8953-9ee1a7cdedbc | note | Verification Activity: Activity - I
65e0ce25-5ea8-50e7-b236-e8790dae2d2d | note | Verification Activity: By - SE
aba2e09b-1e5d-5df7-b8f5-4e2773650758 | checkpoint | 12.05.05 - Polythene sheet at Culvert
5991d9e0-7cd8-5594-b05d-ce26ca3bb89c | note | Acceptance / Conformance Criteria - The polythene sheet between the precast culvert and the structural fill, or site concrete layer. The polyethene sheet shall be a single continuous sheet with no joins. The sheet is to be laid flat with folds or wrinkles prior to the placement of material on top.
19e71153-3232-5a11-86a9-11e61b000a24 | note | Standard / Specification - PS 19.20.2
b8d16b07-f630-5f83-b656-235e1be8d24f | note | Verifying Document - Site Records
b1f51d42-7fdf-58f4-93ef-64cd3a384b8d | note | Frequency - Each Culvert Entrance
41dee811-b245-5135-b129-832df89b5639 | note | Verification Activity: Activity - R
6edb354f-f6c9-5216-9ecf-fbcd6d640e16 | note | Verification Activity: By - SE
b4e7e5fe-c530-558c-b051-926e772ea5ec | section | 12.06 Joint Sealing and Waterproofing
506e7714-f4ea-58a4-abfa-cd064c80c570 | checkpoint | 12.06.01 - Preparation
5d7bbdbc-f755-569a-8f9a-fa254f81719d | note | Acceptance / Conformance Criteria - The joints surfaces should be accurately formed and must be thoroughly dry, clean, and free from frost. Remove all laitance, curing compounds, form release agents, loose material, and any contaminating foreign matter from joint faces by grinding, grit blasting or wire brushing. The prepared sealing slot should be blown out with dry, oil-free compressed air. The sealant may be applied in joints up to a maximum of 30mm wide. All moving joints should be designed to an optimal width to depth ratio of 2:1, with a minimum joint size of 12mm sealant depth.
3bc8b98b-94fd-5061-91f1-b11f188ab7f1 | note | Standard / Specification - PS 19.22.2
885b8885-a7f4-5274-b986-bf500c08bcb8 | note | Verifying Document - Site Records
90de3242-c47e-54ee-a49b-97c14699917f | note | Frequency - Each Joint
2a747138-0b09-5102-8289-e944882a281d | note | Verification Activity: Activity - R
58d8a73d-e89e-54cd-a0c6-5ad087167a50 | note | Verification Activity: By - SE
cba9df5e-1840-510c-b3e6-9ee45b1732d9 | checkpoint | 12.06.02 - Movement joints
f03ebee9-f7cd-5468-8d78-7f1319e1d97f | note | Acceptance / Conformance Criteria - In movement joints, the sealant must not be allowed to bond to the back face of the joint.
514cc399-9405-5d0a-8f7f-20be8d1162ea | note | Standard / Specification - PS 19.22.3
0cca0e20-e009-503e-8ec3-549246a52b20 | note | Verifying Document - Site Records
31579e73-faae-5eaf-a395-ffd888935200 | note | Frequency - Each Joint
d7de1117-97dc-5b70-aaa5-8c3e141e88e7 | note | Verification Activity: Activity - R
41f31158-fa43-5200-8979-82b2d915e749 | note | Verification Activity: By - SE
657d9132-bd5a-562f-b479-70bcd42119b6 | checkpoint | 12.06.03 - Concrete Age
fe53c593-0267-5577-96d4-604c0bea8809 | note | Acceptance / Conformance Criteria - New concrete must be allowed to cure for a minimum of 28 days before sealant installation.
68ab1006-65f1-5dd5-855a-2d0f4d9c652a | note | Standard / Specification - PS 19.22.4
4b83813e-2902-561c-876f-8145b655db3b | note | Verifying Document - Site Records
b14e58e1-91ab-5f0e-83ba-1f903583fbdf | note | Frequency - 28 days post pouring
3d872b7a-2089-5eb3-8628-130ce3c9a3ce | note | Verification Activity: Activity - R
7c65108e-a28e-5ec4-83f6-50b2a7719d4b | note | Verification Activity: By - SE
fa894895-71d0-52ec-b7ef-6e8c9d0da791 | section | 12.07 Supply and Install of Non-slip Coating
a29779db-d9dc-5a4f-a7fc-c2d7bb96fe8a | checkpoint | 12.07.01 - Install of Non-slip Coating
210d8962-d820-5561-8b8b-b10f5611d3d6 | note | Acceptance / Conformance Criteria - The top of the underpass floor slab and bottom chamfers will have Sikafloor 91 or Sikafloor 150 applied after the installation of the box culvert segments. The thickness of this is to be between 3 and 5mm. The application of the product must be done in accordance with the manufacturer’s specifications.
361ee72d-6b14-58e7-a214-8302400f0f22 | note | Standard / Specification - PS 19.23.2
6dc65402-eaef-5574-a37f-caeebdaba588 | note | Verifying Document - Site Records
8e004a1b-45ce-5859-ba43-e1bb3110465c | note | Frequency - Each Underpass
fc45356d-a80a-5427-be4e-c4ae7e569c3f | note | Verification Activity: Activity - I
162c219f-eb33-504b-8b25-a7090b63752e | note | Verification Activity: By - SE
d3adefc2-67da-5698-9ca4-d2400ca3e896 | section | 12.08 Anti-Graffiti Finish
77be84ea-a9a2-57a2-970e-999b184ae026 | checkpoint | 12.08.01 - Anti-Graffiti Application
0c19da87-d2b5-5f99-a8ce-2175df192f51 | note | Acceptance / Conformance Criteria - The anti-graffiti coatings shall be applied and maintained in accordance with the manufacturer's requirements.
b2413297-e63a-58e5-b09a-ea373ac23381 | note | Standard / Specification - PS 19.24.3
b5753973-8bf5-5edf-be6a-0516caf866fb | note | Verifying Document - Site Records
d5184914-b959-51a0-84fc-9b4815cef828 | note | Frequency - Each Application
8f972ae3-62ff-5495-bbfe-f879d6b7e665 | note | Verification Activity: Activity - R
740241d6-aa63-5f6d-88df-ea85b4e18d84 | note | Verification Activity: By - SE
efacb135-16e5-55ca-a64a-5494421f2fce | section | 12.09 Steelwork Fabrication and Installation
72a3fc25-ec20-5289-8196-77d5b59e0577 | checkpoint | 12.09.01 - Welding
16751529-328b-54a6-a050-64f14cda672f | note | Acceptance / Conformance Criteria - Welding shall comply with AS/NZS 5131, Section 7.
3d59caa6-5f37-537a-9c1c-5c1184d292ca | note | Standard / Specification - PS 19.26.8
451ad658-6d7e-5e3b-a655-3f850bfac03a | note | Verifying Document - Site Records
4fc643ed-359b-5ef3-a1c5-321b6b850e42 | note | Frequency - Each Weld
9a4348ac-e5fd-5ad4-a583-969f679f5332 | note | Verification Activity: Activity - S
8833962e-21e5-52fd-9b93-cfdeba2f10ee | note | Verification Activity: By - SE
88697b26-9511-5008-b735-86c64b81f050 | checkpoint | 12.09.02 - Holing
4c79acc3-999f-5b79-aa6a-0249f6ee2d8e | note | Acceptance / Conformance Criteria - Holing shall comply with AS/NZS 5131, Section 6.7.
604cfa92-affc-5d27-8a65-0f9c81726051 | note | Standard / Specification - PS 19.26.9
731de60c-7468-5728-b64e-d2ae6b0e4b39 | note | Verifying Document - Site Records
8c6638bd-8e92-5248-925d-092ab764605b | note | Frequency - Each Hole
d88c7e97-baa1-535e-9205-0a1dd78cb79d | note | Verification Activity: Activity - S
81bfd94e-d1ea-55cf-850c-93fbb087d234 | note | Verification Activity: By - SE
005199f0-55dc-51b6-a050-65a89216e346 | checkpoint | 12.09.03 - Installation
3146d7d0-b9f8-5d10-b1f0-f10e2dfb0ff9 | note | Acceptance / Conformance Criteria - Holing shall comply with AS/NZS 5131
19ba649c-58c8-5a4d-b76d-78905c4a7191 | note | Standard / Specification - PS 19.26
8a09410a-7da4-5032-b8a6-32073c4c0632 | note | Verifying Document - Site Records
f6c31072-e530-536d-ade7-e52348df97d3 | note | Frequency - Each Item
5eb9ade7-9c32-5437-9ebc-a60715d907f2 | note | Verification Activity: Activity - S
22d6da77-5bc8-5137-94e4-73ca7cfebd4f | note | Verification Activity: By - SE
32f26889-aec1-582e-aec7-39adc34c3a13 | section | 12.10 uPVC Pipe
71941ead-6a23-5072-b6db-602aa1b01232 | checkpoint | 12.10.01 - Plastic Pipe Trench Backfill
5a033622-6c1b-59bf-8b09-27f63198ba35 | note | Acceptance / Conformance Criteria - Plastic Pipe Trench Backfill
77342c8d-718c-5a89-8ee2-b1e5e36bae9b | note | Standard / Specification - Except as shown otherwise on the drawings, or directed otherwise by the Engineer, support material shall be as per AS/NZS 2566.2.2002 “Buried flexible pipelines – installation” corresponding to the relevant pipe support type as detailed. All materials in bedding zones, side zones and haunching zones shall comply with the grading specification in the aforementioned AS/NZS 2566.2.2002.
f3a14fc9-6072-556b-bad8-b1e31808be4c | note | Verifying Document - PS 19.27.4
def1b3c1-b197-451e-948c-c383c50cb518 | section | 12.11 Underpass Capping
a76d1cc6-83a2-4ca1-90ee-0e7f3c97d5b7 | checkpoint | 12.11.02 - Pit Sand/Geotextile
6c49cb33-a64b-522b-9c81-820ba4a0b4b1 | note | Acceptance / Conformance Criteria - 100mm min thickness Course (Pit) sand over the culvert and for 2.5m either side.
36e5294b-599c-5883-918a-fb2d99d596a6 | note | ○ The pit sand layer shall be wrapped in geotextile on all sides.
5c6b795f-d0ef-5f8a-b0d5-90feaa40691c | note | ○ Pit sand to be compacted with lightweight plant (and water) and proof rolled for acceptance
f3af56f2-472c-592a-a97d-c62f10249a93 | note | Standard / Specification - RFI-DN1208-DOW-GCO-0149
fa0cb9cd-40f3-53cc-b402-cdd00c2589d6 | note | Verifying Document - Site Records/Data Sheet
9b650d7f-c23f-574b-8695-f34b9036e604 | note | Frequency - Each Underpass
31bc6f02-1deb-5221-8780-ebf63a3a3707 | note | Verification Activity: Activity - R
a0d6b920-cf74-5e37-9590-cc39055a1ba4 | note | Verification Activity: By - PE
cc06c015-7d03-4179-9a5f-3c48c0d21fcd | checkpoint | 12.11.03 - Geogrid (Duragrid X 30/30)
516a0726-de35-5383-9094-736cb54646a6 | note | Acceptance / Conformance Criteria - Geogrid to be placed above the pit sand for 10m above the last bench either side of the underpass
8ec6257a-320a-5d4e-a7aa-d710e3149355 | note | Standard / Specification - RFI-DN1208-DOW-GCO-0149
c0f436e9-ad31-5f84-9ede-f9910a6c13e7 | note | Verifying Document - Site Records
82970b33-cd1c-5444-9750-2330d9260bb8 | note | Frequency - Each Underpass
aab34f5b-8f0c-58d3-81f0-eaece05e474e | note | Verification Activity: Activity - R
d3f23f5b-f6ea-5ea3-b706-f8c00ff704b8 | note | Verification Activity: By - PE
fd213606-5a0d-4cde-b134-62ac3808785f | checkpoint | 12.11.04 - AP40
5c8100a7-90d6-57e5-b781-82021faefb1a | note | Acceptance / Conformance Criteria - Variable depth of AP40. Compacted in 100mm max. layer thickness. NDM testing to be conducted and to achieve MIN of 91 and AVE 95% of MDD
70be349d-a571-55d7-af2e-28bcfe87dfa4 | note | Standard / Specification - RFI-DN1208-DOW-GCO-0150
44719f8f-3755-509a-a068-e8db27b3a75c | note | Verifying Document - NDM Field Sheets
e820e851-ff37-507f-915a-2ff482f67f73 | note | Frequency - Each Underpass
13374df3-703c-5d95-9c09-677ef8304177 | note | Verification Activity: Activity - R
33b460dd-7aec-53cc-a2f6-1014e4ddf7d5 | note | Verification Activity: By - PE
bb36718c-2827-4628-9fe6-cd9d58ef4f71 | checkpoint | 12.11.05 - 10Mpa Concrete
af4bedca-2acf-5323-bb42-d84f8f214e95 | note | Acceptance / Conformance Criteria - Replace Hilab 65 layer with 10MPa Concrete for 2.5m either side of underpass.
34c99ca8-3477-5327-b92e-989c87201129 | note | Standard / Specification - RFI-DN1208-DOW-GCO-0151
7f81494f-d0e0-54a9-ac80-fbea635da1c3 | note | Verifying Document - Site Records/Data Sheet
30fe87ee-7449-53ce-b3c5-800623a1a130 | note | Frequency - Each Underpass
6beea035-14e9-544e-99ed-79d5a3c2d91a | note | Verification Activity: Activity - R
93bd0311-0fc0-5a62-a98d-4243f2f243b2 | note | Verification Activity: By - PE
160370a1-637f-412d-afa3-18366975e670 | checkpoint | 12.11.06 - Hatelite Asphalt Reinforcement
7e5bab8d-70fa-5ac6-b9b1-98bfc4cb872e | note | Acceptance / Conformance Criteria - Hatelite to be installed on top of first layer of AC20 above underpass for 12.5m either side.
7740a713-c10b-5232-8b15-042fe53b41ab | note | Standard / Specification - RFI-DN1208-DOW-GCO-0151
08b2e33f-b0a2-573f-8abb-1573151e011d | note | Verifying Document - Site Records
5dbd11d4-32d7-55ec-be6b-def14f738c2a | note | Frequency - Each Underpass
b312830c-0ae3-5d95-9df5-a53ec5a50dd9 | note | Verification Activity: Activity - R
30068859-95ce-5689-a51d-367c2b6bd026 | note | Verification Activity: By - PE