## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
aa9a099a-2401-545c-b2fb-4fa79037ea1c | checklist | ITP - Earthworks - 101 - Rev 2 | itp | ITP - Earthworks - 101 - Rev 2
ac5ee1ee-5139-57b0-9c55-3196b7da263c | section | 3.01 General
4b182364-c9b8-5807-85b4-26cb6c506fc7 | checkpoint | 3.01.01 - Precondition Surveys
69cd2420-d366-54eb-958b-47ee6ba30c3b | note | Acceptance / Conformance Criteria - A precondition survey of Waka Kotahi and other public / private assets within the extent of the Site and immediately beyond the outside area of the construction activities shall be undertaken in conjunction with the Engineer prior to the Contractor taking possession of the Site.
8a300e3e-8b0d-50e1-92a8-acacc9470272 | note | Standard / Specification - PS 2.13
4012ae1e-5742-5bb3-bd88-9891dd0da569 | note | Verifying Document - Precondition Survey
5ee54bf7-4881-50be-9cbd-b6ca24fbed29 | note | Frequency - Prior to the Contractor taking possession of the Site.
4ee5ad50-8a49-5ef9-b2ce-6829404da63e | note | Verification Activity: Activity - H
042a86d8-9388-5bf2-bc39-fae98a19ea53 | note | Verification Activity: By - PM
2c4b8fd4-5150-5656-bda8-48bbc0f299cc | section | 4.01 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
eec51e33-e195-5fd4-8848-2a84896576bc | checkpoint | 4.01.01 - Source Property Tests and Sampling
c970b435-1a5a-5b52-9c63-6d3dc47a7b24 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Crushing Resistance, Weathering Quality Index, Los Angeles Abrasion, and Soaked CBR at least 2 weeks prior to importing to the site.
5fddf01b-636b-5c1b-9e0f-f9d479c784a9 | note | Standard / Specification - PS 15.7.3 Appendix XIII
c05f86e5-078b-56d0-a84d-743d12ed7c80 | note | Verifying Document - IANZ Lab Reports
0d61936a-619a-5486-b002-fd3bb8ecd191 | note | Frequency - 2 Test Per Material Per Source at least 2 weeks prior to importing to the site.
6c36e154-7375-5049-8d17-38c7ea3fb8aa | note | Verification Activity: Activity - HP
3ce79e68-2cd7-57fc-8b23-187278275664 | note | Verification Activity: By - ENG
943c57a3-9718-5eec-a0c4-4f254ca57b92 | signoff | AUTHORITY HOLDPOINT
e74ba8eb-c7ac-51ca-806d-ce6b2d151d6f | checkpoint | 4.01.02 - Testing for Layer Compaction - MDD
0eea5d39-c7a9-597e-95e8-2d3aa0eb79ce | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Heavy Compaction), Optimum Water Content, Air Voids, and Shear Vane Strength (Su) with Range of Moisture Contents.
3a7cfff1-f254-5419-911c-e86cf81791ad | note | Standard / Specification - PS 15.7.3 Appendix XIII PS 15.13
bac60110-709f-58ca-825f-eef1d568b6fe | note | Verifying Document - IANZ Lab Reports
28d0819b-7509-50e5-aaad-6484fe8c56af | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
93ed1431-f321-5f8b-8125-d991cf43a90b | note | Verification Activity: Activity - HP
5eecf011-989a-5420-a82b-eb0149a57904 | note | Verification Activity: By - ENG
1ad45696-b06f-57ba-991f-876ec2469f8a | signoff | AUTHORITY HOLDPOINT
cc28f368-5ec3-56d4-92e5-eeccc9eacb38 | checkpoint | 4.01.03 - Production Property Test Sampling
6c461bdf-e882-525f-a094-2bcc190ce2e7 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD).
4c2ef108-068a-59d0-b3de-60b2a95c6c7f | note | Standard / Specification - PS 15.7.3 Appendix XIII
6a814afb-0be7-53e5-8592-2862e1a765fd | note | Verifying Document - IANZ Lab Reports
efce84d9-b1b2-5d89-991c-9da04e5ba923 | note | Frequency - 0-400 M3 – 2 Tests
f89666dd-0f56-5b39-b7d2-2694b08c1b13 | note | ○ 400-1,500M3 – 3 Tests
ed92ad50-6f20-5df3-bdee-ddfd8f5eb73d | note | ○ 1,500-4,000M3 – 4 Tests
8473fabf-bde7-5cc9-8e93-e31e0d9d300b | note | ○ >4,000M3 - 1 Test For Each Additional 10,000M3
fd98181f-7bd9-5f53-8201-bb0c6813a688 | note | Verification Activity: Activity - H
29935793-de84-5fc9-9e9a-dc726b88856e | note | Verification Activity: By - PE
d3197014-3f06-5fe0-b1d9-aea439b97c54 | section | 4.04 Type A3 (Site Won Landscaping Fill)
bd572b98-794b-572a-b262-0d8895c651db | checkpoint | 4.04.01 - On Site track-able Testing
8fefcbaf-cb68-5917-9433-3d41137b8e4e | note | Acceptance / Conformance Criteria - Fine grained Type A3 site won materials may be considered suitable for use as landscape fill providing that it is ‘track-able’ by the contractor’s plant. This shall be determined before Sampling.
b4914206-8d0b-5414-9502-17ae4fad6e1c | note | Standard / Specification - PS 15.7.3
e51abaca-32b0-57d1-8544-f906b25a9fc0 | note | Verifying Document - Visual Site Record
aaf6e6a1-d9e9-5a27-86da-31e404a8a62d | note | Frequency - Prior to Sampling
d4f5a2c3-8d72-5a12-84a0-52e374ec9d02 | note | Verification Activity: Activity - W
21e39c46-937e-5756-bf3a-0fa20897c108 | note | Verification Activity: By - PE
bbfc5154-bf5f-5edf-b862-ca5b40d3d743 | checkpoint | 4.04.02 - Testing for Layer Compaction - MDD
da4431ef-f91b-5faf-a07f-ebe5b3ed0ce8 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Maximum Dry Density (Standard Compaction), Optimum Water Content, and Shear Vane Strength (Su) with Range of Moisture Contents.
75366e9f-f170-5da4-8e90-2ba29431f456 | note | Standard / Specification - PS 15.7.3, PS 15.13
01c254a6-d804-5850-b1b7-daee29774ece | note | Verifying Document - IANZ Lab Reports
cd00113d-ee85-5286-956b-580960ae86ae | note | Frequency - 1 Set (3 Tests) Per Material Type And Source Then 1 Test Per 5000M3 For That Material Type And Source
9895d0dc-5a1e-556b-b3a4-f60bb935b694 | note | Verification Activity: Activity - HP
803e0adb-6908-539d-91c5-5f291f829291 | note | Verification Activity: By - ENG
787da1d7-76e7-5318-90fc-d7c5b66f0772 | signoff | AUTHORITY HOLDPOINT
1b403918-b691-5bde-88b7-f3ee9e087117 | checkpoint | 4.04.03 - Insitu Property Test Sampling
b2e3a0b7-200b-54bc-8753-e33bdade2178 | note | Acceptance / Conformance Criteria - The Fill shall be sampled and tested by an IANZ Accredited laboratory for Particle Size Distribution/Grading (PSD) and inspected for deleterious materials such as boulder size fragments and organic materials.
da342694-bd84-565c-b303-933f704abeb3 | note | Standard / Specification - PS 15.7.3
3f8b0f56-e239-5878-82f3-25bd301b0188 | note | Verifying Document - IANZ Lab Reports
54187772-fb0a-5304-b22d-e6fef5571033 | note | Frequency - Prior to use
5f2c876f-b40e-5944-91db-1b5c4f101bfd | note | Verification Activity: Activity - HP
10ebcf48-ad4b-5c4f-ac90-4d24da87969d | note | Verification Activity: By - ENG
f4da45cc-ae32-586a-82a0-8191c8cf5c37 | signoff | AUTHORITY HOLDPOINT
540a5e70-44a2-557d-9a5c-b23f9eba4a3f | section | 4.05 Topsoil
20c79c91-2f0b-5e64-bc79-4fc755ec0ddc | checkpoint | 4.05.01 - Topsoil
c48a7814-415e-5bf0-90db-a1b8443b9fdd | note | Acceptance / Conformance Criteria - Topsoil is defined as the layer of material immediately below the ground surface comprising vegetation, tree roots, other non-decomposed organic matter, turf and humus. The Contractor is to stockpile and utilise site won topsoil for placement on the final batter slopes and for borrow site reinstatement as shown in the Contract Drawings.
e65a11a1-9f5f-5b9b-b31a-005bf9a0f5ad | note | Standard / Specification - PS 15.7.3
cf04a554-dfc6-58b4-9613-62ac16fdabb9 | note | Verifying Document - Site Record
ee11df60-1ce5-585b-8998-69594136d238 | note | Frequency - During Stripping
e137dc49-6b12-5bed-ab75-30d89abce352 | note | Verification Activity: Activity - I
11dd70c8-b8f1-5205-a62a-89a0d37a59b0 | note | Verification Activity: By - SE
d75e34e2-526e-508b-9139-1c41f905aee4 | section | 4.06 Geotextiles
94c5cd81-4c09-5866-a780-a6cb2b294715 | checkpoint | 4.06.01 - Geotextile on Undercut to Waste and Backfill
01a812e1-2a2b-5d7f-a9f9-4d80c94b831d | note | Acceptance / Conformance Criteria - The Contractor shall submit the full details of the filter fabric they propose to use to the Engineer for approval prior to installation.
c17089c8-cde6-5780-af0b-4d44cfe037e4 | note | Standard / Specification - PS 15.10.9
3752352a-df5a-53b2-8094-118f73546c7d | note | Verifying Document - Datasheet
8e7145b3-d717-57d4-8b68-f84837bcbada | note | Frequency - Prior to use
6f3350cc-a5e3-5922-90ec-ceba1cff1e25 | note | Verification Activity: Activity - R
ffc1a14f-5946-57d0-b15d-4eb1e2f5b1a3 | note | Verification Activity: By - SE
00122e61-34f7-53d5-a67f-e0c09f6146f3 | section | 5.01 Site Clearance
aa56f8f4-2f1d-53a7-90e0-bf9bff008cd2 | checkpoint | 5.01.01 - Site Clearance
76735cd9-4858-55a6-aa06-101f02518612 | note | Acceptance / Conformance Criteria - All trees, scrub, non-lawn vegetation and/or self-sown plants within the extent of the earthworks shall be removed to waste in accordance with Clause 3 and Clause 9.4 of TNZ F/1:1997 Specification for Earthworks Construction.
e2b43d2f-4215-5670-89ab-c3b1d39d5dd5 | note | Standard / Specification - PS 14.1.1 NZTA F/1 - 3
f35896e9-18bd-51fb-84bd-a516fea07908 | note | Verifying Document - Site Record
1c9aecd5-6527-5a3f-90f9-fb46fb1152c3 | note | Frequency - Prior to excavation
553d21dc-d656-5d11-a678-49e9091a7776 | note | Verification Activity: Activity - I
b8ac2dc9-f39d-5a4c-88d0-92ffc13d346b | note | Verification Activity: By - SE
0434188f-64e5-5961-b752-f68ed0678033 | checkpoint | 5.01.02 - Dump Site Approval
165908c4-435f-5b36-8fd9-df3fab4ecdd9 | note | Acceptance / Conformance Criteria - The locations of dump areas shall be agreed by the Engineer before use.
e22c6756-65e9-50b5-b8f9-e78161c44d04 | note | Standard / Specification - NZTA F/1 - 9.4
55d5c387-b48b-5e7f-9757-2749a36ece54 | note | Verifying Document - Site Record
f84ff3ba-d111-577e-814d-2f3b3ff0c62e | note | Frequency - Prior to Stockpiling
73737f8f-3ed5-5230-a5fa-7d12fd1ac08c | note | Verification Activity: Activity - HP
74ce0d35-f379-5262-b7f4-46543d42148d | note | Verification Activity: By - ENG
c082bbf0-64bb-5295-803d-efd5e36c07d2 | signoff | AUTHORITY HOLDPOINT
97e973d9-e87b-5abc-b883-a17a57730683 | checkpoint | 5.01.03 - Mulching
7c25105e-22ed-5c83-8240-5f58fa89da29 | note | Acceptance / Conformance Criteria - Where possible, cleared vegetation shall be mulched and stockpiled at a suitable site for future landscaping work.
39aa4f4e-e9d4-5b72-a53a-4a01c43363d6 | note | Standard / Specification - PS 14.1.1
54411dec-bc57-5533-afb7-0f38308d0bf6 | note | Verifying Document - Site Record
d3575c48-3185-5f98-b1fe-4784265e23ac | note | Frequency - During Clearing
449c8392-36d0-5a80-8ce1-30049ce1eaa6 | note | Verification Activity: Activity - R
07fddfa0-d1c0-5767-bf10-aa4ad5673f63 | note | Verification Activity: By - SE
4f7cfdbd-f8a4-5f17-a5dd-b36d0cb99ded | section | 6.01 General Earthworks
7b7266d6-ecf8-561a-b4ca-7b37880265fd | checkpoint | 6.01.01 - Earthworks Methodology
c228e36c-639a-5d64-84a6-17b814e6f41b | note | Acceptance / Conformance Criteria - The Contractor shall submit the construction and QA methodology for each element of Earthworks including construction, Haul roads, Site Access, dewatering, Wet weather, testing, inspection, and hold points for review and approval prior to works.
0b682de4-c8ae-51d1-9923-ecbfc85690dd | note | Standard / Specification - PS 15.13, PS 15.6.2, PS 15.10.13
b50a3242-4781-56d2-9c29-2bfa07bedacd | note | Verifying Document - Approved Methodology
9b77a527-c1c2-52d4-bf08-2baf8fe48a93 | note | Frequency - Prior to Earthworks
00c15935-b738-5367-8878-db856c582b87 | note | Verification Activity: Activity - HP
2e554e60-d952-5dd6-861b-a558370ee856 | note | Verification Activity: By - ENG
326a5f19-66e6-52e8-8259-accb86134d3f | signoff | AUTHORITY HOLDPOINT
ce70eb24-ffd6-534e-9bc3-84ccc496c6db | checkpoint | 6.01.02 - Temporary Excavation Approval
8b4c1814-1483-57a0-a93e-7cf0f5129205 | note | Acceptance / Conformance Criteria - The Contractor shall submit Temporary Excavations details to the engineer for approval prior to excavation.
33ca796d-57e5-58de-b34f-c32e6163735c | note | Standard / Specification - PS 15.13
c6d3b217-5879-5d04-b9ab-a032084546f6 | note | Verifying Document - Engineers Approval
de2c1bd3-ac7a-562d-817a-3f4a0bb05767 | note | Frequency - Prior to Excavation.
cd18a545-923b-5871-b92c-dee9402f4e29 | note | Verification Activity: Activity - HP
b2515f22-7df2-58c2-ac65-fe920a60c040 | note | Verification Activity: By - ENG
7f24d1ae-eaea-5164-a39d-b9602a701e03 | signoff | AUTHORITY HOLDPOINT
7be180f9-b731-51bf-aa2a-2646cc8a1c69 | checkpoint | 6.01.03 - Temporary Works Design
6bf13ae3-7a65-50e5-8ee5-356f37e5f99f | note | Acceptance / Conformance Criteria - The Contractor shall submit the temporary works design for Review and approval of prior to excavation.
34321cd1-593b-53a3-963f-41929191a96b | note | Standard / Specification - PS 15.13
725dbc6f-43b7-58dd-b840-2a9e1cc7a0a5 | note | Verifying Document - Approved Design
e4fec50b-b4eb-5cfa-bc23-b5a1182bdb5c | note | Frequency - Prior to Excavation.
2ac192cb-bf2e-52c2-b62a-50c4c4697492 | note | Verification Activity: Activity - HP
e421222d-e59e-5ba2-9fce-d91b87b2c1cd | note | Verification Activity: By - ENG
bd223daf-c7ae-5c7b-b6da-6f123e740f86 | signoff | AUTHORITY HOLDPOINT
55e3284f-9a58-588c-bbef-d9a461605980 | checkpoint | 6.01.04 - Temporary Stockpiles
baf815d3-1ef3-59b4-94ad-daf49ffc72eb | note | Acceptance / Conformance Criteria - Temporary stockpiles shall not be located within the footprint of the permanent works unless approved by the Engineer.
18b30793-18bf-5c62-9ab2-12c0e2ba5c49 | note | Standard / Specification - PS 15.6.5
cc98758a-ecad-5043-bcc8-3a0f6433d90f | note | Verifying Document - Engineers Approval
58eb1e17-79a1-52e1-b4e4-ff51e4c2a10c | note | Frequency - Prior to stockpiling
08cfbbd5-6e1b-5ca2-872e-ed4df362935a | note | Verification Activity: Activity - HP
8f11b887-eb69-534b-b326-59012efc3a5c | note | Verification Activity: By - ENG
a94c983f-b77c-5257-ba7c-2cf26f751c21 | signoff | AUTHORITY HOLDPOINT
9f916a51-531e-50f9-ab39-015b1c560d11 | checkpoint | 6.01.05 - Surplus Material
02f14ce9-3ef4-562b-b104-58d1241b50c7 | note | Acceptance / Conformance Criteria - Surplus or waste soils may be deposited outside the site boundaries with the written approval of the Engineer.
c85b74b4-9183-55a7-ae2f-345297038e49 | note | Standard / Specification - PS 15.1
ef2e0cf0-e7d5-51ba-8a6d-bbc82bdf9e2f | note | Verifying Document - Engineers Approval
a960256b-958b-5eb6-af8e-bc4d99728fb0 | note | Frequency - Each Occurrence
52fea67b-14ca-5826-8d8a-c11dc3466cf4 | note | Verification Activity: Activity - HP
4b1848f4-9510-5def-95f4-d24b7a6c808e | note | Verification Activity: By - ENG
291238e6-3d02-5ec2-b9a8-ab81fb7023ca | signoff | AUTHORITY HOLDPOINT
918a1145-c5ce-509f-bed1-f62ab59e0117 | checkpoint | 6.01.06 - As-Builts
db708295-8b31-57be-bec5-77dab4401720 | note | Acceptance / Conformance Criteria - As-Built records and drawings shall accurately record the layout and extents of all the work including all of the cuts and fills, monitoring instrumentation, ground improvements, and locations of foundation / subsurface drainage systems and their outlets.
a24bef18-ed19-5402-9911-8d0aa41611d7 | note | Standard / Specification - PS 15.11.7
44a3c1ca-2b3c-5bd8-bcd9-8166bc6a932f | note | Verifying Document - Survey Records
b240b2d4-ab96-5982-84a2-2fd25825db00 | note | Frequency - During Earthworks
f0563e63-58d2-5281-99f2-223329a109a7 | note | Verification Activity: Activity - D
0379ef52-f0a4-5de8-b838-16ad532332f7 | note | Verification Activity: By - SV
44d1c624-06c3-5e22-b6df-9c6af47c6102 | section | 6.02 Cutting and Subgrade
e2056d42-43d7-5262-8e7d-f3a1023524d6 | checkpoint | 6.02.01 - Cut slope inspections
f0c9e4d3-35fc-5484-b867-873378bcdcc6 | note | Acceptance / Conformance Criteria - Cut slope inspections will be required to allow inspection of the soils exposed and check for seepages. Inspection records are to include photographs, logged soils (to NZ Geotechnical Guidelines) and hand shear vane testing on fine grained soils. Results will be submitted to the Engineer.
a5050965-657c-5cb4-ba54-29f7a81a36c0 | note | Standard / Specification - PS 15.10.2, PS 15.13
0ca6644d-27bc-50cb-82c3-e9215beabdf8 | note | Verifying Document - Engineers Approval
ee095220-c54a-544f-8c85-d2e244c4a0fd | note | Frequency - Each Occurrence
6854b9e5-08d8-53bf-b4c4-25cc08b491a4 | note | Verification Activity: Activity - HP
3b8c7bd6-7173-5f1c-9873-a15adf5e3876 | note | Verification Activity: By - ENG
e91cf135-5c98-52a7-a54a-3c6af3be7601 | signoff | AUTHORITY HOLDPOINT
d2fbe478-ad1f-5048-8657-8f4e357aec4a | checkpoint | 6.02.02 - Dewatering
45ad7851-3863-514c-bd5d-d0013775f8f7 | note | Acceptance / Conformance Criteria - Trenches and excavations shall be dry at all times during construction works and a constant water level is to be maintained at 300mm below the base of the trench. No construction works may occur if there is any water in an excavation.
10bf3c53-35d3-54c6-aa6d-417ba63dc5da | note | Standard / Specification - PS 15.10.18
fbd2f8c6-64ab-5c47-af05-cb3418296a2c | note | Verifying Document - Site Records
bc3137ea-86db-5fc7-b231-fea3db637513 | note | Frequency - Ongoing
f642d9fb-44aa-5900-a964-19c664e82209 | note | Verification Activity: Activity - S
83904629-984d-510e-b1a8-050717dedc6a | note | Verification Activity: By - SE
0478f66f-1630-5596-ad8d-f38a4cc2b1c9 | checkpoint | 6.02.03 - Subgrade CBR Testing (Road and Embankment)
f3d10b4e-addd-5538-a957-2a37e0034faf | note | Acceptance / Conformance Criteria - The subgrade shall be tested for CBR via Shear Vane or Scala depending on site conditions. Testing to be undertaken to maximum 3m depth at 0.5m interval with hand auger holes required for test deeper than 900mm.
2ce0f2e8-1f40-5e35-8e0b-a78fd0b55a7b | note | This test shall be undertaken at the design subgrade level and at a depth of 300mm below the design subgrade level. Scala penetrometer testing to be undertaken instead of shear vane tests where shear vane is unable to penetrate subgrade material.
8b65a2ae-cac6-521a-a731-1c5b9ef6ea23 | note | ○ Shear Vane Average minimum su: > 60kpa
4ccae70e-9d5a-53e4-8f6b-a4e00f80f67e | note | ○ Shear Vane Single test minimum su: > 50kpa
3ff01897-8d7b-537a-9e0a-bdedcefe185a | note | ○ SCALA: Minimum 3 blows per 100mm penetration
630d469c-d4b6-528c-8e3d-4302c9510b53 | note | Standard / Specification - PS 15.10.4, PS 15.10.5 Appendix XIII
0c3bb1ce-aaf0-5272-9b8f-4d902e6bbc45 | note | Verifying Document - Shear Vane or Scala Report
85d3bae8-7bf8-56b3-9602-213fb78a5576 | note | Frequency - 4 test per 400M2
55a69f30-35b2-5c05-9282-92604524f101 | note | Verification Activity: Activity - I
8a1bfe00-8ce7-590a-a5cb-d9ae236fa6a6 | note | Verification Activity: By - SE
55b576e1-21ed-531a-aacd-d94250dc6129 | checkpoint | 6.02.04 - Undercut Subgrade Compaction
f841e758-4cd2-5891-b08c-751a3c88b535 | note | Acceptance / Conformance Criteria - The degree of compaction of each layer shall be such that when trimmed to a smooth surface, the resultant impression in the surface under a smooth wheel roller having a minimum loading of 6259kg per metre width of fill or equivalent as agreed by the Engineer, shall not be greater than 7 mm for bulk fill or 5mm for subgrade fill.
8fb02c88-5c79-5b58-a1dd-92a07552b833 | note | Standard / Specification - PS 15.10.4
a629293c-385f-5bce-b059-933f4c7d43dd | note | Verifying Document - Site Records
2a96cae7-3c6a-51cb-9454-6091224f2d6f | note | Frequency - Prior to Backfilling
4ff321f5-d0cb-5131-9bac-f2447b9cd5d8 | note | Verification Activity: Activity - S
9afabe93-cf7b-5ea2-9907-09925e3a24f2 | note | Verification Activity: By - SE
9bb70f82-94b7-566d-9ef1-4b61c37556a1 | checkpoint | 6.02.05 - Soft Road Subgrade Areas
6fd65fab-6193-5462-afeb-d69af1a8db96 | note | Acceptance / Conformance Criteria - Any soft area observed during rolling of the subgrade shall be referred to the Engineer.
d76e99d9-c656-55e3-acb1-1c1df46f6945 | note | Standard / Specification - PS 15.10.4
1be23212-e8df-5d9f-8313-9a5254ebe069 | note | Verifying Document - Notice
1c0d6418-f406-5f50-950c-5444425f50bf | note | Frequency - When Encountered
34656019-18b2-5fea-94d4-d598e2a8138a | note | Verification Activity: Activity - S
c035f040-40a1-576d-b193-c59e6a453dad | note | Verification Activity: By - SE
c3b7c71e-cfaa-5a96-a625-454bb0cc64fa | checkpoint | 6.02.07 - Finished Surfaces
9bec837e-b683-55ad-bd75-4a248c626262 | note | Acceptance / Conformance Criteria - The works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for Subgrade is 0 to -30mm before placing aggregate layers.
a6991efb-ab9a-5b99-bf23-cb2f8b77c50b | note | Standard / Specification - PS 15.6.8
be65fa83-a107-5342-9c6d-a54c8b435c69 | note | Verifying Document - Survey Records
887ad7d3-09f0-5edf-a3ba-45e2f89d1d67 | note | Frequency - Each Finished Surface
157d7177-0edf-5110-9131-f02c3d9f1433 | note | Verification Activity: Activity - D
1fe43a96-441d-52f3-9c61-b1ddff480ba2 | note | Verification Activity: By - SV
9149e6ff-1de8-5094-9b9f-ead6fee4ce61 | checkpoint | 6.02.08 - Subgrade Proof Roll and Foundation Inspection (Road and Embankment)
b64008e4-8e18-5171-b4ca-a72a0d91c282 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect the Foundation surface prior to Filling during the Proof Roll. No filling shall be undertaken until an inspection has been made and the Engineer has approved the cut and stripping of unsuitable materials. Visual Observation Across The Stripped Area Displacement < 15mm.
677d8b3a-9fe5-5e7f-9e11-0862609e0580 | note | Standard / Specification - Appendix XIII PS 15.13, PS 15.10.5
9841c2a6-be7e-500d-bcca-506f57b64c31 | note | Verifying Document - Engineers Approval
4e231911-13ab-5ecd-9b53-75b332d5bfb0 | note | Frequency - Prior to filling with 24h notice
c10bf413-07c4-5174-9e14-7c2fbcd9358d | note | Verification Activity: Activity - HP
950b4e24-66ad-5e1f-946a-4eebbe8609ed | note | Verification Activity: By - ENG
f05195d4-07ae-5bad-820d-5d958fa1f023 | signoff | AUTHORITY HOLDPOINT
cbfd5119-9511-5f05-a1a3-eb568e57c7a2 | section | 6.03 Filling General
6da130e7-ec1a-5eb6-b735-c0a7919ee1b0 | checkpoint | 6.03.01 - Compaction Trials
082af659-e5a1-5e55-bb14-86dcfa2c12cc | note | Acceptance / Conformance Criteria - The Contractor shall carry out compaction trials of the various soil types and combinations on site, and any imported fill materials, using different layer thicknesses, types of rollers and conditioning plant (i.e. construction discs and scarifiers). The trials shall be conducted over the duration of the earthworks operation with the objective of determining the most suitable and efficient techniques to meet the compaction requirements. The trial details, test data and conclusions shall be reported and copied to the Engineer within five days of completion of each trial.
b932f253-0659-5483-8431-149e22a51f34 | note | Standard / Specification - PS 15.10.15
0ff16a2c-7e89-5fe7-97b9-0d0dc811e560 | note | Verifying Document - Trial Results
5fa74afb-d11f-58b9-9267-b51498af3937 | note | Frequency - During Works before placement of each material.
103d17fd-0df9-56e9-949a-dda4690eb715 | note | Verification Activity: Activity - R
66efe4f8-ef07-5b70-852c-a42dccaab6c1 | note | Verification Activity: By - PE
e6b0ff49-10c9-5967-b663-f2fc4e147aa3 | checkpoint | 6.03.04 - Geotextile on Undercut to Waste and Backfill
b66a3f7f-c101-55fc-a488-65023d32f225 | note | Acceptance / Conformance Criteria - Geotextile shall be laid across the undercut base and the sides and joints shall be overlapped in accordance with the manufacturers specification to prevent squeezing of the underlying foundation.
39fe306a-53bb-58ff-84b4-d25744279b95 | note | Standard / Specification - PS 15.10.9
2215bfc9-484e-5f67-adce-6df3c540172a | note | Verifying Document - Site Records
2d33a3f7-a446-54bb-a02a-dbae2920cdbb | note | Frequency - Prior to Backfilling undercuts
8477f682-7f40-53b2-9c76-46de57fde771 | note | Verification Activity: Activity - R
f661c483-12d8-5268-8d41-625af8658963 | note | Verification Activity: By - SE
29370bd4-2ff3-5032-ac70-4629fb46ed01 | checkpoint | 6.03.06 - Weaving or Pumping
bd1991d0-5093-5804-aff8-c52b44e7385d | note | Acceptance / Conformance Criteria - Any weaving or pumping of the soil or subgrade during the compaction process is likely to indicate that either the water content is excessive or the material has been over-compacted. If weaving or pumping is observed, the Engineer should be contacted to advise the appropriate solution.
e605ba42-46c5-5a4e-888c-2477e598e0b8 | note | Standard / Specification - PS 15.10.16
d39f9c2c-ed77-5b28-9068-8d5502076351 | note | Verifying Document - Site Records
68e095e6-4a9f-530e-83a7-48b3803bce4c | note | Frequency - When encountered
27e7c1ea-82b6-5046-a56c-510159c3d998 | note | Verification Activity: Activity - S
ed838f5a-7bf1-5227-8006-76b8f7af37f3 | note | Verification Activity: By - SE
8121b3c2-5c62-5f8a-95d7-1511aca62833 | checkpoint | 6.03.07 - Finished Surfaces
3070b6ed-33d2-59d9-86fa-a87d75982015 | note | Acceptance / Conformance Criteria - The proposed works shall meet the minimum geometric extent both horizontally and vertically as specified in the Contract Drawings. Minimum general survey tolerances for earthworks construction purposes shall be level +/25mm unless stated otherwise, Subgrade; 0 to -30mm before placing aggregate layers, Bulk fill ±100mm, Preload and surcharge ±100mm, Batter slope tolerance ±100mm
3c16fa38-3eaf-5ad1-9f22-07ba1a84a45f | note | Standard / Specification - PS 15.6.8
816b2da5-1e05-56ee-b0d4-f4dad76d85e7 | note | Verifying Document - Survey Records
41c5a73c-3d7a-5d08-99a6-a6c30a41296c | note | Frequency - Each Finished Surface
d8403246-e1a7-5f1e-a63f-c616a6f86317 | note | Verification Activity: Activity - D
6183135d-77a3-5020-94fc-7c8fb634a0f3 | note | Verification Activity: By - SV
28941e1a-7c86-5b6c-b4be-2bd9aa06435c | checkpoint | 6.03.08 - Final Trimmed Shape Inspection
929f9aa7-dcab-55ef-848e-e713dd5186b9 | note | Acceptance / Conformance Criteria - The Engineer shall Inspect final trimmed shape prior to placing topsoil or track rolled fill.
a0d0e862-2504-55af-b439-f3f7356c1fcf | note | Standard / Specification - PS 15.13
51f6149e-c97b-5a09-af39-5267730b4dd8 | note | Verifying Document - Engineers Approval
1d64599f-c05f-5017-bfc2-421633c38bf0 | note | Frequency - Prior to placing topsoil or track rolled fill.
ec8638c9-6512-5db2-95d2-d6d3f35119b8 | note | Verification Activity: Activity - HP
72c74c91-2072-5a09-8013-ca846e10480a | note | Verification Activity: By - ENG
2fa4e556-dcd6-5d59-898c-5d69fcba5b07 | signoff | AUTHORITY HOLDPOINT
9009fa4f-63e9-5b9f-b8f5-3feccfd591cc | section | 6.04 Type A1 Imported Structural Fill (Granular Bulk Fill, GAP40, GAP65)
25dd2c92-e278-54c8-aa60-59679d5bfb86 | checkpoint | 6.04.01 - Imported Structural Fill Layers
6878fdaf-0bcd-5db1-a513-1fc0df376bbf | note | Acceptance / Conformance Criteria - The material shall be placed and compacted in layers no greater than 300mm thick.
8b06cea0-2762-5a10-b343-8660f98e0189 | note | Standard / Specification - PS 15.10.14
1a89ef0a-9801-51bc-aee0-85e181a5627d | note | Verifying Document - Site Records
30797fec-d05d-5e1d-9407-2ca3ce812dbc | note | Frequency - Each Layer
e9f5e8d3-b7f2-5398-be87-1d5e695a0fb9 | note | Verification Activity: Activity - R
d72c325b-87d7-5b7a-abca-566cc22d1211 | note | Verification Activity: By - SE
7d79ea5d-74fb-5020-a7fc-15bc0d20fe88 | checkpoint | 6.04.03 - Structural Fill Zone - Strength – Clegg Impact Value (CIV)
33972346-eaf4-5b1b-adab-39ff4c57e4e4 | note | Acceptance / Conformance Criteria - A1 Imported Structural Fill Strength shall be tested by Clegg Hammer every 200m3 per area per day per lift
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Minimum CIV = 18
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Average CIV= 20
b21d6bc2-fa63-5bc1-8d96-b05121b299af | note | Standard / Specification - Appendix XIII
9e78cce7-cd0a-5ffe-b4f7-52f1a5f40ad1 | note | Verifying Document - Clegg Results
edfa4ec3-1fcc-5df9-ba9c-81716eabe644 | note | Frequency - 1 Set (5 Tests – 5x5m Square Grid) Per 200m3 Of Placed Per Area Worked Of Day Per Lift
c952f64f-f2ef-5aeb-b6b7-5b247ddc0cdb | note | Verification Activity: Activity - I
e91737f2-9daa-590c-ba83-c4825556312f | note | Verification Activity: By - SE
e7febe44-92c4-5796-b0f2-b82320d4484e | checkpoint | 6.04.05 - Structural Fill Zone Insitu Density Insitu Compacted Dry Density Insitu Water Content
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - A1 Structural Fill Compaction shall be tested by NDM in Backscatter Mode every 200m3 per area per day per lift
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | ○ Average >95% Of In-Situ MDD
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | ○ Minimum >92% Of In-Situ MDD
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Standard / Specification - Appendix XIII
69d85f65-b61d-579d-940f-2b691894d755 | note | Verifying Document - NDM Results
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
e2147c12-4568-5322-b418-283ae63070af | note | Verification Activity: Activity - I
09a8aad4-3fc9-597d-b419-c865f36b4acc | note | Verification Activity: By - SE
b9a8462b-715b-5c2d-8c25-e4f73254a4ca | checkpoint | 6.04.06 - Solid Density
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - The Solid Density Of Aggregate Particles shall be tested by collecting 1 sample with every set of NDMS completed (1 Test Per 200m3 For That Material Type And Source). Test Results Provide Input To Acceptance Criteria For Insitu Compacted Dry Density Determined By Nuclear Moisture Density Gauge (NDM)
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - Appendix XIII
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Solid Density Lab Report
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - 1 Set (5 Tests) Per Material Type And Source Then 1 Test Per 200m3 For That Material Type And Source
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
504915a0-29d1-5b8a-891c-a7b613638c3c | checkpoint | 6.04.07 - Organic Content
f09d0ff0-01ec-50cb-9988-3a078371cb3d | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
5d4c6d19-d8fb-5765-9b80-10ed32dbffe9 | note | Standard / Specification - Appendix XIII
ea12d870-db9e-5048-94de-56f316678975 | note | Verifying Document - Site Records
4b4f2a35-1e50-5341-80c6-541a73664b53 | note | Frequency - Ongoing
f77c9bbc-fb8f-5e0f-86c9-c66a4643254e | note | Verification Activity: Activity - I
dbb35f07-7f2f-5414-a8b4-c69adbcef37c | note | Verification Activity: By - SE
f910ed7f-8370-57c8-b1bd-2fb721606286 | checkpoint | 6.04.08 - Completed Fill Approval
cb670aff-3430-5d2c-ac3e-1482548f09ee | note | Acceptance / Conformance Criteria - Prior to pavement construction the Engineer shall complete a Desktop review of all structural fill compaction testing for acceptance.
e3ea5880-55a7-54a4-9ee9-9323b972ab79 | note | Standard / Specification - PS 15.13
eb4e4dcc-9679-50a0-8275-a70670f63fd0 | note | Verifying Document - Engineer Approval
5b1465a0-9c5b-51b0-8b4b-9694e85f2324 | note | Frequency - Prior to Pavement Construction
a3b40c94-fe59-5b33-bcda-878d287d2995 | note | Verification Activity: Activity - HP
696e1611-579b-5ae6-b3d8-5701063db1b8 | note | Verification Activity: By - ENG
5e0c2555-3e93-5160-beb9-af9efce873aa | signoff | AUTHORITY HOLDPOINT
faf4f3a3-1299-5382-bb2c-73748ed0cb2e | section | 6.05 LANDSCAPE FILL
a57c22bd-882b-5e15-98f1-6cc1024a010c | checkpoint | 6.05.01 - Cohesive Fill Layers
c352122b-b969-515a-bd14-4ee2d6d77a2c | note | Acceptance / Conformance Criteria - Cohesive structural and non-structural fill material, shall generally be compacted in layers of less than 200mm thickness. All fill surfaces shall be sealed at the end of each day’s work.
eb2c9836-d46b-5735-a171-5b7c260a8373 | note | Standard / Specification - PS 15.10.16
16c87f21-2b6f-5a9e-950f-ce52726911a4 | note | Verifying Document - Site Records
f997564b-0a06-59cc-aaf8-0d04c169bb65 | note | Frequency - Each Layer
48daa9bc-dbe2-5457-aa35-ebb3d2f05eee | note | Verification Activity: Activity - R
a63751f3-0140-5d7c-80c1-864752f123ce | note | Verification Activity: By - SE
e9f6dd3e-48b2-53bf-8c70-05c59c2b86d9 | checkpoint | 6.05.03 - Non-Structural Fill - Air Voids
8e28b866-fa38-519b-918f-3d14bb22ecfb | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill compaction (Air Voids) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift.
8d53921a-09d5-5ddd-b361-6ff29682cbca | note | ○ Average Maximum Air Voids < 8%
c3c1296c-564e-5332-8f97-a1742c8a6a85 | note | ○ Single Test Maximum Air Voids< 10%
b6a6dfee-f164-5998-9bdb-0af48b5f824e | note | Standard / Specification - Appendix XIII
bebdea1e-dece-5fe9-9b48-a107125b16b9 | note | Verifying Document - NDM Results
e003f7a2-352b-5d80-9fd5-e44eddfe06fe | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
3f5e0ef0-3697-5f92-8b8c-ec24df3f2e89 | note | Verification Activity: Activity - R
da65e1bd-770b-59ad-9793-ebeab9e626dd | note | Verification Activity: By - SE
2254b6f8-ca87-5831-8381-537164057ab6 | checkpoint | 6.05.04 - Non-structural Fill – Shear Strength (SU)
9edd37d7-9376-551e-84f9-b888b8840c61 | note | Acceptance / Conformance Criteria - Cohesive Non-Structural Fill Strength shall be tested by hand held Shear Vane or Scala every 500m3 per area per day per lift of fill placed.
5b2f902a-75e1-52ba-831a-286d435423d5 | note | ○ Average Minimum Su > 60kPa
0d47f6a9-9a9c-5830-a715-20e29444a71c | note | ○ Single Test Minimum Su > 50kPa
cd8cbc5d-5199-51fe-8b4d-b38294c9026a | note | ○ Scala: Minimum 2 Blow Per 100mm up to 1.0m deep
3987cf23-05e1-5604-91fa-7c85db88248f | note | Standard / Specification - Appendix XIII
7cd5ddd4-8c1e-52f1-aeba-5f314cce96f9 | note | Verifying Document - Shear Vane or Scala Results
6c04cc44-a270-5c2c-903f-8ca50b667f73 | note | Frequency - 1 Set (5 Test) Per 500m3 Of Fill Placed Per Area Worked Per Day Per Lift
031b41c8-0684-5bd5-9692-1238e6978165 | note | Verification Activity: Activity - I
2f45e865-55b9-5d5f-94f9-2cda2e27e330 | note | Verification Activity: By - SE
67d2cb19-a2ab-56fe-9362-2a11a6148fa9 | checkpoint | 6.05.05 - Non-Structural Fill - MDD
8538573c-cf3b-5d93-9368-25bca6185db5 | note | Acceptance / Conformance Criteria - Non-Cohesive Non-Structural Fill compaction (Dry Density) shall be tested by NDM (Direct Transmission) every 200m3 per area per day per lift. 90% Minimum Dry Density (MDD).
0859020c-bdbe-53a9-aa8e-86fa06eb9044 | note | Standard / Specification - Appendix XIII
d1330c35-522e-5ba6-999b-78f42cdedb3c | note | Verifying Document - NDM Results
f71ac2b1-40f1-5836-9882-b3e5ee872755 | note | Frequency - 1 Set (5 Test) Per 200m3 Of Fill Placed Per Area Worked Per Day Per Lift
69d85f65-b61d-579d-940f-2b691894d755 | note | Verification Activity: Activity - I
8ab19fa7-6aa1-5a12-b545-cf914fee74be | note | Verification Activity: By - SE
940c74e2-d6b4-59ce-a549-e065a128c6e6 | checkpoint | 6.05.06 - Non-Structural Fill - Granular Mixed Materials
0419e26d-8e73-55d6-8166-f030f49ff305 | note | Acceptance / Conformance Criteria - Mixed non-structural material requires proof roll to ensure compliance with the 7mm requirement. Proof roll to be done where soils cannot be penetrated via shear vanes or scala
6b8338ea-3136-54bc-aec4-0e1145900e7a | note | Standard / Specification - TNZ F1 Section 10.5.1
06771a40-5a5a-5d5d-8674-41bfaeebf1b9 | note | Verifying Document - Site Records
69aaa7ae-4003-5c0e-ba1f-ddc69c9b29da | note | Frequency - Formation level
19c9408e-b96a-516b-b78e-a5dd3fe8565c | note | Verification Activity: Activity - I
5540bb1d-6af1-5d75-a199-fe2a1662c21b | note | Verification Activity: By - SE
c83c1a95-6cc3-5b55-ac8c-57dd36cf1a2e | checkpoint | 6.05.07 - Organic Content
f09d0ff0-01ec-50cb-9988-3a078371cb3d | note | Acceptance / Conformance Criteria - Visual observation continuous field observation and recording aggregate shall be free from organic, calcareous or other deleterious materials.
5d4c6d19-d8fb-5765-9b80-10ed32dbffe9 | note | Standard / Specification - Appendix XIII
ea12d870-db9e-5048-94de-56f316678975 | note | Verifying Document - Site Records
4b4f2a35-1e50-5341-80c6-541a73664b53 | note | Frequency - Ongoing
f77c9bbc-fb8f-5e0f-86c9-c66a4643254e | note | Verification Activity: Activity - I
dbb35f07-7f2f-5414-a8b4-c69adbcef37c | note | Verification Activity: By - SE
8a6e4423-2a66-5b93-af2a-67e156f07a85 | checkpoint | 6.05.08 - Water content
cb670aff-3430-5d2c-ac3e-1482548f09ee | note | Acceptance / Conformance Criteria - The water content shall be tested by collecting 1 sample with every individual NDM test.
e3ea5880-55a7-54a4-9ee9-9323b972ab79 | note | Standard / Specification - Appendix XIII
eb4e4dcc-9679-50a0-8275-a70670f63fd0 | note | Verifying Document - Water Report
5b1465a0-9c5b-51b0-8b4b-9694e85f2324 | note | Frequency - Every NDM
a3b40c94-fe59-5b33-bcda-878d287d2995 | note | Verification Activity: Activity - I
696e1611-579b-5ae6-b3d8-5701063db1b8 | note | Verification Activity: By - SE
94ecb72f-b511-5fef-99c9-b75caaae5292 | checkpoint | 6.05.09 - Bulk Density, Dry Density, Air Voids
2ff13b7b-02c2-5a7b-8118-f41c41b17271 | note | Acceptance / Conformance Criteria - The Bulk Density, Dry Density, Air Voids shall be tested by collecting 1 sample (Sample Tube) for every 10 NDM Sets completed.
c39051d9-945b-528b-a585-33d79297aaee | note | Standard / Specification - Appendix XIII
dd793333-b4d3-5ea8-9644-25cf03ccc6e5 | note | Verifying Document - Lab Report
d69a3d8f-c798-532b-a15c-6f7e4df14e4c | note | Frequency - 1 Test Performed For Every 10 NDM Test Results Provide
2d5640eb-932b-5ba9-87eb-2c7ce14f8894 | note | Verification Activity: Activity - I
c9a19186-767d-535f-9741-6cc10a171f11 | note | Verification Activity: By - SE
| checkpoint | Client Final Inspection - the signature below verifies that this ITP has been completed in accordance with the Specifications and verifies lot compliance.
| textbox | Contractor's Rep Name:
| textbox | Engineer's Rep. Name:
| date | Date:
| signoff | Add Signature