## PA-01
type A | name PA-01 | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Edge Lifter 2.5T | 2
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 40 Panel Mix - B80 | 1
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 35mm
checkpoint | Panel Thickness confirmed
dropdown |  | 200mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness | 200
textbox | Nexus 2.5T Edge Lifter (T845) | 2
textbox | ID Plate | 1
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Aluminimum Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 35mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix B80 - N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?

## PA-02
type A | name PA-02 | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Edge Lifter 2.5T
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 40 Panel Mix - B80
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 35mm
checkpoint | Panel Thickness confirmed
dropdown |  | 200mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness | 200
textbox | Nexus 2.5T Edge Lifter (T845) | 2
textbox | ID Plate | 1
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Aluminimum Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 35mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix B80 - N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?

## PA-03
type A | name PA-03 | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Edge Lifter 2.5T
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 40 Panel Mix - B80
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 35mm
checkpoint | Panel Thickness confirmed
dropdown |  | 200mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness | 200
textbox | Nexus 2.5T Edge Lifter (T845) | 2
textbox | ID Plate | 1
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Aluminimum Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 35mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix B80 - N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?

## PA-04
type A | name PA-04 | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Edge Lifter 2.5T
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 40 Panel Mix - B80
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 35mm
checkpoint | Panel Thickness confirmed
dropdown |  | 200mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness | 200
textbox | Nexus 2.5T Edge Lifter (T845) | 2
textbox | ID Plate | 1
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Aluminimum Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 35mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix B80 - N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?

## PB-01
type A | name PB-01 | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Edge Lifter 2.5T
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 40 Panel Mix - B80
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 35mm
checkpoint | Panel Thickness confirmed
dropdown |  | 200mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness | 200
textbox | Nexus 2.5T Edge Lifter (T845) | 2
textbox | ID Plate | 1
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Aluminimum Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 35mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix B80 - N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?

## PB-02
type A | name PB-02 | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Edge Lifter 2.5T
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 40 Panel Mix - B80
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 35mm
checkpoint | Panel Thickness confirmed
dropdown |  | 200mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness | 200
textbox | Nexus 2.5T Edge Lifter (T845) | 2
textbox | ID Plate | 1
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Aluminimum Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 35mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix B80 - N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?

## PB-03
type A | name PB-03 | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Edge Lifter 2.5T
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 40 Panel Mix - B80
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 35mm
checkpoint | Panel Thickness confirmed
dropdown |  | 200mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness | 200
textbox | Nexus 2.5T Edge Lifter (T845) | 2
textbox | ID Plate | 1
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Aluminimum Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 35mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix B80 - N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?

## PB-04
type A | name PB-04 | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Edge Lifter 2.5T
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 40 Panel Mix - B80
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 35mm
checkpoint | Panel Thickness confirmed
dropdown |  | 200mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness | 200
textbox | Nexus 2.5T Edge Lifter (T845) | 2
textbox | ID Plate | 1
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Aluminimum Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 35mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix B80 - N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?

## PC-01
type A | name PC-01 | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Edge Lifter 2.5T
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 40 Panel Mix - B80
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 35mm
checkpoint | Panel Thickness confirmed
dropdown |  | 200mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness | 200
textbox | Nexus 2.5T Edge Lifter (T845) | 2
textbox | ID Plate | 1
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Aluminimum Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 35mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix B80 - N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?

## PD-01
type A | name PD-01 | values
checklist-sectioned | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction" |  | upload a copy to CONQA?
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
tickbox | Edge Lifter 2.5T
tickbox | Reinforcement
tickbox | ID Plate
tickbox | 40 Panel Mix - B80
checkpoint | Upload sufficient number of photos pre pour
section | Concrete Pour Checks
checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
tickbox | All Concrete Dockets Attached
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 35mm
checkpoint | Panel Thickness confirmed
dropdown |  | 200mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Panel Thickness | 200
textbox | Nexus 2.5T Edge Lifter (T845) | 2
textbox | ID Plate | 1
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Aluminimum Formwork
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 35mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - GOOD as near face is outside face of building
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix B80 - N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN |  | upload docket?
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER |  | signoff?