## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Installers Checklist | [5 empty] | Installers Checklist (Abutment Base)
checkpoint | Complete Material "Bucket List"
textbox | Foot Anchors 2.5T 170mm
textbox | Grout Tubes 290mm
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK - Wall Height 684mm
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Bridge Plank Mould
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Use Bridge Mould
checkpoint | Check Concrete cover around reo 30mm
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required -Off Form Steel Trowel
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
holdpoint | Request Signoff
checklist | Installers Checklist | [5 empty] | Installers Checklist (Abutment Wall)
checkpoint | Complete Material "Bucket List"
textbox | Foot Anchors 2.5T 170mm
textbox | Ferrules - M24 Elephant Foot
textbox | Grout Tubes 290mm
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Bridge Mould
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 30mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required -Off Form Steel Trowel
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
holdpoint | Request Signoff