## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Precast Components ITP
section | Manufacturing Documents
checkpoint | Shop drawings reviewed and updated. Issued "As For Construction"
section | Pre-Pour Checks
checkpoint | Final Inspection - all placed in accordance with approved shop drawings
checkpoint | Upload sufficient number of photos pre pour
section | Transport
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist
checkpoint | Overall Measurements
checkpoint | Void Correct Position
checkpoint | Ferrules - Measurements & Size - NS / FS
checkpoint | Lifters Correct - Position, Size, Orientation
checkpoint | Fillet is Installed
checkpoint | Check Concrete cover around Reo 30mm
checkpoint | Panel Thickness confirmed
dropdown | Panel Thickness: | 150mm
checkpoint | Magnets are 100% Secure
checkpoint | Panel is Clean
checkpoint | Photo Taken
checklist | Installers Checklist
checkpoint | Complete Material "Bucket List"
textbox | Eye Anchor - 2.5T
textbox | Ferrules - M20 x 96mm
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Bridge Plank Mould
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 30mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required - Broom
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
holdpoint | Request Signoff
checklist | Installers Checklist | [5 empty] | Installers Checklist (Abutment Base)
checkpoint | Complete Material "Bucket List"
textbox | Foot Anchors 2.5T 170mm
textbox | Ferrules - M24 Elephant Foot
textbox | Grout Tubes 290mm
textbox | ID Plate
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Bridge Mould
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | Check Concrete cover around reo 30mm
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required -Off Form Steel Trowel
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
holdpoint | Request Signoff
checklist | Installers Checklist | [5 empty] | Installers Checklist (Abutment Wall)
checkpoint | Complete Material "Bucket List"
textbox | Foot Anchors 2.5T 170mm
textbox | Grout Tubes 290mm
checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK - Wall Height 884mm
checkpoint | Apply bond breaker or wax 1 2 3
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Bridge Plank Mould
checkpoint | Install Reo as-per Shop Drawing Plan
checkpoint | Use Bridge Mould
checkpoint | Check Concrete cover around reo 30mm
checkpoint | Lifters to be Firm & Square against Formwork
checkpoint | DOUBLE CHECK EVERYTHING
checkpoint | Finish Required -Off Form Steel Trowel
checkpoint | QA - Final Check of ALL measurerments & Photos
checkpoint | QA - Concrete Mix N40 Panel Mix
checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
checkpoint | CONCRETE TEST TAKEN
date | Pour Date
checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
holdpoint | Request Signoff