## zres_siteapp_NEW
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | T3084984 - Wiri RAP Interface Returns - ITP Rev03 | itp | T3084984 - Wiri RAP Interface Returns - ITP Rev03 |  | 26d5c926-22b6-4b66-a692-bf3c6a53a00e
| section | T3084984 - Wiri RAP Interface Returns
| checkpoint | 1 - Issued For Construction Drawings
d2d3d592-1220-5184-8225-0c99609f38d4 | note | SPECIFICATION REFERENCE - IFC Drawings Issued by Client/Engineer
0465e994-184f-55ac-bd8f-8c5a0db96f43 | note | ACCEPTANCE CRITERIA - Issued For Construction Drawings Available
3f3c3605-106c-562b-9192-9eeb0363ad5a | note | DATE/SIGN - Contractor Rep - H
| signoff | HOLD POINT
| checkpoint | 2 - Underground Services Confirmation
a37a942c-d0bd-5791-a67c-1ab3b1c67752 | note | SPECIFICATION REFERENCE - CTS Permit to Work
fc916314-fd16-5f1d-9214-0fe3c5a3e7df | note | ACCEPTANCE CRITERIA - Underground Services Drawings to accompany permit and marked out onsite where excavation is to be undertaken
347dc77a-1cbf-59a2-b295-e0fcf482667d | note | DATE/SIGN - Contractor Rep - P
62e04558-f065-507f-89a8-f62ccbf9b36a | note | ○ CTS Civil Inspector - R
| checkpoint | 3 - Survey & Setout
cbd1f752-33b5-506d-bd63-5950a89130ae | note | SPECIFICATION REFERENCE - IFC Drawings
d4afb149-9778-5015-ad61-0b1384e31b21 | note | ○ CTS General Civil Construction Spec
8d848bd8-1b34-548c-93e6-57817b672559 | note | ○ CTS Excavation Works Spec
441da9a3-7842-59bb-95a0-74356e398b21 | note | ACCEPTANCE CRITERIA - Foundations and embedded items shall be setout following the tolerances, heights and positions shown in each foundations respective drawing.
| checkpoint | 4 - Waste Management & Disposal
e02d9587-b526-51be-85de-fe2425abeeec | note | SPECIFICATION REFERENCE - CTS General Civil Construction Spec
bf830f9a-d36c-5b18-9b6b-adff7b739734 | note | ○ CTS Excavation Works Spec
a9324c03-a16a-5841-94a5-ed10144effea | note | ○ CTS Contaminated Environmental Ground Soil Managenet Plan RW-231
d698d631-2ff6-5f24-83ab-17fb30363a60 | note | ACCEPTANCE CRITERIA - Waste management plan prepared and followed. Supporting documents available on request.
f0310620-c07d-5436-98da-b69e98f8615c | note | DATE/SIGN - Contractor Rep - P
de13c16d-6b02-5894-8f64-eb82212db644 | note | ○ CTS Civil Inspector - R
| checkpoint | P1185A - Demolition
96b42369-db5a-579d-bf20-091c72d9e2ec | note | SPECIFICATION REFERENCE - IFC Drawings
eef97807-ab81-5a7c-a03a-69791c11bed7 | note | ACCEPTANCE CRITERIA - Existing pedestal removed at ground level. Concrete removed to approved landfill.
fb8f982b-4ec4-5a9a-9bbf-5834fc0dd2de | note | DATE/SIGN - Contractor Rep - P
59ae458c-7aa8-51b8-bbab-07a5eec50860 | note | ○ CTS Civil Inspector - R
| checkpoint | P1185A - Position of Pump Pedestal Setout
89cff21c-7ee8-5e29-8174-f912077176e4 | note | SPECIFICATION REFERENCE - IFC Drawings
ae395ee4-f086-5c04-85ca-bd101547a3e2 | note | ACCEPTANCE CRITERIA - Setout as per IFC Drawings
2b9c23da-03a6-58b9-bafe-96ae93208701 | note | DATE/SIGN - Contractor Rep - P
ed9c69d5-e306-5d77-9399-ecfd97861ad1 | note | ○ CTS Civil Inspector - R
| checkpoint | P1185A - Pump pedestal location Cleaned & Scabbled
0f2417d3-6a20-5461-9706-b6b46bd7416d | note | SPECIFICATION REFERENCE - IFC Drawings
75d0af9b-1d71-5eb7-807b-1c3745e4fc23 | note | ACCEPTANCE CRITERIA - Foundation area cleaned and free from contamination and dust/oil or grease, surface roughened to accept further concrete pour
362aea47-8e7b-53e6-b8d1-781178f90abc | note | DATE/SIGN - Contractor Rep - P
16c4daea-76ce-5da0-9209-3cff325fae35 | note | ○ CTS Civil Inspector - R
| checkpoint | P1185A - Cast in Items - Bolts & Nuts
4848d4f8-7a8d-57b0-b6d6-1018971fbe03 | note | SPECIFICATION REFERENCE - IFC Drawings
14721145-e2f1-53a9-9854-794ff645c8bf | note | ○ CTS General Civil Construction Specification
8561f67c-adae-5aba-a12b-ab748d2f0240 | note | ○ CTS Epoxy Grouting of Anchor Bolts
bcad05b1-160d-5008-80fb-cec11a3beeda | note | ○ Manufacturers Documentation
8b3b2537-3e7c-5e16-a079-d101bceb13bf | note | ○ Inspection Records
98410c91-1eee-57a7-900a-da056a0f0bba | note | ACCEPTANCE CRITERIA - If drilled in, Epoxy Grout Shall be Ramset C8 placed in accordance with manufacturers recommendations to the levels and positions setout in the drawings
7e185da0-cf3a-55a6-b141-f2f0fa9cc071 | note | ○ Drilled holes for Anchors shall be inspected
dd3baf8c-b7e5-5ee2-a2b3-b4c01e8cc006 | note | ○ Cast in anchor bolts shall be set to spec in IFC drawings and positioned with template to design measurenments in IFC drawings
254ceb82-770a-50a8-91e4-eec25878f291 | note | DATE/SIGN - Contractor Rep - P
40705005-1af2-51f8-a72f-5b951e4db7e2 | note | ○ CTS Civil Inspector - R
| checkpoint | P1185A - Formwork, Reinforcing & Concrete
18e550aa-0b92-5a54-a458-54a48cb00654 | note | SPECIFICATION REFERENCE - IFC Drawings
66fed2f5-2f83-56df-8a06-68b89404b4d0 | note | ○ CTS General Civil Construction Specification NZS3109/3112
f484051a-abc1-598e-a33a-9b9e8dc7eb6d | note | ○ Manufacturers Documentation
a4163e98-9e5f-52fa-a81e-3eadc936a8e5 | note | ○ Inspection Records
2172f7ca-f0e9-5136-aefd-a2fe0391c161 | note | ACCEPTANCE CRITERIA - All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
3824b303-50b5-588a-9d26-6a4d74bf77ea | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
68cf3d62-48e2-5f99-bf11-a619a44d4258 | note | ○ All reinforcing and formwork to comply with IFC drawings
8cfb73bd-5e0a-5d2b-a4f6-3ad7d06b1f57 | note | ○ Concrete to be min 30MPa at 28 days
56299576-6561-52b4-9a56-6c56bbd9bef5 | note | ○ Testing of concrete per CTS Specifications
47d7ea3c-08e7-5c98-ab99-9cabea7bb4e4 | note | ○ Prepour Inspection Record Filled out Prior to Concrete
d45ceaa6-d0f2-5f2f-b6db-0d476925877c | note | DATE/SIGN - Contractor Rep - P
97c3507e-4d0a-5f57-b9c2-03ee99a8e1d7 | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | P1185A - Grouting of Baseplate
c2bee6e0-8ff0-582b-8d2a-5b631f90f095 | note | SPECIFICATION REFERENCE - IFC Drawings
ac92b210-8160-5f86-819c-02734b4a8891 | note | ○ CTS General Civil Construction Specification
4b9918ae-6458-5bbf-9f16-5ed7aa67df56 | note | ○ Manufacturers Documentation
d570c04a-72f4-59c8-a7be-d11f05744010 | note | ACCEPTANCE CRITERIA - Grouting shall be Sika 212 or Sika 214 placed in accordance with manufacturers recommendations and the IFC drawings
83eedfab-311b-5edb-9850-fdcad87a6104 | note | DATE/SIGN - Contractor Rep - P
cb737adc-c4bb-5166-ab05-2424ebc2494a | note | ○ CTS Civil Inspector - W
| checkpoint | P1185B - Demolition
a63e5b12-77b4-59e3-ad4f-3acd51bc99f7 | note | SPECIFICATION REFERENCE - IFC Drawings
cc5db4ef-5929-5fb9-b398-b547d649986e | note | ACCEPTANCE CRITERIA - Existing pedestal removed at ground level
b2e50c35-aeaf-521a-9886-47bf77620337 | note | DATE/SIGN - Contractor Rep - P
c088ba33-f410-574f-92b4-0a08926187ad | note | ○ CTS Civil Inspector - R
| checkpoint | P1185B - Position of Pump Pedestal Setout
e6595284-d317-51dd-bfbc-61cb0aa8e34c | note | SPECIFICATION REFERENCE - IFC Drawings
a775dcc3-b644-566b-a9ca-aa6808e9bedb | note | ACCEPTANCE CRITERIA - Setout as per drawings
6bc182b2-dd70-5117-bf84-3d3e16e21c8b | note | DATE/SIGN - Contractor Rep - P
1c267ad4-2ea5-500c-99f5-f23e05a988ac | note | ○ CTS Civil Inspector - R
| checkpoint | P1185B - Pump Pedestal Location Cleaned & Scabbled
2d58e169-696d-58ed-acc6-1acd36cd7f6e | note | SPECIFICATION REFERENCE - IFC Drawings
60bbba16-5046-532e-9866-ab90cc17c02e | note | ACCEPTANCE CRITERIA - Foundation area cleaned and free from contamination and dust/oil or grease, surface roughened to accept further concrete pour
7ced8917-799b-5b8c-9afd-4a8704b10328 | note | DATE/SIGN - Contractor Rep - P
71015ac4-85e4-5ddf-a600-3644a17efc9c | note | ○ CTS Civil Inspector - R
| checkpoint | P1185B - Cast in Items - Bolts & Nuts
f33c8c71-1435-5c23-9ab7-b6e530d096a7 | note | SPECIFICATION REFERENCE - IFC Drawings
9f4720c2-f78c-5498-95ed-c8cee1b1414e | note | ○ CTS General Civil Construction Specification
2d1409e3-36cc-586b-a430-1e04c8a8c015 | note | ○ CTS Epoxy Grouting of Anchor Bolts
ce4e18c2-5954-5a92-a4a4-0f347976f75e | note | ○ Manufacturers Documentation
7bc5e43a-7b2d-5026-98bf-db6cf0c8c08e | note | ○ Inspection Records
3185565c-6633-527a-a255-cd8283246da4 | note | ACCEPTANCE CRITERIA - If drilled in, Epoxy Grout Shall be Ramset C8 placed in accordance with manufacturers recommendations to the levels and positions setout in the drawings
4dc3c6a7-d654-50ee-a18a-06bd25a3cbeb | note | ○ Drilled holes for Anchors shall be inspected
385b557e-3bce-5fe7-8379-560dd65601ad | note | ○ Cast in anchor bolts shall be set to spec in IFC drawings and positioned with template to design measurenments in IFC drawings
766a0a41-21b5-5f9a-88c4-4219f7df6016 | note | DATE/SIGN - Contractor Rep - P
298eb471-7af3-5bbd-b9f6-32f333f41e0f | note | ○ CTS Civil Inspector - R
| checkpoint | P1185B - Formwork, Reinforcing & Concrete
e7ce2ef2-1e6d-587d-b836-986cd5dc56ce | note | SPECIFICATION REFERENCE - IFC Drawings
b4512d25-bd96-59c1-a2d9-aad0c0580fee | note | ○ CTS General Civil Construction Specification NZS3109/3112
c575ee6e-3758-5369-b2ff-064cb798cc25 | note | ○ Manufacturers Documentation
c8b705f6-eecf-5c16-9f87-e76d129bcc52 | note | ○ Inspection Records
cce93493-9c13-5c7e-8e7b-3fdb04b518f2 | note | ACCEPTANCE CRITERIA - All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
b7aa9ff6-0ab3-56a3-a4ac-6460da61db33 | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
5be56634-d8a2-5869-ab67-7e0ed7190984 | note | ○ All reinforcing and formwork to comply with IFC drawings
40e26f16-f26d-5e04-9cd3-aca246d05ce9 | note | ○ Concrete to be min 30MPa at 28 days
32f1e969-dd61-55e7-bbda-ba38e357e3e1 | note | ○ Testing of concrete per CTS Specifications
15590b35-9a95-5944-8340-8a74076039e8 | note | ○ Prepour Inspection Record Filled out Prior to Concrete
88277227-f293-586c-a5f3-7c0910497c90 | note | DATE/SIGN - Contractor Rep - P
63ec835d-a6d0-55f1-8df9-797385f63d65 | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | P1185B - Grouting of Baseplate
3fde85df-eaa2-5aed-9bdd-030de7b8232f | note | SPECIFICATION REFERENCE - IFC Drawings
780cd39b-90c7-568e-9c2d-0f8ac2665d6e | note | ○ CTS General Civil Construction Specification
8d2a1f0c-30fa-5980-9a93-7b0a71b135df | note | ○ Manufacturers Documentation
351a9352-da88-581b-bf25-e474eef39855 | note | ACCEPTANCE CRITERIA - Grouting shall be Sika 212 or Sika 214 placed in accordance with manufacturers recommendations and the IFC drawings
7346fc9d-7031-5468-b7a7-921b7f18ffdf | note | DATE/SIGN - Contractor Rep - P
8b0cc0b7-6784-513b-b81a-f42b63eb63e2 | note | ○ CTS Civil Inspector - W
| checkpoint | PSS3259/PSS3263/PSS3264/PSS3282 - Setout of Pipe Sleeper
d89868fc-629c-5924-9cab-f7df2fcc6cef | note | SPECIFICATION REFERENCE - IFC Drawings
3faf2d3e-d040-5285-bb3f-ed119c3c564b | note | ACCEPTANCE CRITERIA - Comply with setout in drawings
3948583a-13a1-58dd-9a8e-f54c96ba3f5e | note | DATE/SIGN - Contractor Rep - P
a297606c-645f-5665-b9e6-b761ac60ca82 | note | ○ CTS Civil Inspector - R
| checkpoint | PSS3259/PSS3263/PSS3264/PSS3282 - Excavation & Foundation Preparation inc Site Concrete
5edb43d0-6a81-53f8-8d91-5ac64928bd1d | note | SPECIFICATION REFERENCE - IFC Drawings
69a6c6d5-55fe-59d7-acde-33a3148dc8bb | note | ○ CTS Excavation Works Specification
d6252ef3-310c-575a-8d59-31e682571520 | note | ○ CTS General Civil Construction Specification
89927cff-3151-5fc7-9231-4a91c6cb933a | note | ACCEPTANCE CRITERIA - Excavated as per IFC drawings to line and levels shown. Foundation compaction Inspection Record completed.
5f3225c8-72d5-5774-b783-1e7cb2b95cc3 | note | DATE/SIGN - Contractor Rep - P
2a54887f-5e9f-5d7c-98db-0f72e51d6174 | note | ○ CTS Civil Inspector - W
| checkpoint | PSS3259/PSS3263/PSS3264/PSS3282 - Formwork, Reinforcing & Concrete
05cad429-3d8e-5e38-85b4-5082d899a4d2 | note | SPECIFICATION REFERENCE - IFC Drawings
351b37ab-0aa4-56e7-a8a8-f7f8d4742abe | note | ○ CTS General Civil Construction Specification NZS3109/3112
3bc355e5-d9fe-56f4-b306-d74e13959e99 | note | ○ Manufacturers Documentation
c50e4bb4-d451-5bcc-8cfd-3e5b6a3ff89f | note | ○ Inspection Records
2e23418a-5b50-52a8-8457-c0124d980a7a | note | ACCEPTANCE CRITERIA - All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
17e59dc2-4c22-5822-88c4-8de2cc997b00 | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
05900b9d-9af8-5518-b597-25f0c3c49316 | note | ○ All reinforcing and formwork to comply with IFC drawings
e62839a6-017a-57a6-82a4-b21f6facc292 | note | ○ Concrete to be min 30MPa at 28 days
56d6c6fa-79e8-5a22-ab3e-73f2637f8b6e | note | ○ Testing of concrete per CTS Specifications
c5898c84-a2c6-5b7c-a05e-85555a483764 | note | ○ Prepour Inspection Record Filled out Prior to Concrete
fc172450-8b3c-516f-9ebc-d2c9c48dbd79 | note | DATE/SIGN - Contractor Rep - P
92058a5c-5bbd-587e-bc66-29af3d705584 | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | PSS3268/PSS3269 - Position of Slab Extension Setout
bac641da-c053-57dc-9404-02b01a8ed07b | note | SPECIFICATION REFERENCE - IFC Drawings
3bd40c11-0274-5563-970d-24e61e47d5c4 | note | ACCEPTANCE CRITERIA - Setout as per drawings
c3a40300-467e-55ed-9218-da08056f5bd0 | note | DATE/SIGN - Contractor Rep - P
a4466e46-41a5-5b7a-bb31-a05281db594b | note | ○ CTS Civil Inspector - R
| checkpoint | PSS3268/PSS3269 - Excavation & Foundation Preparation inc Site Concrete
fa5e9d38-168f-587b-9acc-075c158f8aa4 | note | SPECIFICATION REFERENCE - IFC Drawings
bbba09ea-5915-5b76-a03a-d540403b1fbc | note | ○ CTS Excavation Works Specification
67741041-31a4-5ee4-ac9d-6e01cecd2610 | note | ○ CTS General Civil Construction Specification
cdf66b29-2322-525a-9376-c8d0f9412361 | note | ACCEPTANCE CRITERIA - Excavated as per IFC drawings to line and levels shown. Foundation compaction Inspection Record completed.
634c1b05-a8ca-58ce-9ba5-03f48371a1c3 | note | DATE/SIGN - Contractor Rep - P
8a39c3a8-9389-5bf3-95e9-0f122aa92c75 | note | ○ CTS Civil Inspector - W
| checkpoint | PSS3268/PSS3269 - Formwork, Reinforcing & Concrete
48a1b742-417c-571c-b647-da69d5301e4c | note | SPECIFICATION REFERENCE - IFC Drawings
38176a7e-d536-55d3-8392-24f4800aa208 | note | ○ CTS General Civil Construction Specification NZS3109/3112
de0dc8e6-dbf3-5c20-963a-bb02fe0e65fe | note | ○ Manufacturers Documentation
245f8c25-43cd-5223-8749-4a6dc2ca8269 | note | ○ Inspection Records
4b84c154-1a64-534f-b0bc-f0effa8585df | note | ACCEPTANCE CRITERIA - All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
dd239b03-829f-5ac9-b5aa-f9853098dd82 | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
21b4b8f6-329c-55fa-9a1c-93ab0467207c | note | ○ All reinforcing and formwork to comply with IFC drawings
84a012aa-e85d-514a-bb2f-5cd073f8159e | note | ○ Concrete to be min 30MPa at 28 days
0e606058-8076-5ea1-9d8d-fc28dff3dd1c | note | ○ Testing of concrete per CTS Specifications
a6571016-19ea-5a7a-8779-a6ed00717d83 | note | ○ Prepour Inspection Record Filled out Prior to Concrete
2bae2e87-3f4b-5436-be88-87dc7c317937 | note | DATE/SIGN - Contractor Rep - P
49aea235-4cd4-5bce-ad2a-f22428c1cecf | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | PSS3272/PSS3273 - Position of Slab Extension Setout
f9bfe1a6-fa9c-516f-ab78-35d1c67434ea | note | SPECIFICATION REFERENCE - IFC Drawings
5d8b1b87-d641-5fe7-b7da-8268f57cf488 | note | ACCEPTANCE CRITERIA - Setout as per drawings
0beec65f-83a7-5989-acf0-906afc500079 | note | DATE/SIGN - Contractor Rep - P
77ff334f-8a4e-579c-8c82-d3478daf2870 | note | ○ CTS Civil Inspector - R
| checkpoint | PSS3272/PSS3273 - Excavation & Foundation Preparation inc Site Concrete
02f0a22d-34f1-59df-8c32-ca56bd11b86a | note | SPECIFICATION REFERENCE - IFC Drawings
81a042c8-3131-598c-9422-1e40c18c86ba | note | ○ CTS Excavation Works Specification
22166bda-4d06-5226-8293-6f0ccbea0cfd | note | ○ CTS General Civil Construction Specification
f00587a4-d1b1-5231-9e81-fd9800caab38 | note | ACCEPTANCE CRITERIA - Excavated as per IFC drawings to line and levels shown. Foundation compaction Inspection Record completed.
720fa2da-f935-5b72-9327-256b0b8c2575 | note | DATE/SIGN - Contractor Rep - P
f28cfa22-062c-5f17-87fc-ef6fa5673fe6 | note | ○ CTS Civil Inspector - W
| checkpoint | PSS3272/PSS3273 - Formwork, Reinforcing & Concrete
0c302280-4007-5d75-9bb2-99ab35b3a6df | note | SPECIFICATION REFERENCE - IFC Drawings
674573bc-2ce7-52b1-ae14-1b8285164d42 | note | ○ CTS General Civil Construction Specification NZS3109/3112
31cc02c0-9c0a-54ae-8e33-1bdbfaf5ccd6 | note | ○ Manufacturers Documentation
7131412d-070f-5941-801a-b6de5dc5583e | note | ○ Inspection Records
6e427401-3833-56f4-820a-942f8b2f1785 | note | ACCEPTANCE CRITERIA - All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
ccb1a1f9-8d68-51d5-9624-dc08aee94497 | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
ba89c926-8785-5703-abff-c56c267a46ea | note | ○ All reinforcing and formwork to comply with IFC drawings
0169c798-e9e9-5ef5-a588-d4e6368bf0ca | note | ○ Concrete to be min 30MPa at 28 days
84fdc905-63ea-5dbb-acd4-1f0ec515bbc3 | note | ○ Testing of concrete per CTS Specifications
90fdab7c-8d2a-564b-ba3a-19c80b03258f | note | ○ Prepour Inspection Record Filled out Prior to Concrete
07586369-e35f-5a45-a895-43c57ab739d0 | note | DATE/SIGN - Contractor Rep - P
cbcb71aa-f403-50b7-8442-a3448ae92d52 | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | P3658 - Position of Pump Pedestal Setout
dca692a0-8d2e-5358-ab62-8ccd8262ac4e | note | SPECIFICATION REFERENCE - IFC Drawings
76c8936c-a171-5560-8e60-0c5c79530366 | note | ACCEPTANCE CRITERIA - Setout as per drawings
5e9ebe18-b431-53b9-8c66-3e72e764f647 | note | DATE/SIGN - Contractor Rep - P
336576db-396b-537b-9eb7-8024fdd3a571 | note | ○ CTS Civil Inspector - R
| checkpoint | P3658 - Pump Pedestal Location Cleaned & Scabbled
b8042d7a-01ff-56c6-b7bb-9715c1d0b060 | note | SPECIFICATION REFERENCE - IFC Drawings
6f224088-92c3-5b88-a355-8f519e796de6 | note | ACCEPTANCE CRITERIA - Foundation area cleaned and free from contamination and dust/oil or grease, surface roughened to accept further concrete pour
abfc77b6-f077-5ada-8672-c6af97365120 | note | DATE/SIGN - Contractor Rep - P
8354199c-2d87-5989-a261-20d163152c38 | note | ○ CTS Civil Inspector - R
| checkpoint | P3658 - Cast in Items - Bolts & Nuts
8cdeac5b-b037-50f0-b96b-266bc316d381 | note | SPECIFICATION REFERENCE - IFC Drawings
0753049c-5b1b-58f9-b7ca-15fcbf410f50 | note | ○ CTS General Civil Construction Specification
f73576e0-7a5a-5386-a36f-de0e37066152 | note | ○ CTS Epoxy Grouting of Anchor Bolts
8c64c512-c171-57f0-b710-452852487221 | note | ○ Manufacturers Documentation
753a4ac0-c97a-561b-80f0-4eb229262734 | note | ○ Inspection Records
dbd1962b-5d87-547c-bc1a-6402360ce3f2 | note | ACCEPTANCE CRITERIA - If drilled in, Epoxy Grout Shall be Ramset C8 placed in accordance with manufacturers recommendations to the levels and positions setout in the drawings
238ac032-af71-50da-9a71-a3788fbcb3c4 | note | ○ Drilled holes for Anchors shall be inspected
44417a48-5c5b-5221-a9ab-d867ee6c1c61 | note | ○ Cast in anchor bolts shall be set to spec in IFC drawings and positioned with template to design measurenments in IFC drawings
462e0ba2-27a6-55c1-b39a-714196d16f8d | note | DATE/SIGN - Contractor Rep - P
5fc9839b-88b7-5761-99c7-fec82686e95e | note | ○ CTS Civil Inspector - R
| checkpoint | P3658 - Formwork, Reinforcing & Concrete
12016907-362e-5a07-b9d2-89b299dfe862 | note | SPECIFICATION REFERENCE - IFC Drawings
a26f2db7-1c03-5d93-b85a-9c2a5dc4e403 | note | ○ CTS General Civil Construction Specification NZS3109/3112
120b3767-12a0-50cd-9f36-b5d23c902ac0 | note | ○ Manufacturers Documentation
20ee2e1e-7ead-55f2-adbb-ab12cf4f5fae | note | ○ Inspection Records
935c42a8-99e3-5c67-989b-19c4691fbfa6 | note | ACCEPTANCE CRITERIA - All reinforcing bars shall be Micro-Alloy Class E to AS/NZS 4671 as shown in IFC's.
2509e191-6d3f-58a6-bbbc-f38d441cda3e | note | ○ All reinforcing bar hooks, laps and bends shall be in accordance with NZS3109 unless otherwise noted.
fc67347e-b845-530f-85c2-3c7f1adffa66 | note | ○ All reinforcing and formwork to comply with IFC drawings
a416a89b-6a1e-54dc-ac66-95c8d2f309ff | note | ○ Concrete to be min 30MPa at 28 days
22172ea6-8e4e-5d43-b5f4-c1e30150ed6b | note | ○ Testing of concrete per CTS Specifications
4b0ad07a-5f61-52d6-bac4-09ccebfe68b0 | note | ○ Prepour Inspection Record Filled out Prior to Concrete
352190d1-46e9-5059-977d-6c57df34c6e0 | note | DATE/SIGN - Contractor Rep - P
9d684929-aba3-5546-b700-9d51329717ed | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | P3658 - Grouting of Baseplate
3bfded69-5e77-591e-a69b-903853346a54 | note | SPECIFICATION REFERENCE - IFC Drawings
c8b23e27-869a-529d-982f-dce027ffa759 | note | ○ CTS General Civil Construction Specification
56c5af78-52d1-50f0-99da-cc64212520c0 | note | ○ Manufacturers Documentation
598d85bc-57e5-5b21-b917-78545c0f9b69 | note | ACCEPTANCE CRITERIA - Grouting shall be Sika 212 or Sika 214 placed in accordance with manufacturers recommendations and the IFC drawings
18ba2e0e-6dd8-5bef-ae87-0b6f6c1657e4 | note | DATE/SIGN - Contractor Rep - P
a3865cc4-8eb5-5970-9f13-0e8fd496b63f | note | ○ CTS Civil Inspector - W
| checkpoint | Structural Base Plate Grouting - Grouting of Remaining Baseplates
| note | SPECIFICATION REFERENCE - IFC Drawings
| note | ○ CTS General Civil Construction Specification
| note | ○ Manufacturers Documentation
| note | ACCEPTANCE CRITERIA - Grouting shall be Sika 212 or Sika 214 placed in accordance with manufacturers recommendations and the IFC drawings
| note | DATE/SIGN - Contractor Rep - P
| note | ○ CTS Civil Inspector - W
| checkpoint | 6 - Complete final Civil Inspection and close off ITP
9623f555-435d-55ed-b6ea-b2da8421242e | note | SPECIFICATION REFERENCE - IFC Drawings
643e4692-9b03-5515-a00e-573d912039cd | note | ○ CTS General Civil Construction Specification
6a76b2a9-72f1-5a0d-962c-b8a01ff175af | note | ○ Manufacturers Specification
89c85df7-d8c5-550d-bc51-47c300277289 | note | ACCEPTANCE CRITERIA - ITP/QC has been completed; all steps & hold points signed byrelevant party.
ec83da9a-0325-5644-868a-c779a769b4c8 | note | ○ All work completed as per work pack, and any field instructions issued during construction compiled
77bba869-7ca3-5303-ad29-5d4f1fa7b0a7 | note | DATE/SIGN - Contractor Rep - P
ceb98418-f4ea-52f6-ab60-341c094dbda5 | note | ○ CTS Civil Inspector - H
| signoff | HOLD POINT
| checkpoint | 7 - Non-Conformance Reporting
5d2e0205-35ce-525a-8af4-8e7e65a41920 | note | SPECIFICATION REFERENCE - UCC Internal NCR and or Lucidity event NCR
fb14026d-d691-581f-8c60-428c6368d834 | note | ○ QC Requirements for Civil Works
e776f05f-9afd-5582-a3bd-25ce8e1aa501 | note | ACCEPTANCE CRITERIA - All Non-Conformance reports and Investigations are attached and closed out
6fd5ffa1-463b-5f3a-95b0-aa9925d9f3c6 | note | DATE/SIGN - Contractor Rep - R
| checkpoint | 8 - As Built & Final Design Documentation
46fa36d5-816a-5309-a01b-b77fd539a331 | note | ACCEPTANCE CRITERIA - Confirmation From Engineer on as built records & redline mark ups
ca14c6eb-b2b1-5be8-9c2c-7d587c3e9f93 | note | DATE/SIGN - Contractor Rep - P
| checkpoint | 9 - Reference Info, Specifications
98e6eabc-afb7-5be5-a266-fb371ce36651 | note | ACCEPTANCE CRITERIA - All Reference Information and relevant Product Specifications
| checkpoint | 10 - Punch Listing
e0f0fb42-7d0f-5438-af26-58a312305dae | note | SPECIFICATION REFERENCE - CTS QC Requirments for Civil Work
309c5f9e-fb78-589e-88ec-e4ea1afc67ff | note | ACCEPTANCE CRITERIA - All punch list items are closed out in the relevant timeframe to the required standard
11283e89-5ebf-5bd4-ae4e-d3d80f0fd73b | note | DATE/SIGN - Contractor Rep - P
0aa1e3f5-4140-5554-9505-623cb6b13b89 | note | ○ Project/Construction Engineer - R
| checkpoint | 11 - Compilation of ITP
9d847bd3-b030-5272-8840-ec7136b88a04 | note | ACCEPTANCE CRITERIA - ITP Completed and Signed off
c1eccc4c-cf6d-56a5-a77b-e7150dc0eb62 | note | DATE/SIGN - Contractor Rep - H
331d23de-39a0-5e72-a4a0-49268f2746a6 | note | Project/Construction Engineer - H
| signoff | HOLD POINT