## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-024
Revision : 1
Client: |  | Wyndham City Council |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | K Rd |  | Soft Landscaping |  | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  | N400378 |  | Specifications: VicRoads Standard Specification Section 720 and Drawings
|  |  |  | Structure / Component: Landscaping |  | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: K rd Cliffs, Werriee South |  | Date : | 2024-07-30 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Prior to Works
1.1 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP | OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.3 | Induction and safety measures are in place, safe work method statement (SWMS) undertaken |  | Prior to Commencing | All personnel on site have been inducted to the K Rd Project site and are informed of all relevant environmental management plans. Additionally, all necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS | Inductions Register/OH&S Co-Ordination Plan | Document review | Site Induction Signed. SWMS Signed | IP | Site Engineer / Site Foreman | N/A |  | N/A
1.4 | Relevant Permits Issued |  | Prior to Commencing | All relevant and/or applicable permits have been submitted and approved including details of all areas to be affected by works. | Permit Review | Document review | Excavation Permit # | IP | Site Engineer | N/A |  | N/A
1.5 | Revegetation |  | Prior to Commencing | The selection of suitable plant species and a hydromulch / growth medium for achieving sustainable growth and effective erosion control has been determined by a qualified seed supplier or consulting professional engaged by the Contractor or a regulatory agency. | Document review | Document review | This ITP signed off | IP | Project Engineer | N/A |  | N/A
2 | Construction Works
2.01 | Survey set-out |  | Prior to Commencing Excavation | Survey activities undertaken to ensure all works meet level and location requirements. Establishment and integrity of the survey network shall be verified before commencing any survey and setout activity. | Drawings | Site Inspection | Survey records & pegs on the ground | IP | Site Engineer & Surveyor | N/A |  | N/A
2.02 | Enviromental & Cultural Heritage Factors |  | Prior to Commencing Excavation | Work affecting surrounding environment which is not pre-planned/approved in either Cultural heritage management plan (CHMP), Root Mapping Report, or Geotechnical reports is approved by client representative. | CHMP, Root Mapping Report, Cliff stability Report, Geotechnical Report | Site Inspection | Signed ITP | HP | Superintendent |  |  | N/A
2.03 | Removal of Top Soil |  | During Excavation | Where the removal of topsoil is required, it is to be moved to an appropriate area and stockpilled in accordance with Melbourne Water's Specification for Soils and Landscaping. | AS4419-2018 | Site Inspection | Signed ITP | IP | Site Engineer | N/A |  | N/A
2.04 | Material Source Management |  | Prior to Commencing Excavation | Supply fill material is from one source and will not change without first advising the Company’s Representative and agreeing with them the volume of fill to be obtained from that source. | Document review | Document review | Signed ITP | HP | Site Engineer |  |  | N/A
2.05 | Supply of Materials |  | During Excavation | All materials shall be supplied by the Contractor unless otherwise noted. If any materials are supplied by VicRoads, a joint inspection of the materials shall be made by the Contractor and the Superintendent following delivery of the materials to the site. The materials, if satisfactory, shall thereafter become the responsibility of the Contractor. | 720.04 | Visual Inspection | This ITP signed off | IP | Site Engineer/ Superintendent | N/A |  | N/A
2.06 | Pest and Weed Control |  | During Excavation | Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing. Weed control shall be programmed and implemented to deplete the potential weed seed bank within the topsoil to be used in planting beds. | 720.05 | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.07 | Fertilisers |  | During Excavation | Fertilisers for planting areas and advanced trees shall be slow release with a 9‑12 month release period and suitable for the establishment of plant types, sizes and species specified in the plant schedule(s). | 720.04(f) | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.09 | Mulch |  | During Excavation | All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454. | 720.04(h) AS4454 | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.1 | Weed Control Mat and Erosion Control Mat |  | During Excavation | The Contractor shall supply and install jute or approved equivalent, biodegradable, fire retardant weed and erosion control mat as indicated on the Drawings or as specified. Weed Control Mat shall be minimum 700 grams per square metre and Erosion Control Mat shall be 300 grams per square metre. The surface of the mat shall permit water infiltration. | 720.04(i) | Visual Inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.11 | Ripping |  | During Excavation | The Contractor shall make available each ripped planting area, individual tree planting and grassing area prior to mulching, planting or grassing. The Contractor shall not proceed until the Superintendent acknowledges requirements for ripping have been met. In areas where ripping is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review. | 720.07 (b) | Visual inspection | This ITP signed off | HP | Site Engineer/ Superintendent |  |  | N/A
2.12 | Stockpilling |  | During Excavation | Excavated material which is deemed to be not suitable for use as fill material in accordance with the requirements of this Specification or excavated fill which is excess to fill requirements shall be stockpiled as spoil at locations approved by the Company’s Representative or otherwise removed from site. | 720 | Site Inspection | Signed ITP | IP | Site Engineer / Site Foreman | N/A |  | N/A
2.13 | Topsoil Finished Surface Levels |  | During Excavation | The Contractor shall make available each ripped, topsoiled and cultivated planting area, individual tree planting and grassing area prior to mulching, planting or grassing. The Contractor shall not proceed until the Superintendent acknowledges requirements for topsoiling and cultivation have been met. In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review. | 720.07 (e) | Visual inspection | This ITP signed off | HP | Site Engineer/ Superintendent |  |  | N/A
2.14 | Plant Installation |  | During Excavation | Dimensions and preperation of planting holes meet appropriate dimensions for plant size. Plants have been installed at correct depth and orientation. | Drawings | Visual inspection | This ITP signed off | IP | Site Engineer / Site Foreman | N/A |  | N/A
Comments: |  |  | ________________________________________________________________________________________________________________________________________________________________________ ________________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent