## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1.24 - ITP-SOFT LANDSCAPING | itp |  |  |  |  | 1.24 - ITP-SOFT LANDSCAPING
section | 1 - Prior to Works
checkpoint | 1.1 - Implementation of all measures and controls
label | FREQUENCY - Prior to commencing any activity
label | ACCEPTANCE CRITERIA - All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP
label | REFERENCE DOCUMENTS - OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP
label | INSPECTION / TEST METHOD - Visual Inspection
label | RECORD OF CONFORMITY - This ITP signed off
label | IP
label | RESPONSIBILITY - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Induction and safety measures are in place, safe work method statement (SWMS) undertaken
label | FREQUENCY - Prior to Commencing
label | ACCEPTANCE CRITERIA - All personnel on site have been inducted to the K Rd Project site and are informed of all relevant environmental management plans. Additionally, all necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS - Inductions Register/OH&S Co-Ordination Plan
label | INSPECTION / TEST METHOD - Document review
label | RECORD OF CONFORMITY - Site Induction Signed. SWMS Signed
label | IP
label | RESPONSIBILITY - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Relevant Permits Issued
label | FREQUENCY - Prior to Commencing
label | ACCEPTANCE CRITERIA - All relevant and/or applicable permits have been submitted and approved including details of all areas to be affected by works.
label | REFERENCE DOCUMENTS - Permit Review
label | INSPECTION / TEST METHOD - Document review
label | RECORD OF CONFORMITY - Excavation Permit #
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 1.5 - Revegetation
label | FREQUENCY - Prior to Commencing
label | ACCEPTANCE CRITERIA - The selection of suitable plant species and a hydromulch / growth medium for achieving sustainable growth and effective erosion control has been determined by a qualified seed supplier or consulting professional engaged by the Contractor or a regulatory agency.
label | REFERENCE DOCUMENTS - Document review
label | INSPECTION / TEST METHOD - Document review
label | RECORD OF CONFORMITY - This ITP signed off
label | IP
label | RESPONSIBILITY - Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.01 - Survey set-out
label | FREQUENCY - Prior to Commencing Excavation
label | ACCEPTANCE CRITERIA - Survey activities undertaken to ensure all works meet level and location requirements. Establishment and integrity of the survey network shall be verified before commencing any survey and setout activity.
label | REFERENCE DOCUMENTS - Drawings
label | INSPECTION / TEST METHOD - Site Inspection
label | RECORD OF CONFORMITY - Survey records & pegs on the ground
label | IP
label | RESPONSIBILITY - Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.02 - Enviromental & Cultural Heritage Factors
label | FREQUENCY - Prior to Commencing Excavation
label | ACCEPTANCE CRITERIA - Work affecting surrounding environment which is not pre-planned/approved in either Cultural heritage management plan (CHMP), Root Mapping Report, or Geotechnical reports is approved by client representative.
label | REFERENCE DOCUMENTS - CHMP, Root Mapping Report, Cliff stability Report, Geotechnical Report
label | INSPECTION / TEST METHOD - Site Inspection
label | RECORD OF CONFORMITY - Signed ITP
label | HP
label | RESPONSIBILITY - Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Removal of Top Soil
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - Where the removal of topsoil is required, it is to be moved to an appropriate area and stockpilled in accordance with Melbourne Water's Specification for Soils and Landscaping.
label | REFERENCE DOCUMENTS - AS4419-2018
label | INSPECTION / TEST METHOD - Site Inspection
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
checkpoint | 2.04 - Material Source Management
label | FREQUENCY - Prior to Commencing Excavation
label | ACCEPTANCE CRITERIA - Supply fill material is from one source and will not change without first advising the Company’s Representative and agreeing with them the volume of fill to be obtained from that source.
label | REFERENCE DOCUMENTS - Document review
label | INSPECTION / TEST METHOD - Document review
label | RECORD OF CONFORMITY - Signed ITP
label | HP
label | RESPONSIBILITY - Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.05 - Supply of Materials
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - All materials shall be supplied by the Contractor unless otherwise noted. If any materials are supplied by VicRoads, a joint inspection of the materials shall be made by the Contractor and the Superintendent following delivery of the materials to the site. The materials, if satisfactory, shall thereafter become the responsibility of the Contractor.
label | REFERENCE DOCUMENTS - 720.04
label | INSPECTION / TEST METHOD - Visual Inspection
label | RECORD OF CONFORMITY - This ITP signed off
label | IP
label | RESPONSIBILITY - Site Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.06 - Pest and Weed Control
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - Pre-planting weed control shall be undertaken to ensure that planting areas and new grassed areas are free of visible weeds prior to the commencement of planting and grassing. Weed control shall be programmed and implemented to deplete the potential weed seed bank within the topsoil to be used in planting beds.
label | REFERENCE DOCUMENTS - 720.05
label | INSPECTION / TEST METHOD - Visual Inspection
label | RECORD OF CONFORMITY - This ITP signed off
label | IP
label | RESPONSIBILITY - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.07 - Fertilisers
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - Fertilisers for planting areas and advanced trees shall be slow release with a 9‑12 month release period and suitable for the establishment of plant types, sizes and species specified in the plant schedule(s).
label | REFERENCE DOCUMENTS - 720.04(f)
label | INSPECTION / TEST METHOD - Visual Inspection
label | RECORD OF CONFORMITY - This ITP signed off
label | IP
label | RESPONSIBILITY - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.09 - Mulch
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - All wood mulch shall be supplied, delivered, handled and applied in accordance with AS 4454.
label | REFERENCE DOCUMENTS - 720.04(h), AS4454
label | INSPECTION / TEST METHOD - Visual Inspection
label | RECORD OF CONFORMITY - This ITP signed off
label | IP
label | RESPONSIBILITY - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.10 - Weed Control Mat and Erosion Control Mat
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - The Contractor shall supply and install jute or approved equivalent, biodegradable, fire retardant weed and erosion control mat as indicated on the Drawings or as specified. Weed Control Mat shall be minimum 700 grams per square metre and Erosion Control Mat shall be 300 grams per square metre. The surface of the mat shall permit water infiltration.
label | REFERENCE DOCUMENTS - 720.04(i)
label | INSPECTION / TEST METHOD - Visual Inspection
label | RECORD OF CONFORMITY - This ITP signed off
label | IP
label | RESPONSIBILITY - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.11 - Ripping
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - The Contractor shall make available each ripped planting area, individual tree planting and grassing area prior to mulching, planting or grassing. The Contractor shall not proceed until the Superintendent acknowledges requirements for ripping have been met. In areas where ripping is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
label | REFERENCE DOCUMENTS - 720.07 (b)
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - This ITP signed off
label | HP
label | RESPONSIBILITY - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.12 - Stockpilling
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - Excavated material which is deemed to be not suitable for use as fill material in accordance with the requirements of this Specification or excavated fill which is excess to fill requirements shall be stockpiled as spoil at locations approved by the Company’s Representative or otherwise removed from site.
label | REFERENCE DOCUMENTS - 720
label | INSPECTION / TEST METHOD - Site Inspection
label | RECORD OF CONFORMITY - Signed ITP
label | IP
label | RESPONSIBILITY - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.13 - Topsoil Finished Surface Levels
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - The Contractor shall make available each ripped, topsoiled and cultivated planting area, individual tree planting and grassing area prior to mulching, planting or grassing. The Contractor shall not proceed until the Superintendent acknowledges requirements for topsoiling and cultivation have been met. In areas where topsoiling or cultivation is not practicable, the Contractor shall submit alternative methods to achieve an equivalent result to the Superintendent for review.
label | REFERENCE DOCUMENTS - 720.07 (e)
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - This ITP signed off
label | HP
label | RESPONSIBILITY - Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.14 - Plant Installation
label | FREQUENCY - During Excavation
label | ACCEPTANCE CRITERIA - Dimensions and preperation of planting holes meet appropriate dimensions for plant size.
label | ○ Plants have been installed at correct depth and orientation.
label | REFERENCE DOCUMENTS - Drawings
label | INSPECTION / TEST METHOD - Visual inspection
label | RECORD OF CONFORMITY - This ITP signed off
label | IP
label | RESPONSIBILITY - Site Engineer / Site Foreman
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP