## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [6 empty] | Document # ITP-034
Revision : 1
Client: |  | Wyndham City Council |  | Construction Process: | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | K Rd Cliffs Project |  | Shared Path | Name: | Jarvis Gleeson | Name: |  |  | Name:
Contract No: |  | N400378 |  | Specifications:
|  |  |  | Structure / Component: | Signed : | J.GLEESON | Signed : |  |  | Signed :
|  |  |  | Location: | Date : | 2024-06-12 | Date : |  |  | Date :
Lot No: |  |  | Lot Details: |  |  |  |  | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Inspection / Test Method | Acceptance Criteria | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | Date
1 | Construction Works
1.01 | Site Preparation |  |  | Confirm site is cleard and graded as per design levels. | Surface graded to within +/- 10mm of design levels | Site Inspection |  |  | N/A
1.02 | Subgrade Preparation |  |  | Proof roll subgrade to identify sot spots. | No visible deflection under loaded vehichle | Site Inspection |  |  | N/A
1.04 | Bedding Layer Placement |  |  | Spread and compact 100mm of class 3 crushed rock | min. 89% standard compaction (AS 1289.5.4.1) | Site Inspection & Compaction testing |  |  | N/A
1.05 | Bedding Layer tolerances |  |  | verify thickness and width of bedding layer. | Depth = 100mm, Width 2500mm | Measurement & Survey |  |  | N/A
1.06 | Pavement Placement |  |  | pour gravel layer per specification. | 100mm Thickness | site inspection |  |  | N/A
1.07 | Surface Finish |  |  | Ensure correct levels, crossfalls and finish | Crossfall 2.5%, no visible defects | site inspection |  |  | N/A
1.08 | Final Inspection |  |  | Ensure compliance with all requirements | Footpath meets all design and quality requirements. | Final site walkover |  |  | N/A
COMMENTS |  | _______________________________________________________________________________________________________________________________________________________________ ________________________________________________________________________________________________________________________________________________________________
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: | [5 empty] | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent