## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | 1.34 - ITP-PV04 (SHARED PATH) | itp |  |  |  |  | 1.34 - ITP-PV04 (SHARED PATH)
section | 1 - Construction Works
checkpoint | 1.01 - Site Preparation
label | INSPECTION / TEST METHOD - Confirm site is cleard and graded as per design levels.
label | ACCEPTANCE CRITERIA - Surface graded to within +/- 10mm of design levels
label | RECORD - Site Inspection
date | Date Completed:
checkpoint | 1.02 - Subgrade Preparation
label | INSPECTION / TEST METHOD - Proof roll subgrade to identify sot spots.
label | ACCEPTANCE CRITERIA - No visible deflection under loaded vehichle
label | RECORD - Site Inspection
date | Date Completed:
checkpoint | 1.04 - Bedding Layer Placement
label | INSPECTION / TEST METHOD - Spread and compact 100mm of class 3 crushed rock
label | ACCEPTANCE CRITERIA - min. 89% standard compaction (AS 1289.5.4.1)
label | RECORD - Site Inspection & Compaction testing
date | Date Completed:
checkpoint | 1.05 - Bedding Layer tolerances
label | INSPECTION / TEST METHOD - verify thickness and width of bedding layer.
label | ACCEPTANCE CRITERIA - Depth = 100mm, Width 2500mm
label | RECORD - Measurement & Survey
date | Date Completed:
checkpoint | 1.06 - Pavement Placement
label | INSPECTION / TEST METHOD - pour gravel layer per specification.
label | ACCEPTANCE CRITERIA - 100mm Thickness
label | RECORD - site inspection
date | Date Completed:
checkpoint | 1.07 - Surface Finish
label | INSPECTION / TEST METHOD - Ensure correct levels, crossfalls and finish
label | ACCEPTANCE CRITERIA - Crossfall 2.5%, no visible defects
label | RECORD - site inspection
date | Date Completed:
checkpoint | 1.08 - Final Inspection
label | INSPECTION / TEST METHOD - Ensure compliance with all requirements
label | ACCEPTANCE CRITERIA - Footpath meets all design and quality requirements.
label | RECORD - Final site walkover
date | Date Completed:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
signoff | Sign ITP