## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
cd4160fa-ca9b-40c6-a0ef-aca8b3a37421 | checklist | DTM-ITP-001- Clearing and Grubbing Rev0 | itp | DTM-ITP-001- Clearing and Grubbing
978d3c0a-7747-4b99-83ca-ecbaeb8ba080 | section | 1 - Preliminary Works
f221dbc5-e143-4614-a874-4554378c07a3 | checkpoint | 1.1 - Check for correct documentation
b95c5f0c-11bb-52b8-8212-813958013045 | note | FREQUENCY: Prior to commencing any activity
7d5ddbac-fbf8-5407-951e-596fa573a7c8 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
65bbcb94-b151-5b75-9c6c-e5f13f1a1dc6 | note | – using the correct and complete set of drawings & all drawings are the latest revision
e74b2e37-1e25-51eb-8460-50e28e63059f | note | – Signed onto work pack
8de91b5a-0d0d-52cf-b60c-59e914fd3a39 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
ec18207d-e8a8-5b7a-b8dd-503cf9ebe8a8 | note | INSPECTION/TEST METHOD: Visual inspection
e839934b-0753-597a-8036-ef1e53ee90de | note | RECORD OF CONFORMITY: This ITP signed
4e5ae235-e8fa-513d-ac2f-3a67d50835e2 | note | HP*
3708c0ab-c870-5cf3-ba43-31c81b715047 | note | RESPONSIBILITY: Site Engineer
56cdb1c4-b025-5088-bab0-3fde9c3bfe5c | date | Date Completed:
485cf77c-9a7f-498b-a96c-1f88289e621c | checkpoint | 1.2 - Limits of work
6986b71f-10f9-54f4-ba48-75833b69e278 | note | FREQUENCY: Prior to pre commencment inspections
b0a446b7-0218-53a5-9ecd-0fe2241b93d0 | note | ACCEPTANCE CRITERIA: Clearing extents to be marked out as per drawings and ATC's/ RFI's.
741cd4f1-9d14-5a87-b4ae-440e65898768 | note | ○ Southern Outlet Highway is Road A0171, Link 5, CH 0.33 to CH 0.00.
8d59367b-1b74-58f9-aa79-4a6d517a38dd | note | ○ Davey Macquarie Couplet Main Road A1010, Link 5, CH 0.00 to CH 0.09.
dafe03b4-ea83-5376-bf7f-af0407061411 | note | ○ Davey Macquarie Couplet Main Road A1010, Link 10, CH 0.00 to CH 0.1 (approx.)
0e3b2984-c822-5138-991f-d734420bfdcb | note | REFERENCE DOCUMENTS: Cl 201.03
fd521529-655f-5dfa-9bb9-a25048f004a0 | note | INSPECTION/TEST METHOD: Visual inspection
8819e083-54f0-5acf-a92f-0622bf7eebbb | note | RECORD OF CONFORMITY: This ITP signed
9aace2a4-9a2e-5a85-a0ec-9b99f2c7034a | note | HP*
74b43e52-8f8d-5b71-a688-bd3a280e6fed | note | RESPONSIBILITY: Surveyor / Site Engineer / Foreman / Clearing Contractor
db282bd0-48fb-5114-bbd9-ef6fa91da74c | date | Date Completed:
2961961f-5fef-4f51-8943-fcb98c4d8a99 | checkpoint | 1.2 - Implementation of all measures and controls
d1b594a0-25e2-5e19-ba71-c53e42dc6be2 | note | FREQUENCY: Prior to commencing any activity
622630fc-0fa2-5d8a-ba35-eca41bf2df2a | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, including: PSP, EMP, TMP, SWMS & WP
483316a1-2d33-5271-9e9f-601953098e53 | note | REFERENCE DOCUMENTS: PMP, EMP, TMP, SWMS, Work Pack
ce3d923e-2652-59b7-83e0-cc1eec4f4dc0 | note | INSPECTION/TEST METHOD: Visual Inspection
b657f43c-adc2-5903-a1a4-d1832bdc43f7 | note | RECORD OF CONFORMITY: This ITP signed
a55ecc6e-2c88-5290-8f39-cc98916bc127 | note | HP*
ac66bc81-0d6e-5fa2-8a64-271cec937abf | note | RESPONSIBILITY: Site Engineer
9d26fd4d-7426-50f3-ab1f-dce4021aa70e | date | Date Completed:
4c336d60-d2ac-46e9-b845-a15843fc929f | checkpoint | 1.3 - Implementation of environmental measures and controls
87dda4f8-f8d5-57a6-bff3-eca8184cc618 | note | FREQUENCY: Prior to commencing any activity
c380380e-9686-5547-bb60-51ec3bfdf8a4 | note | ACCEPTANCE CRITERIA: Hold Point
68d7c897-9ed6-5daf-ad2d-32d51ba29215 | note | ○ EMP meets the requirements of the specification and all controls have been implemented as per approved EMP
72481796-685e-507a-99c7-533a9209f0e7 | note | REFERENCE DOCUMENTS: Project Spec Cl160.24 EMP
f4cd4980-7ba3-5189-abba-8166853b77da | note | INSPECTION/TEST METHOD: Verify
09fdd594-e413-57a8-90df-9f6a7e57c6f1 | note | RECORD OF CONFORMITY: This ITP signed
69a8138c-3d07-5fbe-9a62-5414570075c0 | note | HP*
2e582631-845e-5355-8dd6-237fdb21550a | note | RESPONSIBILITY: Site Engineer
01112224-bd0d-5660-b162-13ddebad2ccd | date | Date Completed:
29876525-1f8e-4b96-ba43-fa34e1528849 | checkpoint | 1.4 - Flora and Fauna
6d201ff0-31ce-5bba-82b0-ac109cacfbb8 | note | FREQUENCY: Prior
768182a0-d263-515e-87a6-004ac0d8c2eb | note | ACCEPTANCE CRITERIA: Hold Point
b6baab11-a1f3-52d9-871a-64dd8471c6cf | note | ○ Vegetation to be removed clearly marked and agreed. All removal consistent with contract drawings and permits.
d56bdb8d-be0f-5e29-864f-6109f6309b50 | note | REFERENCE DOCUMENTS: EMP Cl176.I1(c)
80961749-d9ae-5a3e-904f-bb21e2424a68 | note | INSPECTION/TEST METHOD: Verify
c254e81d-846c-52f9-a90a-865e56fb2bc5 | note | RECORD OF CONFORMITY: This ITP signed, Vegetation Removal and Clearing Permit
6666e963-96af-55dc-967e-33581ec66f46 | note | HP
0c8aa277-1f1d-54cc-a94c-c144b44412d4 | note | RESPONSIBILITY: Site Engineer / QAV
6688cf9c-28c0-52ca-b77c-b311608985bb | date | Date Completed:
cc49166c-f91d-4348-b875-c39c1adb8494 | signoff | AUTHORITY HOLDPOINT
7d3152d4-3bea-43c4-933d-9bbf5896589d | checkpoint | 1.5 - Protection of Existing Vegetation
2d264ab3-fd01-5487-b6a4-7ab60d913fc0 | note | FREQUENCY: Prior to comencement of any work
4eb5b136-d200-52c3-9f6c-82b0718ba33a | note | ACCEPTANCE CRITERIA: Prior to the commencement of any work, the Contractor and the QAV shall conduct a joint inspection of the site to identify vegetation to be retained and protected.
e46c452f-1e38-53fa-ba91-121421d7dda7 | note | ○ If directed by the QAV, existing trees, shrubs, native grasses and groundcovers and other areas of existing vegetation shall be protected by temporary fencing and incorporated into the works by the Contractor.
a4680e63-bed2-551b-ac47-b56eeb481e31 | note | REFERENCE DOCUMENTS: EMP Cl201.10,Cl160.24, 176.I1
886d51df-c7dd-5730-90eb-0aa0d1df30ef | note | INSPECTION/TEST METHOD: Visual inspection
4ac6c785-e3b2-5ec1-b07e-a5a5e1c9d48e | note | RECORD OF CONFORMITY: Vegetation Removal and Clearing Permit, Tree Protection Plan
f8e94bad-5992-5597-ba14-961f028d1835 | note | IP
29bd3e7a-66e8-5acf-a88c-56283241438d | note | RESPONSIBILITY: Site Engineer / QAV
6e0f9275-cbf8-5c84-b3d9-0f35c8cc2c37 | date | Date Completed:
632d5c5d-6ee8-424f-a136-35784a7aff7e | checkpoint | 1.6 - Cultrual Heritage
6e651572-afdc-5e9c-8573-43e023289f16 | note | FREQUENCY: Prior to removal of vegetation
4c30c36c-95fd-5c4c-b790-8e4d14cea67f | note | ACCEPTANCE CRITERIA: Hold Point
7568c301-9bc8-57e1-8548-c5e2ff08c7ef | note | ○ Nominated sites of archaelogical and / or heritage significance inspected on-site and clearly identified and protected as No-Go zones
8f5da0ed-aea7-5d96-ba36-444ed2354b54 | note | REFERENCE DOCUMENTS: EMP Cl176.J1(e)
3cfd59fa-295f-58f7-824d-4588055cbb06 | note | INSPECTION/TEST METHOD: Verify
22ad1479-77ac-5bbf-9337-bec46374c948 | note | RECORD OF CONFORMITY: Vegetation Removal and Clearing Permit, Tree Protection Plan
35b0fe92-ed26-5caa-95bb-c05ed4f9dd59 | note | HP
f5d0a6a8-87d1-5fcd-b233-1a85e8022573 | note | RESPONSIBILITY: Site Engineer / QAV
3a91009f-fcdf-5b63-b0b9-a92effc19bfa | date | Date Completed:
084ca863-f8ae-4ed2-984e-149419237db6 | signoff | AUTHORITY HOLDPOINT
cd370f2f-489b-453b-b982-deb672d58016 | checkpoint | 1.7 - Authorisation for works
36a3075a-7ad4-51ef-af56-03609344b910 | note | FREQUENCY: Prior to commencing works
fb3b54b8-71e3-59b4-b5d8-3679e0c7828d | note | ACCEPTANCE CRITERIA: Check that all relevant approvals (Access to 241 Davey, 326 Macquarie) have been granted including verification of the works area.
8e29ec26-dc8c-59d0-95c9-84118d80b584 | note | ○ Ensure work pack is reviewed & signed
68988739-b1ff-5959-b3b2-9dfdd09b1baa | note | REFERENCE DOCUMENTS: Work Pack 160.08
e2f3e977-804f-5f01-bc43-fc17b7586dfb | note | INSPECTION/TEST METHOD: Verify
14c63dc5-315f-5208-a91d-17b01abeaa6e | note | RECORD OF CONFORMITY: This ITP signed, Property Access Approval
78e054fc-418b-5d40-b724-3972ee32e47d | note | HP*
5611b064-7a63-5466-9202-4c5bd47f3072 | note | RESPONSIBILITY: Site Engineer
11105919-1f33-541c-8ac9-bbaeb6797e7d | date | Date Completed:
b263f5cf-4f17-494e-b51e-6ce510fa3e8b | checkpoint | 1.8 - Utilities
db61a8cf-77a4-544f-ab50-2b7d82468a15 | note | FREQUENCY: Prior to commencing works
b3bb7563-761e-5939-9af0-c4720ace3635 | note | ACCEPTANCE CRITERIA: DBYD - locate and mark all existing services and confirm clearance from proposed work
1d8c708a-7a7f-553c-aa4c-d630e5890074 | note | REFERENCE DOCUMENTS: DBYD Records, Plan Mark-Ups, Excavation Permit
9742321b-ec0a-5d37-8374-db933beb50f6 | note | INSPECTION/TEST METHOD: Verify
f1000026-16aa-5393-8910-95be20fa72a0 | note | RECORD OF CONFORMITY: This ITP signed
a385f50f-ae0c-5b03-ac1c-1235b819d039 | note | IP
caf65a5d-d16e-593e-b1ab-5354174010bb | note | RESPONSIBILITY: Site Engineer
a53d7a95-6a9c-5403-9202-880c83cbaa06 | date | Date Completed:
35d9a4b5-99b5-427b-b648-00ba29e210b0 | checkpoint | 1.9 - Traffic Management
4f8f2031-f747-5de6-a207-0b98f72fa2b5 | note | FREQUENCY: Prior to commencing works
6e92de9e-223d-5029-adee-78d80c4a1f20 | note | ACCEPTANCE CRITERIA: Consider the requirements for traffic management, ensuring all works comply with required TMS, TMP and TGS. Where localised speed reductions are required they shall be at the discretion of the QAV. TGS shall be submitted and approved by the Superintendent.
5f036104-e406-5f90-a630-7f70a5c18b8c | note | REFERENCE DOCUMENTS: TMS, TGS, TMP, 160.07
f6d0534b-ef37-5413-91a6-cc1a59a91203 | note | INSPECTION/TEST METHOD: Verify
4c1ccd6b-22e2-54c0-988e-b0845e902e23 | note | RECORD OF CONFORMITY: This ITP signed
5521c832-8b66-54b9-aa1e-28a75edd2097 | note | IP
e1a95a07-9a49-53de-a511-71512b6549fc | note | RESPONSIBILITY: Site Engineer
145d7c15-0390-5793-ad0b-874974fe4ca4 | date | Date Completed:
e75dcb2a-eff8-4502-9bd9-1c4c9c48064b | section | 2 - Clear & Grub
7b3e8eaa-2984-4daf-9625-fcb2227531df | checkpoint | 2.1 - Clear and grub trees and vegetation
50186ea9-b68d-5954-8064-716aa7df6b73 | note | FREQUENCY: Each Lot
fdd95a45-b152-5755-8866-d27b4c95f642 | note | ACCEPTANCE CRITERIA: Area within specified limits cleared of all vegetation, refuse and obstructions down to natural surface. Trees brought down in a manner so as to avoid danger to personnel and traffic as well as damage to other trees, structures and property.
4b0a80d2-f9e7-551f-a25d-4ab78b92af91 | note | REFERENCE DOCUMENTS: Cl201.04
0e71f4f6-4d4b-5d47-a6b5-2968ac2e7554 | note | INSPECTION/TEST METHOD: Visual Inspection
a07841ef-527b-566e-ad41-314a557d1877 | note | RECORD OF CONFORMITY: This ITP signed
e04997f7-5156-5e72-9217-75db12823421 | note | IP
1fb784be-af17-5b63-950d-f406fbf0df85 | note | RESPONSIBILITY: Site Engineer
8de3606e-462f-54c1-892e-a6baa3b38c59 | date | Date Completed:
0c70dc08-416c-402e-9b0d-6390a2b081be | checkpoint | 2.2 - Clear and grub trees and vegetation
9f1575bf-8394-5bc9-b565-f7413de4d6b6 | note | FREQUENCY: Each Lot
429f80ac-4467-5202-a587-ea86216e2e62 | note | ACCEPTANCE CRITERIA: In areas where excavation is to occur: all vegetation, refuse and obstructions totally grubbed or grubbed > 0.3m below subgrade and batters (whichever is the lesser treatment)
c4b0f60c-ef0f-580a-a35f-478cef69d5c4 | note | REFERENCE DOCUMENTS: Cl201.05
51a4a279-8076-5c7b-888a-6eb82301c676 | note | INSPECTION/TEST METHOD: Visual inspection
72d28079-259c-5101-924d-a4a6fafd39a7 | note | RECORD OF CONFORMITY: This ITP signed
d5d4d87e-deec-5595-ae64-8aabbd47354a | note | IP
0363a4b8-9e4c-5b08-8b9a-c22c546ed2a0 | note | RESPONSIBILITY: Site Engineer
6f2c79ce-9b79-5b84-aef1-09b9e2e5387c | date | Date Completed:
3fea4e0e-64e0-4dd8-8ebd-3243cf88c6c3 | checkpoint | 2.3 - Clear and grub trees and vegetation (embankment areas)
871b09e6-b563-5344-9466-86e9049f3f9d | note | FREQUENCY: Each Lot
4abdea04-bafc-5aeb-9d07-2d58eb933b02 | note | ACCEPTANCE CRITERIA: In areas to be covered by embankments < 1.0m in height: all vegetation, refuse and obstructions grubbed > 0.3m below stripped surface OR > 0.6m below subgrade level (whichever is the lesser treatment)
1fb1d363-cd1a-5d44-a20d-410e29e6551b | note | ○ In areas to be covered by embankments > 1.0m in height: foundations may remian if located or cut off not more than 0.4m above natural surface but not less than 1.0m below subgrade
36fe859e-d562-5171-8842-c3ef83cffda9 | note | REFERENCE DOCUMENTS: Cl201.05
347372dd-857a-5305-a489-a82cc7a3ccf5 | note | INSPECTION/TEST METHOD: Visual inspection
36349761-d9bc-5976-9713-2f5a00dddaee | note | RECORD OF CONFORMITY: This ITP signed
d12603bf-3aef-5728-abb9-04ae5f94b3bb | note | IP
826bcc99-4c54-5121-abbb-cf208e26d95e | note | RESPONSIBILITY: Site Engineer
70aa8aa3-27d0-569d-a98f-9dd9e2f8c819 | date | Date Completed:
e4492093-5490-4bf5-859d-5865dae265ab | checkpoint | 2.4 - Clear and grub trees and vegetation at culvert sites
86a86409-02e9-5239-9587-0ef9571bdc39 | note | FREQUENCY: Each Lot
fc162fa0-733c-5544-ba01-4f443cd00570 | note | ACCEPTANCE CRITERIA: Clear and grub trees and stumps within 10m of any proposed bridge or culvert having a waterway area > 6m2 (unless otherwise shown on drawings)
5402f6e0-43c7-5089-9b94-8a0617a183d2 | note | REFERENCE DOCUMENTS: Cl201.06
c51e21a3-43a7-5bbc-a485-49d8103291f2 | note | INSPECTION/TEST METHOD: Verify
c7783ec9-28ad-56e6-bbb5-1ea14270ca92 | note | RECORD OF CONFORMITY: This ITP signed
bfff7fde-82d1-5ac1-b1c3-7979ac7f4ef2 | note | IP
fe634f17-c416-5434-8144-52aa5fe04379 | note | RESPONSIBILITY: Site Engineer
6ff5f44b-db46-5961-adc0-b0326d95bcba | date | Date Completed:
7238c519-32d0-44cb-b878-03d93b64ae75 | checkpoint | 2.5 - Backfill holes
9d70a48c-e269-59dd-8e76-c7ca935e7fb2 | note | FREQUENCY: After clearing
6c7b5e58-0a6b-5502-8c20-3d8a8eb66bca | note | ACCEPTANCE CRITERIA: Any remnants of pits shall be backfilled with similar material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
2405bb84-105d-562a-b305-3d027d77b53b | note | REFERENCE DOCUMENTS: Work Pack Cl201.05
375985ca-7351-5e79-8975-4a65964c7456 | note | INSPECTION/TEST METHOD: Verify
a11d151d-fcb2-56d0-84cc-0e56a6b81321 | note | RECORD OF CONFORMITY: This ITP signed
6113525d-a67d-52d4-904e-72e6de7205b5 | note | TP
96d532c1-fb1d-5475-b2cd-4bdde76b94ae | note | RESPONSIBILITY: Site Engineer
3f3d4923-203c-5928-b904-059d3c47df76 | date | Date Completed:
2fb30172-3a6a-4bde-8553-4ce009c86671 | checkpoint | 2.6 - Dispose of Trees and vegetation
eed877d1-f64c-56fc-b17b-f799ab710708 | note | FREQUENCY: After clearing
a410877f-4afc-51ba-89a3-bb96c4f9ab2e | note | ACCEPTANCE CRITERIA: All vegetation within clearing limits shall be removed from site. Weeds not to be mulched and disposed of appropriately.
945b3756-20bc-5603-959c-de2aac83f47d | note | REFERENCE DOCUMENTS: Cl201.07
fe801138-cd85-503c-9c4a-7aeffc4d6f88 | note | INSPECTION/TEST METHOD: Verify
9b4cc6ec-a2b4-502f-b75b-3502b6b6f8c7 | note | RECORD OF CONFORMITY: This ITP signed
bee1236d-395f-5e33-b326-5abecacc03a3 | note | IP
7af4b583-d0e0-53bf-9b39-ba7ea70fc531 | note | RESPONSIBILITY: Site Engineer
7d2501bf-115b-543e-87c7-53cd986e7e86 | date | Date Completed:
1dac20ce-7d06-40b7-81e7-998ca642f827 | checkpoint | 2.7 - Damage to Fencing
98b70d25-b997-56df-ad11-b88d2f4f0d05 | note | FREQUENCY: During Clearing
c4093e29-5214-5216-ae3f-9f4e9d14718f | note | ACCEPTANCE CRITERIA: Immediately repair any damage to fences to a condition at least equal to that before damage
c93ee17f-8c34-512e-b4e9-a2bce4dc8e4a | note | REFERENCE DOCUMENTS:
7f21f095-b9f6-5dc3-8d5c-019cc5aa86b2 | note | INSPECTION/TEST METHOD: Verify
f93c19e4-0427-5a3b-ba41-38c0c42c578f | note | RECORD OF CONFORMITY: This ITP signed
92c25d65-4cf3-574b-b562-ed02251f1281 | note | IP
757cadaa-1d83-52f2-a79d-de725a5da008 | note | RESPONSIBILITY: Site Engineer
0a1320b5-a237-523f-987d-41c97d79a9d3 | date | Date Completed:
0cc48126-9a7f-44f7-8948-9daf8e9d31f4 | checkpoint | 2.8 - Salvage of Vegetation
c4e5ae7b-9cd0-5526-b180-181c64792695 | note | FREQUENCY: During Clearing
33337043-e448-519a-a7b5-09e81fe84368 | note | ACCEPTANCE CRITERIA: Co-ordinating works with activities involving the salvage of plants and the collection of cuttings and available seed from areas of native vegetation on the site.
ea752a98-2893-54cc-ae5f-c5c1710326a2 | note | REFERENCE DOCUMENTS:
4235e68d-d813-5542-8848-aaad66ac5a34 | note | INSPECTION/TEST METHOD: Verify
96b6ca11-d379-5431-92df-fda6caca8d26 | note | RECORD OF CONFORMITY: This ITP signed
78c9f3d2-f55a-577c-a408-3e757735b698 | note | IP
d9414b16-d038-55f8-bb95-8fc25afc98b6 | note | RESPONSIBILITY: Site Engineer
7b68940d-888f-5cec-bd79-628f7fce2b6a | date | Date Completed:
4b3ff4e1-ec59-44ea-990c-1779139eb4bf | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ed646561-6cc6-52f1-86c3-8f5f8defd656 | textbox | Fulton Hogan - Print Name:
1564af1a-5ea5-5f2a-a445-60f29007d5d1 | textbox | Fulton Hogan - Position:
6b45587f-aa7b-5edf-baac-d8b136e3fbe1 | date | Work Completed On:
aa8f376b-2657-4dee-aa1b-40042ea2a8ed | signoff | Add Signature
21401525-0012-46e5-a968-0d0b2a27afd9 | checklist | DTM-ITP-003- Earthworks Demolition Rev0 | itp | DTM-ITP-003- Earthworks Demolition
35832db6-d0bb-4f06-9f0e-b770577bfb82 | section | 1 - Preliminary Works
87a550e6-0823-455c-89c2-8025f6dfee9e | checkpoint | 1.1 Check for correct documentation
f0eb97b3-8884-596f-abaa-8e5b31c89424 | note | FREQUENCY: Prior to commencing any activity
7bde79dc-68f9-553f-9cdf-02f244d9539d | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
b267049b-4f74-5b2a-9c89-b8d00a2189c0 | note | – using the correct and complete set of drawings
d522b19d-258e-5e07-899f-329031c6f2bd | note | – all drawings are the latest revision
94ce975c-6385-5712-a5d2-1fb6cc36f580 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
1ecbc5e7-8191-5398-a2b1-3b7962442904 | note | INSPECTION/TEST METHOD: Visual inspection
a5e9656f-e3a3-5a44-9234-49e0d75b552f | note | RECORD OF CONFORMITY: This ITP signed off
3ba874b5-de5d-5e5a-98e1-9504da249f5f | note | HP*
3491bcb4-f82a-5df7-b394-f04cb5b819b3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
0a4be045-86ab-500f-90a7-fcec3db23047 | date | Date Completed:
032acfb9-6dda-4e9c-ad6f-f84cc679b8f9 | checkpoint | 1.2 Implementation of all measures and controls
d9b7d730-67a0-52d9-8ba8-8cefb94abd0c | note | FREQUENCY: Prior to commencing any activity
a82ea240-8562-5539-b354-6bb766749e3e | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, JSEA, SWMS & Work Pack
d918cc24-2253-517a-99eb-8fa99dc63b2f | note | REFERENCE DOCUMENTS: PMP, EMP, TMP, JSEA, SWMS, Work Pack
75ff653f-05fa-55e3-848d-e1aedd909702 | note | INSPECTION/TEST METHOD: Visual Inspection
b6df93bb-63bb-5dc2-af80-bd1716fa4026 | note | RECORD OF CONFORMITY: This ITP signed off
408bb220-1a1a-5a27-89cb-7b70c47334de | note | HP*
e499f18c-a063-5160-a3a4-d1cc0bcb364d | note | RESPONSIBILITY: Site Engineer / Site Foreman
25863c8f-39b9-556c-9050-76f58ae23774 | date | Date Completed:
3f1f832a-0615-469e-99ef-e735ff17c243 | section | 2 - Construction Works
ecf8d1d9-4189-4cc7-a17e-d01a5f229498 | checkpoint | 2.1 Survey Set-Out
fc9dffbd-3174-552c-b711-d84a9ae21816 | note | FREQUENCY: Prior to commencement of excavation
77546868-73df-59de-971c-813bc2f7776a | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
4e97442e-f261-5375-83a3-de1af1ce7fbd | note | REFERENCE DOCUMENTS: Work Procedure
f3102c44-38f5-51f2-9cce-bb8a5cd55897 | note | INSPECTION/TEST METHOD: Verify
8d576cb8-adff-5460-819a-65845488b1c0 | note | RECORD OF CONFORMITY: This ITP signed off
c3360caa-8efc-52ec-8d40-01de15685fd8 | note | IP
393a68e8-dae2-5138-8f38-30f1e9499771 | note | RESPONSIBILITY: Site Engineer/ Surveyor
c64eeaa5-60f0-5ef3-a37f-4f6340830527 | date | Date Completed:
799d83a3-4f60-4da3-a129-c9650fedeb28 | checkpoint | 2.2 Excavation Permit
03eb3bad-7ee9-50b3-b054-d02a81a33a55 | note | FREQUENCY: Each lot
05b20a37-81a5-5cf8-9b91-985e561ce0e5 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
3aeecd28-b75a-5483-84db-bd898de9d456 | note | ○ Plant and equipment shall be appropriate for the task.
d88258eb-17bc-57de-a38a-45b790172f74 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
33018481-990d-53f4-bc09-839027b492cd | note | REFERENCE DOCUMENTS: Excavation permit
c0f8ad95-80c9-56c5-a750-a969cc6f066e | note | INSPECTION/TEST METHOD: Verify
5dafb385-edab-5d89-9c4a-14050ad9a859 | note | RECORD OF CONFORMITY: This ITP Signed Off
17f183a9-6bb2-5fc6-9d4d-898311581265 | note | HP*
caa09739-1063-5027-8877-e1fd60810f81 | note | RESPONSIBILITY: Site Engineer
cd9def00-e488-5dce-b086-8294d98cbf22 | date | Date Completed:
01e0efe8-6555-4cfa-92fc-46f32da51b2f | checkpoint | 2.3 Material Categorisation
2e2a43ac-dda0-5624-9ebd-6848c33f50b0 | note | FREQUENCY: Each lot
f66df72f-eaa7-55c3-a4f8-c1d1bcaa2692 | note | ACCEPTANCE CRITERIA: HOLD POINT
8e9c4190-083b-5d8c-b240-29abbc4a92a5 | note | ○ Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
102ad923-cc7b-5f18-b693-32a5841f0d23 | note | REFERENCE DOCUMENTS: 204.06(c)
bf2fe195-4921-572f-8140-c77901b61772 | note | INSPECTION/TEST METHOD: Verify
2a43679b-e731-5176-93b3-5dd905e9305f | note | RECORD OF CONFORMITY: This ITP Signed Off
e77b0694-6eb8-55dd-8508-c6848e4971ec | note | HP
719594ee-7180-545b-aaac-1febda669b93 | note | RESPONSIBILITY: Site Engineer/ Superintendent
3003c5aa-8f02-5f51-a752-630c9cf8f867 | date | Date Completed:
112364dd-e9fd-4bcb-8993-955052ee4a4e | signoff | AUTHORITY HOLDPOINT
96b08bd4-bdac-408a-a1f7-45c225d32790 | checkpoint | 2.4 Stripping of Topsoil
3f4ef5b5-67e5-5e33-8d7b-586726814c51 | note | FREQUENCY: Each lot
08a89dc1-0e50-5da8-95de-ef0c137739bd | note | ACCEPTANCE CRITERIA: Topsoil stripped to full width of the formation and placed in approved stockpile location. Stockpile shaped to shed water and stripped surfaces graded to be self draining. Topsoil shall not be removed from site unless approved by the superintendent.
6d71dd34-8267-5d72-9939-ef4c0eddd28e | note | REFERENCE DOCUMENTS: 204.05
7e7f9716-06e9-5751-836e-9100dc68ee5f | note | INSPECTION/TEST METHOD: Visual inspection
45faca66-4638-5ed4-ac6d-a7bf4b16fa80 | note | RECORD OF CONFORMITY: This ITP Signed Off
39a5732f-1070-5922-9a22-59783bafaa49 | note | IP
fa042f8e-bf1c-5596-ad26-9e30cb195214 | note | RESPONSIBILITY: Site Engineer
40d0c638-78f3-5b9a-951e-2930651098e6 | date | Date Completed:
e85876a2-2a79-4e3f-a47f-468eb41f12d0 | checkpoint | 2.5 Type A Material
c6385ed8-e19a-5063-bde7-dc62970bf13a | note | FREQUENCY: Prior to Commencing
486f9b1a-7cbe-5f77-843f-cf17f3891565 | note | ACCEPTANCE CRITERIA: Type A material shall comply with the requirements of Table 204.041 and shall be free of topsoil, deleterious and/or perishable matter.
14364c38-6933-5ce8-bf19-0a09eec74b08 | note | ○ HOLD POINT
0adca298-cf97-5c83-a2fa-d17a3c4ed838 | note | ○ Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent.
414e8c1b-e78d-5a9d-b224-880ac1b5d245 | note | REFERENCE DOCUMENTS: 204.04(b)
3bec5ae9-ecd0-550c-b528-3412cf682347 | note | INSPECTION/TEST METHOD: Document Review
18f95cb7-f662-5205-b412-59f76a60b16c | note | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation, Signed ITP/ records
0dbe48c2-e32a-5dd9-8498-807147e38d1b | note | HP
9556e1d4-47c2-581a-be78-7a4fb7053085 | note | RESPONSIBILITY: Site Engineer/ Superintendent
fa5b24e3-f84d-5e85-b64f-266c2f54be93 | date | Date Completed:
8d12b47e-76a7-40f8-883d-5e8cfddb8078 | signoff | AUTHORITY HOLDPOINT
3a3b3349-32b3-4155-a2d3-57ec1a873ac3 | checkpoint | 2.5 Type B Material
b6de7786-2ebb-59e3-bdd2-88b08901c7fc | note | FREQUENCY: Each Lot
2d7717db-2730-56f6-9f51-e768f533654a | note | ACCEPTANCE CRITERIA: Type B material shall be free of topsoil, deleterious and/or perishable matter. Type B shall have a minimum assigned CBR >5% and Assigned Percent Swell < 2.5%. Materials with swell greater than 2.5% can only be used as Type B material if approved by the superintendent.
de4c311e-4fad-5813-b20a-d43eaeac8a99 | note | REFERENCE DOCUMENTS: 204.04(c)
ebb5d02e-b628-5f42-930e-7d8d35bf6e99 | note | INSPECTION/TEST METHOD: Test Point
4f70ade5-0698-530e-8b70-ad08da4fab16 | note | RECORD OF CONFORMITY: Test Reports
c71bb65d-9aac-50fd-a36b-01f64f4c6ee5 | note | IP
1458fd14-f723-5c3b-b46f-e4c74f217a23 | note | RESPONSIBILITY: Site Engineer / Superintendent
18cbd72d-7a3b-5440-af0b-695ce57f08e2 | date | Date Completed:
81ed21a7-f55a-4363-b766-4a08a7efa18e | checkpoint | 2.6 Acceptance of Rock Subgrade (when applicable)
db11a445-a0be-5af9-b5b4-8184e3dc76b9 | note | FREQUENCY: Prior construction of the regulating layer
e22ce874-a3d7-5210-8e47-53405c59624a | note | ACCEPTANCE CRITERIA: HOLD POINT
1f4d7da2-f230-55e4-8338-461948c4454e | note | ○ Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
f2d75627-e524-5667-bac6-e243cf368281 | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
72e91fa5-48d8-598d-b469-ac303dae96b8 | note | REFERENCE DOCUMENTS: 204.06(f)
fac5d2db-1cae-527c-83a4-a47c62b36c21 | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
2d667551-9b67-5e52-939a-910a4f732a0b | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
61d3dceb-6934-51a1-ac6c-c4b515315204 | note | HP
09119aea-7373-5cbe-a486-b184ba43328b | note | RESPONSIBILITY: Site Engineer/ Superintendent
4a91920e-4536-5ac2-8f0b-650fcbc5892e | date | Date Completed:
68e5c353-724f-405c-9f5a-adaabdfa86e8 | signoff | AUTHORITY HOLDPOINT
520847a1-7c23-490b-97a4-6df72926d306 | checkpoint | 2.7 Unsuitable Material
323daa7c-a5ac-5900-8e6f-e6ec0fb7c1a7 | note | FREQUENCY: Each Lot
a2ecb495-4483-5a2e-957f-71db8672a6f1 | note | ACCEPTANCE CRITERIA: HOLD POINT
c09e2b2d-1596-57d1-b740-1d9cbd7c05dd | note | ○ Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
548698ef-8757-54ef-87b5-421884ef1556 | note | REFERENCE DOCUMENTS: 204.07(d)
20aaa280-b18c-515b-bb26-e69b506acbbc | note | INSPECTION/TEST METHOD: Visual Inspection
81791d72-cb0d-54c9-b5a3-6a287116a44a | note | RECORD OF CONFORMITY: This ITP Signed Off, Work Procedure
99f652d2-38cf-5453-9531-48fcd6fe6491 | note | HP
9b104fb8-17ab-5f65-ad13-24b3a76b19f3 | note | RESPONSIBILITY: Site Engineer/ Superintendent
f6ccb8a5-6d8c-5dda-bfc7-ab1af2764bbc | date | Date Completed:
348cbeab-bae8-463b-8676-8d6a00709b19 | signoff | AUTHORITY HOLDPOINT
c63d6ada-d230-4e34-a13e-bd4a2d0278c4 | checkpoint | 2.8 Groundwater
48d3b861-9fbc-5f42-aedd-2530ff07913b | note | FREQUENCY: Each Lot
ba66d295-176e-5106-8aff-817ba6356966 | note | ACCEPTANCE CRITERIA: HOLD POINT
6d6ee4d2-1332-53db-a2dc-4632119ffceb | note | ○ Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review. The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
d831d6a0-810a-5c2c-a519-2823043c86c7 | note | REFERENCE DOCUMENTS: 204.06 (h)
0d25939a-de83-58f8-b59b-63fa53ad254f | note | INSPECTION/TEST METHOD: Visual inspection
69a2eb79-73f9-5cbb-87c1-21251d6b783d | note | RECORD OF CONFORMITY: This ITP signed off, Work Procedure
84bea4da-5652-58b3-b50d-b8377048b3ab | note | HP
cdff3982-fd09-56b1-960a-68de902c5242 | note | RESPONSIBILITY: Site Engineer/ Superintendent
8540a718-eca2-59bf-a535-996c9d0e0bb7 | date | Date Completed:
f2843205-91b0-41e8-b4f7-44d4aef2e735 | signoff | AUTHORITY HOLDPOINT
529633bb-7275-4f85-b94f-4a96b82225bd | checkpoint | 2.9 Trimming and Level conformity
4ee68268-b510-5d45-b984-811e1bdcda75 | note | FREQUENCY: Each Lot
5cd83eca-144c-5154-8c2d-78fdeb22fc05 | note | ACCEPTANCE CRITERIA: The level at any point on the subgrade shall not lie more than 20 mm below a 3 m straightedge laid in any direction, except across a crown and water shall not pond at any point.
95f78799-1a3f-57da-9a65-5f3696188661 | note | ○ Level tolerances:
b917797b-c3fc-51d5-a5e2-02cc75a9a8e9 | note | – Range x = +5, -15mm
5d207bd9-0148-5446-bed9-621d68e0d702 | note | – Max S = 12 mm
59ef12d0-833d-5c68-a6d0-a0947c31495c | note | ○ 80 measurements per lot (Scale A)
b63ccf20-6014-5a75-9884-9892740cb4f3 | note | – Range x = +5, -25mm
8d4298a9-283e-5262-8f7d-1565cf406271 | note | – Max S = 15 mm
5ef8f02e-ff2f-523b-a2e1-877dfa697eac | note | ○ 40 measurements per lot (Scale B)
b2f023de-ee30-5292-9c70-4e4fe4d97d67 | note | REFERENCE DOCUMENTS: 204.03(f)(g)(h)
bdd35211-3e11-550d-87d9-b60ad9f78bd4 | note | INSPECTION/TEST METHOD: Survey Report
f03d3755-7c5d-586a-ab69-a45bad93d1ca | note | RECORD OF CONFORMITY: Survey Record
c0fe898f-30c1-51cd-bc79-18943c7c4031 | note | SCP
11106bc9-a8bd-55c0-afea-fcf70dc7671c | note | RESPONSIBILITY: Site Engineer/ Surveyor
af574adb-b15b-5696-a94d-72f8e9cd9e70 | date | Date Completed:
0f86b799-5844-47a6-8f4e-b1070736e7dd | section | 3 - Testing
bc9cc799-b643-41c8-9c20-975c243250ec | checkpoint | 3.1 Proof Rolling
ddaba18d-d39f-5410-a4f6-aee6a6cefeeb | note | FREQUENCY: Each Lot
57b502ae-556d-5308-98b9-2222bcb83eaf | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173, before proceeding to subbase construction.
68753619-4725-59cf-a1dd-c590823aa400 | note | ○ The Contractor shall submit a test rolling procedure to the Superintendent including the method of preparing an area for test rolling, the extent of test rolling and a requirement to provide not less than 24 hours notice of the location and commencement time for the test rolling to the Superintendent.
cd64ca2b-49d5-50c3-adab-81adf5d36d66 | note | REFERENCE DOCUMENTS: 173.03, 204.12
db4fc166-42d7-5d70-9306-f02162f10c46 | note | INSPECTION/TEST METHOD: Visual Inspection
bfe32bb9-084e-5c7d-880f-9046f3cf4fa0 | note | RECORD OF CONFORMITY: This ITP signed off
f17fc5ac-e72a-5422-807e-18c8dfaf44bf | note | HP* WP
a79c5175-5624-58b8-9fff-134715fa6aae | note | RESPONSIBILITY: Site Engineer/ QAV
dcb079dd-777b-59e0-b082-2d8debdba3d6 | date | Date Completed:
3198912b-0f7b-4825-b939-c3982114c903 | signoff | AUTHORITY HOLDPOINT
13e1b6d0-9e53-48e9-8e9b-1f6f5005eddd | checkpoint | 3.2 Compaction Testing
abc22811-c840-5992-b948-9ae3df6fe68e | note | FREQUENCY: Each Lot
3bc05732-42e1-533e-b5b7-8542046feb10 | note | ACCEPTANCE CRITERIA: Ripped and re-compacted material below Cut Floor Level = minimum compaction 99% MDD.
9ec8cb80-5601-5d82-b310-d3ed9e798577 | note | ○ Type B Material placed within 400 mm of top of Type B Material = minimum compaction 99% MDD.
10b66637-9338-5571-a90b-b907fb6cbc95 | note | ○ Type B material 400mm below the top of Type B material and Top 150mm of where fill is to be constructed = minimum compaction 97% MDD.
17c76ed2-2355-58be-b819-26960a36b8b8 | note | REFERENCE DOCUMENTS: Table 204.131
d1c596e3-d5f1-5be9-bb49-7103663b4fad | note | INSPECTION/TEST METHOD: Test Point
2fe9e162-11c2-515e-a885-0237346cf665 | note | RECORD OF CONFORMITY: Test Records, Lot Register
0d401493-e3dc-5d24-8e3e-db5a45584a08 | note | TP
d12ba0f2-dc20-5804-9b58-0cf190840ab8 | note | RESPONSIBILITY: Site Engineer
5307e531-53aa-582c-acb4-cf9e33d6ada1 | date | Date Completed:
322d4055-e4d5-4161-8f24-fea433470604 | checkpoint | 3.3 Materials Property Testing
654718eb-72fb-5ba3-bf09-696db7c57dcc | note | FREQUENCY: Each Lot
ff0045d9-c52e-5807-9d19-e190ce2d27e0 | note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Frequency of Testing and Material Properties Testing Requirements.
52aca5c9-3c21-5ef4-9e14-f7d43aa52643 | note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
fa1b8d13-3232-5b31-8058-1edda881493f | note | REFERENCE DOCUMENTS: Tables 204.141, 204.142, 204.161
84f993c5-4f09-51f8-bf92-7d863e18d7aa | note | INSPECTION/TEST METHOD: Verify
25e52858-1eae-51e1-80c6-0bbbb4d9fa0e | note | RECORD OF CONFORMITY: This ITP Signed, Test Records
b8cd9b0e-4a01-5a84-835f-5dd297ad718c | note | TP
2730d33c-f14b-50c2-9af1-fd92b2659ce9 | note | RESPONSIBILITY: Site Engineer
bc563173-1b81-5226-a628-d8f4db97854f | date | Date Completed:
39ac548f-3700-4231-beba-9becf60e8c94 | checkpoint | Final Inspection
1824ad7b-2037-5e72-923e-c95f1c4c7009 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
98480b67-069c-5523-b958-20807d491c24 | textbox | Print Name:
c6dac621-e790-528a-a936-7af5f6ae13a3 | textbox | Position:
71550dec-7b12-55ef-a6cb-542898c0718f | date | Work Completed On:
fce7aed6-771a-47b2-bdb4-e0a52c44e5aa | signoff | Add Signature
a0d1a2b7-9d17-43a3-b4e5-4a179b167459 | checklist | DTM-ITP-004- Service Relocations - Telstra and NBN Rev1 | itp | DTM-ITP-004- Service Relocations - Telstra and NBN
e2929edf-a48c-4495-a490-5e51752822b5 | section | 1 - Preliminary Works
a8e3ef38-a922-4d7e-b6b9-305edcd9ef5c | checkpoint | 1.1 - Check for correct documentation
8739de85-a719-53ad-ae88-fe3abe7991fb | note | FREQUENCY: Prior to commencing any activity
7b2706f3-eed3-520b-bf03-cd4bcddbeb26 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
cfab979a-0043-59b1-8013-01d8750c4906 | note | – using the correct and complete set of drawings
aef4afea-cc0f-5722-868c-25b67e3e11a3 | note | – all drawings are the latest revision
4f64324d-dc54-512a-9c12-b2a1f19a461e | note | REFERENCE DOCUMENTS: Drawings and drawing registers
8e074d9b-b15d-534a-affd-2f213516bb5b | note | INSPECTION/TEST METHOD: Visual inspection
903a8c05-cf0c-54e9-9ef9-1e4eb546e1c9 | note | RECORD OF CONFORMITY: This ITP signed off
a4b19705-7fcc-56c5-93c9-a26eee34c696 | note | HP*
f21b82c4-3551-5cc8-8aec-238ddd4fddb2 | note | RESPONSIBILITY: Fulton Hogan Engineer
7774f7ef-2a25-59e0-aebb-4bd0eb2530f0 | date | Date Completed:
fba94add-43b2-43ab-8477-fc2ad1a7d90c | checkpoint | 1.2 - Implementation of all measures and controls
c6f7b3fa-bed3-5e87-befb-03efdbff5439 | note | FREQUENCY: Prior to commencing any activity
4b5a6131-2fba-5860-99a6-a8086f6e3f61 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP/TGS, JSEA, SWMS & WP
e346acfd-a32d-5896-bdb9-06ff31850176 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
1e33b699-e9d5-5ce8-b362-df46f8693411 | note | INSPECTION/TEST METHOD: Visual Inspection
050c4651-7f1a-5c03-99e1-0a305c093b86 | note | RECORD OF CONFORMITY: This ITP signed off
b22980e5-5ae6-5a5d-9538-6ec97c21a301 | note | HP*
92b5eed7-be37-5d22-9127-44154718d429 | note | RESPONSIBILITY: Fulton Hogan Engineer
b9df3831-dd87-579d-8fad-74898d49a90c | date | Date Completed:
bc5fb38a-c27f-4962-bf53-fc06c9f6dd4d | checkpoint | 1.3 - Scheduling trenching works with Telstra/NBN contractor
3a44dbe7-c764-5a16-8b53-b241a6ca4771 | note | FREQUENCY: Prior to commencing works
218e374c-b8e8-508d-8b2b-30af758b3bc1 | note | ACCEPTANCE CRITERIA: Provide Telstra with an accurate date for when the trenches will be available for cable installation and when final ground levels will be established
d289c897-3936-5562-bc2d-734dc675e5e3 | note | REFERENCE DOCUMENTS: APPENDIX L
aa568454-9bdf-5272-b238-99073affd167 | note | INSPECTION/TEST METHOD: Verify
21bc649c-6936-5274-8d7e-c4ce392d8a75 | note | RECORD OF CONFORMITY: Service Installation Programme
d74c72e0-c2c0-59a2-a525-6f0d0ad216f9 | note | HP*
93e4c8e4-fd5e-51bc-913c-b665f24098e9 | note | RESPONSIBILITY: Fulton Hogan Engineer
f80677c2-85c8-5cd6-aac2-4e2456cc6def | date | Date Completed:
9b0faa9a-a6f8-4fce-879f-26db6d90bc2b | checkpoint | 1.4 - Proving Services
8900a367-4b6e-51e6-93bb-eb76bc8301bf | note | FREQUENCY: Prior to commencing works
a1e2adf4-52ec-5302-97da-60f3127af6aa | note | ACCEPTANCE CRITERIA: Underground services shall be proved by clearly marking the location of the service on the ground and physical exposure of relevant services at appropriate locations, in accordance with service authority requirements.
230c2d71-7f9b-58ed-a702-b3e4d972b94c | note | REFERENCE DOCUMENTS: 160.12B
aad6f317-3890-58ea-9cf4-9e65c38d3d6e | note | INSPECTION/TEST METHOD: Verify
f92132f4-7ceb-513c-813e-ce23c5eb0750 | note | RECORD OF CONFORMITY: This ITP signed off
5165d4e0-06b8-5cbc-a2bc-20c8f8dc30d3 | note | HP
79285147-1b84-5fcd-bf7c-6a5031d440ea | note | RESPONSIBILITY: Fulton Hogan Engineer/QAV
7adc9435-dda9-5df2-b9a2-26edc31eaa73 | date | Date Completed:
439c7f63-f6ba-4f9f-abcb-8b3c3e4e8906 | signoff | AUTHORITY HOLDPOINT
6b22b14f-cab4-4e5a-9dca-9d48e426a202 | section | 2 - Construction Works
8b0645aa-f560-4853-a4c9-cfc489917a9c | checkpoint | 2.1 - Survey set-out
f39d6dbc-fe7d-58e4-9f58-7dae6c1caef6 | note | FREQUENCY: As required
cbad503e-5e24-5951-89fa-5f7dce3854ed | note | ACCEPTANCE CRITERIA: Prior to setting out trench, advice should be sought from Telstra/NBN for accuracy of cable routes. Cable routes shown on drawing are only approximate.
8375a272-ab55-5dba-be7f-79f303725ff2 | note | REFERENCE DOCUMENTS: APPENDIX L
c0944b17-126c-573b-88b2-13195a724a92 | note | INSPECTION/TEST METHOD: Verify
591366a0-c10d-561e-91ca-e45b6c7d2591 | note | RECORD OF CONFORMITY: This ITP signed
c525372b-78a7-51a0-a531-21bb8e12cb46 | note | IP
209f92bf-bb19-5024-94d1-e2b95696fe2b | note | RESPONSIBILITY: Fulton Hogan Engineer
b1c8588f-dedd-5531-9394-d62be1cfd845 | date | Date Completed:
a899e2f5-928a-42fb-9050-581c4aec190e | checkpoint | 2.2 - Excavation
2329d397-a2cd-5cd6-bf60-93cd38e3e8ec | note | FREQUENCY: Each Lot
d1a765c2-5197-56da-9313-b8f0485cabab | note | ACCEPTANCE CRITERIA: The edges of all trenches located within a road pavement shall be sawcut
29e786bd-b579-5808-a897-23ea0ca016b3 | note | ○ Trench to be excavated to the nominal trench depth of 1.8m with a minimum width of 1.0m.
5e9ed78b-c45d-5713-9575-fae9de8e4d6c | note | ○ If trench depth is greater than 1.5m; bench, batter or shore
e2fc3c4d-6f20-58ad-a877-a31323ff7e8e | note | ○ 5m EW shall be provided for all conduit bends
ecf27a6a-7b28-5d04-ba3b-c2313c50e4a2 | note | REFERENCE DOCUMENTS: APPENDIX L
0ce2f4b1-15d2-55df-84f5-402ad6f9fccd | note | INSPECTION/TEST METHOD: Verify
994dd539-4a78-5c04-9074-00e914a49447 | note | RECORD OF CONFORMITY: This ITP signed
1a26cd82-a07f-5df6-8aeb-aa3dff83cd99 | note | IP
36df679e-4a7a-5549-8cef-afa8f472f77e | note | RESPONSIBILITY: Fulton Hogan Engineer
ac042d2c-b7ac-5403-9471-b1e1f2642523 | date | Date Completed:
f0893a60-b6ca-4372-b1c3-001d559c370f | checkpoint | 2.3 - Material Assessment
41c04de9-a0a2-53f9-8b5f-efa760a18c41 | note | FREQUENCY: Each Lot
5a6a02fc-7da0-5e9f-ab6f-85bc2df38e88 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
0e6bc110-e6bf-5f63-b781-4ef550460c96 | note | REFERENCE DOCUMENTS: 204.06
548bd80e-05c6-5ca5-a5eb-ac79aaacca9b | note | INSPECTION/TEST METHOD: Verify
c7a55852-4f0b-5397-8f53-b924936328bd | note | RECORD OF CONFORMITY: This ITP signed
abf8d17e-de0d-5d82-97b1-473d48fe1570 | note | HP
ced14e5c-5abf-5a81-a081-17584b689f38 | note | RESPONSIBILITY: Fulton Hogan Engineer/Superindentant
04119fb9-fe4e-5a49-a021-24e35f62fddb | date | Date Completed:
d59f233d-7e4f-48e5-a73f-f4df27c19519 | signoff | AUTHORITY HOLDPOINT
abd4f865-02e6-496d-80d8-578e82104a09 | checkpoint | 2.4 - Bedding
8fa01f5a-eabd-5aaf-8ecf-93561fd67dee | note | FREQUENCY: Each Lot
37ce90cd-8eeb-562f-b08d-c8e6402bf804 | note | ACCEPTANCE CRITERIA: Bedding material shall be placed and compacted for the full width of the trench to a depth of not less than 80 mm on an earth foundation or 200 mm on a rock foundation.
18c7439b-0b46-5d11-b893-518efa45c0ee | note | REFERENCE DOCUMENTS: 733.06(B)
85db5793-11c0-5263-b888-3fec1ce16b65 | note | INSPECTION/TEST METHOD: Verify
3b839f2c-4bb1-586e-a6d5-3fd5aa3de385 | note | RECORD OF CONFORMITY: This ITP signed
d45b9d85-56c7-5b84-bca2-8d57d2e36bf4 | note | IP
03c93edb-3821-5a76-a641-ef9f33a164cb | note | RESPONSIBILITY: Fulton Hogan Engineer
79822215-beb5-5866-ac66-a86d41f9ec8d | date | Date Completed:
c1263f74-23ae-433e-a389-cf028fa587e4 | checkpoint | 2.5 - Installation of Conduits and Cables
dae95c93-ac43-53ac-b2c5-e16a2e71ff09 | note | FREQUENCY: Each Lot
a51ec234-9580-58f1-bec0-a0737532b8c1 | note | ACCEPTANCE CRITERIA: Conduits and cables to be installed by Telstra/NBN contractor.
7c47345d-0c2e-5642-9cfc-175d31340329 | note | ○ Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by superintendent or representative.
03ec30e0-1c3a-559a-84df-2df1b00267d9 | note | ○ Conduit bends to be concrete encased as per Telstra Specifications
9aaa7c45-f32a-5975-b476-bce61227b5f7 | note | REFERENCE DOCUMENTS: 160.12A, 733.06(B)
7602de14-0da9-5872-bf5a-210defceed44 | note | INSPECTION/TEST METHOD: Verify
045df1ce-6467-5cd1-92d4-4320b9e3cfe3 | note | RECORD OF CONFORMITY: This ITP signed WP
2b618832-5c6a-5486-aa0d-06e1c0ff24b3 | note | HP
93805304-677f-5da0-9d62-2faa1e01aafe | note | RESPONSIBILITY: Fulton Hogan Engineer
ac6daedc-ee23-5629-9b71-237310b7feb9 | date | Date Completed:
ffff246c-8ed5-4565-a527-016f019cd24e | signoff | AUTHORITY HOLDPOINT
63e18159-0385-4e6a-9bb3-99daa7522f13 | checkpoint | 2.6 - Back Fill of Trenches
b9398c22-8c94-5525-a70a-2eb32045ae4b | note | FREQUENCY: Each Lot
6bc3edfb-70f2-524d-ba14-64c0169033b2 | note | ACCEPTANCE CRITERIA: Conduits to be backfilled as per Table 733.061
9d089547-29de-5dfd-94d8-d4689d1ebc05 | note | ○ Conduits shall be backfilled with stablised sand to 100mm above top of conduits as per AS3000.
f9e8f717-ecd0-5dad-9627-2e4cbb19fd2f | note | REFERENCE DOCUMENTS: 733.06, APPENDIX L
72521bd2-d281-5db5-9920-580702f40cbf | note | INSPECTION/TEST METHOD: Verify
e86a5be9-15c2-55c6-97be-526d736cca0a | note | RECORD OF CONFORMITY: This ITP signed
6b403bef-6cbe-569b-8b8a-bf51ad2d3db9 | note | IP
9f7b1a2e-cfda-5ada-8168-2acbca98235b | note | RESPONSIBILITY: Fulton Hogan Engineer
f9ba14c7-f502-535c-8a91-c5f784aa2868 | date | Date Completed:
1e6771ae-ed86-40be-b1f7-bc8c006b6165 | checkpoint | 2.7 - Compaction
0dc75fd3-d078-5ffa-b9c3-c0cccfa5c0c4 | note | FREQUENCY: Each Lot
be7bdaa5-c6d3-5f35-95d5-601f293adfbf | note | ACCEPTANCE CRITERIA: Bedding, and backfill shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Standard compaction test.
e1e1f1f0-5347-5bfe-91b2-ca3e2d8f8b88 | note | ○ All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
34c85aa6-e08f-5a0d-805e-6a5dce4eabb6 | note | ○ Backfilling beneath areas to be paved shall be assessed for compaction:
14c9f831-dc47-550e-a696-d939418b7818 | note | – The number of tests per lot shall be three
d05336f0-c0ae-5b9e-9abf-a8af5f7c7dc1 | note | – Compacted to a mean value of density ratio of not less than 95% (passing 37.5mm AS sieve)
aadb7a7f-d0ae-582a-a36e-155a0f1d31b4 | note | ○ Backfilling of pavement materials shall be assessed for compaction:
f189c219-817e-5869-879c-6b889c2d57f5 | note | – Compacted to a mean value of density ratio of not less than 98%
afed51f1-1a3a-5c65-9063-9364e8a36451 | note | REFERENCE DOCUMENTS: 733.06 (D)
95d7aec6-d931-5978-aafc-2c0896ad2cc4 | note | INSPECTION/TEST METHOD: Verify
23650fc9-48e5-585e-a275-5d8a9f4285f4 | note | RECORD OF CONFORMITY: Test Reports
a1cac03f-9765-5c8f-a67c-2334db86aee9 | note | TP
38b1660b-6800-53a5-90f8-469811a003b5 | note | RESPONSIBILITY: Fulton Hogan Engineer
167d8989-0121-54eb-90d8-3381108e8a3a | date | Date Completed:
87f17174-82ee-49f4-b325-4263f28be014 | checkpoint | 2.8 - Installation of marker tape
7cfa4074-6d05-5626-8aff-0018805c8876 | note | FREQUENCY: Each Lot
bef6c66a-664f-5358-9ade-613c6c7d346b | note | ACCEPTANCE CRITERIA: Marker tape to be installed by Telstra/NBN contractor
dd9d543e-0052-5c43-af6a-8731b02b46e1 | note | REFERENCE DOCUMENTS: 160.12A
d7be2bfb-5e6c-5c40-bde2-9162eef172a9 | note | INSPECTION/TEST METHOD: Verify
b1d55b4e-dfb9-55fa-9810-55440c7112e6 | note | RECORD OF CONFORMITY: This ITP signed
b79201e5-e59b-5ad1-8de4-795d119d48ba | note | IP
a99550db-9f12-5491-8a77-36555000cb59 | note | RESPONSIBILITY: Fulton Hogan Engineer
df26bd6a-f6fb-54a6-84b4-56e41d19f121 | date | Date Completed:
6d5e003d-1c86-4739-8632-87f8108dfebf | checkpoint | 2.9 - Cable Pits & Pit Lids
7a94789e-f7d2-52bb-aca4-47ea49f74860 | note | FREQUENCY: Each Lot
02a82bc7-f5ab-5f12-aac3-a4f4cbb0b63d | note | ACCEPTANCE CRITERIA: Cable pit excavation to be provided by Fulton Hogan
8d227917-8a3b-5165-b67d-00ad7766f8e2 | note | ○ Cable pit bedding to be installed and approved by Telstra/NBN contractor
6eb8c85d-9c01-5f77-b7d1-4db4c3aec3f9 | note | ○ Cable pits and lids to be installed by Telstra/NBN contractor
c5d824b2-05c5-55e0-bf26-c791ad1fdd07 | note | ○ Lift Analysis to be provided to Fulton Hogan by Telstra/NBN contractor 24-48hrs prior to lift.
3d255024-cef9-526a-adcd-c43125eb1947 | note | REFERENCE DOCUMENTS: 160.12A
3585c0de-ef2e-579c-aa91-d9cc3ff2cde7 | note | INSPECTION/TEST METHOD: Verify
e69a4ee5-d914-5b4f-ab07-b7070610675a | note | RECORD OF CONFORMITY: This ITP signed
755da37d-cc88-5a71-bfa9-67f617123994 | note | IP
4a925ebd-4e95-50cb-b620-e798184246aa | note | RESPONSIBILITY: Fulton Hogan Engineer
04da2545-fcf2-5df3-b0e5-8a0b1cc0860d | date | Date Completed:
f49b3102-d5a7-49d0-a850-9b00287921d6 | section | 3 - Completion
d41ed426-2765-4984-a7d3-e8c244b6a200 | checkpoint | 3.1 - Cleaning of Site
061ac621-351b-518d-92e8-9c8cbe4ec562 | note | FREQUENCY: Each Lot
f4fc0d99-b8a7-5aff-be6d-c7836b5aed53 | note | ACCEPTANCE CRITERIA: Surplus excavated material shall be removed from road reserve. All affected areas shall be restored to similar conditions that existed prior to work.
f253f432-33f6-58a0-884d-b230566e4b68 | note | REFERENCE DOCUMENTS: 733.09
8ff1cbf2-d64a-502d-aac8-67a370b1f9d0 | note | INSPECTION/TEST METHOD: Visual inspection
83d9fddc-e932-5070-bc3a-31f055738996 | note | RECORD OF CONFORMITY: This ITP signed
96865f95-a9e7-579f-bd6e-bb8594cdf6d6 | note | IP
741e4ad7-c220-53f5-96b7-7f52697ae402 | note | RESPONSIBILITY: Fulton Hogan Engineer
d0f6ba4f-90d2-5b2a-bda8-ab9003a1224c | date | Date Completed:
7a358ba3-9e3f-401f-8e20-fc0822f47132 | checkpoint | 3.2 - Recording/As Built
65693317-e1d0-5661-bf7f-27e37788ae19 | note | FREQUENCY: Each Lot
537eecac-24d8-5173-93d4-abadee2cc90a | note | ACCEPTANCE CRITERIA: Record any changes to cable routes on red line mark-ups. The final alignment of installed Telstra and NBN conduits shall be updated on the service plan
3ef40f8e-3b33-5f2c-8298-0d63d82b65e7 | note | REFERENCE DOCUMENTS: 160.12A
e0f4c80d-93e8-5f05-b60a-38454952486d | note | INSPECTION/TEST METHOD: Verify
4d99107e-d698-5a77-8dbb-ab82c1d4865b | note | RECORD OF CONFORMITY: This ITP signed, As Built Drawing
fb55a1bd-2000-5321-bc67-13fb97569314 | note | *HP
56f8010a-4a0a-5f3e-b395-ad2f89c31d83 | note | RESPONSIBILITY: Fulton Hogan Engineer
28de0ab5-3e73-5425-9bf3-a52f0c279f50 | date | Date Completed:
e446cb49-2ade-4ccb-a53e-416b54ea4173 | checkpoint | Final Inspection
39810d0f-f90b-5f68-835f-223c9f2c0c51 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9e6f536b-4fad-5044-a6be-16dedc437053 | textbox | Print Name:
4192c946-79ef-5d3a-be50-506a02b2c6d7 | textbox | Position:
18b70c10-43d6-5236-be4c-ad767e9dc8af | date | Work Completed On:
ff5276c4-a850-477d-a08a-7321eb093909 | signoff | Add Signature
8380e5f3-85ef-4d86-acf4-d566cff7fbcd | checklist | DTM-ITP-005- Service Relocations - Power (TasNetworks) Rev1 | itp | DTM-ITP-005- Service Relocations - Power (TasNetworks)
d939b3fc-278e-4d62-868c-df54f125cbcf | section | 1 - Preliminary Works
2ea71fd8-e69a-42c1-b39a-ec0d4e4e8acd | checkpoint | 1.1 - Check for correct documentation
4233d5bf-120e-53f1-8e7d-5d65a0981ea0 | note | FREQUENCY: Prior to commencing any activity
8f5c8733-cd0d-59c8-acaf-958478f3b05b | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
541acc5e-45ad-5502-b70b-b70d3bff793c | note | – using the correct and complete set of drawings
41b77edc-7783-5239-8431-ada38a7ce11d | note | – all drawings are the latest revision
da8eb80c-8856-5d7d-b794-d5694d0fdf9f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
194f0b86-01ea-5efd-9652-d0f99dcfa4b5 | note | INSPECTION/TEST METHOD: Visual inspection
7ba87a31-400d-5251-b1b4-2cb96010129e | note | RECORD OF CONFORMITY: This ITP signed off
eb116be9-5088-510b-bf8c-ffb608201949 | note | HP*
a0f34ef4-a9b8-5c5b-a522-19cdb3006ba5 | note | RESPONSIBILITY: Fulton Hogan Engineer
d27a18ce-27c3-5018-b3a9-81ee58e7158c | date | Date Completed:
317d7c09-9b94-46b5-8a7d-c880c8291dd8 | checkpoint | 1.2 - Implementation of all measures and controls
1759240f-3f10-593f-bdf7-c5c859a9f693 | note | FREQUENCY: Prior to commencing any activity
d7312306-1ec0-5c7c-a8b2-a3c4f453747c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP/TGS, JSEA, SWMS & WP
d148d02d-edcd-517e-98c0-0bbf8a77a811 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
3b83f8d1-1e03-542b-8ab7-05fc0e46e674 | note | INSPECTION/TEST METHOD: Visual Inspection
9d9019c4-2bc4-5a7d-862b-0efc6e2679c2 | note | RECORD OF CONFORMITY: This ITP signed off
c20b328a-d7d1-512e-9273-9cd8c3032bf5 | note | HP*
bd4f9120-640d-5ec3-9768-968a674efffd | note | RESPONSIBILITY: Fulton Hogan Engineer
05bcead0-affe-5137-a9d8-9f577785fcbb | date | Date Completed:
72c0e01b-1725-47be-acb6-b02577f6ef1b | checkpoint | 1.3 - Scheduling trenching works with TasNetworks
8c2e19b5-125f-59b3-9a64-de7d3b2647bc | note | FREQUENCY: Prior to commencing works
92cbbaa1-77a7-52b4-aa27-a91b60c1d4bd | note | ACCEPTANCE CRITERIA: Provide TasNetworks with an accurate date for when the trenches will be available for cable installation and when final ground levels will be established
31324708-486d-52d9-8935-3f1c5b86389e | note | REFERENCE DOCUMENTS: AS-32433
b5f80a46-9784-5f0d-b1b3-cc2225abc234 | note | INSPECTION/TEST METHOD: Verify
bcb3fe6f-733a-5cee-b001-840a0c2a5157 | note | RECORD OF CONFORMITY: Service Installation Programme
2bf0c941-13b2-59b1-9713-b66c47c83624 | note | HP*
34a3fb09-f2aa-57e8-9f4f-5357b104e75e | note | RESPONSIBILITY: Fulton Hogan Engineer
41baa004-54ca-5fc7-91e7-6389d7bf27d2 | date | Date Completed:
255c5a3f-9d48-45ef-b6ce-695a28da53c8 | checkpoint | 1.4 - Proving Services
1396a90b-2490-563c-9093-827ad4fe9636 | note | FREQUENCY: Prior to commencing works
98d90d5b-31d0-5ca7-97df-9503c264ea33 | note | ACCEPTANCE CRITERIA: Underground services shall be proved by clearly marking the location of the service on the ground and physical exposure of relevant services at appropriate locations, in accordance with service authority requirements.
2e70bd91-9a2e-5c0e-ab81-58448eead14a | note | REFERENCE DOCUMENTS: 160.12B
b736b6d2-f18f-5729-8197-574f622f8a98 | note | INSPECTION/TEST METHOD: Verify
980fa25b-edaf-5c3e-8be8-28051693b809 | note | RECORD OF CONFORMITY: This ITP signed off
ec39c5ff-3a20-5f5d-9626-14771c428e7d | note | HP
8ae9bec3-3725-5fbc-a13c-3533dd39026b | note | RESPONSIBILITY: Fulton Hogan Engineer/QAV
98f804af-9068-5aed-bb08-7de89ef83f6b | date | Date Completed:
368b19a6-c847-4fed-aaf5-5c683d124078 | signoff | AUTHORITY HOLDPOINT
98364c4f-845e-4c6e-88ab-5de31cb3f3ce | checkpoint | 1.5 - Excavations within 3m of poles or stays, Exacavtions within 1m of Underground Assets
f2c1a4cc-888b-58a8-ac82-d44526c9d10c | note | FREQUENCY: Prior to commencing works
97cdd966-bd88-559a-a414-412e93e3d8b0 | note | ACCEPTANCE CRITERIA: Advice must be sought for any excavations within 3m of poles or stays, or 1m of Underground assets
109fb950-4338-52c8-949c-94647d36284d | note | REFERENCE DOCUMENTS: 160.12A
1edf7c48-1c8c-56ca-9909-d23760273f73 | note | INSPECTION/TEST METHOD: Verify
7daf5271-e4aa-5067-b66f-23613dba0412 | note | RECORD OF CONFORMITY: This ITP signed
c20ad7a0-708b-51af-8302-b2c9cc5f095d | note | WP
c7a3366c-e2df-55d6-854a-0afc0ef03a70 | note | RESPONSIBILITY: Fulton Hogan Engineer/ TasNetworks
65c17231-a658-5515-9d24-5275ad60c2f6 | date | Date Completed:
3bee79c7-32ea-427e-b0b8-970c33db4411 | section | 2 - Construction Works
33e8a60c-420a-4465-b7b8-d02dd7bf7507 | checkpoint | 2.1 - Survey set-out
56a267a6-83f5-5bad-9db3-7e32686fd6cf | note | FREQUENCY: As required
8b900195-1112-58ff-8839-c3f1dd7dff7d | note | ACCEPTANCE CRITERIA: Prior to setting out trench, advice should be sought from TasNetworks for accuracy of cable routes. Cable routes shown on drawing are only approximate.
3810cb95-de5e-50d9-a745-24a9be68b0c2 | note | REFERENCE DOCUMENTS: AS-32433
261064b6-74ba-5c31-8a0b-95f08075c186 | note | INSPECTION/TEST METHOD: Verify
d644a3e4-36d6-563e-9b60-2fd9cfd860e0 | note | RECORD OF CONFORMITY: This ITP signed
db98ed0d-5714-5127-a686-0dcd702034b4 | note | IP
b4bd8982-7f25-573c-ae9a-88168a9086a9 | note | RESPONSIBILITY: Fulton Hogan Engineer
bd7a19ed-1b83-5944-98de-1f708704e8cb | date | Date Completed:
a4dc456e-3c6f-4b8c-893f-c8f6eca26baa | checkpoint | 2.2 - Excavation
d3e5fbfc-266a-5d92-89f8-2649c7e4927e | note | FREQUENCY: Each Lot
cdfa50dc-67d3-521b-bd85-82d32d19533a | note | ACCEPTANCE CRITERIA: Check drg AS-32433 to confirm trench detail
fd516152-2ee8-5b3a-88b9-06afe1f92a1c | note | ○ The edges of all trenches located within a road pavement shall be sawcut
2bd45980-f634-51a3-a4e9-80d9660741ad | note | ○ Trench to be excavated to the nominal trench depth shown on drg AS-32433
65b43533-9ea4-5b5e-a6ce-fa055d408d18 | note | ○ If trench depth is greater than 1.5m; bench, batter or shore
1a3a9728-32a0-524e-b631-727a9009872e | note | REFERENCE DOCUMENTS: AS-32433
1a8f2bd6-f159-5294-9a81-a4163b0371bf | note | INSPECTION/TEST METHOD: Verify
3a7b1ad6-b43a-5a3e-8d6a-09242098ffcb | note | RECORD OF CONFORMITY: This ITP signed
473b576a-107f-5248-9177-9431e3d0fd85 | note | IP
ea2921e4-6f3c-5b21-be8a-59a82d901ba2 | note | RESPONSIBILITY: Fulton Hogan Engineer
8fbdb4a7-b7c1-5af4-87eb-2cafe8c2205d | date | Date Completed:
caa4fd3d-449c-4888-a301-cbdacdd98381 | checkpoint | 2.3 - Material Assessment
6ac9d39a-2be4-5a9c-9f5d-7ed0e95e0ecc | note | FREQUENCY: Each Lot
db62f081-a394-5732-b01e-f4701e709721 | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04.
63a264bc-1642-52cc-bef4-5b5ec37616fa | note | REFERENCE DOCUMENTS: 204.06
20e6c71b-6b2d-5334-9ed5-e0ae0177e59b | note | INSPECTION/TEST METHOD: Verify
aafef60e-d3f7-5453-865a-feaafdd6ba1d | note | RECORD OF CONFORMITY: This ITP signed
a8d727c1-cd23-5b31-97e7-8137d4de0cbf | note | HP
472fe792-0dac-5cda-bd00-46be07045025 | note | RESPONSIBILITY: Fulton Hogan Engineer/Superindentant
a45758cc-342e-5762-bb8c-8474388646c2 | date | Date Completed:
a1117ce2-70f4-42c3-910b-fb486ee46144 | signoff | AUTHORITY HOLDPOINT
82a33b10-d3c9-4af5-b2c8-ea01862c9564 | checkpoint | 2.4 - Bedding
236844bb-4b7e-5f5d-a9ca-708b57e907f3 | note | FREQUENCY: Each Lot
1b670bc5-1c1a-5d2c-b3dc-5a591730b864 | note | ACCEPTANCE CRITERIA: TasNetworks to place sand bedding
d707f8c3-ebd2-5aaa-b883-deef10be29ad | note | REFERENCE DOCUMENTS: 160.12A
90ed6bc7-995f-5541-b5c1-d0cf8f9d9e09 | note | INSPECTION/TEST METHOD: Verify
be997fb6-152a-52c9-a8de-afcf03f08e2c | note | RECORD OF CONFORMITY: This ITP signed
8e1979ea-1c6d-556e-b1ed-12859198b5dc | note | IP
e509421f-ea61-5e83-8d33-c8968b1815ed | note | RESPONSIBILITY: Fulton Hogan Engineer
021fd59a-8917-5dda-b014-357d26d6499c | date | Date Completed:
671918a0-6483-41b6-9d49-eea9d1a8883e | checkpoint | 2.5 - Installation of Conduits and Cables
26d489af-66af-5947-915b-8a2c7382864f | note | FREQUENCY: Each Lot
fec3b8bc-acdd-5cff-94f6-16efc078ad22 | note | ACCEPTANCE CRITERIA: Conduits and cables to be installed by TasNetworks.
f5dd55ac-45f3-58b6-a91c-fc7765131d33 | note | ○ Once the bedding material has been laid and the conduits put in place, works shall not proceed prior to inspection by superintendent or representative.
57e648f4-247b-579d-b7e4-cd1cebf06bbe | note | REFERENCE DOCUMENTS: 160.12A, 733.06
dce75d9f-3b55-52a1-a517-52a7162261c1 | note | INSPECTION/TEST METHOD: Verify
d40dab27-dbef-5405-b9e2-f0547e9bc728 | note | RECORD OF CONFORMITY: This ITP signed WP
61e10f7d-7a1b-582e-b4c2-66e0cc0423c9 | note | HP
5b431d3d-7c77-548b-b029-9c9879c537d8 | note | RESPONSIBILITY: Fulton Hogan Engineer
ce7e57bd-c1d8-56cf-9881-2fd5072e87c4 | date | Date Completed:
9baf5c5b-4bb5-4a66-a719-8650db4cb44a | signoff | AUTHORITY HOLDPOINT
171c3922-604a-4511-b9ec-abca4e6bdb79 | checkpoint | 2.6 - Back Fill of Trenches
3d628aff-d635-5cc6-b66a-32ad554fcd6a | note | FREQUENCY: Each Lot
5a94b26d-4b80-54bb-94b9-73d33e30d1d2 | note | ACCEPTANCE CRITERIA: Conduits to be backfilled with approved FCR or site won backfill material under the approval of TasNetworks
6f8c3d2d-2caa-5126-bad9-b9cb12d54741 | note | ○ Conduits may be backfilled with stab sand under the approval of TasNetworks
989494cb-8c23-5f50-bbd5-4e4c92e31e9d | note | REFERENCE DOCUMENTS: 733.06, AS-32433
9d79c7a6-b01d-5685-8a02-cbb2c2fb073f | note | INSPECTION/TEST METHOD: Verify
f552f145-e6dd-5018-8594-470aa916defe | note | RECORD OF CONFORMITY: This ITP signed
f52cefd0-8260-563f-8855-2cfca0c58a3c | note | IP
9a0a453c-3a37-5acf-9d09-213b819e9e4f | note | RESPONSIBILITY: Fulton Hogan Engineer
cf27b670-0bf1-5add-9d01-cbec39f360f1 | date | Date Completed:
b0ad1601-b4c2-47fa-b3b9-07de07483016 | checkpoint | 2.7 - Compaction
fa7ac0cb-9a90-5233-b51c-efa578411b8d | note | FREQUENCY: Each Lot
5e8768bc-b7fc-51ce-a642-9e8e20da1557 | note | ACCEPTANCE CRITERIA: Bedding, and backfill shall have during compaction a uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Standard compaction test.
5ad669e4-3ef4-58a2-881c-92c21e1a15b7 | note | ○ All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test.
1cb0bbaf-9e51-5c57-b034-161980161d6b | note | ○ Backfilling beneath areas to be paved shall be assessed for compaction:
50f91a05-943c-533d-9146-bc4895658dcb | note | – The number of tests per lot shall be three
61bee9e7-50e8-5ed2-9aac-7b2f8b1261cd | note | – Compacted to a mean value of density ratio of not less than 95% (passing 37.5mm AS sieve)
abf08659-068e-56ab-9208-6b592e84f245 | note | ○ Backfilling of pavement materials shall be assessed for compaction:
3600eaa0-cecd-553c-a2a8-02946b7b1950 | note | – Compacted to a mean value of density ratio of not less than 98%
9d3ee4a7-83c5-544e-99ed-eb833cdc51b0 | note | REFERENCE DOCUMENTS: 733.06 (D)
5cdab68f-cd28-506d-a896-faeadd4a2c15 | note | INSPECTION/TEST METHOD: Verify
2f62bc96-a90f-5952-8ad6-9ece8175a8a5 | note | RECORD OF CONFORMITY: Test Reports
90f3d0ba-1658-52c7-b590-b22f6639605d | note | TP
e34e080a-0744-5721-9927-488a0266d0ca | note | RESPONSIBILITY: Fulton Hogan Engineer
7aa64389-7af8-50e9-958e-3069682e8a9e | date | Date Completed:
a605a1f4-0cb3-435b-8348-1dfe8cf8f215 | checkpoint | 2.8 - Installation of marker tape
ef455e35-ac7b-536e-bb3b-fe6d4591fc85 | note | FREQUENCY: Each Lot
3332028d-dd69-5f41-95cf-5ae467426449 | note | ACCEPTANCE CRITERIA: Marker tape to be installed by TasNetworks
399e8d32-7791-5a24-b8af-796f5ab86bad | note | REFERENCE DOCUMENTS: 160.12A
a9d13828-7e44-5322-ac8c-e17000921279 | note | INSPECTION/TEST METHOD: Verify
4ae89711-3816-5ed6-bce9-ef8ff6dd1890 | note | RECORD OF CONFORMITY: This ITP signed
5875a302-3bf1-5f72-97d0-37845f1135ed | note | IP
8b1bce2d-bdc5-507d-9bb0-24ec2df5a85a | note | RESPONSIBILITY: Fulton Hogan Engineer
8a1f8861-4255-5ae7-b08f-35f163dcfa20 | date | Date Completed:
bf395b5d-3961-4cf0-94f2-244e18aa0632 | checkpoint | 2.9 - Cable Pits & Pit Lids
fa8d89b4-7e89-5075-8fea-0cfae1fc0a78 | note | FREQUENCY: Each Lot
c87361e6-e170-5fab-aa38-cb26f2864f58 | note | ACCEPTANCE CRITERIA: Cable pits and lids to be installed by TasNetworks
d4d3a8d4-2ad8-5a51-8e11-f6cd5428b8ff | note | REFERENCE DOCUMENTS: 160.12A
8649850f-7e06-5581-8372-78e75c34f9cc | note | INSPECTION/TEST METHOD: Verify
2734d5cf-0230-5e62-8a69-10dda69602c6 | note | RECORD OF CONFORMITY: This ITP signed
99e1fb6c-df4d-54ad-937b-7222a9b697a7 | note | IP
0df0a70e-c223-533a-9727-ec60a9dac1db | note | RESPONSIBILITY: Fulton Hogan Engineer
9a6da8ca-983b-5f33-9f20-f9ba754e5973 | date | Date Completed:
47bf6d72-5df1-40bd-bbe3-819c549ffccd | section | 3 - Completion
28e46eb7-d3b7-41c4-ad8d-35de5463f74b | checkpoint | 3.1 - Cleaning of Site
7a9dec18-113a-5d76-903f-65ecf31534cc | note | FREQUENCY: Each Lot
98dce7e7-c10a-58c0-8bb5-a8ce4c440b03 | note | ACCEPTANCE CRITERIA: Surplus excavated material shall be removed from road reserve. All affected areas shall be restored to similar conditions that existed prior to work.
264e7725-f6a4-5bc6-9413-154e74c53b56 | note | REFERENCE DOCUMENTS: 733.09
3c0093a9-d20c-5f38-9b8e-84bedd4b5a98 | note | INSPECTION/TEST METHOD: Visual inspection
5c945f7b-be30-5d99-9a02-246ad7674c70 | note | RECORD OF CONFORMITY: This ITP signed
ed5ac589-b828-5d4f-8256-2d8357c12624 | note | IP
dc6041bf-23ed-562c-be64-8baf0aab6e0e | note | RESPONSIBILITY: Fulton Hogan Engineer
d7d4cec8-65e9-5bb7-aab1-60f1c943dde6 | date | Date Completed:
2136825f-22c8-43e4-af91-381847c6a986 | checkpoint | 3.2 - Recording/As Built
ab719fe3-bf72-5312-8285-2762ec4d5083 | note | FREQUENCY: Each Lot
77c8246a-881e-57ab-b65c-e4bf1530de4b | note | ACCEPTANCE CRITERIA: Record any changes to cable routes on red line mark-ups
4a9b190f-2db0-5be6-b327-8b675d1d7c55 | note | REFERENCE DOCUMENTS: 160.12A
c53db618-0320-5a4a-af8c-f00dfdec5e95 | note | INSPECTION/TEST METHOD: Verify
50227621-c6c8-5c3a-ae45-061d51a6790c | note | RECORD OF CONFORMITY: This ITP signed, As Built Drawing
8a7772b0-df17-54c5-9793-b2305bdf5fe4 | note | *HP
e1276f20-b32c-5afc-8626-8603512ec923 | note | RESPONSIBILITY: Fulton Hogan Engineer
e3635b30-053a-514e-a0be-03081782dadc | date | Date Completed:
405c33de-087e-4ad3-bdf8-9c0f8b3b4512 | checkpoint | Final Inspection
765caa9d-6107-5579-b9fb-9bd546c78009 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
fe9a5ce3-65d0-5351-9d3e-339534a622c4 | textbox | Print Name:
9887c2af-41e9-5c86-a47c-80c57fffe257 | textbox | Position:
0378c736-65c6-58b4-bd2b-12221383be64 | date | Work Completed On:
d94314d0-43a4-4c64-b6e6-6b92b66bd72c | signoff | Add Signature
86c7edee-b38e-4391-b135-bbba6c1d17e9 | checklist | DTM-ITP-006- Unbound Flexible Pavement Construction Rev0 | itp | DTM-ITP-006- Unbound Flexible Pavement Construction
1a8775ca-8808-4828-be75-2ee2b40877ad | section | 1 - Preliminary Works
5eddf287-a6f1-4e48-abac-dad025f95fbd | checkpoint | 1.1 - Check for correct documentation
e05b1258-b4c6-54ec-a92f-959fc204c337 | note | Frequency - Prior to commencing any activity
a0756a10-4aa1-5475-a467-03928b5cef17 | note | Acceptance Criteria - Ensure that all employees and subcontractors are:
2ac1746c-a1ab-5955-a62d-9e69207e7b0a | note | – using the correct and complete set of drawings
73568102-2ed7-5fb3-b92c-f5964bed16af | note | – all drawings are the latest revision
34696bd9-bf22-5ef8-885b-1e66054b2e9a | note | Reference Documents - IFC Drawings
b9ea98d3-758f-56c4-aed2-4cb2c33082de | note | Inspection/Test Method - Visual inspection
fa53e52c-57b5-51df-9e5e-4fe215d03c18 | note | Record of conformity - This ITP signed
5a5efa5c-a2dc-56ae-a7d6-b9c607924274 | note | HP*
0ad274df-2c8b-5d9a-84ee-c8403439b2a1 | note | Responsibility - Site Engineer
9145bf74-02d9-54d4-8292-89ab14a5dc9f | date | Date Completed:
e3d763b4-d05b-4437-b648-a8952cd9ec03 | checkpoint | 1.2 - Material Mix Design
efce4ed2-f7d0-52db-95de-4fe0e0fa5487 | note | Frequency - Prior to commencing works
66205b41-111a-5751-b121-5500c25fe130 | note | Acceptance Criteria - Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mixes RC500.02 as listed in Section 175.
3f325e40-6cce-5bfd-9729-cdb6fe74cbde | note | Reference Documents - 812.04, VicRoads RC500.02
87fdf747-4978-5281-b676-f39ad1b198f2 | note | Inspection/Test Method - Document Review
db1b15b3-cdd3-56df-981a-890f8c7eb3ef | note | Record of conformity - Crushed Rock Registration, This ITP signed
2367df4c-24b9-5f02-a72a-28c7aef4852a | note | HP
cc66152d-9eb9-50e1-a3ed-5f1f02f4290d | note | Responsibility - Site Engineer / QAV
3510e962-d684-530b-8eae-d48d1936fb71 | date | Date Completed:
f54053d9-69ff-4bdb-be08-e864b9434296 | signoff | AUTHORITY HOLDPOINT
7bb1899d-ef75-43c6-a077-08316a5628bc | checkpoint | 1.3 - Material Quality
3dedca60-ea26-5995-8b06-f7eaa549da80 | note | Frequency - Prior to commencing works
445e555d-e4d0-5439-a734-4e3803f790bd | note | Acceptance Criteria - Material complies with the Class 4 specification for crushed rock
e1effdb3-545c-5927-93fc-b7a2fbe7cc09 | note | Reference Documents - 812, Table 812.121
1060e3f6-cc1d-5052-8114-88cef4ef8e05 | note | Inspection/Test Method - Measure
10395d39-0e6d-5f2f-96ae-ab051e277063 | note | Record of conformity - Test Results
08ebec4d-3c23-595e-a057-f1fea8f07a09 | note | IP
7c7857cd-aa37-58bc-9aae-105293ce53b3 | note | Responsibility - Site Engineer
7bf14732-7239-593d-8158-cfbd8f78b720 | date | Date Completed:
71ca29a6-b1d3-4b76-96fa-2b069695d14a | section | 2 - Placement
a8574eba-4b79-408f-80ec-d218634417a8 | checkpoint | 2.1 - Layer Thickness
01aa338c-6f4c-5883-bf53-60c31453ce81 | note | Frequency - Each layer
b9be0ccc-cd61-5695-b974-9b052f97db5c | note | Acceptance Criteria - In addition to complying with pavement layer surface tolerances specified in Clause 304.06(b), the following tolerances shall apply to the thickness of any pavement layer:
96f633b2-02d4-5565-8694-df1c2076620c | note | (i) the subbase course shall be not less than the specified thickness by more than 15 mm;
4afb7f21-810c-5c38-b010-c01a1717e69a | note | (ii) the base course shall be not less than the specified thickness by more than 10 mm and the average thickness of base over every 100 m section, over the full carriageway width, shall be not less than the specified thickness;
3731f1e3-52ad-5b9d-81c9-35477fbfb62a | note | (iii) the combined thickness of subbase and base courses shall be not less than the specified thickness by more than 15 mm.
718ea684-c783-593c-9bdc-55edf1e0705a | note | Reference Documents - Drawings and 304.06(c)
3d28ebb9-d6a4-567c-8c40-353b74407110 | note | Inspection/Test Method - Visual and Measure
af432db7-84ad-5584-afda-fe469c64dbd8 | note | Record of conformity - This ITP signed
2d737984-8822-5e49-bceb-4a921cedb5fa | note | IP
8efe5d45-7fce-55d3-8379-fd1ced244ba9 | note | Responsibility - Site Engineer
443f77d9-f154-5c6e-aa50-42f7e14f0d85 | date | Date Completed:
62cf241d-6e12-464f-b479-2e259baba906 | checkpoint | 2.2 - Jointing
1febb21e-ab73-5d4b-99de-4e5e947ed256 | note | Frequency - Each lot
80d1b681-0354-507b-934a-f00d2ea84d37 | note | Acceptance Criteria - The layout of joints shall conform to the following requirements:
c512cd25-58da-5d43-962a-2d1c865e9c55 | note | (a) material shall be spread in such a manner as to minimize the number of joints;
9a94eac2-c6ad-5759-ae24-4069fe963a81 | note | (b) for all pavement layers, transverse joints in adjoining paver runs shall be offset by not less than 2 m;
63921b0e-d161-50be-8422-f3118dff2a40 | note | (c) transverse joints shall be offset from one layer to the next by not less than 2 m;
81a1dbbc-58d6-57cf-ae19-557e05516638 | note | (d) longitudinal joints shall be offset from one layer to the next by not less than 150 mm;
77a0305c-a928-5ffe-817d-56611733b9a5 | note | (e) longitudinal joints shall be located within 300 mm of the planned position of traffic lanes lines or within 300 mm of the centre of a traffic lane.
2968fb0f-887c-57f4-8c7a-6282657de1fa | note | Reference Documents - 304.07
ccd9c6a2-3c9e-553f-94bb-a863e3099ec3 | note | Inspection/Test Method - Visual Inspection
6fc41273-9e14-51ad-97af-4e60cbbcb55c | note | Record of conformity - This ITP signed
2ef0ba38-335f-57ee-b854-6298b3141c87 | note | IP
7dc5dec1-74f3-5df8-9dbc-adaadb6aa6e8 | note | Responsibility - Site Engineer
9eeefbfb-3ee5-5f12-b4d4-448167661dfb | date | Date Completed:
0df55d27-e8a1-4c0a-a3bc-6a8969eedcc9 | checkpoint | 2.3 - Test Rolling
2f71ffd5-7bf9-51e2-8afc-14b7f476ea22 | note | Frequency - Each lot
18ca211a-b7e4-5ae8-8c79-840b0b5db85d | note | Acceptance Criteria - All pavement layers shall be compacted to withstand rolling and shall be test rolled in accordance with Section 173, prior to acceptance of the layer.The Contractor shall provide for the Superintendent to be present during all test rolling.
09ea5a48-5a25-5199-a05a-985fb2944899 | note | Reference Documents - 304.08
8cabdd34-716b-5371-835d-06fd43f6f254 | note | Inspection/Test Method - Test Roll
fe1290bd-5dbd-5bc9-af6d-3c519a8bc20a | note | Record of conformity - Witness Point
fb993113-0f33-51c5-9691-31242a05f680 | note | HP
84a099d2-9477-5585-9778-37cf4f6dfd40 | note | Responsibility - Site Engineer / QAV
4ae2c90c-f022-56b2-9344-ad6d64fcc93a | date | Date Completed:
049e51fd-ce8d-41f9-b9b2-7b6750f138bd | signoff | AUTHORITY HOLDPOINT
1efc5127-2654-4b11-bc08-9f7da2354171 | section | 3 - Testing and Conformance
98dde69d-9e6a-4a4c-a0c0-d9b6155ded2d | checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
351f6066-fce6-5750-b37c-dd65d1cb8993 | note | Frequency - Prior to Testing
90f8f1a0-4bac-58df-86cc-ebd5f1c74394 | note | Acceptance Criteria - Scale B - The first lot of each material type shall be tested to demonstrate compliance with the material property requirements specified in Clause 204.04. Where the first lot of each material type satisfies the material property requirements in, no further testing will be required unless changes are observed or where directed by the Superintendent.
a9c48088-e400-5a16-bf5d-8f248fe6a238 | note | Reference Documents - 204.161
056c3e23-ec99-5b12-a2d5-8dacc1833f35 | note | ○ 304.08 (a)
f4870894-c595-5676-89c1-3655dcb6d411 | note | ○ 304.11 (b)
1499bbc4-97d8-5445-b40f-dc63e62c8c3c | note | ○ 304.11 (c)(iii)
6bea931e-dc01-5ca3-ada1-c4bb28aa466e | note | ○ Table 304.111
1a4801c9-34db-5be8-9348-8fea4a05c46e | note | ○ Table 304.121
5e276bec-eb13-548c-8c42-393c0d553f7e | note | Inspection/Test Method - Document Review/ Site Inspection
73c78cc6-768c-545a-9ada-7898de088814 | note | Record of conformity - Signed ITP
dd044276-bd46-5e64-962e-b0711eb1955a | note | AP
414f04fb-dca9-5aff-9256-00bbdc1abaea | note | Responsibility - Site Engineer
197ba428-6e86-5104-8ea1-ffe601920e8d | date | Date Completed:
d41c5992-c0db-4ecb-8171-975cab200ba7 | checkpoint | 3.2 - Compaction Testing
a472dce2-9ff2-5994-932e-362682476d9a | note | Frequency - Every Lot, Every second lot (reduced frequency)
bb0d979a-b833-5736-9686-a1e6fa708150 | note | Acceptance Criteria - Minimum Characteristic Density Ratio (CDR) of not less than 97% (subbase) for Scale B, using Modified compaction effort. Material during compaction shall have a moisture content of not less than 85% of optimum.
e0505b7c-c60f-54a8-960b-01b8591bc482 | note | Reference Documents - 304.081, 304.11 (b), Table 304.111
d26f15f8-7c89-59b5-98c3-8bab5b325761 | note | Inspection/Test Method - Test point
3e45ed57-aae7-567c-b1b6-fec8751a6f2d | note | Record of conformity - This ITP signed off; Test reports
c008aed0-3675-51ef-ae40-e0afede0af49 | note | TP
b50aa93d-9ce8-529d-b693-bdd2285e2fe6 | note | Responsibility - Site Engineer
4501c3ee-d325-5362-ba4c-4b16adbc3d75 | date | Date Completed:
706b13e7-d288-40bf-b151-8a4655b98238 | checkpoint | 3.5 - Completed Surface Level Compliance
ff2c3ae3-d37a-5419-bbbf-b7d9e2e63b1a | note | Frequency - Each lot
e75f8fd1-102a-5a01-be58-1ef58ec3d89e | note | Acceptance Criteria - Layer to be finished to a smooth and uniform surface and after compaction shall conform within the following limits:
fbe73e80-9490-5885-87a9-ed82737f6d98 | note | ○ Shape: no point deviation > 8mm from 3m straight edge in any direction
ba3534f3-4f9f-559e-9177-c43499e4bc11 | note | ○ Surface level tolerances: As per table 304.062 below
8bfe2e7d-29cb-53e9-af9c-7daea85c14ae | note | – 40 measurements per lot (Scale B - Davey Street, Macquarie Street, Southern Outlet)
0e1f2ab3-3508-5de6-ae4e-3db3213e78ce | note | Reference Documents - 304.06, IFC Drawings Table 304.062
c12859b6-4009-5df4-a6ea-511f6a6d619f | note | Inspection/Test Method - Survey
a42b464b-e520-596e-b5ac-b88f63744b8c | note | Record of conformity - This ITP signed off; Survey Report
e447ac31-dce0-593e-8013-e7971a73ddb2 | note | TP
b798766c-d316-5000-92ab-3e699d2496e9 | note | Responsibility - Site Engineer
4c6ab624-8013-5ec4-9fd1-8db368c92a2e | date | Date Completed:
075f394c-80ce-4057-a11e-ef7e5dc8cf54 | checkpoint | 3.6 - Pavement Dryback and Embedment
d1c0858a-1de0-5165-9097-50d7128ee45f | note | Frequency - Prior to sealing works (only for uppermost layer below asphalt)
ce41f9eb-42b7-5f2a-ad75-d6c0ae059d08 | note | Acceptance Criteria - Scale A - The uppermost pavement layer after preparation of the surface and prior to sealing shall be allowed to dry back so the moisture content of the layer meets the requirements of Table 310.031 for each test lot. Also, pavement embedment shall be assessed by Ball Penetration testing when required as detailed in Table 310.031
9a02ee6a-2e52-590e-9887-d6a1df98ff69 | note | Reference Documents - 310.03, Table 310.031
507695b9-a376-56a0-bdc2-769c1fdac2ce | note | Inspection/Test Method - Review
280075d4-4c40-558c-9e3d-558fbb8ff1df | note | Record of conformity - Test Results
f870b41d-28c1-588a-9508-ffae6031b3b0 | note | TP
5b9531e0-7048-50dd-9331-94940801f093 | note | Responsibility - Site Engineer
d667f806-b586-545b-83e1-9ef7b9efce8d | date | Date Completed:
e82ffce7-6014-48f3-a443-0291bd6dd3c5 | checkpoint | Final Inspection
c0d66bd6-2c7f-5526-bc16-161f4f316dba | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4b4094f9-cca4-5ada-812b-56aaf4886a19 | textbox | Print Name:
3ce844e7-d77d-5973-86a8-df16e2cf17d6 | textbox | Position:
a2539846-c8ab-5499-b45b-9ecd077a6fdc | date | Work Completed On:
85fd8af8-39c4-474d-ae23-c75ec95c4642 | signoff | Add Signature
e78519cf-ceda-4932-b412-399c52203b7b | checklist | DTM-ITP-007- Concrete - Kerb, Footpaths & Islands Rev0 | itp | DTM-ITP-007- Concrete - Kerb, Footpaths & Islands
8587b250-4ac9-4954-8aa5-05e0a8064cf1 | section | 1 - Preliminary Works
848131cd-e4d8-4305-b178-ee1bdd6ee1e8 | checkpoint | 1.1 - Check for correct documentation
200ba909-2b06-5ad8-a01e-5fdf243b8ead | note | FREQUENCY: Prior to commencing any activity
279a1729-db84-56da-9f85-7a6500c85038 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
5677ebfc-11e4-54a1-ba8c-6057d92e5f24 | note | – using the correct and complete set of drawings
ef075d72-de72-553c-910a-dc0acbbb95fe | note | – all drawings are the latest revision
1d78284e-b271-50fe-b59f-1ad5172a7427 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9bbcf534-9ff4-5a1d-93ef-95b05441b3b5 | note | INSPECTION/TEST METHOD: Visual inspection
ba6dadc2-e4d5-54ea-8c22-016eeac094ba | note | RECORD OF CONFORMITY: ITP Signed
088e3529-518a-5613-9235-6c6f7628bafb | note | HP*
2c0fc233-394d-57cf-b5cf-8050565339e9 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
b8541d51-d2a4-5ce0-99f3-77e74366e671 | date | Date Completed:
962a4bd3-2c4f-4f7e-b79b-418c02c67dc3 | checkpoint | 1.2 - Implementation of all measures and controls
d43c56c6-8efb-5e15-a057-a1de82ac1675 | note | FREQUENCY: Prior to commencing any activity
8509cef8-e77a-505c-a4d9-d95adee56e5f | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
b2246847-2c35-5a5d-8e59-4eb4b7e49b48 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, SWMS, WP
04cd1ed4-686d-500e-8a22-007eb3180066 | note | INSPECTION/TEST METHOD: Visual Inspection
ea7ce021-0028-5604-bff3-da6fc2468095 | note | RECORD OF CONFORMITY: ITP Signed
12776a1e-0f86-58f4-9a30-41e6556b274c | note | HP*
1bc77a51-2af7-547e-9dfc-a0aa7b40666f | note | RESPONSIBILITY: Site Engineer/ Site Foreman
33382e64-1eca-5904-a758-aad338b40918 | date | Date Completed:
fd6e1172-46c4-47f6-a30f-01200c7b0813 | checkpoint | 1.3 - Submission & Approval of Concrete Mix Design
5d571063-878e-5abf-8736-343bb8d4fc4d | note | FREQUENCY: Prior to first concrete pour
28214e52-2084-514b-bbf2-324938006fc0 | note | ACCEPTANCE CRITERIA: The Contractor shall submit the concrete mix design details for review by the Superintendent not less than 4 weeks prior to the placement of concrete. Concrete shall not be placed until the mix design has been reviewed by the Superintendent
8cb009d1-08f6-5c5a-8c3d-6817a9e0d598 | note | REFERENCE DOCUMENTS: 610.07(b)
689b7f7f-b66e-5304-950c-4d56cfc96716 | note | INSPECTION/TEST METHOD: Verify
204785dd-9777-5ff0-8fa2-bd3b5109f2f7 | note | RECORD OF CONFORMITY: ITP Signed, Mix design approval
0e62b656-f53c-5da2-9a06-390e113aeb3d | note | HP
5fdb82a6-1fee-5a1d-84c7-598bf49fa2a7 | note | RESPONSIBILITY: Site Engineer/ Superintendent
6fecd785-ff35-55e3-8ba2-dbf290ec42cc | date | Date Completed:
f7e100be-57d9-4296-8d65-39ac21df0153 | signoff | AUTHORITY HOLDPOINT
2ae7a3fe-1db3-4675-9ef8-beb9e88ff515 | section | 2 - Construction Works
ee4aade4-b3f7-43dc-a800-8e6271705889 | checkpoint | 2.1 - Setting Out
30842fe9-7251-5f1c-a440-7948213ec842 | note | FREQUENCY: Prior to start
a742f6f2-4803-5902-bf6a-0078c224ae8a | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works
876e96d4-af04-5302-9f5d-8745ff92f441 | note | REFERENCE DOCUMENTS: 703.17
581576e5-3be0-57d3-9170-8f9972695b31 | note | INSPECTION/TEST METHOD: Verify
d9824a3e-f61b-536a-99b1-b8db339ae473 | note | RECORD OF CONFORMITY: This ITP Signed
b2ce0834-ded4-5a8a-b915-8f9aaa439d4c | note | HP
c66c67f1-b51e-5608-91f6-0b1f6b3df708 | note | RESPONSIBILITY: Site Engineer/ QAV
959532ee-d650-53f4-ac5b-95154a2c0ed8 | date | Date Completed:
c8d6e16f-9586-416d-afa3-b41c2dc3fc06 | signoff | AUTHORITY HOLDPOINT
55bbaaac-52e3-4957-8f7b-ced13500270e | checkpoint | 2.2 - Excavation Permit
d4165a4b-6a84-501d-b014-871880e4237f | note | FREQUENCY: Each lot
e8043bb3-9605-5182-9912-013aec2fff1c | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
a4d62f73-5eb6-5f44-bb79-eb9df74170ba | note | ○ Plant and equipment shall be appropriate for the task.
a6b8c4cb-e82b-5fed-836d-ab43b50b4c5d | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
df2c7cfd-6721-5b4e-acda-1c3d8c19892a | note | REFERENCE DOCUMENTS: Excavation permit
16a3b6b4-298a-54c0-bf33-e83c8a43ef0e | note | INSPECTION/TEST METHOD: Verify
49dfa375-f0d2-56eb-b0ef-1a0e6536507a | note | RECORD OF CONFORMITY: ITP Signed
dc638b44-04e8-548a-a183-b9eaad2d938e | note | HP*
6e63c946-3726-5c1f-be2c-6517287d6a54 | note | RESPONSIBILITY: Site Engineer
6bf503b7-94ed-5273-9a3a-58eb2cd15610 | date | Date Completed:
80b2fd9a-908c-403b-91a2-ed3e8fdf5ec7 | checkpoint | 2.3 - Excavation
ea7a407f-b5e2-50ca-a543-40ffeb782a1d | note | FREQUENCY: Each Lot
381abc9e-7968-51bd-b8ed-4cba47ad072a | note | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
5c8b938f-51a0-5587-9363-b146a1b97772 | note | REFERENCE DOCUMENTS: 703.2
157c0834-7bcd-56eb-abd4-6cdcbea03af9 | note | INSPECTION/TEST METHOD: Verify
5924dd57-870a-5a64-bcc3-2a34d79c4746 | note | RECORD OF CONFORMITY: ITP Signed
7654e520-2302-5c64-b127-90aa165ddeb2 | note | IP
0ccf9c8f-0e27-5400-b50b-f556521cd9a1 | note | RESPONSIBILITY: Site Engineer
c7e5d1f3-80d1-57e2-824f-d9ea59b2026b | date | Date Completed:
e2abcf28-711c-4a6b-afa4-2235906e937b | checkpoint | 2.4 - Bedding
160383a1-5c42-5088-93f5-f8cf748c19e0 | note | FREQUENCY: Each Lot
58914862-bc1e-5996-bacb-2ee65dddb9aa | note | ACCEPTANCE CRITERIA: Depth and type of bedding material varies, refer to IFC and LGAT drawings
4da9e5e9-67aa-5452-9995-10453147c22c | note | ○ Bedding shall be not less than 150 mm thick compacted for shared use paths
01dc1f94-7b89-50c8-876f-2c535c71fa84 | note | ○ Bedding shall be not less than 100 mm compacted thickness for footpaths and other surfacings
356895b9-8f54-5411-894e-3ebc14ff9798 | note | ○ Bedding trimmed, moistened, and compacted
d1885221-e459-5c15-bcd2-d3060665a7fc | note | REFERENCE DOCUMENTS: 703.21 Drawings, LGAT standard drawings
3c1ad301-28ed-50d2-9ba6-e89bea058461 | note | INSPECTION/TEST METHOD: Visual Inspection
81528387-cf95-53d2-ba03-a5e4083ea060 | note | RECORD OF CONFORMITY: ITP Signed
e273995b-57bb-5f4d-b4db-fa5ec68d1018 | note | IP
e0ed6444-6761-5949-be35-3ac8c1891533 | note | RESPONSIBILITY: Site Foreman
ebc4a4d6-e748-558a-be5e-c75d5092c0d0 | date | Date Completed:
c0d82fc7-1f08-4895-bf49-209a72373cb6 | checkpoint | 2.5 - Formwork
f6a6fc83-775c-587b-ada0-356957ed296c | note | FREQUENCY: Each Lot
a4bc42c7-ef20-51cb-acdb-f2aee4350bca | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
d9839ca4-e39b-5a0f-8ff0-63eda2b78c60 | note | REFERENCE DOCUMENTS: 703.12, AS 3610
15221b15-425f-5cec-a103-0324cc3742e7 | note | INSPECTION/TEST METHOD: Verify
5b421aef-b7ca-5979-b353-b691368964a8 | note | RECORD OF CONFORMITY: ITP Signed
75c7412e-c40b-5879-925e-6a37e176c3cc | note | IP
3ffdaa19-1947-51f3-849e-d927874cd705 | note | RESPONSIBILITY: Site Engineer
68252195-e2b8-5006-8707-388e3132eae3 | date | Date Completed:
00f3403c-9e06-425e-9668-f0eab3d41316 | checkpoint | 2.6 - Reinforcement
55357e10-898d-5ec1-b8be-0b22fcf94f7a | note | FREQUENCY: Each Lot
077296d0-0135-5ec3-9c78-83647ebb060f | note | ACCEPTANCE CRITERIA: Reinforment used shall consist of SL72 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
ffc1fe15-dbe5-542e-b5ff-406262f0f334 | note | ○ Reinforcement must comply with the requirements of AS/NZS 4671
d3352d1d-2c4c-5adf-8538-34e9cd4668f9 | note | REFERENCE DOCUMENTS: 703.13, 703.16 LGAT TSD-R18
760ad494-baa8-5d14-a304-1945da501a47 | note | INSPECTION/TEST METHOD: Verify
c60c5500-6996-52ac-998a-77b4c1f7297f | note | RECORD OF CONFORMITY: ITP Signed, Pre Pour Checklist
94039e42-0d18-5f49-841c-d56f70cfa02f | note | IP
c3540c97-bdcd-5a9d-9109-1505e8f564f1 | note | RESPONSIBILITY: Site Engineer
8f43a3b2-0c87-50f7-bd36-056900d1189e | date | Date Completed:
8e7dbbe3-6750-4205-8abd-b079a86b3d49 | checkpoint | 2.7 - Sampling Strength and Consistency
e47a9b03-8cee-58c9-a3a7-8740a86891e2 | note | FREQUENCY: Each 50m3
b3cb0e66-c46d-5d92-a796-c60301d134fc | note | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with clause 6.2 of AS 1379.
392624e0-c6fc-59cc-92e9-776aea587035 | note | ○ The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and clause 5.2 of AS 1379.
526c0475-5c86-52c2-955f-3f1753e4fb16 | note | ○ The temperature of concrete,measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
df734a89-a1c1-57c8-8b15-936295d84cab | note | REFERENCE DOCUMENTS: 703.11, Table 703.111, 703.09, 610.17, AS1379
3f564b65-006b-594c-89a0-9475952ad337 | note | INSPECTION/TEST METHOD: Pre Pour Checklist
929b9528-1810-5a4a-8854-41332a7b52e6 | note | RECORD OF CONFORMITY: ITP Signed, Pre Pour Checklist
4dae9514-edc6-5e2d-bfe6-9a42b65711ca | note | IP
81d14abd-7411-573f-81fa-c4ab60c59a3c | note | RESPONSIBILITY: Site Engineer
f7ba360e-a795-5a69-89b7-c0a445607f54 | date | Date Completed:
b8f0f4b9-4972-4541-90c2-20b88e90c745 | checkpoint | 2.8 - Concrete Placement
a4910370-9a2f-5269-8fc0-f90ca80e6d18 | note | FREQUENCY: Each Lot
e047571b-f676-512b-9305-3b494ac541a7 | note | ACCEPTANCE CRITERIA: Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
1c11404b-0f0c-5b6b-ae97-f2da99fb4bf1 | note | ○ Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
d5e96b37-c729-5f98-ac09-e84ee75226cf | note | – N20 for island infills
88e4ca67-049d-5496-91d5-622cac12160c | note | – N25 for footpath, mowing strip, pram ramps
d45f31b6-d1dd-5d10-b140-b93d20977722 | note | – N32 for kerb
28ace98e-c057-53e8-b3da-e54b726681ba | note | REFERENCE DOCUMENTS: 703.05(a), 703.08, AS1379
385d1c5c-a6b7-51ca-9dfa-ee993d1372ea | note | INSPECTION/TEST METHOD: Visual Inspection
203e8b4f-913c-502d-b646-306e75ed8712 | note | RECORD OF CONFORMITY: ITP Signed, Pre Pour Checklist
5a2f1cd4-0fd0-5606-977e-6c90582b6f6c | note | IP
1762d839-ed33-52f2-a2c7-72232b005e3d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
4c867137-f7b1-5a1a-91b5-7eee7b33cb07 | date | Date Completed:
dd73854b-0942-4906-8d0d-d26be2b82419 | checkpoint | 2.9 - Record location of each batch
b839a2cd-8dc5-5359-9c06-1cd12848ebf3 | note | FREQUENCY: Each concrete pour
3cb1475a-c9d4-579f-bc74-45ff64108bd7 | note | ACCEPTANCE CRITERIA: Batch location recorded on Load Batch Traceability Checklist
489fc38f-f762-5477-9729-8aaa4220506c | note | REFERENCE DOCUMENTS: 610.15
b5af0a83-e92c-5d01-8246-713b61906502 | note | INSPECTION/TEST METHOD: Checklist
65a01c9e-f07b-58e7-b33e-95b6c72efc27 | note | RECORD OF CONFORMITY: This ITP Signed, Load batch tracebility checklist
f48d6c73-2281-5bc9-ba2f-3b20c44211ee | note | IP
59c4e5ce-80b6-53bc-9b41-a83b3e6f0674 | note | RESPONSIBILITY: Site Engineer
d2ca7653-0cca-547f-bdf5-1e21cc40cf2b | date | Date Completed:
dfad3b82-83d2-4711-8ff5-29662ce3d2ef | checkpoint | 2.10 - Surface Finish
695f1828-be0d-5158-a096-e1ce6786d410 | note | FREQUENCY: Each Lot
0aa0fc7f-aedf-5994-ab5e-dba5aeb071fa | note | ACCEPTANCE CRITERIA: Concrete elements shall have a Class 3 surface finish (Good visual quality when viewed as a whole) for external surfaces and a Class 4 surface finish (Texture not important. Good general alignment) for permanently hidden surfaces in accordance with AS 3610.
862c44a5-b4f2-5ca6-a8f4-bc3a4c968bc3 | note | ○ Footpaths and other Surfacing shall be compelted with a wooden float.
45fb7c21-564c-5532-a749-481d8f36b10f | note | REFERENCE DOCUMENTS: 703.25
5e6408ad-bb19-5808-9e7f-a3853feaaeec | note | INSPECTION/TEST METHOD: Visual Inspection
f25128c4-a386-524d-b311-61d694ccbdde | note | RECORD OF CONFORMITY: This ITP Signed
92c25cbf-5d13-591b-b9b2-d57f2efc76cc | note | IP
6c8afe75-3ee3-5675-9872-41a39d2241ba | note | RESPONSIBILITY: Fulton Hogan Engineer
80ae7836-3c1e-5542-8090-41c3297f8fb6 | date | Date Completed:
e870c0f9-fc5a-4bce-8786-8743a865b990 | checkpoint | 2.11 - Pram Crossings
69a45381-a31f-5ea4-b558-6ad0a5a87e5e | note | FREQUENCY: Each Lot
4efb0267-b5af-5b00-b6c7-1cd0354993ce | note | ACCEPTANCE CRITERIA: Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
823bb7a5-630d-5853-a456-d5ddf9b26a53 | note | ○ Type A and B pram crossings to be constructed as per LGAT Drawings TSD-R18
9bd85418-5f9c-5721-a815-be21b9ef4108 | note | REFERENCE DOCUMENTS: IFC Drawings, LGAT TSD-R18
aba530a4-edde-56ce-9a9a-84166163095d | note | INSPECTION/TEST METHOD: Verify
533a4070-a1e6-5675-8209-80809c696ab3 | note | RECORD OF CONFORMITY: This ITP Signed
42a8686d-1ec0-56e6-a0a3-8e37415206b3 | note | IP
179d9a19-c8dd-576d-afe2-26f22d285013 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
e1cb46cc-9c26-5e88-a4c8-8af67973ccae | date | Date Completed:
22ea5a08-9264-4b2f-921d-b92a092cc3a9 | checkpoint | 2.12 - Driveways - Acommodation Works
d1a11e17-c2a3-5ef3-a0be-883e7df3ed77 | note | FREQUENCY: Each Lot
6f80ad81-b7e8-51fb-bc11-e9d35ef21635 | note | ACCEPTANCE CRITERIA: Driveways to be constructed as per Accommodation Works Drawings and LGAT Drawings TSD-R09
f065f9e6-bd2e-5bfe-80db-4fc03ecd6be4 | note | REFERENCE DOCUMENTS: IFC Drawings, LGAT TSD-R09, Accommodation Works Drawings
1e88a899-b85e-5e06-a472-913113d5bd03 | note | INSPECTION/TEST METHOD: Verify
8e94b824-8f80-56a8-ada6-525b112a1c60 | note | RECORD OF CONFORMITY: This ITP Signed
ef633e17-83ab-50a5-8d42-053bd624e81a | note | IP
baa184b8-9288-526b-bbe9-43d7d8723cbe | note | RESPONSIBILITY: Site Engineer/ Site Foreman
51a0c786-08f6-5031-9ec7-6efac3a690fd | date | Date Completed:
1478a29c-cafc-446a-a022-5e0aa64bf8cd | checkpoint | 2.13 - Joints
807419b6-0222-568b-ab2c-00880caa11f0 | note | FREQUENCY: Each Joint
a9a9d2ac-77c7-5559-98d7-3e8ab8ad2acd | note | ACCEPTANCE CRITERIA: Expansion joints shall be installated at 18.3m regular intervals using 10mm compressible joint filler. Connolly joints at 6.1m regular intervals.
b1fd5cbe-727c-5c40-bba0-c2919ff6b174 | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
42b26b9c-6362-5b6e-af5b-ec6225d5b358 | note | REFERENCE DOCUMENTS: 703.26, LGAT TSD-R11-v1
f2eba9a4-3ccc-5285-955d-edbd21326190 | note | INSPECTION/TEST METHOD: Visual Inspection
5dfcd618-bde3-52d4-b618-a47a4be656a5 | note | RECORD OF CONFORMITY: This ITP Signed
e664809c-b854-5718-8314-ac01c78f18fc | note | IP
f4fdcfca-371b-5416-8c91-5caea633a966 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
3bbb10b1-0d55-525d-925b-8a8512c76e9f | date | Date Completed:
34685acd-ace4-4460-905e-33219c9e508b | checkpoint | 2.14 - Protection of concrete
e7bcc02d-6272-5162-8b33-b26d15a8ea55 | note | FREQUENCY: Each Lot
11465fdb-040b-5989-938a-ea0baa8ee5b0 | note | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
ab066564-da23-5042-850a-66d9e93bdd22 | note | ○ No crossing until a minimum of 4 days from casting of concrete.
f2bb57d1-8d33-5891-b36a-0a7fda26c75b | note | ○ Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
f1f73e5b-6057-51a2-afe0-34b74c5d20ba | note | REFERENCE DOCUMENTS: 703.27
de77c6eb-c0c7-5cf8-80fc-87bc3ab0dc8e | note | INSPECTION/TEST METHOD: Verify
676fc484-3972-5910-9f12-acb9742c2791 | note | RECORD OF CONFORMITY: This ITP Signed
145aadc7-bc8f-5ec5-901c-f30f55b7d915 | note | IP
4fdd77d0-f759-5688-9caa-8dc8aa93efc7 | note | RESPONSIBILITY: Site Foreman
3080237d-d02c-5070-bca9-aa523bbd5abc | date | Date Completed:
0963db15-ef4b-463d-9e6e-6f7688af09fc | checkpoint | 2.15 - Curing
5de264fc-8e62-5941-84e9-7eaadce6f4f7 | note | FREQUENCY: Each Lot
3d7240b5-2c3d-5afe-8ba8-40cbbca2a685 | note | ACCEPTANCE CRITERIA: Concrete shall be cured immediately either by water curing, wet hessian, polyethylene sheeting which is adequately sealed, curing compound or a combination of these.
36283663-0f45-5d20-a173-398c9ef187f3 | note | ○ Curing compounds shall comply with AS 3799. The curing compound shall be applied in two coats using a fine spray at the rate stated on the certificate of compliance
90f81a0b-7d41-5669-8057-273f5f4e981f | note | REFERENCE DOCUMENTS: 703.1
462e0b24-4ff9-5925-af2c-370af4abea26 | note | INSPECTION/TEST METHOD: Verify
d6f6191c-f3c3-5eb1-9f1f-dde99536798d | note | RECORD OF CONFORMITY: This ITP Signed, Post Pour Checklist
d24a7f66-f70b-508b-b75e-e0199575de30 | note | IP
8cf5496f-ab6c-5eff-956b-7f217ff5a4b0 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
d93c3e63-7a5c-52d5-9804-4b7f3e94efcb | date | Date Completed:
a8f81fe1-5b24-49fe-aa89-40ab9d2e7fe2 | section | 3 - Completion
ebdd19e1-1b15-486c-b40f-0c3e04e8e188 | checkpoint | 3.1 - Tolerances
d8320208-fce3-58d9-a665-06b614ffb2a5 | note | FREQUENCY: Each Lot
04dffd92-5dd5-504c-afe0-6d701bf4388a | note | ACCEPTANCE CRITERIA: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
966d9b4c-ff3f-51d1-a92c-782a36c95a85 | note | Section dimensions shall be constructed within the following tolerances:
42b0f91a-b1a7-5361-bdc4-6a746dcc4033 | note | ○ 5mm and 15mm for width; or
3592d5ca-361c-5247-b17f-6d82d91a6082 | note | ○ ±3mm for dimensions less than 25mm.
ca4794eb-203c-55e9-9795-e0d325b41dca | note | REFERENCE DOCUMENTS: 703.15 Drawings
b4fa97ba-110c-5f00-ba9c-b225076710d6 | note | INSPECTION/TEST METHOD: As-Built Records
63438882-70b8-5512-a049-d55bcfcc0683 | note | RECORD OF CONFORMITY: This ITP Signed
24cb10ca-1733-5316-a58d-bff5c0418a9e | note | IP
2fcc4778-533b-5459-b604-2006828e6027 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
ca16d20e-00af-5855-b2e4-ff2c94896c7c | date | Date Completed:
c5377c7b-a186-4c6a-97e5-1dd9246eebb3 | checkpoint | 3.2 - Backfilling
77b3c760-eab9-5210-9850-2c9dc8452d41 | note | FREQUENCY: Each Lot
354a3e2c-171e-526b-84f0-ff309a7390e3 | note | ACCEPTANCE CRITERIA: After curing, no earlier than 3 days, backfilling shall be completed as per the below:
714b9c29-ecdc-5236-b8a8-57094d75f916 | note | ○ Topsoil compacted in layers < 150mm
b3a0c04b-3d32-586f-b246-7d3a22958901 | note | ○ Width ≥ 300mm behind edging to top of edging
452e7f74-9a9a-535c-9d72-11bbcfefb165 | note | REFERENCE DOCUMENTS: 703.29
aa6195c4-5c47-577b-84d6-f146c63ccf09 | note | INSPECTION/TEST METHOD: Verify
e71a1bcc-351b-528b-8c90-3d38cb7ef9b8 | note | RECORD OF CONFORMITY: This ITP Signed
ce2e14c7-64bc-5f71-995d-a267c4ff15b9 | note | IP
952f69a7-6a63-53f6-a680-aafd5940b646 | note | RESPONSIBILITY: Site Foreman
23ee3eff-f2e0-5065-998c-3781f3700392 | date | Date Completed:
f433ab47-c19d-4972-b509-0d74cbb57fc9 | checkpoint | 3.3 - Compressive Strength Conformance
6bf34c2f-1bac-5ee0-a803-526508f32330 | note | FREQUENCY: Each Lot
20b0b710-95e9-563d-99b9-402acc376cbd | note | ACCEPTANCE CRITERIA: The minimum compressive strength requirements for each concrete grade shall be as shown in Table 703.111.
1441a5f5-33cc-5fc8-800d-55390dc6eac7 | note | ○ Compressive strength testing shall not be required for concrete used in extruded kerbs.
f2637a17-1812-5d85-8475-33a8e134e5f4 | note | REFERENCE DOCUMENTS: 703.11, Table 703.111
6727789d-c473-5738-b5ce-34324e8e1ba0 | note | INSPECTION/TEST METHOD: Verify
c6bed0c3-56c0-55d7-8cf7-7fe5c156dff3 | note | RECORD OF CONFORMITY: This ITP Signed, Test records
639a7954-7c46-5f34-bde8-8fe603a5b94e | note | IP
c71a771b-de8e-5aa8-bd4b-6bb07a618d34 | note | RESPONSIBILITY: Site Engineer
a715de8e-efce-56e5-98ca-f4e252b09c65 | date | Date Completed:
9e8be9b9-9e52-454b-b928-dcb644eaeb67 | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
987c8610-fbee-5e1d-86b8-6f82038cdc4c | textbox | Fulton Hogan - Print Name:
f657ac47-45d6-5a51-9b00-75b42775611a | textbox | Fulton Hogan - Position:
a9f0ce52-aae3-57d2-908d-972214ff6ef6 | date | Work Completed On:
b8faee8a-407a-40f7-9a8e-1396cafa4221 | signoff | Add Signature
f803f3f1-a911-43a5-89c9-bbefbebc5f9b | checklist | DTM-ITP-008- Stormwater Drainage Rev0 | itp | DTM-ITP-008- Stormwater Drainage
47c5b580-7a4e-48d9-b3ef-4d10619b258c | section | 1 - Preliminary Works
69221198-7e3f-46f9-a9be-9188de2c9ed5 | checkpoint | 1.1 - Check for correct documentation
7f8c5b73-4308-5cd8-bc5b-73b4588f9f7c | note | FREQUENCY: Prior to commencing any activity
90bb94c7-bf6b-5639-b321-9f1088b365a6 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
970ad1dd-b639-597f-bbb3-c745ca0e298b | note | – using the correct and complete set of drawings
3eddf108-b22d-5f89-9c5b-bea713c048de | note | – all drawings are the latest revision
b7485cf0-e6a8-555c-a583-57e284eb1632 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
7703a567-7dcb-57fc-bfeb-dc728f869312 | note | INSPECTION/TEST METHOD: Visual inspection
52f2d40f-a8fe-5d15-b93a-b216e99483ed | note | RECORD OF CONFORMITY: This ITP Signed
8a7b6241-935d-5d0c-8c9e-d345048df46c | note | HP*
bcaca3ca-39ce-5680-bffd-c0dffdda4474 | note | RESPONSIBILITY: Site Engineer
ffde6022-84c0-52f6-b81c-4edc7b5249c9 | date | Date Completed:
9adb4ca9-bbc6-430c-91f5-2427cb39ac9c | checkpoint | 1.2 - Implementation of all measures and controls
fd8428b9-955c-5e81-9020-689a9c056852 | note | FREQUENCY: Prior to commencing any activity
03eaf50e-b06c-5fa0-a6b9-a3dc541c085d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, SWMS & WP
83871e18-ce89-5518-931e-986e6bda8f5d | note | REFERENCE DOCUMENTS: OHSMP, EMP, TMS, SWMS, WP
a31955e5-6901-5849-8614-d403999882ec | note | INSPECTION/TEST METHOD: Visual Inspection
fb185b71-0c65-56ce-b781-7eac638f98ca | note | RECORD OF CONFORMITY: This ITP Signed
5f7e9290-3382-56e9-bd49-0c5adbe9d959 | note | HP*
24cd3256-330e-556d-80e3-c556ab569313 | note | RESPONSIBILITY: Site Engineer
26682638-8b5d-52a8-bda5-9294f7798d47 | date | Date Completed:
0f03afd7-cc9c-4e40-8eca-1fbb821b0968 | section | 2 - Procurement of Materials
c775c4f7-7724-4b6b-8b23-f17f1f3f7e8a | checkpoint | 2.1 - Precast Reinforced Concrete Pipe Supply
af0ff8aa-e416-5b94-bf99-e3126c79b8d6 | note | FREQUENCY: Prior to works commencing
9e7a95f8-b2b5-5310-82a1-c91d9b515551 | note | ACCEPTANCE CRITERIA: All portland cement-based precast reinforced concrete pipes shall be produced in accordance with AS4058. Rubber ring joints shall comply with the requirements of AS 1646.
8fa34ae5-880a-5929-8f5b-5022bed5db80 | note | ○ Pipes shall arrive onsite free from defect or deformity.
43ec0713-4283-5451-9dc2-b63df1f940c6 | note | REFERENCE DOCUMENTS: 701.05, AS4058, AS1646
a673eaa6-5179-5e69-943a-efc1e20ff3f2 | note | INSPECTION/TEST METHOD: Verify
8511953f-0394-5cec-94f2-141a4c9e6051 | note | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
2038ec1c-d0ae-5758-ac49-7f1b234c740a | note | HP*
49d93e04-e3a3-5f8c-b68d-ffd6ea8021b6 | note | RESPONSIBILITY: Site Engineer
074fcbfc-e5ad-59ce-b6d6-c5b5941766f2 | date | Date Completed:
c9738c4a-00d7-4aeb-99fc-735a61f66149 | checkpoint | 2.2 - Precast Reinforced Concrete Pit Supply and Inlet and Outlet Structure
14b81a5d-c36b-5801-8757-8c0e76365588 | note | FREQUENCY: Prior to works commencing
fdecb4a7-8fdf-56af-86af-a0dbc34206bb | note | ACCEPTANCE CRITERIA: The supply of precast pits and inlet and outlet structures shall conform with the requirements of the specification section 705.
86be4f79-79a8-51a9-aa6d-b6268bb7d6ad | note | ○ Concrete supply shall conform with Section 610 and reinforcement supply shall comply with Section 611.
0a9f5c02-5def-554a-a173-65c5e2ec2978 | note | REFERENCE DOCUMENTS: 610.474, 611, 705.07
06f53f6f-0f3a-52c8-af3c-050bd85c63d8 | note | INSPECTION/TEST METHOD: Verify
aa31c7b8-fe9c-5857-b528-0ef1ab032093 | note | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
a643ed25-40a9-5ec0-b570-aac10a2ed3c1 | note | HP*
a324bed4-ff90-5e96-a638-57869d77353c | note | RESPONSIBILITY: Site Engineer
fb7dc051-42af-5f01-8b3c-e9c88cd6537e | date | Date Completed:
d6e5b176-6853-41c1-a755-b2d8a8d99690 | checkpoint | 2.3 - Covers, Lintels and Grates
4a954307-51d5-5d5c-8553-34a8d5863694 | note | FREQUENCY: Prior to works commencing
c4a8bb64-fabe-5da5-b9d2-d7a5d7776644 | note | ACCEPTANCE CRITERIA: Covers, Lintels and Grates shall be as shown on DSG standard drawings
9a41e196-2e38-5b5b-aa20-63ac0b7a4088 | note | REFERENCE DOCUMENTS: DSG Standard Drawings 3402-9 P20 to P30
0ede429b-3a4a-5d5a-83b0-3f4307561f7a | note | INSPECTION/TEST METHOD: Verify
e552c5bb-cd29-585c-b1a6-e993a35dac0d | note | RECORD OF CONFORMITY: This ITP Signed, Recievable Inspection Checklist
50421523-bdc4-5502-921a-9d0c94d64b6d | note | IP
22374310-e525-5bbd-9866-bdb5b06810c0 | note | RESPONSIBILITY: Site Engineer
2d89ae8d-319a-57ba-b444-9b8fab7f32c1 | date | Date Completed:
6184cbf2-9833-4353-bab0-dd995bbf2a4b | checkpoint | 2.4 - Provision for Stormwater Connections in Pits
ada54654-73cd-5c64-a047-7ac1cad3b71d | note | FREQUENCY: Prior to works commencing
091af229-5bcc-5399-ad39-66f34b3903c9 | note | ACCEPTANCE CRITERIA: Precast pits must allow 150mm diameter holes for subsurface drains and holes of sufficient diameter to allow for connections of stormwater culverts as shown on the drawings with the holes not greater than 50mm larger than required.
ef893a98-c6bb-50f9-9855-24ae92721801 | note | REFERENCE DOCUMENTS: 705.09, 705.11
fb43eae2-bc96-5ccf-8bf9-28a268d0d899 | note | INSPECTION/TEST METHOD: Verify
eebdead7-5540-5390-95c6-66585c0545ac | note | RECORD OF CONFORMITY: This ITP Signed
256d4ffa-aa52-5ef7-952b-34b170afc834 | note | IP
26355c8d-4aa9-5056-8dae-46bd2c463618 | note | RESPONSIBILITY: Site Engineer
e82ce2f4-4a8b-53d5-8ba2-e8d34cc46c76 | date | Date Completed:
8a73ae90-ef99-4de3-beb2-33865ffc05f3 | checkpoint | 2.5 - Bedding and Backfill Material Specification
0a799cb3-1c61-5c89-a8f4-714e66090b2d | note | FREQUENCY: Grading 1 test per 1,000t
106dd1dd-89fb-5224-b847-e174ce2e5d0a | note | ACCEPTANCE CRITERIA: Bedding and Backfill materials to conform to sieve requirements of Table 701.091 in the specification. Select Backfill shall also conform to the plasticity requirements of table 701.092
50bfc650-1e82-5cd7-ad59-8e4398f7f94d | note | REFERENCE DOCUMENTS: Table 701.091, Table 701.092
2db91944-f232-583a-86f8-890d1cc8a2f8 | note | INSPECTION/TEST METHOD: Verify
54de130b-109b-50b1-a7f6-bbf6fdbc004d | note | RECORD OF CONFORMITY: This ITP Signed, Quarry test report
02b655b4-1f27-5834-a335-697179b7c77f | note | HP*
3a53a52d-def8-51a8-9fad-117c5f89c9b3 | note | RESPONSIBILITY: Site Engineer
4a9ac342-d0eb-518d-9c08-c7005ceb5a26 | date | Date Completed:
1a3cf757-b83b-411a-877c-b2f19da8501f | checkpoint | 2.6 - Setout of Works
a44fb256-a0b3-59d4-855b-f3e08a9380f6 | note | FREQUENCY: Prior to works commencing
eaddbb64-ee0d-571c-9f37-92144cb04d7b | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall confirm the position of all culverts with the Superintendent.
1e11bbff-1a0d-5794-b08a-b5a6ab55ca6c | note | ○ Works to be setout to true line and level by a surveyor.
cf2aafde-ecd9-5e69-849e-b6b0fa6eb766 | note | REFERENCE DOCUMENTS: 701.1
bb72067c-ae0a-5a98-aa30-d075602a0bb3 | note | INSPECTION/TEST METHOD: Verify
ff7a6d60-d0cd-5f11-b8b1-eecc8fc204e4 | note | RECORD OF CONFORMITY: Survey records, pegs on ground & this ITP Signed
6148a768-4c6c-5490-9b87-ea51f3281d8b | note | HP
b7f5d205-349d-5b8d-a213-766ac9f0cd2e | note | RESPONSIBILITY: Site Engineer / QAV
c201bbfd-58e2-50ab-a396-a83c24525ec7 | date | Date Completed:
21ecb27b-d76c-44bb-8019-06ed60d416e2 | signoff | AUTHORITY HOLDPOINT
b9810ba5-ebec-40eb-a6e2-9c975f987256 | section | 3 - Installation of Underground Stormwater Drainage
a2865515-d33c-4396-af23-f8de62bea131 | checkpoint | 3.1 - Excavation for pipe
8be10e95-2d62-5286-92f9-a7ebfe4000b3 | note | FREQUENCY: Each Lot
6474cacb-c3df-5d31-93b9-64f0752e09ea | note | ACCEPTANCE CRITERIA: Excavation for the installation of pipes shall allow for the clearance from the outside of the pipe to the wall of the trench between 300mm and 600mm
15a31952-c20b-5e98-8f1e-5d03fbcce713 | note | REFERENCE DOCUMENTS: 701.15, Table 701.151
33564a92-33b8-56a5-88be-a69465b7ebf9 | note | INSPECTION/TEST METHOD: Visual Inspection
4b3a83bb-b6a0-554f-8fd2-a915a87c03bc | note | RECORD OF CONFORMITY: This ITP Signed
0a0ef7db-d3e4-5e31-8db0-5476ef4cd994 | note | IP
908c10ac-03cf-5e06-a8b9-fd28234b7219 | note | RESPONSIBILITY: Site Engineer
b3c70046-71ea-52c2-b7fa-0173abec431d | date | Date Completed:
da0f5240-e8a9-4494-81bb-5bcd6f698d6c | checkpoint | 3.2 - Trench Base Preparation / Bedding
b2fbe3f6-ef19-51cd-a3d1-e8d88d51596d | note | FREQUENCY: Each Lot
435b4b49-f638-58b4-9773-18a0bc37ddc3 | note | ACCEPTANCE CRITERIA: Treat or replace all soft, wet or unstable material below the level required.The compacted thickness of bedding material following any shaping necessary shall be not less than 100mm where D < 1500 mm.
751c23fa-c7a0-5871-bc5b-b21a25a468f7 | note | REFERENCE DOCUMENTS: 701.16
420c61e6-6cd3-53b3-94b1-1ab94aa22b08 | note | INSPECTION/TEST METHOD: Verify
d8c2a80f-9cd6-5e70-a563-5b2cd2e686c5 | note | RECORD OF CONFORMITY: This ITP Signed
1e772ea2-b9e7-5b7f-a08b-0b507e346201 | note | IP
0a9c542f-e023-508d-b283-fa16dcf85b7c | note | RESPONSIBILITY: Site Engineer
6cf374ec-68cf-5992-aca5-9bba8a4b77a8 | date | Date Completed:
72673e06-f986-4cb1-ae36-cb213173d162 | checkpoint | 3.3 - Laying of pipes
ba37b5fb-34cf-5caf-8777-665069af8199 | note | FREQUENCY: Each Lot
56f67604-6d40-581e-b76e-294649af3a5f | note | ACCEPTANCE CRITERIA: Pipes to be laid with rebate or socket end facing upstream, design grade tolerance of +- 10mm in 10m and +-50mm invert level of pipes at pits.
de3d2366-4666-5adb-b0de-41b4d6a67f1b | note | ○ Multiple pipes to be laid with a horizontal spacing of 0.3m for pipes under 600mm diameter and D/2 for pipes with a diameter of 600mm or greater.
4619d772-a4f2-5a52-b811-291b321c84c5 | note | REFERENCE DOCUMENTS: 701.17, Table 701.171
8852aab1-777d-5077-b718-7f1e9b6468e5 | note | INSPECTION/TEST METHOD: Verify
cf545d41-85f0-5c08-81e1-58055438231b | note | RECORD OF CONFORMITY: This ITP Signed
df9da1e8-ed0c-5b00-bb7d-797acce57557 | note | IP
f4c8db40-ff95-522c-ba84-3abd0eb50fc4 | note | RESPONSIBILITY: Site Engineer
f1e3eb1e-6a75-56cb-9ce3-7f97980d173e | date | Date Completed:
eb647d35-6445-4fe9-83bb-c19f37ceced7 | checkpoint | 3.4 - Jointing
a19a1d11-0708-5594-9573-133d8832f861 | note | FREQUENCY: Each Lot
3935ee83-04bd-5a80-8602-b2b59a9c45d7 | note | ACCEPTANCE CRITERIA: Reinforced concrete pipes shall be wrapped with a 200mm wide external joint rubber band. Rubber rings shall be kept undisturbed, clean and free from dirt and other foreign materials.
c9bdd8b8-8807-5fce-9af9-5335a0c13d1e | note | ○ Rubbers are to be inspected afer each connection and in place before proceeding to next section.
45eaa7f3-0174-5cb6-b02c-4b2fa44df84e | note | REFERENCE DOCUMENTS: 701.18
482c517f-cb64-5f2b-b924-ed0eb9ab2279 | note | INSPECTION/TEST METHOD: Verify
274638cb-2a85-5789-aa14-c08de012f64b | note | RECORD OF CONFORMITY: This ITP Signed
f2c62e56-4e53-526f-a018-455f581cf478 | note | IP
d671ff03-b674-5991-8d99-40ac585ceffa | note | RESPONSIBILITY: Site Engineer / Foreman
5d0ccc66-059d-5e73-be89-23cc43f25f2b | date | Date Completed:
29754aa9-6958-43c6-94f4-715042f707df | checkpoint | 3.5 - Haunching
d113e8fe-36f8-574f-91dc-1b7f9cc78d89 | note | FREQUENCY: Each Lot
7be6323f-7880-5f08-beb4-e257f358d5e7 | note | ACCEPTANCE CRITERIA: Haunching layer to be reaching a height equal to 30% of nominal diameter. Layer thickness shown below:
a7b8949f-9863-5e4d-91af-20e0bf59feae | note | ○ DN600 Pipe Bedding above = 200MM
ba1bd5d6-bee1-5348-ae73-9f605bb66b02 | note | ○ DN525 Pipe Bedding above = 175MM
9fb40173-01cd-56af-9e04-a3319f33d7a9 | note | ○ DN450 Pipe Bedding above = 150MM
bbe6eff8-7841-5ab5-8426-6781096574c4 | note | ○ DN300 Pipe Bedding above = 100MM
81ae7421-b928-52ee-a635-5723a46a5675 | note | ○ DN225 Pipe Bedding above = 100MM
0b2fefb0-36aa-504e-9df3-dc67849e10ed | note | REFERENCE DOCUMENTS: 701.2
42abd899-b540-58bf-a6fb-b96e4c2be879 | note | INSPECTION/TEST METHOD: Verify
cef0c1cc-0472-5650-8d7d-20d286d1156a | note | RECORD OF CONFORMITY: This ITP Signed
5d5be12f-edcd-53db-acd2-406a5993d608 | note | IP
fc607c31-3a9b-5bc9-b7a6-c7a3e2102bd1 | note | RESPONSIBILITY: Site Engineer
d11846ce-a371-5e51-8348-4d1475c5eee5 | date | Date Completed:
2d1cb00a-21d8-4d1b-ab95-f68ba096969f | checkpoint | 3.6 - Pit Connections
b59814cf-8ea8-5f55-861e-f3deec66f92a | note | FREQUENCY: Each Lot
5bdfc2c0-3730-564e-8522-8cf983609ab3 | note | ACCEPTANCE CRITERIA: Weepholes or holes installed on site shall be cut and not broken out. Pits shall be replaced if cracking occurs as a result of installing holes or if the hole exceeds the pipe dia by more than 50mm.
c6a10f03-1cc1-5538-b620-f150bc2c8551 | note | REFERENCE DOCUMENTS: 705.11
ca63ba19-a8d5-553f-8a9c-f94d03db29f2 | note | INSPECTION/TEST METHOD: Verify
68f70bb2-22e1-59b5-9d17-8cc4d66c4f56 | note | RECORD OF CONFORMITY: This ITP Signed
03271ec8-812d-508b-93ab-0d33f4485e48 | note | IP
0879c71e-ad61-59aa-8b3e-656c6b000b7b | note | RESPONSIBILITY: Site Engineer
dd4fb099-6f6d-58e9-a62a-f9c2b0b44926 | date | Date Completed:
3749c2df-23ca-46c1-aced-1f047343536f | checkpoint | 3.7 - Culverts
7f2bd848-e881-5e9e-9d2b-4b775c10496d | note | FREQUENCY: Each Lot
9abdf869-6915-5e87-8f59-ea59c160c63a | note | ACCEPTANCE CRITERIA: Prior to commencement of any excavation for culverts the position shall be confirmed with the superintendant
c2ef615e-b172-5972-b0e0-d59e4ee06bf6 | note | REFERENCE DOCUMENTS: 701.1
b5a13ba0-8195-5331-a785-2f7ba1c2d20d | note | INSPECTION/TEST METHOD: Verify
644492a3-67b0-55e0-9dba-d2d5bb728155 | note | RECORD OF CONFORMITY: Hold point release
b1848968-0dd4-5dc3-8847-e800dcdb1377 | note | HP
5202f5cc-795d-5551-b074-7fc7d5619d0e | note | RESPONSIBILITY: QAV
fc5257b2-3549-5f53-bb77-72487221cde9 | date | Date Completed:
d66ead1d-85f8-4602-9470-6ab6ebfd0082 | signoff | AUTHORITY HOLDPOINT
0a177f69-5ec7-49c2-b321-863876633591 | checkpoint | 3.8 - Tolerance
6d0134d4-751b-5aaa-9423-28e0490862c5 | note | FREQUENCY: Each Lot
3e6386c2-3b12-5c38-9951-03b78d1fb694 | note | ACCEPTANCE CRITERIA: Location of each culvert run verified by survey prior to backfilling and recorded in as-constructed drawings.
90e6c306-5c72-5a23-9a94-0c0ca46436d6 | note | ○ Tolerance:
759a04cc-728b-5bd2-9fbd-83f895e88129 | note | – Offset of entry pits required to match lines of kerbs or barriers ± 20mm
cfe6b4c7-da2f-57f5-b952-2a0937daf5fb | note | – Plan location of pits other than offsets to kerb lines or barriers ± 100mm
2c4a40aa-91a5-53b7-bdb2-e1fb44f05242 | note | – Invert level of pipes at pits ± 50mm
d046ee14-1f73-5bf2-8caa-3e9b3ffd6bce | note | – Departure from design grade of pipe runs ± 10mm in 10m provided min grade > 1:250
c52ab5d0-f8b2-5c6e-a65c-809e7c913c93 | note | REFERENCE DOCUMENTS: 701.1
eff1b7ab-5f95-59c4-afb9-bf70d839e42f | note | INSPECTION/TEST METHOD: Verify
cdd5a0fd-1ec7-517d-84d7-3c2595881638 | note | RECORD OF CONFORMITY: This ITP Signed
1abd2408-a66c-585c-a748-b9acd278f78a | note | SCP
90ece154-79fa-5c2b-aac4-6f9cfbfc1e16 | note | RESPONSIBILITY: Surveyor, Site Engineer
6953a4a8-8e22-57bb-9942-e089e3f45f78 | date | Date Completed:
cef7209a-6873-42e7-9512-565120aa78a3 | section | 4 - Backfilling of Stormwater
7c4e3467-0cb8-48a4-bc43-f55fc7dad5c9 | checkpoint | 4.1 - Filling
8f14dab1-c501-518e-a4c4-61935f06ca84 | note | FREQUENCY: Each Lot
c8544a1f-9db7-51d5-ab39-6b160702f072 | note | ACCEPTANCE CRITERIA: (i) Culvert Under Area to be Paved
4e2e658b-e602-5847-ad7b-c8f18a184fb9 | note | – The trench shall be backfilled as per requirements from Table 701.091 and 701.092. Above subgrade level, materials as per pavement design.
b7004f59-6ed2-5f4b-91e3-3ec7b97b7884 | note | (ii) Culvert Under Area not to be Paved
56dbe809-4056-5152-be08-47687179343a | note | – The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
72662cbb-9c7c-5efb-9b64-00ae4cd0f45b | note | – Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using hand held mechanical equipment.
68f28d4c-bbe1-57a0-8e2d-023b963d3dfc | note | REFERENCE DOCUMENTS: 701.19, 705.18
d075f1fc-f8fc-5942-a63f-533f4417672e | note | INSPECTION/TEST METHOD: Verify
d16af8a0-4e3a-5b09-b21d-e88bc52e6c52 | note | RECORD OF CONFORMITY: This ITP Signed, Particle size distribution certificate of selected backfill material
efef20b9-795d-59ec-b833-aaf388619d10 | note | IP
0725f950-6c69-552c-a0d3-0157439862d2 | note | RESPONSIBILITY: Site Engineer
5e49515c-25a7-58c4-bce3-5c85baee7d66 | date | Date Completed:
bf7ee17b-70a1-4741-8809-9e3437b96227 | checkpoint | 4.2 - Testing and Acceptance of Fill Materials
b381542e-64de-59f6-a3b6-340e473159d4 | note | FREQUENCY: 3 Tests per Lot tested with 20% of all Lots for each culvert tested
9a669bf1-d9c9-5e43-a58f-328eab7f20cd | note | ACCEPTANCE CRITERIA: Bedding and backfill materials shall be placed and compacted in layers not exceeding 150mm loose thickness and shall be assessed for compaction and moisture content.
cbeabd06-cf36-572c-919f-dfe71d2e49ec | note | ○ Bedding shall be compacted to refusal using hand held mechanical equipment.
ba9d91e2-0e9e-5828-9b4e-146011260805 | note | ○ Backfill material (nominal size < 40mm after compaction) shall be compacted to a mean density ratio of not less than 97% SDR.
c06c9f1b-6f86-5c6f-b526-c3bd3d7a6131 | note | ○ Backfill (nominal size > 40mm after compaction) material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
945ec37a-0f98-54a3-86a8-1ce5607b50ae | note | REFERENCE DOCUMENTS: 701.2
26269cd3-220e-5a8b-a9bd-054883be4565 | note | INSPECTION/TEST METHOD: Verify
7273558c-01cf-54ef-915c-5636e893d575 | note | RECORD OF CONFORMITY: Compaction Test Result
842c3bbe-6603-5c2d-bcd6-94b799449448 | note | TP
8dd6ff99-f357-5fbd-a4d8-8780cdca3442 | note | RESPONSIBILITY: Site Engineer
7c08ab6c-42a3-5286-8393-b1734d28ac78 | date | Date Completed:
7c02ade6-36d0-4085-8d76-c873935a2d83 | checkpoint | 4.3 - Installation of Inlet or Outlet Structure
db7e36ee-925f-5e50-8c53-56e2e1869f5c | note | FREQUENCY: Each Lot
20055737-212f-5232-8812-1febff77ee47 | note | ACCEPTANCE CRITERIA: Inlet and outlet structures shall be installed to a tolerance of +-20mm where matching kerbs or barriers or +-100mm in all other areas.
a6e9351b-58fb-5bf1-ad96-824ed1e493cb | note | REFERENCE DOCUMENTS: 701.10, 701.25
99a04fa7-0cb6-536f-b841-6e511fda03ac | note | INSPECTION/TEST METHOD: Verify
cdf3a147-6409-5648-8ced-1e42251c63e4 | note | RECORD OF CONFORMITY: This ITP Signed
48eff23c-45ee-5fe0-8320-e73eb292ecdb | note | IP
4667def4-a32d-5c7d-902f-6b1900c761fd | note | RESPONSIBILITY: Site Engineer
b0eb9528-2cbf-5f2c-ac53-b16799d62c3e | date | Date Completed:
05aee72a-a821-44bf-abba-17bfdbfeb2be | checkpoint | 4.4 - Culvert Coverage
098284d9-1a0d-537f-ae56-c012d389237f | note | FREQUENCY: Each Lot
40ad8794-e7f5-54b1-a3a6-0e40e5a1825e | note | ACCEPTANCE CRITERIA: Until the minimum compacted thickness of cover in Table 701.141 for each type of vehicle are met, construction shall not be allow to travel over the culvert
abc78094-292e-509f-b82e-43217ba78040 | note | REFERENCE DOCUMENTS: 701.14, Table 701.141
18151f62-e6e1-54e2-8b98-544507a8a5ec | note | INSPECTION/TEST METHOD: Visual inspection
0cd4dadd-c1f4-5422-9c00-51b2cfd898f7 | note | RECORD OF CONFORMITY: This ITP Signed
90fed762-3536-50d0-b620-2cccf468bdda | note | IP
f1a2fc7e-4adf-50a7-a1f0-7cdc3c97ec79 | note | RESPONSIBILITY: Site Engineer
4f98b1ce-9c11-532c-9110-d3889abf45dc | date | Date Completed:
7e33f3cb-2243-4733-a716-03f5f4fb6328 | section | 5 - Finishing and Commissioning
9b491a65-1e2f-436e-8b70-0cbb879331e1 | checkpoint | 5.1 - Finishing and Rendering Pipes
1315350b-d965-50af-a4ce-7f68882bdebf | note | FREQUENCY: Each Lot
666ae082-5f9e-57be-b4b2-d09838777781 | note | ACCEPTANCE CRITERIA: All stormwater connections and subsurface drain connections shall be cut trimmed neat and finished with cementitious mortar.
1f64556c-a8eb-5808-81d9-98224891e688 | note | REFERENCE DOCUMENTS: 705.11, 705.15
bb5ef8bf-c5b8-5610-a023-8fbbd1351801 | note | INSPECTION/TEST METHOD: Verify
72e43d61-aecc-5441-a868-88fcc87204f6 | note | RECORD OF CONFORMITY: This ITP Signed
f673d52e-efde-5125-b6f5-48b165563b06 | note | IP
1833ecbd-4f7d-51ab-aa80-297f2b84c11e | note | RESPONSIBILITY: Site Engineer
799b0844-9971-5f74-9c91-df210e46c9db | date | Date Completed:
294b43fd-2148-470c-b1d0-012c421dbde2 | checkpoint | 5.2 - Repair of Damaged Pipes
96d39035-a472-554f-bf53-145a73d3f5f2 | note | FREQUENCY: Each Lot
bda9de78-0bc6-5ed5-b7ce-93e234ba0af7 | note | ACCEPTANCE CRITERIA: Damaged pipes shall be repaired in accordance with 701.31 of the Specification, no repairs shall be undertaken without the Superintendent's approval. Repairs to be in accordance with relevant ITP.
55e75df9-c1ea-5457-bba2-18a31be59dac | note | REFERENCE DOCUMENTS: 701.31
69635456-3399-54f9-a68c-6cedc336aae0 | note | INSPECTION/TEST METHOD: Verify
fd0b6525-17f8-5237-8ffe-2090f59711aa | note | RECORD OF CONFORMITY: This ITP Signed
f52c5ba8-fa4e-5fc0-8947-da02acc54978 | note | HP
7b46850a-c9df-52ac-8732-88b15b2c4a49 | note | RESPONSIBILITY: Superintendent / Site Engineer/ QAV
e16ef4c5-7b4e-5bc9-ac6c-4ea661d4a5a0 | date | Date Completed:
2b4d847a-8c27-426e-8bb6-39eeb29226db | signoff | AUTHORITY HOLDPOINT
4aac5730-98b9-4edc-ae16-46ff82d97da9 | checkpoint | 5.3 - CCTV
cb15d638-611b-597a-8cbf-b2ecda7f4060 | note | FREQUENCY: Each Lot
6efabaf3-a43b-5164-946b-19249c624993 | note | ACCEPTANCE CRITERIA: All drainage lines constructed beneath pavements shall be inspected after earthworks to subgrade level are complete and prior to the construction of pavement layers by an indpendent organisation using CCTV in accordance with WSA 05-2013 - Conduit Inspection Reporting Code of Australia. Verify that the flow of water is not obstructed by waste construction material and check for visible signs of defects
0718b63e-c88a-57f9-8689-03a859401816 | note | REFERENCE DOCUMENTS: 701.30, WSA 05-2013
e7ae3593-0f25-53e4-8273-6d8fdb0ffbeb | note | INSPECTION/TEST METHOD: Verify
04160332-f3e8-5d6e-8fce-e6882bab7d6f | note | RECORD OF CONFORMITY: This ITP Signed
9a82d08c-d41d-5227-ab04-26bee047218a | note | HP
b726e68c-5341-5821-ad9e-1d224e44be98 | note | RESPONSIBILITY: Site Engineer / QAV
b0f5412c-6067-5747-b8d5-69f0e960d9ea | date | Date Completed:
a742b8fd-79c7-47f3-8531-705b4adc3df5 | signoff | AUTHORITY HOLDPOINT
49ab4c00-ccc9-4f41-bb81-6d2a92d8235b | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
afb867ec-45c1-59ce-a91e-598016d45f50 | textbox | Fulton Hogan - Print Name:
9bbe1327-5e26-547d-8b0a-6782bdbb6636 | textbox | Fulton Hogan - Position:
5237d247-5cc9-508e-a3dd-85ed9d8f4b58 | date | Work Completed On:
c101f08c-9db2-47ab-8923-83252faaee39 | signoff | Add Signature
8bc8354d-b78b-4610-a459-d5aff1735b25 | checklist | DTM-ITP-009- Traffic Signals Rev1 | itp | DTM-ITP-009- Traffic Signals
978eb9df-2213-467d-a087-b27dc189d7af | section | 1 - Preliminary Works
5979ee92-a087-46f6-8666-37145708a39a | checkpoint | 1.1 - Check for correct documentation
e8d77ab1-d609-5c09-ac80-ff1e3c853c9b | note | FREQUENCY: Prior to commencing any activity
0da88d19-0a5b-5e9f-8fa8-afa386f5b9e5 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
5cb875cb-f2d0-53b6-8ebf-ac33557a78cf | note | – using the correct and complete set of drawings
3ff2b733-ea22-5c49-a2f1-28775fa9c709 | note | – all drawings are the latest revision
230f52c3-2d1d-5863-842b-ef4f7df07da6 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
de1c5046-6032-56f9-94ed-9d3674e95104 | note | INSPECTION/TEST METHOD: Visual inspection
b34e183a-2285-506f-8d13-15b4a3f33aae | note | RECORD OF CONFORMITY: This ITP signed off
c2362f3e-9241-5986-9bfe-e0d93cd9710a | note | HP*
1ca9d6a3-8495-5665-ba25-42090b1c32d9 | note | RESPONSIBILITY: Fulton Hogan Engineer
e74611ef-e618-5faf-9033-f16e9cd1ab28 | date | Date Completed:
d0df7f0d-1d3c-4669-9a3a-e04d230f055f | checkpoint | 1.2 - Implementation of all measures and controls
9491d49d-abd5-5d97-a023-90c6e1e6c2b6 | note | FREQUENCY: Prior to commencing any activity
06df5f93-8dee-5053-9b2c-fe52a10ca480 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP/TGS, JSEA, SWMS & WP
6de9f26d-f4a2-50ff-8a34-743ce626a6ce | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
be2a3b1f-3e97-5572-9a0f-c1748eec7fdd | note | INSPECTION/TEST METHOD: Visual Inspection
9e356792-de7e-5cc3-8031-4e9767bc0f12 | note | RECORD OF CONFORMITY: This ITP signed off
d9882869-233b-5e59-b9cf-09ca028b6389 | note | HP*
804a6b40-0cf3-5425-822b-7f3c746291fd | note | RESPONSIBILITY: Fulton Hogan Engineer
39a567fc-3029-5ca5-afb0-7446a4dc31f7 | date | Date Completed:
369d855c-087b-40b3-81ce-5788e8d1a996 | checkpoint | 1.3 - Ensure correct materials are being used
ce1aad09-bba7-56e6-9a9b-34b16ac14a6c | note | FREQUENCY: Each Product/ Supplier
ab494bae-a8d3-513d-bd37-06aeef16987d | note | ACCEPTANCE CRITERIA: Hold Point 730.07, Written acceptance of conditions must be supplied to Department of State Growth prior to purchase for equipment outside of this Specification
a0584ad3-b71c-52b3-abd9-7dbb096625e0 | note | ○ Electrical Conduit:All conduits installed underground for electrical wiring, traffic signals and traffic services shall be heavy duty grade , rigid orange, UPVC conduit to AS/NZS 2053.2
2b88927e-1f6d-5967-b056-4a407a67eed4 | note | ○ Communications Conduit: Rigid white UPVC communication conduit complying with AS/NZS 2053.2
e9a91d30-c760-546c-a95f-9aac4e34a789 | note | ○ Pit Lids: Cable pit lids shall be in accordence with DSG standard drawings from Table 733.071.
473d8d95-1116-5540-a9e6-51131183cf3b | note | ○ Bedding and Backfill Material: Materials used for bedding shall be free from perishable matter and shall conform with the appropriate grading and plasticity index requirements specified in Table 733.061
2e5491f3-e7ab-5388-8c65-23e537915b43 | note | ○ Cable pits shall be in accordence to 730.10. and DSG standard drawings from Table 733.071
23684528-74b5-5722-8ec6-55979e1f8ddc | note | ○ Detector pits shall be in accordence to DSG Stand drawing SD-101-023
5414317c-6709-5732-adaa-e6cb71e4b047 | note | REFERENCE DOCUMENTS: 730.07
8d123269-b979-5aa2-baec-6ed7ffdff763 | note | INSPECTION/TEST METHOD: Verify
4c9d4a39-7fc7-53bd-a4bc-e1a26d1319b4 | note | RECORD OF CONFORMITY: This ITP signed off, Materials List Submited for Approval
f94dc1c9-9c33-578e-a4d9-05ace6f5f819 | note | HP
33a171fd-df13-5a95-b0a4-5910dc470e5a | note | RESPONSIBILITY: Fulton Hogan Engineer/Superintendant
1f88687c-d35b-5c7b-9d4d-e40add72405c | date | Date Completed:
f5742071-ba23-4f82-b67a-9b8586b5c28b | signoff | AUTHORITY HOLDPOINT
6e419394-9f1f-47fb-8144-47183afb104a | checkpoint | 1.4 - Pre-installation
7c1ca217-f7e0-5347-b263-4240710db3ca | note | FREQUENCY: Prior to Works commencing
d448de5e-411e-587c-8a11-d885d0448175 | note | ACCEPTANCE CRITERIA: A Pre-installation site walk is to be completed with the Electrical subcontractor, Civil Contractor, Superindentant and DSG SM Representative.
f0f1331e-f91e-5db4-b97e-d8fc093aaac2 | note | ○ The Contractor shall not commence installation of the traffic signal pedestals, poles, controller bases or pits until the pre-installation report has been approved.
858c58fd-296a-5517-b502-2f5eb7f381ef | note | REFERENCE DOCUMENTS: 730.08
e9b93e76-873c-585e-be19-0240a97c2e7a | note | INSPECTION/TEST METHOD: Verify
31cebded-c82f-590f-8290-8a8b431a52bf | note | RECORD OF CONFORMITY: Signed Pre-installation report by all parties
a6e3deeb-9f75-5996-bec6-63a9587a156f | note | HP
94141a47-896d-5ae4-a467-35cfac735547 | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendant/DSG SM/Elect Subcontractor
22005dd0-cffe-50d1-9d41-e2c73422a38d | date | Date Completed:
02c362e0-cdc6-4603-9b55-a622d5491ebf | signoff | AUTHORITY HOLDPOINT
41740bd0-8121-47c9-b7d9-adbdea600c05 | checkpoint | 1.5 - Set Out
146c6bf5-b4b9-53b6-8ec0-0a98fe9b4310 | note | FREQUENCY: Prior to commencing any activity
7020b87c-9388-500d-a25a-7067580dc673 | note | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. IFC and latest available revision used.
5290f333-f44c-5073-a3b8-8d8883ba8456 | note | ○ Where alternative foundations, conduits or pit locations are proposed, they shall be approved by the Superintendent prior to the Contractor installing items.
0d098f3c-c2ac-5756-b67b-030ed73c8743 | note | REFERENCE DOCUMENTS: 730.11
9856b128-4ce7-561c-93da-8489470d776f | note | INSPECTION/TEST METHOD: Verify
1417dc13-0699-5f58-8ac3-a497679e67d0 | note | RECORD OF CONFORMITY: This ITP signed off
f83237b5-3f8e-5fd3-be20-2dd86f5ffa7e | note | HP*
a24b0edf-60ea-57f2-b38d-b27d3b674dc0 | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendant
71a64056-b834-5726-b0a4-9cb7a6ea800e | date | Date Completed:
522278bf-388b-4ae4-bb50-46de64c50619 | checkpoint | 1.6 - Proving Services
566f17e1-51a8-584a-bf7c-f0e069d1cb96 | note | FREQUENCY: Prior to commencing works
2189083d-7d86-5a9b-a067-1ca4aad067cb | note | ACCEPTANCE CRITERIA: Underground services shall be proved by clearly marking the location of the service on the ground and physical exposure of relevant services at appropriate locations, in accordance with service authority requirements.
21129ca3-e070-5b59-83a9-eab69d546ecf | note | REFERENCE DOCUMENTS: 160.12B
4b03f6fe-2b3a-50b9-9096-5a6b8083f283 | note | INSPECTION/TEST METHOD: Verify
dadb7182-a399-512d-be78-d8f7285b49f3 | note | RECORD OF CONFORMITY: This ITP signed off
82e67865-fb8b-53af-b9a3-fbdf1ebc582c | note | HP
013d52dd-74ac-5bad-bfc1-ee4aa7001ee5 | note | RESPONSIBILITY: Fulton Hogan Engineer/QAV
8bda551f-886c-5a52-af58-71692b4d3bc1 | date | Date Completed:
8a6d460a-c7fe-4b1b-af51-0142540862fc | signoff | AUTHORITY HOLDPOINT
3dd6e944-c6b8-430e-b6c5-f16b3b2d8486 | checkpoint | 1.7 - Excavations within 3m of poles or stays, Exacavtions within 1m of Underground Assets
fd3bc247-f93f-5018-8bc2-915dd1a8bb34 | note | FREQUENCY: Prior to commencing works
2694c7b9-b2d8-5ef1-8ea3-5b2998f332f6 | note | ACCEPTANCE CRITERIA: Advice must be sought for any excavations within 3m of poles or stays, or 1m of Underground assets of TasNetworks.
7640024e-2fb4-5047-a956-cb407ae360fe | note | REFERENCE DOCUMENTS: 160.12A
cbe27b27-bd49-5a72-9b2b-e49fad229b08 | note | INSPECTION/TEST METHOD: Verify
54ac9710-06ac-5e18-b7fe-5ce52036864b | note | RECORD OF CONFORMITY: This ITP signed
b23def8c-fc9c-5c24-af59-1f691f1fdda2 | note | WP
e89b7ec5-4294-5887-b23a-2f0295d31fa7 | note | RESPONSIBILITY: Fulton Hogan Engineer/ TasNetworks
91fa1da8-5758-5575-9236-965be487a37d | date | Date Completed:
5b3c6e00-fa5e-41ee-afdd-800a11d14ad5 | checkpoint | 1.8 - Boring proposal
1fe1191f-430c-5b0a-9e82-584aede56667 | note | FREQUENCY: Prior to boring
994d7202-4496-5bcc-bc53-704b4e20dc63 | note | ACCEPTANCE CRITERIA: Detailed proposal for any boring under carriageways submitted to superintendent two weeks prior to programmed commencement
a1a1dce9-f291-5ec6-9a9a-f1fbc5a1668a | note | REFERENCE DOCUMENTS: 733.03
e7671d1f-976f-501c-992a-069cb6d14ed3 | note | INSPECTION/TEST METHOD: Verify
2885e3fa-fa76-5b5e-b63a-a9dc4fc53ce6 | note | RECORD OF CONFORMITY: This ITP signed
07385401-4ad0-5b90-b7d1-a2faf0c6b74a | note | HP
ad3fd1ee-3e53-5c4e-9972-7eb7e9b2f71d | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendant
75ca3ecc-57b8-5f94-9bbe-c68c38cd815c | date | Date Completed:
fbd8411c-ce29-4d59-a82c-6c61284f36ef | signoff | AUTHORITY HOLDPOINT
372757f0-7c02-4ecf-b67f-3e50b5d19238 | checkpoint | 1.9 - Submission of Mix Design
442a46f5-dcfa-5a05-a748-199bab6d184c | note | FREQUENCY: Prior to commencing
2df6a7c2-32c1-547c-86fa-28013310e1c3 | note | ACCEPTANCE CRITERIA: Hold Point
b20c32e8-1322-5492-a332-bcc082ba941f | note | ○ Concrete mix design complies with requirements of Section 610 and appears on the Register of State Growth approved concrete mixes.
2469abfa-e7f0-5de6-b63f-6772dd55d3a5 | note | ○ Submit for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
b8de3f1a-83ad-5a63-a449-161587bc612b | note | REFERENCE DOCUMENTS: 610.07
9dfd7f35-b722-5813-876f-dcb75027602a | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
1a9a967a-687f-5925-a468-4359f83c4aa8 | note | RECORD OF CONFORMITY: Superintendent HP Release on Procore
2efac93d-6f3f-5308-bad8-41ec927830f2 | note | HP
eac626ce-e71d-5e64-aecb-bc855d68d0da | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendant
c31c7833-a570-5c6c-bbdd-bf90b068e3e4 | date | Date Completed:
1d2350f2-177d-44da-ab4e-13d20d19c299 | signoff | AUTHORITY HOLDPOINT
c277e17b-77b0-4645-b6e3-35c17a1a5a93 | section | 2 - Conduits and Pits
f5646802-04a6-4729-9454-516890ae0abf | checkpoint | 2.1 - Excavation/Boring & Trenching
7e313455-b3bc-5ba7-828c-de97b896cce5 | note | FREQUENCY: Prior to Backfill
5cfe781e-bce0-52f7-bcde-d8d04aa3d5a8 | note | ACCEPTANCE CRITERIA: Where conduits are laid under carriageway pavements, the minimum cover from top of conduit to the pavement surface shall be 1200 mm for freeways and arterial roads, and 600 mm for local roads.
6cb88fc9-df8e-52a6-8642-9b44ae4183ed | note | ○ In areas where ground conditions preclude a minimum cover of 600mm, Superintendent may agree to alternative arrangements providing comparable level of protection
b96d3b94-9319-560f-a362-e376a0e203be | note | ○ Saw cut edge of trench within road pavement
93e745bd-a20b-5135-ad1a-57ae1b71f2ef | note | REFERENCE DOCUMENTS: 733.03
9ba137ed-1612-538d-9423-4419c533372e | note | INSPECTION/TEST METHOD: Verify
51cc07f8-a6c3-5ab2-9145-cf31b96132db | note | RECORD OF CONFORMITY: This ITP signed
016ac7e4-c58e-5ffd-8f69-0a711e6e242b | note | IP
6d4b65d5-aeba-5f8e-88dd-fe78dc8e2dd0 | note | RESPONSIBILITY: Fulton Hogan Engineer/ Superintendant/DSG SM
3f58b466-6b3b-54a3-b316-7d1a7079d63e | date | Date Completed:
38eaa046-b887-420d-8a83-792b2de9d0ba | checkpoint | 2.2 - Installation of Conduits
e0039e11-2635-5005-8ed6-7b41b78d5ab1 | note | FREQUENCY: Each Lot
22564871-8135-54b3-be93-04b55cfda016 | note | ACCEPTANCE CRITERIA: All conduits to terminate in a pit in accordance with the arrangement in DSG Standard Drawings (Table 733)
c3eee515-394e-524d-906f-8709cbd97dd3 | note | ○ Conduits for detector cables installed as per TC-1207 and TC-1320
56fb813f-780b-5d83-b0d1-15a285ac3073 | note | ○ No bends in continuous sections of conduit shall be permitted. Changes in conduit direction shall only occur at a pit.
7d758b13-54f3-5221-a712-e0c0bc6b606a | note | ○ Cables laid in continuous unjoined lengths between relevant standard points of connection
b688ff23-20a3-53ae-9cdb-84132bbfdd36 | note | ○ Changes in conduit direction or depth made by natural set or wept bend – no elbows or tees
2c45b231-07df-5a4b-b862-06498b57bf4f | note | ○ Through conduits shall be suitably aligned as they enter and leave pits to aid pulling cables
3a355096-c1a5-5764-9a2b-3540370afc2a | note | ○ Conduits shall not be subject to construction loadings
0df149c9-128c-50a7-bdc8-cdd2569e50fe | note | REFERENCE DOCUMENTS: 733.04
77e1a909-d85d-5837-b719-c8fbb730e118 | note | INSPECTION/TEST METHOD: Verify
15611206-4c91-5d36-b7e2-479bec204435 | note | RECORD OF CONFORMITY: This ITP signed WP
ba616208-daa8-5608-994a-906f585c1d66 | note | IP
ffca6881-30c2-5c12-8679-4ed776486685 | note | RESPONSIBILITY: Fulton Hogan Engineer
4043376c-e405-5ef4-8030-70db6446de40 | date | Date Completed:
4923d9e1-10e1-41db-87b5-0bb9968a13c9 | checkpoint | 2.3 - Installation of Draw Cords
d267c123-d2e8-59bf-aa9e-d407ab3fba63 | note | FREQUENCY: Each Lot
0f1f9db0-d4fe-5070-8bf9-eec77e9ee005 | note | ACCEPTANCE CRITERIA: All conduits shall be provided with a draw string secured at the ends
6dbc6f6a-9334-5ff4-a8a8-f47c79d179d1 | note | REFERENCE DOCUMENTS: 733.05
76ce0d1d-23ff-5380-bcdd-a3c72c1312ec | note | INSPECTION/TEST METHOD: Verify
cb385d48-8062-5d1f-9811-bfa2c1b916a0 | note | RECORD OF CONFORMITY: This ITP signed
92e1ba79-7205-5822-bf3e-92c1cca84015 | note | IP
4741a2f0-0f9e-5c45-b127-31e2fef10fad | note | RESPONSIBILITY: Fulton Hogan Engineer
2da87a8d-9ab0-5cb2-abb4-c8477091634e | date | Date Completed:
f1fee20a-5bc7-42de-8b52-12411a7c95c3 | checkpoint | 2.4 - Back Fill of Trenches - Open Trench
894783da-5e18-53d1-8d70-656394026915 | note | FREQUENCY: Each Lot
b11169fe-9928-56ec-b1f6-59a82673e6b0 | note | ACCEPTANCE CRITERIA: Bedding:
bc18f726-2729-569a-8349-25fbfdf71043 | note | – Bedding material shall be placed and compacted for the full width of the trench to a depth of not less than 80 mm on an earth foundation or 200 mm on a rock foundation
467d7c2f-71e1-5bed-948b-9264c6b1699b | note | – when conduits are positioned, additional 150mm layer shall be place and compacted above previous layer
bb46aab3-6832-5c2d-b6cb-c54fb7f5fd52 | note | ○ Filling:
90525c15-dd5f-518f-b5cd-69814d9cba91 | note | – conduits under area to be paved backfilled with select back fill to subgrade level
ed14830b-86f2-5b86-852b-0777a3703c87 | note | – conduits under area not to be paved backfilled with select fill to 0.4m above top of conduit and common back fill above that
c6686ec0-ffd1-51f5-ac0c-e5656243dec2 | note | – conduits may be backfilled with stab sand.
e1a0a624-0068-54d1-870c-63c37c969a52 | note | REFERENCE DOCUMENTS: 733.06
62ea5ee5-9b87-5250-a418-938942c6e0e6 | note | INSPECTION/TEST METHOD: Verify
baf8c561-9726-586c-9715-854f7136a6e7 | note | RECORD OF CONFORMITY: This ITP signed
33a398b2-3cb7-5fe4-8304-c644de0ae235 | note | IP
12561658-9f39-53e1-af29-08a85fda7b80 | note | RESPONSIBILITY: Fulton Hogan Engineer
9c4092c9-9a02-581a-9960-52e4dd60ea64 | date | Date Completed:
6e8fd152-343f-4838-95eb-69350c2e095b | checkpoint | 2.5 - Back Fill of Trenches - Inspection (Open Trench)
1570d64b-99da-5c29-9cbd-ccc926e81ccf | note | FREQUENCY: Each Lot
87a7a34f-ecf0-53d7-b471-301a4cc6f5a2 | note | ACCEPTANCE CRITERIA: All conduit, pit and foundation works shall be inspected by the Superintendent and Department of State Growth TSM SME prior to the Contractor covering the works.
8473aa9c-d322-5b80-96e1-9d2df897ab70 | note | REFERENCE DOCUMENTS: 733.06
ecbdb08f-f140-5b1e-86aa-ef83478a8ba6 | note | INSPECTION/TEST METHOD: Verify
fa9dfcba-44e5-569c-a8ef-598702048344 | note | RECORD OF CONFORMITY: This ITP signed
ad093a24-c88f-5b04-b338-ad2a80c61cff | note | HP
c6812f20-3859-52c6-8958-74b6943efff3 | note | RESPONSIBILITY: Fulton Hogan Engineer/SI/ DSG SM
3a98c040-e6cc-5e77-b8a0-c5b0d46616b7 | date | Date Completed:
37ada6d0-8bac-4440-8bc3-149eadeffaf0 | signoff | AUTHORITY HOLDPOINT
a99d8270-fee0-46cf-bfca-a3c6add70baf | checkpoint | 2.6 - Back Fill of Trenches - Grout & Inspection (Direction Bore Trench)
d6913990-8a9b-5c1a-8ca6-f3eaa5246646 | note | FREQUENCY: Each Lot
f5e279c1-7034-5ccb-aedd-7250335b6e3f | note | ACCEPTANCE CRITERIA: Before backfilling the bore access excavation, the pressure grouting shall be inspected by the superintendent or representative.
038ac1b1-1980-58ec-a4ab-f5d60839d160 | note | The annulus between the bore and the carrier conduits shall be filled by low thermal resistivity, flowable and pumpable grout mixture (comprising sand, cement and suitable additives such as flowable fill). The grout mixture shall be suitable for backfilling around conduits carrying high voltage electrical cables and shall have the following properties:
6776e1e7-1210-5674-9e0b-a4bc7df10fac | note | ○ low exothermic temperature generation during curing
92154150-0705-5ddc-a960-49a5e84ec3de | note | ○ a thermal resistivity (TR) value of less than 1.2K.m/W when fully dried
8f44a5ba-92a7-57d0-910e-47611b6419d6 | note | ○ a maximum grout flow time through a standard flow cone test of 30 seconds in accordance with AS 1478.2
a7c35cac-6aec-5711-8ce0-f144282674c8 | note | ○ compressive strength in the range of 0.5 to 2.0 MPa at 28 days
d852e996-9935-5b1b-bcd3-638d7066db17 | note | ○ a maximum heat of hydration of 35ºC when tested in an insulated 300mm x 300mm cube.
b68b5273-5295-5e83-a373-b807d696d0f9 | note | Grouting shall fill the voids at low injection pressures without causing deformation to the conduits within the bore holes. The ends of conduits shall be sealed watertight to prevent ingress of grout.
9a317700-9d3e-5d40-b22f-898548e7fa14 | note | REFERENCE DOCUMENTS: 733.06
b79daf75-036d-5eeb-add9-1ac4de39a2e5 | note | INSPECTION/TEST METHOD: Verify
7410be2d-11e8-555e-959b-66b5b22bc303 | note | RECORD OF CONFORMITY: This ITP signed
569627a9-8c34-5714-b9ae-01bca0ac787b | note | HP
abce2aea-730d-5ac6-9104-e09ce3f0b81c | note | RESPONSIBILITY: Fulton Hogan Engineer/SI/ DSG SM
a561ce16-68e5-520f-887d-6c3847a3bd8c | date | Date Completed:
9926d959-0048-47bb-9c9f-d619f0bf21c2 | signoff | AUTHORITY HOLDPOINT
c51b2b28-e043-4c3f-95f4-def70d70591d | checkpoint | 2.7 - Compaction
fdfffdcb-aa75-5293-9842-b206934d684b | note | FREQUENCY: Each Lot
8e183e3b-d03f-5771-9683-b81e67952cf2 | note | ACCEPTANCE CRITERIA: All pavement material shall have during compaction, uniform moisture content within the range 85% to 115% of the optimum moisture content as determined in the Modified Compaction test. All pavement layers shall be placed and compacted in layers to a density ratio of not less than 98%. The calculation of density ratio shall be based on Modified compactive effort.
cbe80574-7f92-5e90-a47b-ad5307a2dbd5 | note | REFERENCE DOCUMENTS: 733.06
f7cc9c5e-f121-5ea5-9998-822b7df60f35 | note | INSPECTION/TEST METHOD: Verify
8880e7b1-83fc-51da-a630-703659d7747d | note | RECORD OF CONFORMITY: This ITP signed
ecf8dcff-de0c-5dfa-9798-216f91fbcb0a | note | TP
c3c61b7a-fc0d-5102-8fa2-3b5965f08abc | note | RESPONSIBILITY: Fulton Hogan Engineer
23746b49-5c8c-5d67-ae32-622d6fdd4f6d | date | Date Completed:
fb3709ab-5f45-4cfe-8768-535cf60fba0d | checkpoint | 2.8 - Installation of marker tape
8dcf05a7-2960-5984-8d77-130838348aa4 | note | FREQUENCY: Each Lot
832239f9-7a58-58b1-8549-25a5fc0220aa | note | ACCEPTANCE CRITERIA: Marker tape at 100mm wide is to be installed 300mm above each line of conduits in all trenches where electrical and communications conduits are provided. When constructed in a shared trench, it must be ensured that the electrical warning tape is on top.
6deace48-0968-5333-97be-4f0eb5ab8ed3 | note | REFERENCE DOCUMENTS: AS/NZS 3000:2018
719c9faf-a41d-55d7-9c60-1e21ca826613 | note | INSPECTION/TEST METHOD: Verify
d1a3de82-f16b-5d7a-8044-a198e2af8c7e | note | RECORD OF CONFORMITY: This ITP signed
e5f09c8a-f092-5fd2-b63e-feac3d657b1f | note | IP
962315d2-1f33-5e59-b73f-cc874e0c8eaf | note | RESPONSIBILITY: Fulton Hogan Engineer
1d94b6eb-fd01-5a77-82ec-4205ec933988 | date | Date Completed:
bc1bdabe-4ef1-4432-8b01-87ef79fa13ab | checkpoint | 2.9 - Cable Pits & Pit Lids
63ec5b86-37e1-5438-8508-57ad2c1c7dda | note | FREQUENCY: Each Lot
610a4fc4-4ade-5700-a333-c195e72ce64f | note | ACCEPTANCE CRITERIA: Cable pits constructed and installed as per drawings
24b1fafd-21c6-56ce-b984-518d61d689c6 | note | ○ Cable pits for traffic signals constructed and installed as per DSG standard drawings from Table 733.071
b4f9823c-cce9-5745-84fa-69d946a1395c | note | ○ Cable pit lids shall be labelled in accordance with SD-101-022 as appropriate.
d1e4e0ad-8b31-5f31-b568-30c3953c8855 | note | ○ Reinforced concrete apron installed around pits that aren’t within footpath area (unsealed area)
d0a02380-5a10-52e8-b2fc-26b17bbef718 | note | ○ Heavy pit lid provided where pit is located in trafficable areas
e9f63dd8-a982-5293-ae7c-c5e7074fffd3 | note | ○ All pits, junction boxes or terminal pits for electrical purposes shall be watertight
adea43b6-cefd-56b3-b156-bd2ae17b0140 | note | ○ Pits shall be constructed such that the level of the top of the pit lid matches surrounding finished surface level, top of pit wall is finished so that lid fits without movement
0c73dabc-940c-52a2-9d08-f85c0bd8e846 | note | ○ All conduit connections to cable pits shall be neatly made and the ends of the conduits trimmed off and fitted with a conduit bush. The area between the conduit bush and pit wall shall be stopped with a suitable sealant that bonds to the pit wall and the conduit.
9473c3eb-510b-5121-b009-b09dfaee78f4 | note | REFERENCE DOCUMENTS: 733.07
ca8b4e11-c0fd-535f-9f97-b1a7a1fca2f4 | note | INSPECTION/TEST METHOD: Verify
e04df5a2-b06b-5d0a-aae6-4dce7ef5048e | note | RECORD OF CONFORMITY: This ITP signed
9b8f299f-e6a9-5767-b814-22a2c4fc16b0 | note | IP
159fe0c2-0a22-5e02-9fff-162d408d8d65 | note | RESPONSIBILITY: Fulton Hogan Engineer
7b18d6cf-4fd9-5129-885a-6b65d72a38a0 | date | Date Completed:
26290f90-8886-4664-94b7-4eb81dd80d8c | checkpoint | 2.10 - Asbestos Removal
8660796d-40aa-5654-a165-74b2cd35c73b | note | FREQUENCY: Each Lot
f9f361f4-adb2-57c9-b957-7e38f7f8ffe9 | note | ACCEPTANCE CRITERIA: Asbestos or suspected asbestos found on site that is not identified in the Project Specification shall be immediately reported to the Superintendent. The Contractor shall not disturb any asbestos or suspected asbestos unless approved by the Superintendent in writing.
f8ad81b7-57cd-52ed-bf21-6e7f564aac28 | note | REFERENCE DOCUMENTS: 733.07 (b)
07088681-2642-5ee4-9806-87a577ecc88b | note | INSPECTION/TEST METHOD: Verify
05ef8bd7-f784-5c18-a8f7-2e0f45cc97cb | note | RECORD OF CONFORMITY: This ITP signed
1d683fef-4130-5001-bdcb-4f02520eda97 | note | HP
e3b5d3c8-3025-57dc-b3a3-711c22a89351 | note | RESPONSIBILITY: Fulton Hogan Engineer/Superindentant
461d90ca-f12b-568c-bd6b-a5c98fdcce17 | date | Date Completed:
72b49e02-c820-47ad-9d01-38cd67a061d3 | signoff | AUTHORITY HOLDPOINT
572974aa-bfd0-4c33-9ed7-bb3435a06f74 | checkpoint | 2.11 - Pit Lid Surrounds
3ca5372b-ce89-52a9-b177-911addaacf72 | note | FREQUENCY: Each Lot
acf5f112-64e2-5163-824f-64b4b74fcb58 | note | ACCEPTANCE CRITERIA: Before the pit lid surround or pre-formed collar is cemented into position an inspection by Department of State Growth Superintendent or representative must be carried out. Cable pit lids and frames, where required, shall be installed with an approved surround. The app types of pit lid surround are:
7603872d-709b-555d-a66a-c5a5e9c91e06 | note | (i) a poured ‘in situ’ concrete apron (typically used where two or more pits are co-located)
6652c2d3-41c2-5615-ad47-600d244e9806 | note | (ii) a steel pre-formed collar that requires concrete in-filling ‘in situ’
f9bef7d5-b505-5ecf-988f-a2d8f7e59dcd | note | (iii) a pre-formed composite material collar.
f11a79d0-22b2-5d01-ae42-5d84efa29f83 | note | REFERENCE DOCUMENTS: 733.07 (c)
7a6942a3-52f9-5eaa-9579-53b7d869a2ca | note | INSPECTION/TEST METHOD: Verify
fca4d1ec-bf08-553a-838f-5993f12893eb | note | RECORD OF CONFORMITY: This ITP signed
6dc651d9-ebd0-5153-b80f-e137d309deb1 | note | HP
dba372d5-6c29-57ed-9673-e8cb381bc641 | note | RESPONSIBILITY: Fulton Hogan Engineer/Superindentant/DSG SM
98843029-8538-5a5e-acc2-bc1084fc696b | date | Date Completed:
dee30665-39a0-4171-9fae-cc9bdd000539 | signoff | AUTHORITY HOLDPOINT
09c5c38d-39ef-4686-b0ae-18c2d024156e | section | 3 - Posts/Pedestals
61298ee7-5b74-452b-ad6f-c781dfb21a2a | checkpoint | 3.1 - Determine footing required at location
4f2160e2-0926-5392-b03b-c6b69d23bac4 | note | FREQUENCY: Prior to Commencing
2793d22f-f8c2-5365-9540-93a9615ba10b | note | ACCEPTANCE CRITERIA: Check against IFC Drawings and standard drawings that the correct footing will be constructed each area
7fa7d725-a3e1-5c2f-94ae-c99270f22e7f | note | REFERENCE DOCUMENTS: IFC Drawings
f02c3703-45c7-53a1-9802-05d2a36dbc07 | note | INSPECTION/TEST METHOD: Visual Inspection
981d0fb6-1d66-59d4-b35a-79383e2b0720 | note | RECORD OF CONFORMITY: This ITP Signed
7293e875-4ae3-5e81-9690-8941639f0382 | note | IP
b4c02cc6-57da-51fc-ba70-8b2781270df4 | note | RESPONSIBILITY: Fulton Hogan Engineer
e8297500-a52d-5fd6-9975-bf534f968bf0 | date | Date Completed:
a8f00aba-5473-426d-8d54-8d90172bff75 | checkpoint | 3.2 - Excavation Levels
b62a5cac-4a79-5e23-b713-9324146a0bdd | note | FREQUENCY: Each lot
db5ff1b6-45d9-530a-bccf-3c9ad6dac33b | note | ACCEPTANCE CRITERIA: Check levels conform to relevant drawing depending on type of pole to be installed.
6fdf15c6-83b0-5151-8827-f1ecf99122c6 | note | REFERENCE DOCUMENTS: IFC Drawings
df1eb911-8267-5f82-a52d-94f67c3ccdb5 | note | INSPECTION/TEST METHOD: Visual Inspection
96111037-e5fb-5973-b496-72beeb7c09d7 | note | RECORD OF CONFORMITY: This ITP Signed
3cbd7144-057f-5c54-9a1f-3e1fafaca4fb | note | IP
49a33737-6c3a-55dd-9cfd-148a48d8c5fa | note | RESPONSIBILITY: Fulton Hogan Engineer
a28959bd-0c6e-5bbc-9c70-7207e975ab26 | date | Date Completed:
c0f18b75-e46e-4587-8fdb-86c6c42e31eb | checkpoint | 3.3 - Rag Bolt Assembly
bd5ce8d5-c8db-59b6-a856-385bed95711f | note | FREQUENCY: Each location where rag bolts are required as apart of Standard Drawings
33f989b1-0cfb-578c-b53a-610f97878091 | note | ACCEPTANCE CRITERIA: Check rag bolts are assembled as per DoSG Standard Drawings and/or manufacturers specifications (relevant to type of foundation required). Rag Bolt assembly shall comply with Standard Drawings TC-1200 and/or Table 730.111 drawings
d6184d74-20ea-5fb5-8e4b-a89548da1d41 | note | REFERENCE DOCUMENTS: State Growth Standard Drawings - Rag Bolt Assembly TC-1200
076bc63a-d8c7-5b18-8bab-1ce5d8618ba4 | note | INSPECTION/TEST METHOD: Visual Inspection
25e307b3-23b7-5e8a-ae17-3bd55bf53227 | note | RECORD OF CONFORMITY: This ITP Signed
20aad30e-b7f1-5bd9-af2f-53032c33ea18 | note | IP
e47a6de9-8272-5889-bb45-96b830087e97 | note | RESPONSIBILITY: Fulton Hogan Engineer
1e7e6808-cd10-572c-9adf-62dbae2132de | date | Date Completed:
08e58e6b-0043-46bf-aa27-8ed0bc4bbf57 | checkpoint | 3.4 - Pre-pour inspection
8826da91-6ac3-5a83-b49a-42aee484ddbd | note | FREQUENCY: Prior to covering the works
37db1405-9997-51ef-b115-7bcf0948109b | note | ACCEPTANCE CRITERIA: All conduit, pit and foundation works shall be inspected by the Superintendent prior to the Contractor covering the works.
f9e8ea63-faaf-5af0-9ed8-4f7135022972 | note | REFERENCE DOCUMENTS: 730.11
bac6fa7f-da48-5631-a19e-e0b4b28dff41 | note | INSPECTION/TEST METHOD: Visual Inspection
5bcd0d8b-1480-56c1-83af-b3359b2ad95d | note | RECORD OF CONFORMITY: This ITP Signed
d5d6af73-2863-5c22-aa05-bdf68ea8de1e | note | HP
8787c7d2-f31e-5cc6-a526-7e8d2f09c03e | note | RESPONSIBILITY: Fulton Hogan Engineer/Superindentant/DSG SM
b481b0fd-a3b7-5eb1-aa7b-a10aa042a468 | date | Date Completed:
cb64f576-81ea-4478-b8b5-902b5fc89f61 | signoff | AUTHORITY HOLDPOINT
20392813-74fe-4ba8-8635-54ffada0bdda | checkpoint | 3.5 - Pouring of concrete - foundations
9d4432c9-6279-5552-b4cc-f39b994fe54f | note | FREQUENCY: Each Lot
1a8c8f07-e4f9-5e50-add6-e97efe10d644 | note | ACCEPTANCE CRITERIA: All concrete works shall conform to VicRoads standard drawings and to be undertaken in accordance with Section 730.13 of the Specification and Section 610. Concrete to be a minimum concrete grade of VR330/32 or approved alternative.
9469bb22-6699-5d92-9c7f-173315f0eca2 | note | REFERENCE DOCUMENTS: 730.13
96d0cf9e-6c91-58da-89cb-fde187e3db9b | note | INSPECTION/TEST METHOD: Document review & Site inspection
680311fa-29af-5c16-8d73-2b8241cb6cf3 | note | RECORD OF CONFORMITY: This ITP Signed
5801f43b-532f-5925-af8e-28846e9c730e | note | IP
2e9adb9d-9a69-5655-97db-af86e8bcee4d | note | RESPONSIBILITY: Fulton Hogan Engineer
ae370273-d480-581e-9576-7a5e5e8222de | date | Date Completed:
55d0529b-c89e-47bb-a546-095d77731599 | checkpoint | 3.6 - Sampling and Concrete Testing
8c0ae402-1260-526f-ad48-4db959e5ae33 | note | FREQUENCY: Each Pour
641c59b9-a87c-5192-af5f-c950f537cdbc | note | ACCEPTANCE CRITERIA: Concrete Strength Grade shall be N32 to the requirements of AS 1379.
c35a8892-ccfc-5c44-8e15-8940aa0e3bb8 | note | ○ Testing to be in accordance with AS 1012 and AS 1379. Each sample of concrete shall be testing for compressive strength and slump.
b21c93f3-de97-5fd2-b393-9478d31b2ce5 | note | ○ Standard compression tests shall comprise of 3 cylinders ( 1x7day, 2x28day).
6f1d9643-0985-54f0-a672-9148b1224c2a | note | ○ Sampling shall be undertaken as for Table 730.131:
0c55c44e-e55c-53a2-9f64-a3f74c2739f8 | note | 1 Sample = 0-10m3
d07f4ccd-6683-598f-be59-61f49b5ba38c | note | 2 Sample = 10-25m3
e9759f93-f813-5a3e-95ea-39247eef77e2 | note | 3 Sample = 25-50m3
d442d104-e4ac-50fe-815d-84f1aa966178 | note | 4 Sample = 50-100m3
b452ed37-cda9-5b62-b2ef-c71a50aa43aa | note | REFERENCE DOCUMENTS: 730.13
189f495f-e248-5db1-b3ad-cf19eee64ae1 | note | INSPECTION/TEST METHOD: Test
258a467f-5e46-583c-9284-0849cbc0a7c8 | note | RECORD OF CONFORMITY: This ITP Signed
183d8e35-94e7-558f-bd7b-8d6d19efa3ec | note | TP
6769a530-7640-56a6-9a8f-0817b19cb987 | note | RESPONSIBILITY: Fulton Hogan Engineer
8c0fd196-60a4-5884-ae78-5f5b970dce94 | date | Date Completed:
812e79d7-1f06-47bd-9121-f59de876b716 | checkpoint | 3.7 - Standing of Pedestals and Poles
5135cb25-9516-58f4-a952-3d97229dccde | note | FREQUENCY: Each Lot
d3129abc-e170-56ce-b123-73d7009be7e2 | note | ACCEPTANCE CRITERIA: Pedestals and poles shall be installed in accordance with the following requirements:
2db6c510-d0a6-5367-bcd2-bc9874322223 | note | (1) for all new and major remodels, all Type 2 pedestals shall be 2T
ba41776b-6c89-5d84-9658-37b8dcb8bb81 | note | (2) for minor remodels 2T pedestals shall be used
5903b7c7-3453-55dd-b09e-1e64f2e6c7b0 | note | (3) where specified, Type 3 pedestals shall be installed for pedestrian detectors
98e24ae8-0b3f-54d3-ad02-fa7137253f1b | note | (5) pedestals and poles shall be fastened to the rag bolt assembly cast into the foundations, as detailed in Standard Drawing SD-101-003, with the nuts tightened to 150 Nm of torque
056af3e6-1bcf-5885-9df7-4c89167ee97f | note | (6) pedestals and poles shall be installed such that they are vertical when fully loaded
665dce2f-06cd-5235-9e22-b03a23a5984f | note | (7) pedestals shall not be stood within 48 hours of casting of the foundations
b5150a2b-4213-51a8-a170-e47a936c9cc9 | note | (8) JUP, MA and JUMA poles shall not be stood within 7 days of the casting of the foundations
63578d8e-94cb-585c-8fae-befaac7c613f | note | (9) JUP, MA and JUMA poles shall be installed such that the access door is on the face furthest from the traffic flow.
c83dc7c9-e5cd-5120-952b-d2aca7be8790 | note | REFERENCE DOCUMENTS: 730.14 (A)
aec6b87d-1864-50e9-be45-e2c1860d4ef9 | note | INSPECTION/TEST METHOD: Verify
06822132-1192-56de-b9de-ad5468f38e88 | note | RECORD OF CONFORMITY: Test Reports
55064c48-2738-58e1-bd33-e48bcbb81c5a | note | IP
169be109-dbdf-546d-a3b0-238b68d3ff7e | note | RESPONSIBILITY: Fulton Hogan Engineer
fdb476e0-f588-5c2c-b8f2-18a9fc9c30db | date | Date Completed:
9600b003-feb9-47a9-b441-9b000b84737b | checkpoint | 3.8 - Post pour Inspection
4e78a6cb-a640-5580-8808-712a594fb515 | note | FREQUENCY: Each Lot
770c6d9d-931c-5cef-a931-3a6d8bebf19e | note | ACCEPTANCE CRITERIA: Complete post pour inspection. Cure concrete and inspect for cracks and defects
f9ff4f46-afe4-5422-81be-b9da6ee3e54e | note | REFERENCE DOCUMENTS: 730.12 (d)
b2e1b7ba-fe43-5e2a-8264-74fd9b523496 | note | INSPECTION/TEST METHOD: Test
aa89d5db-f654-5cdb-ab3d-c6cb0fcc7f5e | note | RECORD OF CONFORMITY: This ITP signed off
5ece1989-8dff-58fd-89d2-7a771185399d | note | IP
75bff59d-6651-52a1-8db7-35aadf91d311 | note | RESPONSIBILITY: Fulton Hogan Engineer
9afc961e-88c4-5502-8fca-587f83c26a2a | date | Date Completed:
30e630ad-4c79-4bb4-ab79-e507febb38d5 | section | 4 - Lantern/Hardware Installation
3d021c98-6d98-4153-9794-2b185dfec0e4 | checkpoint | 4.1 - Hardware Installation
9da0c1a4-a1db-5570-a5c8-b16c68939898 | note | FREQUENCY: Each Lot
8ce38d4f-f004-5f7b-937a-9596281666bb | note | ACCEPTANCE CRITERIA: Hardware shall be installed in accordance with the following requirements:
00fb4145-2bc8-5136-8d3b-5d441471fe66 | note | (1) all lanterns shall be mounted vertically, using standard straps securely fixed to mounting brackets or lugs
58a5ce82-f12e-5919-b96a-e8f6c6ea4364 | note | (2) upper mounting brackets shall be oriented and fixed to the top of pedestals in accordance with Standard Drawing SD-101-102
107864c5-ed0b-5cd1-9b53-e93d77ddca58 | note | (3) two-way and four-way lower mounting brackets shall be fixed as required to provide suitable mounting points for the installation of lanterns
cf00e8a2-c281-5ce1-bb9d-cedb9f6fb23e | note | (4) the top and bottom of each lantern must be firmly attached to ensure that it will not rotate
bf4ee383-2881-54bf-b8d9-f1d1b3ba5b48 | note | (5) each lantern shall be attached so as to provide an unobstructed line of sight to the traffic which it controls, and such that the potential to be hit by vehicles is minimised
14645421-3da8-559e-8173-0645293524a7 | note | (6) external cables and conduits shall be fixed to pedestals, poles or supports using suitable plastic cable ties
f79e8aee-7b9a-5171-9d9d-9632cba8d4b9 | note | (7) cable connections to lanterns shall be of sufficient length to hang below the cable entry point on the lantern (this is referred to as a drip loop), but not hang below the lower mounting strap, as shown in Standard Drawing SD-101-103, and shall be securely fixed by means of cable ties allowed; this will typically require the cables supplied with lanterns to be replaced with longer cables when installed on mast arm outreaches
1762d9e0-0af2-5d50-bf08-5ebf67271188 | note | (8) cable connections to lanterns shall be made with continuous lengths of cable; no joins shall be
a89a640f-6e8a-51eb-9812-fccc2b12edd3 | note | (9) junction boxes, key switches, and all other electrical hardware shall comply with the relevant Australian Standards.
c33ca77d-6e2f-5a7f-b0b4-aae20fc47a20 | note | REFERENCE DOCUMENTS: 730.14 (c)
c756059b-0e5e-5874-94e8-7469d535ca74 | note | INSPECTION/TEST METHOD: Visual inspection
8c6d4301-4b29-5381-aebd-c7224dae45a0 | note | RECORD OF CONFORMITY: This ITP signed
70fdc61f-6f8d-573e-a9c9-b5a3959e8362 | note | IP
830b6707-6b51-5b6a-8baa-f44f8ca28b62 | note | RESPONSIBILITY: Fulton Hogan Engineer
af2f745a-d771-5c5d-b83b-d945101dd06a | date | Date Completed:
61b9a707-54de-49cd-952b-d0ee581a9337 | checkpoint | 4.2 - Lantern Mounting Height
f70ac781-155b-5a83-9f42-6aa9c3156922 | note | FREQUENCY: Each Lot
6db8b931-eb7c-5f9d-b925-d070a83e2afe | note | ACCEPTANCE CRITERIA: Lantern mounting heights shall be in accordance with the following requirements:
d4fe7ce2-b9cd-50da-a6f5-90eed3860991 | note | (1) mounting heights for lanterns on 2T pedestals shall be as specified in Standard Drawing SD-101-202
92ad28d5-14f7-5990-a7cf-09d4866f9606 | note | (2) lanterns installed on the vertical section of an MA, JUP and JUMA shall be mounted on lugs so as to give the same mounting heights for the respective lantern positions as specified in Standard Drawing SD-101-202
8ae89189-725b-5573-bee2-ff6d7c445d36 | note | (3) lanterns on the outreach of an MA or JUMA shall be mounted in accordance with Standard Drawing SD-101-011
759ccc53-95c8-52d2-8224-7f2dc9142db6 | note | (4) 1 and 2 aspect lanterns shall be installed to achieve the mounting height of an aspect of the same colour as if it were part of a 3-aspect lantern
b73ed369-663e-5a56-99e3-5637bda9fce9 | note | (5) 2 aspect bicycle lanterns shall be mounted at the same height as pedestrian lanterns
ca90d977-2e4c-5f91-881d-5d1ac2a51731 | note | (6) aspects fitted with white or lunar white lenses shall be mounted at the same height as a green aspect
b59875c5-bf0d-5ee0-904b-d37e02e883ed | note | (7) lanterns mounted on poles not belonging to Department of State Growth shall be mounted at the same heights as specified in Standard Drawing SD-101-202
c91fbe51-b318-5d29-9166-a6b95cb74124 | note | (8) internally illuminated signs shall be mounted at a height to provide a clearance of not less than 2.4 m from the finished surface level
6154c8fd-c529-548a-8e59-b2c787321a9a | note | (9) flashing yellow signals used at pedestrian crossings shall be mounted at the height specified in Standard Drawing SD-101-203.
24bc9732-4299-5dfb-b90d-9b6c414cdef5 | note | REFERENCE DOCUMENTS: 730.14 (d)
0cb6ce64-e1ce-5c9d-860e-b83f2ef9c669 | note | INSPECTION/TEST METHOD: Visual inspection
29db6d0f-d4a9-56e0-b507-0421ffe90143 | note | RECORD OF CONFORMITY: This ITP signed
09931e9e-22ef-581d-9ccf-8b8a694167af | note | IP
d027ffe4-484f-550d-a387-1950506ff914 | note | RESPONSIBILITY: Fulton Hogan Engineer
7151fef1-4d32-5af5-9629-75f76ccdd92d | date | Date Completed:
3e39634c-0bd8-4613-99b1-c50ea3febea7 | checkpoint | 4.3 - Lantern Mounting Locations and Allignment
8e271a5f-5569-5c03-b5e8-eb0076a5d419 | note | FREQUENCY: Each Lot
669e6f2a-55b8-5849-a083-418fa164536a | note | ACCEPTANCE CRITERIA: Lantern mounting locations shall be in accordance with the following requirements:
ac38ce76-794e-573d-b57b-f3afb559d898 | note | (1) lanterns shall be mounted as indicated in Standard Drawing SD-101-102and SD-101-202
f7adc9c0-597c-5a0e-bb8a-0db9b1b6101a | note | (2) pedestrian lanterns shall be mounted not more than 1 m from the projection of the nearest crosswalk line
f4699afb-0edb-55ca-bec6-740ccd0931e6 | note | (3) where 2 aspect bicycle lanterns are installed adjacent to pedestrian lanterns, the bicycle lanterns shall be located on the furthest side from the pedestrian crossing (i.e. left side of the pedestrian lantern when looking at the displays).
980e8631-7f9b-593e-94a7-b1a078c33394 | note | The alignment of lanterns shall be in accordance with the following requirements:
1122d30b-9a1e-5c81-b537-f4ed666e57f6 | note | (1) vehicle lanterns shall be aligned so as to provide optimum visibility for approaching traffic considering road alignment, speed, visibility and other site characteristics
a1f36cc7-a32c-5b83-a527-150614f62962 | note | (2) generally, lanterns shall be aimed at a point on the centre of the approach, at a distance before the stop line as shown in Table 730.141.
34cda7fc-feb9-50f9-b26c-377651e4fca6 | note | (3) pedestrian lanterns shall be aimed at the mid-point of the cross walk on the opposite side of the carriageway to which it applies.
1f0a42eb-e030-59ff-ac0a-9334a18a61b9 | note | REFERENCE DOCUMENTS: 730.14 (e & f)
2e9470c0-a7fd-5403-a84e-c27cc5fea045 | note | INSPECTION/TEST METHOD: Visual inspection
492643c8-71ed-55bb-a645-ef9f8ab6d1f0 | note | RECORD OF CONFORMITY: This ITP signed
c663de0a-3b58-57af-ab3f-bd22a17e32e1 | note | IP
58ae6718-dcad-581f-a794-44f52bc7f7b1 | note | RESPONSIBILITY: Fulton Hogan Engineer
056710b2-fbe3-5e22-885d-bdfd91bc0b0d | date | Date Completed:
6b345740-d4d0-42e8-a596-3b513e4c0033 | checkpoint | 4.4 - Target Boards, Visors and Louvres
26c27054-5eb9-5d00-8f74-968c00f55252 | note | FREQUENCY: Each Lot
80c64566-ccd7-58b4-a1b8-4d2e809a4360 | note | ACCEPTANCE CRITERIA: All target boards shall suit the housing type (metal, plastic) of lanterns and include a white border around the outside edge
dec3e987-3118-547a-85bf-7d385a0cb85c | note | ○ Target boards shall be fitted to all lanterns in accordance with Standard Drawing SD-101-103
372925f9-e480-5e65-a212-eb25018da29b | note | ○ All visors for vehicle lanterns shall be type 3 with no cutaway.
9fa7155d-eae4-5535-ba6e-1b4d5f721193 | note | ○ All visors for pedestrian and bicycle lanterns shall be type 4 with no cutaway.
782c3484-c352-5305-9f63-48931afd1b0d | note | ○ Refer to Department of State Growth Standard Drawing SD-101-104 for details of the visor types.
3403fff7-e6bb-58bf-9209-4252b407bfcc | note | ○ Louvres shall not be installed on LED lanterns unless otherwise specified.
5f48675c-6ed8-5c67-9844-2ea52877a58e | note | REFERENCE DOCUMENTS: 730.14 (g)
ce888629-ca5f-523e-b658-a41808b3062b | note | INSPECTION/TEST METHOD: Visual inspection
1f3dfde2-4e01-5a99-9cc7-d5ee4178ad2a | note | RECORD OF CONFORMITY: This ITP signed
62b07c95-eb95-5a55-8fee-02203e6ec82c | note | IP
31983706-b671-56d3-8676-75c8b466aa2e | note | RESPONSIBILITY: Fulton Hogan Engineer
4a3a015a-dfa1-536e-bbc4-7e7bc85f9693 | date | Date Completed:
f6c4b2fc-0361-4529-b0f2-ba824425332d | checkpoint | 4.5 - Installation of Pedestrian Push Buttons
24463ff0-19f3-503d-bb2e-fbd5036ffa3c | note | FREQUENCY: Each Lot
d9cad650-4281-539c-96cb-3de348e1a3cd | note | ACCEPTANCE CRITERIA: Pedestrian push buttons shall be installed in accordance with following requirements:
9364a23f-f9ca-597a-9315-779579e5fa07 | note | (1) pedestrian push button assemblies shall be mounted clear of any access openings and such that the centre of the button is 0.9 m above finished surface level, as shown in Standard Drawing SD-101-202
c1b8e0cc-7f66-5c1b-b8d0-e358badb95a1 | note | (2) Pedestrian push button shall be mounted within proximity of ramps, preferably in ramp wings to enable reachable access maximum distance is 300 mm as specified in Standard Drawing.
661b2f40-ea8f-5feb-9992-dd3a8f89ada4 | note | (3) the face of the button shall be in line with the direction of the associated walk lines
98c39d09-5a25-5e81-9f3e-b9083e655f26 | note | (4) the tactile arrow indicator shall be oriented to indicate the walk direction to which the button relates, with the arrow pointing up to indicate a straight ahead walk direction
d087d811-7606-5d5d-b677-46aa29440a2d | note | (5) where a single button is mounted in a median, a double headed arrow plate shall be used with the arrow oriented horizontally and the front face of the button shall be parallel with the walk direction
a5045ade-0997-5edc-be90-5ef2631c8abe | note | (6) a label complying with Standard Drawing SD-101-402 shall be installed on the pedestal or pole directly above each pedestrian push button.
67e5806e-075d-595d-8624-a02df2f35742 | note | REFERENCE DOCUMENTS: 730.14 (h)
c1cb86e9-9866-5dca-b917-06746fe7781e | note | INSPECTION/TEST METHOD: Visual inspection
a7e213ea-9088-5fd2-9e0a-a9835b18cd2a | note | RECORD OF CONFORMITY: This ITP signed
114a306c-f0a2-5b26-bb06-fae68327f7f9 | note | IP
bb1dc1c6-c5ea-5111-ab3a-7ee12d784c0e | note | RESPONSIBILITY: Fulton Hogan Engineer
4fb262ba-e813-5f37-a3ed-23550af31c60 | date | Date Completed:
7bc4d42d-e455-4da2-a837-983a54c5f70a | checkpoint | 4.6 - Non-Commissioned Lanterns
785d58af-8675-5e6e-9408-be1d768159e0 | note | FREQUENCY: Each Lot
54283be9-a484-531d-b697-2221509ee533 | note | ACCEPTANCE CRITERIA: The faces of all installed but not yet operating lanterns shall be covered.
13b11e35-6dd5-5308-9cdc-47d56fab2169 | note | ○ At sites that have not been switched on, all vehicle lanterns shall be covered with ‘NOT IN USE’ signs as shown in SD-101-403.
b5762854-2701-59ab-8244-22baab67069c | note | ○ At remodel sites, or sites where existing lanterns are operating, all non-operating lanterns shall be covered with a ‘NOT IN USE’ sign or other approved method.
0cc10b7d-0b0a-56c5-bca7-5173c10267cc | note | REFERENCE DOCUMENTS: 730.14 (h)
12e41178-68be-59ca-94cb-d030de01a9d6 | note | INSPECTION/TEST METHOD: Visual inspection
af1053ba-2f70-5adc-8e83-b6e8e39feccb | note | RECORD OF CONFORMITY: This ITP signed
21ee5152-fc94-51ff-8c5b-8a9935d4150f | note | IP
1ade252f-e7e9-5379-ac8c-027dffc2ba1d | note | RESPONSIBILITY: Fulton Hogan Engineer
4e18d9cd-4bcb-5804-a31f-a13df5146623 | date | Date Completed:
f9de5734-6329-44ab-859d-f1b7dbe5fb3a | checkpoint | 4.7 - Inspection
43c0b59a-5ec2-57cf-aba0-85a27bda6590 | note | FREQUENCY: Each Lot
23a70bab-4b06-5cdb-a853-23b24391a89c | note | ACCEPTANCE CRITERIA: All installed hardware shall be inspected by the Superintendent prior to works proceeding
c12e1289-a0f3-50ac-98fa-be64e4782cfc | note | REFERENCE DOCUMENTS: 730.14
2356c3b6-d7df-5507-a177-88969731221d | note | INSPECTION/TEST METHOD: Visual inspection
0635e975-ffd9-5753-9bc3-3dbe3a03f4c6 | note | RECORD OF CONFORMITY: This ITP signed
35e51dcf-3e28-5a4b-a247-d8aeede0df01 | note | HP
cdfb08ba-bc26-563b-aced-ae921291bf58 | note | RESPONSIBILITY: Fulton Hogan Engineer/SuperIndentant
ac96d5d4-ea92-5935-b0b3-c86eafaac64f | date | Date Completed:
d3feda99-7032-4374-b939-957e47ccceb4 | signoff | AUTHORITY HOLDPOINT
d7267c15-4aad-4abe-ba28-e3616b76178c | checkpoint | 4.8 - ITS Installation
a0b75592-840a-5f3d-b9cf-bd4a2a20d51c | note | FREQUENCY: Each Lot
ec8479c7-8ebc-5155-b68a-32060d9b3fef | note | ACCEPTANCE CRITERIA: All ITS equipment shall be supplied and installed in accordance with 732.
62972511-3b5c-5633-aacb-e099cd735597 | note | REFERENCE DOCUMENTS: 732
12e7a831-98e7-51e4-8478-9e76cc915ceb | note | INSPECTION/TEST METHOD: Visual inspection
37ff2867-b2cd-5d29-b28c-76eea2c9590f | note | RECORD OF CONFORMITY: This ITP signed
cdfed908-c15c-5ccb-91ce-ecdde35247d1 | note | IP
d0369857-9fc9-5920-a22b-6825ead03894 | note | RESPONSIBILITY: Fulton Hogan Engineer
8e3fea94-2b9a-5b72-a439-6ef852ed74d0 | date | Date Completed:
7336bf2f-0be3-404f-8313-ce5db1683095 | section | 5 - Electrical
83e7b31a-17cf-4245-84a9-a46eb33816c9 | checkpoint | 5.1 - Point of Supply
71964f82-f6f6-5046-8721-c8054e989be6 | note | FREQUENCY: Each Lot
8f8d93cd-94f4-5f5d-bfc6-be9c1dc33913 | note | ACCEPTANCE CRITERIA: Point of Supply to be Installated as per 730.16 (a) to be captured on "DTM-ITP-005 - Service Relocations - TasNetworks".
717c24f7-ee1a-529b-b1f9-f2c5b683ec20 | note | ○ The Contractor shall lodge all relevant associated documentation to comply with the requirements of TasNetworks and WorkSafe Tasmania for the provision of a 240 v 50 Hz single phase power supply for final termination on not less than a 32 amp service fuse.
2f3d9b2d-4293-5998-93fe-e852ad9fc45a | note | REFERENCE DOCUMENTS: 730.16 (a)
5d5db819-84ca-564c-9882-2d8989c50c5b | note | INSPECTION/TEST METHOD: Verify
78b5195d-fd55-596b-b75d-78894ec994b3 | note | RECORD OF CONFORMITY: This ITP signed
4d17182f-e50f-562c-8a27-0e8089b7d9f6 | note | IP
e334c8a1-f0d6-5656-8793-df7241b6e130 | note | RESPONSIBILITY: Fulton Hogan Engineer
c253d04b-c019-5c9e-8a72-f52fabbae93d | date | Date Completed:
b9b513ee-d3c9-4ca9-a0ef-05ba25964693 | checkpoint | 5.2 - Connection of Traffic Signal Controller
a63ac265-38c0-5707-bcea-2b5f41f7c917 | note | FREQUENCY: Each Lot
6ce9e13e-ae96-5528-b1ce-f9b821d3b08a | note | ACCEPTANCE CRITERIA: The Contractor shall install a 2 or 3 core low voltage power supply cable in a Dia. 50 mm HDPE conduit between the point of supply and the controller base in accordance with the requirements of the supply authority.
5ec00f06-ad06-5856-92d1-0ff851519f55 | note | ○ Sufficient cable shall be provided to reach 1.0 m above the controller base.
908289d7-4ea8-5284-bd2f-ff47a1c04747 | note | ○ An additional length of at least 1.5 m of the power supply cable shall be left coiled in the pit closest to the controller base.
f1e2db01-49f3-5352-981f-cd3fb79bc060 | note | ○ The active and neutral cores of the power supply cable shall have a cross sectional area not less than 6mm2
1eddeedc-9c00-5c04-8a41-051204136945 | note | REFERENCE DOCUMENTS: 730.16 (b)
0e42a52a-5335-5609-aabd-f8857e9464b8 | note | INSPECTION/TEST METHOD: Verify
f79bd73c-2701-5835-b644-312e4a84e69d | note | RECORD OF CONFORMITY: This ITP signed
92b3b555-2862-59f9-888e-6941983bc72f | note | IP
c4b715e3-8103-5590-abfd-841113ce7b7a | note | RESPONSIBILITY: Fulton Hogan Engineer
dca66736-bb26-5401-9e8e-68bb735be7c0 | date | Date Completed:
c2918d62-db4f-45fd-acf6-37df0bff777b | checkpoint | 5.3 - Site Cabling
4ce7d5a7-9424-50ab-b28c-dcf94ad3696b | note | FREQUENCY: Each Lot
470f0d5b-6fa5-5c9f-b8bb-160c8950ff02 | note | ACCEPTANCE CRITERIA: All Cabling to be installed as per 730.17.
ec2a6fe1-e3cd-5f0d-8ad9-5b83cb3e0da3 | note | REFERENCE DOCUMENTS: 730.17
a22629d4-000e-5f81-bca6-3b8850825586 | note | INSPECTION/TEST METHOD: Visual inspection
a33c605b-b40b-54a5-95c2-39bf9ebf5741 | note | RECORD OF CONFORMITY: This ITP signed
a1a7dec9-4431-509a-a7c3-c32b9cada13b | note | IP
fe638f17-79cb-5414-b81f-3aa08c69e74a | note | RESPONSIBILITY: Fulton Hogan Engineer
8af48218-cc41-5077-b2e5-e49f87a601f6 | date | Date Completed:
47b4f2d6-b325-490f-bc1c-30639d8449a2 | checkpoint | 5.4 - Installation of Detector Loops
32bdfff6-0c07-5aa6-a939-35adbb6d8cc5 | note | FREQUENCY: Each Lot
3c92e7bc-0dbb-5e7b-8708-2c872dd45bf8 | note | ACCEPTANCE CRITERIA: The Contractor shall arrange for the installation of vehicle detector loops in accordance with the drawings. Traffic Signals Maintenance can assist in the installation of vehicle detector loops as agreed.
7dc851eb-8327-52ef-8e4d-c045ac2ab260 | note | ○ Where the road is to be resurfaced Sub-Pavement Loops (EZY Loops) shall be installed under the wear surface of the final bitumen seal.
3edbba1a-d204-58fd-a13d-f8bab27b708d | note | REFERENCE DOCUMENTS: 730.17 (f)
e387b96f-e69e-504f-aec1-6130c11ab7ac | note | INSPECTION/TEST METHOD: Visual inspection
55a2cdf7-6460-5875-a88a-0d896cd25fe1 | note | RECORD OF CONFORMITY: This ITP signed
f79aca4b-9589-5070-b142-9132655123a2 | note | IP
cb3e9544-004d-5f8a-acd9-f12a876728a6 | note | RESPONSIBILITY: Fulton Hogan Engineer
7b916c3d-4724-5206-8d0c-7a4401e74798 | date | Date Completed:
a1feab56-f699-4a83-9215-c95b3547138f | section | 6 - Comissioning and Testing
fd196d5b-2799-4322-974e-e14ec661373f | checkpoint | 6.1 - Testing of Electrical Works/PreCommisioning
4bc51e55-788d-5c70-afd0-92d9dcd5fa48 | note | FREQUENCY: All Electrical Works
dc56b170-ae9e-58ee-9f19-d56f83c9efbc | note | ACCEPTANCE CRITERIA: Electrical installation testing in accordance with AS 3000 and AS 3017, including:
f78ad71b-326d-5ab7-910f-feb9005152be | note | ○ continuity of all active conductors
4436af4c-3d11-5300-9cba-adef013af549 | note | ○ continuity of neutral and ELV conductors
3e57d07e-e298-5ce2-89e5-cd5a83ca4df3 | note | ○ continuity of earthing system in accordance with Clause 8.3.3 of AS/NZS 3000
68765660-4230-5be9-b20b-bb4714aca6ee | note | ○ insulation resistance test of all field cables in accordance with Clause 8.3.3 of AS/NZS 3000 wiring rules
01aaa041-4901-501b-8df7-5f28c89f9537 | note | The following reports (VRS 730) completed and made available to the Superintendent:
53aba27e-dc3e-5aad-9a16-f592c4be9a1c | note | ○ Electrical Test Report
6e53b3bf-143b-5495-8e20-f0bcc809fb33 | note | ○ Insulation Resistance Test of All Field Cables
c10bf8f2-5e58-5de0-8e70-7e516679de60 | note | ○ Power Consumption Record
dd38e4d7-aa47-511c-89b3-f5321a645153 | note | ○ Continunity Test Report
a268ac53-d3c4-532d-8152-4462cf25ede0 | note | Flash Test is to be carried out. Once the flash test has been confirmed as acceptable, the site is to run with the lamps circuit breaker isolated for seven days to confirm correct operation of site
24502a56-c881-52c0-921c-fd1c5ff8f490 | note | REFERENCE DOCUMENTS: 730.22
0d441469-9d43-5230-9ed9-df3fff23f5dd | note | INSPECTION/TEST METHOD: Verify
5a25dc50-0cbc-5aef-ae2f-29ee79057277 | note | RECORD OF CONFORMITY: All Electrical Reports Listed
00bbb6ad-b350-5201-affa-2ac0af208b5f | note | HP
b8296a95-3bfa-5775-b701-f83f886f6108 | note | RESPONSIBILITY: Fulton Hogan Engineer/Superindentant
56be50c4-d936-5512-85b5-36cc221755bb | date | Date Completed:
eb0d3c8f-48fe-4469-9e08-f00960c33675 | signoff | AUTHORITY HOLDPOINT
e88408ef-3663-4544-90cd-41b5bad3afcc | checkpoint | 6.2 - Provision of Power
d01d46a0-ea40-526f-b9bb-f0db0c5abedf | note | FREQUENCY: All Electrical Works
f21c9e66-afa0-5756-b208-060f305e25c4 | note | ACCEPTANCE CRITERIA: The Contractor shall arrange for the submission of all necessary paperwork, inspections, payment of fees, etc., to obtain connection to mains supply.
c421c173-cd3d-526b-8570-d2aaa0bbc5d6 | note | ○ The Contractor shall advise the Superintendent when power is available at the site.
a8da7458-436c-5c26-aec9-5243be7d3a5e | note | ○ The Contractor shall arrange for the issuing of the Certificate of Electrical Compliance and be responsible for the submission of all necessary paperwork, inspections, payment of fees, etc., to obtain connection of mains supply to the site.
9d9da7a0-c4ba-56ca-9dab-7d23acf7d5ab | note | REFERENCE DOCUMENTS: 730.22 (b)
5d738f6c-d57e-558f-9c11-687297d3b558 | note | INSPECTION/TEST METHOD: Verify
f7900b90-924a-5b37-8b1d-674fd1d2192c | note | RECORD OF CONFORMITY: This ITP signed
21bfcf6f-30ba-51f6-8739-d5f855122977 | note | HP*
0cfeacae-5c88-5f1b-843d-d853cd077bfe | note | RESPONSIBILITY: Fulton Hogan Engineer
8239227f-3b2c-5c61-a037-920335887f41 | date | Date Completed:
e888aabe-18bb-45b1-bfc4-5c2b33073fec | checkpoint | 6.2 - Traffic Signal Controller Installation
b3ae0f65-9891-5046-b94f-2c254cc8ef57 | note | FREQUENCY:
1a5c0808-537a-53d1-a806-2c824ef8f508 | note | ACCEPTANCE CRITERIA: The Traffic Signal Controller is to be installed as per 730.23 following the successful release of all Holdpoints in 6.1, as outlined in 730.23 (a) and (b).
b597720c-19cd-5940-a987-16907661cef5 | note | REFERENCE DOCUMENTS: 730.23
c9c7749b-bd5f-559d-97e3-575192ba0ee1 | note | INSPECTION/TEST METHOD: Verify
fefa1da2-4bfc-5471-aae0-1caaaa09b19d | note | RECORD OF CONFORMITY: This ITP signed
20858063-98e1-57eb-8426-b383bd053743 | note | IP
32520a07-5d87-506c-88c5-5d033d0526e8 | note | RESPONSIBILITY: Fulton Hogan Engineer
a4dd1a76-cbdd-51d4-869a-e709f500e643 | date | Date Completed:
ccacc1f6-b6de-4c65-a955-885956cd1f0c | checkpoint | 6.2 - As-constructed drawings
06748b05-57af-51ff-b7c2-d09604542c4e | note | FREQUENCY: At completion of works
b7e89a80-9484-51d8-9f01-9e9bd3abb100 | note | ACCEPTANCE CRITERIA: Installed location and depth of conduits, and location of pits and pedestals, shall be accurately recorded on as-constructed drawings.
a7534fd3-7f61-52f3-94c8-234e27c119b4 | note | REFERENCE DOCUMENTS: 733.24 (f)
c4184607-ee8a-5333-806f-6ad5cba7cf1d | note | INSPECTION/TEST METHOD: verify
a14180ad-ff26-5227-82d9-e63d79fe5737 | note | RECORD OF CONFORMITY: Red-line mark-up
d324cec0-d5ee-5549-b16e-b6ce6556e0d8 | note | IP
59b85fa0-ee44-58ea-922c-cc8a961a3b68 | note | RESPONSIBILITY: Fulton Hogan Engineer
b9e5e9ba-2e06-51a7-a301-201cb9982026 | date | Date Completed:
cd6bea8f-28c1-4dec-b27d-3e202ad4f483 | checkpoint | 6.3 - Comissioning
6e562cfc-3baf-5983-a1d2-fd4c5c1fdb1f | note | FREQUENCY: At completion of works
e9f59f82-3ffc-50cd-b0cb-4dca63200d77 | note | ACCEPTANCE CRITERIA: Prior to switching the signals on, ‘flash’ test of the installation carried out by the Contractor and controller installer, to ensure that each lantern is connected to the correct cable core. Flash test witnessed by the Superintendent and confirmed as acceptable.
bfb7a3de-0c18-59c5-a06e-7671503a95dd | note | ○ Comissioning Report (Post Switch on)
9b5a3db1-581b-5f89-852f-105aadff16be | note | ○ Power Cunsumption Record (After Switch on)
28cb15d6-44a8-5ffb-8e84-b4ac4492c680 | note | REFERENCE DOCUMENTS: 730.24 (g)
211ae83e-dfac-53e8-98c9-e23c2bfe20ce | note | INSPECTION/TEST METHOD: verify
359ba446-c9e6-5e61-bb1b-0e720b1254c8 | note | RECORD OF CONFORMITY: This ITP signed off
f2964943-d15e-539e-bae1-e60ecd563fe4 | note | HP
77562e85-0139-521d-96ca-2ed4ba93261a | note | RESPONSIBILITY: Fulton Hogan Engineer
d5cea143-9abb-5df3-816e-191a42a776da | date | Date Completed:
fe5b7527-1b06-41b5-a440-b281e3e782b6 | signoff | AUTHORITY HOLDPOINT
f5f21524-c68a-43cb-9a28-e250d0157ea1 | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
a39d8c1b-05af-59ef-8ef0-b30f4c75dfb4 | textbox | Fulton Hogan - Print Name:
53d7d87b-e9b6-5a30-925c-da57caa43687 | textbox | Fulton Hogan - Position:
a248136f-219d-55c8-bf3c-a3b584fdf329 | date | Work Completed On:
84956b51-cd6b-4e78-a7de-4d16cc4b5cbb | signoff | Add Signature
dc232b7a-2959-4d39-a978-5948154fc088 | checklist | DTM-ITP-010- Subsurface Drainage Rev0 | itp | DTM-ITP-010- Subsurface Drainage
bd97bc43-1f96-416b-a154-51379636303c | section | 1 - Preliminary Works
98616a05-61cd-477e-bd26-2ea9c4c66be5 | checkpoint | 1.1 - Check for correct documentation
409cffda-331b-5df5-8865-945146d6225f | note | FREQUENCY: Prior to commencing any activity
a5b8b007-f536-5c78-a0dc-899b1e8a1752 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
6c719146-7229-5163-b222-1e70dee7ec29 | note | – using the correct and complete set of drawings
49334d76-a888-51b7-8843-b38c07af43f9 | note | – all drawings are the latest revision
ddc9a292-43c5-5f70-8f0f-4576ae2ff29d | note | REFERENCE DOCUMENTS: Drawings and drawing registers
3f722864-2ab1-548c-a017-7cbf1abedf0a | note | INSPECTION/TEST METHOD: Visual inspection
f12ae0ea-3ac9-59c3-a5fb-864a760b546a | note | RECORD OF CONFORMITY: This ITP signed off
034c1cdf-757f-5604-b5f2-0df89b1a031c | note | HP*/WP
f06f6a97-042a-5c26-ac70-23988b3ea3df | note | RESPONSIBILITY: Site Engineer
22a16a33-71bc-5524-812b-d319503c6d2b | date | Date Completed:
4d1c4009-c7d3-44f1-a24d-640202d5b509 | checkpoint | 1.2 - Implementation of all measures and controls
f2e4360b-97f3-5d51-8cab-e455b9d6d719 | note | FREQUENCY: Prior to commencing any activity
6ade91af-21d4-5e6a-a982-de6aaeba020f | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
bac34797-5705-5d5a-a9a4-716f303e6628 | note | REFERENCE DOCUMENTS: PSP, EMP, TGS, SWMS, WP
2cf975d9-185b-5f88-90d8-0508bc5d83a9 | note | INSPECTION/TEST METHOD: Visual Inspection
67b30f81-afb2-5ca5-852d-52c7d106a4e0 | note | RECORD OF CONFORMITY: This ITP signed off
1decf2b5-7ca3-51da-a4e0-bc54a7286b86 | note | HP*/WP
ef7670a5-e691-54a8-9678-aba089f05d61 | note | RESPONSIBILITY: Site Engineer
dfd1c25b-eb3f-5835-a7d5-8c2caf61c4ab | date | Date Completed:
5ee9d1a3-898d-4fca-b867-bdebfb48c3fd | checkpoint | 1.3 - Material Classification
dc235f54-7ab1-5b2c-b447-9e44eae672c9 | note | FREQUENCY: Each Lot
bb992774-5171-5b58-9724-19934b6497e8 | note | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000 and 400 corrugated perforated plastic pipe
9ffce2c8-2277-5627-9f76-215a2871e745 | note | ○ Granular filter material for bedding and backfill: Trench backfilled with B3 granular filter material complying with Cl 702.05
9eb87afb-78e1-5915-b3a2-51e417830e0d | note | ○ No Fines Concrete: Shall consist of 4.0% Type GP cement
f4c3c85f-5d59-5898-abe4-b8ec3f16f3d0 | note | ○ Geotextiles: Robust geotextiles shall comply with Cl 702.12 and Table 702.061 and have a minimum robustness of 600-900.
35c8637b-4bf0-5eef-a9a4-4878a469b85f | note | ○ Subsurface drain pits: Stormwater drainage pits are to be used as access points. Invert levels in pits to comply with Cl 702.10
1d32d2f5-f68a-5cbe-a51d-29ba0a46578e | note | ○ Flushout risers: Shall have surface fittings as shown on the drawing
b53845e8-f908-5bc1-ae07-bdfcd2853153 | note | REFERENCE DOCUMENTS: 702.04
bd8e62e8-f383-5535-8450-622c9cc398a7 | note | ○ 702.05
17d37116-5073-5720-ae97-88a20aea90d7 | note | ○ 702.06
00d3bea1-fb03-52a2-9ab4-7fedcdf5e472 | note | ○ 702.1
a6497bf6-3bd5-567d-ac60-0cc891d35825 | note | ○ 702.12
276841f0-222f-5df9-bcc2-29043394d7d3 | note | ○ 702.061
c5205ac4-7b35-566a-89bd-46499eeb70a1 | note | INSPECTION/TEST METHOD: Verify
ed20a4fc-1c5f-5ddb-85b1-719c540c3ecc | note | RECORD OF CONFORMITY: This ITP signed off
740f7d45-c679-57af-9c20-bd9ffa9d856f | note | IP
e8c590b7-33a8-5bd5-80e0-08c490b95555 | note | RESPONSIBILITY: Site Engineer
76f8d80d-391c-5a79-943a-74e3eb898d6f | date | Date Completed:
18babd6e-91fd-43ec-96db-990a5896fac2 | section | 2 - Construction Works
3a3ed7b0-512f-4248-893b-871de7ba4549 | checkpoint | 2.1 - Excavation Permit
d17db5fb-6a3d-52e1-b7ac-33ef81e3d481 | note | FREQUENCY: Each lot
6cf8ed64-cb59-5113-872b-5ba5f9a3a2bf | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
d766e8dc-b2e4-5d45-9388-8b660458f4e7 | note | ○ Plant and equipment shall be appropriate for the task.
802d7971-5e75-5f6b-8815-ac505f30d653 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
4f02dba2-34b6-5924-94a5-0a55c4fc1800 | note | REFERENCE DOCUMENTS: Excavation permit
d14b565c-aeac-59b1-95b0-6f12b341b870 | note | INSPECTION/TEST METHOD: Verify
2e5b3f75-eede-509a-a27f-cd44bfb3dcdc | note | RECORD OF CONFORMITY: This ITP Signed Off
4c63dead-481a-5b8e-a01b-e82f7b413ebb | note | HP*
8472a4d5-4fbb-5011-a9e2-d653e4d32ed7 | note | RESPONSIBILITY: Site Engineer
42f6bbe1-40c0-52ad-ad46-c749452997de | date | Date Completed:
487677f5-13fb-4c27-9098-1bb1cecdfb93 | checkpoint | 2.2 - Excavation of Trench
6e829872-c714-5055-90ca-1a1b9a0b7b74 | note | FREQUENCY: Each Lot
f655a975-1ccb-5ff5-b0a6-1b2a33f13688 | note | ACCEPTANCE CRITERIA: Hold Point
11054bef-a09b-5596-ab4a-0f381283f589 | note | ○ Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by QAV with at least 24 hours notice prior to placement of bedding.
9a78f787-721f-5904-8f1f-c99237f0d4de | note | REFERENCE DOCUMENTS: 702.08
1ac91226-21ed-5e02-8164-c9ae679c5ae0 | note | INSPECTION/TEST METHOD: Visual Inspection
e41bb413-3978-5958-bac6-852522fce04f | note | RECORD OF CONFORMITY: This ITP signed off
5e82c7cd-8976-5fe5-a382-ba1f21504df9 | note | HP
e99dcdfc-2a37-5055-b89e-c8541c865b82 | note | RESPONSIBILITY: Site Engineer/ QAV
3c04b69d-0dec-536c-9a72-8205621c1aba | date | Date Completed:
b12eff82-9f89-4d5d-a66c-60d15752cfd9 | signoff | AUTHORITY HOLDPOINT
ba4c4a36-0ade-4db6-beb7-f31869f31388 | checkpoint | 2.3 - Placement of bedding
c62be6b0-0ad3-532f-a089-28fd506a3b1d | note | FREQUENCY: Each Lot
f33bed24-a8ad-5085-89e8-c2ddd954588a | note | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
eea00629-ab33-5618-b8fc-efd7da6c7866 | note | REFERENCE DOCUMENTS: 702.09 (c)
87cacce3-0d85-5ad0-be0c-715f8a955d1d | note | INSPECTION/TEST METHOD: Visual Inspection
12f3f87c-589b-55ba-8c0f-529ba29bfbeb | note | RECORD OF CONFORMITY: This ITP signed off
c94bd974-4bac-5548-9432-1c3b3fdaa90f | note | IP
de9c812c-6bfc-573c-9784-5f02e9c2f05a | note | RESPONSIBILITY: Site Engineer
f1704d27-552c-5727-acb4-6109dadf4988 | date | Date Completed:
dad8b9cf-4db9-41cc-a38c-e93a10c0b205 | checkpoint | 2.4 - Placing pipes and geofabric (if required)
505b4ad0-cf14-5533-81d4-ecee88821045 | note | FREQUENCY: Each Lot
bbe2ad53-647f-55f7-aa19-35f42561108f | note | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
654f7290-c000-539e-88ff-0db2d96ac7eb | note | ○ If geofabric required (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
d2299543-831f-580f-95ed-f2825f1841c4 | note | REFERENCE DOCUMENTS: 702.09(d)
0ab45924-1ba9-5fbc-adbb-cba41238eebf | note | INSPECTION/TEST METHOD: Visual Inspection
7c37582b-76aa-5f06-b5f1-ed9b6b20185a | note | RECORD OF CONFORMITY: This ITP signed off
c7c2d1e2-d489-530d-8443-3a2cb42e9120 | note | IP
e6057ffb-1054-5d6b-ba01-465603ebcc6b | note | RESPONSIBILITY: Site Engineer
31d755da-09c8-5ddb-ade6-e2fb2677d362 | date | Date Completed:
181b4424-e726-47ff-9358-e9943a8d5cee | checkpoint | 2.5 - Placement of granular backfill methodology
8d99ac40-f0f1-5161-b526-d9aff491ddd4 | note | FREQUENCY: Prior to backfilling
2b7e3cdd-25d3-5b3a-9250-4e807e703e4d | note | ACCEPTANCE CRITERIA: Hold Point
6322698a-8052-595d-a885-3db63dd484a6 | note | ○ Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
2374df2b-e24a-5ecb-a380-3072b8702cc7 | note | ○ Where no fines concrete is used, the contractor shall submit quality procedures for review by the QAV which detail the method of placing. No fines concrete shall be placed and compacted within 1 hour of mixing.
24003fff-6440-5513-9fa1-7aa0451ebf65 | note | REFERENCE DOCUMENTS: 702.09(g)
a0faed30-2f01-5992-b869-db612e60f53e | note | INSPECTION/TEST METHOD: Visual Inspection
b15fee7a-7ab2-5144-acc0-c8cb7e607c8d | note | RECORD OF CONFORMITY: This ITP signed off
79750820-2ec0-53a6-8374-0037640a110e | note | HP
224d63b8-92e2-5f8b-bd75-e1d2cd37596e | note | RESPONSIBILITY: Site Engineer/ QAV
39f8acde-0093-56c7-8869-09c14138f32d | date | Date Completed:
52aeb88b-d4c1-47e1-8364-d47edee539ab | signoff | AUTHORITY HOLDPOINT
cbcf76a6-c348-4d35-87b6-1173e9fd3137 | checkpoint | 2.6 - Placement of backfill
bdbdbda7-14a5-525c-838b-f43c935e2a62 | note | FREQUENCY: Each Lot
35981b9e-7c0c-5a9f-b566-d4b45be84867 | note | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
b21f08f6-a4d6-5d97-b781-49d13bb0a69b | note | REFERENCE DOCUMENTS: 702.09 (g)
c136b5c2-b5d9-5f4c-9355-3784e5537085 | note | INSPECTION/TEST METHOD: Visual inspection
8c92d47e-8847-5f6b-a682-bf7abe473cdf | note | RECORD OF CONFORMITY: This ITP signed off
8993ef62-5778-51fe-abb5-d74bdaea110f | note | IP
554681f2-a65e-52e8-b957-1d2591b165bc | note | RESPONSIBILITY: Site Engineer
d8a2bdfb-5506-52e5-9de7-a614e6afa9bf | date | Date Completed:
f0df95ac-82f6-4461-ad7e-3f1381fffac8 | checkpoint | 2.7 - Install Pits and Flushouts
a78f719a-99b2-55e6-8d61-7d66ec54c83b | note | FREQUENCY: Each Lot
c2dd364f-0e87-54f9-807e-70124b51d48e | note | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
1020c20f-af52-54e8-b80e-9536d890cab6 | note | REFERENCE DOCUMENTS: 702.1
f2b51e0f-a62c-5a0c-82b3-5a338a04dc87 | note | INSPECTION/TEST METHOD: Verify
f3799620-ec2d-58c5-a44c-5ce0c94fe8a7 | note | RECORD OF CONFORMITY: This ITP signed off
f21ea46c-4743-5fb4-9b65-141fb80da1c1 | note | IP
e19a6a0c-439c-5810-91a7-1975c897066d | note | RESPONSIBILITY: Site Engineer
e41b5248-2c36-5550-8294-f92a242a3e40 | date | Date Completed:
ba79380c-4974-431c-9a08-1e326b448ea6 | checkpoint | 2.8 - Flushing Test
15f2fab8-66ed-54cb-b75d-1401844b5065 | note | FREQUENCY: At completion of stage
c2660abd-51d1-5044-84d9-97bd78645743 | note | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
35e223d3-ef7b-59a3-834b-737f76525a5b | note | REFERENCE DOCUMENTS: 702.09(h)
9ebf03ea-02f0-56fa-8b95-97e2f33a6737 | note | INSPECTION/TEST METHOD: Site inspection
5679f132-5e5c-5897-8780-156f7a251327 | note | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
5ffea4a5-bb2a-5015-a974-a2aacbbaa497 | note | WP
e3b23650-dd53-5513-8148-19014d8b76a9 | note | RESPONSIBILITY: Site Engineer
18ad722a-5ea4-54a3-9399-0dbb8791b5ff | date | Date Completed:
d94157dd-8110-433e-8c8b-da71e1428c6c | checkpoint | 2.9 - CCTV
d0afa496-352d-5d67-a397-71bf0c839ae8 | note | FREQUENCY: At completion of stage
df769d8c-a57e-5469-8cf6-da265623b015 | note | ACCEPTANCE CRITERIA: Hold Point
7754c56d-18e3-5dcc-8d7b-57b148d92d10 | note | ○ All subsurface drainage lines constructed shall be inspection, after completion of the flushing test and prior to the placement of asphalt, by an independent testing organisation using CCTV, in accordance with WSA 05-2013.
9c2f7655-f5b4-5e01-9998-8e4195a27604 | note | REFERENCE DOCUMENTS: 702.09(i), WSA 05-2013
98a12b70-034f-5448-a8c0-27dae87c426b | note | INSPECTION/TEST METHOD: Site inspection
c22f18ea-e040-5284-9ac0-4f9cb369b0b4 | note | RECORD OF CONFORMITY: Signed ITP/ CCTV Reports
a306f78d-1155-5670-bc25-623d5873b18d | note | HP
f3523f26-a11d-5446-b389-25defe21facb | note | RESPONSIBILITY: Site Engineer / QAV
1ac21938-feac-5318-8b29-b1569e052b54 | date | Date Completed:
b75743a4-0841-4a71-8e67-fc1cf0e9c1c6 | signoff | AUTHORITY HOLDPOINT
89c3767d-80e3-4b9c-82a6-c03941dfe38a | checkpoint | 2.10 - Marker Posts
078e97ca-8c09-5a20-8150-08df92276faa | note | FREQUENCY: Each Lot
8978ecb0-778c-59ce-a313-d60e4d3a9662 | note | ACCEPTANCE CRITERIA: At all fill batter and drain outlets, supply and erect marker posts as shown on the drawings.
7d37a242-e70a-559d-bfc3-ca343b857493 | note | REFERENCE DOCUMENTS: 702.11, DSG 3401-3/P17-4
214946ec-1779-5604-ab05-bdabdb4ce614 | note | INSPECTION/TEST METHOD: Site inspection
c933ac4a-5924-52e0-a1e4-b2e21af7f8b6 | note | RECORD OF CONFORMITY: Signed ITP/ As-Built records
5ffb0ff5-15d5-5e83-9ca0-857dcbf3f528 | note | IP
17412c65-ebba-573d-b070-760eb9505ef4 | note | RESPONSIBILITY: Site Engineer
4749e34f-8301-58ee-bf51-95343b8a7938 | date | Date Completed:
03e48390-87e9-4f98-9cb8-74282de1adc1 | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
3b517259-83fb-5352-b615-9bba48ad516e | textbox | Fulton Hogan - Print Name:
ab3c8b50-1433-5947-b4c1-2c4d663241fd | textbox | Fulton Hogan - Position:
bb14e7a2-8ff4-5467-95d4-a1c1d3d3b86e | date | Work Completed On:
72ac3149-98af-428d-b50b-9e2a016350f3 | signoff | Add Signature
041041fa-09db-4ea3-917f-d9255d0adc68 | checklist | DTM-ITP-011- Structural Concrete Rev0 | itp | DTM-ITP-011- Structural Concrete
cd24f451-08a4-4aad-8a36-c36e1a3b7711 | section | 1 - Pre-Construction
65092dbc-a9d9-4da6-9b1f-826ae829ad12 | checkpoint | 1.1 - Check for correct documentation
8a03c51e-1af8-5110-a2bc-a295b36fcfb8 | note | FREQUENCY: Prior to commencing any activity
4d346f47-7a5a-5a74-b20d-b087772f17d9 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
b441da6b-067f-54bd-a289-b48e6707db86 | note | – using the correct and complete set of drawings
903f5e0e-5f7e-5852-aa6a-c3e566c649d1 | note | – all drawings are the latest revision
e5a5a54e-2e16-514a-bd29-fbe374426169 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
790fbe54-cc4b-580e-bc16-903e856d3287 | note | INSPECTION/TEST METHOD: Visual inspection
15dc6909-2710-5f0b-98e0-ef85db689158 | note | RECORD OF CONFORMITY: This ITP signed off
6cb7f46f-fff4-56ca-bd6a-50571f4972d1 | note | WP
c578c2a5-99aa-53ca-969a-5a5481eb5284 | note | RESPONSIBILITY: Fulton Hogan Engineer
38a7c2d2-e406-5e02-93cc-89b4d403dc39 | date | Date Completed:
b841d815-f7f7-4669-b632-4044e4535179 | checkpoint | 1.2 - Implementation of all measures and controls
106dbb3f-37f1-53ad-baed-b1bf9542a13b | note | FREQUENCY: Prior to commencing any activity
f38f0efa-413b-5df6-aca1-4c35a14baf88 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
452c1e0b-ba8c-5bdc-8915-f52ff48f92e7 | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, OHSMP, SWMS, WP
a69df833-e7b6-511d-8989-6f6600d11985 | note | INSPECTION/TEST METHOD: Visual Inspection
660e9809-8186-5a0a-8500-5e696dd17c54 | note | RECORD OF CONFORMITY: This ITP signed
7d7b85bd-7a57-5480-a0c0-4f4b04adfabe | note | WP
2e9e3975-027a-5daa-ace6-3f612b94fc37 | note | RESPONSIBILITY: FH Engineer / Site Foreman
0a31d7eb-4223-511f-926c-37bf3cbd543b | date | Date Completed:
58f71b0d-0c67-44f8-9bc9-4dc7496428f2 | section | 2 - Prequalification
b0e5e0e3-eda4-400e-be2e-227fa91046ba | checkpoint | 2.1 - Submission of Mix Design
08c3cf74-eeba-5382-8c39-72663912bb03 | note | FREQUENCY: Prior to commencing
ed97241b-7630-5357-af62-7473a61f21bd | note | ACCEPTANCE CRITERIA: Hold Point
c4c5ee24-0e52-5f1f-bf1b-e0c9438ac1a7 | note | ○ Concrete mix design complies with requirements of Section 610 and appears on the Register of State Growth approved concrete mixes.
e41a8b14-6308-59ec-b26a-1ddca183a23d | note | ○ Submit for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
68b59e3d-9530-54db-bcda-d072a6ea18b2 | note | REFERENCE DOCUMENTS: Specification Section 610.07
616ce297-03d6-5ab3-8cf2-f2f4685d9548 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
bac388c2-929c-518f-8396-c3cc71a46ee6 | note | RECORD OF CONFORMITY: Superintendent HP Release on Procore
3330c793-82ba-5894-9adf-119bafec12e9 | note | HP
c6b815d8-437e-5cdd-85ac-f358ec364ab9 | note | RESPONSIBILITY: FH Engineer/ Superintendent
0c2973ed-4108-51b7-88b7-aebd51c5814d | date | Date Completed:
caacd260-df44-47e5-82ff-796a38088089 | signoff | AUTHORITY HOLDPOINT
3d6a6bd7-a402-467a-be92-ba1219704b20 | checkpoint | 2.2 - Reinforcement
b3810cdb-eb99-5ccc-b770-6e7d6e1a5678 | note | FREQUENCY: Prior to commencing
07ddf801-f4e7-5439-b1ae-83eab7d48996 | note | ACCEPTANCE CRITERIA: Steel reeinforcement complies with the requirements of Section 611.
b51ccd34-7df9-500a-88e5-2c35cce020d9 | note | REFERENCE DOCUMENTS: Specification Section 611
1cada896-f509-5003-8720-b09931b92ee2 | note | INSPECTION/TEST METHOD: Visual Inspection
0fcffdea-9f4b-5980-b09a-cbd49d2b2969 | note | RECORD OF CONFORMITY: This ITP signed, Pre-pour inspection checklist
406c7b52-1502-5d4e-867d-fcc2d2650369 | note | IP
e9d273f3-23ad-5288-b4d0-c741c49bef39 | note | RESPONSIBILITY: FH Engineer / QAV
127bb8d5-0e95-52e2-a8cc-ec9f3903d36b | date | Date Completed:
703dce7f-ebf8-4b97-8f34-1c293012f2a1 | checkpoint | 2.3 - Reinforcement supply and certification
032e5e8b-4a30-55a0-9ec8-62b1f48c3fd6 | note | FREQUENCY: Prior to commencing
eb546b5d-5fbd-56f7-91da-a09f3f5c4409 | note | ACCEPTANCE CRITERIA: Supplier must hold Australian Certification Authority for Reinforcing Steel (ACRS) certificate.
2472e3a5-fb47-5263-8d5a-4a83ead76c61 | note | ○ Hold Point
9961e116-6393-56cc-9b87-67cb24209bcc | note | ○ No Third Party Certification. Approval shall be obtained in writing from the Superintendent for the use of steel reinforcing materials that are not covered by the long-term quality level of AS/NZS 4671 at least 14 days prior to the intended first date of use of such steel.
ccf64c50-160f-53a1-abd4-aa01dd374765 | note | REFERENCE DOCUMENTS: Specification Section 611.05
23e75b6a-ccf3-5df9-848a-db086bd3b6ae | note | INSPECTION/TEST METHOD: Verify
cad162f2-60f1-50a6-8dff-45a7f63e34df | note | RECORD OF CONFORMITY: HPR release in Procore if required
8b64e635-f662-54bc-b0a8-21e12ebe46a0 | note | HP
a59ebc6c-d2b9-57eb-9a7e-f402626c27c3 | note | RESPONSIBILITY: FH Engineer / QAV
66918531-898a-56b1-927a-5ebafb37b0cb | date | Date Completed:
72ab0999-418d-4185-855b-10b4611e1e0f | signoff | AUTHORITY HOLDPOINT
5f3c74eb-8a42-467f-a4e5-0bc775ea8281 | section | 3 - Testing and Acceptance
30845b54-b1bc-43c8-a0d0-644bd56e818b | checkpoint | 3.1 - Pre-mixed concrete
0765fbba-89aa-571a-a66e-d6163fbb617d | note | FREQUENCY: as per table 610.161
5f3faf2e-d492-5719-baed-d6b54552136b | note | ACCEPTANCE CRITERIA: Concrete sampled at the worksite and complies to requirements of Section 610 including slump and temperature
20bdce44-3e5a-5d28-9ccd-9cf6dec93f8f | note | REFERENCE DOCUMENTS: Specification Section 610
65fb736b-c3d9-51c9-8f78-a0a554f9d1bc | note | INSPECTION/TEST METHOD: Test Point
ba4f263c-2bc1-5484-a9e9-5dd7fc3ceda7 | note | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
acbb384b-42aa-5ca7-8c27-6812b2577c7c | note | TP
db8d59c8-315f-56fe-81b0-ae334d3664bc | note | RESPONSIBILITY: FH Engineer
e2a83b6c-12e1-54d5-b6c2-d790db1343e7 | date | Date Completed:
cc9f6e56-f6f6-430f-9e22-86a1f47977b2 | checkpoint | 3.2 - Concrete Testing - Sampling Frequency
31e339ae-d0ed-52e9-a551-6cf418d15cbd | note | FREQUENCY: Each Lot
5226f4a7-8302-553f-8734-173af10d1a46 | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
70ec6fce-2793-5bc0-be1d-1abf64c3cc35 | note | ○ 0m³ to 10m³ = 1 sample
b29d67f1-62b0-5918-8a75-bd58c1620ac8 | note | ○ 10m³ to 25m³ = 2 samples
a97b1c70-a9d1-53eb-b5e4-097cb8dfc872 | note | ○ 25m³ to 50m³ = 3 samples
88d40c2e-f1a0-5392-8408-4319293dfade | note | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
1c15220e-4f65-524f-980d-ba0c76925fdd | note | For each additional 50m³ and additional sample shall be taken.
c707f23a-082d-5f15-be9c-d79f6d6f2b9a | note | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
16ec4a83-f102-5f5a-9d62-ebef0efd69ec | note | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
43514cdb-e7b9-5c6a-b5f2-cf91e03f581f | note | – Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads.
652098d1-03c8-518b-bf65-6af483c27d78 | note | Record: Required information on the Concrete Pour Record.
1e50a1f5-9e48-59aa-9d3f-2af0115cad5f | note | REFERENCE DOCUMENTS: 610.16 (b), 610.16 (g), 610.16 (j)
fbc4e240-461a-5762-8731-2732ab23305c | note | INSPECTION/TEST METHOD: Test Point
2b0b6a67-2362-583e-b334-59d060d99682 | note | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
aefe5433-5bba-56b1-8702-4e21e3acb856 | note | TP
5961d24a-a965-5c8a-8e1b-08d0f5ece5a9 | note | RESPONSIBILITY: FH Engineer
b55cffdb-040d-5278-842d-6e1c15b84b73 | date | Date Completed:
3990f8ca-8731-455d-8e47-03921b8266e7 | checkpoint | 3.3 - Concrete Testing - Core Sample Frequency (Post construction)
3cfcd789-4e2c-5b39-bfb8-af0f79d9488a | note | FREQUENCY: Each Lot
adc92e12-cb4f-5116-9690-7dd899cd9691 | note | ACCEPTANCE CRITERIA: If required by the Superintendent:
d73c2935-a959-5f6e-a5e9-5df24809dad8 | note | Hold Point: The coring procedure and core locations shall be submitted for approval by the Superintendent.
53553817-d8e6-5287-a935-190545710cf3 | note | 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below:
e839ed4e-bf7c-5056-95d0-62f646a42acc | note | ○ 0m³ to 25m³ = 1 sample
6672cd96-0968-5ff6-b507-5bdea731c753 | note | ○ 25m³ to 50m³ = 2 samples
2bee23f8-64e5-56b8-a2e0-bd35c71f875d | note | – For each additional 50m³ an additional sample shall be taken.
95f27ec2-4560-5b29-b30d-bf3715991625 | note | – Each sample shall consist of 6 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum.
c5aedec4-0a84-5d3f-aa1a-eb9899425e42 | note | Core samples shall be tested for:
d76a130e-9048-599a-83b5-df87767beab0 | note | ○ 1 no. 3 day compressive strength
331931b0-227b-5cd4-a985-acf5a5bde5c4 | note | ○ 1 no. 7 day compressive strength
db5aff80-32e4-5d1a-b379-d9dd06da74bd | note | ○ 2 no. 28 day compressive strength
63005791-8994-5ad6-ba08-a93cc7dd87ea | note | ○ 2 no. VPV tests
c9aa2491-57c4-5928-9c81-79812c487ffe | note | REFERENCE DOCUMENTS: 610.16 (b)
5b3eab55-e43b-5b09-b6ab-b9ac8dbbc336 | note | INSPECTION/TEST METHOD: Test Point
dbf22156-6451-51f2-8660-d24a4364ae98 | note | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
aa361e96-ff68-5b82-a867-1a7df31c80aa | note | HP
8e9d37d2-2200-500e-8fa4-e0b787605531 | note | RESPONSIBILITY: FH Engineer
16bed8bd-687b-5e5d-819d-9f5a9466e57e | date | Date Completed:
f91b2447-719c-4015-a497-bc88b5ff7747 | signoff | AUTHORITY HOLDPOINT
706cd974-6cf4-4870-b761-792da31c41ac | checkpoint | 3.4 - Concrete Testing - Slump
52586c26-b4b9-5e49-91f1-fe928eb9700f | note | FREQUENCY: Each Lot
791ec36b-3627-5334-8eba-84ef7c1de345 | note | ACCEPTANCE CRITERIA: Slump testing tolerances =
437876c9-27bb-505c-9c41-98cd23179407 | note | ○ <60mm = ±10mm
39ad17b7-a0be-59a5-abb0-ea5450604fc1 | note | ○ ≥60mm to ≤80mm = ±15mm
9a6b7195-45be-5279-aa58-8f8d3c10d204 | note | ○ >80mm to ≤110mm = ±20mm
b1521d1a-7105-538a-aec6-20772940532c | note | ○ >110mm to ≤150mm = ±30mm
96050f5d-6376-5eb7-9e93-7838563d2d4a | note | ○ >150mm = ±40mm
af02e170-9a33-5068-8dc9-3163bb894cc4 | note | Record: Required information on the Concrete Pour Record.
6740d7b6-77af-595a-ac3c-3383fd176728 | note | REFERENCE DOCUMENTS: 610.16 (c)
bf266e86-e613-5ea2-a1c0-ccb5f2e9dc7a | note | INSPECTION/TEST METHOD: Test Point
6042ddc7-eb8f-5faf-a2c4-de380387a228 | note | RECORD OF CONFORMITY: This ITP signed
206a22e0-a3e3-5390-b682-e5f4d1a71a5e | note | TP
68a7bfd3-307f-5efc-9e5d-ee84d79c063f | note | RESPONSIBILITY: FH Engineer
626e169a-60d8-5511-9c84-3f0f7521e0b4 | date | Date Completed:
6277f857-9036-4bc3-b5bd-fba360d6289d | checkpoint | 3.5 - Reinforcement
1098d801-56de-53c9-9cbf-4487d6e987d6 | note | FREQUENCY: Prior to commencing
310c736a-f08c-5f27-9ba1-f2823d728e5d | note | ACCEPTANCE CRITERIA: Steel reinforcement placement, fixing and lapping complies with requirements of Drawings
62ea848c-f259-5042-85d8-33e6998233c4 | note | REFERENCE DOCUMENTS: Structural Drawing Set
d23902b1-caf8-5788-934d-a046b4c7a9b2 | note | INSPECTION/TEST METHOD: Visual Inspection
d4c75d1d-ca23-58b3-b2e7-39c7042c612e | note | RECORD OF CONFORMITY: Pre-pour inspection checklist, Subcontractor ITP
fee818bc-0e96-5bc6-ac8e-13dd3bd7ab39 | note | IP
180d495a-47da-5c31-b926-fb355c3acb8b | note | RESPONSIBILITY: FH Engineer
aec7001e-92ec-5e01-9713-e179079966ad | date | Date Completed:
81673fae-77c8-45a3-8fbf-02b3307f48a6 | checkpoint | 3.6 - Building Permit
c8e74abc-b0ec-580e-802e-5b1946d6c9ed | note | FREQUENCY: Prior to commencing
4c6abf96-b676-5b94-b8db-ccd290acfdb2 | note | ACCEPTANCE CRITERIA: Building Surveyor has provided Start Work Notification (Form 39) and inspected element prior to concrete pour
c5b5b01f-2fe1-5d48-b35d-f2cdf33195d8 | note | REFERENCE DOCUMENTS: 160.08
3b1f9746-eadc-549c-8827-20d55c9095f8 | note | INSPECTION/TEST METHOD: Verify
86375244-b8a1-5366-98ec-6ba3685b8cdb | note | RECORD OF CONFORMITY: Start Work Notification (Form 39), Pre-pour inspection checklist
0fb77fb9-67f1-5651-bd14-f5853f338162 | note | IP
b7bf37f5-9b8c-5924-bea9-88ca53ad2262 | note | RESPONSIBILITY: FH Engineer
b1b0f5e7-ed81-578a-8ae3-9d1a5d4ec229 | date | Date Completed:
6405d846-567b-4b51-a5d5-c8cf78a93044 | section | 4 - Application
aa726a36-c375-4598-9427-c5a29d505122 | checkpoint | 4.1 - Pre-pour
bac48b13-7c4c-5835-8fda-43669eef6b3c | note | FREQUENCY: Each Lot
0ee932fd-ad25-5e97-8622-583c8a8652ac | note | ACCEPTANCE CRITERIA: Pre-pour inspection checklist completed and details recorded (Temperature, Evaporation limits and concreting operations).
2aff895e-69f6-5ccc-a788-b27144dbcebf | note | REFERENCE DOCUMENTS: Specification Section 610, Figure 610.171
0486ea2b-a0e4-5a54-a2bf-06a59c60a178 | note | INSPECTION/TEST METHOD: Verify
a6041ca9-b5eb-5be2-b8ae-cbd5972685b5 | note | RECORD OF CONFORMITY: Pre-pour inspection checklist
aa38297a-a0ce-502a-a0b4-210b6755ebdd | note | IP
b4691ff3-eb9c-5c31-9d9d-214c70aa7316 | note | RESPONSIBILITY: FH Engineer
82c2556f-6f30-5ccb-a589-a6674769d349 | date | Date Completed:
a657e027-0a34-4337-9b51-8b7bf32b6207 | checkpoint | 4.2 - Concrete Pumping
17e964e6-71c7-5bf4-aa02-da453c3565b5 | note | FREQUENCY: Each Lot
637224d3-aa99-536c-b2a5-72f6661c89b5 | note | ACCEPTANCE CRITERIA: Initial discharge of concrete pumped to waste until a consistent workable mix observed
a06fd8de-f36a-5f49-bb4f-156a709d28c6 | note | REFERENCE DOCUMENTS: Specification Section 610.18
b67df94b-6b10-58f2-820c-90e48958e121 | note | INSPECTION/TEST METHOD: Visual Inspection
ce0bdf0c-284e-5996-9ff6-a98a00c64b69 | note | RECORD OF CONFORMITY: Pre-pour inspection checklist
ccc8729c-6206-5cc1-a6e4-4f440dfdb149 | note | IP
64ce8ee1-96cf-596b-9964-bb2aa2128c2a | note | RESPONSIBILITY: FH Engineer
9fa71d1b-c2a9-5979-8c0b-77758c52b2fa | date | Date Completed:
d8b82dbc-8bb8-4222-afa9-8380eb884f3d | checkpoint | 4.3 - Traceability
11e30783-6d6c-5f2a-bb23-de10d77319ab | note | FREQUENCY: Each Lot
610bff69-6700-5914-8408-614021f4d98b | note | ACCEPTANCE CRITERIA: All concrete deliveries traceable from the batch plant to location in the structure including time from batching to spraying. Continuous concrete pours max lag between trucks = 25 minutes
5b4e5960-abc9-526c-9473-3a8901d15ee6 | note | REFERENCE DOCUMENTS: Specification Section 610.15
5dd724a0-2b8e-5a25-9496-0e6581a7e512 | note | INSPECTION/TEST METHOD: Verify
062bef85-73c4-54e0-86ea-ecb5b78a8909 | note | RECORD OF CONFORMITY: Concrete traceability checklist, Pour Record
fd5e58a1-7f46-5a71-8339-0914bde354d1 | note | IP
12296a8e-c111-5c80-8ff5-df5f32f650fe | note | RESPONSIBILITY: FH Engineer
db3dec81-3185-5794-add3-8bd00c8aa69e | date | Date Completed:
478721ce-83e8-46f2-a3f1-e6c317960552 | checkpoint | 4.4 - Finishing
5f6322ce-ff1f-5f52-921f-d787296a6c51 | note | FREQUENCY: Each Lot
3fc2cdf2-8c3e-559f-8f20-b8f042ea6c4d | note | ACCEPTANCE CRITERIA: Not specified in project specification. A trowel finish will be applied. No decorative/anti-carbonation coating required as footing will not be exposed in anyway following construction
40a2f7d7-1f44-5567-8535-44b1c528a6d7 | note | REFERENCE DOCUMENTS: Specification Section 610.31
6324b0ba-395b-5686-85b9-62ba3b34ded9 | note | INSPECTION/TEST METHOD: Visual Inspection
b8b276cd-5352-5b37-9bc3-be8c28cd1013 | note | RECORD OF CONFORMITY: This ITP signed
b710fcd0-d34d-56bb-9ebf-d713556d87f4 | note | IP
55520c26-2e3d-5989-8ccf-16ebdc48f125 | note | RESPONSIBILITY: FH Engineer
61115f73-4380-54dd-b79f-e08d779b659f | date | Date Completed:
ee4f6591-f1dd-4907-ac6e-1bee00f22e0d | checkpoint | 4.5 - Curing
1769809a-58ba-5ab0-b807-ebea3fe04862 | note | FREQUENCY: Each Lot
7b86e86d-be13-51c6-b858-38a8f9997166 | note | ACCEPTANCE CRITERIA: Curing in accordance with Specification Section 610. Freshly finished concrete protected where erequired from sun, wind or rain until curing implemented
7289230d-7df1-5648-ac83-f05e2a8808b3 | note | REFERENCE DOCUMENTS: Specification Sections 610
f11254ca-0236-5584-8a36-1c929c748d81 | note | INSPECTION/TEST METHOD: Visual Inspection
336953d7-5430-5055-b1a9-4d892d96203d | note | RECORD OF CONFORMITY: This ITP signed / Post pour inspection checklist
b60699df-1879-5f98-ab44-b9e84987efda | note | IP
e0676821-3c67-55ac-960c-c008a5f404e9 | note | RESPONSIBILITY: FH Engineer/JSCB
7d9fdf0f-cbd3-5e7e-bc60-6a2384c8967b | date | Date Completed:
66d5a2e4-b4b8-4a6e-bdce-21aaad58e355 | checkpoint | 4.6 - Joints
a551a617-e805-5f87-b39d-fad3c6c4de20 | note | FREQUENCY: Each Lot
ff2be32a-57c1-527c-b4bf-e934160fbcd8 | note | ACCEPTANCE CRITERIA: All joints formed in accordance with Specification Section 610, Drawing requirements
c00c928a-7afd-55da-85ca-52e5fb77ccc7 | note | REFERENCE DOCUMENTS: 610.20, Structural Drawing Set
0c9ac79a-da33-5f97-bf0f-2852fbcaba64 | note | INSPECTION/TEST METHOD: Visual inspection
7443c91c-f73f-5b91-8a18-f44482096ea8 | note | RECORD OF CONFORMITY: This ITP signed
0c0d60c1-ab5d-56e4-ba94-dde02bcc1687 | note | IP
49f44de9-9c71-5103-a691-111d81cb3a3b | note | RESPONSIBILITY: FH Engineer
cf65200a-af3e-5a57-853b-5e32438aca8a | date | Date Completed:
f0ef5e11-6e91-4baf-bf1a-9b86e34dff97 | checkpoint | 4.7 - Dimensional Tolerances
2d13cf46-f979-586f-aaf0-efe3cc1a7b5b | note | FREQUENCY: Each Lot
228980f2-80ae-5358-9be6-0781fcf16444 | note | ACCEPTANCE CRITERIA: Maintain records of dimensional measurements to demonstrate that all completed concrete members comply with Spection Section 610.
d79b0841-cc7e-5cad-bbbf-9d8944fa5cf9 | note | ○ Ensure that the records are available for review by the Superintendent.
ce16011d-d4b1-5867-80c4-8070b0d4c486 | note | REFERENCE DOCUMENTS: 610.47
e487d6a2-80a0-5656-9596-68fc4c7b9d07 | note | INSPECTION/TEST METHOD: Verify
81c24242-ab75-5838-9f62-045644110791 | note | RECORD OF CONFORMITY: This ITP signed, AS BUILT
269bee73-f769-5e80-871c-a4dbaf61a4d3 | note | IP
4a84d29b-2c65-5b3a-8ed8-1a7707632968 | note | RESPONSIBILITY: FH Engineer
017ca5f4-8f65-52ca-8383-7da4bc1a2cab | date | Date Completed:
766ae396-a9c5-45c1-b352-8c974d17694a | section | 5 - Finishing Activities
327501b0-f709-415a-9c02-37edd693654a | checkpoint | 5.1 - Final inspection
5210f7bc-997a-5073-b48e-7d38b47f7157 | note | FREQUENCY: Each Lot after 28 days
9f1d03bb-e547-575c-9e66-fc6e4053370f | note | ACCEPTANCE CRITERIA: Visual and soundness inspection conducted for analysis of compaction, dry patches, voids or sand pockets. Soundness inspection for drummy or hollow response.
2619ad85-5886-57be-82df-9a35fb364638 | note | REFERENCE DOCUMENTS:
57afc8b1-8522-55de-8ede-ca3ea5171760 | note | INSPECTION/TEST METHOD: Visual Inspection
d2ba0d43-a39b-5406-9e98-8307f75f34ca | note | RECORD OF CONFORMITY: This ITP signed, post pour inspection checklist
a34b4ea9-c3fc-5419-89d5-5360583151d5 | note | IP
1d13e970-615c-5541-aaa2-9abb126a55f2 | note | RESPONSIBILITY: FH Engineer
b34400af-e50e-5d3e-88e6-56999cfc544a | date | Date Completed:
31a22d8b-d49a-4eb3-a47b-9c1d7baac184 | checkpoint | 5.2 - Repair of defective areas
9bceb06b-8bd1-514e-95c1-8902f50720cc | note | FREQUENCY: Each occurrence
65a0e940-490f-5460-bb15-2cd927ba3f8a | note | ACCEPTANCE CRITERIA: Areas of finished work that have been deemed non-conforming alerted to the QAV and rectification method approved
0e90f58a-b4d6-5ff5-aaa9-518b7de4727c | note | REFERENCE DOCUMENTS:
5104692a-9305-5919-9dcd-4d7c09718fa8 | note | INSPECTION/TEST METHOD: Verify
7212d5ff-db39-5096-ae53-7527294ac15c | note | RECORD OF CONFORMITY: This ITP signed, NCR report
e5f63f32-8635-5c28-896d-ec41a066f24d | note | HP*
08de9c1b-4130-54ec-a0cb-9d353782c33a | note | RESPONSIBILITY: FH Engineer
64f0f259-c8b1-5855-b5fe-ed91784d30cc | date | Date Completed:
291ac375-bdc9-4577-8093-66fc40d59ed5 | checkpoint | 5.3 - As Built Documentation
7e651e3f-7e6a-5d57-b0ee-e9515836e165 | note | FREQUENCY: Each Lot
01b4d208-bd8d-586a-883a-146aa8f33041 | note | ACCEPTANCE CRITERIA: Survey pick-up to be progressively completed. As built drawings to be be progressively completed. Test data, ITPs, Concrete Dockets, Checklists to be compiled and lot to be closed out.
1be74762-77ec-54ae-ab93-b54a2511948f | note | REFERENCE DOCUMENTS: FH Detailed Construction Methodology - Shotcrete Works
e23e77a0-4b5e-5a54-9cc7-bcb6cefe74a6 | note | INSPECTION/TEST METHOD: Verify
14ce2990-fb99-5952-80df-929b5f3a14e1 | note | RECORD OF CONFORMITY: This ITP signed
c52d6e56-3f68-50a5-b6ce-8f91facb2c0e | note | IP
95d937e3-a122-5198-a844-4ad61e41c77d | note | RESPONSIBILITY: FH Engineer
26381139-5236-5f0d-9964-814fa3a413ea | date | Date Completed:
cedba04e-447a-477e-9010-ccdc21e579d3 | section | 6 - Post Construction
b9559682-8c4c-4bd1-9bf0-6f86b7b9b0ba | checkpoint | 6.1 - Compressive Strength (& VPV Test Results if requested by Superintendent)
43cf25d8-1f3d-5986-b53f-8c3402f86e41 | note | FREQUENCY: Each Lot
9ea0e21f-435a-51e9-8ae8-cd831de69f0c | note | ACCEPTANCE CRITERIA: 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly.
0b1e2050-cbed-5cd1-b46e-8f5cde607684 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength comply with table 610.061.
acdc5c10-db6f-5aa5-91c7-f6f2030870af | note | ○ Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects.
524fa496-876f-554e-8a41-ee3e25ef8784 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
7fdc9741-b60f-5bd2-8028-8d014d1d1812 | note | Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%.
84057dc1-1073-5856-a19c-4d0e9065dc50 | note | Attach: Compressive Strength Test Results
cfd2fc52-4d0a-53d9-a835-9ecfd8673367 | note | Attach: Core Sample Compressive Strength Test Results
fd8170d0-2b85-5204-b49a-a583bbdf3cba | note | REFERENCE DOCUMENTS: Table 610.051, Table 610.061, 610.16 (g)
5e592cc3-d919-54de-a207-ff37c6ed8ac3 | note | INSPECTION/TEST METHOD: Document Review, Each cylinder and core sample
e2f1b474-c3d6-5d5d-9694-6092b0f222ae | note | RECORD OF CONFORMITY: This ITP signed
ee9a0217-2e12-58dd-ba3f-50ae52d9df86 | note | IP
2163f7c6-9bc5-51bd-81a2-21f90431ee72 | note | RESPONSIBILITY: FH Engineer
f2cf88e6-5f5f-543a-9893-4e9663a6ea33 | date | Date Completed:
da4f4ea3-4996-4e16-82b1-d4bd9c454175 | checkpoint | 6.2 - Surface Inspection
cd2d4ac1-5212-5e8c-8e9a-845de4ff6c24 | note | FREQUENCY: Each Lot
ee084fde-06b6-5dc0-b6d2-4ecc7ef188b2 | note | ACCEPTANCE CRITERIA: Surface to be as per the required class of finish with no visible lack of compaction, dry patches, voids or sand pockets.
0e2519ef-6abb-5f6a-a2c3-ea0535043dec | note | ○ Soundness inspection shall be conducted with a small hammer to locate ‘drummy’ or ‘hollow’ response areas which indicate a possible lack of bond, delamination or other defect.
d6761f47-adb2-56e7-913d-d1ed7764f012 | note | ○ For core sample penetrations and if any visual defects are observed, follow Structural Concrete Cementitious Patch Repair ITP for investigation and repair.
18651a0b-0030-51cf-9d1c-d09eee29da28 | note | ○ No cracks greater than 0.2mm (exposure classification B1)
cfbd30f6-4c86-5a1d-a59b-f3f524ffea8b | note | ○ If cracking is observed, follow Structural Concrete Crack Repair ITP for investigation and repair.
a81e9677-d152-5d1a-97cc-85be2cbfc6b7 | note | REFERENCE DOCUMENTS: 610.31 (a) - (n), 610.32, 610.24
788f9b3c-ef82-5abf-a2a6-87155c7305a7 | note | INSPECTION/TEST METHOD: Visual, Measure
26bf255a-1e3d-52a6-ac15-baff3403c97b | note | RECORD OF CONFORMITY: This ITP signed
e9a77b44-50d2-5b4a-b4db-046ecab02cac | note | IP
933a5fa6-2169-5987-a6e2-137f81ff3e73 | note | RESPONSIBILITY: FH Engineer
eb4e1b91-dacc-5a2b-b918-dd380a66ad70 | date | Date Completed:
e3a3d7eb-1976-4fd6-bded-783566e9de77 | checkpoint | 6.3 - As-built Survey
a70f2013-60a8-5852-b327-6705b91b3525 | note | FREQUENCY: Each Lot
9dbe8e7e-be4e-5308-987e-7327c49eae9c | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the Table 610.472 as applicable to the element.
3ae54a66-3726-58c0-ae7d-54b729518bb1 | note | ○ Where a shape is required, ±25mm with no depressions greater than 15mm.
9add3e58-c350-5a36-9695-c916ad804221 | note | Attach: Survey As-builts / Survey Report
1db14454-1686-5de7-a04c-11260afc7b0b | note | REFERENCE DOCUMENTS:
ec9694d9-bcd7-542f-b8d9-7fd3c19beed5 | note | INSPECTION/TEST METHOD: As built
e4380606-d84a-530e-bd17-027c58f1f385 | note | RECORD OF CONFORMITY: This ITP signed, HPR release in Procore
963c8a0b-50ce-51a4-baea-ff92aa416014 | note | IP
996b627d-e86f-5752-b2a9-e7c2a7389301 | note | RESPONSIBILITY: FH Engineer
04802b8a-081d-5b80-b5c3-ea8ac6f3a751 | date | Date Completed:
baa6cd40-16e4-44f3-85fa-0968f39845c6 | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
ab3f5aa4-5d5c-5fda-ae6f-a974218cc7a4 | textbox | Fulton Hogan - Print Name:
e2c7b403-f7c2-5bd0-be46-63ee852b9335 | textbox | Fulton Hogan - Position:
6fbcbd51-8b48-56e7-9090-760192706601 | date | Work Completed On:
c94b3d3b-cec4-48b5-84d3-63e1d23a3094 | signoff | Add Signature
ee10a12d-3ca6-4748-adc8-cb989e549b24 | checklist | DTM-ITP-012- Masonry Block Wall Rev0 | itp | DTM-ITP-012- Masonry Block Wall
3f823e9a-480b-4e39-bd5e-d7a0cba2dff9 | section | 1 - Pre-Construction
7a59b4bd-7f55-439a-a880-1ba35944b03f | checkpoint | 1.1 - Check for correct documentation
efd0c353-114e-518d-b3c2-22cd18fbdbbf | note | FREQUENCY: Prior to commencing any activity
dc9cfe7b-1270-5ffa-9fc6-c9d325bb6fbf | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
50f5b26b-2e6f-55aa-b1cb-e8ddf0672181 | note | – using the correct and complete set of drawings
fbd3b734-45c0-5bf6-8f91-e7d143a24028 | note | – all drawings are the latest revision
a9072318-129f-5fa5-ac66-2dbf0f67933b | note | REFERENCE DOCUMENTS: Drawings and drawing registers
e669cd79-cc33-5666-8515-e88cc1c1c112 | note | INSPECTION/TEST METHOD: Visual inspection
9190a8c2-1f14-5c48-b582-7dcb71540cdc | note | RECORD OF CONFORMITY: This ITP signed off
76e181dd-0268-579e-805b-7da330de6dbb | note | WP
8cf53dbf-b4c8-5883-a88d-9939ab3a76d1 | note | RESPONSIBILITY: Fulton Hogan Engineer
e2886653-f46b-5a18-b626-466264434445 | date | Date Completed:
6fce617a-2388-431a-90de-54d2021799f1 | checkpoint | 1.2 - Implementation of all measures and controls
1feb87e0-acab-5c74-be0f-3b1a8b7417ef | note | FREQUENCY: Prior to commencing any activity
8e595d85-12b3-5128-b999-6d1d4aa361c2 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
90e679a9-982c-5922-9830-1683a8ea5b5c | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, OHSMP, SWMS, WP
2d7d260a-f8d3-59a4-ad1e-33ea9e33b2c6 | note | INSPECTION/TEST METHOD: Visual Inspection
d52b3110-04d6-5f3f-b9c5-4d8494119782 | note | RECORD OF CONFORMITY: This ITP signed
f7d043f7-4c1f-5bdc-917e-a044ccf314f0 | note | WP
ad93d196-aaf9-5de5-96a9-034c35d5fa40 | note | RESPONSIBILITY: FH Engineer / Site Foreman
cd6f4ec1-5f5c-543b-855f-5916c2e9703b | date | Date Completed:
e49b99fe-9560-426c-8641-85326dda0dba | section | 2 - Prequalification
54e706aa-f210-4d84-b31d-dfebc2cdb3aa | checkpoint | 2.1 - Reinforcement
c55a19e6-d7f3-51bb-b02c-a2e5d5b049c4 | note | FREQUENCY: Prior to commencing
2144e926-6d13-5f95-a6e9-ce0b7d9aa6c2 | note | ACCEPTANCE CRITERIA: Steel reeinforcement complies with the requirements of Section 611 and the design drawings
e440ba8f-71c4-53dd-a9c9-900ec51e4b40 | note | REFERENCE DOCUMENTS: Specification Section 611
e8f444cf-d1cb-5b11-a67a-58bccd155844 | note | INSPECTION/TEST METHOD: Visual Inspection
d155ea72-8914-58d2-9761-c388a6d69d37 | note | RECORD OF CONFORMITY: This ITP signed, Pre-pour (core-fill) inspection checklist
a0497470-5db9-5258-9869-145ac33a9a04 | note | IP
c3fb022c-8496-5cab-8a70-3437633bc0ee | note | RESPONSIBILITY: FH Engineer / QAV
8ce8cd93-f857-51b5-be7e-3e483ebd91ad | date | Date Completed:
4afe8365-404d-4799-92ed-7ba9856d9697 | checkpoint | 2.2 - Reinforcement supply and certification
4445e100-342f-57b8-86db-145ed441c2da | note | FREQUENCY: Prior to commencing
8376195d-47e4-5c32-b7fe-31779c947163 | note | ACCEPTANCE CRITERIA: Supplier must hold Australian Certification Authority for Reinforcing Steel (ACRS) certificate.
d26bdc66-3d4e-53ae-ad24-1527aca3a4f1 | note | ○ Hold Point
63aa58dd-ed9b-5078-a0d5-3fce5ec87f8c | note | ○ No Third Party Certification. Approval shall be obtained in writing from the Superintendent for the use of steel reinforcing materials that are not covered by the long-term quality level of AS/NZS 4671 at least 14 days prior to the intended first date of use of such steel.
07af6a56-456d-5faf-96b5-e6b5ec4730f8 | note | REFERENCE DOCUMENTS: Specification Section 611.05
932802f3-ee1b-5776-9d47-f7949fad6e41 | note | INSPECTION/TEST METHOD: Verify
38ef012d-ffce-5038-be98-00cd2b0726b9 | note | RECORD OF CONFORMITY: HPR release in Procore if required
2b2b9fd1-bec7-52b2-95bb-2b6fe9745c8d | note | HP
5f1aab61-c9d9-58e5-a09f-6abea80c2dbc | note | RESPONSIBILITY: FH Engineer / QAV
53fe0d80-608a-5b33-8485-12ca2d1eac85 | date | Date Completed:
e6510f24-51d5-42bd-9081-9d4d844ca53e | signoff | AUTHORITY HOLDPOINT
4a52e7f7-3121-416e-8372-c0e4100c9bc9 | checkpoint | 2.3 - Supply of masonry blocks
12aeb244-8f1e-50e2-b1ff-3414faa730f8 | note | FREQUENCY: Prior to commencing
e5afd546-79db-5858-89a1-75eb8798f864 | note | ACCEPTANCE CRITERIA: Ensure blocks comply with sections 713 and 765 of the AS/NZS 4455.1:2008 and section 765 of AS3700:2018 standards and are of the same type/description as set out in IFC drawings: Adrbri Masonry Versawall (oatmeal) blocks.
2127d520-90a1-53d0-b939-efe53ca6a98d | note | REFERENCE DOCUMENTS: IFC drawings
c686b1c9-0b7a-5618-a7dc-2d0ce6aed38a | note | INSPECTION/TEST METHOD: Verify
fb984687-258b-5c52-b070-5e5bd342f4a2 | note | RECORD OF CONFORMITY: This ITP signed off
b2dbd533-4e7a-5154-b059-579187bd727a | note | IP
988e0298-46a4-5881-88b4-37d5907e32d8 | note | RESPONSIBILITY: FH Engineer / QAV
d38ff23b-2c8e-5e9b-8fc4-212babe78677 | date | Date Completed:
6a91e5e1-7b2c-45af-9119-27606daf2daf | section | 3 - Testing and Acceptance
9ea29579-ab9d-42de-b7d4-421ea80ea5f3 | checkpoint | 3.1 - Pre-mixed concrete
947043df-c5b8-5844-836b-7aaea0bd1cc2 | note | FREQUENCY: As per M14 of A0171.005 sheet 0301 Rev 0
510dfdf8-6cd7-5552-92ae-2dbd936cd31c | note | ACCEPTANCE CRITERIA: Ensure concrete strength is of the minimum specified f'c strength rating of 20MPa to AS3600. Ensure minimum cement content, max aggregate size and slump are as designated in note M14 are adhered to.
dd92f0b5-058e-5ed7-88ea-25ae12902e17 | note | REFERENCE DOCUMENTS: As per M14 of A0171.005 sheet 0301 Rev 0
a8e8a144-719c-5e08-a7b4-a3779ee81669 | note | INSPECTION/TEST METHOD: Test Point
6f077354-505c-5561-8954-3c4a1d22af64 | note | RECORD OF CONFORMITY: Mix design, concrete docket, this ITP signed off
c243af6e-9eeb-59e3-8732-1d06590b8347 | note | TP
7893ed1d-962d-5016-ac5b-41704ce35ec8 | note | RESPONSIBILITY: FH Engineer
57aca44d-7654-5dce-be7c-c2b896c98742 | date | Date Completed:
8a9d84bc-6d53-4e56-9c34-07b133bc8121 | checkpoint | 3.2 - Concrete Testing - Sampling Frequency
4929d8c2-0b30-5d39-a629-003c00036528 | note | FREQUENCY: Each Lot
23321796-5125-5540-b8ab-56fa564d2a33 | note | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
a0fb10dd-e0fd-5c74-832c-b4c20eab981e | note | ○ 0m³ to 10m³ = 1 sample
2de064d8-76cf-5c43-9e00-2601154371f4 | note | ○ 10m³ to 25m³ = 2 samples
5f037a64-8a9b-5117-a2da-a2b6b87d1330 | note | ○ 25m³ to 50m³ = 3 samples
5315045d-92f6-57ab-b7bd-a0c5f53dde74 | note | ○ 50m³ to 100m³ = 4 samples + 2 no. VPV cylinders.
68356533-1f29-5ecb-b3da-10c6762a0c83 | note | For each additional 50m³ and additional sample shall be taken.
3854b372-e9ff-5ddd-b571-36d7c7b78fa9 | note | – Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
61ff1243-5180-5425-bf03-1e63626e09b7 | note | – Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
0bd41027-9235-5180-8fd3-2546b86452d2 | note | – Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads.
ee2522f6-66a7-5de8-98c9-409f9023fe3a | note | Record: Required information on the Concrete Pour Record.
8e9d0974-1569-5766-912f-19339881997a | note | REFERENCE DOCUMENTS: 610.16 (b), 610.16 (g), 610.16 (j)
f33eb6b6-7219-5a0c-98c7-f39ea0bba244 | note | INSPECTION/TEST METHOD: Test Point
4fefa2f5-90b1-5e3d-ac7a-863290cc2f7b | note | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
1b0d7500-21c8-52e9-8193-dba34cfcad14 | note | TP
b5bea604-efb4-56cf-ab7f-5642ef8f42f6 | note | RESPONSIBILITY: FH Engineer
5334e244-b5c2-5138-96a2-b5a729002dd0 | date | Date Completed:
ae113922-a123-4451-a416-36f0125c6fc2 | checkpoint | 3.3 - Concrete Testing - Core Sample Frequency (Post construction)
73330d5b-bb39-5b6c-af25-cd2a44731291 | note | FREQUENCY: Each Lot
efdf98de-0e86-5ee0-a6c0-864462754712 | note | ACCEPTANCE CRITERIA: If required by the Superintendent:
2d9aa3a4-2ca0-55bd-9ca0-024b6f3606a6 | note | Hold Point: The coring procedure and core locations shall be submitted for approval by the Superintendent.
284e6ec5-51f0-503b-9612-fb1b4f96eea0 | note | 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below:
a7cbccc3-51eb-5c40-a291-4daee227e3a2 | note | ○ 0m³ to 25m³ = 1 sample
d3f26338-0abc-5ec0-a1cf-c8542f2c75f5 | note | ○ 25m³ to 50m³ = 2 samples
6768e929-3370-5a10-8f78-46987778b9a4 | note | – For each additional 50m³ an additional sample shall be taken.
e38cd7bd-d61b-5924-8f38-b1e4b7f550dd | note | – Each sample shall consist of 6 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum.
57d2f93f-ad30-5680-ac03-5419af734b6a | note | Core samples shall be tested for:
e790a6c0-c4da-540c-ac74-45cc72f4f8b1 | note | ○ 1 no. 3 day compressive strength
edddb85d-cb9d-5c36-b325-94fbbdaf59af | note | ○ 1 no. 7 day compressive strength
b53edc57-e46f-564f-909d-c179c0d263ea | note | ○ 2 no. 28 day compressive strength
01107fb0-fe6f-5d86-958c-a632be911a2c | note | ○ 2 no. VPV tests
8eb3886c-41a5-5742-86b8-854a03f378e2 | note | REFERENCE DOCUMENTS: 610.16 (b)
b952c166-5786-5b80-a439-b0a8543ca12b | note | INSPECTION/TEST METHOD: Test Point
b0a4da10-0292-540d-b4a5-fc0874d676af | note | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
056f282d-7a77-59dc-b04d-ec192edbcfd1 | note | HP
2d97f399-6767-56de-a8b3-5e58de46278d | note | RESPONSIBILITY: FH Engineer
a009cdb7-ffef-52f1-9c92-a1b827f35d63 | date | Date Completed:
928d62bc-5c9a-4078-a3d8-b3d542a284b7 | signoff | AUTHORITY HOLDPOINT
a2c532a2-53b4-4e93-a438-1905270807d9 | checkpoint | 3.4 - Concrete Testing - Slump
2f2e4631-7945-51d9-9fa4-51e0d38fbae9 | note | FREQUENCY: Each Lot
9445dc90-0f63-58dc-aadf-93506b81452e | note | ACCEPTANCE CRITERIA: Slump testing tolerances = >80mm to ≤110mm = ±20mm
61a0c6b1-f64a-5c4b-abb6-37c98c550c14 | note | Record: Required information on the Concrete Pour Record.
a6a9e06c-03c9-5e4c-bc6b-517751a32961 | note | REFERENCE DOCUMENTS: 610.16 (c)
c3f5965a-bdee-5fed-b9e7-7a12c883ba52 | note | INSPECTION/TEST METHOD: Test Point
12f892a3-96f0-5000-b634-44f95967a27a | note | RECORD OF CONFORMITY: This ITP signed
f3aa6dda-a70d-5826-96d0-9b9d3e8f0204 | note | TP
c5a8e458-0545-5b83-aab2-1ae4c7fc1158 | note | RESPONSIBILITY: FH Engineer
7da9ce9c-8067-56bc-b937-4f0a076697ee | date | Date Completed:
8844882c-fdb6-4fb5-a1e3-23fc650fe037 | checkpoint | 3.5 - Reinforcement
ebab1a87-eb7d-5cf4-8a21-d3d6a95d3c36 | note | FREQUENCY: Prior to commencing
5f23a318-b140-53a5-a9ae-89aad15250c5 | note | ACCEPTANCE CRITERIA: Steel reinforcement placement, fixing and lapping complies with requirements of Drawings
e2a5ae96-5f88-57ed-98a5-0335fc5aee51 | note | REFERENCE DOCUMENTS: Structural Drawing Set
d77e72ab-db01-5c43-b4bc-07d379d1118c | note | INSPECTION/TEST METHOD: Visual Inspection
e1452e54-a13e-542d-ab90-4aab5f357dac | note | RECORD OF CONFORMITY: Pre-pour inspection checklist, Subcontractor ITP
42e7488e-d915-5ba7-8e9e-a735647cf632 | note | IP
924a9be2-1349-5c9b-aafe-02e1b43954e3 | note | RESPONSIBILITY: FH Engineer
93484c8b-ab06-5af0-bffc-d49ba17b6598 | date | Date Completed:
042036c9-7979-4070-86c1-5335d08e7a93 | checkpoint | 3.6 - Mortar
94a5e6f1-264f-5ff8-912e-34029a395c06 | note | FREQUENCY: Prior to placement
32e8c3cb-cdc3-5844-94c6-696f5999c2e5 | note | ACCEPTANCE CRITERIA: Use class M3 Mortar: 1 part cement:5 parts sand and a methyl cellulose water thickener to AS3700. Use white cement to AS3972 type GP or GB.
dbe1c0da-b001-5527-93ed-5a300d61b1aa | note | REFERENCE DOCUMENTS: Structural Drawing Set
42d5a375-ef80-5e39-b3e1-d42fd0a3b715 | note | INSPECTION/TEST METHOD: Visual Inspection
eb82244f-c50c-5dfd-883d-0518f7fd70f8 | note | RECORD OF CONFORMITY: This ITP signed
32ece6e8-623d-54a7-8e8d-4f999531cd98 | note | IP
e987a792-432b-5c1e-b0d4-80797a9e838e | note | RESPONSIBILITY: FH Engineer
bcb3cf8a-b7e6-5f9a-89a6-d02e6dffd056 | date | Date Completed:
d34b206f-9c87-4b7d-b908-c9fdf84741a5 | checkpoint | 3.7 - Building Permit
761e69c3-7ce1-54e0-84af-02f492898096 | note | FREQUENCY: Prior to commencing
632c269f-a0b2-5d7b-8db0-d5073c8d1f4d | note | ACCEPTANCE CRITERIA: Building Surveyor has provided Start Work Notification (Form 39) and inspected element prior to concrete pour
7a0f84b2-b5e6-5cca-8cf4-2e18652979b6 | note | REFERENCE DOCUMENTS: 160.08
24290b3c-cfe7-563d-b4a7-681c215ecc54 | note | INSPECTION/TEST METHOD: Verify
1eefa158-d591-54d9-b7da-b147dc99545a | note | RECORD OF CONFORMITY: Start Work Notification (Form 39), Pre-pour inspection checklist
55e64b36-3559-5c0f-aa30-5855d51e99e1 | note | IP
027668c3-770a-57ec-ba48-4b3a910fc70d | note | RESPONSIBILITY: FH Engineer
7cb975e8-88a5-5452-8212-19b637595791 | date | Date Completed:
82914298-454d-44d0-96ab-5b484bdbddca | section | 4 - Application
d2fa15cf-da34-432f-855c-5fca5af14c19 | checkpoint | 4.1 - Pre-pour
c4107b84-8135-5bbc-9b84-65ed4fc5db88 | note | FREQUENCY: Each Lot
d41e3082-f412-5959-be20-0b5765750a06 | note | ACCEPTANCE CRITERIA: Pre-pour inspection checklist completed and details recorded (Temperature, Evaporation limits and concreting operations).
b8621b9a-c7ae-5bcd-9b4f-5e7bd94b2a72 | note | REFERENCE DOCUMENTS: As per M20 of A0171.005 sheet 0301 Rev 0
9574cce4-9743-5bbe-85cc-a6b51f7b21ea | note | INSPECTION/TEST METHOD: Verify
0bbec126-5f85-5c06-accb-40f6fe648c0d | note | RECORD OF CONFORMITY: this ITP signed
2a058c9d-d33d-5d9a-9c6a-f4396f348c8d | note | IP
44bb712a-6ff1-5502-8974-8d95f9575ca4 | note | RESPONSIBILITY: FH Engineer
0c4c5b4f-3208-5a8f-a918-936b0219e31a | date | Date Completed:
3cc4e9a5-5547-4afa-b748-031bbec0351d | checkpoint | 4.2 - Concrete Pumping
4ad2018e-1abc-5a1a-a4f7-71b07463f9c9 | note | FREQUENCY: Each Lot
03ab9e9e-a1fb-5e7d-9ac5-132871532031 | note | ACCEPTANCE CRITERIA: Initial discharge of concrete pumped to waste until a consistent workable mix observed.
6cb2e94c-b1f9-5cea-803e-4bcc541e9973 | note | REFERENCE DOCUMENTS: Specification Section 610.18
43ca57d2-cee1-5fe7-9bf0-21c730718644 | note | INSPECTION/TEST METHOD: Visual Inspection
ccc6de95-536b-5ef5-ac4e-019e4eed515e | note | RECORD OF CONFORMITY: Pre-pour inspection checklist
d61e1d24-1b2e-5e54-8c61-206b0b30c19d | note | IP
9f70dbf4-1988-5151-a832-66dc55fb0b97 | note | RESPONSIBILITY: FH Engineer
c3fb75a1-1edd-5197-80f4-a7997ff4b201 | date | Date Completed:
f4de6baf-8a0e-4b43-a88e-ef4f2459de6c | checkpoint | 4.3 - construction of blockwork
064e14ee-d518-505b-8070-d598400752ea | note | FREQUENCY: 6 courses / 1500mm
27bda691-f8fd-5af3-82f4-216908e6f8e9 | note | ACCEPTANCE CRITERIA: Do not proceed with blockwork construction more than 6 courses or 1500mm ahead of concrete placement. Wet masonry blocks before placing concrete.
958ba8ff-b0ab-5a44-bb92-cac245b0bbf8 | note | REFERENCE DOCUMENTS: As per M20 of A0171.005 sheet 0301 Rev 0
341c338b-fcb4-5669-9e64-e1d326083c57 | note | INSPECTION/TEST METHOD: Visual Inspection
58492f08-1e7d-5cb1-babc-1fc5275596a0 | note | RECORD OF CONFORMITY: this ITP signed
9e096092-d544-5d66-b186-4f80ace05fd2 | note | IP
ebf930ca-470a-58c0-928c-acdcc1e7fa37 | note | RESPONSIBILITY: FH Engineer
a10cd7fe-bdaf-5eb6-8dc4-ef9a3ad7accb | date | Date Completed:
bb73539f-b983-47c3-b5a3-f128e4411fa4 | checkpoint | 4.3 - Core-filling
859e0dd8-148d-50a5-93fd-65d3f8277252 | note | FREQUENCY: 6 courses / 1500mm
ea1a5275-aa41-5177-9248-0918614081cb | note | ACCEPTANCE CRITERIA: Wet masonry blocks before placing concrete. Stop concrete 50 mm below top of blocks to provide key for following concrete. Ensure proper compaction of concrete by 'rodding' or other approved means
e3ab2a65-da29-5f1b-941c-84a97e969e80 | note | REFERENCE DOCUMENTS: As per M21 of A0171.005 sheet 0301 Rev 0
cebc0886-94dc-5c76-a718-8cc95c0fee22 | note | INSPECTION/TEST METHOD: Visual Inspection
5ee16268-d7a7-5d5f-ac55-d04de696adae | note | RECORD OF CONFORMITY: this ITP signed
136d9bd5-298a-518a-9484-b192ecf917b1 | note | IP
7cc36cb2-195b-51fc-9719-c109a73a0411 | note | RESPONSIBILITY: FH Engineer
3153612d-dae8-5e50-9d5b-5bd3d01f9f37 | date | Date Completed:
f3b6e5fd-72be-4581-b8c8-27ec23d34cdb | checkpoint | 4.4 - Traceability
10da3764-0c7d-5f40-b0f3-f1b49a406521 | note | FREQUENCY: Each Lot
13de9bc3-dd1f-57c7-a8bf-9a6d67f73faf | note | ACCEPTANCE CRITERIA: All concrete deliveries traceable from the batch plant to location in the structure including time from batching to spraying. Continuous concrete pours max lag between trucks = 25 minutes
eacaeaa7-c7f1-5984-a2a4-0c892eb2108f | note | REFERENCE DOCUMENTS: Specification Section 610.15
906f7ec4-28c6-5843-8f6d-16c2b22f6931 | note | INSPECTION/TEST METHOD: Verify
64c19b92-f20c-582b-9307-717d54ec9169 | note | RECORD OF CONFORMITY: Concrete traceability checklist, Pour Record
a8df6886-7dfc-5e65-8a16-12ac73680472 | note | IP
ffbe5903-56eb-5aec-a945-9704200862dc | note | RESPONSIBILITY: FH Engineer
9b62c462-7748-533a-832a-373fefda9c9b | date | Date Completed:
44ec3e43-3666-404a-874e-e0f60fd865c9 | checkpoint | 4.5 - Curing
78a213c4-2b59-528f-8a69-42554312d0ba | note | FREQUENCY: Each Lot
c8b5f70f-191d-5cce-bb87-5cc3477d54c7 | note | ACCEPTANCE CRITERIA: Curing in accordance with Specification Section 610. Freshly finished concrete protected where erequired from sun, wind or rain until curing implemented
67405c7b-b6b9-5fa7-9c69-1265ca97b8c0 | note | REFERENCE DOCUMENTS: Specification Sections 610
919778eb-315c-589d-a478-139d34f78384 | note | INSPECTION/TEST METHOD: Visual Inspection
e5f045ba-44ab-5b45-a53b-cab5763c372e | note | RECORD OF CONFORMITY: This ITP signed / Post pour inspection checklist
57e99766-70d2-5a31-94a8-07105a8b9fbd | note | IP
3a5f6ac3-0813-50a9-bb94-d9f917d2e3b0 | note | RESPONSIBILITY: FH Engineer/JSCB
60ab46a0-dcc6-573b-b3e6-db4bdf7b9bd8 | date | Date Completed:
007e32be-9de1-4e91-9f82-63813093b204 | checkpoint | 4.6 - Joints
fa931ad9-4c0f-5f2e-bbd7-e43930883ffd | note | FREQUENCY: Each Lot
0a45561a-a00b-5d81-9ae4-d02b465c8920 | note | ACCEPTANCE CRITERIA: All control joints as per control joint detail on A0171.005 sheet 0321 using R12-400 Galv. Dowels 450 long (greased and wrapped one end) and flexible joint filler and 10x10 approved joint sealant each face.
3201cb51-dc40-5d48-bb84-83a958709a82 | note | REFERENCE DOCUMENTS: structural drawing set
21d88c1d-aa33-5744-a54c-f463f6c6bfd5 | note | INSPECTION/TEST METHOD: Visual inspection
d56c0af4-f1d7-54c5-8264-2cfce1cf858e | note | RECORD OF CONFORMITY: This ITP signed
6f2c0541-583e-5c51-a308-9a445f2656e8 | note | IP
264ff9db-a79a-5617-a379-f009380f5bf6 | note | RESPONSIBILITY: FH Engineer
7cb38731-c57d-5a9f-8a2b-c4b8dcc0ff7b | date | Date Completed:
3f0f657e-13a1-4496-9423-0a378cb129a4 | checkpoint | 4.7 - Cleaning
82c38400-4c4d-5e60-ad46-01c7cee6cb24 | note | FREQUENCY: Each Lot
f9619824-6b7b-5b9b-b105-dd0df95900db | note | ACCEPTANCE CRITERIA: clean masonry progressively. Clean face work to remove mortar smears, stains, discolouration etc. Use cavity batten (lift progressively) to keep cavities clear of mortar fins, droppings etc.)
73a73711-eb20-5fdf-ae19-1768a4be1d83 | note | ○ Remove mortar droppings from bottom of cores by use of cleanout blocks before placing concrete and at horizontal breaks in construction. Remove mortar fins protruding from joints before placing concrete.
305d9b3a-d7ad-5039-aa57-af25a8630b23 | note | REFERENCE DOCUMENTS: As per M12 and M19 of A0171.005 sheet 0301 Rev 0
4cb0549f-3479-5d50-9450-37908514427f | note | INSPECTION/TEST METHOD: Visual inspection
f147cd9a-6e7c-551b-9b90-1a459c71be96 | note | RECORD OF CONFORMITY: This ITP signed
05194725-f384-5c80-988a-ad1d2dd90597 | note | IP
4610c801-28b0-5d04-9c68-0fb8b4ff7205 | note | RESPONSIBILITY: FH Engineer
bd6a76fd-5988-562d-a7d6-5e844b2b8acb | date | Date Completed:
5a2e3822-e913-4f2c-a25f-30fa52fc8e81 | section | 5 - Finishing Activities
fdcd2e2b-8ff2-49d3-bff1-55a37809739e | checkpoint | 5.1 - Repair of defective areas
10937b26-8ecc-5fbe-9ac4-b68fb1055657 | note | FREQUENCY: Each occurrence
efdce0ea-df2f-5195-a421-c4bda1870a5c | note | ACCEPTANCE CRITERIA: Areas of finished work that have been deemed non-conforming alerted to the QAV and rectification method approved
9d01b979-5390-59b5-995f-461ebc4533dc | note | REFERENCE DOCUMENTS:
4c23cdfd-318c-5830-a661-16c2c6ddd5cd | note | INSPECTION/TEST METHOD: Verify
8385901a-4cf8-5286-b50f-1d3cf1520033 | note | RECORD OF CONFORMITY: This ITP signed, NCR report
97ec95a3-85cb-5274-98ea-d84aa64dcc1a | note | HP*
f7f4c8e8-6b88-5df6-8531-706926bd4d8e | note | RESPONSIBILITY: FH Engineer
9395bb82-a0ce-504e-9749-623f3eaa6526 | date | Date Completed:
35c5084f-5e72-4b6d-8d87-35bdc9013e82 | checkpoint | 5.2 - As Built Documentation
9f7a072f-2a3e-50fe-b8f8-6295c15ed21f | note | FREQUENCY: Each Lot
1c0758f7-b144-556e-9006-84000b7b87d9 | note | ACCEPTANCE CRITERIA: Survey pick-up to be progressively completed. As built drawings to be be progressively completed. Test data, ITPs, Concrete Dockets, Checklists to be compiled and lot to be closed out.
11ec2ae6-f85e-50c2-9893-9519748dfd71 | note | REFERENCE DOCUMENTS: FH Detailed Construction Methodology - Shotcrete Works
43c7d5d3-8049-5092-bb2b-d005018c86ad | note | INSPECTION/TEST METHOD: Verify
d6dae1d1-4a53-55da-8143-d2bdf5ae7f3c | note | RECORD OF CONFORMITY: This ITP signed
efed0d29-bf6f-51b1-992b-53283fef500e | note | IP
2e5fa304-9205-5b0c-bfa2-58f88cfdda40 | note | RESPONSIBILITY: FH Engineer
8b47992e-d4ef-533d-ab54-eeadec51409f | date | Date Completed:
2f5862cf-def7-4865-b831-7e86a9f80d85 | section | 6 - Post Construction
65bcbc86-2419-46c1-9afc-0288907b3bee | checkpoint | 6.1 - Final inspection
50864489-c0d4-504b-a87e-0207b6bfc47d | note | FREQUENCY: After construction complete
89881c02-b53d-54ab-890e-c358eb5e7ba7 | note | ACCEPTANCE CRITERIA: Visual inspetion conducted by Lee Tyers Building surveyors following the completion of construction
6f6e7ee1-da19-5198-8285-18f9855670ac | note | REFERENCE DOCUMENTS:
546e401b-2f9c-51b1-963f-afbdd2f2136f | note | INSPECTION/TEST METHOD: Visual Inspection
c440e53c-d559-5f9c-b1a6-26b2ba520ec0 | note | RECORD OF CONFORMITY: Form 39 signed
1f09531c-2efa-58e6-9550-3bcff1504f1a | note | HP
a2abcea7-e819-57f2-9223-64f175322a5f | note | RESPONSIBILITY: FH Engineer
ddc67779-cd19-5700-b574-af5fa76c12b6 | date | Date Completed:
e83d74bc-a4e1-4a62-b273-b610d4cf4ffa | signoff | AUTHORITY HOLDPOINT
ff934360-3875-4af3-bdb1-7a25d5cdca3d | checkpoint | 6.2 - Compressive Strength (& VPV Test Results if requested by Superintendent)
8e2a09f9-42da-5c89-9827-8f412a5030f0 | note | FREQUENCY: Each Lot
fe6fa56b-a282-5766-ae24-c1789526c122 | note | ACCEPTANCE CRITERIA: 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly.
eecd0689-397a-5089-a20a-7276f2130da7 | note | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength comply with table 610.061.
61bc9f88-38e9-55f0-a12a-297f0b795243 | note | ○ Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects.
45970119-1de3-5905-a795-da9a08238da8 | note | Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
c67df8c0-9a30-5d72-b23a-6520b970c1e0 | note | Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%.
dcaf87d5-56d8-5f93-bd9c-7fecc445b6c1 | note | Attach: Compressive Strength Test Results
028cbd36-4b22-5b16-80ab-e6d68be5c679 | note | Attach: Core Sample Compressive Strength Test Results
ee1f1e6a-e97e-53a9-9894-56a32b1e8789 | note | REFERENCE DOCUMENTS: Table 610.051, Table 610.061, 610.16 (g)
57e2493a-0bfe-50ff-a155-1b1c9db99a23 | note | INSPECTION/TEST METHOD: Document Review, Each cylinder and core sample
ad95f48d-c6cf-5b70-b7d3-e6e5ba1a4c65 | note | RECORD OF CONFORMITY: This ITP signed
86cbc675-1755-5b1a-84b3-8823f888d0b8 | note | IP
8ba5c28f-8e82-52e9-90c9-dcf4847929fa | note | RESPONSIBILITY: FH Engineer
4ddf2602-755b-525f-be63-475af05867f3 | date | Date Completed:
da20fcc3-68fd-496a-829e-bd76ba753029 | checkpoint | 6.3 - As-built Survey
b04b84d7-5ef7-5022-a05f-785f49efbaef | note | FREQUENCY: Each Lot
964f6a1d-7030-518f-996d-3cef54e4d06d | note | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the Table 610.472 as applicable to the element.
82632639-5635-5823-8b0a-7590a670e740 | note | ○ Where a shape is required, ±25mm with no depressions greater than 15mm.
9d661cf5-3928-57d8-9974-8c967f5463d9 | note | Attach: Survey As-builts / Survey Report
686ee25c-e9b3-5660-987b-9bf358714970 | note | REFERENCE DOCUMENTS:
23159588-1045-5c3e-aced-4c489f21292d | note | INSPECTION/TEST METHOD: As built
95aef172-6e1a-581d-a43b-e5fb39883bf2 | note | RECORD OF CONFORMITY: This ITP signed, HPR release in Procore
f00c4bed-2134-5530-ba39-fc3b2bcef061 | note | IP
1bb636f0-89ec-53c2-bd5c-8b6cb12d2322 | note | RESPONSIBILITY: FH Engineer
725da39c-ed9f-5fff-8681-7f6a2e09267f | date | Date Completed:
df42dae1-f712-4b2e-9822-882d45320018 | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
db440574-e264-5edc-9ca9-fb5df415516d | textbox | Fulton Hogan - Print Name:
48ae8cf6-ba80-575a-a738-d144a6497d05 | textbox | Fulton Hogan - Position:
29260148-b70e-5047-98be-aa55c392fb35 | date | Work Completed On:
b36b3825-ee2c-4600-a6f3-84673207d25d | signoff | Add Signature
fa2d44d2-c2da-46d5-9a73-d554af6546e1 | checklist | DTM-ITP-013- Retaining Wall Backfill Rev0 | itp | DTM-ITP-013- Retaining Wall Backfill
d9f6cbcf-f749-4847-80b3-1e05704a35b4 | section | 1 - Preliminary Works
6c3dc384-e42b-4ec6-9db1-01b901a32553 | checkpoint | 1.1 - Check for correct documentation
466407c4-9947-5f63-86ba-472d6cd1c202 | note | FREQUENCY: Prior to commencing any activity
eb3d9b5e-69bf-5d6c-9c7f-2919e9330b48 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
f8b7c5c1-ecd5-5cf2-aa9b-570791d54993 | note | – using the correct and complete set of drawings
e01b82bd-eac6-587c-a4c0-891939311034 | note | – all drawings are the latest revision
31605e70-40e8-5e4a-b13f-29fc4aa19969 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
fdb78761-1c0a-524a-b1c1-c242ae45ec0e | note | INSPECTION/TEST METHOD: Visual inspection
88faa5e1-3c2a-5212-81ef-095616827c90 | note | RECORD OF CONFORMITY: This ITP signed off
9cf63fc6-4d8c-51fb-8bf4-e83826aaaada | note | HP*
2905e69b-5e79-5416-85ed-2c5593303dc4 | note | RESPONSIBILITY: Site Engineer / Site Foreman
763fddb3-c0c1-56b2-b3f2-bec9a80b850d | date | Date Completed:
54c63e4f-ccff-4174-bf1d-a1371ce361fe | checkpoint | 1.2 - Implementation of all measures and controls
6af7d1a0-e8fe-5b72-a7ac-f709c52bb10f | note | FREQUENCY: Prior to commencing any activity
9ce60c56-996c-5ee5-9148-c284168b4a14 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, JSEA, SWMS & Work Pack
af740d1b-ab94-5b04-aa9e-2bb71a24c1f6 | note | REFERENCE DOCUMENTS: PMP, EMP, TMP, JSEA, SWMS, Work Pack
48ac95af-a786-5a8a-ad75-ba821d734cae | note | INSPECTION/TEST METHOD: Visual Inspection
9191e411-462f-5031-b6ad-4b421ae12dbc | note | RECORD OF CONFORMITY: This ITP signed off
3fa203fc-da87-5b64-b78a-5e3f8e578e81 | note | HP*
9583045d-0da0-55b2-a2db-5c32e5dba252 | note | RESPONSIBILITY: Site Engineer / Site Foreman
79e7b745-d795-5660-bccc-3a6b36fbd3d2 | date | Date Completed:
f4426c88-fdf3-4b2f-92d1-3bc2f0b40efb | section | 2 - Construction Works
69e5d19d-8323-4733-a52a-690ac4e68dcd | checkpoint | 2.1 - Survey Set-Out
f4973134-843d-585c-b5d1-b692992d531e | note | FREQUENCY: Prior to commencement of excavation
5e0548f5-8fba-5393-8340-9fd4b013a550 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
f1b31e20-b211-5e50-96cf-4e53192445ec | note | REFERENCE DOCUMENTS: Work Procedure
68a3762d-57e1-5c95-8bb6-a814b6eb088d | note | INSPECTION/TEST METHOD: Verify
bdd6c21e-61e8-5dc3-a29c-3793ccda03d7 | note | RECORD OF CONFORMITY: This ITP signed off
7eedeedb-e43f-5474-96cd-51bcfc02dbb7 | note | IP
8a77abcc-99db-5620-ac09-75f2e7251810 | note | RESPONSIBILITY: Site Engineer/ Surveyor
7ac87722-91ed-5b1a-b618-293d744a0727 | date | Date Completed:
32ba6314-8ef6-43dd-8034-50be4b033b7e | checkpoint | 2.2 - Excavation Permit
52168f8d-9baa-51ea-abb2-54550925aa1d | note | FREQUENCY: Each lot
227157b8-9802-54d6-a512-1084b9c31d11 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
06f15d88-b448-593c-bca6-7e51e772542d | note | ○ Plant and equipment shall be appropriate for the task.
b8d21019-3e56-570d-aad7-9e475a849bc2 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
3b8e3138-43e2-564b-8104-863105bd3fdd | note | REFERENCE DOCUMENTS: Excavation permit
012429e1-c97c-5f21-8955-04078460f5c8 | note | INSPECTION/TEST METHOD: Verify
1a2c9f29-abc0-546c-8995-1b9259bd9dbd | note | RECORD OF CONFORMITY: This ITP Signed Off
5ad78e71-bf5a-5470-b1a2-68f77ad3d028 | note | HP*
49cdf381-0414-5b56-b68f-765b38718c7c | note | RESPONSIBILITY: Site Engineer
04f04126-07cd-55af-820b-6886bf2f34f1 | date | Date Completed:
f42db735-296b-40ce-b19f-45af67413292 | checkpoint | 2.3 - Placing Fill
bca2a56c-2a7f-5561-82ad-1d463c3beed8 | note | FREQUENCY: Prior to Commencing Fill
58219216-fcb0-5953-8e50-43dfd75d7e43 | note | ACCEPTANCE CRITERIA: Placing fill shall not commence on the prepared areas until the area has been reviewed by the Superintendent
01187042-8622-5823-94a6-a9a70b9cdd44 | note | REFERENCE DOCUMENTS: DSG Spec. Cl. 204.10(b)
5debd80e-16ac-5306-bb66-f7c2a5c2646a | note | INSPECTION/TEST METHOD: Site Inspection
3abf9c9a-0694-5b1f-8644-6777985941c7 | note | RECORD OF CONFORMITY: Area reviewed by Superintendent, Signed ITP
fac355ad-9eae-5f3f-bb1c-45a489cd0fd0 | note | HP
0ef89db5-a69e-5fe6-a9cd-8521e6ce1495 | note | RESPONSIBILITY: Site Engineer / QAV
3a51379c-877c-5fb0-8f52-09064fe9c929 | date | Date Completed:
4601da15-fdd3-4bd6-9f15-632b64a047ae | signoff | AUTHORITY HOLDPOINT
83a2a118-f4bb-4f7a-92b3-2e26ae7de22e | checkpoint | 2.4 - Groundwater
9257b6fc-8e57-583d-9cfd-d38f1d73dc3e | note | FREQUENCY: Each Lot
dc89abf0-bad9-5ecc-bb11-0d0f7e43e7bf | note | ACCEPTANCE CRITERIA: HOLD POINT
93b42053-0d01-57be-ae02-26b118a78ebc | note | ○ Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
6f6a63aa-edc1-59e4-978d-7514398f4e46 | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
7f66898e-6141-585b-ae80-0842e06d28c6 | note | REFERENCE DOCUMENTS: 204.06 (h)
7398543c-e4e1-5a52-9d5a-6c1c792113b1 | note | INSPECTION/TEST METHOD: Visual inspection
2abcc108-891c-5938-966b-f1503ef2b1a0 | note | RECORD OF CONFORMITY: This ITP signed off, Work Procedure
081fea63-53e6-5bd9-a1aa-57606a708ffa | note | HP
762b0fd5-6d7f-5bc1-95b6-031e44e057ac | note | RESPONSIBILITY: Site Engineer/ Superintendent
6c47193b-6d0e-5d19-91bc-23fc531d3c53 | date | Date Completed:
d05bbe7f-d667-421e-8406-5c471a0166c9 | signoff | AUTHORITY HOLDPOINT
e68a4dd3-4899-4d5b-9fa3-3e71a7e7d4de | checkpoint | 2.5 - Fill Placement next to Structures
8bde2795-8d15-5916-be63-8c37bb1bfb74 | note | FREQUENCY: Prior to Placement
30723264-9a9a-5171-a4c8-2ffd1f389d83 | note | ACCEPTANCE CRITERIA: HOLD POINT
39816d72-8060-54a7-a910-09365a476424 | note | ○ No fill shall be placed against or within 3 m of a structure until the foundation for the fill has been reviewed by the Superintendent.
dec85bdb-fa4d-5eba-a28f-33465c54a6cd | note | REFERENCE DOCUMENTS: DSG Spec. Cl. 204.11(b)
4a2828cc-489f-597b-861a-c22390882511 | note | INSPECTION/TEST METHOD: Site Inspection
76e2711f-8ea6-5c59-92b2-a0d3a077774d | note | RECORD OF CONFORMITY: Signed ITP
11ec58f1-6a07-55dd-a5ff-1ba9765583ff | note | HP
b97b2aff-7b9a-5904-87c7-2bf337402a27 | note | RESPONSIBILITY: Site Engineer / QAV
56c984a3-5854-57a4-8009-72a73c713ded | date | Date Completed:
b5d2e139-f4f7-4c7f-883e-e4de27de1b46 | signoff | AUTHORITY HOLDPOINT
8a6ee360-fc9a-4c1b-8f39-e8413e897dd2 | checkpoint | 2.6 - Compaction of Fill next to Structures
32b824bc-5276-5cf8-a264-69dee3a8e337 | note | FREQUENCY: Placement of Fill
46bce60f-807d-52e6-9225-39f24eaa1d89 | note | ACCEPTANCE CRITERIA: The permeable fill material shall be placed in conjunction with the adjacent fill in layers not exceeding 150 mm compacted thickness, and compacted to refusal using hand operated 120Kg vibratory plate compactor.
a4b57551-f924-59f9-be58-f6a2d051705f | note | ○ Compaction plant shall not be operated within the minimum distances from structures shown in Table 204.111
042c86dd-0d7d-5e01-91c5-97b7307a7c0c | note | ○ The difference in level of any fill being placed on opposite sides of a structure or structural component shall not exceed H/4 or 500 mm, whichever is the lesser, where H is the height of the structure.
8c20c2aa-4a5a-5461-8a98-ec9ad1f98a96 | note | REFERENCE DOCUMENTS: DSG Spec. Cl. 204.11(b), Drawing 0320-0321
782ac52a-e961-592e-840a-e4eb2e044f8a | note | INSPECTION/TEST METHOD: Visual Inspection
a02b1969-9b1f-5acf-a1c8-9d8a7bfeac52 | note | RECORD OF CONFORMITY: This ITP signed off, Work Procedure
9afed4ce-e0bc-56a4-b001-7af0cc6fce33 | note | IP
c8e50fe8-3070-5fa2-a7f1-32fc374c4f06 | note | RESPONSIBILITY: Site Engineer / QAV
06746bfd-835b-58cf-9381-ccf652589c38 | date | Date Completed:
47ccfbe0-ca86-4b65-919c-be6c661e39bd | checkpoint | 2.7 - Topsoiling (Behind Wall)
6d7b8a25-d67d-552e-8fb7-f78169f210b2 | note | FREQUENCY: Each Lot
3e8dc0b6-7e7c-56b3-bc14-df25f3c9124f | note | ACCEPTANCE CRITERIA: Supply of Imported Topsoil meets requirements of Specification Section 720 and Table 720.03, at a minimum depth of 75mm
dfd7feb1-caea-5912-8a0e-315a30a14a95 | note | REFERENCE DOCUMENTS: DSG Spec. Cl. 720.03, Table 720.031, Table 720.051
e2a8c720-382b-5ed7-8a3b-5026439b900c | note | INSPECTION/TEST METHOD: Visual Inspection
6807333a-e134-585a-b668-e08323b9aafe | note | RECORD OF CONFORMITY: Signed ITP
118151a5-d65f-59d3-870d-18e3512f1feb | note | IP
ff71c01b-8aea-5bc5-b5b2-a63a2d1e10bb | note | RESPONSIBILITY: Site Engineer
55520ec3-eb58-5a81-a63a-2951ca381e1e | date | Date Completed:
19399d21-c23d-4847-a251-d1ad9e0943ad | checkpoint | 2.8 - Landscape Works (Behind Wall)
d5ba1b20-fc7f-53d0-a908-2296d4f2df82 | note | FREQUENCY: Each Lot
00afc08a-bb6b-5f25-b92d-ef6911f45fc3 | note | ACCEPTANCE CRITERIA: Landscaping and/or Grassing as per NOAW Agreements, drawings
6b9fa622-21c9-5469-ba58-357e8c4be9fc | note | REFERENCE DOCUMENTS: Notice of Acommodation Works, Drawing 0320-0321
5ad30d2e-b75e-56b1-aa2d-525b42355768 | note | INSPECTION/TEST METHOD: Visual Inspection
9bddce12-6e38-5677-b763-fcf7b2b7781e | note | RECORD OF CONFORMITY: Signed ITP
43592398-3ae0-552c-8cc9-119962e8dabe | note | IP
9502bf3c-61b7-5b25-8063-a1d95d4acda3 | note | RESPONSIBILITY: Site Engineer
e22f2d02-16db-50a2-abc9-2a493c193af6 | date | Date Completed:
e6c0c3ab-8134-4b50-abdc-cafc728615b9 | section | 3 - Testing
6d67a054-547c-484d-98f2-c97bed3310d0 | checkpoint | 3.1 - Proof Rolling
0fb86792-2445-58fb-a73f-2b8e5565a0d3 | note | FREQUENCY: Each Lot
b9b85ed2-824b-5305-9ae3-627a5c9d9136 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173, before proceeding to subbase construction.
27924d92-94dd-57a0-9416-25ffff810a6a | note | ○ The Contractor shall submit a test rolling procedure to the Superintendent including the method of preparing an area for test rolling, the extent of test rolling and a requirement to provide not less than 24 hours notice of the location and commencement time for the test rolling to the Superintendent.
321ffd6a-9609-59a6-8248-d2e10c0c972f | note | REFERENCE DOCUMENTS: 173.03, 204.12
994a572e-9456-54de-86fb-27319b21fcc5 | note | INSPECTION/TEST METHOD: Visual Inspection
89ce7536-4468-5177-9007-d9c50fb2ed68 | note | RECORD OF CONFORMITY: This ITP signed off
101ffec6-2948-5084-bd55-1fc274c998e7 | note | HP*, WP
0ca46d23-d0e6-5f50-90f2-bd234e700500 | note | RESPONSIBILITY: Site Engineer/ QAV
b0d2ed88-67a8-5b61-acda-d27095cb2ca9 | date | Date Completed:
6db08148-1893-4599-9cf1-b5ea953a9ca7 | checkpoint | 3.2 - Materials Property Testing
32f458f9-6e3b-5611-a7ef-e4595a963fb5 | note | FREQUENCY: Each Lot
0defae89-9527-5406-8631-5745f73e3252 | note | ACCEPTANCE CRITERIA: Refer to Reference Documents for particular Frequency of Testing and Material Properties Testing Requirements.
03815164-17a8-5e22-8c0f-d80d6410bd2a | note | ○ Table 204.161 for Project Specific Scales for each applicable Road Name or Area.
58bc8c49-fc8b-53bf-b0c2-f5b73d3fac2c | note | REFERENCE DOCUMENTS: Tables 204.141, 204.142, 204.161
f3dbb51f-3f7e-5b69-a58e-a14673e0d507 | note | INSPECTION/TEST METHOD: Verify
007bf080-e70b-5be7-95d1-a6d1a62a574d | note | RECORD OF CONFORMITY: This ITP Signed, Test Records
26058823-0dc2-5142-92ce-9aeb265872ff | note | TP
336dafc1-49f8-52b9-b3f3-abf356200de7 | note | RESPONSIBILITY: Site Engineer
1cab148b-a920-56e2-a165-6213819d5ca3 | date | Date Completed:
c42598fe-70ee-48b6-a2c1-8c7a436ef951 | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1fa048d2-8aa8-540b-ade7-2c6dd1810c8d | textbox | Fulton Hogan - Print Name:
6f3c3874-6e35-5e89-81f0-dda74b41344d | textbox | Fulton Hogan - Position:
0812c7db-47c0-5c3f-b638-d19dd74aa484 | date | Work Completed On:
16877d15-c7cd-4a96-b0c6-630f66e5f6f8 | signoff | Add Signature
777e032f-8dfa-4220-a09d-10394b1f4972 | checklist | DTM-ITP-014- Water Main Relocation Rev0 | itp | DTM-ITP-014- Water Main Relocation
d496d25e-09a5-421d-97f3-dc7477647c4e | section | 1 - Preliminary Works
fe7ee578-0d2d-4ff3-a7e5-6feb5f24f680 | checkpoint | 1.1 - Obtain the TasWater Engineering Design Approval
e8da18da-195a-51e7-aa16-cf8e8c5f2319 | note | FREQUENCY: Prior to commencing any activity
66c12489-fb04-5789-a569-4297f25e1989 | note | ACCEPTANCE CRITERIA: Ensure that project drawings are listed on the engineering design approval document and that it has not expired during time of construction
1f3d09d4-1a0d-5261-a624-63994da77a0d | note | REFERENCE DOCUMENTS:
55fb851e-9583-5f3a-a03e-77a214cd0ca1 | note | INSPECTION/TEST METHOD: verify
68d59cd2-4387-57b4-ad55-ffd16bd60e86 | note | RECORD OF CONFORMITY: This ITP signed off
26c8fb27-546b-52c1-87dd-0090ccca0ff9 | note | HP*
b42f458e-bfb2-501d-a950-2a62e9ddf6fe | note | RESPONSIBILITY: Site Engineer / Site Foreman
fde1d9f4-4b06-5a43-814d-7bd0c9fe4255 | date | Date Completed:
e8514f03-bcd4-4888-9513-5198fd99a99b | checkpoint | 1.2 - Pre job-start meeting with TasWater
351f0444-b549-5b4d-ac7a-d5724ac2a911 | note | FREQUENCY: Prior to commencing any activity
e2881f6b-c10e-53d4-a68c-85f547f088f7 | note | ACCEPTANCE CRITERIA: Prior to receiving the permit to construct, a pre-start meeting between responsible contractor and TasWater relevant project manager and ground crew is to be held on site.
34987b56-8f40-5876-9deb-fd4c0524f1a9 | note | REFERENCE DOCUMENTS:
f01434b7-a82e-5028-aae8-b8a71c3acecc | note | INSPECTION/TEST METHOD: verify
8cf330b6-3f0a-5d8e-b4c6-48ed80c5fea6 | note | RECORD OF CONFORMITY: This ITP signed off
8fd02161-cd97-536e-866c-34a8be562d11 | note | HP*
2d5196f2-b0a1-5edb-b9fa-4f0c65cafc15 | note | RESPONSIBILITY: Site Engineer / Site Foreman
16144df7-fb6b-557b-89b9-613af61dd9c3 | date | Date Completed:
363fd45e-8862-4b8c-85d6-a0531df61008 | checkpoint | 1.3 - Apply for and obtain permit to construct
680dbd1c-8d51-5850-8f8a-0709b929103b | note | FREQUENCY: Prior to commencing any activity
8126b1ef-97ee-5eb9-997f-872fcd5a8db0 | note | ACCEPTANCE CRITERIA: prepare and submit application for a permit to construct no less than 10 business days before commencing any activities.
9f07800e-4ccf-5fbd-b471-c9ae2c9fc685 | note | REFERENCE DOCUMENTS:
8fffab7b-26d9-537f-b26f-279cbfc6f33b | note | INSPECTION/TEST METHOD: verify
0d0993d0-653b-55f7-bb8d-d9589a2e11f0 | note | RECORD OF CONFORMITY: This ITP signed off
531cc681-c06e-5cc4-a544-8295f6c8a00f | note | HP*
a2b655ac-9ca6-5ca6-99cf-c86a7b8e8f03 | note | RESPONSIBILITY: Site Engineer
9ea0e470-2a28-5b43-b5a2-017f0ba0e01e | date | Date Completed:
37c658c0-1228-416e-bc5d-83291351816b | checkpoint | 1.4 - Preparation and submission of construction management plan
ed9a86b1-0a54-5126-9ced-d7a0670920ed | note | FREQUENCY: Prior to commencing any activity
cc2092d2-ffa3-5416-b69c-13db356f6058 | note | ACCEPTANCE CRITERIA: Prepare a construction management plan. This must detail how the new TasWater infrastructure will be constructed while maintaining current levels of services provided by TasWater to the community.
e7c50529-53e8-5351-a91c-4a5fe22a4d71 | note | ○ The construction plan must also include a risk assessment and contingency plans covering major risks to TasWater during any works.
31bdee25-e58b-5455-b54b-a23d37ca5ceb | note | ○ The construction plan must be to the satisfaction of TasWater.
d28aa461-1326-5323-ac5f-cb12dd2a419b | note | REFERENCE DOCUMENTS:
11c26ad4-38bc-5fde-8a27-8bc084fdad3b | note | INSPECTION/TEST METHOD: verify
e18606bb-0cd3-5eaf-8dba-a1625514c8c3 | note | RECORD OF CONFORMITY: This ITP signed off
4b0d1b95-52b3-5328-b5f5-6f57660b13ec | note | AP
01dcae4d-7c0c-53a5-b4f1-d0c2e9311eeb | note | RESPONSIBILITY: Site Engineer
c652b985-2093-586e-8202-bec116e5905a | date | Date Completed:
42868a3d-c2db-41bf-b459-d77ce3125e4c | checkpoint | 1.5 - Request and schedule booking for a witness pressure test with TasWater
58c39eb6-b4a8-5e21-a774-5d3e908bb75b | note | FREQUENCY: Prior to commencing any activity
6fd41f56-2fad-5eb4-be2a-1856bb2bd870 | note | ACCEPTANCE CRITERIA: After new section of main is installed, TasWater must witness a pressure test of the new section of main.
f6ebc6d2-6acd-5207-b7e1-349c5fb629d8 | note | REFERENCE DOCUMENTS:
31e68e88-a311-581a-b3c0-ce0bccb5dd70 | note | INSPECTION/TEST METHOD: verify
94172802-3310-5edc-b2a0-909089a4bd9f | note | RECORD OF CONFORMITY: This ITP signed off
9fa42711-643f-541a-ab2e-9007fbf7ee55 | note | WP, HP*
9ec414d7-1d9c-5e98-a625-734cdc808939 | note | RESPONSIBILITY: Site Engineer
e23be929-8631-5c3d-97af-9c7b844d7e9c | date | Date Completed:
84fd54f4-c6d8-4083-813d-fc781908ef83 | checkpoint | 1.6 - Request and schedule the isolation and cuttover to new infrastructure
3c16bfee-1d51-5150-924a-75aa711643df | note | FREQUENCY: Prior to commencing any activity
7e1ef549-27e0-5bf8-91df-55e70b69d201 | note | ACCEPTANCE CRITERIA: A permit for shutdown must be applied for through the TasWater Application for Development Services portal. A minimum of 2 weeks notice must be given to TasWater before required service isolation so that affected residents and businesses can be made aware through a letter drop
09fa0900-c40d-5d1f-bb68-5712c6feb51d | note | REFERENCE DOCUMENTS:
1b41dbb0-338b-508b-af89-fc49d3cb33e6 | note | INSPECTION/TEST METHOD: verify
65d84091-b59c-515b-9cd8-28ac8204fc65 | note | RECORD OF CONFORMITY: This ITP signed off
ad5d0edf-b3aa-5f24-8fdb-c27bddbdae84 | note | HP*
60e4bce8-5882-5d86-ba70-b65e6ac4664c | note | RESPONSIBILITY: Site Engineer / Site Foreman
426914d7-1f95-5ef6-8238-6f934259a5de | date | Date Completed:
eef61063-7ec6-417a-911c-655035789859 | checkpoint | 1.7 - Check for correct documentation
a29d15b8-5c6d-5cea-9d35-0a19e2c30228 | note | FREQUENCY: Prior to commencing any activity
f0e0807b-99aa-52cd-b33a-a81f795540b2 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
9ea49b1c-29b7-50f3-ad00-082a2b22eebd | note | – using the correct and complete set of drawings
f6eb75b7-fd05-5e5a-8bc6-f3bb42673c70 | note | – all drawings are the latest revision
d5306717-b9dd-5859-abff-b574613a04f9 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
8d23cc56-6a57-55ec-8570-4671806332ff | note | INSPECTION/TEST METHOD: Visual inspection
f7b1867a-3373-5613-8c6c-58a777feb272 | note | RECORD OF CONFORMITY: This ITP signed off
a508d17a-5c24-53d7-8819-38bd70b693f2 | note | HP*
9831b150-8dda-5666-9f26-337cf7d80abe | note | RESPONSIBILITY: Site Engineer
0249369e-cafb-52e0-bc7b-df95e385d1c3 | date | Date Completed:
42c3f71d-1670-4910-a235-80cfff564252 | checkpoint | 1.8 - Implementation of all measures and controls
de3a827b-abfd-5d66-9e44-2ba14c9d4617 | note | FREQUENCY: Prior to commencing any activity
aead9c98-663c-5cfd-bdae-80bcbfd52fda | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PMP, EMP, TMP, JSEA, SWMS & Work Pack
ea7a9ea0-8193-554b-8a6a-9e4b46449f83 | note | REFERENCE DOCUMENTS: PMP, EMP, TMP, JSEA, SWMS, Work Pack
ea341d2d-ef42-5748-86b0-3031ceb62361 | note | INSPECTION/TEST METHOD: Visual Inspection
ed2bff33-8a35-55fa-9b41-84ee4d82b3e7 | note | RECORD OF CONFORMITY: This ITP signed off
a97ad796-55d2-5504-8011-9967b1db6c56 | note | HP*
89c5ceb9-7975-5e6e-aab3-cf1d3ea91dfa | note | RESPONSIBILITY: Site Engineer / Site Foreman
e59ec1ab-07fe-5ec4-a92f-c7a6eed11bdb | date | Date Completed:
b2096b29-eb15-4a5e-a163-659910146c1c | section | 2 - Construction Works
562ee27f-41d6-46b4-b088-f3d496e94063 | checkpoint | 2.1 - Survey Set-Out
de10e731-913a-5ce0-9798-9254205a3283 | note | FREQUENCY: Prior to commencement of excavation
be3bf968-c07b-51f5-879f-14d4367a53f7 | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
72f640e0-20be-5877-ac1c-e264c4b885ef | note | REFERENCE DOCUMENTS: Work Procedure
ca036739-5552-5286-af64-599f2ef2f5ec | note | INSPECTION/TEST METHOD: Verify
3f8f9a1e-1d5e-5225-a05c-7d5fcc9b64b2 | note | RECORD OF CONFORMITY: This ITP signed off
2627791c-06a1-55be-87a2-5e41a63a67c2 | note | IP
74336e6c-38b2-561b-87c8-e3e74f717cba | note | RESPONSIBILITY: Site Engineer/ Surveyor
6ce3c93e-1ae2-5c06-8042-0ff65b6b6d25 | date | Date Completed:
672049b5-6871-4bc8-9a18-6f1e931c52ff | checkpoint | 2.2 - Excavation Permit
91086cfd-3e96-58ea-aee7-ee0e512afa9c | note | FREQUENCY: Each lot
423dfe42-ccb1-5bf6-83e4-bd261d01ce46 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
77f287b7-fc9e-5f42-9a17-14382b72e88f | note | ○ Plant and equipment shall be appropriate for the task.
00369439-51d2-50ec-83f8-ee2674b69131 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
0a81f4f6-b7f9-59cd-bede-4878b5fc12be | note | REFERENCE DOCUMENTS: Excavation permit
b1c94557-fec4-58bd-9ddc-1c30de51e8ed | note | INSPECTION/TEST METHOD: Verify
7e94827e-b381-5aee-a3c0-3b8e2dfcbaf0 | note | RECORD OF CONFORMITY: This ITP Signed Off
37c43dfe-c537-55f0-91bd-e5a8c3a74d7b | note | HP*
3cdfad7a-4645-5c70-b431-1b26e28c9168 | note | RESPONSIBILITY: Site Engineer
ae12c668-0644-531a-904e-594fae872222 | date | Date Completed:
19b3cfdc-7317-4e89-8798-673f3086b1ef | checkpoint | 2.3 - Vacuum excavation of trench
e992f9f4-cbad-5d89-a7bd-d232e3241e90 | note | FREQUENCY: Each lot
ec6a7ce7-bcef-5b9a-9f15-a8bde6211a5c | note | ACCEPTANCE CRITERIA: As above with excavation permit. Ensure any known and previously proven services are marked on the ground prior to excavation commencing.
d76d3394-ae67-5864-a36c-60b1fa7e79a9 | note | REFERENCE DOCUMENTS: Excavation permit
7a119293-2d22-52a2-95e8-b5253abfcabd | note | INSPECTION/TEST METHOD: Verify
534c1c4b-9386-5285-b485-844525a7ed8d | note | RECORD OF CONFORMITY: This ITP Signed Off
0e5e4365-dbd1-5c35-907c-0d223ea6fbd1 | note | HP*
d40b613e-1f4a-5dec-b80f-7edd89eff6b6 | note | RESPONSIBILITY: Site Engineer
151dde77-6bb9-51e2-b1e1-c1aa09a5c3c2 | date | Date Completed:
835c0978-fb1e-4580-869f-396277a9561f | checkpoint | 2.4 - Installation of pipework (including new property connection).
4a267d65-faa1-5233-af95-00678f61a306 | note | FREQUENCY: Each lot
f4cb4106-9d4d-512f-89c4-e6add2f3460a | note | ACCEPTANCE CRITERIA: Pipework is installed as per certified and approved Water Main Relocation design drawings
24a73bf7-863e-5fbf-845d-0221bde2ba1e | note | REFERENCE DOCUMENTS: A1071.005 Sheet 0240,0241
a5cf5494-892f-5f60-b5a6-aac2e9e729a0 | note | INSPECTION/TEST METHOD: Verify
2c73fc13-0cc5-5d40-b714-a9a31cb09a34 | note | RECORD OF CONFORMITY: This ITP Signed Off
a4c96453-9e21-5db5-9eff-43277474d5ba | note | HP*, WP
f485ad22-4fee-5bc8-8ce4-fa75e59ef8bc | note | RESPONSIBILITY:
26e85112-e065-5330-ac21-2e4042f0af7b | date | Date Completed:
7823b1b6-1dc1-41ef-875e-4a0aa21a5f13 | checkpoint | 2.5 - Installation of thrust blocks (temporary and permanent)
2ac924f7-8e5d-52bb-829d-0bca7dccb29a | note | FREQUENCY: Each lot
5f6f53dc-59eb-5c9b-b293-07b438f47cb6 | note | ACCEPTANCE CRITERIA: Thrust blocks are installed as per MRWA-W-204
bbc63af8-8f42-50e3-a5ae-796b418d1b0d | note | REFERENCE DOCUMENTS: MRWA-W-204
d606b286-7fa2-5281-8da2-8cbf6dc19c63 | note | INSPECTION/TEST METHOD: Verify
897fa4d1-c432-5991-a312-ce2136730343 | note | RECORD OF CONFORMITY: This ITP Signed Off, TasWater written approval
d8254d28-865f-5c0f-92eb-9f1acf8e6cca | note | HP*
8e9028e3-5fc0-518d-9cee-e58c8c94b1d9 | note | RESPONSIBILITY: Site Engineer
c237dc25-01fe-5d7c-bf59-831a05608f82 | date | Date Completed:
25371a40-79bf-4ff2-8f6c-12f603c76a1e | checkpoint | 2.6 - TasWater Inspection
d0f47db2-e9fa-5d3b-9904-d144da613da5 | note | FREQUENCY: Each lot
6586dc27-98d2-5b74-a2c7-662ae20c3bfc | note | ACCEPTANCE CRITERIA: Installation of pipes/valves/hydrants/thrust blocks prior to backfill
2e011441-35ae-5928-a3b5-36dbdf0febc0 | note | REFERENCE DOCUMENTS: TasWater Permit to Construct
e2d54644-2b58-5743-be74-011688ad31d0 | note | INSPECTION/TEST METHOD: Visual Inspection
172eb2de-7d0b-5f0c-ab60-fc29ea9f5610 | note | RECORD OF CONFORMITY: This ITP Signed Off
2627e464-e2fe-5a0c-9404-84315ae813f2 | note | HP*, WP
57355d39-6b40-5830-8f60-8a4b3b3a2997 | note | RESPONSIBILITY: Site Engineer, TW representative
7d45969a-4a4b-5675-a136-8ea864ef4e3c | date | Date Completed:
db27057a-edc4-4277-8978-b0c47e5d9301 | checkpoint | 2.7 - Back-fill of trench for purpose of pressure testing
098db92b-d1a6-5868-a4f5-fba9d56c3ddc | note | FREQUENCY: Each lot
93b2dac0-a855-55f3-9607-b07c261e075d | note | ACCEPTANCE CRITERIA: Pipework is back-filled as per A0171.005 using pipe embedment to either WSA-PS-361 if 5mm clean back-fill or WSA-PS-360 if sand to 70% compaction and 20mm crushed rock to 95%R compaction above.
78398470-aa4b-5bd1-8dbc-9992d5c971de | note | REFERENCE DOCUMENTS: A0171.005 Sheet 0240, 0241, WSA-PS-360 OR WSA-PS-361
753abf0d-bb12-5907-a020-2ef416093b49 | note | INSPECTION/TEST METHOD: Verify
c94e8df1-8d1d-53d5-87ae-f5a3ccc4ff20 | note | RECORD OF CONFORMITY: This ITP Signed Off, Delivery dockets, Compaction test results
a2dfc8f6-97d4-502f-89e6-d87dec519a23 | note | HP*
7035b1f3-a560-5962-9cc4-a4dae3f88304 | note | RESPONSIBILITY: Site Engineer
38da03a2-ce85-56e1-91f9-6ede9601259b | date | Date Completed:
ae30c52e-51fe-44a7-b6ca-9eec76324ee8 | checkpoint | 2.8 - Removal of old section of water main
5517653f-3cf7-520b-8796-e1d7a27379ed | note | FREQUENCY: Each lot
7a872391-5ce2-5e6e-a576-56358a480d3a | note | ACCEPTANCE CRITERIA: Removal of existing water main following successful cuttover to new section of water main. Method of removal will be mechanical excavation.
28acae8e-6288-5e0f-9b3e-f6451a1fafae | note | REFERENCE DOCUMENTS: Work Procedure
08b2e013-8150-527c-9f55-f07732892d89 | note | INSPECTION/TEST METHOD: Verify
c9fa96f4-a217-57db-b80e-949631ba5052 | note | RECORD OF CONFORMITY: This ITP Signed Off
e22f1fc6-b2be-58ce-bb6a-ebd8e71dbb2e | note | HP*, WP
433edad7-592b-5f29-b8fe-e63bbce1c620 | note | RESPONSIBILITY: Site Engineer
d496686f-2883-5d0a-a7d3-18c019b1b079 | date | Date Completed:
da13ad04-ccfc-45ba-bb91-2d0139f4a912 | section | 3 - Testing
07956759-af1c-42d8-b3f0-4168a4dcb757 | checkpoint | 3.1 - Pressure Testing of new pipework
786fde94-a59a-5e81-84e0-4b55ee9e7901 | note | FREQUENCY: Each Lot
6f7f8c36-eee6-50c5-af5e-9f84c2bd83ff | note | ACCEPTANCE CRITERIA: Hydrostatic Pressure testing 1.25 times the designed working pressure as claculated by the Supervising Engineer in accordance with section 19.4 of WSA 03-2011-3.1 Water Supply Code of Australia Part 2: Construction Third Version 3.1
2a0daaf2-9e52-5657-a8bf-ccec4919bb51 | note | REFERENCE DOCUMENTS: WSA 03-2011-3.1
a9ed8119-025d-55d9-8644-39bd7bcb81a7 | note | INSPECTION/TEST METHOD: Verify
5eadd537-1aeb-56a6-85ea-54df3da80b5c | note | RECORD OF CONFORMITY: This ITP Signed, Test Records, TasWater written approval
180d1573-ec23-551e-aa1d-6f30fbd97cf9 | note | TP, WP, HP*
c8fb61fa-6e26-52ca-aacf-99cfc34fca55 | note | RESPONSIBILITY: Site Engineer, TW representative
8383c184-4487-5c75-985c-566c8c2f1fab | date | Date Completed:
d6d1f9cf-eee7-4f22-bf5b-3cb06e73e796 | checkpoint | 3.2 - Cut-Over
a09b7381-541b-5e47-9c26-c979537e27d0 | note | FREQUENCY: Each Lot
218b4cd3-4198-5a12-8f8c-7e2e9b986a89 | note | ACCEPTANCE CRITERIA: TasWater to isolate existing watermain to allow for the cut-over from the existing section of water main to new.
8aadad40-7ae1-5b8b-b861-07fb97de8f73 | note | REFERENCE DOCUMENTS: A1071.005 Sheet 0240,0241
7a5e8633-a87a-5e6f-b216-67589ef64d01 | note | INSPECTION/TEST METHOD: Verify
e76e9722-f269-5648-a46d-1d230c741707 | note | RECORD OF CONFORMITY: This ITP Signed, Test Records, TasWater written approval
713cab08-88eb-5206-82d8-b75f66813c3b | note | TP, WP, HP*
b153e358-542e-52a6-a3f1-d2bff2160b75 | note | RESPONSIBILITY: Site Engineer, TW representative
90715bd7-ea62-5719-b852-6f8b8ce96b1c | date | Date Completed:
8c0d7d6b-344f-42e2-9877-dff57978cdee | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e6cb0346-bec7-5cc3-b9e0-60b6cfe3d849 | textbox | Fulton Hogan - Print Name:
169143e6-2cb3-5eb4-a15e-d55b159b986e | textbox | Fulton Hogan - Position:
f76ded3e-f7c4-5615-ab53-88571866a9f3 | date | Work Completed On:
4225f234-9562-4b1b-9548-4b0b63f89b2e | signoff | Add Signature
01f0dcfb-3bfa-4507-83e5-7d0c249f124b | checklist | DTM-ITP-015- Asphalt Placement Rev1 | itp | DTM-ITP-015- Asphalt Placement
b7d5a63c-d42c-4c36-8dab-38d43ad7b48c | section | 1 - Preliminary Works
e6584f21-8731-4375-b19b-9fe56481a4cd | checkpoint | 1.1 - Mix Design approval
f1461c80-f27c-5adc-8813-86415046a32b | note | FREQUENCY: Prior to commencing paving
7a602ad8-d4fd-59d3-b847-f6737462bae3 | note | ACCEPTANCE CRITERIA: Mix design to be used has been approved by project superintendent, prior to use
31cf87a0-c6f3-578e-85cc-4de893bdb707 | note | REFERENCE DOCUMENTS: 407.09 Mix Design Registration
1af4be20-4910-538b-81c1-b714743d1b25 | note | INSPECTION/TEST METHOD: Approval Correspondence
93a4a562-042b-5f3e-b087-36e64fb30068 | note | RECORD OF CONFORMITY: Supply of registration certificate
1101f2cb-7b9a-51ee-b6c0-89198e18a81d | note | HP
6211b1e1-f994-5bc4-bb57-dff70385459f | note | RESPONSIBILITY: Engineer
bebdbe30-b1cc-57ea-9ecd-4fb97b46c79e | date | Date Completed:
9a4e309b-9606-41d8-9a79-71987d8cb80c | signoff | AUTHORITY HOLDPOINT
59dd2a18-8997-4347-bf44-1cc6a9abce56 | checkpoint | 1.2 - Site Inspection and Base Condition
96f4832b-b759-50c6-881c-906922f6eb7e | note | FREQUENCY: Prior to commencing paving
a985246a-31d0-5f25-a1f1-58b98bec1be9 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles, defects (holes, cracks, unstable material and edge irregularities) and loose materials.
848a3803-1ee9-5d20-9504-596fdbb36a15 | note | REFERENCE DOCUMENTS: 407.17, AS2150 10.1, AS2150 10.3
f38e5cb1-d231-582f-978d-5973e316aa1c | note | INSPECTION/TEST METHOD: Visual Inspection
728d7655-bcbf-5731-baa3-096fa4362348 | note | RECORD OF CONFORMITY: Completed ITP Photograph
5a7c5d0f-8682-550f-ad16-b1401689cddb | note | WP
b641356d-c44b-52e1-8a06-835d5de3b165 | note | RESPONSIBILITY: Asphalt Supervisor
8187c94e-4422-55f8-be8f-9504e12dd2e3 | date | Date Completed:
2b9d6932-2dc8-4dd6-9d53-8c6bde0d9558 | checkpoint | 1.3 - Ambient Conditions for Placing
996e10c0-17f8-5855-b1c9-7c331f434736 | note | FREQUENCY: Prior to commencing paving
1d964590-dcdc-56aa-8968-d84ebec423da | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
eb2b2c59-81c7-53d5-b1b5-9a6b94ff01b2 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
5ee2f21e-9b5a-5e48-b56a-eada17f2a13e | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
2a342779-4232-51a6-86ed-6e533f6f2137 | note | ○ Where the above temperatures cannot be achieved, asphalt must be laid under the "Fulton Hogan Cold Weather Paving Plan"
d4fab6cf-753d-5d83-a2f8-95f19025cb27 | note | REFERENCE DOCUMENTS: 407.17
19de2d53-dec5-5f44-bf13-7d0107887169 | note | INSPECTION/TEST METHOD: Infrared Thermometer
61d50a3a-a7a9-56c7-8d3c-54842c513899 | note | RECORD OF CONFORMITY: Completed ITP Weather forecast Thermometer reading
6bcc2cca-f9df-5af9-864c-ada15faf1020 | note | IP
e0ca07c0-972d-57a8-b04a-45b7cad39259 | note | RESPONSIBILITY: Asphalt Supervisor or Foreman
f244d6f6-0f64-51bf-8882-d3362723b3f2 | date | Date Completed:
d63baa61-8211-477c-ad2b-d527ac61c0b0 | checkpoint | 1.4 - Planning of Joints
7dbeb188-8d88-5165-bd53-ca36c6977758 | note | FREQUENCY: Prior to commencing paving
4059daa3-4ead-5810-be26-07a02607749c | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of all Longitudinal Joints satisfy the following unless otherwise approved by the Client: Transverse Joints Offset from layer to layer by at least 2m Longitudinal Joints for the final Wearing Course are located on lane lines
de34daf6-0f7f-5535-9ef9-a21c63dd690f | note | ○ Longitudinal Joints for Intermediate and Base Layers offset from layer to layer by 150mm, and no more than 300mm from lane lines
9f944b8f-4c15-5fd8-8ecc-c3dd78ca3802 | note | REFERENCE DOCUMENTS: 407.21
163303f2-0168-55b6-8c6d-414ceb5a7185 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
d3837549-2912-5a7f-9346-0f0b3c3d21ae | note | RECORD OF CONFORMITY: Preliminary join plan submission & photograph on site
d62996d6-27b5-5ad9-ae18-dccb87490db7 | note | WP
d09300a3-81bc-5e4b-aeba-179fe0243651 | note | RESPONSIBILITY: Engineer / Supervisor / Asphalt Foreman
f63b9ba0-5054-524d-90e9-35d87af98dec | date | Date Completed:
b89f67e2-09f1-46c2-9838-78a66a5765fe | checkpoint | 1.5 - Tack Coat
ccd0202a-bae9-54d4-908c-f9bf51ecfa79 | note | FREQUENCY: Prior to Commencing paving
2eb0c982-66c1-5c69-9956-9f2b9c03861b | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.25-0.50 L/m2 of CRS60. This rate is to be doubled on joints and chases. Tack coat must be allowed to fully cure .
fe5702cc-7ad2-5432-9c05-b1820b7a06b5 | note | ○ NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces
26b129c5-97d8-5b97-ba4c-0739d7f79fe5 | note | ○ Photographical evidence must be obtained (with an identifiable landmark)
e26c5b9e-7d24-5451-948b-d10e31f34232 | note | ○ *from 1st July 2023, "trackless Tack Coat" must be used
cbbd2774-192c-5aec-84d1-fbcea2fe0a17 | note | REFERENCE DOCUMENTS: 407.19, AS2150 11
7808549d-78c8-5c99-a420-73463caf1071 | note | INSPECTION/TEST METHOD: Spray area and inspect
43f60b1c-733b-52b6-9ef5-6ce7b09fa973 | note | RECORD OF CONFORMITY: Completed ITP Photograph
796d2751-29ad-5249-b4ba-bc034ddabb43 | note | IP
bbaa6055-38cb-5cbb-a531-d84e987629fa | note | RESPONSIBILITY: Asphalt Foreman
62101368-3248-59db-8e1d-cfa9e2fa9a48 | date | Date Completed:
b646a67a-6db4-41e9-bff2-e6038d501376 | checkpoint | 1.6 - Selection of compaction equipment to satisfy clause 160
568e3502-f50e-5458-920e-be6d5b85614b | note | FREQUENCY: Prior to commencing paving
7efb8d22-12ff-58ad-8dd6-47e637311544 | note | ACCEPTANCE CRITERIA: An oscilating roller will be used if available or static rolling will be conducted on site. Number of rollers and appropriate rolling paterns will be determined prior to the works to achieve the required compaction of the mix. This will be assessed by compaction testing.
4b5246a7-8652-56e4-89f0-f32c5ecae86c | note | REFERENCE DOCUMENTS: 401.04 & 160
690cbdfc-851f-58c9-81c8-d2dc780f1282 | note | INSPECTION/TEST METHOD: Nuclear Density Test, DGA Compaction Procedure
0af7119f-dbf6-55da-b4d2-d1685f40feed | note | RECORD OF CONFORMITY: Completed ITP, Compaction reports
1dbd02fc-f9da-51da-885f-36607ed01d1a | note | AP
4f8ed472-d65f-58e0-8a6e-39b92362bf80 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
5c215c3b-7a51-5653-a13f-e207fcbac0c6 | date | Date Completed:
cc57a0af-f4f7-4771-a141-7911fbf34b92 | section | 2 - Asphalt Placement works
8182c62d-efe3-4b72-b816-5dd329b6b9e9 | checkpoint | 2.1 - Commencement of Placing
36ed56fd-8ff5-5d8d-9d6a-ba39a5ff2971 | note | FREQUENCY: Prior to Commencing paving
804a1e9f-763f-55cb-a9a1-cbe135fda258 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client's nominated authority.
a4db787c-c958-5fc5-b7fa-db72407b184e | note | REFERENCE DOCUMENTS: 407.23
b1125a32-de26-5ee2-84c4-554ee92d684d | note | INSPECTION/TEST METHOD: Visual Inspection
c38d54e7-1dc4-59b6-b121-4fe447620bc7 | note | RECORD OF CONFORMITY: Completed ITP Email corresponance
a45e27b0-f34c-5f8e-af81-13b1e773a719 | note | HP
6b61b01c-0c4f-53f4-8e3e-08031991686f | note | RESPONSIBILITY: Asphalt Supervisor / Superintendent
aec74d4e-19f2-5965-8bd9-9d429076a929 | date | Date Completed:
87e3a2c0-65ba-4d12-acf1-9acc3c0da91e | signoff | AUTHORITY HOLDPOINT
1cabd8de-91c1-471e-ae5e-5e36e47990f7 | checkpoint | 2.2 - Delivery of Mix
0681d9ff-d4ca-52d1-bd95-4d49d2e16687 | note | FREQUENCY: Each lot
3dc08e2c-9c04-55a5-ae0a-4ef96175a964 | note | ACCEPTANCE CRITERIA: Check correct mix design has been supplied, as per pavement design.
fb832523-304c-514d-8daa-fcd4047265b0 | note | REFERENCE DOCUMENTS: Pavement Design Details 407.20
31d2dabd-d307-59c2-ab2d-02c4b7a2f6c6 | note | INSPECTION/TEST METHOD: Check asphalt delivery docket
fac5a3e9-660c-54a0-ab1c-4d952cd0d0d1 | note | RECORD OF CONFORMITY: Traceability sheet
d3729402-ec22-58af-a5d4-43596ad4bafe | note | IP
2fccec77-4af9-5deb-afd3-d096306cee4e | note | RESPONSIBILITY: Asphalt Foreman
61df111c-e47d-5367-add1-39d142b06e43 | date | Date Completed:
cacbe3f7-2f18-42b4-802f-a609e7370f0e | checkpoint | 2.3 - Delivery of Mix
95bddeab-f226-5af2-af14-71a98f518a5c | note | FREQUENCY: Each load
1e79ec97-02e1-572b-bb86-5097eacaf4f3 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
d9596093-88d8-5f5d-8498-81ec39811190 | note | REFERENCE DOCUMENTS: 407.11 Table 407.111
4e869d4f-7e58-574e-a50e-b3f24230fe19 | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
d9a1d438-e829-54e4-bc21-ef71025ebfa8 | note | RECORD OF CONFORMITY: Traceability sheet
c1b072c2-1ae1-5731-91c1-117b59ead1c7 | note | WP
18104e52-90fd-5a58-a25c-99d40b866460 | note | RESPONSIBILITY: Asphalt Foreman
6bad2f16-a6d8-5c2d-b49d-cd400ed98c9e | date | Date Completed:
7be16ef5-82d2-49a9-82da-75d3ef1aa99b | checkpoint | 2.4 - Traceability
45b16292-9b81-55b9-8323-0274243dd7d6 | note | FREQUENCY: Each lot
d767e35a-3910-550c-97c6-53d3e56e2a3b | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
4ceecc96-ef27-5348-a934-28dd2c30e9bc | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
15724847-a4fb-53d0-aab4-9f0ac249b5bd | note | INSPECTION/TEST METHOD: Measure and Record on Daily Lot Record
b54fef0e-754c-5d32-abc1-835b636e2432 | note | RECORD OF CONFORMITY: Traceability sheet
ad622faa-d5cf-50d5-a270-002f9afcb839 | note | IP
c9b00581-d6e0-566b-9441-a2d24d99b353 | note | RESPONSIBILITY: Fulton Hogan Foreman/ Engineer
11ce75d7-e682-54a4-a587-222bc595fdb8 | date | Date Completed:
998c32a1-5641-4902-9b72-2fef3836a9fa | checkpoint | 2.5 - Layer Thickness and Level Control
86183d6a-f38f-5e3d-8d2b-995a333d9261 | note | FREQUENCY: Regularly during paving
e65a3ebb-7bae-5633-8e3d-7718b0844031 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
851c9ded-8450-547e-86e9-7335293b69de | note | REFERENCE DOCUMENTS: Pavement Design Details 407.25(a),(b)
6df7e944-659d-53fb-9f54-045c7637f14b | note | INSPECTION/TEST METHOD: Dips using ruler or dip stick
c81a3602-11dd-5d92-b0a2-177aa691c945 | note | RECORD OF CONFORMITY: Level and stringline record
c6c5e97f-9920-59b1-bbdc-fcf860e96818 | note | WP
4990afc7-5a46-591c-bf32-94cd1cccd1a6 | note | RESPONSIBILITY: Asphalt Foreman
a5bfacf9-a50a-5f81-a290-e74755de1041 | date | Date Completed:
c82e3e23-7a00-4050-995d-64505ff8f2d1 | checkpoint | 2.6 - Paver Stoppages
2f7a8f86-b71a-5b63-9f6e-3c472a894f82 | note | FREQUENCY: If paver stops
e7615f5b-9ef2-528e-8864-946b3e224486 | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
5ab58eb5-958c-5572-93e0-dbe214a011eb | note | REFERENCE DOCUMENTS: 407.25 (c)
1c17aca5-e59f-53ed-8dcb-2c6b1a71cd60 | note | INSPECTION/TEST METHOD: Thermometer
593ac53c-17d2-5af1-8c6f-7552ddf9d6d7 | note | RECORD OF CONFORMITY: Traceability sheet
e94ac733-8882-5537-9e43-18789ca7c8d3 | note | WP
a43b1327-c158-5582-b9c9-8c7b298a0521 | note | RESPONSIBILITY: Asphalt Foreman
8a99df12-07eb-5628-9af7-f97c3bbb7768 | date | Date Completed:
7e3165ee-105d-415b-abf9-071837858eef | checkpoint | 2.7 - Surface Finish of Wearing Course
ef44fc55-3477-51c8-90c3-16780796d045 | note | FREQUENCY: During paving and after final roll
cf857460-7870-5694-953a-e015b912aa61 | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
94f0e32f-83e7-5967-97fe-9a683e287d45 | note | REFERENCE DOCUMENTS: 407.25 (c)
7c4acf53-583b-5b98-a49d-37313d8a75d5 | note | INSPECTION/TEST METHOD: Visual Inspection & straightedge
b64154bf-a529-5f32-9190-baac478b56f3 | note | RECORD OF CONFORMITY: Completed ITP or photograph
04b8f84d-9bc7-5d76-be17-1fbad0942b5e | note | WP
0180e968-180d-5645-a980-500bc1ef00ca | note | RESPONSIBILITY: Asphalt Foreman
f6ead3c9-3f6f-5ef6-8d49-da960dcf0672 | date | Date Completed:
12b32dcb-625a-4205-9238-5cc5db6f956b | checkpoint | 2.8 - Kerb and Channel
068e5c27-51a3-5b5f-b37c-0dc24aee5ac1 | note | FREQUENCY: During paving and after final roll
53e40956-a8cc-599c-a66f-be5033e5b837 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
a6a7482e-7bac-5f42-b0c6-fd1ae9ac5534 | note | REFERENCE DOCUMENTS: 407.29 (a)(ii)
c712f562-5c43-591c-ac9c-c878951ee4ae | note | INSPECTION/TEST METHOD: Visual Inspection & Measurement
638b5bfb-7483-5b26-ad10-de3db086a3c2 | note | RECORD OF CONFORMITY: Completed ITP or photograph
5baaa019-dc1d-5de2-8513-bb2de90ee73b | note | WP
4ac9ad79-a519-5f32-b1f6-11b2b9d6b93f | note | RESPONSIBILITY: Asphalt Foreman
04331480-fa9a-5ee6-948d-cb18f86d95f8 | date | Date Completed:
e642238e-7797-4230-bb9c-8b178017134c | checkpoint | 2.9 - Trafficking pavement after placement
797d2de2-301a-5cb8-935a-abf8d3da4edc | note | FREQUENCY: After final roll
822e7e29-077d-5ead-a1c4-bf1b5ee62532 | note | ACCEPTANCE CRITERIA: Trafficking or placement of asphalt over type SF asphalt is not permitted unless the majority of the SF asphalt has a surface temperature of 50°C or less and Falling. Where trafficking of SF asphalt results in deformation, further trafficking shall cease until such time that the type SF asphalt has adequately cooled to allow works to continue without further damage.
8d03325d-ea19-5a76-b75b-b8eb8f2b0a38 | note | ○ For Stone Mastic Asphalt, this must be 40°C
5a45696f-724e-55b8-824f-9bdbe2bb59ce | note | REFERENCE DOCUMENTS: 407.28, 404.14
762b6f5c-c39b-59c1-8d0a-7fc4de5f35ec | note | INSPECTION/TEST METHOD: Visual Inspection & Thermometer
ee6579a5-0158-5830-9eaa-124d14297250 | note | RECORD OF CONFORMITY: Completed ITP & thermometer reading
4c4c0a23-25a7-558a-90c0-3ca809c5019e | note | HP
295c3c13-9808-53d0-bec7-126eab279005 | note | RESPONSIBILITY: Asphalt Foreman
06259743-9928-5874-bf6c-28849d386d0a | date | Date Completed:
4c08df8c-9ccc-4082-b852-aaef98a56727 | signoff | AUTHORITY HOLDPOINT
5d53ee20-3a2d-4f15-bb42-62927612cfc9 | section | 3 - Testing
f2229942-9e19-4e1b-a215-a4c4d268fdd0 | checkpoint | 3.3 - Compaction Testing (Dense Graded Asphalt)
e43578f9-0a80-5889-b155-6fbf7141a88d | note | FREQUENCY: Per Lot
c354355a-4703-5f5e-b3ab-42e2f1fd81ba | note | ACCEPTANCE CRITERIA: Test Lots >500m2, Per lot, the Characteristic Density Ratio must meet the following Minimum Limits:
a305df5e-9585-5e30-81e9-1dd7f33b8ae6 | note | — >50mm layer depth = 96.0%
95f532e2-32da-58c5-8610-abd1cab25df8 | note | — <50mm layer depth = 95.0%
ca36683e-7258-57b5-93db-a0cf6fec4646 | note | ○ Additional Test must be undertaken on the longitudinal joints for wearing courses
19c79b79-84ee-56f7-a47c-2e51e88027c7 | note | ○ Test Lots 50m2-500m2, may be treated as a small area, in which the mean of 3x test sites must exceed the appropriate compaction requirement by 2.0%
d3629042-14bc-5f02-b1a8-1d54db67b7c2 | note | ○ Test Lots <50m2, compaction for all lots shall be accepted on a procedural basis
0d898531-eaca-52a1-af4e-005b20d4fc98 | note | ○ Mix Types where total contract supply <300t, compaction for all lots shall be accepted on a procedural basis
817b310e-1aaf-555f-9d88-b31cb76cf000 | note | REFERENCE DOCUMENTS: Section 407.27(a),(c.) 407, Section 173, Dense Graded Compaction Procedure
88992777-206e-58ca-94c8-e4cda70cff71 | note | INSPECTION/TEST METHOD: Nuclear Density Test, DGA Compaction Procedure
8b3c9fe3-df59-54ce-8c1a-794f89e5a7dc | note | RECORD OF CONFORMITY: Completed ITP, Compaction reports
75ee6485-75b7-5f73-93f8-82fbad5f5d21 | note | TP
b070e86a-ce15-528c-b09a-14e29ebda1f5 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician, Asphalt Foreman / Engineer
68a1f51a-ebdc-5a4b-a5c8-73ddf1eef463 | date | Date Completed:
00602149-8718-4f06-afdd-39921c529412 | checkpoint | 3.4 - Level Conformance
bed1e19c-f501-5dd7-923f-5eee9f178c54 | note | FREQUENCY: Each Lot
5866edb8-17c0-5f62-a306-07e44b05102e | note | ACCEPTANCE CRITERIA: The mean surface level and the variation in surface level for the base, intermediate and wearing courses within each lot shall meet the requirements as specified in 407.30 (b)
afcc579a-f646-5dea-8ef1-4f3f661c5612 | note | ○ Scale A: +/- 5mm Range, +/- 8mm standard deviation
d7c9d096-98e5-5671-874c-530b05ad65e9 | note | REFERENCE DOCUMENTS: 407.30, 407.29
5ce3f110-55b6-5b8a-9732-ff2f55503eb8 | note | INSPECTION/TEST METHOD: Survey Results
c7f64e24-696a-57a4-a1e3-e929105631d1 | note | RECORD OF CONFORMITY: Completed ITP, Survey Conformance Results
028f05cf-dad0-5ea8-9ee3-cdff28f55dc3 | note | WP
e350a470-c7f1-5b1d-81b9-61dea6cf5a2f | note | RESPONSIBILITY: Surveyor / Superintendent
6bb4e7db-1387-50ba-bb40-db131430ef0f | date | Date Completed:
06886c9b-b0c0-4950-9fd2-2e2084e61cf8 | checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f3037c11-ea1a-572a-ac9f-daa2d3ab4509 | textbox | Fulton Hogan - Print Name:
44657c40-fa17-5446-bc12-52bfe78922b0 | textbox | Fulton Hogan - Position:
c801164e-48d4-5ce7-aaea-bb7b2e1337d4 | date | Work Completed On:
bd9f5a9e-b48c-4e1c-9e4d-2fa811816d01 | signoff | Add Signature