## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | DTM-ITP-016- TasNetworks Street Lighting | itp |  |  |  |  | DTM-ITP-016- TasNetworks Street Lighting Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, EMP, TMP, OHSMP, SWMS, WP. Spec 610.18 (a)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP
label | RESPONSIBILITY: FH Engineer / Site Foreman
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Street Light Conduits Installed from POS to Street Light Pit
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Street Light Conduits installed as outlined in "DTM-ITP-005 - Service Relocations - TasNetworks"
label | REFERENCE DOCUMENTS: DTM-ITP-005 - Service Relocations - TasNetworks
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: DTM-ITP-005 - Service Relocations - TasNetworks complete
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.4 - Street Light Pits (PL-629) Installed
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Confirmation of Street Light Pit Installation by TasNetworks Subcontractor as per TasNetworks Standard Drawing "Public Lighting Civil Pit Installation - PL-626 - Rev A" and "AS-32433"
label | REFERENCE DOCUMENTS: Public Lighting Civil Pit Installation - PL-626 - Rev A and AS-32433
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: DTM-ITP-005 - Service Relocations - TasNetworks complete
label | WP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
checkpoint | 1.5 - Street Light Column Foundation Location
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Final Streetlight Pole/Column locations are to be confirmed on-site and to be accurately surveyed prior to commencing works.
label | REFERENCE DOCUMENTS: AS-32433, 12556430-C0465.dwg (Sheet 0460-0462)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed, TasNetworks Project Officer visual inspection (if required)
label | IP
label | RESPONSIBILITY: Fulton Hogan Engineer
date | Date Completed:
section | 2 - Prequalification
checkpoint | 2.1 - Submission of Mix Design
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Hold Point
label | ○ Concrete mix design complies with requirements of Section 610 and appears on the Register of State Growth approved concrete mixes.
label | ○ Submit for review by the Superintendent not less than 4 weeks prior to the placement of concrete.
label | REFERENCE DOCUMENTS: Specification Section 610.07
label | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | RECORD OF CONFORMITY: Superintendent HP Release on Procore
label | HP
label | RESPONSIBILITY: FH Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Reinforcement
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Steel reinforcement complies with the requirements of Section 611.
label | REFERENCE DOCUMENTS: Specification Section 611
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed, Pre-pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 2.3 - Reinforcement supply and certification
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Supplier must hold Australian Certification Authority for Reinforcing Steel (ACRS) certificate.
label | Hold Point
label | ○ No Third Party Certification. Approval shall be obtained in writing from the Superintendent for the use of steel reinforcing materials that are not covered by the long-term quality level of
label | ○ AS/NZS 4671 at least 14 days prior to the intended first date of use of such steel.
label | REFERENCE DOCUMENTS: Specification Section 611.05
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ACRS certificate. HPR release in Procore if required
label | HP
label | RESPONSIBILITY: FH Engineer / QAV
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Street Light Columns
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Street Light Columns are 12m high 3m outreach Ingal Eps or Approved Equal
label | REFERENCE DOCUMENTS: PL-602 (Rev B), 12556430-C0465.dwg (Sheet 0465)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed, TasNetworks Project Officer visual inspection
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 3 - Column Foundation - Testing and Acceptance
checkpoint | 3.1 - Pre-mixed concrete
label | FREQUENCY: as per table 610.161
label | ACCEPTANCE CRITERIA: Concrete sampled at the worksite and complies to requirements of Section 610 including slump and temperature
label | REFERENCE DOCUMENTS: Specification Section 610
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
label | TP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.2 - Concrete Testing - Sampling Frequency
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete cast in one continuous operation to be tested at a frequency as shown below:
label | 0m³ to 10m³ = 1 sample
label | 10m³ to 25m³ = 2 samples
label | 25m³ to 50m³ = 3 samples
label | 50m³ to 100m³ = 4 samples cylinders.
label | For each additional 50m³ and additional sample shall be taken.
label | ○ Each sample shall consist of 1 no. slump or spread test and 3 no. compressive strength cylinders minimum.
label | ○ Compressive strength cylinders = 1 no. 7 day strength, 2 no. 28 day strength.
label | ○ Where applicable, fibre dosage rates are to be tested at a frequency of 1 in every 5 truck loads.
label | ○ Record: Required information on the Concrete Pour Record.
label | REFERENCE DOCUMENTS: 610.16 (b), 610.16 (g), 610.16 (j)
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
label | TP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.3 - Concrete Testing - Core Sample Frequency (Post construction)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: If required by the Superintendent:
label | Hold Point:
label | ○ The coring procedure and core locations shall be submitted for approval by the Superintendent.
label | 75mmØ core samples shall be taken after avoiding reinforcement, from each day's production for each lot at a frequency as shown below:
label | ○ 0m³ to 25m³ = 1 sample
label | ○ 25m³ to 50m³ = 2 samples
label | ○ For each additional 50m³ an additional sample shall be taken.
label | Each sample shall consist of 6 no. core samples, taken perpendicular to the surface, no closer than 200mm from the edge and after 48 hours minimum.
label | Core samples shall be tested for:
label | ○ 1 no. 7 day compressive strength
label | ○ 2 no. 28 day compressive strength
label | REFERENCE DOCUMENTS: 610.16 (b)
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: Test Report, Pre-pour inspections checklist
label | HP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Concrete Testing - Slump
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Slump testing tolerances =
label | <60mm = ±10mm
label | ≥60mm to ≤80mm = ±15mm
label | >80mm to ≤110mm = ±20mm
label | >110mm to ≤150mm = ±30mm
label | >150mm = ±40mm
label | ○ Record: Required information on the Concrete Pour Record.
label | REFERENCE DOCUMENTS: 610.16 (c)
label | INSPECTION/TEST METHOD: Test Point
label | RECORD OF CONFORMITY: This ITP signed
label | TP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.5 - Reinforcement
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Steel reinforcement placement, fixing and lapping complies with requirements of Drawings and Specification
label | REFERENCE DOCUMENTS: 12556430-C0465.dwg (Sheet 0465), PL-607, PL-608, Specification Section 610.26
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Pre-pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 3.6 - Street Light Foundation Conduit and Draw Wire
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: A 50mm conduit and draw wire installed within the foundation to the corresponding Street Light Pit.
label | REFERENCE DOCUMENTS: 12556430-C0465.dwg (Sheet 0465), PL-607, PL-608
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Pre-pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 4 - Column Foundation - Application
checkpoint | 4.1 - Pre-pour
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pre-pour inspection checklist completed and details recorded (Temperature, Evaporation limits and concreting operations).
label | REFERENCE DOCUMENTS: Specification Section 610, Figure 610.171
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Pre-pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer/TasNetworks Project Officer
date | Date Completed:
checkpoint | 4.2 - Concrete Pumping
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Initial discharge of concrete pumped to waste until a consistent workable mix observed
label | REFERENCE DOCUMENTS: Specification Section 610.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Pre-pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.3 - Finishing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Not specified in project specification. A trowel finish will be applied. No decorative/anti-carbonation coating required as footing will not be exposed in anyway following construction
label | REFERENCE DOCUMENTS: Specification Section 610.31
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.4 - Curing
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Curing in accordance with Specification Section 610. Freshly finished concrete protected where erequired from sun, wind or rain until curing implemented
label | REFERENCE DOCUMENTS: Specification Sections 610
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed / Post pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.5 - Joints
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All joints formed in accordance with Specification Section 610, Drawing requirements
label | REFERENCE DOCUMENTS: 610.20, Structural Drawing Set
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 4.6 - Dimensional Tolerances
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Maintain records of dimensional measurements to demonstrate that all completed concrete members comply with Spection Section 610.
label | ○ Ensure that the records are available for review by the Superintendent.
label | REFERENCE DOCUMENTS: 610.47
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, AS BUILT
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 5 - Column Foundation - Finishing Activities
checkpoint | 5.1 - Final inspection
label | FREQUENCY: Each Lot after 28 days
label | ACCEPTANCE CRITERIA: Visual and soundness inspection conducted for analysis of compaction, dry patches, voids or sand pockets.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed, post pour inspection checklist
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 5.2 - Repair of defective areas
label | FREQUENCY: Each occurrence
label | ACCEPTANCE CRITERIA: Areas of finished work that have been deemed non-conforming alerted to the QAV and rectification method approved
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed, NCR report
label | HP*
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 5.3 - As Built Documentation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Survey pick-up to be progressively completed. As built drawings to be be progressively completed. Test data, ITPs, Concrete Dockets, Checklists to be compiled and lot to be closed out.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 6 - Column Foundation - Post Construction
checkpoint | 6.1 - Compressive Strength
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: 3 & 7 day compressive strengths (cylinders and core samples) to comply with table 610.051 for early indication that the strength is tracking correctly.
label | ○ 28 day compressive strength (average of the 2 no. cylinders) per sample comply with the design strength comply with table 610.061.
label | ○ Visual inspection of all cores confirm that the minimum thickness of no less than 85% x thickness, and there are no signs of defects.
label | ○ Note: 1 of the 2 no. 28 day cylinders per sample may be as low as 90% of the required strength, so long as the average meets the required strength.
label | ○ Note: The average of the 2 no. 28 day cores per sample may be as low as 85% of the required strength, as long as the difference between each core, does not exceed 20%.
label | ○ Attach: Compressive Strength Test Results
label | ○ Attach: Core Sample Compressive Strength Test Results
label | REFERENCE DOCUMENTS: Table 610.051, Table 610.061, 610.16 (g)
label | INSPECTION/TEST METHOD: Document Review, Each cylinder and core sample
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 6.2 - Surface Inspection
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Surface to be as per the required class of finish with no visible lack of compaction, dry patches, voids or sand pockets.
label | ○ Soundness inspection shall be conducted with a small hammer to locate ‘drummy’ or ‘hollow’ response areas which indicate a possible lack of bond, delamination or other defect.
label | ○ For core sample penetrations and if any visual defects are observed, follow Structural Concrete Cementitious Patch Repair ITP for investigation and repair.
label | ○ No cracks greater than 0.2mm (exposure classification B1)
label | ○ If cracking is observed, follow Structural Concrete Crack Repair ITP for investigation and repair.
label | REFERENCE DOCUMENTS: 610.31 (a) - (n), 610.32, 610.24
label | INSPECTION/TEST METHOD: Visual, Measure
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 6.3 - As-built Survey
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Provide record of dimensional measurements to demonstrate concrete members comply with tolerances as per the Table 610.472 as applicable to the element.
label | ○ Where a shape is required, ±25mm with no depressions greater than 15mm.
label | ○ Attach: Survey As-builts / Survey Report
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: As built
label | RECORD OF CONFORMITY: This ITP signed, HPR release in Procore
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
section | 7 - Street Light Column Installation & Commissioning
checkpoint | 7.1 - Street Light Column Assembly
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Street Light Columns are to be assembled as per TasNetworks Standard Drawings Public Lighting
label | REFERENCE DOCUMENTS: PL-601, PL-602, PL-603, PL-604
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 7.1 - Street Light Column Installation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Street Light Columns are to be Installed as per TasNetworks Standard Drawings Public Lighting
label | REFERENCE DOCUMENTS: PL-612
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer
date | Date Completed:
checkpoint | 7.1 - Street Final Works and Commisioning
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All other associated to be completed by TasNetworks contractor.
label | ○ On completion of construction and commisioning by TasNetworks contractor, site walk to be completed by TasNetworks Project Officer
label | REFERENCE DOCUMENTS: 12556430-C0465.dwg (Sheet 0465)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: FH Engineer/TasNetworks Project Officer
date | Date Completed:
checkpoint | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | QAV - Print Name:
textbox | QAV - Position:
textbox | Fulton Hogan - Print Name:
textbox | Fulton Hogan - Position:
date | Work Completed On:
signoff | Add Signature