## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | ITP 03 - Application of Waterproofing Template (External Membrane Under Screed) |  | ITP 03 - Application of Waterproofing Template (External Membrane Under Screed) | 1330e8e9-5068-4bf9-8c17-5962859ad3a3
| checkpoint | Obtain clearance to commence work.
| checkpoint | Obtain approved shop drawings
| checkpoint | Prepare substrate.
040cb998-6f3e-5400-b85a-e0f2388b2d44 | note | Surfaces to be waterproofed must be sound, smooth and free from dust, loose matter, oil, grease or other contaminants.
| checkpoint | Inspect prepared substrate.
38fb96ba-c27b-5252-887f-86266dc03667 | note | Visual inspection.
89f75e43-1ec1-508c-a0dc-10cec764d99f | note | Correct Falls 1:100
ccfc0cd8-7cd0-59ff-9235-c49d9eed38f0 | note | Moisture Meter ready under 5%
| signoff | Hold Point
| checkpoint | Apply Primer BS
fa7bb142-71a0-5bba-866b-2354b340d586 | note | Apply one coat of Primer BS at 0.15kg/m2 approximately 5-7m2/L Allow to dry.
| checkpoint | Apply Silcor LM PU. Detail internal corners, joints, turn-ups and penetrations to floor and wall
ad3fe93a-b595-5af7-be33-525562e51d37 | note | Minimum 15mm x 15mm fillet PU to all internal corners/turn-ups, joints and around penetrations.
| checkpoint | Apply Silcor 560HB
4cbce863-6d34-5f58-a733-ecf72b0a3f76 | note | Silcor 560HB polyurethane to be applied by brush or roller in two coats at a combined thickness of 1.5mm (DFT).
62c668e4-da2d-51dd-9a5a-5ed9aecf56c8 | note | 0.875mm (WFT) per coat
f77041e8-0e44-5341-a5e2-d1e34ee31cf6 | note | Sand seeding to final coat
| checkpoint | Holiday Testing – ELD (Electronic Leak Detection)
8c245e5d-ba5c-5d80-baf8-c39a8dd5e015 | note | Pinhole testing
| signoff | Hold Point
| checkpoint | Final QA review prior to sign off. Record and document.
| signoff | Hold Point
| checklist | ITP 04 - Application of Waterproofing Template (Balconies UV Stable) |  | ITP 04 - Application of Waterproofing Template (Balconies UV Stable) | 02a27bcd-1b97-42ff-829f-139eba95200d
| checkpoint | Obtain clearance to commence work.
| checkpoint | Obtain approved shop drawings
| checkpoint | Prepare substrate.
b6a18fc6-bce1-570b-bf13-98023f95a600 | note | Surfaces to be waterproofed must be sound, smooth and free from dust, loose matter, oil, grease or other contaminants.
| checkpoint | Inspect prepared substrate.
3f519ae7-8539-5dac-bfbd-0ca4a6048a71 | note | Visual inspection.
4b993251-c5ac-5811-858c-baad5d620588 | note | Correct Falls 1:100
a01ce624-9a89-52eb-a6c9-7d3300395036 | note | Moisture Meter ready under 5%
| signoff | Hold Point
| checkpoint | Apply Primer BS
be35a78c-4b8f-5124-964f-ce38f8cf2f98 | note | Apply one coat of Primer BS at 0.15kg/m2 approximately 5-7m2/L Allow to dry.
| checkpoint | Apply Silcor LM PU. Detail internal corners, joints, turn-ups and penetrations to floor and wall
e1589605-f0fc-5a6d-bff4-93315fbac8ae | note | Minimum 15mm x 15mm fillet PU to all internal corners/turn-ups, joints and around penetrations.
| checkpoint | Apply Silcor 560HB
81265cf0-c2bc-5db1-9cbc-4df4fe6aa524 | note | Silcor 560HB polyurethane to be applied by brush or roller in two coats at a combined thickness of 1.5mm (DFT).
a55b8909-1a93-539b-8908-284038680429 | note | 0.875mm (WFT) per coat
| checkpoint | Apply Silcor TC 75
f9ea0936-f0f4-5184-b703-105207906049 | note | Silcor TC 75 aliphatic polyurethane to be applied by brush or roller in two coats at a combined thickness of 0.15mm (DFT).
| checkpoint | DFT Testing
7dc940e4-4121-5b4b-8771-b4070a0cf49b | note | Silcor 575LB polyurethane to be applied by brush or roller in one or two coats at a combined thickness of 1.5mm (DFT).
5b44e6d1-b372-591c-82f0-0e11abcaeec0 | note | 1.75mm (WFT) Total
| checkpoint | Holiday Testing – ELD (Electronic Leak Detection)
21707622-bf89-5a14-8697-89e440734486 | note | Pinhole testing
| signoff | Hold Point
| checkpoint | Final QA review prior to sign off. Record and document.
| signoff | Hold Point
| checklist | ITP 05 - Application of Waterproofing Template (Fire Tanks) |  | ITP 05 - Application of Waterproofing Template (Fire Tanks) | 2d7baaa1-7be6-4919-a4a4-ade3949539b6
| checkpoint | Obtain clearance to commence work.
| checkpoint | Obtain approved shop drawings
| checkpoint | Prepare substrate.
23689ad0-bb9c-563b-a5ce-06f73c1abb6b | note | Surfaces must be sound, smooth and free from dust, loose matter, oil, grease or other contaminants by means of scraping, brushing, vacuuming and grinding if required
62a4fa60-9c0e-57b7-92a7-fbe81dd9de68 | note | Substrate to be damp when applying membrane
| checkpoint | Inspect prepared substrate.
| signoff | Hold Point
| checkpoint | Install reinforcement bandage
132ba1b4-e366-58d9-b435-51cc1a770396 | note | Install reinforcement bandage to perimeter junctions
| checkpoint | Apply Drizoro Maxseal Flex
30fee668-2993-5be1-9217-3e3cf12553a3 | note | Drizoro Maxseal Flex cementitious to be applied by brush or roller in two coats at a combined thickness of 2mm (DFT).
5509caeb-564c-57cb-8192-d2822811bf36 | note | 1mm (WFT) per coat
fcd78ef5-6d0e-5f07-92c9-70893e73c571 | note | Curing times between coats: 16-72hours
| signoff | Hold Point
| checkpoint | WFT/DFT Testing
1213d344-afa7-5108-b89b-6693a5c0d621 | note | Drizoro Maxseal Flex cementitious to be applied by brush or roller in two coats at a combined thickness of 2mm (DFT).
| checkpoint | Final QA review prior to sign off. Record and document.
| signoff | Hold Point
| checklist | ITP 07 - Application of Waterproofing Template (Window Thresholds) |  | ITP 07 - Application of Waterproofing Template (Window Thresholds) | bdf1f71e-1ade-46ae-8727-3d442eb522ec
| section | Details
| checkpoint | Obtain clearance to commence work.
| checkpoint | Obtain approved shop drawings
| checkpoint | Inspect and prepare substrate
0149a693-3806-5467-a1cc-4b09e34f0e8d | note | Surfaces to be waterproofed must be sound, smooth and free from dust, loose matter, oil, grease or other contaminants.
| checkpoint | Apply Epocote F100W epoxy primer
66d9fd2b-02e2-50bf-af85-4d84ee99396a | note | Apply one coat of Epocote F100W at a rate of 4m2/L
| checkpoint | Apply Silcor LM PU. Detail internal corners, joints, turn-ups and penetrations to floor and wall
720547ff-a60c-5e97-b1f2-68d72aa63ca6 | note | Minimum 15mm x 15mm fillet PU to all internal corners/turn-ups, joints and around penetrations.
| checkpoint | Apply Silcor 140FB
b1ac943b-2831-514c-b1b9-32f6615553c7 | note | Silcor 140FB acrylic to be applied by brush or roller in two coats at a combined thickness of 1.0mm (DFT).
| checkpoint | Final QA review prior to sign off. Record and document.
| signoff | Hold Point
| checklist | ITP 08 - Application of Waterproofing Template (Podium) |  | ITP 08 - Application of Waterproofing Template (Podium) | 8a96997e-cbb7-4631-be58-c2fec78c324c
| section | Details
| checkpoint | Obtain clearance to commence work.
| checkpoint | Obtain approved shop drawings
| checkpoint | Prepare substrate.
a67d2d08-e430-5ac1-b560-de558bb24cd8 | note | Surfaces to be waterproofed must be sound, smooth and free from dust, loose matter, oil, grease or other contaminants.
| checkpoint | Inspect prepared substrate.
5432166a-a1bf-51ee-9006-be75d27d58b5 | note | Visual inspection.
5135d30f-2be0-5999-bded-8f41894977cc | note | Correct Falls 1:100
85153d04-da5d-5152-980c-8d2eb9560f29 | note | Moisture Meter ready under 5%
39e8162d-d94e-5afb-887a-421e7205ed59 | textbox | Moisture Meter Results:
| signoff | Hold Point
| checkpoint | Apply Primer BS
82c4514c-b37e-5b74-b09e-c7dff4938ba1 | note | Apply one coat of Primer BS at 0.15kg/m2 approximately 5-7m2/L Allow to dry.
| checkpoint | Apply Silcor LM PU. Detail internal corners, joints, turn-ups and penetrations to floor and wall
ed7ba8d2-f66d-57f2-8d9d-507522c3bdf9 | note | Minimum 15mm x 15mm fillet PU to all internal corners/turn-ups, joints and around penetrations.
| checkpoint | Apply Silcor 575LB
a8d49ae7-1e7b-5029-addd-d1bac1da8ce5 | note | Silcor 575LB polyurethane to be applied by brush or roller in one or two coats at a combined thickness of 1.5mm (DFT).
29ab7230-6321-541a-8975-79a8d2563528 | note | 1.75mm (WFT) Total
| checkpoint | DFT Testing
16573e12-5b40-5113-88e5-3a1c57dce62e | note | Silcor 575LB polyurethane to be applied by brush or roller in one or two coats at a combined thickness of 1.5mm (DFT).
9133ff81-cfaa-554e-951b-2ef85dd75212 | note | 1.75mm (WFT) Total
73e9bf67-7722-5f74-a25d-f3541a386eab | textbox | DFT testing results:
| signoff | Hold Point
| checkpoint | Holiday Testing – ELD (Electronic Leak Detection)
90b1d840-1dd7-5115-a9dd-479688486c4d | note | Pinhole testing
967a35d6-5150-5193-bf10-6e5129b507b0 | textbox | ELD testing results:
| signoff | Hold Point
| checkpoint | Final QA review prior to sign off. Record and document.
| signoff | Hold Point
| checklist | TP 01 - Application of Waterproofing Template (Planter Boxes) |  | TP 01 - Application of Waterproofing Template (Planter Boxes) | 74ebcfcd-a3e8-42b1-9614-7e1a9f548df4
| checkpoint | Obtain clearance to commence work.
| checkpoint | Obtain approved shop drawings
7c74642b-efb6-5cff-9275-0a4bb4fdae8c | note | Surfaces to be waterproofed must be sound, smooth and free from dust, loose matter, oil, grease or other contaminants.
| checkpoint | Prepare substrate.
| checkpoint | Inspect prepared substrate.
f2521327-e16f-5c35-afa3-8c068d3e6a75 | note | Visual inspection.
4b6acbc5-bf85-51ff-bda3-3a4a7f4d780c | note | Correct Falls 1:100
dfc4896f-2d01-509c-806d-159b9f04a99b | note | Moisture Meter ready under 5%
| signoff | Hold Point
| checkpoint | Apply Primer BS
8a15e6ee-9d11-52eb-a1d4-68ae6e6c58ef | note | Apply one coat of Primer BS at 0.15kg/m2 approximately 5-7m2/L Allow to dry.
| checkpoint | Apply Silcor LM PU. Detail internal corners, joints, turn-ups and penetrations to floor and wall
daa50c1e-5b16-55db-ba39-a28a05604de4 | note | Minimum 15mm x 15mm fillet PU to all internal corners/turn-ups, joints and around penetrations.
| checkpoint | Apply Silcor 560HB
a4fad41a-bdcb-506d-801c-c734b59b074c | note | Silcor 560HB polyurethane to be applied by brush or roller in two coats at a combined thickness of 1.5mm (DFT).
bc4db935-6a46-5420-a6d1-27166ff08016 | note | 0.875mm (WFT) per coat
| checkpoint | DFT Testing
f8224f06-60ef-5ffd-af04-020671f173e1 | note | Silcor 560HB polyurethane to be applied by brush or roller in two coats at a combined thickness of 1.5mm (DFT).
597b25df-5c90-5f9b-b72c-d4a84fdcb077 | note | 0.875mm (WFT) per coat
| checkpoint | Water Testing
c9d5840b-0ebc-50fa-b333-49b579d52dbd | note | Water Testing 24h hours
| signoff | Hold Point
| checkpoint | Holiday Testing – ELD (Electronic Leak Detection)
f6476e7b-3d38-58a4-96f7-418504389fd1 | note | Pinhole testing
| checkpoint | Final QA review prior to sign off. Record and document.
| signoff | Hold Point
| checklist | TP 02 - Application of Waterproofing Template (Roof and External UV Areas) |  | TP 02 - Application of Waterproofing Template (Roof and External UV Areas) | 28d48a9f-fead-462a-a194-ea8ec9132684
| checkpoint | Obtain clearance to commence work.
| checkpoint | Obtain approved shop drawings
| checkpoint | Prepare substrate.
23af253e-55ba-5904-b549-a9a3dcf8e243 | note | Surfaces to be waterproofed must be sound, smooth and free from dust, loose matter, oil, grease or other contaminants.
| checkpoint | Inspect prepared substrate.
6249e12c-7bce-5109-888e-b97fa74fbbec | note | Visual inspection.
8320de2b-36b0-5df6-9ff5-ba3cec32a9d7 | note | Correct Falls 1:100
4d271a18-3a21-564a-af8e-983f945e8028 | note | Moisture Meter ready under 5%
| signoff | Hold Point
| checkpoint | Apply Primer BS
b2fa41c8-50bb-5c7d-8d30-f125511f5fdf | note | Apply one coat of Primer BS at 0.15kg/m2 approximately 5-7m2/L Allow to dry.
| checkpoint | Apply Silcor LM PU. Detail internal corners, joints, turn-ups and penetrations to floor and wall
c9b82e40-c556-5b1d-9f8d-2d5ee38d6951 | note | Minimum 15mm x 15mm fillet PU to all internal corners/turn-ups, joints and around penetrations.
| checkpoint | Apply Silcor 575LB
c7d58882-27f3-561c-bdae-b62429217441 | note | Silcor 575LB polyurethane to be applied by brush or roller in one or two coats at a combined thickness of 1.5mm (DFT).1.75mm (WFT) Total
| checkpoint | Apply Silcor TC 75
62d8f846-e666-5ad8-b4b0-c3172757ca4d | note | Silcor TC 75 aliphatic polyurethane to be applied by brush or roller in two coats at a combined thickness of 0.15mm (DFT).
| checkpoint | DFT Testing
e4b0e7a8-7100-59c7-a896-b55b1a772b9d | note | Silcor 575LB polyurethane to be applied by brush or roller in one or two coats at a combined thickness of 1.5mm (DFT). 1.75mm (WFT) Total
| signoff | Hold Point
| checkpoint | Holiday Testing – ELD (Electronic Leak Detection
e6547295-f9d2-5e34-b63e-0b1617d37e3c | note | Pinhole testing
| signoff | Hold Point
| checkpoint | Final QA review prior to sign off. Record and document.
| signoff | Hold Point