## Schedule
Site | 106 Beach Road, Waihi Beach (Library)
Customer | Tasman Aluminium
Item | Description | Size
1 | Auto Door Unit | 2750 x 2750
2 | Hinged Door | 2665 x 1015
3 | Hinged Door | 2610 x 1000
4 | W-01 FG Seismic | 2750 x 7850
5 | W-02 FG Seismic | 2750 x 4050
6 | W-03 FG Seismic | 2750 x 7300
7 | W-04 Curved Window | 1700 x 800
8 | W-05 Curved Window | 1700 x 800
9 | W-06 Curved Window | 1700 x 800
10 | W-07 FG Seismic | 2630 x 2200
11 | W-08 FG Seismic | 2750 x 4500
12 | W-09 FG Seismic | 2750 x 3350
13 | W-07 FG Seismic | 2550 x 1000

## Checklist
Substrate prepared for Install (Waterproofing etc.)
Hole centres as specified, Countersunk (450 mm max, 150 mm from corners/Mullions)
WANZ bars fixed/Level (Maximum hole centres 300 mm)
Window Level, Plumb and fixed in the correct position on the horizontal plane
Window packed and fixed off
Window aligned Vertically (Where required)
PEF Rod fitted
internal air seal complete
Head Flashing Installed as specified (When Required)
All Frames Glazed, Sash Installed, Sliding Door fitted
Threshold Installed (Hinge doors)
Free from marks, dents, scratches,