## ITP-019
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # FHC-ITP-016
[11 empty] | Revision : 1 | Date : 26/04/2022
Client: |  | MRPA |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  |  |  | Road Sign Installation |  | Name: Martin Syawish |  | Name: Patrick Fagan |  |  | Name: Shaun Kent
Job No: |  |  |  | Specifications: VicRoads Section 714 - Sign Installation. Austalian Standard 1742
|  |  |  | Structure / Component: Signage |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: |  | Date : 26/04/2022 |  | Date : 26/04/2022 |  |  | Date : 26/04/2022
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for correct documentation |  | Prior to commencing any activity | Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision | Drawings and drawing registers | Visual inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to commencing any activity | All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS | Visual Inspection | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Signage Conformance |  | Before commencement of activity | Ensure sign size and immage correspond with contract drawings and meets specification | Drawings AS 1742 | Verify | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Service Identification |  | Prior to start | Check for any services in proximity to points of installation or coring for spigots | DBYD, Service chart | Verify | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
2 | Construction Works
2.1 | Setting Out |  | Prior to start | Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections. | Drawings | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Post & Foundations |  | Prior to Start | The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences. | 714.06 | Visual inspection | This ITP signed off | HP | Superintendent |  |  | N/A
2.3 | Signage Install |  | Each Sign | Sign to be installed as per most current drawings, local council documentation, and to the correct height and position. Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition | AS 1742 TS 1313 Drawings | Verify | This ITP signed off | WP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FHDB |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.