## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-016 - Road Sign Installation | itp |  |  |  |  | ITP-016 - Road Sign Installation Rev1
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | REFERENCE DOCUMENTS: OHSCP, PHSCP, PCMP, EMP, ECP, CEMP, ERA, QMP, CHMP, SWMS
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 1.3 Signage Conformance
note | FREQUENCY: Before commencement of activity
note | ACCEPTANCE CRITERIA: Ensure sign size and immage correspond with contract drawings and meets specification
note | REFERENCE DOCUMENTS: Drawings AS 1742
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed off
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 1.4 Service Identification
note | FREQUENCY: Prior to start
note | ACCEPTANCE CRITERIA: Check for any services in proximity to points of installation or coring for spigots
note | REFERENCE DOCUMENTS: DBYD, Service chart
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed off
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
section | Construction Works
checkpoint | 2.1 Setting Out
note | FREQUENCY: Prior to start
note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections.
note | REFERENCE DOCUMENTS: Drawings
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 2.2 Post & Foundations
note | FREQUENCY: Prior to Start
note | ACCEPTANCE CRITERIA: The required positions of all posts and signs shall be as directed by the Superintendent who shall confirm the positions before the erection of posts commences.
note | REFERENCE DOCUMENTS: 714.06
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | HP
note | RESPONSIBILITY: Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Signage Install
note | FREQUENCY: Each Sign
note | ACCEPTANCE CRITERIA: Sign to be installed as per most current drawings, local council documentation, and to the correct height and position.
note | • Spigot embedment shall be within +/- 5mm of design horizontal position and +10mm of vertical design position
note | • Signs specified to be re used are to comply with AS 1742 standards, and must be replaced if deemed in unsatisfactory condition
note | REFERENCE DOCUMENTS: AS 1742 TS 1313 Drawings
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed off
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: