## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | ITP-019 - Line / Road Marking | itp |  |  |  |  | ITP-019 - Line / Road Marking Rev1
section | Preliminary Works
checkpoint | 1.1 Check for correct documentation
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
note | – using the correct and complete set of drawings
note | – all drawings are the latest revision
note | REFERENCE DOCUMENTS: Drawings and drawing registers
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 1.2 Implementation of all measures and controls
note | FREQUENCY: Prior to commencing any activity
note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | WP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
section | Construction Works
checkpoint | 2.1 Setting Out
note | FREQUENCY: Prior to start
note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings and in accordance with alignments, levels, grades, and sections
note | REFERENCE DOCUMENTS: Drawings
note | INSPECTION/TEST METHOD: Visual Inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | IP
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 2.2 Position of Markings
note | FREQUENCY: Prior to application
note | ACCEPTANCE CRITERIA: Painting/ application of material shall not commence unitll the Superintenent has inpsected the setout and given approval to proceed, unless an exemeption is granted.
note | • Works shall be set out as required in clause 721.A03, that is: the dimensions and colour of pavement markings shall conform to the VicRoads Traffic Engineering Manual Volume 2
note | REFERENCE DOCUMENTS: VicRoads Traffic Engineering Manual Volume 2 Drawings
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | HP
note | RESPONSIBILITY: Fulton Hogan Engineer & Superintendent
textbox | DATE:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 Materials
note | FREQUENCY: Prior to commencement
note | ACCEPTANCE CRITERIA: All paints shall be approved under the Australian Paint Approval Scheme (APAS). Paint shall comply with the requirements of AS 4049.1 for solvent‑borne paint or AS/NZS 4049.3 for water‑borne paint as listed in Section 175.
note | REFERENCE DOCUMENTS: 712.A04(c)
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 2.4 General Markings
note | FREQUENCY: Prior to commencement
note | ACCEPTANCE CRITERIA: Linemarking shall be applied by a self propelled machine, and stencils shall be used with all roadmarking.
note | • All work must be undertaken by a contractor eligible for accreditation under the Painting Contractors Certification Programme (PCCP). This programme is administered by the CSIRO.
note | REFERENCE DOCUMENTS: 712.D01(c)
note | INSPECTION/TEST METHOD: Visual inspection
note | RECORD OF CONFORMITY: This ITP signed off
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
section | Completion
checkpoint | 3.1 Tolerances
note | FREQUENCY: Each marking
note | ACCEPTANCE CRITERIA: The Contractor shall comply with the tolerances as shown in Table 721.A101 when installing pavement markings.
note | (i) Distance between centreline of marking and set out marks <30mm
note | (ii) Width of completed paint markings <15mm
note | (iii) Length of completed stripes and blocks 0 to +10% of specified length
note | REFERENCE DOCUMENTS: Table 712.A101
note | INSPECTION/TEST METHOD: Verify
note | RECORD OF CONFORMITY: This ITP signed off
note | HP*
note | RESPONSIBILITY: Fulton Hogan Engineer
textbox | DATE:
checkpoint | 3.2 As-Built
note | FREQUENCY: Post Completion
note | ACCEPTANCE CRITERIA: As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
note | REFERENCE DOCUMENTS: IFC Drawings Survey Records
note | INSPECTION/TEST METHOD: Document Review
note | RECORD OF CONFORMITY: This ITP signed off
note | SCP
note | RESPONSIBILITY: Project Engineer/Surveyor
textbox | DATE:
checkpoint | Final Inspection
label | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
text | Print Name:
text | Position:
text | Date: