## Table 1
Underground Drainage |  |  |  | Hayden Brett Created Tue, 16 Jan 2024, 3:50 PM (UTC+11)
Subcontractor (if applicable)
ITP Details:
| Client |  | Construction Process |  | Contract Number: |  | Speciﬁcations |  | Structure / Component |  | Prepared By |  | Approved By
| Regional Roads Victoria |  | Underground Storm |  |  |  | Vicroads Speciﬁcation |  | Drainage
|  |  | water Drains |  |  |  | Section 173, 175, 205,
210, 290, 304, 702 and
720, VR Code of Practice
500.2
Project Location
Lot no.
Lot details
Lot size/qtys
Date Start: - End: -
Text Legend:
1. Preliminary Works
Task/Activity Description |  | Acceptance Criteria |  | Reference Documents |  | Method & Record of conformity |  | Responsibility |  | Signature |  | Comments
1.1 Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to. Frequency: Prior to commencing works |  | Refer to the VicRoads Traﬃc Management speciﬁcation 166 |  | Traﬃc Mgmt. Plan |  | Visual Inspection Signed ITP |  | IHP SWA Project Manager
1.2 Purchase of pre-cast pits, pipes and end-walls Frequency: Approval prior to placement of order |  | Refer to Construction Drawings |  | Vic roads Standard drawings |  | Review and approval of documentation Visual inspection Signed ITP |  | IHP SWA Project Manager
2. Construction works
2.1 CONFORMITY WITH DRAWINGS The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed. Frequency: Each lot as required |  | Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent. |  | Vicroads std sec 701.09 |  | Construction Drawings Signed ITP |  | IHP SWA Project Manager Site Supervisor
2.2 CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level Frequency: Each Lot |  | Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be: (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250 |  | Vicroads std sec 701.09 |  | Construction Drawings Signed ITP |  | IHP SWA Project Manager Site Supervisor
2.3 EXCAVATION Frequency: Each Lot |  | For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm |  | VicRoads Std Specs 701.14 |  | On-site Measurement Signed ITP & Drainage Checklist |  | WP Project Engineer Site Supervisor
2.4 CULVERT BEDDING – Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert Frequency: Each Lot |  | The compacted thickness of bedding material following any shaping necessary shall be not less than: • 100 mm where D < 1500 mm • 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width. |  | VicRoads Std Specs 701.15 |  | Site Inspection Signed ITP |  | WP Project Engineer Site Supervisor
2.5 PLACEMENT OF FILLING Frequency: Each lot as required |  | (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15. (I) Culvert Under Area not to be Paved. The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level. |  | VicRoads Std Specs 701.18 |  | Site Inspection Signed ITP |  | WP Project Engineer Site Supervisor
2.6 INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS Frequency: Each lot as required |  | Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV). Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia. |  | VicRoads Std Specs 701.28 |  | Visual inspection Signed ITP |  | HP Project Engineer AP Clients Superintendent
2.7 Where required installation of Geofabric or Jute matting and beaching material in swale drains Frequency: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse |  | Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows. Rock shall be placed with a geo-textile liner. |  | NIL |  | Visual inspection Signed ITP |  | IHP Project Engineer/Site Supervisor
3. Testing Requirement
3.1 REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness. Frequency: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls) |  | (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. (b) Backﬁll (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer. |  | Vicroads std sec 701.19 |  | Lab Test Signed ITP |  | IHP SWA Project Manager
Photo and video
Final Inspection Comments
Project Team signature -
Photo and video
Final Inspection Comments
Client Signature -