## MFU-FH-ITP-0010
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-007
Client: | DTP |  | Construction Process: | Guardrail Installation |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: | [5 empty] | Name: | Ruby Lewis | Name: | Nikhil Patil |  | Name: | Nikhil Patil
Contract No: |  |  | Specifications: | VicRoads Specifications Section 708, 703 & Manufacturer specs
|  |  | Structure / Component: | Guardrail & Maintenance Strip
|  |  | Location: |  |  | Date : | 2024-02-15 | Date : | 2024-02-15 |  | Date : | 2024-02-15
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Superintendent | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Induction |  | Prior to Commencing | All personnel on site have been inducted to the Project site | Inductions Register | Document review | Site induction signed. | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.2 | Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken |  | Prior to commencing | All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS | Health and Safety Co-Ordination Plan | Document Review | SWMS(s) signed | IP | Site Engineer / Site Foreman | N/A
1.3 | Check that current revision drawings are being used |  | Prior to Commencing | Issued For Construction (IFC) and latest available revision used | Project Drawings / Drawing Register | Document review | Latest Revision Drawings | AP | Site Engineer / Site Foreman | N/A |  | N/A
1.4 | Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place |  | Prior to Commencing | All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified | IFC Drawings CEMP CHMP | Document review & Site inspection | Signed ITP | IP | Site Engineer | N/A
1.5 | Excavation Permit issued |  | Prior to Commencing | Current Excavation Permit signed and specific for the area where works will be executed. | Excavation Permit | Document review | Excavation Permit # | IP | Site Engineer | N/A |  | N/A
1.6 | Approval of Guardrail System |  | Prior to Commencing | Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used. | RDN 06-04 | Document review | Signed ITP/Email | HP | Superintendent / Site Engineer |  |  | N/A
2 | Mateiral Approvals
2.1 | Approved steel supply |  | Prior to Commencing | The Contractor shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation. | VicRoads Spec. Cl.708.05(b) | Document review | Supplier's NATA (or otherwise approved) Material Test Certificates | HP | Superintendent / Site Engineer |  |  | N/A
2.2 | Approved Galvanisation records |  | Prior to Commencing | Surface preparation in accordance with AS1627 parts 1 & 4. Zinc coating mass of galvanised components to be in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform | VicRoads Spec. Cl.708.05(d) | Document review | Supplier's NATA (or otherwise approved) Manufacturer's certificate of compliance Test Certificates | HP | Superintendent / Site Engineer |  |  | N/A
3 | Installation of Guardrail & Maintenance strip
3.1 | Survey set-out |  | Prior to Commencing | Survey activities undertaken to ensure and validate that all works meet level and location requirements.. IFC and latest available revision used | Latest IFC Drawings | Site inspection | Signed ITP | SCP | Superintendent / Site Engineer |  |  | N/A
3.2 | Service Location |  | Prior to Commencing | Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile. | Services file & Current DBYD notifications | Site inspection | Services marked on the ground | IP | Site Engineer | N/A |  | N/A
3.3 | Approval of location and length |  | Prior to Installation | Prior to installation the Contractor shall confirm with the superintendent the required location and length of all guard fence. | VicRoads Spec. Cl.708.08 | Site inspection | Signed ITP | HP | Superintendent / Site Engineer |  |  | N/A
3.4 | Install posts, rails and terminations |  | During construction. | Tolerances W-beam guard fence shall be erected to the following tolerances: (i) Variation from true plan position of posts ±20 mm (ii) Variation of line of w-beams from specified vertical profile ±10 mm (iii) Variation of w-beams from specified horizontal alignment ±20 mm (iv) Variation of posts from vertical (measured at top of the post) ±15 mm (v) Orientation of block and/or post to w-beam +0 mm, -15 mm (measured at the point of greatest offset between the block or post to the w-beam) (vi) Dimension of holes -0 mm, +50 mm (vii) Top of bolt head relative to w-beam -0 mm, +5 mm After installation the top of the rail shall be within 25 mm of the specified level and 50 mm of the specified line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length | VicRoads Spec. Cl.708.08(d) | Document Review | Signed ITP | IP | Site Engineer | N/A |  | N/A
3.5 | Construct crushed rock base for maintenance strip |  | During construction. | Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock | VicRoads Spec. Cl.708.12(a) | Site inspection | Signed ITP | WP | Superintendent / Site Engineer |  |  | N/A
3.6 | Construct concrete maintenance strip |  | During construction. | Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam. Separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative), full depth expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set | VicRoads Spec. Cl.708.12(a) | Site inspection | Concrete dockets/Signed ITP | WP | Superintendent / Site Engineer |  |  | N/A
4 | Testing
4.1 | Compliance Audit of Barrier System Installation |  | Prior the issue of the Certificate of Practical Completion | Prior to the issue of the Certificate of Practical Completion, the Contractor shall arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract and the Contractor shall complete and submit to the superintendent a signed copy of the Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual. | VicRoads Spec. Cl.702.10 | Document Review | Safety barrier compliance audit Manufacturer compliance certificate | HP | Superintendent / Site Engineer |  |  | N/A
5 | Completion
5.1 | Delineators |  | Once installation of assets is completed | The Contractor shall arrange delineators so that vehicles approaching from either direction at night will only see: • red delineators on the left side of one-way and two-way roadways; • white delineators on the right side of two-way roadways; and • yellow delineators on the right side of one-way roadways. | VicRoads Spec. Cl.702.11 | Site inspection | Site Photos/Signed ITP | IP | Superintendent / Site Engineer |  |  | N/A
5.2 | Survey data captured for As-Builts |  | Completion of Works | As-Built drawings to be submitted to client | VicRoads Spec. 708 | Document Review | As-Builts Survey reports | IP | Superintendent / Site Engineer |  |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
AP | Approval Point | Written or verbal approval given by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
WP | Witness Point | An inspection which must be witnessed by the Superintendent