## Table 1
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-010 Revision : 1 15/08/24
Client: SGSC Project: Sanders Road Contract No: |  |  |  | Construction Process: Bored Piling Specifications: VicRoads Standard Specification Section 705 Structure / Component: Retaining Wall Location: |  | Prepared by: Name: Ruby Lewis Signed : Date : 15/08/24 |  | Revie wed by Cameron Name: Beattie Signed : Date : 15/08/24 |  |  | Approved by : Cameron Name: Beattie Signed : Date : 15/08/24
Lot No: Lot Details: Lot Size/ Quantity:
Item No. | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility Project Engineer Site Engineer Superintendent Surveyor Foreman | Checked by:
|  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  |  | Client | Fulton Hogan | FH's Sub- contractor | Date
1 | Design and Submissions
1.1 | Check for correct documetation |  | Before commencement of activity | Check correct documentation is being utilized (latest drawing revision) and IFC/ Proof Engineering | Drawings | Current revision of drawing | Current revision of drawing | HP* | Project Engineer Site Engineer | N/A
1.2 | Approval of Mix Design |  | No less than 4 weeks prior to commencement of activity | Mix design reviewed and approved by superintendent. | Cl 610.07(b | Approval | VicRoads letter of approval | AP | Superintendent
1.3 | Approval of Quality Procedure |  | No less than 4 weeks prior to commencement of activity | Proposed materials and pile construction procedures reviewed by the superintendent | Cl 606.03(a) | Approval | VicRoads letter of approval | HP | Superintendent
1.4 | Ensure Traffic, Safety, Quality and Environmental management measures are in place |  | Prior to commencement of activity. EMP at least 2 weeks prior | Safety plan, traffic management plan and environmental management plan | PSP, TMP & EMP | Ensure all measures in place as per plan | Inspection | HP | Site Engineer Superintendent
1.5 | Certification of approved Hot Dip Galvanising |  | Prior to Epoxy coating | Galvanising treatment in accordance with appropriate Standard documents and Design specification 200 microns | Drawings AS/NZ4680 | Verify | Manufacturers certificate | HP* | Project Manager Site Engineer | N/A
1.6 | Certification of approved Epoxy coating |  | Prior to arrival on site | Epoxy treatment in accordance with appropriate Standard documents and Design specification 2 x Base Coat GFX @ 250 microns 1 x Top Coat Polyurethane, 100 microns | Drawings AS2312 | Verify | Manufacturers certificate | HP* | Project Manager Site Engineer | N/A
2 | Bored Piling
2.1 | Survey and setout |  | Each Pile | Survey and confirm position and depth as per drawing | Drawings | Survey | This ITP Signed off | IP | Site Engineer Geotechnical Engineer | N/A
2.2 | Excavation Levels |  | Each Pile | Check the excavation levels and base are acceptable and conform to the drawing prior to commencement of piling works. | Drawings | Verify | Drilling check sheet | HP | Site Engineer Geotechnical Engineer | N/A
2.3 | Inspection of Pile Excavation |  | Each Pile | First 3 piles to be inspected by Geotechnical Engineer to check dimensions and toe level are correct and within tolerance. Correct Toe level. Material encountered consistent with design. | Drawings Cl 606.06 | Inspection / Test Method | This ITP Signed off | HP | Site Engineer Geotechnical Engineer | N/A
2.4 | Bore Logs |  | Each Pile | All bore logs and pile installation records to be sent to and reviewed by designer | Bore logs | Verify | Drilling check sheet | HP | Site Engineer Geotechnical Engineer | N/A
2.5 | Spacers installed on Reinforcement Cage |  | Each Pile | Spacers/supports to be placed along steel reinforcement at a maximum 2m intervals | Cl 611.10 | Inspection | This ITP Signed off | HP* | Site Engineer Superintendent
2.6 | Inspection of column and cage height and centre |  | Each Pile | Ensure heights, centre and spacing of reinforcement cage and column are in accordance with drawings and within tolerance | Drawings Cl 606.08 | Inspection | This ITP Signed off | IP | Site Engineer Superintendent
3 | Placing and Finishing Concrete
3.1 | Quality Checks |  | Prior to each concrete pour | Relevant ITPs and Quality Control checklists completed and reviewed | Cl 610.18 | Inspection | This ITP Signed off | HP | Site Engineer Superintendent
3.2 | Carry out sampling of concrete |  | Each concrete pour | Sampling in accordance with 610.16 Slump: As per VR450/50 mix 675mm (+/- 125mm) (550mm - 800mm) | Cl 610.16 Table 610.161 | Verify | Checklist | IP | Site Engineer | N/A
3.3 | Record location of each batch |  | Each concrete pour | Batch location recorded | Cl 610.15 | Verify | Checklist | IP | Tester | N/A
3.4 | 7 Day concrete test result |  | Each sample | Concrete cyclinder test smples: 7 day concrete strength achieved of 35MPa | Cl 610.05 | Test Report | This ITP Signed off | TP | Site Engineer | N/A
3.5 | 28 Day concrete test result |  | Each sample | Concrete cyclinder test smples: 7 day concrete strength achieved of 50MPa | Cl 610.05 | Test Report | This ITP Signed off | TP | Site Engineer | N/A
3.6 | Tolerance Check and As Built Survey |  | Each Pile | Check tolerances and survey pile positions. Mark all details correctly on as-builts. Pile head position and verticality | Cl 605 | Survey | Survey report | WP | Site Engineer | N/A
Final Inspection The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications. Date: Print Name: Position: Signature: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent