## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP-001 - Clearing & Grubbing | itp |  |  |  |  | ITP-001 - Clearing & Grubbing Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check current drawings are used on site for works
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Permit to distrurb flora & fauna
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: VicRoads has already obtained permits and/or approvals to disturb flora/fauna sites. Ensure that a copy of these permits are obtained prior to the commencement of tree removal works.
label | REFERENCE DOCUMENTS: Condition Plans endorsement
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Clear & Grub
checkpoint | 2.1 - Define work area
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: The work area has been determined, and the extent of clear and grub has been reviewed by Fulton Hogan and the Superintendent. Any trees to be removed have been clearly marked and confirmed on site.
label | REFERENCE DOCUMENTS: 201.1
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Cultural Heritage and Areas of Significance
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Areas determined to be No-Go Zones are securely fenced and clearly identified by signage installed in the fencing.
label | ○ Works are to be suspended immediately and Cultural Heritage representatives (BLCAC) are to be notified, if any items of significance are discovered or identified during construction.
label | ○ Works may recommence with the cultural heritage approval or if works can resume without risk to the discovered Cultural Heritage.
label | REFERENCE DOCUMENTS: CHMP
label | INSPECTION/TEST METHOD: Inspect
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Joint Inspection to Mark vegetation or habitat to be removed
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the project Arborist and project Ecologist
label | REFERENCE DOCUMENTS: Drawings, CEMP, Tree Management Plan 176.I1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Felling of Trees
label | FREQUENCY: Prior to commencing clearing
label | ACCEPTANCE CRITERIA: Trees shall be brought down in such manner as to avoid danger to personnel and traffic or damage to other trees, shrubs, structures or property outside the area being cleared or designated to be retained within the area being cleared
label | REFERENCE DOCUMENTS: 201.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.5 - Backfill holes
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Any holes produced from grubbing operations have been backfilled with similar material and compacted
label | REFERENCE DOCUMENTS: 201.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.6 - Dispose of Trees and vegetation
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Trees that are to be removed shall be mulched to the extent possible and the mulch retained for use in the Landscaping Works.
label | ○ Noxious weeds shall not be mulched.
label | REFERENCE DOCUMENTS: 201.07
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Dispose of concrete, bituminous and other recyclable materials.
label | FREQUENCY: After clearing
label | ACCEPTANCE CRITERIA: Salvaged concrete, bituminous materials over 50mm and other recyclable materials have been sent to approved recycling establishments.
label | REFERENCE DOCUMENTS: 201.07
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Stripping of topsoil
label | FREQUENCY: Prior and after commencement of any ground disturbing activities
label | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation. Declared noxious weeds, pests and pathogens shall be treated and monitored before stripping of topsoil, and after spreading, to prevent and/or minimise the spread of weeds and other pathogens throughout the site.
label | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re-spread as soon as practicable.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.9 - Removal of abandoned services
label | FREQUENCY: Prior to commencing works
label | ACCEPTANCE CRITERIA: Pits which are no longer required shall be removed or broken back to a depth not less than 0.3 m below the finished surface of the subgrade. Remaining pipe openings shall be sealed with concrete. Any remnants of pits shall be backfilled with material and compacted to a density ratio of not less than 95%. The calculation of density ratio shall be based on Standard compactive effort.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.10 - Clearing of Trees and Vegetation
label | FREQUENCY: During clearin works
label | ACCEPTANCE CRITERIA: Clearing work shall not be undertake outside of the specified limits of work.
label | ○ Tree branches extending over the carriageway shall be trimmed to provide a clearance of at least 6 m above the carriageway surface. Where whole branches are to be removed, the three cut method shall be used.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.04
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.11 - Grubbing of vegetation
label | FREQUENCY: Prior and after commencement of any ground disturbing activities
label | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment. In areas to be covered by embankments, to a depth of not less than 0.3 m below the stripped surface or not less than 0.6 m below the finished surface of the subgrade, whichever is the lesser treatment.
label | ○ Holes resulting from grubbing shall be backfilled with material similar to the surrounding material and compacted to the same degree as the surrounding material
label | REFERENCE DOCUMENTS: CEMP VicRoads Spec. Cl.201.05
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-002 - Construction of Underground Stormwater Drainage | itp |  |  |  |  | ITP-002 - Construction of Underground Stormwater Drainage Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Precast Materials Inspection
label | FREQUENCY: Each Delivery
label | ACCEPTANCE CRITERIA: Precast materials have been inspected and fit for purpose and free of defects
label | REFERENCE DOCUMENTS: 701.04b
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed Receival and Inspection Checklist
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.4 - Precast Pipe Compliance
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Precast Reinforced Concrete Pipes shall comply with requirements of AS 4058
label | ○ Pits deeper than 1.00m to be fitted with step irons as shown on the drawings. Step irons are compliant with AS4680 with a minimum average coating thickness equivalent to 600 g/m2.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.619
label | ○ Cl. 701.04(a)
label | ○ Cl. 701.04(b)(i)
label | ○ Cl. 705.04(d)
label | ○ Cl. 705.11
label | ○ AS4058
label | ○ AS4680
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Receival & Inspection Checklist, Manufacturer cetificate or accreditation
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.5 - Bedding material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | ○ 100% passing 19mm sieve.
label | ○ 5%-40% passing 0.075mm.
label | ○ PI = 20 max.
label | REFERENCE DOCUMENTS: 701.04e, Table 701.041, Table 701.042, Table 701.231
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.6 - Backfill material Classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Nominated material shall be free from perishable matter and conform with the requirements below:
label | ○ 100% passing 37.5mm sieve.
label | ○ 5%-40% passing 0.075mm sieve.
label | ○ PI = 20 max.
label | REFERENCE DOCUMENTS: 701.04e, Table 701.041, Table 701.042, Table 701.231
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.7 - Mortar material classification
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Cementituous grouts shall be minimum Type C class dual shinkage compensating, with a minimum 28 day compressive strength of 40 Mpa
label | REFERENCE DOCUMENTS: 610.33
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports from supplier
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.2 - Set out drainage
label | FREQUENCY: Prior to excavation
label | ACCEPTANCE CRITERIA: The position of all drainage lines are to be confirmed with the superintendent
label | REFERENCE DOCUMENTS: Drawings 701.10
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Excavation (pipes)
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Horizontal clearance ( between the walls of trench to the side of pipe shall be 300mm – 600mm for pipes, and 0.5 to 1 times the overall height of the culvert for box culverts.
label | ○ Trench walls to be vertical where practical
label | Depth of trench:
label | ○ > 100mm below underside of pipe (for pipe width < 1500 mm)
label | ○ > 200mm below underside of pipe (for pipe width > 1500 mm)
label | REFERENCE DOCUMENTS: 701.15, Table 701.151
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
checkpoint | 2.4 - Compact base of trench
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Compacted to refusal using mechanical plant.
label | REFERENCE DOCUMENTS: 701.1
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.5 - Place bedding material & compact
label | FREQUENCY: Each Trench
label | ACCEPTANCE CRITERIA: Bedding material shall be compactied to no less than the below thickness:
label | ○ 100mm under pipes.
label | ○ 80mm (earth foundation)
label | ○ 150mm (rock foundation)
label | REFERENCE DOCUMENTS: 701.19
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Place pipes
label | FREQUENCY: Each Line/Pit
label | ACCEPTANCE CRITERIA: Pipes & pits placed as shown on the drawings. No laying to occur until bedding lines and levels and compaction requirements have been satisfied
label | REFERENCE DOCUMENTS: Drawings 701.17
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Jointing pipe sections
label | FREQUENCY: Each Line
label | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance to manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
label | REFERENCE DOCUMENTS: 701.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Place & compact backfill material over pipes
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: Backfill under paved area:
label | ○ fill trench with selected back fill material to subgrade level
label | Backfill under area not paved:
label | ○ Back fill trench with selected back fill to a level 0.3 m above the top of pipe or culvert, and ordinary back fill above that level
label | ○ Loose layer thickness <= 150mm.
label | ○ 1 lot = 150mm layer
label | REFERENCE DOCUMENTS: 701.14, 701.15
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.9 - Repairs to damaged pipes
label | FREQUENCY: Each damaged pipe
label | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the superintendents approval of the repair materials and procedures
label | ○ All repair procedures undertaken in accordance with Cl 701.25
label | REFERENCE DOCUMENTS: 701.31
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Engineer / Forman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing & Completion
checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
label | FREQUENCY: as required/requested
label | ACCEPTANCE CRITERIA: Backfill material shall be compactied to a mean density ratio of 92% using standard compactive effort.
label | ○ Bedding material shall be compacted using a compaction plated to refusal.
label | REFERENCE DOCUMENTS: 701.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Reports
label | TP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-003 - Earthworks Foundation | itp |  |  |  |  | ITP-003 - Earthworks Foundation Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Project site
label | REFERENCE DOCUMENTS: Induction Register
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Excavation Permit issued
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Excavation Permit No.
label | IP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 1.4 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.5 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.6 - Verification of Site Clearing
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: In areas where excavation will be made, all vegetation, refuse and obstructions shall be totally grubbed or grubbed to a depth of not less than 0.3 m below the subgrade and batters, whichever is the lesser treatment.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.201.05, ITP-001
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.7 - Material Category
label | FREQUENCY: Prior and During Excavation
label | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of material in accordance with Clause 204.04
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.204.04, Cl.204.06(c)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.8 - Placing Fill
label | FREQUENCY: Prior to Commencing Fill
label | ACCEPTANCE CRITERIA: Placing fill shall not commence on the prepared areas until the area has been reviewed by the Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.10(b)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.9 - Rock Subgrade
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Details of any necessary amendments to the sub surface drainage design including trasverse subsurface drainage at the interfaces shall be submitted to the Superintendent for review.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.10 - Ground Water
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: The Superintendent shall be notified where groundwater or seepage is encountered and the proposed action to be taken, shall be submitted for review. Any necessary approvals from relevant authorities for treatment and disposal of this groundwater shall also be submitted .
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(h)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 1.11 - Unsuitable Material
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
label | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity. Survey activities undertaken to ensure and validate that all Works meet level and location requirements. Verification of conformity with latest IFC drawings.
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Survey records & pegs on the ground
label | SCP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.2 - Surface Preparation
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: For areas where the subgrade height is less than one metre above cut height, the cut should be scarified to 150mm and recompacted with Type B material
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04, Cl. 204.06
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Foundation Treatment (if required)
label | FREQUENCY: Prior to Treatment (if required)
label | ACCEPTANCE CRITERIA: Proposed method reviewed, refer relevant ITP
label | REFERENCE DOCUMENTS: Relevant ITP
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-004 - Underground Drainage | itp |  |  |  |  | ITP-004 - Underground Drainage Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to.
label | FREQUENCY: Frequency: Prior to commencing works
label | ACCEPTANCE CRITERIA: Refer to the VicRoads Traﬃc Management speciﬁcation 166
label | REFERENCE DOCUMENTS: Traﬃc Mgmt. Plan
label | METHOD: Visual Inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
checkpoint | 1.2 - Purchase of pre-cast pits, pipes and end-walls
label | FREQUENCY: Frequency: Approval prior to placement of order
label | ACCEPTANCE CRITERIA: Refer to Construction Drawings
label | REFERENCE DOCUMENTS: Vic roads Standard drawings
label | METHOD: Review and approval of documentation
label | Visual inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: SWA Project Manager
date | Date Completed:
section | 2 - Construction works
checkpoint | 2.1 - CONFORMITY WITH DRAWINGS - The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed.
label | FREQUENCY: Frequency: Each lot as required
label | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent.
label | REFERENCE DOCUMENTS: Vicroads std sec 701.09
label | METHOD: Construction Drawings
label | RECORD: Signed ITP
label | IHP, SWA
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 2.2 - CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level
label | FREQUENCY: Frequency: Each Lot
label | ACCEPTANCE CRITERIA: Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be:
label | (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm
label | (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm
label | (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
label | REFERENCE DOCUMENTS: Vicroads std sec 701.09
label | METHOD: Construction Drawings
label | RECORD: Signed ITP
label | IHP, SWA
label | RESPONSIBILITY: Project Manager, Site Supervisor
date | Date Completed:
checkpoint | 2.3 - EXCAVATION
label | FREQUENCY: Frequency: Each Lot
label | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm
label | REFERENCE DOCUMENTS: VicRoads Std Specs 701.14
label | METHOD: On-site Measurement
label | RECORD: Signed ITP & Drainage Checklist
label | WP
label | RESPONSIBILITY: Project Engineer, Site Supervisor
date | Date Completed:
checkpoint | 2.4 - CULVERT BEDDING – Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert
label | FREQUENCY: Frequency: Each Lot
label | ACCEPTANCE CRITERIA: The compacted thickness of bedding material following any shaping necessary shall be not less than:
label | ○ 100 mm where D < 1500 mm
label | ○ 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
label | REFERENCE DOCUMENTS: VicRoads Std Specs 701.15
label | METHOD: Site Inspection
label | RECORD: Signed ITP
label | WP
label | RESPONSIBILITY: Project Engineer, Site Supervisor
date | Date Completed:
checkpoint | 2.5 - PLACEMENT OF FILLING
label | FREQUENCY: Frequency: Each lot as required
label | ACCEPTANCE CRITERIA: (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
label | (I) Culvert Under Area not to be Paved. The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
label | REFERENCE DOCUMENTS: VicRoads Std Specs 701.18
label | METHOD: Site Inspection
label | RECORD: Signed ITP
label | WP
label | RESPONSIBILITY: Project Engineer, Site Supervisor
date | Date Completed:
checkpoint | 2.6 - INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS
label | FREQUENCY: Frequency: Each lot as required
label | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV). Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
label | REFERENCE DOCUMENTS: VicRoads Std Specs 701.28
label | METHOD: Visual inspection
label | RECORD: Signed ITP
label | HP
label | RESPONSIBILITY: Project Engineer
label | AP
label | RESPONSIBILITY: Clients Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.7 - Where required installation of Geofabric or Jute matting and beaching material in swale drains
label | FREQUENCY: Frequency: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse
label | ACCEPTANCE CRITERIA: Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows.
label | ○ Rock shall be placed with a geo-textile liner.
label | REFERENCE DOCUMENTS: NIL
label | METHOD: Visual inspection
label | RECORD: Signed ITP
label | IHP
label | RESPONSIBILITY: Project Engineer/Site Supervisor
date | Date Completed:
section | 3 - Testing Requirement
checkpoint | 3.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT - Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
label | FREQUENCY: Frequency: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls)
label | ACCEPTANCE CRITERIA: (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | (b) Backﬁll
label | (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
label | REFERENCE DOCUMENTS: Vicroads std sec 701.19
label | METHOD: Lab Test
label | RECORD: Signed ITP
label | IHP, SWA
label | RESPONSIBILITY: Project Manager
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-005 - Crushed Rock Classed | itp |  |  |  |  | ITP-005 - Crushed Rock Classed Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Project site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | HP
label | RESPONSIBILITY: Site Engineer, Site Foreman & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Crushed Rock Mix design
label | FREQUENCY: Prior to Commencing Work
label | ACCEPTANCE CRITERIA: Crushed rock mixes proposed for use on specified works shall be registered in accordance with VicRoads Code of Practice for Registration of Crushed Rock Mix Designs as listed in Section 175.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.812.09
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Mix Design VicRoads Approval
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Placing Fill
checkpoint | 2.1 - Transverse Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsTransverse joints shall be offset from one layer to next by not less than 2 metres
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (c)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Longitudinal Joints
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: Material should be spread to minimize number of jointsLongitudinal joints offset from one layer to next by not less than 150mmLongitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.07 (a), Cl.304.07 (d), Cl.304.07 (e)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.3 - Lot Size
label | FREQUENCY: Check prior to placing material
label | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08 (b)(ii) Table 304.111
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.4 - Proof Roll
label | FREQUENCY: After placing material
label | ACCEPTANCE CRITERIA: Pavement lots should be subject to proof roll as outlined in VicRoads Section 173, under supervision of Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.304.08(b)(iv), Cl. 173
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | WP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
section | 3 - Testing Requirements
checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
label | FREQUENCY: Prior to Testing
label | ACCEPTANCE CRITERIA: Table 204.161 from VicRoads Standard nominates the level of testing required for acceptance of Surface Level Measurement.
label | ○ Scale A - Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.08. and 304.10. If no failures, Reduced Frequency applies as specified in Table 304.111.
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 204.161
label | ○ VicRoads Spec. Cl.304.08 (a), Cl.304.11 (b), Cl.304.11 (c)(i) Table 304.111
label | INSPECTION/TEST METHOD: Document Review/ Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.2 - Modified Compactive Effort
label | FREQUENCY: As per 3.1
label | ACCEPTANCE CRITERIA: Characteristic Value of Density Ratio for Subbase:- > 98.0% (Scale A) 6 lot test Initial Frequency
textbox | Test No. |  |  | — > 97.0%
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.081
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Permeability Testing
label | FREQUENCY: As per 3.1
label | ACCEPTANCE CRITERIA: Class 4 Crushed rock max 5x10^-9 m/sec.
label | ○ Where the Class 4 material is used as a levelling layer in a deep strength asphalt pavement, the Superintendent grants dispensation from 5x10-9 m/s Max permeability requirement in clause 3040.05(a) and table 3040.051 and allows FH to use 9x10-9 m/s Max permeability
label | REFERENCE DOCUMENTS: Project Spec. Cl.3040.05(a) Table 3040.051, RFI-0085.01
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records from Supplier
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.4 - Survey Level
label | FREQUENCY: At completion
label | ACCEPTANCE CRITERIA: Scale A:
label | — Minimum number of measurements per lot: 80 For Upper
label | — Upper Subbase: Mean + 4mm to - 8mm with a maximum Standard Deviation of 8mm
label | — Lower Subbase: Mean +6mm to -10mm with a maximum Standard Deviation of 10mm.
label | — Base: Mean ± 5 with a maximum Standard Deviation of 8mm.
label | REFERENCE DOCUMENTS: VicRoads Spec. Table 304.061, Table 304.062
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-006 - Subgrade Preperation | itp |  |  |  |  | ITP-006 - Subgrade Preperation Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Project site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures and site controls to be implemented as per current CEMP and CHMP. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings, CEMP, CHMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.4 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: PSP, CEMP, TMP, JSEA, SWMS,
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | IP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Excavation Permit No.
label | IP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey set-out
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks required for the works. The establishment and integrity of the survey network shall be verified before commencing any survey and set out activity.
label | REFERENCE DOCUMENTS: Project Spec. Cl.1190.07, Latest IFC Drawings
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Compliance with latest IFC drawings. Survey records & pegs on the ground.
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.2 - Unsuitable Material
label | FREQUENCY: During Excavation
label | ACCEPTANCE CRITERIA: Where unsuitable material is encountered, actions shall be:
label | a) excavate the unsuitable material and backfill with 20mm Class 3 Crushed rock and compacted to min 98% Standard MDD to the approval of Superintendent
label | REFERENCE DOCUMENTS: IFC Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.3 - Material Category
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Prior excavation, Superintendent and Fulton Hogan responsible shall inspect each type of material encountered and, subject to verification by laboratory testing, agree on category of material in accordance with VicRoads Spec Section 204.04
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04, Cl. 204.06(c)
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Superintendent agreement, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Trimming and level conformity
label | FREQUENCY: Each Lot (one day's production) prior to Commencing
label | ACCEPTANCE CRITERIA: Ensure that the level at any point on the surface of the Cut Floor Level immediately below capping not differ by more than 5 mm above or 15 mm below the specified level. Level at any point of sugbrade shall not lie more than 20mm below a 3m straightedge in any direction excepting crowns. Water shall not pond at any point. The mean and standard deviation of the departures from the theoretical surface level within each lot shall meet the requirements of Table 204.031.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.03(f), Cl. 204.03(g) Table 204.031
label | INSPECTION/TEST METHOD: Survey Report
label | RECORD OF CONFORMITY: Survey Record
label | SCP
label | RESPONSIBILITY: Site Engineer & Surveyor
date | Date Completed:
checkpoint | 2.5 - Acceptance of Rock Subgrade (when applicable)
label | FREQUENCY: Prior construction of the regulating layer
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | INSPECTION/TEST METHOD: Site Inspection/ Document Review
label | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
label | HP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Cut to Fill Zones
label | FREQUENCY: Each Lot (one day's production) prior to Commencing
label | ACCEPTANCE CRITERIA: All pavement and verge areas at cut to fill zones shall be excavated to a minimum depth of 600mm below the cut floor level or top of the type B material, for a distance of not less than 15m into the cut and 30m under the fill from the cut-fill line at the upper surface of the Type B material.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(g)
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 3 - Testing for Compaction and Material Properties
checkpoint | 3.1 - Proof Rolling
label | FREQUENCY: Each Lot (one day's production), prior to Commencing Fill
label | ACCEPTANCE CRITERIA: Test rolling of all fill layers and subgrade shall be in accordance with Section 173 and 204 of the VicRoads Standard Specification.
label | ○ Fulton Hogan to provide not less than 24hrs notice to the Superintendent of the location and commencement time for test rolling. Superintendent to be present during all test rolling.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 173.03, Cl. 204.12
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Proof Rolling Register signed.
label | WP
label | RESPONSIBILITY: Site Engineer & Superintendent
date | Date Completed:
checkpoint | 3.2 - Testing for Compaction and Material Properties
label | FREQUENCY: Testing as per table 204.141 of VicRoads Spec. for Roadworks and Bridgeworks
label | ACCEPTANCE CRITERIA: Type B Material placed within 400 mm of top of Type B Material and Ripped and re-compacted material below Cut Floor Level= minimum compaction 99% MDD.
label | ○ Type B material 400mm below the top of Type B material and Top 150mm of cuts= minimum compaction 97% MDD.
label | REFERENCE DOCUMENTS: VicRoads Spec.
label | ○ Cl. 173.04
label | ○ Cl. 204.13
label | ○ Cl. 204.14
label | ○ Table 204.131
label | ○ Table 204.141
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: Test Results
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-007 - Guardrail Installation | itp |  |  |  |  | ITP-007 - Guardrail Installation Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Induction
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All personnel on site have been inducted to the Project site
label | REFERENCE DOCUMENTS: Inductions Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Site induction signed.
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Safety measures are in place, Safe Work Mathod Statement (SWMS) undertaken
label | FREQUENCY: Prior to commencing
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, CEMP, TMP & SWMS
label | REFERENCE DOCUMENTS: Health and Safety Co-Ordination Plan
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: SWMS(s) signed
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Check that current revision drawings are being used
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Issued For Construction (IFC) and latest available revision used
label | REFERENCE DOCUMENTS: Project Drawings / Drawing Register
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Latest Revision Drawings
label | AP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.4 - Confirm understanding of current CEMP and CHMP related to the work area and that all prescribed environmental controls are in place
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: All environmental measures to be implemented as per current EMP and local authorities. Sediment control measures to be installed and protected vegetation to be clearly identified
label | REFERENCE DOCUMENTS: IFC Drawings CEMP, CHMP
label | INSPECTION/TEST METHOD: Document review & Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.5 - Excavation Permit issued
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Current Excavation Permit signed and specific for the area where works will be executed.
label | REFERENCE DOCUMENTS: Excavation Permit
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Excavation Permit #
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 1.6 - Approval of Guardrail System
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Only safety barrier products listed in VicRoads Road Design Note 06-04 shall be used.
label | REFERENCE DOCUMENTS: RDN 06-04
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Signed ITP/Email
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Approved steel supply
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent all test certificates related to the supply of steel for the Works at least 14 days prior to commencement of installation.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.05(b)
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Supplier's NATA (or otherwise approved), Material Test Certificates
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Approved Galvanisation records
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Surface preparation in accordance with AS1627 parts 1 & 4. Zinc coating mass of galvanised components to be in accordance with AS 4680 or for components of proprietary end treatments as per the manufacturer's recommendations/requirements. All galv coatings to be smooth, adherent and free from stains, gross surface imperfections, markings, brand names and/or inclusions. Colour shall be uniform
label | REFERENCE DOCUMENTS: VicRoads Spec.Cl.708.05(d)
label | INSPECTION/TEST METHOD: Document review
label | RECORD OF CONFORMITY: Supplier's NATA (or otherwise approved) Manufacturer's certificate of compliance, Test Certificates
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.1 - Survey set-out
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Survey activities undertaken to ensure and validate that all works meet level and location requirements.. IFC and latest available revision used
label | REFERENCE DOCUMENTS: Latest IFC Drawings
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | SCP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | 3.2 - Service Location
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Where geotextile is to be used as a first stage filter in contact with a trench wall, the trench wall shall be excavated to allow the geotextile to be in close contract with the wall when granular material is placed against the geotextile.
label | REFERENCE DOCUMENTS: Services file & Current DBYD notifications
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Services marked on the ground
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Approval of location and length
label | FREQUENCY: Prior to Installation
label | ACCEPTANCE CRITERIA: Prior to installation the Contractor shall confirm with the superintendent the required location and length of all guard fence.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.4 - Install posts, rails and terminations
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: Tolerances
label | W-beam guard fence shall be erected to the following tolerances:
label | (i) Variation from true plan position of posts ±20 mm
label | (ii) Variation of line of w-beams from specified vertical profile ±10 mm
label | (iii) Variation of w-beams from specified horizontal alignment ±20 mm
label | (iv) Variation of posts from vertical (measured at top of the post) ±15 mm
label | (v) Orientation of block and/or post to w-beam +0 mm, -15 mm (measured at the point of greatest offset between the block or post to the w-beam)
label | (vi) Dimension of holes -0 mm, +50 mm
label | (vii) Top of bolt head relative to w-beam -0 mm, +5 mm
label | ○ After installation the top of the rail shall be within 25 mm of the specified level and 50 mm of the specified line. Variations from specified line and level shall not occur at a rate exceeding 15 mm in any 5 m length
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.08(d)
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Signed ITP
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - Construct crushed rock base for maintenance strip
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: Min 75mm thick class 3 CR, min 2% crossfall away from road. All bedding material used for cast in place concrete construction works shall be in accordance with Section 812 for Class 3 Crushed Rock
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.12(a)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP
label | WP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | 3.6 - Construct concrete maintenance strip
label | FREQUENCY: During construction.
label | ACCEPTANCE CRITERIA: Min 75mm thick N20 grade portland cement-based concrete, finished to Class 3 crushed rock, 300mm clear of rear of post and face of w-beam. Separation from the kerb or pavement by the use of a cork expansion joint (or approved alternative), full depth expansion joints 200mm either side of posts. Fresh concrete to be protected from rain or other damage until hard set
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.708.12(a)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Concrete dockets/Signed ITP
label | WP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
section | 4 - Testing
checkpoint | 4.1 - Compliance Audit of Barrier System Installation
label | FREQUENCY: Prior the issue of the Certificate of Practical Completion
label | ACCEPTANCE CRITERIA: Prior to the issue of the Certificate of Practical Completion, the Contractor shall arrange for a safety barrier compliance audit on all proprietary guard fence end treatments constructed under the Contract and the Contractor shall complete and submit to the superintendent a signed copy of the Checklist / Inspection and Test Plan as per the manufacturer’s Product and Installation Manual.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.10
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Safety barrier compliance audit, Manufacturer compliance certificate
label | HP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Completion
checkpoint | 5.1 - Delineators
label | FREQUENCY: Once installation of assets is completed
label | ACCEPTANCE CRITERIA: The Contractor shall arrange delineators so that vehicles approaching from either direction at night will only see:
label | ○ red delineators on the left side of one-way and two-way roadways;
label | ○ white delineators on the right side of two-way roadways; and
label | ○ yellow delineators on the right side of one-way roadways.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.702.11
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Site Photos/Signed ITP
label | IP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | 5.2 - Survey data captured for As-Builts
label | FREQUENCY: Completion of Works
label | ACCEPTANCE CRITERIA: As-Built drawings to be submitted to client
label | REFERENCE DOCUMENTS: VicRoads Spec. 708
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: As-Builts, Survey reports
label | IP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-008 - Insitu Pit Construction | itp |  |  |  |  | ITP-008 - Insitu Pit Construction Rev1
section | 1 - Preliminary Activities
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Supervisor
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP signed
label | HP*
label | RESPONSIBILITY: Site Engineer/ Supervisor
date | Date Completed:
checkpoint | 1.3 - Use of approved mix design
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Concrete mixes used will be inline with Table 705.041 - VR330/32 for drainage pits
label | REFERENCE DOCUMENTS: Cl 705.04
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing including removal of unsuitable material.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Excavation and erection of falsework/formwork
checkpoint | 2.1 - Excavation
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Excavations shall be to the depths shown on the drawings and that necessary to provide satisfactory foundation
label | REFERENCE DOCUMENTS: Cl 705.05
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | 2.2 - Construction Methodology
label | FREQUENCY: Prior to erection
label | ACCEPTANCE CRITERIA: Formwork shall be used in such a manner that it can be removed without damage to the concrete. Formwork shall be placed in locations where steel reinforcement and other fixtures can be inspected, and sufficiently tight at joints to to confine freshly placed concrete and maintain position and shape during construction.
label | REFERENCE DOCUMENTS: Cl 703.12
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
section | 3 - Steel reinforcing
checkpoint | 3.1 - Placement methodology
label | FREQUENCY: At all times
label | ACCEPTANCE CRITERIA: All steel reinforcement to be securely held during placing and compacting of concrete
label | ○ Supports shall be of a material durable to impose loads without movement of the reinforcement
label | ○ The placement method shall not allow the reinforcement to become contaminated by contact with other steel
label | REFERENCE DOCUMENTS: Cl 703.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | 3.2 - Minimum Cover
label | FREQUENCY: At all times
label | ACCEPTANCE CRITERIA: The specified minimum cover must be maintained at all tire wire positions. A tolerance of 0 to +5mm is allowed.
label | REFERENCE DOCUMENTS: Cl 703.13
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
section | 4 - Pre-pour Planning and Inspection
checkpoint | 4.1 - Pre-pour inspection
label | FREQUENCY: Prior to concrete pour
label | ACCEPTANCE CRITERIA: Superintendent confirms that the inspected formwork, reinforcement and embedments comply with the project drawings and specifications.
label | ○ Hold Point released by the Superintendent.
label | REFERENCE DOCUMENTS: CL 705.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 5 - Placing Concrete
checkpoint | 5.1 - Carry out sampling of concrete
label | FREQUENCY: 0-50m3 - 1 sample
label | ACCEPTANCE CRITERIA: No. of Samples: 0 to 50m3 - 1 No.
label | REFERENCE DOCUMENTS: Cl 703.11
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: CLB, CLC
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 5.2 - Compressive testing
label | FREQUENCY: 0-50m3 - 1 sample
label | ACCEPTANCE CRITERIA: A minimum of one cylinder shall be tested at 7 days and a minimum of 2 cylinders at 28 days.
label | ○ The average compressive strength at 28 days shall not be lower than the specified minimum compressive strength. Additioinally, the compressive strength of each individual cylinder shall be no less than 90% of that at 28 days.
label | REFERENCE DOCUMENTS: Cl 703.11
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Concrete test records
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 5.3 - Placement methodology
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Concrete shall be tansported, handled and placed in a manner that will prevent segregation or loss of materials
label | ○ Concrete shall not be freely dropped from height >2m
label | ○ Concrete shall not be moved horizontally by vibrators
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | 5.4 - Compaction
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Vibration shall be applied to the full depth of each layer and extended into the top 100 mm of the underlying layer. Vibration shall continue at each point until air bubbles cease to emerge from the concrete, then withdrawn slowly. Concrete shall not be vibrated to the point where segregation of the ingredients occurs.
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Supervisor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-009 - Bored Piling | itp |  |  |  |  | ITP-009 - Bored Piling Rev1
section | 1 - Design and Submissions
checkpoint | 1.1 - Check for correct documetation
label | FREQUENCY: Before commencement of activity
label | ACCEPTANCE CRITERIA: Check correct documentation is being utilized (latest drawing revision) and IFC/ Proof Engineering
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Current revision of drawing
label | RECORD OF CONFORMITY: Current revision of drawing
label | HP*
label | RESPONSIBILITY: Project Engineer Site Engineer
date | Date Completed:
checkpoint | 1.2 - Approval of Mix Design
label | FREQUENCY: No less than 4 weeks prior to commencement of activity
label | ACCEPTANCE CRITERIA: Mix design reviewed and approved by superintendent.
label | REFERENCE DOCUMENTS: Cl 610.07(b
label | INSPECTION/TEST METHOD: Approval
label | RECORD OF CONFORMITY: VicRoads letter of approval
label | AP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
checkpoint | 1.3 - Approval of Quality Procedure
label | FREQUENCY: No less than 4 weeks prior to commencement of activity
label | ACCEPTANCE CRITERIA: Proposed materials and pile construction procedures reviewed by the superintendent
label | REFERENCE DOCUMENTS: Cl 606.03(a)
label | INSPECTION/TEST METHOD: Approval
label | RECORD OF CONFORMITY: VicRoads letter of approval
label | HP
label | RESPONSIBILITY: Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.4 - Ensure Traffic, Safety, Quality and Environmental management measures are in place
label | FREQUENCY: Prior to commencement of activity. EMP at least 2 weeks prior
label | ACCEPTANCE CRITERIA: Safety plan, traffic management plan and environmental management plan
label | REFERENCE DOCUMENTS: PSP, TMP & EMP
label | INSPECTION/TEST METHOD: Ensure all measures in place as per plan
label | RECORD OF CONFORMITY: Inspection
label | HP
label | RESPONSIBILITY: Site Engineer Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.5 - Certification of approved Hot Dip Galvanising
label | FREQUENCY: Prior to Epoxy coating
label | ACCEPTANCE CRITERIA: Galvanising treatment in accordance with appropriate Standard documents and Design specification
label | ○ 200 microns
label | REFERENCE DOCUMENTS: Drawings AS/NZ4680
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Manufacturers certificate
label | HP*
label | RESPONSIBILITY: Project Manager Site Engineer
date | Date Completed:
checkpoint | 1.6 - Certification of approved Epoxy coating
label | FREQUENCY: Prior to arrival on site
label | ACCEPTANCE CRITERIA: Epoxy treatment in accordance with appropriate Standard documents and Design specification 2 x Base Coat GFX @ 250 microns
label | ○ 1 x Top Coat Polyurethane, 100 microns
label | REFERENCE DOCUMENTS: Drawings AS2312
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Manufacturers certificate
label | HP*
label | RESPONSIBILITY: Project Manager Site Engineer
date | Date Completed:
section | 2 - Bored Piling
checkpoint | 2.1 - Survey and setout
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: Survey and confirm position and depth as per drawing
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
date | Date Completed:
checkpoint | 2.2 - Excavation Levels
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: Check the excavation levels and base are acceptable and conform to the drawing prior to commencement of piling works.
label | REFERENCE DOCUMENTS: Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Drilling check sheet
label | HP
label | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Inspection of Pile Excavation
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: First 3 piles to be inspected by Geotechnical Engineer to check dimensions and toe level are correct and within tolerance. Correct Toe level.
label | ○ Material encountered consistent with design.
label | REFERENCE DOCUMENTS: Drawings Cl 606.06
label | INSPECTION/TEST METHOD: Inspection / Test Method
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Site Engineer Geotechnical Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Bore Logs
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: All bore logs and pile installation records to be sent to and reviewed by designer
label | REFERENCE DOCUMENTS: Bore logs
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Drilling check sheet
label | HP
label | RESPONSIBILITY: Site Engineer, Geotechnical Engineer
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Spacers installed on Reinforcement Cage
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: Spacers/supports to be placed along steel reinforcement at a maximum 2m intervals
label | REFERENCE DOCUMENTS: Cl 611.10
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP*
label | RESPONSIBILITY: Site Engineer, Superintendent
date | Date Completed:
checkpoint | 2.6 - Inspection of column and cage height and centre
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: Ensure heights, centre and spacing of reinforcement cage and column are in accordance with drawings and within tolerance
label | REFERENCE DOCUMENTS: Drawings Cl 606.08
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | IP
label | RESPONSIBILITY: Site Engineer Superintendent
date | Date Completed:
section | 3 - Placing and Finishing Concrete
checkpoint | 3.1 - Quality Checks
label | FREQUENCY: Prior to each concrete pour
label | ACCEPTANCE CRITERIA: Relevant ITPs and Quality Control checklists completed and reviewed
label | REFERENCE DOCUMENTS: Cl 610.18
label | INSPECTION/TEST METHOD: Inspection
label | RECORD OF CONFORMITY: This ITP Signed off
label | HP
label | RESPONSIBILITY: Site Engineer Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.2 - Carry out sampling of concrete
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Sampling in accordance with 610.16 Slump: As per VR450/50 mix 675mm (+/- 125mm) (550mm - 800mm)
label | REFERENCE DOCUMENTS: Cl 610.16 Table 610.161
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Checklist
label | IP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.3 - Record location of each batch
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Batch location recorded
label | REFERENCE DOCUMENTS: Cl 610.15
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Checklist
label | IP
label | RESPONSIBILITY: Tester
date | Date Completed:
checkpoint | 3.4 - 7 Day concrete test result
label | FREQUENCY: Each sample
label | ACCEPTANCE CRITERIA: Concrete cyclinder test smples: 7 day concrete strength achieved of 35MPa
label | REFERENCE DOCUMENTS: Cl 610.05
label | INSPECTION/TEST METHOD: Test Report
label | RECORD OF CONFORMITY: This ITP Signed off
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.5 - 28 Day concrete test result
label | FREQUENCY: Each sample
label | ACCEPTANCE CRITERIA: Concrete cyclinder test smples: 7 day concrete strength achieved of 50MPa
label | REFERENCE DOCUMENTS: Cl 610.05
label | INSPECTION/TEST METHOD: Test Report
label | RECORD OF CONFORMITY: This ITP Signed off
label | TP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 3.6 - Tolerance Check and As Built Survey
label | FREQUENCY: Each Pile
label | ACCEPTANCE CRITERIA: Check tolerances and survey pile positions. Mark all details correctly on as-builts. Pile head position and verticality
label | REFERENCE DOCUMENTS: Cl 605
label | INSPECTION/TEST METHOD: Survey
label | RECORD OF CONFORMITY: Survey report
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-010 - Miscellaneous Concrete Paving | itp |  |  |  |  | ITP-010 - Miscellaneous Concrete Paving Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Engineer/ Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | REFERENCE DOCUMENTS: 703.17
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | HP
label | RESPONSIBILITY: Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.3 - Excavation
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Excavation completed to required depth to allow placement of the bedding layer
label | REFERENCE DOCUMENTS: 703.2
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.4 - Bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All bedding material used shall be as follows:
label | ○ 75mm thick layer of 20mm Class 2 crushed rock bedding for median infill
label | ○ Bedding trimmed, moistened, and compacted as per Section 304
label | REFERENCE DOCUMENTS: 703.21 Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
checkpoint | 2.5 - Formwork
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
label | REFERENCE DOCUMENTS: 703.12, AS 3610
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.6 - Reinforcement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Reinforment used shall consist of SL62 mesh is to be placed with a minimum cover of 50mm from the top (unless shown otherwise on drawings).
label | ○ Reinforcement must comply with the requirements of AS/NZS 4671.
label | REFERENCE DOCUMENTS: 703.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.7 - Concrete Quality
label | FREQUENCY: Each Batch
label | ACCEPTANCE CRITERIA: Check the deleivery of the batch is an approved concrete mix as ordered. VR330/32. Check for the time from plant to site,Check for the water qty added.
label | REFERENCE DOCUMENTS: 703.13
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.8 - Concrete Placement
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Concrete shall be thoroughly compaction via contious tamping and internal vibration. Where concrete is unformed it shall be hand tamped to a smooth surface and screeded in accordance with the construction drawings.
label | ○ Where fresh concrete is being placed against concrete which has taken initial set a properly formed construction joint must be used.
label | — N32 for concrete infill
label | REFERENCE DOCUMENTS: 703.05(a), 703.08
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.9 - Record location of each batch
label | FREQUENCY: Each concrete pour
label | ACCEPTANCE CRITERIA: Batch location recorded on Load Batch Traceability Checklist
label | REFERENCE DOCUMENTS:
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.10 - Surface Finish
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Footpaths and other Surfacing shall be compelted with a wooden float.
label | REFERENCE DOCUMENTS: 703.25
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 2.11 - Pram Crossings
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Ensure that pram crossings are constructed in accordance with requirements for access and mobility.
label | REFERENCE DOCUMENTS: Booroondara Standard drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.12 - Joints
label | FREQUENCY: Each Joint
label | ACCEPTANCE CRITERIA: Expansion joints shall be installated at 10m regular intervals using 15mm wide cork or bituminous imtergrate particle board.
label | ○ Control joints at 2.5m regular intervals, 25% of pavement depth and 5mm wide
label | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
label | REFERENCE DOCUMENTS: 703.26
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.13 - Protection of concrete
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: All concrete shall be protected from damage from early loading by pedestrians, animals, vehicles and from rain or any other cause.
label | ○ Vehicles equal to or less than 1.5 tonnes in weight may be permitted to cross after 4 days, vehicles greater than 1.5 tonnes may be permitted to cross after 7 days.
label | REFERENCE DOCUMENTS: 703.27
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Site Foreman
date | Date Completed:
section | 3 - Completion
checkpoint | 3.1 - Carry out sampling of concrete - strength and consistency
label | FREQUENCY: Lot
label | ACCEPTANCE CRITERIA: Sampling and testing of the strength of concrete shall be carried out in accordance with Clause 6.2 of AS 1379.
label | ○ The consistency of the concrete shall be determined by a slump test of each concrete strength sample in accordance with AS 1012.3 and Clause 5.2 of AS 1379
label | REFERENCE DOCUMENTS: 703.11
label | INSPECTION/TEST METHOD: Checklist
label | RECORD OF CONFORMITY: ITP Signed/Test Records
label | TP
label | RESPONSIBILITY: Engineer
date | Date Completed:
checkpoint | 3.2 - Tolerances
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Where matching in with existing surface levels, the new surface shall be within ± 5mm existing.
label | Section dimensions shall be constructed within the following tolerances:
label | ○ 5mm and 15mm for width; or
label | ○ ±3mm for dimensions less than 25mm.
label | REFERENCE DOCUMENTS: 703.15 Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed
label | IP
label | RESPONSIBILITY: Engineer/ Site Foreman
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-011 - Construction of Subsoil Drainage | itp |  |  |  |  | ITP-011 - Construction of Subsoil Drainage Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Material Classification
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Subsurface drainage pipes: 100mm DIA Class 1000 corrugated perforated plastic pipe- with a perforation size of maximum 1.5mm width and minimum length of 150 mm per m^2.
label | ○ Granular filter material for bedding and backfill: Trench backfilled with no fines concrete filter medium complying with Cl 702.05
label | ○ Geotextiles: Shall comply with Cl 702.06.
label | ○ Subsurface drain pits: All subsurface drain pits shall be Type S1 to the specification of SD 1611
label | ○ Pit Lids: Type M3 circular lid (as per SD 1051) for Type S1 pit
label | ○ Flushout risers: constructed to the detail of SD 1631
label | REFERENCE DOCUMENTS: Cl 702.04, Cl 702.05, Cl 702.06
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Excavation Permit
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Site Engineer
date | Date Completed:
checkpoint | 2.2 - Excavation of Trench
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bottom of trench shall be compacted and at a depth no more than 50mm below the specified pipe invert. Grade of the base of the trench shall not allow ponding of water Any loose material shall be removed. To be inspected by Superintendent
label | REFERENCE DOCUMENTS: Cl 702.08
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Placement of bedding
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Bedding of granular filter material of thickness between 25 mm and 50mm placed across bottom of trench and screeded or graded to level
label | REFERENCE DOCUMENTS: Cl 702.09 (c )
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.4 - Placing pipes and geofabric (if required)
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Pipes placed centrally in trench and held firmly in place positioned with openings at the lower half of the pipe.
label | ○ If geofabric required as per Cl 3030.07 (subsurface drains installed in expansive materials), minimum width of geotextile used for wrapping is 450 mm
label | REFERENCE DOCUMENTS: Cl 702.09
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.5 - Placement of granular backfill
label | FREQUENCY: Prior to backfilling
label | ACCEPTANCE CRITERIA: Filter material shall be moistened and compacted with minimal disturbance to pipes. The method of compaction shall be in accordance with the procedures and reviewed by the Superintendent.
label | REFERENCE DOCUMENTS: Cl 702.09
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Site Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Placement of backfill
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Granular filter material placed and compacted compacted in layers not exceeding 300mm with minimal disturbance to pipes. Concrete is to be placed and compacted within one hour of mixing
label | REFERENCE DOCUMENTS: Cl 702.09 (g)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | IP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.7 - Install Pits and Flushouts
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Installed in accordance with drawings and Cl 702.10
label | REFERENCE DOCUMENTS: Cl 702.10
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed off
label | WP
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 2.8 - Flushing Test
label | FREQUENCY: At completion of stage
label | ACCEPTANCE CRITERIA: Flushing test shall be witnessed by a representative nominated by the superintendent and shall confirm that the drainage line is free of obstruction. To be complete after installation of kerb and channel, barriers and road furniture.
label | REFERENCE DOCUMENTS: Cl.702.09(h)
label | INSPECTION/TEST METHOD: Site inspection
label | RECORD OF CONFORMITY: Signed ITP/ Record of flushing tests
label | WP
label | RESPONSIBILITY: Superintendent / Site Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-012 - Pavement Construction | itp |  |  |  |  | ITP-012 - Pavement Construction Rev0
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & ITP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, ITP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Project Engineer / Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Survey Set-Out
label | FREQUENCY: Prior to commencement of excavation
label | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
label | REFERENCE DOCUMENTS: Work Procedure
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP signed
label | IP
label | RESPONSIBILITY: Engineer/ Surveyor
date | Date Completed:
checkpoint | 2.2 - Excavation Permit
label | FREQUENCY: Lot
label | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
label | ○ Plant and equipment shall be appropriate for the task.
label | ○ Excavation operations shall not disturb areas outside the limit of excavation
label | REFERENCE DOCUMENTS: Excavation permit
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP*
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.3 - Material classified as silt
label | FREQUENCY: Prior to Commencing
label | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(c)
label | INSPECTION/TEST METHOD: Document Review
label | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation, Signed ITP/ records
label | HP
label | RESPONSIBILITY: Engineer or Forman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.4 - Acceptance of Rock Subgrade (when applicable)
label | FREQUENCY: Prior construction of the regulating layer
label | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
label | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
label | INSPECTION/TEST METHOD: Site Inspection/ Document Review
label | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
label | HP
label | RESPONSIBILITY: Engineer or Forman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.5 - Unsuitable Material
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
label | REFERENCE DOCUMENTS: 204.07(d)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP Signed Off
label | HP
label | RESPONSIBILITY: Engineer or Forman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.6 - Groundwater
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
label | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
label | REFERENCE DOCUMENTS: 204.06 (h)
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP
label | RESPONSIBILITY: Engineer or Forman / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
section | 3 - Testing
checkpoint | 3.1 - Proof Rolling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
label | REFERENCE DOCUMENTS: Cl 204.12 Section 173
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*, WP
label | RESPONSIBILITY: Engineer or Forman / Superintendent
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-013 - Construction of Kerb and Channel | itp |  |  |  |  | ITP-013 - Construction of Kerb and Channel Rev1
section | 1 - Preliminary Works
checkpoint | 1.1 - Check for correct documentation
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
label | — using the correct and complete set of drawings
label | — all drawings are the latest revision
label | REFERENCE DOCUMENTS: Drawings and drawing registers
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP*
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
section | 2 - Construction Works
checkpoint | 2.1 - Setting Out
label | FREQUENCY: Prior to start
label | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
label | REFERENCE DOCUMENTS: 703.17
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Temporary Drainage Provisions
label | FREQUENCY: If Required
label | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
label | REFERENCE DOCUMENTS: Cl 703.18
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.3 - Bedding
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
label | ○ Unless otherwise stated, 20mm Class 3 or 4 bedding shall be used adn compacted to a thickness of not less than 100mm.
label | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
label | REFERENCE DOCUMENTS: Cl 703.21
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.4 - Pre-concrete check
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
label | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
label | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
label | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
label | REFERENCE DOCUMENTS: Cl 703.08
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
textbox | Ambient Temperature |  |  | °C
textbox | Concrete Temperature |  |  | °C
label | HP*/ WP
label | RESPONSIBILITY: Project Engineer/ Superintendent
date | Date Completed:
checkpoint | 2.5 - Concrete Placement
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl 703.23
label | INSPECTION/TEST METHOD: Site Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | 2.6 - Finish Surfaces
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
label | ○ Concrete to have a neat appearance and uniform colour
label | REFERENCE DOCUMENTS: 703.25
label | INSPECTION/TEST METHOD: Visual inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.7 - Joints
label | FREQUENCY: Each joint
label | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
label | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
label | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
label | REFERENCE DOCUMENTS: 703.26
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer/ Site Foreman
date | Date Completed:
checkpoint | 2.8 - Backfilling
label | FREQUENCY: Each Lot
label | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
label | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
label | ○ Layers shall not exceed 150mm compacted depth
label | REFERENCE DOCUMENTS: 703.29
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Project Engineer
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date:
checklist | ITP-014 - Sealing works - Asphalt laying works | itp |  |  |  |  | ITP-014 - Sealing works - Asphalt laying works Rev1
section | 1 - Construction Works
checkpoint | 1.1 - Submission of Mix Design
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is approved by Superintendent prior to laying mix.
label | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
label | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
label | RECORD OF CONFORMITY: VR approval Completed ITP
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 1.2 - Implementation of all measures and controls
label | FREQUENCY: Prior to commencing any activity
label | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, JSEA, SWMS & WP
label | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: This ITP signed off
label | HP*
label | RESPONSIBILITY: Site Engineer / Site Foreman
date | Date Completed:
checkpoint | 1.3 - Site Inspection and Base Condition
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
label | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 1.4 - Ambient Conditions for Placing
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
label | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
label | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
label | REFERENCE DOCUMENTS: 407.13
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Thermometer
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 1.5 - Planning of Joints
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
label | ○ Transverse Joints Offset from layer to layer by at least 2m
label | ○ Longitudinal Joints Offset from layer to layer by at least
label | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
label | REFERENCE DOCUMENTS: 407.17 (b) & (c) Pavement Drawings
label | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
label | RECORD OF CONFORMITY: Paving Plan
label | WP
label | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
date | Date Completed:
section | 2 - Asphalt Placement works
checkpoint | 2.1 - Tack Coat
label | FREQUENCY: Prior to commencing paving
label | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
label | REFERENCE DOCUMENTS: 407.15, AS2150 11
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Spray area
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.2 - Commencement of Placing
label | FREQUENCY: Prior to commencing Paving
label | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
label | REFERENCE DOCUMENTS: 407.18
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | HP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
date | Date Completed:
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.3 - Delivery of Mix
label | FREQUENCY: Each load
label | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
label | REFERENCE DOCUMENTS: 407.16 Table 407.081
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: Delivery Docket
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.4 - Traceability
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
label | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Daily Lot Record
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.5 - Layer Thickness and Level Control
label | FREQUENCY: Regularly during paving
label | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
label | REFERENCE DOCUMENTS: 407.20 (a) & (b) Drawings
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Dips using ruler or dip stick
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.6 - Surface Finish of Wearing Course
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
label | REFERENCE DOCUMENTS: 407.23 (a)(i)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.7 - Kerb and Channel
label | FREQUENCY: During paving and after final roll
label | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
label | REFERENCE DOCUMENTS: 407.23 (a)(ii)
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | WP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
checkpoint | 2.8 - Alignment of layers not placed against concrete edge
label | FREQUENCY: During paving and at completion of work
label | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
label | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
label | REFERENCE DOCUMENTS: 407.23 (a)(iv) Drawings
label | INSPECTION/TEST METHOD: Visual Inspection
label | RECORD OF CONFORMITY: ITP Signed
label | IP
label | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
date | Date Completed:
section | 3 - Testing
checkpoint | 3.1 - Compaction
label | FREQUENCY: Per Lot
label | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
label | ○ 94.0% or greater Accept lot
label | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
label | For layers ≥50mm, if characteristic thickness is:
label | ○ 96.0% or greater Accept lot
label | ○ 91.0% to 95.9% Lot may be accepted at reduced rate
label | REFERENCE DOCUMENTS: Table 407.221
label | INSPECTION/TEST METHOD: Verify
label | RECORD OF CONFORMITY: Test Report
label | TP
label | RESPONSIBILITY: Site Engineer/ FH Lab Technician
date | Date Completed:
checkpoint | 3.2 - Level Conformance
label | FREQUENCY: Per 4,000m2 at completion of work
label | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
label | REFERENCE DOCUMENTS: Table 407.232
label | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
label | RECORD OF CONFORMITY: Survey Conformance
label | SCP
label | RESPONSIBILITY: Site Engineer/ Surveyor
date | Date Completed:
checkpoint | Final Inspection
note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
textbox | Print Name:
textbox | Position:
date | Date: