## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Flood Recovery Combined | itp |  |  |  |  | ITP - Flood Recovery Combined - v1
section | 1.0 - PRELIMINARIES – PROJECT MANAGER RESPONSIBILITY
checkpoint | 1.1 - Possession of Site
label | RESPONSIBLE - RCC
label | REMARKS - Date of possession: 22/04/2025
checkpoint | 1.2 - Dial Before You Dig (DBYD) and Permit to Excavate completed and signed onto by personnel
label | RESPONSIBLE - RCC
checkpoint | 1.3 - Confirmation of Scope and Extent of Works with Project Team, including RCC and BySC
label | RESPONSIBLE - RCC
label | INITIAL - JH
label | REMARKS - BySC Scope Agreed: 22/04/2025
checkpoint | 1.5 - Traffic Control – TGS approved and appropriately selected for the works
label | RESPONSIBLE - BySC
label | INITIAL - JH
label | REMARKS - BySC: 22/04/202
checkpoint | 1.6 - Erosion and Sediment Control:
bool | Silt Boom
bool | Earth Bund /Sediment Fence
bool | Other
textbox | Other:
label | RESPONSIBLE - RCC
section | 2.0 - C213 EARTHWORKS
checkpoint | 2.1 - Minor clearing of vegetation undertaken – where applicable.
label | RESPONSIBLE - RCC
checkpoint | 2.2 - Demolition works / Spoil Removal undertaken and spoil removed from site to Quirks Quarry.
label | RESPONSIBLE - RCC
checkpoint | 2.3 - HOLD POINT: If unsuitable is encountered BYSC to be notified prior to works continuing
label | RESPONSIBLE - RCC
textbox | REMARKS - BySC Direction:
holdpoint | HOLD POINT
checkpoint | 2.4 - Table drains shaped to allow water to flow freely and best marry into existing surfaces.
label | RESPONSIBLE - RCC
section | 3.0 - CTB Pavement
checkpoint | 3.1 - HOLD POINT: Proof roll subgrade: If foundation fails BySC to be notified and to provided direction
label | RESPONSIBLE - BySC
textbox | REMARKS - BYSC Approval:
holdpoint | HOLD POINT
checkpoint | 3.2 - Road base Material: Material source along with conforming material NATA test certificates have been submitted and approved by the Principal (Material Stockpile Lot)
label | RESPONSIBLE - RCC
checkpoint | 3.3 - If testing required - Layers compacted to 100% Standard compaction for full formation width. Compaction testing to be done 1 test per 500m2, minimum of 3 test taken at a time (per lot) or as directed otherwise.
label | RESPONSIBLE - RCC
checkpoint | 3.4 - Deep lift CTB of minimum 2.8% @ 150mm required
label | RESPONSIBLE - RCC
checkpoint | 3.5 - HOLD POINT – Carry out a proof roll of finished pavement where applicable
label | RESPONSIBLE - BySC
textbox | REMARKS - BYSC Approval:
holdpoint | HOLD POINT
section | 4.0 - ROCK REVETMENT
checkpoint | 4.1 - Geotextile – A34 Geotextile separator placed prior to rock placement IF DIRECTED or WITHIN SCOPE
label | RESPONSIBLE - RCC
checkpoint | 4.2 - Rock Placement - Rock to be placed in completed drain profile as per agreed scope.
label | Correct Rock Size Placed:
bool | 40-70mm
bool | 150-300mm
bool | 300-500mm
bool | 600-900mm
bool | Other
textbox | Other:
label | RESPONSIBLE - RCC
checkpoint | 4.3 - GROUTED ROCK PITCHING:
label | ○ Existing rock to be grouted as per agreed scope.
label | ○ Rocks to be cleaned down at end of grouting for neat finish
label | RESPONSIBLE - RCC
section | 5.0 - CONCRETE WORKS
checkpoint | 5.1 - EXCAVATION AND PREPARATION
label | ○ Suitable subgrade material and prepared to suitable surface
label | RESPONSIBLE - RCC
checkpoint | 5.2 - FORMWORK AND REINFORCEMENT
label | ○ Dimensions and positions of forms shall be carefully checked after the forms are erected. Forms shall be aligned accurately and the location of all fittings, hold formers etc. checked prior to placing of concrete.
label | ○ Placing of reinforcement as per agreed scope, with reference to Typical Construction Details. Reinforcement to maintain a 50mm vertical and horizontal cover unless directed otherwise.
label | RESPONSIBLE - RCC
checkpoint | 5.2.3 - HOLD POINT – PRE-POUR INSPECTION The formwork shall be inspected by the Superintendent, and the placing of reinforcement in the spaces formed, where specified, shall not commence until the formwork is approved by the Superintendent.
label | RESPONSIBLE - BySC
label | REMARKS - BySC Approval: Send photos to BySC PM of rock armouring prior to pouring of concrete
holdpoint | HOLD POINT
checkpoint | 5.3 - READY MIX CONCRETE
label | ○ The concrete shall be mixed and delivered in accordance with the requirements of AS 1379 relating to: -
label | Concrete Mix Used:
bool | 20/20/80
bool | 25/20/80
bool | 32/20/80
bool | 32/20/100
bool | 40/20/80
bool | Grout
bool | Shotcrete
bool | Shotcrete w/ poly-fibre
bool | Other
textbox | Other:
label | RESPONSIBLE - RCC
checkpoint | 5.4 - CONCRETE PLACEMENT
label | ○ The freshly placed concrete compacted by continuous spading, slicing or by vibrator units. Exposed surfaces of the concrete shall be struck off and finished with a wooden float. Corners and edges should be as per the drawings.
label | ○ Surfaces are floated, finished and cured as required to a quality finish. Broom finish as required.
label | RESPONSIBLE - RCC
checkpoint | 5.5 - TESTING – WHERE REQUIRED
section | 7.0 - CLOSE OUT
checkpoint | 7.1 - SITE HANDOVER: All works complete, demobilised and site handed back to BySC
date | REMARKS - Date of handback:
holdpoint | BySC Signature:
checkpoint | 7.2 - Verify conformance including close out of NCR’s
label | Records:
bool | NATA Certificates
bool | Survey Report
bool | Geotechnical testing reports
bool | Concrete test reports
bool | Proof of works report
bool | Photographs of completed work
label | RESPONSIBLE - RCC
textbox | REMARKS - NCR No:
checkpoint | 7.3 - Damage No. (DM) signed off and closed by PM or representative
textbox | Name:
textbox | Title:
label | RESPONSIBLE - RCC
holdpoint | Signature:
checkpoint-no-status | Additional Comments:
checkpoint-no-status | Variations to Scope
checkpoint-no-status | Typical Construction Details