## Sheet1
Form 087 Quality Assurance Form - Inspection and Test Plan
Work Order Number:
Product Description:
Date of Manufacture:
W: Witness H: Hold Point where work does not proceed unless approved R: Review M: Monitoring X: Self inspection by performer of work
ITEM | Description of Activity | Specification/Control Documents | Acceptance Criteria | Verifying Documents | Inspection By | Inspection By | Inspection By | Inspection By
[5 empty] | MJB | Customer
Preliminary Activities
1 | Review Work Instruction | Scope of works | All work instruction documents and drawings to be reviewed. | Approved Drawings | R
Customer order
Client supplied drawings
Precast shop drawings
Lifting design drawings
2 | Certification of lifting points/ cast in items | AS/NZS 4671 | All materials to be new and free of defects. All materials to have manufacturer/supplier test certificates supplied. | Lifting Drawing certified by Ancon | H
AS 3679
AS 3850
AS 4680
3 | Concrete mix design | AS 3600 | Concrete Mix design meets requirement S50 MRWA Mix (MJBMRWAS50) as approved. | Mix design | H
Historical records
4 | Pre-Inspection Meeting |  | To promote and coordinate effort by Contractor and Vendor |  | W
Materials
5 | Assemble reinforcing cage | MJB Production Drawing | Drawings are available, bars placed as shown on MJB Production Drawing. | MJB Production Drawing | X
Pre-Pour
6 | Set up formwork/moulds | AS 1597 | Formwork is suitable for surface finish. | This ITP | H
|  | AS 3610 | Dimensions checked in accordance with MJB production drawings. Refer Table 2.7 Dimension Tolerances.
7 | Apply form release | AS 1597 | Applied prior to pouring | This ITP | H
AS 3600
AS 3850
8 | Installation of reinforcing | AS 1597 | Cover and location of reinforcement checked. | This ITP | H
AS 3600
AS 3850
9 | Installation of cast-in items (Lifting Pins, Ferrules etc) | AS 1597 | Cover and location of cast-in items checked. | This ITP | H
AS 3600
AS 3850
Batching Concrete
10 | Concrete testing | AS 1379 | Compressive strength test. Minimum 28 day compressive strength for S50 is 58 Mpa. Testing required every 20m3. | Concrete Test Report | H
|  | AS 1012 | Slump Testing. Slump = 160mm ±40mm
Concrete Placement, Handling & Finishing
11 | Pour concrete | AS 3600 | Correct concrete supplied | Concrete delivery docket | X
Concrete temperature between 10-32 degrees Celsius at discharge. Freefall distance less than 2m
12 | Finishing | AS 1597 | Finish level to be trowelled as per AS 3610 | Visual Inspection | X
AS 3600
AS 3610
Post Pour
13 | Remove from mould | AS 1597 | Dimensions, lifting points and visual appearance are correct and within tolerance. Minimum of 20MPa or 3 days, whichever is earlier. | MJB Work Instruction | H
AS 3600
14 | Curing | AS 3799 | All precast concrete cured by Master Builders Solutions Masterkure CC 100WB | MJB Work Instruction | X
Repairs (if required) and storage of product
15 | Identify and repair defects | AS 3610 | Identify defects, complete repairs as directed by MJB work instructions. | MJB Work Instruction | X
AS 1597
16 | Final inspection and storage of items | Australian Standards | All items inspected, approved product have quality tick, moved to storage area prior to despatch. | MJB Quaity Tick on product. | H
17 | Quality Documentation |  | MJB quality documentation to be forwarded to customer | Quality Documentation | H