## Table 1
ITEM | PROCESS DESCRIPTION IN SEQUENCE | QUALITY CONTROL ACTIVITY & RESPONSIBILITY | ACCEPTANCE CRITERIA |  | VERIFICATION | INSPECTION ACTIVITY
|  |  | REFERENCE/STANDARD | CLAUSE | RECORDING DOCUMENT | ACTIVITY | ACTIVITY | ACTIVITY
1 | PRE-START
1.1 | Technical specifications & Construction drawings | Review the Technical Specification(s) and client supplied construction drawings for requirements | Structural Specification Client IFC drawings | All | — | P | P | —
1.2 | Receipt of Approved Construction Drawings | Shop drawings (fabrication drawings) showing details for all steel elements shall be prepared and submitted to the Clients Engineer no less than 14 working days prior to commencing fabrication, the review process shall be completed prior to commencement of fabrication | AS/NZS 5131 AS1100, AS 1101.3 Structural Specification | 4.4 All 9.6 | Drawings and document revision review | R | R | H
2 | PROCEDURES AND DOCUMENTS
2.1 | Quality Management System | ISO 9001 & AS NZS 3834 certification is current | ISO 9001 AS/NZS ISO 3834 | All All | — | — | R | —
2.2 | SFC Certified | SFC Certification to be current and minimum CC2 as per construction category, if non SFC contractors are to be utilised for structural steel fabrication, approval from the design engineer is required | AS/NZS 5131 Structural Specification | 4.1 10.2.1 / 9.8 | — | — | R | —
2.3 | ITP | ITP to be developed and approved, ITP to be submitted to design engineer for review prior to commencement of fabrication | AS/NZS 5131 Structural Specification | 9.3 | — | H | H | H
3 | MATERIALS
3.1 | Procurement of materials | Structural steel material is to be procured from mills with third party product certification schemes such as ACRS accredited mills with ILAC accreditation, any steel that does not meet this criteria shall have verification testing completed in accordance with the requirements of SCNZ report 111:2018 section 5, all steel conformity paths and verification testing results shall be submitted to the design engineer/construction reviewer for approval | AS/NZS 5131 NZS 3404: 1997 Structural Specification | 5.3.1 2 9.8.1 | — | H | H | H
3.2 | Inspection of delivered materials and test certificates | On delivery of materials, Inspection of materials will be undertaken to ensure they match the purchasing requirements and that the material certificates comply with project specific requirements | AS/NZS 5131 | 4.7 & 5.2 | — | P | H | —
3.3 | Marking | After checking incoming materials, the materials will be marked with the PO number, The Project/Job number and heat number | AS/NZS 5131 | Section 5.2 | — | P | C | —
3.4 | Traceability | Construction Category CC2 ‘Basic traceability’ is required, material certificates and nests to be collated and supplied in the MDR with associated material certificate register providing traceability requirements | AS/NZS 5131 | 4.7 & 5.2 | — | P | P | —
4 | Production
4.1 | Cutting | Steel may be cut by sawing, shearing, cropping, machining, or thermal cutting. All corners and edges on steelwork to be painted or galvanized shall be ground to a minimum radius of 2mm. No edges are to be sheared in areas designated as yielding regions for seismic design. Site cutting and hand gas cutting is not permitted, unless approved by the Engineer. | AS/NZS 5131 Structural Specification | 6.5 10.2.2 | — | P | C | —
4.2 | Holing | Holes for bolts shall be drilled or machine cut, slotted holes are not to be used for connections other than those documented in approved drawings | AS/NZS 5131 Structural Specification | 6.7, 6.13 10.2.8 | — | P | C | —
4.3 | Re-entrant corners | Re-entrant corners to have a minimum 10mm radius, a re-entrant corner being any corner in which the open angle between cut faces is less than 180 degrees | AS/NZS 5131 | 6.5.3 | — | P | C | —
4.4 | Splicing of members | All members shall be cut to the lengths required and to be of one length without welding, unless approved by the Engineer. | Structural Specification | 2010-02-02 | — | — | — | —
5 | ASSEMBLY
5.1 | Fit up and dimensional checks | Checks are to be made prior to any cutting or welding taking place and on completion of welding of individual items and completed fabrication | AS/NZS 5131 | 6.9, 6.10, Appendix F | — | P | R | —
5.2 | Weld Access holes | Weld access holes shall be in accordance with AS/NZS 5131 section 6.7.7 and approved by the design engineer, where there is any doubt referral back to the design engineer is required | AS/NZS 5131 | 6.7.7 | — | P | C | —
5.3 | Temporary attachments | Temporary attachments to be ground flush and tested with magnetic particle examination | AS/NZS 1554.1 | 5.9 | — | P | C | —
6 | WELDING
6.1 | Welding procedures to be approved | CEC Welding Inspector shall review and approve welding procedure specifications to ensure they are suitable for the joint type, material, welding consumables and process to be used | AS/NZS 1554.1 Structural Specification | Section 4 | WPS Register | — | H | H
6.2 | Welding Consumables | Welding consumables to be used as stated on the relevant WPS and stored in accordance with the requirements of AS/NZS 5131 and manufacturers recommendations as applicable | AS/NZS 5131 AS/NZS 1554 Structural Specification | 7.5 All | Welding Consumables Register | P | R | —
6.3 | Welder Qualifications | CEC Welding Inspector shall review and approve welder qualifications to ensure they are suitable for the welding being undertaken | AS/NZS 2980:2018 AS/NZS ISO 9606: 2017 Structural Specification | All sections | Welder Qualification Register | — | H | H
6.4 | Welding Traceability | Welding traceability to be provided by welders ID recorded adjacent to the weld and on the workshop drawing in the production check point stamp, this shall then be transferred to the welding and fabrication inspection record by the welding inspector | AS/NZS 5131 | 7.4.2 & table 7.4 | — | P | P | —
6.5 | Weld Category | All welds are category SP ‘structural purpose’ | AS/NZS 1554.1 Project Drawings Client IFC Drawing | All General Notes | — | P | R | —
7 | POST WELD INSPECTION
7.1 | Welding Inspection Requirements | 100% Visual examination of all welds | AS/NZS 5131 Structural Specification | Appendix I 10.2.5-Table 11 | Visual Inspection Report | — | H | W
7.2 | In-House Visual Welding Inspection | CEC Welding Inspector to undertake all visual welding inspection requirements, with minimum qualifications as stated in section 7.2 of AS/NZS 1554.1 and the structural specification | AS/NZS 5131 AS/NZS 1554.1 Structural Specification | 13.6.1.3 4.12, 7.2 10.2.5-Table 11 | — | — | P | —
8 | NON-DESTRUCTIVE (NDT) and DESTRUCTIVE TESTING
8.1 | NDT requirements | 10% Ultrasonic testing of all butt welds. Non-visual examination requirements as per AS/NZS 5131 and AS/NZS 1554.1. NDT to be supplied by an IANZ accredited test laboratory | AS/NZS 5131 AS/NZS 1554 Structural Specification | Appendix I Section 6 10.2.5-Table 12 | NDT Request NDT Reports | H | H | W
8.2 | Weld Defects | All weld defects revealed by visual examination or NDT shall be repaired with the same process as used in the initial weld and subject to at least the same method/type of NDT method undertaken that revealed the defect | AS/NZS 5131 AS/NZS 1554 | 13.6 6.7 | — | P | C | —
9 | FINAL INSPECTION AND DOCUMENTATION
9.1 | NCR | Non-conformances to be closed out prior to practical completion | ISO 9001 | All | — | H | H | —
9.2 | Manufacturers Data Report (MDR) | Compile all quality documentation as required by the specification and submit to client | AS/NZS 5131 | Appendix E | — | R | P | R
10 | SITE ERECTION
Refer to separate site erection ITP