## Table 1
ITEM | PROCESS DESCRIPTION IN SEQUENCE | QUALITY CONTROL ACTIVITY & RESPONSIBILITY | ACCEPTANCE CRITERIA |  | VERIFICATION | INSPECTION ACTIVITY
|  |  | REFERENCE/STANDARD | CLAUSE | RECORDING DOCUMENT | ACTIVITY | ACTIVITY | ACTIVITY
1 | PRE-SITE INSTALLATION/ERECTION
1.1 | Compile Site Delivery Schedule/Truck Lists | Truck Lists/Delivery Dockets to be maintained, fabricated components to be delivered to site in such a sequence to minimize time for erection and exposure to potential damage | ISO 9001 | CEC QMS | — | P | — | —
1.2 | Drawings and document revision review | Drawings showing details for all steel elements shall be prepared and submitted to the Clients Engineer no less than 14 working days prior to commencing site installation | AS/NZS 5131 AS1100, AS 1101.3 Structural Specification | 4.4 All 9.6 | Drawings and document revision review | R | R | H
1.3 | Erection Sequence Methodology | Confirm erection methodologies and install sequence, Fabricated steelwork shall be delivered to site in such sequence as shall minimise time for erection, and exposure to potential damage | AS/NZS 5131 | All | CEC Erection sequence Methodology | P | — | —
1.4 | Bolting procedure | Installation of all high strength structural bolts to be carried out in accordance with CEC SOP – “Installation of High Strength Structural Bolts” | CEC SOP 02-037-01 | All | — | — | — | —
2 | MATERIAL RECEIPT
2.1 | Material Check | Check for any damage to delivered assemblies/components or products and report all non-conforming materials to CEC Quality department, any non-conforming assemblies/components or products to be segregated/quarantined, NCR to be raised as applicable. | AS/NZS 5131 ISO 9001 | 5 All | — | P | R | —
2.2 | Material Storage | Store products to avoid visual damage, environmental damage, mechanical damage and distortion. | AS/NZS 5131 Structural Specification | 6.11 & 11.5.6 3411.3.2 | — | P | R | —
2.3 | Bolts, Nuts & fasteners | All bolts, nuts and washers are to comply with AS/NZS 1252:2016, inclusive of verification testing by the manufacturer or supplier, any bolt assemblies supplied to the previous version of this standard shall have verification testing completed in accordance with appendix A of SCNZ practise note MAT1010 by the manufacturer or supplier | AS/NZS 1252 AS/NZS 5131 Structural Specification SCNZ MAT 1010 | All 5.5 9.8.2 | — | R | R | —
2.4 | Threaded Rod | All threaded rod is to comply with the requirements of SCNZ MAT 1011 including verification testing completed in accordance with appendix A by the manufacturer or supplier, unless otherwise approved by the design engineer | Structural Specification | 9.8.3 | — | P | R | —
3 | INSTALLATION AND ERECTION
3.1 | Snug Tightening of Bolts | Snug tightening shall proceed from the stiffest part of the connection towards the free edges, snug tightening to be achieved by a few impacts of an impact wrench or by the full effort of a person on a standard spud wrench | AS/NZS 5131 CEC SOP 02-037 | Section 8 | Bolting Records | P | — | —
3.1 | Tensioning of Bolts | Type /TB and /TF bolts are to be tightened using either the part-turn method or load indicating washers. Where the part-turn method is used, the nut and shank are to be clearly marked to allow easy visual identification of degree of turn. Bolt Tensioning is to be monitored by a suitably qualified person. Tensioned bolt heads to be permanently marked by tensioning crew when compliant. Bolt tensioning records to be compiled released as areas are completed. | AS/NZS 5131 Structural Specification | Section 8.5 11.2.2 | Bolting Records | P | R | —
3.3 | Chemical Anchors | Chemical anchors to be installed in accordance with the manufacturer’s instructions. All anchor holes shall be cleaned out using water and a mechanically powered brush to ensure that no concrete dust or paste residue remains prior to insertion of the epoxy grout. Raise RFI’s and confirm remediation methodologies If correct embedment cannot be achieved | AS/NZS 5131 Structural Specification | — | — | P | R | —
3.4 | Proof Testing of Chemical and Mechanical Anchors | Chemical and mechanical anchors to be proof load tested at the specified load and testing rate. Prior to installing shear brackets, 3 x test anchors shall be installed in the deck soffit using This installation methodology: following curing of the epoxy adhesive, pull out tests at a load of 30kn (approximately 80% of ULS tensile load capacity of anchors) shall be undertaken. Anchor load (pressure gauge) to be monitored during pull out test, and if anchors are failing prior to 30kn, load achieved and pull-out force at time of failure is to be recorded. Results to be submitted for engineer's review and further advice. For the shear bracket anchors to be installed, clear quality assurance documentation for all anchors is to be submitted to the engineer for review. After testing, test anchors to be cut off flush with concrete surface and two coats of zinc rich paint applied to cut surface for corrosion protection (Resene Armourzinc 110 or similar approved). | Structural Specification General Notes drawings | — | — | P | R | —
3.6 | Stiffener Cutting Methodology | Cutting methodology to existing stiffeners shall be provided to design engineer for approval. All care must be taken to avoid damage to the girder. | Drawing General Notes | — | Methodology Statement | H | R | —
4 | SITE DIMENSIONAL CHECKS
4.1 | Site Dimensional Checks | Dimensional documentation to be submitted in MDR of erected structural steelwork to verify the structure and components have been installed as defined on the Project Drawings to the tolerances defined in AS/NZS 5131. | AS/NZS 5131 | 11.3 & Appendix F | — | H | H | —
4.2 | Tolerances | Erection tolerances shall conform to the requirements of AS/NZS 5131, the tolerance class for functional tolerances shall be Class 1 UNO on the project drawings. | AS/NZS 5131 | Appendix F | — | H | R | —
5 | SITE WELDING
5.1 | Chemical Composition Testing | Chemical composition testing in accordance with AS/NZS 1050 shall be carried out on the existing steel to determine the material composition. Culham Engineering shall review chemical composition results and develop a welding procedure appropriate to the material composition. | Structural Specification | 2010-02-04 | — | H | H | —
5.2 | Welding Procedure Specifications | Welding procedure specifications shall be prepared by Culham Engineering and approved by the Welding Inspector then submitted together with any necessary test certificates | AS/NZS 1554.1 Structural Specification | All 10.2.4 | WPS Register | R | H | —
5.3 | Welder Qualifications | CEC Welding Inspector to review all welder qualifications prior to welding taking place | AS/NZS 1554.1, AS/NZS 2980, AS/NZS ISO 9606 Structural Specification | All | Welder Qualification Register | R | H | —
5.3 | Welding Consumables | Welding consumables to be used as stated on the relevant WPS and stored in accordance with the requirements of AS/NZS 5131 and manufacturers recommendations as applicable | AS/NZS 5131 AS/NZS 1554 | 7.5 All | Welding Consumables Register | P | R | —
5.4 | Paint Removal Before Welding | Paint on the existing structure at weld locations shall be removed prior to welding. | Drawing General Notes | — | — | H | R | —
5.5 | Weld Defects | All weld defects revealed by visual examination or NDE shall be repaired with the same process as used in the initial weld and subject to at least the same method/type of NDE method undertaken that revealed the defect | AS/NZS 5131 AS/NZS 1554 Structural Specification | 13.6 6.7 10.2.6 | Weld Control Record | P | H | —
6 | INSPECTION
6.1 | Visual inspection of completed welds | 100% visual scanning of all welds, 100% visual examination of all welds to be complete by Culham Engineering certified welding inspector | AS/NZS 5131 Structural Specification | Appendix I | Visual Inspection Report | — | H | —
6.2 | NDE requirements | 100 % Ultrasonic Testing of Complete Penetration Butt Site Welds. | AS/NZS 5131 AS/NZS 1554 Structural Specification | Appendix I Section 6 | Weld Control Record NDT Reports | — | H | —
6.3 | Bolting Inspection | Inspection of all bolted connects shall be performed, all bolts shall be the correct size and grade, and be tightened and marked in accordance with the requirements | AS/NZS 5131 Structural Specification | Section 13.7 | Bolting Records | P | R | —
7 | RELEASE AND HANDOVER
7.1 | All Non-Conformances and Remedial work Closed Out | All relevant CEC and Sub Contractor quality records audited any non-conformances relating to the project are closed | ISO 9001 | CEC QMS | — | H | H | —
7.2 | Site is Clean and tidy | All rubbish, construction materials equipment and tools removed from site | Contract Requirement | — | — | P | — | —
8 | FINAL INSPECTION AND DOCUMENTATION
8.1 | Construction Producer Statement (PS3) | Project manager or nominee to complete the construction producer statement(s) in accordance with the local territorial authorities’ requirements | Structural Specification | — | — | H | H | —
8.2 | Manufacturers Data Report (MDR) | Compile all quality documentation as required by the specification and submit to client | AS/NZS 5131 | Appendix E | — | R | P | —