## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Resource Id
| checklist | ITP-004 - Underground Drainage | itp | ITP-004 - Underground Drainage | c6237bdd-ebd4-47f6-aabf-2398893739d9
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Obtain MOA and Traﬃc Management Plans. Ensure Traﬃc Management Plan is adhered to.
ef182760-a2b0-566e-b6dc-50630b8bdc36 | note | FREQUENCY: Prior to commencing works
06756991-7972-5028-a973-c420311fba16 | note | ACCEPTANCE CRITERIA: Refer to the VicRoads Traﬃc Management speciﬁcation 166
130f1776-5fc8-5401-b80d-85727a25e024 | note | REFERENCE DOCUMENTS: Traﬃc Mgmt. Plan
bc010f64-7f9a-5b8e-9b26-c6b44ad5d89b | note | METHOD: Visual Inspection
753c1780-808c-59a8-a028-92b5b4eba4d7 | note | RECORD: Signed ITP
0ce8c081-be2e-5bfb-9257-014df7c2255b | note | IHP
05638e1d-e663-5eb9-a6dd-bcf411e06e8b | note | RESPONSIBILITY: SWA Project Manager
799cca7f-5acf-5446-85dd-155f5fd7332a | date | Date Completed:
| checkpoint | 1.2 - Purchase of pre-cast pits, pipes and end-walls
2bd8d3c1-52bb-55ab-98a3-57d47d7f8b32 | note | FREQUENCY: Approval prior to placement of order
f5e54773-2368-5eda-9f28-cd6c5d6726ce | note | ACCEPTANCE CRITERIA: Refer to Construction Drawings
d7367779-92c4-500a-8ea9-dd0d4c927163 | note | REFERENCE DOCUMENTS: Vic roads Standard drawings
3154322a-9033-5969-a11a-380938b2f6a4 | note | METHOD: Review and approval of documentation, Visual inspection
0b538252-fbb8-5f38-8bf1-7aeb3d684af6 | note | RECORD: Signed ITP
e6c1293b-6acb-599d-bebe-adec0bbbf8c8 | note | IHP
744cdc87-2389-5363-a51a-e6e4808f3842 | note | RESPONSIBILITY: SWA Project Manager
713258dd-f8dc-59c3-82e3-0b7d1ef7db45 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - CONFORMITY WITH DRAWINGS - The Contractor shall set out the drainage work in accordance with the drawings or as speciﬁed.
7acbc719-26ff-560a-8b74-1c8fdf4b4698 | note | FREQUENCY: Each lot as required
1ba4cf9e-2d45-5eaa-8151-7b598fa23b5d | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the culverts the Contractor shall conﬁrm the position of all culverts with the Superintendent.
e7701963-566c-52fa-9e6d-32549f9529a1 | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
635b1039-6b7c-5ab7-b39f-7fd442f57e43 | note | METHOD: Construction Drawings
e70b9052-10f0-573b-81c0-333e1be5616e | note | RECORD: Signed ITP
ff99b250-ba56-54b0-886e-33a52f4ab63e | note | IHP
7eb7538b-abd7-5023-b9d0-2d63bfb1c5dd | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
3d172417-6ca0-572f-8217-eb533db51cdf | date | Date Completed:
| checkpoint | 2.2 - CONFORMITY WITH DRAWINGS – The culverts constructed shall be constructed true to line and level
6d732245-4e64-5a9c-a099-ab348c43152f | note | FREQUENCY: Each Lot
f55415e5-d355-5583-ac27-035a1490b805 | note | ACCEPTANCE CRITERIA: Unless speciﬁed otherwise the tolerance on location of pipes compared to the design or a change to the design notiﬁed in accordance with this clause shall be:
ea115b19-af91-56ec-8498-d32a6e86a20c | note | (a) oﬀset of entry pits required to match lines of kerbs or barriers ±20 mm
e2274cff-7adc-5155-9853-97bf4a4a5baa | note | (b) plan location of pits other than oﬀsets to kerb lines or barriers ±100 mm
98d4c065-d360-52cf-8431-af8b9b3dcddd | note | (c) invert level of pipes at pits ±50 mm (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:250
c4b72f68-f6b1-566f-be3d-cc606c8205cc | note | REFERENCE DOCUMENTS: Vicroads std sec 701.09
a3b85459-add5-507b-9b9a-03db3d9cf8d9 | note | METHOD: Construction Drawings
f3f230c3-21cb-50a3-a899-eb1907e81145 | note | RECORD: Signed ITP
97df6d56-5607-566c-9631-3a1e17a11c56 | note | IHP
75252ec4-ba17-5e13-95ce-d96a2f57bb0e | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
74112e77-bfd5-5a4c-add7-70db54f092f3 | date | Date Completed:
| checkpoint | 2.3 - EXCAVATION
251b1328-5c52-5707-9680-8f19ae6307f2 | note | FREQUENCY: Each Lot
f22ebd74-e1c7-5603-ac14-32781a39a6b5 | note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm
7d7128fd-e0bd-51d2-a24e-46f4da9d3c6b | note | REFERENCE DOCUMENTS: VicRoads Std Specs 701.14
5a856166-d33c-5bb5-a571-6702c7bedae9 | note | METHOD: On-site Measurement
fd6b0db2-ef5e-5a93-b4bb-c9262650ccfd | note | RECORD: Signed ITP & Drainage Checklist
9bf71b55-11ba-50d9-b8eb-7881329986b5 | note | WP
2fd9193f-2415-5d63-9495-3b08167d4d30 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
46116078-bf8b-5eb8-8467-0d7b78cb5ad3 | date | Date Completed:
| checkpoint | 2.4 - CULVERT BEDDING - Bedding material shall be provided and placed for the full width of the trench or, where the culvert is to be placed without trenching, to a width 0.8 m greater than the overall width of the culvert
42bb4442-513f-5cc5-915a-00fcd9741912 | note | FREQUENCY: Each Lot
6881588b-42a7-57cd-ac32-3df0eebace08 | note | ACCEPTANCE CRITERIA: The compacted thickness of bedding material following any shaping necessary shall be not less than:
049d5ab0-3954-53f2-9164-3e0ddc872a52 | note | ○ 100 mm where D < 1500 mm
d62509e7-b0db-5383-a1c5-f1a0ea59f27b | note | ○ 200 mm where D ≥ 1500 mm where D is the nominal pipe diameter or culvert width.
317b3065-9388-5bc0-ae63-427df2a02bc3 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.15
773ea527-b5a0-5691-8f7f-01b1719fe36e | note | METHOD: Site Inspection
318b0694-04a4-5df0-9588-b57fef7188d1 | note | RECORD: Signed ITP
d5745b38-6365-5c71-b4ac-4971977035ee | note | WP
32879b5a-a55c-5bf0-a043-253234f21230 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
54da8318-b275-5df2-8328-6dba7a8246c2 | date | Date Completed:
| checkpoint | 2.5 - PLACEMENT OF FILLING
447c1f96-cd99-51e1-b4b1-085091b5e93d | note | FREQUENCY: Each lot as required
4e712bce-8911-57fd-8746-72212bf4e9bf | note | ACCEPTANCE CRITERIA: (a) Unless the culvert is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
0d345166-f974-5ce4-864a-825cd9893bfd | note | (I) Culvert Under Area not to be Paved
b93605f5-9eff-51a2-bb6e-302bfdfda97d | note | ○ The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
b965a43d-110b-5e7b-a1e2-497df3169a9c | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.18
d7edc73b-2603-5421-8988-a8c4d891ed7d | note | METHOD: Site Inspection
314cce22-1f2f-55d8-b0bc-ed2d676b448a | note | RECORD: Signed ITP
72f7f5cf-49b4-52b2-9ad9-31eb7e601c90 | note | WP
c2cce175-2c6a-522d-bfca-3d7d6a96af99 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
39215f5c-4b26-5d89-83cd-25375fdbbfb1 | date | Date Completed:
| checkpoint | 2.6 - INSPECTION OF DRAINAGE LINES BENEATH PAVEMENTS
6643ab65-9b90-5ddd-96af-3c60760fcbaa | note | FREQUENCY: Each lot as required
dbd97b05-3512-5b84-9707-02e993e91e6f | note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV).
7575bc15-5348-5998-89f9-f23e78e3c03c | note | ○ Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
e60ffd2f-1269-52dd-9fd5-199855e53b84 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 701.28
21917ffc-8436-5615-b116-3ce1ad9a49af | note | METHOD: Visual inspection
ef884568-06bf-5f15-b20f-7aa266b540f9 | note | RECORD: Signed ITP
b455c61e-aba2-5115-9516-3f1e73592f9b | note | HP/AP
9e62fa93-21ed-5125-9f06-832d1f09169c | note | RESPONSIBILITY: Project Engineer/Clients Superinten dent
47288ec0-a934-54cc-80a3-60fa161d3f3a | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.7 - Where required installation of Geofabric or Jute matting and beaching material in swale drains
321fd623-007b-52aa-a79e-d4a6a6ed0a60 | note | FREQUENCY: After installation of pipes, pits, end-walls and placement of asphalt wearing coarse
688fff99-d9ba-57a4-9a8c-66fd9a85a2f2 | note | ACCEPTANCE CRITERIA: Rock used, should be an assortment of sizes where possible. The smallest rock size must be able to resist dislodgment in peak ﬂows. Rock shall be placed with a geo-textile liner.
191efa34-ee9b-5e1c-a13f-a82a4afb577d | note | REFERENCE DOCUMENTS: NIL
35c41066-398d-569a-9a93-d643518e2a75 | note | METHOD: Visual inspection
6dcfae5c-5cbd-54a8-bc26-54c858a6f7fb | note | RECORD: Signed ITP
ce381245-5782-5ad2-bb64-872458aaa8f8 | note | IHP
cd79132e-0b54-5f71-aa41-2c9198350f50 | note | RESPONSIBILITY: Project Engineer/Si te Supervisor
14449841-8e6c-54e5-9907-199d9bfe67c3 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - REQUIREMENTS FOR TESTING AND ACCEPTANCE OF COMPACTION AND MOISTURE CONTENT - Bedding and backﬁll materials shall be placed and compacted in layers not exceeding 150 mm loose thickness.
ad7ea4e0-3d8a-549c-a12d-33bfc5af6008 | note | FREQUENCY: 3 per Lot (A lot shall consist of one layer of bedding or backﬁll for a culvert length between adjacent pits or endwalls)
199aabd3-b885-562f-a7e7-cc52f2af4009 | note | ACCEPTANCE CRITERIA: (a) Bedding Bedding shall be compacted to refusal using hand held mechanical equipment. Bedding material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
4dffa674-2fd9-5478-b735-5a61ccfaf99e | note | (b) Backﬁll
b25e21dd-9fdd-5774-8cf2-88fff28caace | note | (i) Material of Nominal Size 40 mm or Less After Compaction Backﬁll material which will have a nominal size after compaction of 40 mm or less shall be compacted to a mean value of density ratio of not less than 97%. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
5164cba3-2397-540b-b0b9-5f9e5b54b09a | note | (ii) Material of Nominal Size Greater than 40 mm After Compaction Backﬁll material which will have a nominal size after compaction greater than 40 mm shall be compacted using a grading, mixing, watering and rolling procedure. Backﬁll material which has a swell equal to or greater than 2.5% shall be maintained at a mean moisture ratio of 92% between the completion of rolling and the placement of the overlying layer.
7c8d847e-507b-5ffc-88d1-dce337666c8c | note | REFERENCE DOCUMENTS: Vicroads std sec 701.19
ff22700d-a43a-5fd6-a8a4-2d1d221acdf0 | note | METHOD: Lab Test
124526e3-33d9-5a56-82c0-ef64da56765b | note | RECORD: Signed ITP
24ec6541-9256-5f2a-b008-5d188102d2bf | note | IHP
34afc8a9-3629-5e54-847e-15d753c1a4b4 | note | RESPONSIBILITY: SWA Project Manager
fd2de7a3-42a1-58be-af80-95624a5e5c67 | date | Date Completed:
| checkpoint | Final Inspection
f3e25195-8b96-559d-a51a-7bd6d992fd0e | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
e1814260-c74e-52e6-8261-6cb3145f5779 | textbox | Print Name:
56e603ae-4ab1-5344-966f-ba593fada043 | textbox | Position:
01c4d859-b669-5849-b271-07deefcdd1d6 | date | Date:
| signoff | Sign ITP
| checklist | ITP-006 - Kerb & Channel | itp | ITP-006 - Kerb & Channel | f1397304-f75d-469c-9986-3c4c4dacb6f0
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
1924891d-be8a-5cb0-bf40-93550bd87ea1 | note | FREQUENCY: Prior to commencing any activity
e10b2f3d-80b2-5e40-9cc4-1735a915f15b | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
1dae58cc-1017-548a-914a-df3e1c645ee2 | note | – using the correct and complete set of drawings
96628885-9c2d-5cad-9bfb-84a9fe6d671b | note | – all drawings are the latest revision
f38bf0d7-cf68-5ff9-9b7a-eae3319917c8 | note | REFERENCE DOCUMENTS: Vicroads std sec 100.6
dcfb40c7-2e61-50b0-8459-b34296206f94 | note | METHOD: Drawing Register
d2a98cd4-181a-5d01-8cc5-b64bdff74f6b | note | RECORD: Signed ITP
35f9e4af-77ad-57b0-9097-76611d6bb753 | note | IHP
593bcc06-0379-55ed-91f2-4d36eb8066bf | note | RESPONSIBILITY: Site Supervisor
4536d000-0847-5c2c-99e0-fe0817184a65 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
3cd28ec4-dbdd-54dc-a9aa-ecb4c6bfaeec | note | FREQUENCY: Prior to commencing any activity
f64016e6-fd04-5187-8786-033029fd097d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
dfcb33fc-7fd2-52a2-8967-a060ae16cc88 | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
87b17827-3eaf-5c1f-924a-9f461dee2b35 | note | METHOD: Visual Inspection
7a6ca9df-0e44-59e3-9c84-7ce5e4bd1b21 | note | RECORD: Signed ITP
d5efa8f4-237b-5722-81c8-4203985047cf | note | IP
b9ac02b3-9d56-5c14-b549-96a2d679dff9 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
14386575-4759-5c9a-8774-a1c741d6bfa8 | date | Date Completed:
| checkpoint | 1.3 - Setting Out
670be11c-62e6-53eb-8777-45b19578dd42 | note | FREQUENCY: Prior to commencing any activity
8d2ecea8-30de-5516-9f40-3d2687409024 | note | ACCEPTANCE CRITERIA: Chainage locations clearly identiﬁed for extent of kerb and channel by qualiﬁed surveyor. Oﬀset for lip of kerb alignment shall be set minimum of 1m from Back of Kerb (BOK) and with ﬁnished heights indicated on survey peg.
34567f1b-171a-5442-b435-1557416c58f9 | note | REFERENCE DOCUMENTS: Vicroads std sec 703.13
4ef3ebba-8910-5029-9ad2-818cf35673c6 | note | METHOD: Survey Setout
ba3ab739-64cf-5e17-b6ec-f1b783b2d20c | note | RECORD: Signed ITP
f36f59a8-dc03-5e0f-a8a7-1baac6ba73a4 | note | IP
8d0fea4f-d890-57fe-be93-774349e9da27 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
54995617-8aeb-59fd-bb7b-f730f3cf3773 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation
30e30c2a-17b5-56d2-ae2c-cdea3b9fabe3 | note | FREQUENCY: Check prior to placing material
0d24c930-0896-5d97-b4c4-1e3d1ac87c4d | note | ACCEPTANCE CRITERIA: The base preparation for kerb and channel shall consist of a boxed out area to a depth of 355mm below FL and 1150mm wide. Excavation shall not extend more than 150mm from the edge of the adjacent face.
5b7e9b35-f3dd-5916-b414-28958b6b7aef | note | REFERENCE DOCUMENTS: Vicroads std sec 703.20
58c4991e-d7d2-522f-8aa5-feaba55f7ac8 | note | METHOD: Survey/Site Inspection
53bd3631-5e9b-5ffc-a179-7a3477230f67 | note | RECORD: Signed ITP
774dde34-960c-5fdc-a974-6a66cda88944 | note | IP
20650f50-629f-5737-a0f2-9244b5a3fd6e | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
6bf0ae7f-449a-5b0b-a92d-995cde386e7b | date | Date Completed:
| checkpoint | 2.2 - Subgrade Inspection
29213c78-d6be-54f3-8643-0fbccc77807f | note | FREQUENCY: Check prior to placing material
54af3188-2410-5328-9f1a-d7834483095d | note | ACCEPTANCE CRITERIA: Test roll subgrade to check for No visual deformation or springing. Where deformation is exhibited, the Engineer or Superintendent is to be notiﬁed immediately.
665634af-e202-5339-b216-dcae1fc67668 | note | REFERENCE DOCUMENTS: Vicroads std sec 173.03, 173.03 (ii)
8b54c321-62dc-5e0e-8905-32f3377b25c5 | note | METHOD: Visual Inspection
8fe1e1bb-eace-5cdb-9fe4-60fd816c2cfd | note | RECORD: Signed ITP
39a00fc0-a455-5864-913e-07fa966b7d80 | note | IP
702ca4d4-3252-5e7f-a6f9-82e7b0724cf0 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
d3fb0aa6-5a15-5f40-bbf9-1d7134e64243 | date | Date Completed:
| checkpoint | 2.3 - Bedding Preparation
725f8d62-5171-5674-bc25-3ebd1ff5bd5e | note | FREQUENCY: Each lot as required
f24bd2f9-a487-5d05-97f7-729e02d9d960 | note | ACCEPTANCE CRITERIA: Bedding material to be used for base preparation shall consist of size 20mm Class 3 or Class 4 crushed rock at a minimum of 100mm compacted thickness. Preparation of ﬁnished base shall be 190mm below lip of kerb as per survey marks.
e668d52d-3801-5b6a-bc8d-b771bc6182a9 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21
0cba5a58-3fd6-50c3-905b-8ed80da1db33 | note | METHOD: Site Inspection
c2702dd5-af00-5d15-8698-e3a054b3b641 | note | RECORD: Signed ITP
4ffbfbe8-da8c-52b1-97b1-7853998a575f | note | IP
6a934fbb-4493-5b63-99c1-366dd3fa590f | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
d5440ea8-130a-5ff3-b34c-77e9853a851b | date | Date Completed:
| checkpoint | 2.4 - Kerb Concrete Mixture/Strength
643e64a0-ae04-5d9c-81a2-2108d15dc704 | note | FREQUENCY: Each lot as required
d11052cf-040c-5c27-8957-a3d0c5772349 | note | ACCEPTANCE CRITERIA: Traﬃc routes a minimum of or equivalent to 320kg of cementitious binder material or geopolymer binder per m3 of concrete – VR 330/32
b21b9a0f-ffcb-53a6-96e0-878c5f7956c0 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.05, 703.11
37f67980-20e0-529b-8a3d-60cc2edc41c4 | note | METHOD: Delivery Dockets
7dfe5364-f0c6-5bfe-b70b-91274a68d264 | note | RECORD: Signed ITP
a3e794b9-90f9-59c5-8869-a1c683add0f7 | note | IP
56216fc7-faad-5231-bbfc-796df51c0120 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
f92ddba5-c0ca-5a74-8edd-19f442811821 | date | Date Completed:
| checkpoint | 2.5 - Tolerances on Line, Level & Shape
64d2aed7-2784-52ae-9c0f-41a96ced58e3 | note | FREQUENCY: Each lot as required
d26ff4a8-8938-5038-b939-4ca9a5d8b663 | note | ACCEPTANCE CRITERIA: All surfaces shall be ﬁnished in conformity with the lines, grades, thicknesses and cross sections shown on the drawings or as speciﬁed. Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10mm. Except on curves or in shaped areas, the deviation of the ﬁnished work from a 3m straight edge shall not exceed 5mm at any point.
dd091a68-4fc4-5c33-9ac6-6f3a9bf957f7 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
3b6f85e9-3921-5fa8-8361-c6a345d61a6b | note | METHOD: Visual Inspection
4c3a1b5c-6150-58b3-afd8-8eeef14f4a54 | note | RECORD: Signed ITP
83ed74ef-569a-5f00-8231-1cb9c4b337d8 | note | IHP
b7e036f5-f046-5f1c-a9c5-b761071b9aeb | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
958ca1e2-1c6c-58e2-b248-7638bfab2209 | date | Date Completed:
| checkpoint | 2.6 - Kerb and Channel Finish
baa14357-8d8d-5966-8fef-264215190ef6 | note | FREQUENCY: Each lot as required
41e31629-fd0a-5ddc-bf6d-579a29ec722d | note | ACCEPTANCE CRITERIA: All edging shall consist of a smooth, uniformed and of a trowel ﬁnish. The mortar used shall consist of two parts of ﬁne aggregate, one part cement and suﬃcient water to produce a mix of suitable consistency. Thickness of the rendering shall not exceed 3mm.
2e7dfd62-9d89-5dd2-95a5-89c293701fbb | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.21 (a)
3bf75351-9c1e-5917-96e9-f2b42e230a55 | note | METHOD: Visual Inspection
e66668fe-7cc4-5efc-ac54-74082a2f97c4 | note | RECORD: Signed ITP
bd980ed1-d39e-5776-a759-303ac680aaf0 | note | IHP
1cb06024-62fb-5b24-9dcf-e12b8211a333 | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
2e134a92-6f78-57ec-a62d-83078f2e91d1 | date | Date Completed:
| checkpoint | 2.7 - Kerb Backﬁll
19d12ee3-b158-51a4-9f5f-88d960da18a3 | note | FREQUENCY: Each lot as required
8aa19a7c-7103-5f64-9f86-7f3361817918 | note | ACCEPTANCE CRITERIA: Once concrete has cured, topsoil which is free from perishable matter, shall be placed ﬁrmly compacted in layers less than 150mm thick and to a width of no less than 300mm behind the edging to the top of the edging.
1dfcb6c4-223b-54a9-87d7-866179eb89e6 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.29
585a96c3-4244-5873-9b05-0fe1ec63234a | note | METHOD: Visual Inspection
d6301af8-a37c-511d-8533-0747e9d9d537 | note | RECORD: Signed ITP
4d3bc362-df76-51f1-b4fe-8ec879406020 | note | IHP
d32ede4b-55b6-5642-b552-87feb5fe012d | note | RESPONSIBILITY: SWA Project Manager/Site Supervisor
b7e5b991-9d15-58f1-803a-5ebf19ec3f48 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Compaction Testing
82d263c5-1260-50fa-b38c-812c01147f84 | note | FREQUENCY: Each lot as required
078f003e-35be-5279-844f-ced829e34a76 | note | ACCEPTANCE CRITERIA: For work to be tested for compliance with Scale A or Scale B requirements, the number of tests per lot shall be six. A small lot is classed as an area equivalent to or less than 500m2 and requires only 3 individual tests. Compaction testing for crushed rock material shall be no less than 98%.
08cdfb11-78ad-5245-9522-d5fd6a4b11e1 | note | REFERENCE DOCUMENTS: Vicroads std sec 304.08 (b) Table 304.081, 173.04 (d)
ad5554af-3737-5ad9-a534-6bb511f07073 | note | METHOD: Test Point
6e84cd8b-17c1-53d4-b1df-54749d3dae79 | note | RECORD: Signed ITP
a12daeb8-cf1e-53e1-b390-7d91c3c094f0 | note | TP/HP/AP
28257342-aa78-56f5-9177-5ce3deabfd72 | note | RESPONSIBILITY: External Geo tester/SWA Project Manager/RRV Superintendent
548e1cbc-d9d9-5859-b0d3-633372a2216f | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 3.2 - Conformance Testing for concrete strength & consistency.
84413c19-5130-5e09-a2b9-ffaaf5556741 | note | FREQUENCY: Each lot as required
10d3917c-9070-5668-bad4-eda6af775211 | note | ACCEPTANCE CRITERIA: The minimum compression strength requirements for each strength grade shall be as shown in Table 703.111
6327af6a-5094-5d89-9652-f23d6dbbcc7f | note | REFERENCE DOCUMENTS: Vicroads std sec Table 703.111
d9c0b29b-89b1-56b1-a772-9009875ee291 | note | METHOD: Survey Report
e41cad1e-9883-5bc4-872e-ab5dfca53b19 | note | RECORD: Signed ITP & Test Reports
17623d2d-1497-5c9c-a835-f84f4cf08d67 | note | TP/HP/AP
7644abd1-439f-5c0a-a90c-fe352a060bbc | note | RESPONSIBILITY: External Surveyor/SWA Project Manager/RRV Superintendent
cda5571a-1856-5329-91e9-b2e83fde6035 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | Final Inspection
a87f89f5-f2e7-5b34-a2d0-249e9dadb342 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
ea88190b-bc66-5931-8b9b-571bb9b8b771 | textbox | Print Name:
03bc1384-f919-5538-8999-4474b950f039 | textbox | Position:
57ea1b44-0d0a-5ef7-a69a-31f523d319cf | date | Date:
| signoff | Sign ITP
| checklist | ITP-007 - Hot Mix Asphalt | itp | ITP-007 - Hot Mix Asphalt | 7ca115bb-e2e5-4c41-8f07-dbad4863f9a4
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Site Inspection and Base Conditions
22ca481a-b944-5e83-bfb7-28a351052113 | note | FREQUENCY: Prior to commencing paving.
c5bc9640-5df0-5ab5-ab01-eed230a82e32 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from surface water. All manhole and valve covers have been raised or lowered to the new surface level of the pavement.
4ebc9747-89d7-5786-af30-606cbb172eba | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.1
dff3d967-d3dd-576d-a961-68954bbfd51f | note | METHOD: Visual Inspection
d17abf9c-88d4-5e05-bf9d-7853bf6af01b | note | RECORD: Signed ITP
7fc64dc1-4619-50e7-8506-0077f490cdd5 | note | WP
381404e1-6bc2-5d0a-8c77-0ddc57b09728 | note | RESPONSIBILITY: Site supervisor
befbe481-363f-5145-ab7c-164fd4107b03 | date | Date Completed:
| checkpoint | 1.2 - Ambient Conditions for Asphalt Placement
ab458da5-97a5-5ca4-b9e8-0de7ec7cc85b | note | FREQUENCY: Prior to commencing paving.
ec6976ea-104d-5e6c-bc95-fc707089037c | note | ACCEPTANCE CRITERIA: Asphalt shall not be placed if the majority of the surface area is below:
bdcc1246-5a84-5244-8975-b341d45ac3e3 | note | ○ Base & Intermediate Courses: 5°C for conventional binders or 10°C for PMBs & Class 600
32def7ff-37fe-5273-8493-e1925566a767 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs.
c44b6f8a-5710-5f5e-983d-5e5eb11341fc | note | REFERENCE DOCUMENTS: Vicroads std sec 407.13
698bac0a-50c8-590b-a8d5-17ab33b66004 | note | METHOD: Calibrated thermometer
9b9125fb-9592-50e3-a084-afb8d043d43f | note | RECORD: Signed ITP
053cce18-bdc4-5b3e-bc97-4851200388eb | note | IP
46c7a54f-2d6d-5921-9b9f-323cae8c0075 | note | RESPONSIBILITY: Project Engineer/Site supervisor
f21e4d74-7a29-5f13-bb0e-98a55b43d208 | date | Date Completed:
| checkpoint | 1.3 - Surface Preparation
0e2980ba-4e5d-506a-97c3-c4db1c2abec2 | note | FREQUENCY: Prior to commencing paving.
15c898b7-c7f4-5433-894c-b388a1cb81de | note | ACCEPTANCE CRITERIA: The area to be paved is free of all loose and deleterious material
ccd21397-7570-505b-a284-2865f806f693 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.14, AS2150 10.3
48c5577e-adc0-5b9f-bdc0-d02b82496112 | note | METHOD: Sweep Clean and Inspect
d79cde4b-a101-50ee-9f27-f39f42634a1e | note | RECORD: Signed ITP
65289eea-48c1-5877-8fab-0cf18e533227 | note | WP
0676b451-0dd6-5e07-94e1-a60786129a60 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
4a88a2b1-f31c-535e-9eed-d7c215af86a8 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Application of Tack Coat
8f8c668a-f382-5205-8df5-17f9a039b362 | note | FREQUENCY: Prior to commencing paving
94b03e01-4a19-5f0b-b86d-6dfd4f0977d1 | note | ACCEPTANCE CRITERIA: Tack coat to be sprayed in a uniform ﬁlm over the surface area at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen). This rate is to be doubled on joints and chases. Tack coat must be allowed to turn from brown to black before paving. NOTE: Tack coat is not required on clean, freshly placed asphalt or primed surfaces or when the layer to be placed exceeds 50mm unless directed by the Client
1580f857-5474-5b5f-bbd3-366eb081769c | note | REFERENCE DOCUMENTS: Vicroads std sec 407.15, AS2150 11
4b5834db-c4e2-5f81-b63c-9a38c1549236 | note | METHOD: Visual Inspection & photo evidence
ac962381-74eb-55fb-a30d-2505831f3b90 | note | RECORD: Signed ITP/Spray Record
4755fed6-3ffd-57bd-9903-d765aba4dfc8 | note | WP
1932c9d7-56a5-516b-97e7-7a08beaec093 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
09eb695c-69d7-5f3b-885a-2102a73eaa04 | date | Date Completed:
| checkpoint | 2.2 - Planned Joints
28da8f20-3cd9-5b53-b841-b019cae6cb4d | note | FREQUENCY: Prior to commencing paving
fbdf6bcf-1b47-5240-983a-401876e7db71 | note | ACCEPTANCE CRITERIA: A site speciﬁc paving plan shall be generated by the contractor prior to asphalt commencement to adhere to the following: Transverse Joints: Oﬀset from layer to layer by at least 2m Longitudinal Joints: Oﬀset from layer to layer by at least 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines. Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an oﬀset from layer to layer of not less than 150mm.
34f063bf-41ef-5957-90aa-50b7608157a3 | note | REFERENCE DOCUMENTS: Vicroads std sec 407.17 (b) & (c)
b5a9edd8-15bd-52ba-a278-71ab47af67ab | note | METHOD: Measure and mark out runs and submit Paving Plan to Client if requested
10090cd0-915f-5e16-a773-4f2f42070f91 | note | RECORD: Signed ITP/Job Sheet
8d99cdfc-c369-53a8-b610-9eb904c70423 | note | WP
431398e2-5e98-5716-9b80-f09a5e9841ff | note | RESPONSIBILITY: Project Engineer/Site Supervisor
1ba8e084-2c6b-5885-b1f4-b672ddec418b | date | Date Completed:
| checkpoint | 2.3 - Commencement of Placing
83a0bba4-5b34-5b26-863f-03eea979290d | note | FREQUENCY: Prior to commencing Paving
cc5e127e-e04e-5808-9376-a413dd216dc4 | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub- base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Vicroads Superintendent.
73d90105-16cc-5532-9558-794ee0ff844d | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.18
53b9f824-f190-5dc4-82e3-5166450e8963 | note | METHOD: Visual Inspection
837efbab-58ef-5020-865f-d0483694d9a5 | note | RECORD: Signed ITP
c61e9359-0739-56c9-86f6-376fea96546c | note | HP
67357a49-4105-5b90-83a4-3e7f6d3b2665 | note | RESPONSIBILITY: SWA Project Engineer
08960694-f6d4-52eb-87e1-e7ffd359ba7d | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.4 - Delivery of Mix
c85e0baa-f6ba-5408-9612-af9031365c78 | note | FREQUENCY: Each Load
52376e84-ff07-57c5-bf22-15142dd63100 | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
2334f427-6089-522d-a552-43aad80d3909 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.16, Table 407.081
fd037b8b-4632-5699-93a4-62211bf07056 | note | METHOD: Visual Inspection & Delivery Docket
b6f7fe7c-a005-5576-aec9-b48295ad6e07 | note | RECORD: Signed ITP & Production Dockets
ff65e6cc-711f-590a-8ad4-726976849a99 | note | WP
d6b68d16-b28f-5767-be67-48be4acd9609 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
0cca49cd-acc7-57c9-8e3d-045f4d66025b | date | Date Completed:
| checkpoint | 2.5 - Traceability
da2d67d8-ba7f-5cf5-bb7d-1c8b07462380 | note | FREQUENCY: Each Load
d70e3e5e-97bd-5c79-bca6-767c95b591a8 | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, oﬀset/lane and layer
b5da6be8-c518-5da5-82e0-8f9d66e1ff94 | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
00b97f33-1851-5781-ae19-355a387dc66a | note | METHOD: Project Engineer/Site Supervisor
dc231368-f184-5a70-b5a4-0ffd8bacf28f | note | RECORD: Signed ITP & Traceability
f67dca4d-e290-570a-85f2-afa3b1e431b1 | note | IP
892047aa-eb3c-51a7-be7a-6ce4f4ab2b3e | note | RESPONSIBILITY: Project Engineer/Site Supervisor
d4c5310e-cfd3-5dde-81b9-503821d1020d | date | Date Completed:
| checkpoint | 2.6 - Layer Thickness and Level Control
4421e9d2-46be-5eec-a364-05895d1920e0 | note | FREQUENCY: Regularly during paving
ca358625-6532-55ab-8956-818032f13e25 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or speciﬁcations
fa0c2ab0-c658-57a8-a770-ba2a7c64bd60 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20
9603fa88-2d79-5922-b323-5d14c2b723a7 | note | METHOD: Dips, string line, measurements oﬀ kerb
4e2418da-2a1f-5a92-a509-861d472eaeea | note | RECORD: Signed ITP & Traceability
9b060f42-96cd-52b4-be26-eab438f86449 | note | WP
6827d86f-7e49-517b-a738-720ec7f2bd29 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
f137c235-64d2-5ea6-8ea0-6ab8400a6558 | date | Date Completed:
| checkpoint | 2.7 - Paver Stoppages
ef475d4a-c8a8-5feb-9f4d-c61095e58d27 | note | FREQUENCY: If paver stops
c73b67c2-592b-5031-9a07-3d8db756a1c1 | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
0e4d26f9-abed-5274-bc60-483b3faecec4 | note | Asphalt should be ramped down by constructing a temporary wedge of dense graded or cold mixed asphalt. Max ramp grade:
5567d95b-3186-5254-be44-18b5c1387c08 | note | ○ 40km/h – 20-1
c74bf4f2-4fea-5ba9-a626-1eca5bdaf6da | note | ○ 60km/h – 30-1
1bf5392d-84ef-5fc7-9a0e-fa5b2d63f126 | note | ○ 80km/h – 40-1
310e420f-f2c4-58f6-a46d-9290e5f8c518 | note | ○ >80km/h – 50-1
c3a32b50-b690-5ed0-8083-bc77ae64fb06 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.20 (c)
8c77ba92-fb2e-5f24-813d-fa39edb644fb | note | METHOD: Thermometer
ff44f6f6-acd5-5261-8961-36f399795178 | note | RECORD: Signed ITP & Traceability
5b798b96-e30c-5827-87ee-315dd8eed6cd | note | WP
d7606fc7-9cc2-53f9-b9bd-6389736d9b34 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
2ef2c642-1eca-5919-a7d2-00f2d9682a2a | date | Date Completed:
| checkpoint | 2.8 - Surface Finish of Wearing Course
80e46993-e657-572f-a513-5285dded12bf | note | FREQUENCY: During paving and after ﬁnal roll
c9a69f53-237c-5a30-880d-61b606cf8376 | note | ACCEPTANCE CRITERIA: The ﬁnished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
72e61c75-03a2-533a-b293-b718ae01a6be | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (i)
dcbed238-3566-506e-9c72-31786303c4eb | note | METHOD: Visual Inspection
4ac30c61-da55-5911-94a1-0836dc462769 | note | RECORD: Signed ITP & Traceability
97622e5e-0d08-5297-9349-1bf6ab900a77 | note | WP
c049582d-4566-5cf0-897a-d233d39cd544 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
5385b061-5266-5483-99f1-ea674af07302 | date | Date Completed:
| checkpoint | 2.9 - Kerb and Channel
f3be2380-2d64-5529-8882-65e715283ec8 | note | FREQUENCY: During paving and after ﬁnal roll
b04398ec-a330-576e-a2a1-f92f4cd70ffc | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either ﬂush with or not more than 5 mm above the lip of the channel unless otherwise speciﬁed
73e793a1-0112-5527-a4cd-32042710e2ce | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (ii)
f33a7fff-da80-5001-bb39-ed9394a44b08 | note | METHOD: Visual Inspection & Measurement
8e8ef1fc-f27f-505f-b413-342dcb03e4af | note | RECORD: Signed ITP & Traceability
d960e618-d586-5ab5-85fb-d78168225b6a | note | WP
b43e87ad-768b-5b2c-9b24-7d245fd442f0 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
1d75acae-afe3-5117-8b3e-d6143e69b692 | date | Date Completed:
| checkpoint | 2.10 - Alignment of layers not placed against concrete edge
903f6733-0a10-53fe-b96a-fd36a5dfffc3 | note | FREQUENCY: During paving and at completion of work
75be6c34-fadb-511e-a841-0f481ce6a607 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed oﬀset from centreline or design line. The rate of change of oﬀset of the edge of layer shall not be greater than 25mm in 10m
95ca9caf-f925-5ce3-bef7-1cc723e4420e | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (iv)
24bbfd2b-1dc6-58df-b2d5-bea093d4ea5c | note | METHOD: Alignment as marked by Surveyor and measured
fb4ca98c-0304-50ef-abd9-2ede43f5924d | note | RECORD: Survey Report
535c2b9f-3caa-5834-9d87-bad912f31b66 | note | SCP
01d8a7ea-b9d1-54d5-825b-8073a1de27f7 | note | RESPONSIBILITY: Client Surveyor, Project Engineer, Site Supervisor
3bb653a3-72ee-5c99-886f-66e453a33149 | date | Date Completed:
| checkpoint | 2.11 - Width of layers not placed against concrete edge
2fcaaf9f-f4e5-587e-b3da-43a566d617e6 | note | FREQUENCY: During paving and at completion of work
2dd5ad0e-af48-5d49-8a9f-0e8e4a4576d4 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or speciﬁed width of layer by more than 50mm or greater than the design or speciﬁed width by more than 100mm.
4157f40d-a3fd-53f5-a2ed-a01cc0113a06 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
592332f4-1af9-5f76-88e6-049e531e5c5e | note | METHOD: Measurement
f5d0f6f1-2739-5929-b501-7fd17ef254aa | note | RECORD: Survey Report
bcec00c7-fde0-5092-a1d6-68311396a991 | note | IP
d54df591-ab1f-51f4-ae36-89ceeb3e0acc | note | RESPONSIBILITY: Project Engineer/Site Supervisor
7b41f9ee-5615-5dc7-8fdc-e76a4c7de607 | date | Date Completed:
| checkpoint | 2.12 - Traﬃcking of Asphalt & Paving of multiple layers
dcc1eb93-5867-5054-ad13-1d46469b7463 | note | FREQUENCY: During paving and at completion of work
a98ddf23-4bef-551a-8d17-68c3b7c39d78 | note | ACCEPTANCE CRITERIA: Traﬃcking of asphalt or placement of asphalt over freshly laid asphalt layer is not permitted unless the majority of the asphalt has a surface temperature lower than 50°C
61d90b0a-9b2c-54c3-a990-501bc1474ae6 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 407.23 (a) (v)
5cee8e7f-f5ef-5c93-be8d-30d83899d9fe | note | METHOD: Measurement or suﬃcient time has lapsed
4a87f546-97f7-5d06-b73d-ace79f985e1a | note | RECORD: This ITP
26369cb7-50ed-5b4d-b423-1ada96311dcc | note | IP
40d1494a-598d-5d74-bd07-aa0250355521 | note | RESPONSIBILITY: Project Engineer/Site Supervisor
cb99bf71-8334-5af7-91c1-537336a8bc75 | date | Date Completed:
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Compaction
805be4c5-b0ba-547b-8d9e-d63ad167107b | note | FREQUENCY: Per Lot (6 shot test)
bb3990a0-b489-5def-a047-3c51514fdc22 | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
ab874798-d5cb-5d8b-b244-cf780fc870b3 | note | ○ 95.0% or greater Accept lot
7eec9ae9-9aa7-5cf1-91cf-de82adface94 | note | ○ 94.9% to 93.0% Lot may be accepted at reduced rate
9aea04c4-7085-518d-bcaf-2a5adfbdaa7b | note | ○ 92.9% or less Remove and replace asphalt
2d092927-10d2-5d1d-b139-328e3189da44 | note | For layers ≥50mm, if characteristic thickness is:
edc8eb2f-b95f-5fba-af1f-ee6e8d50f202 | note | ○ 96.0% or greater Accept lot
d416a547-42ba-5318-bea0-7d1b161d7fd3 | note | ○ 95.0% to 94.0% Lot may be accepted at reduced rate.
6ea0dd37-15ae-5e72-a963-8ae0953fd3d1 | note | ○ 93.9% or less Remove and replace asphalt
cf13ca32-070f-514d-8702-bb95e2074371 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.221
7832f8f9-7c64-5d96-ab63-cd4c8f3403c1 | note | METHOD: Compaction Testing
47b995d4-e5f3-5bcb-86ba-39deba4902fb | note | RECORD: Asphalt Field Compaction Report
0eeb4d26-8ade-5de6-8c4d-fb264135763a | note | TP
e7decff9-c24c-54de-aeb2-e5b2441481b2 | note | RESPONSIBILITY: Fulton Hogan Laboratory Technician Veriﬁed by Project Engineer
336431b3-9019-5c89-aed4-7326b7f2ee78 | date | Date Completed:
| checkpoint | 3.2 - Surface Levels
e5292322-a29c-5fc8-9b6f-c8ab4130d1fb | note | FREQUENCY: Each lot as required
6bd8f35a-5d39-5001-9b65-ec1497423956 | note | ACCEPTANCE CRITERIA: Individual departures from design not to exceed ±5mm with a standard deviation of no greater than 8mm (Scale A)
1d2693e2-4cd2-592c-b18b-5d698a4d5347 | note | REFERENCE DOCUMENTS: Vicroads std sec Table 407.222
2e471d8a-0e61-5934-ba2f-1347eee19e98 | note | METHOD: Survey
3d616094-c432-5453-af0d-a900dc6fa318 | note | RECORD: Signed ITP & Survey Reports
198b04ff-01b4-5fd0-91f3-2d93f21ef25a | note | SCP
f3e285fd-4cb8-52b5-87b0-ae390cbe9ae0 | note | RESPONSIBILITY: External Surveyor Project Engineer to verify
a92f3b18-674c-5b45-baef-2a77e0be9646 | date | Date Completed:
| checkpoint | Final Inspection
1cb45c7e-1100-55b4-82f0-43c114b945da | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
360a8c06-6de2-5d07-bede-29e1b5e9ba12 | textbox | Print Name:
7afc5cd4-6e3c-50b3-bc5c-ab55b2b10a83 | textbox | Position:
07ff092b-b8fe-517e-8308-572020cb4890 | date | Date:
| signoff | Sign ITP
| checklist | ITP-008 - Line Marking | itp | ITP-008 - Line Marking | 2dba6bf6-07cf-48e8-b985-0a4c84987c9d
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Line marking Conformance
cf398c00-b1ea-550a-a451-1c5c210de0c0 | note | FREQUENCY: Prior to commencing any activity
f4c982fa-05ea-50b1-977b-f9455b7655ed | note | ACCEPTANCE CRITERIA: Materials to be used conform with specification
2038c41b-4a33-5a48-9344-afee8dadfaca | note | REFERENCE DOCUMENTS: Review Materials Sheet
ca651cc6-beeb-5826-aa7b-32159bb31be9 | note | INSPECTION/TEST METHOD: Visual inspection
2e861195-3326-5449-952a-2762ed452c99 | note | RECORD OF CONFORMITY: ITP Signed
8ec8b554-69f1-5041-ad28-6cb43f310e94 | note | WP
ff8c85e6-65ba-5538-812e-b5efaddf9d79 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
4876419d-2456-5a1f-8d76-3d524fc9bf96 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
8a3ccd34-f90b-51b6-a592-b9096a7d20d0 | note | FREQUENCY: Prior to commencing any activity
295ba275-a745-5053-9f68-7d8cd1f5a60d | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: QMP, TMP, SWMS & WP
b8bb131b-2230-5356-bce6-7dce3783590f | note | REFERENCE DOCUMENTS: QMP, TMP, JSEA, SWMS, WP
03410dfa-9009-5afc-94c3-663fb4e9acd3 | note | INSPECTION/TEST METHOD: Visual inspection
d7bd7207-39a2-519b-8fef-6c0f3797ba5c | note | RECORD OF CONFORMITY: ITP Signed
3fc5ce86-7e5b-59bd-a27b-48317f07ad86 | note | WP
d4a955fc-7f0f-58ff-8d91-68d18251a210 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
f96c3abf-eee6-5ddc-8234-09e89d832541 | date | Date Completed:
| checkpoint | 1.3 - Site preparation
7697e8b1-35e5-5bcf-93f7-8f17c6b5148f | note | FREQUENCY: Prior to commencing any activity
44c8f1b7-f403-5476-aa4c-10ba8649cd39 | note | ACCEPTANCE CRITERIA: Removal of any existing unsound,obsolete or redundant pavement markings. Removal of any foreign material or debris.
5e67b8ba-e4e8-5d6d-841d-67bf600c22c3 | note | REFERENCE DOCUMENTS: 721.A06
f9b2d967-ba74-5f3d-87f8-bc35eeb217fd | note | INSPECTION/TEST METHOD: Visual inspection
66d8160c-eaf9-5435-af93-279a44d20f34 | note | RECORD OF CONFORMITY: ITP Signed
162f438b-fcaa-58ae-b316-378ec9123e09 | note | WP
a5b3164e-799b-5aa5-9367-ec1d13644203 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
7282a4f2-cf92-5e80-afa9-de2f1c7b2262 | date | Date Completed:
| checkpoint | 1.4 - Set-out of Pavement Markings
62f3beab-cecb-5340-b079-0c48da028390 | note | FREQUENCY: Prior to commencing any activity
c30bffd1-0aca-5d8d-86cf-2875425c5d28 | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings.
9b8eabd9-e4f2-51be-9265-c4065b970926 | note | REFERENCE DOCUMENTS: 721.A09
97c893f3-5839-55d3-ab37-2aee3a4f1751 | note | INSPECTION/TEST METHOD: Visual inspection
dc285bbd-596d-5ebe-9746-20f574e2a6a7 | note | RECORD OF CONFORMITY: ITP Signed
31432cc9-08b0-52a9-b551-8e2a11b09742 | note | HP
4da95e02-c203-5bb5-aaf4-ec2156707bd0 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
1997be85-174f-5c8d-bd63-7adc879f97d4 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Construction Works
| checkpoint | 2.2 - Line marking Installation
9c8bf8c2-970b-52b7-8af8-c19972243f60 | note | FREQUENCY: During Construction
62e3c7ee-d31e-53d8-8ece-7446650a889b | note | ACCEPTANCE CRITERIA: Line marking installed as per IFC Drawings
b9984d64-b245-5d0b-a224-d98ba780fdf8 | note | REFERENCE DOCUMENTS: 7210
7fb9566f-3897-5d00-954d-f41057158ad2 | note | INSPECTION/TEST METHOD: Visual inspection
c1e29a32-fc81-5b12-8b34-8407e85afce9 | note | RECORD OF CONFORMITY: ITP Signed
827ee09a-1af4-5276-9f6b-0f8a5410c885 | note | WP
fd0f9cb5-0327-58da-aae4-2e7b0d11d036 | note | RESPONSIBILITY: Project Engineer/ Site Foreman
41309f9c-52be-59d8-b346-2f1c6f65f381 | date | Date Completed:
| checkpoint | 2.3 - Glass bead Install
b9dad2ee-45bd-57b4-a318-154477d09bd9 | note | FREQUENCY: During line marking works
c4a5566d-43a7-5d03-90b7-b73b340f18ea | note | ACCEPTANCE CRITERIA: Glass beads sprinkled/sprayed on to line marking while in a fluid state to ensure embedment. Glass beads to have uniform distribution
e62569ec-6717-5b44-9bf3-435563a8f934 | note | REFERENCE DOCUMENTS: 72100
861e12b2-830f-54fa-b434-cc95c5ec8c99 | note | INSPECTION/TEST METHOD: Visual inspection
d88737ca-e1f6-5a2e-a2c8-9ee1ef94da76 | note | RECORD OF CONFORMITY: ITP Signed
91a05235-3db9-5a56-ba04-3f053f7389da | note | WP
487d6270-9618-59e2-be10-ffd9db185eba | note | RESPONSIBILITY: Project Engineer/ Superintendent
db24e1f3-91be-505d-9815-86fb5caf9e62 | date | Date Completed:
| section | 3 - Completion
| checkpoint | 3.1 - Completion Inspection
9e5addc1-c9d6-58bf-ac79-b46ba119faca | note | FREQUENCY: Each lot
29dee3c7-ac35-5ccb-a7f2-6505136a49e9 | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, streats, overlaps, unbeaded areas, tyre marks or other defects. Edges and cuts-offs shall be neat and sharp, and there shall be no visible run-off, overspray, dribbles,splash or spiliage on to the surrounding area, or on to parked or passing vehicles.
86c75047-2e92-5711-8127-85dd183ecb60 | note | REFERENCE DOCUMENTS: 7210
d83379af-1af6-5053-a1ee-56c0dadfa7e1 | note | INSPECTION/TEST METHOD: Visual inspection
6b359925-b033-5997-a9cf-b5e870da3811 | note | RECORD OF CONFORMITY: ITP Signed
a795c486-6786-5a38-acb1-54c8dab0f474 | note | WP
f61416a0-9e52-5ed2-802c-29a0e4a90d91 | note | RESPONSIBILITY: Project Engineer/ Superintendent
ec5c5f57-5a9b-5e40-a7f8-2470b3ede45c | date | Date Completed:
| checkpoint | Final Inspection
331c3c9a-8381-5dc4-b4c1-2fd63f020827 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b44bba27-ceb7-526f-a40d-f2a0e867f3b9 | textbox | Print Name:
fc826b94-cc56-5057-a310-3e3aa4e0b535 | textbox | Position:
d611732a-44b2-5b66-b64b-b0d5782d1b7a | date | Date:
| checklist | ITP-045 - General Concrete Paving | itp | ITP-045 - General Concrete Paving | 64add901-d0a1-4f56-bccf-ae67d96abe9a
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
f00f81f9-3707-5f98-acef-f0febcd3f763 | note | FREQUENCY: Prior to commencing any activity
f82f4eaa-e858-5067-a61d-060f1fc0b7f4 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
b07bfc8b-4d9a-5ee0-99a9-689054d19446 | note | – using the correct and complete set of drawings
57b2e505-dcc0-5873-822b-c0e8637d7136 | note | – all drawings are the latest revision
4c5e8aad-2368-5b3c-84cf-bb330b3b4ad9 | note | REFERENCE DOCUMENTS: IFC Drawings
2562f631-9bef-5dfa-ad7b-08cd8a11ecda | note | METHOD: Visual Inspection
8a796396-7fd0-5a70-9099-9949bbe0670a | note | RECORD: Signed ITP
e93ebf5a-00e6-54c4-8df0-19d1e19f5e95 | note | IHP
a61a910a-d6f9-599e-af5f-45bfdbfabd8d | note | RESPONSIBILITY: SWA Project Manager
c4d07daa-1232-568c-b687-0608f06513a6 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
5ad8ff52-251e-5977-9b7a-1eb805a35240 | note | FREQUENCY: Prior to commencing any activity
bf3c0c49-f8a6-5f7e-91ff-c153574a2d88 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: EMP, TMP & SWMS.
daae6ff9-77de-5e35-a018-9f5b153008b9 | note | REFERENCE DOCUMENTS: EMP, TMP & SWMS
ed1c7587-55d0-5396-a818-64250afa9554 | note | METHOD: Visual Inspection
6f47df30-efcd-58a1-bbdd-fa00e3af16e8 | note | RECORD: Signed ITP
301d5924-b973-5fae-869c-6daa6371d8e0 | note | IHP
084a71b0-f3cf-56e6-badd-01d3d2d9bcdb | note | RESPONSIBILITY: SWA Project Manager
06310af1-0141-5a71-8dab-7d7af1368a77 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
c24af973-3496-5e44-a116-55351e5c77da | note | FREQUENCY: Prior to commencement of excavation.
5c2a428c-a4e0-5e02-bf63-92d39a81571f | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
ca9ebcfa-e99f-5dbd-a968-914d5795e7c0 | note | REFERENCE DOCUMENTS: Work Procedure
735f3511-5041-5de5-a147-1dd48e48af5f | note | METHOD: Verify
37d815fb-3579-5a0b-a5bf-5a30f659d3b8 | note | RECORD: Signed ITP
cd925ff3-f7e9-5b04-a2d8-32095af968f0 | note | IP
f2c66121-05b2-5579-bd69-eb4eb31a2486 | note | RESPONSIBILITY: SWA Project Manager
3ec15906-91c3-5edf-b9b1-7e4d216f7799 | date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
c6ebc376-79cc-5555-a3a8-3215632ffdc9 | note | FREQUENCY: Each Lot
d48fe07e-d39b-563a-92f2-70cbc771b3fe | note | ACCEPTANCE CRITERIA: An excavation permit or DBYD must be issued prior to any excavation commencing. Plant and equipment shall be appropriate for the task. Excavation operations shall not disturb areas outside the limit of excavation
f1877432-9f21-545e-a304-ebb55ddf6dea | note | REFERENCE DOCUMENTS: Excavation Permit
58f7d024-3df5-5905-b9ec-7205b4aea0b6 | note | METHOD: Verify
22f125e8-e461-533e-bd4a-ffa87be595e3 | note | RECORD: Signed ITP
4f442bb3-d76f-556a-84ee-34eaffe01822 | note | IHP/IP
5b41090a-029a-5e96-b4ef-8eae810df6de | note | RESPONSIBILITY: SWA Project Manager/SWA SEQ Adviser
c62b93cb-ac10-5a76-be4c-2353b57edd62 | date | Date Completed:
| checkpoint | 2.3 - Formwork
80ba972c-7d81-5148-9659-2a741b4295fb | note | FREQUENCY: Each Lot
a6f3236c-9153-5c2d-bcd8-cc7326d67091 | note | ACCEPTANCE CRITERIA: Formwork shall comply with the requirements of AS 3610
86925127-0be5-5760-afab-70fbfebf3536 | note | REFERENCE DOCUMENTS: AS 3610
eb0b519e-6df0-5f32-903b-128bc65e76be | note | METHOD: Site Inspection
d224b59a-ae8b-5c71-9588-f4736c8674e8 | note | RECORD: Signed ITP
41d4d3cf-40d0-5eda-9ba2-e7f90610d425 | note | IP
ced623a3-ec51-5a1c-a380-5ba2311bc646 | note | RESPONSIBILITY: SWA Project Manager
68f7a498-c995-51aa-93e3-153085726728 | date | Date Completed:
| checkpoint | 2.4 - Reinforcement
87bb8f75-0000-50e8-af13-464c7ef219ea | note | FREQUENCY: Each Lot
5f095a83-a38c-5722-af50-5b7046d83367 | note | ACCEPTANCE CRITERIA: Steel reinforcement shall comply with the requirements of AS/NZS 4671. Minimum cover of 50mm.
abde8d06-df05-5156-9011-771e50c4ccf8 | note | REFERENCE DOCUMENTS: AS/NZS 4671
2fa84fec-71b7-5e47-ab98-b3b56b6921bc | note | METHOD: Visual Inspection
3f883550-ce5e-5b17-8286-1506152a979b | note | RECORD: Signed ITP
ffc261a9-a7b7-5e61-a64c-ac2bd7c84d5b | note | IP
a90961cf-c628-5c50-96bb-b475f9b22448 | note | RESPONSIBILITY: SWA Project Manager
04e1b3a2-e0bf-5823-8c5b-5634b0e83281 | date | Date Completed:
| checkpoint | 2.5 - Temporary Drainage Provisions
acebfcb0-0b07-5a7a-913e-3069f6472280 | note | FREQUENCY: Prior to commencing
6ae25447-e7ea-55e1-9504-2503672ac9b7 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place. Obtain written approval from relevant waterway authority.
4200a45e-b0b0-5ee6-b67f-8115122d994d | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.15
f0c1432f-f26e-5abd-bb50-d03744440ee1 | note | METHOD: Visual Inspection
f77a7f7b-888a-558c-bf1b-1fa7f1861db6 | note | RECORD: Signed ITP
f5270248-e568-51bb-bb2a-92185255d7bf | note | IHP
fc36b750-9fa2-5cb0-948a-a9be1c03ce1c | note | RESPONSIBILITY: SWA Project Manager
99c13c11-226b-547b-8b51-77db5d95d52f | date | Date Completed:
| checkpoint | 2.6 - Bedding
ca24433f-dc9a-5132-98fa-c35b60896be6 | note | FREQUENCY: Each lot as required
a6ee738c-4c4c-55ce-81c0-5d46c1f0312b | note | ACCEPTANCE CRITERIA: Crushed rock bedding material as per drawings
3cbe469a-ceda-5093-9a43-c6080b3b9944 | note | ○ Bedding trimmed, moistened, and compacted as necessary
09896a9f-2358-5898-a812-5f1c2c4fdf74 | note | ○ Bedding compacted thickness: Footpaths and other surfacing ≥ 50mm
ba79e28c-6b06-5ced-a400-87e122bcc995 | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.18 IFC Drawings
16c4c2e5-7380-5afa-aecc-8bdeaab89a4c | note | METHOD: Site Inspection/ Document Review
cdac8416-28a0-54bd-929e-0ee2cd49d681 | note | RECORD: Signed ITP
ddeb711a-4dd0-5192-b472-0021d433fa72 | note | IHP/AP
95530929-99f5-54a9-a4c5-42accdda2d90 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
493f0753-f636-5667-98c4-4de520813273 | date | Date Completed:
| checkpoint | 2.7 - Concrete Placement
d8a14385-9ee5-5e60-9c09-767a81a18831 | note | FREQUENCY: Each lot as required
26fc3543-9d86-5b5d-826c-65bafd09538c | note | ACCEPTANCE CRITERIA: Concrete strength as per drawing speciﬁcation
478e45c2-550e-5546-b6ad-bca7d964eae4 | note | ○ Comply with requirements of AS1379
e494c1c7-9c3e-5676-8450-5517dd374f9d | note | ○ Aggregates to comply with Table 703.051
832fdc03-8e8e-5671-bca7-165252eff251 | note | ○ Extrusion machines cement content ≥ 320kg/m3
44720f2c-50c3-5c9a-802b-7a2ea369313c | note | ○ Surface pitting < 5mm diameter
afccc3de-af8f-5b96-b968-dca1c9eca6ea | note | ○ Concrete to be satisfactorily compacted. Proﬁle transitions between 10-20mm per metre.
4646e6f6-2abe-5416-9474-41281da51c53 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.04(b), VicRoads Std Specs 703.20, VicRoads Std Specs 703.21 IFC Drawings AS 1379
1ac2bf45-f0f3-572f-9e49-5ab7afa3ba95 | note | METHOD: Visual Inspection
8100b39a-6f3a-5101-acbb-a81a60db3571 | note | RECORD: Signed ITP & Test Reports
e4d683a0-8b17-5aaa-9ebe-6dcea38e6075 | note | IHP/AP/TP
8b4314d9-ae3f-5534-b4c1-2f064d6621d1 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent/External testing Company representat ive
3d4cc805-b698-583c-a229-4511c5dc8afc | date | Date Completed:
| checkpoint | 2.8 - Finish Surfaces
f18b4c72-b47f-56b2-946d-3ac2f8544bfd | note | FREQUENCY: Each lot as required
e1352f21-6c42-5b0d-ae1a-3dca550a8fee | note | ACCEPTANCE CRITERIA: Footpaths and other Surfacing: Wooden ﬂoat ﬁnish
c56989af-b9ab-5f33-b77e-cf6b3fdb7c2b | note | REFERENCE DOCUMENTS: VcRoads Std Specs 703.22
0e3b2c98-f62c-5b7f-824f-278c8923adc3 | note | METHOD: Visual Inspection
56a5ec29-fdb3-5a71-8224-814df6b05d6a | note | RECORD: Signed ITP & Test Reports
8ebd4263-5d49-570a-afb4-16afd62836d2 | note | IHP/AP
83299a0e-06e1-5ba4-a31e-e9dd12db7095 | note | RESPONSIBILITY: SWA Project Manager/RRV Superintendent
532f2c42-a64f-595f-b006-5c885b473d04 | date | Date Completed:
| checkpoint | 2.9 - Tolerances
d79b99de-b3b5-5cec-b963-61f68884fcd0 | note | FREQUENCY: Each lot as required
1784fca3-fc98-52e8-8512-97129432d6c0 | note | ACCEPTANCE CRITERIA: Match existing surfaces ± 5mm
d432bd61-f521-5649-a374-aea1e2223041 | note | Section dimensions:
5de68d03-3a33-5a5a-b6b8-cd2cf311365b | note | ○ Within 5mm and 15mm for width; and
2a85f256-0467-5081-9879-848725dfe2e5 | note | ○ Within ±3mm for dimensions less than 25mm.
d0a12e48-b4a0-503d-b55b-ab5ac989adf0 | note | Concrete footpath:
e86aa2be-7d86-5956-8b26-7d656271454a | note | ○ 150mm thick
1a8f32f4-a093-5982-904c-546f57814094 | note | ○ SL72 reinforcement
34052b23-8b7c-51dd-8d36-21177f979176 | note | Concrete Surfacing:
a6d747c7-0cbe-5c0b-8c31-ea1db510e25c | note | ○ Type 1 100mm
2a75b862-012e-5673-bad8-aeb367147f63 | note | ○ Type 2 150mm
acb8f211-de9d-5033-9745-05ee9fd0786e | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.13 IFC Drawings
e26c1712-902c-5924-bde8-6dc7fb2b630d | note | METHOD: Visual Inspection
46f5b5fc-b416-5c99-848c-84e5c674ce3d | note | RECORD: Signed ITP
ae8d6666-2934-544a-a884-fd734c6b4ba8 | note | IHP
5b414b1d-fa33-5e69-b88f-1ff99c3a2c79 | note | RESPONSIBILITY: SWA Project Manager
ba4f3d30-4681-5063-b725-3297985141ba | date | Date Completed:
| checkpoint | 2.10 - Joints
d0841567-1986-5285-b2b0-64e1983bbb8c | note | FREQUENCY: Each lot as required
86581333-88d2-573b-be1c-42112834931f | note | ACCEPTANCE CRITERIA: Footpaths and other surfacing:
c45adb2b-5ac4-5cd9-b254-d37864cfefcb | note | ○ Expansion joints at 12.5m regular intervals
725d9bd9-0b0e-5872-8640-aefe7b92e1f1 | note | ○ Control joints at 2.5m regular intervals
a6269077-f7b6-5bf3-87b5-d37c5fde4c7a | note | ○ 20mm deep and 5mm wide
a389b37f-9e10-59b0-bddf-d6d6d8fc463d | note | ○ Prevent bonding between edging and surfacing. Either paint back of edging with bitumen or use a strip of bituminous felt material.
c1949217-b00c-5e2c-9575-34a9a15c8a85 | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.23
67594f63-dc1a-504d-949d-0c01aba6ba54 | note | METHOD: Visual Inspection
0e8d9b35-6951-5020-8240-ae9c36a48f73 | note | RECORD: Signed ITP
d62a5ae5-cb83-54c5-8ca4-6dc6f65af831 | note | IHP
a8d32a8f-2c22-5ea3-af31-8435df435a96 | note | RESPONSIBILITY: SWA Project Manager
f49f0f64-9d57-568f-b306-adc1ee13ec31 | date | Date Completed:
| checkpoint | 2.11 - Backﬁlling
01bc3f61-b785-5ceb-9ac9-6b8a9ce63d67 | note | FREQUENCY: Each lot as required
933d07bf-e431-5b7a-a63c-4abc6e802c3b | note | ACCEPTANCE CRITERIA: Topsoil compacted in layers < 150mm
0285f22e-8d6c-56d0-af46-69e5f1e7d879 | note | ○ Width ≥ 300mm behind edging to top of edging
2188ab9f-adb5-53cd-8ca0-792a68404226 | note | ○ Topsoil placed after 3 days of concrete placement
2673d81d-1523-52a2-9770-c8e5cb1cf45a | note | REFERENCE DOCUMENTS: VicRoads Std Specs 703.26
a6f448e9-fc11-5e2c-9835-82139003f2f5 | note | METHOD: Visual Inspection
fbd8d297-530e-5cc6-ac66-c8a66fa09b86 | note | RECORD: Signed ITP
d716a966-9bbe-5f00-83fb-592a7b41c495 | note | IHP
c6d58390-c94e-5715-827e-6c8ac0c9942e | note | RESPONSIBILITY: SWA Project Manager
f8b0fcb1-8c27-5042-bbc2-6924c0995fae | date | Date Completed:
| checkpoint | Final Inspection
944f36bd-74bb-5da9-9011-8fdc2a066a21 | note | The signature below veriﬁes that this ITP has been completed in accordance with the Fulton Hogan’s Quality system Procedures and veriﬁes lot compliance with speciﬁcations.
890f996a-a125-546a-93ef-5eeeda2ce1d3 | textbox | Print Name:
adcc8951-34eb-54ed-a716-23c759a8e8ba | textbox | Position:
66097dc3-5d50-52f0-ac68-1fe3399c4c08 | date | Date:
| signoff | Sign ITP