## Project Checklist Templates
Id | Type | Name | Values | Prompting Name | Postfix | Resource Id
| checklist | ITP-001 - Pre-commencement of works | itp | ITP-001 - Pre-commencement of works |  | 50840b57-1a50-4b55-80bd-4e69d3841e19
| section | 1 - Construction - General
| checkpoint | 1.1 - Design Drawings
890cbc44-87c2-5bd1-8f23-b73e99bca564 | note | FREQUENCY: Prior to commencing any activity
340a5145-aebb-5212-b46d-26a1a34cef3e | note | ACCEPTANCE CRITERIA: Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
45e141d2-af0b-57b0-83b7-d94b8dfea023 | note | REFERENCE DOCUMENTS: IFC Drawings
cb836af7-da5b-5d24-9404-8d339e9bf012 | note | INSPECTION/TEST METHOD: Visual inspection
f41e993a-7c67-55fb-9951-d46c355b4bc5 | note | RECORD OF CONFORMITY: ITP Signed
244eab21-e7dd-5edc-8463-67a47d938eaf | note | IHP
871dd128-06d1-53d6-bb0a-e80830b18f1a | note | RESPONSIBILITY: Site Engineer / Site Foreman
7f396438-aace-5148-86b5-019b8c23c0cb | date | Date Completed:
| checkpoint | 1.2 - Service Locating / Permits
1bc80bd9-7dc5-5616-872b-fa7b61097ae3 | note | FREQUENCY: Prior to commencing any activity
841dc35e-95f5-5b0e-ac5c-d975183c6b87 | note | ACCEPTANCE CRITERIA: Lodge DBYD application prior to works commence and obtain any relevant permits applicable to the works. DBYD to be renewed every 30 days.
27a54cfd-f58e-5d9b-9a67-6a6afbfdee00 | note | ○ All nominated/aﬀected services from the DBYD application must be located/potholed prior to commencement of works.
616e8e8f-ff47-5dd6-979c-f0442284cddf | note | ○ Works identified within the vicinity of the powerlines to ensure distance exclusions are followed & spotter used, if required.
53a2683e-a3db-523f-b84e-2b6b27da537b | note | REFERENCE DOCUMENTS: DBYD Information
ad587a1d-b175-554e-8b56-99a5ab2d8399 | note | INSPECTION/TEST METHOD: Visual inspection
6024761a-3f10-5001-9a95-73ffcfe3cb13 | note | RECORD OF CONFORMITY: ITP Signed
2278d498-1d37-5d21-9e4a-2e728f461426 | note | IHP
122e1f6b-91b3-512d-9f18-5001f7c6c76b | note | RESPONSIBILITY: Site Engineer / Site Foreman
73d06107-7093-5d03-8bb2-5746941bb609 | date | Date Completed:
| checkpoint | 1.3 - Commencement of work
df8938c1-794b-568c-ad8c-936e59ceb616 | note | FREQUENCY: Prior to commencing any activity
7c0d994c-ce00-52a0-945a-712073892fad | note | ACCEPTANCE CRITERIA: The Contractor shall not commence work on site before the following documents have been submitted to the Superintendent and the Superintendent has authorised release of the Hold Point:
db63491a-31d0-5279-a762-4d478cef10e4 | note | (a) Public Liability and WorkSafe insurance conforming with the requirements of the General Conditions of Contract
e616a285-45ae-5581-8f3b-1b4812c61893 | note | (b) Health and Safety Co-ordination Plan
905cdcf4-2007-5345-a0ca-fd4f1221e71d | note | (c) Environmental Management Plan for initial works
6a2d29fc-d8b6-5e15-89f0-fb56b6a86129 | note | (d) Project Management Plan
4f488af6-2d4c-52d8-8f20-78f37cf10120 | note | (e) Quality Management Plan
b4408503-9831-53d2-bd6e-489a3ff4f9c7 | note | (f) Safety Management Plan
d6fafd5c-d1e1-5651-8d17-4d40c98610e0 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 160, 166, 167, 168 & 176
ba7caf82-17c4-55bb-93d2-c74ca85e3686 | note | INSPECTION/TEST METHOD: Visual Inspection
59d191ba-e607-5672-a7b7-5a3acfc9eed0 | note | RECORD OF CONFORMITY: ITP Signed
aef8a985-967a-5d6e-9981-7e63f279de63 | note | HP
0647dabe-e15d-551d-8a85-65827a4c85bd | note | RESPONSIBILITY: Site Engineer
7a45aa2b-c8a2-5eca-b034-d682a20f1690 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 2 - Traffic Management
| checkpoint | 2.1 - Submission of the TMP to the Superintendent
b0b36336-2f33-5507-afeb-569a4ffc6885 | note | FREQUENCY: Prior to commencing any activity
bb9180e5-5593-5fe2-83b1-a8eae33a39e6 | note | ACCEPTANCE CRITERIA: The Traffic Management Plan shall not be implemented as a Traffic Guidance Scheme until the Superintendent has completed the review of the final Traffic Management Plan and released this Hold Point.
96896934-f059-597a-9305-ee728bf0845c | note | REFERENCE DOCUMENTS: TMP, VicRoads Standard Section 166.08
2a361f16-bb6e-5828-a72c-12c6702ae51c | note | INSPECTION/TEST METHOD: Visual Inspection
499c8df8-eef1-5c32-9838-75ac7b63dfed | note | RECORD OF CONFORMITY: ITP Signed
943f431f-ca33-5b84-a5bb-c7bf639f234e | note | HP
5c69575a-7efc-52a7-814e-8c9fceb066df | note | RESPONSIBILITY: Site Engineer
558f5087-2e9d-53c3-b3ca-0c9098ca95b5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.2 - Detours and Side Tracks (a) Side Tracks, (b) Detours
636bcd22-cf0e-53bd-a89e-8680c15dbd79 | note | FREQUENCY: Prior to commencing any activity
ec873812-4c97-539d-8d9d-4d97edbb5537 | note | ACCEPTANCE CRITERIA: Traffic shall not be diverted on to any side track until permission to use such side track has been given by the Superintendent.
e53976e3-9f6f-59a9-9fdb-490112c28e43 | note | – Permission has been given by the Superintendent and Ballarat City Council.
7cb3821b-469b-5e0f-a54c-f25b8d26107e | note | ○ Where VicRoads as well as the Contractor has some responsibility for the restoration of any detours or sidetracks, the Contractor shall not commence any restoration work until the Contractor has submitted details of the work to be undertaken to the Superintendent for review.
26099bf1-8c08-523b-9f59-1f3d012efcc9 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 166.17 (a) & (b)
adbe43a6-0a76-588c-92aa-02b10a72a4fb | note | INSPECTION/TEST METHOD: Inspection
69f4061c-9910-53bf-95f9-84b79f601249 | note | RECORD OF CONFORMITY: ITP Signed
7733e292-3466-5d29-88a3-6318d72c4768 | note | HP
3aae1ef5-aa9f-580b-8899-06699cf1f9c2 | note | RESPONSIBILITY: Site Engineer
127af6e2-f75a-53de-a89c-f2b283eb273e | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 2.3 - Traffic Management Documentation
e6d8036d-6c2b-5198-ad90-73b39a45428f | note | FREQUENCY: Prior to commencing any activity
e7aa71cb-21b6-5d4e-b189-075cc32a85f5 | note | ACCEPTANCE CRITERIA: Ensure all TGS plans have been reviewed and deemed acceptable for the project. Obtain MoA approval for any road impacts or closures.
a095adfe-48b8-5c9e-9282-653b1e6466e0 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 166
3a91deb0-5c34-5cf2-9732-ac826d669f47 | note | INSPECTION/TEST METHOD: Visual Inspection
3daca8d2-7373-59f7-bca3-5fc0000de893 | note | RECORD OF CONFORMITY: ITP Signed
f40014dd-5183-5e7e-9a0f-386362516ba3 | note | IHP
fdcc82ec-4e53-5df0-a184-485da53cf1b3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c08e7c7c-9705-51c5-911c-b8d322a79845 | date | Date Completed:
| section | 3 - Health and Safety
| checkpoint | 3.1 - Occupational Health & Safety Management Implementation
68593fc8-b891-5146-9a43-0975b940dcd9 | note | FREQUENCY: Prior to commencing any activity
78fac8fc-fe74-5209-a94e-3eae1d60a03f | note | ACCEPTANCE CRITERIA: Signed Safe Work Method Statement (SWMS) in place. All personnel including Subcontractors must complete Site Induction prior to arriving on site.
03955e12-5b60-58cb-bfcb-9c1182ba873e | note | REFERENCE DOCUMENTS: Site Specific SWMS
39ef06a3-162f-5bd1-84a5-a48b2d60968b | note | INSPECTION/TEST METHOD: Inspection
840110b3-e2bf-5dbe-b962-59501f4fefe7 | note | RECORD OF CONFORMITY: ITP Signed, SWMS
828ddaae-1b0a-5799-8f1d-702f906fcf65 | note | IHP
cab37a62-d864-58b2-a3d9-e5976bdd1903 | note | RESPONSIBILITY: Site Engineer / Site Foreman
b9e153ee-5ece-5e99-89a8-65127af61bc5 | date | Date Completed:
| checkpoint | 3.2 - Health and Safety Co-ordination Plan and Declaration
1dbe40c7-90ed-5505-955d-7c239823d087 | note | FREQUENCY: Prior to commencing any activity
54277ac2-b366-58c0-ac39-9a491dbb9ac9 | note | ACCEPTANCE CRITERIA: The Contractor shall, not less than 5 working days prior to commencing work, submit to the Superintendent:
b5366dd0-a6f4-5127-9558-b98832576d6e | note | (a) a reviewed Health and Safety Co-ordination Plan; and
7d84df3c-1cf3-5839-b40d-4a14aaf23e0e | note | (b) a signed HSCP Declaration by an OH&S consultant/advisor that the HSCP meets all the necessary requirements. The Declaration shall be in accordance with the proforma included in the appendices of this Specification.
a50adbb5-61a3-5f48-9051-3966676b9717 | note | (c) a completed VicRoads HSCP Checklist with Contractor’s responses for each checklist item requirement.
c19f349d-ad8e-5dc1-997d-c68b6410c10d | note | REFERENCE DOCUMENTS: VicRoads Standard Section 168.05 (c)
e4068934-6833-5d76-9d89-eb7b3334bd09 | note | INSPECTION/TEST METHOD: Submission
c9a515ef-aaa9-5f94-af29-c0e327e2a95d | note | RECORD OF CONFORMITY: ITP Signed, Safety Management Plan
1b273adc-029a-5b0a-b376-578a2fbc4b1a | note | HP
094270ff-4f5f-5be3-bb0a-1f8658aa3b20 | note | RESPONSIBILITY: Site Engineer
e823716d-3acb-544e-bce6-5dc1e3a0f4c7 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| section | 4 - Environmental Management
| checkpoint | 4.1 - Environmental Impacts, Aspects & Risk Assessment Implementation
f10630f9-ba5a-5f4b-aef4-e49093da5742 | note | FREQUENCY: Prior to commencing any activity
7a666bec-a400-5ba0-855c-bc87fbb00126 | note | ACCEPTANCE CRITERIA: All environmental controls implemented in accordance with the Contract Environmental Impacts, Aspects & Risk Assessment.
e3c1cfe3-f4ea-55c0-bb37-37c456f0aadf | note | REFERENCE DOCUMENTS: EMP & A&I
407133ff-4e91-5b43-b25c-99ddbd4d9287 | note | INSPECTION/TEST METHOD: Visual Inspection
16565929-318d-5f07-a826-d9730b3dc5c4 | note | RECORD OF CONFORMITY: ITP Signed
e1a87b1a-cfe1-500e-a8ce-cc67577bbc09 | note | IHP
826ec9f1-30a2-5303-b8dc-f18279424736 | note | RESPONSIBILITY: Site Engineer / Site Foreman
abc09647-94b9-5a42-812d-817731a6c4da | date | Date Completed:
| checkpoint | 4.2 - Environmental Management Plans
64261596-13e5-5b62-9366-979bdc4bec6e | note | FREQUENCY: Prior to commencing any activity
cb7f2dc1-be20-594d-81a2-9c01cecdf422 | note | ACCEPTANCE CRITERIA: The Contractor shall submit to the Superintendent for review an Environmental Management Plan not less than 2 weeks prior to the commencement of work. Work shall not commence until:
6f42d891-c92c-5d0a-8098-04d4a811a5df | note | – the Superintendent is satisfied that the Plan meets the requirements of this specification; and
e7678e96-6878-54b2-8b7d-9fd6860d8c31 | note | – the controls detailed in the Plan are implemented; and
2a4957c2-8c90-5e11-95c2-e9fcdf009d3d | note | – the Superintendent has authorised release of the Hold Point.
e03c87ed-4c40-5e54-908b-62bedffd6b85 | note | – Limit of works identified in applicable SWMS.
7bcce1f0-8ace-5be2-ba9f-aa59ffb2fb92 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 176.A3, VicRoads Standard Section 177.A3
b6dea57d-232e-5c92-8683-e42ddb95bf76 | note | INSPECTION/TEST METHOD: Submission
7307ddbe-12b8-5285-a453-29f79af177f7 | note | RECORD OF CONFORMITY: EMP, ITP Signed
cdd69948-6494-5863-98fc-614678d15ac0 | note | HP
8a4e10dd-2e46-5a18-bde7-f2eb67fda3a5 | note | RESPONSIBILITY: Site Engineer/Superintendent
6d36dffd-5c37-536c-abcf-9b0a8675ddc5 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.3 - Flora and Fauna
8d81854c-81ac-5e59-a107-edc36d135308 | note | FREQUENCY: Prior to commencing any activity
66afedaa-3152-58e5-b77b-28b0d5d97a68 | note | ACCEPTANCE CRITERIA: Prior to removing any vegetation or habitat, the Contractor shall arrange an on-site inspection with the Superintendent and other relevant authorities to conﬁrm and clearly identify and mark trees, vegetation or habitat to be removed. Any removal shall be consistent with the Contract drawings and any relevant permits and shall fence and sign all sites nominated as No-Go Zones.
b3dd623e-b6b8-5bc2-85ec-009725c5db86 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 176.I1, VicRoads Standard Section 177.I1(c)
d5debdc4-6b19-5787-9cc8-187cee9e3737 | note | INSPECTION/TEST METHOD: Visual Inspection
c018cde0-994e-562a-9303-f9bb17aa0505 | note | RECORD OF CONFORMITY: ITP Signed, Relevant permits, No Go Zone Signage
cec3eca1-a6bb-5016-ac3b-9b680e2b5b52 | note | HP
95bcd282-b792-5cf4-8d4c-e60a0f4b47ea | note | RESPONSIBILITY: Site Engineer
5a76a7d2-c0ec-5579-99c5-eee085b49288 | date | Date Completed:
| signoff | AUTHORITY HOLDPOINT
| checkpoint | 4.4 - Erosion and Sediment Control
8e132a76-33de-537b-a4cd-ce9c3ccac2bd | note | FREQUENCY: Prior to commencing any activity if applicable
1931ecda-0105-535a-8b62-876de832506a | note | ACCEPTANCE CRITERIA: The Contractor shall provide the necessary environmental controls as nominated on the approved Environmental Management Plan and identified on site.
355fe427-1393-53b2-8081-1ecbc14bd7fd | note | REFERENCE DOCUMENTS: VicRoads Standard Section 177.D1(c)
70961975-5e66-5537-9e50-b92f534d3014 | note | INSPECTION/TEST METHOD: Visual Inspection
1bd0fcb6-838b-54d9-8f85-42392afa59f2 | note | RECORD OF CONFORMITY: ITP Signed
b8e21e21-29e9-532a-a8d5-d6bcd6fbab69 | note | IHP
32479b96-1255-5b5b-ad14-85056c0b95ea | note | RESPONSIBILITY: Site Engineer / Site Foreman
dd060abc-96c5-5c60-9a25-15e806ebef17 | date | Date Completed:
| section | 5 - Stakeholder and Community Engagement
| checkpoint | 5.1 - Residents have been informed
1e5b227e-367c-5f77-9a67-8b748ba571c8 | note | FREQUENCY: Prior to commencing any activity
f4d67c25-53eb-52f2-90fc-20645efd8a5f | note | ACCEPTANCE CRITERIA: Residents impacted by construction works are to be notified by letter drop of the construction taking place, the timeframe of the works and information on how the works will affect them.
d7dcd527-45e2-506f-ba7b-63da03b055bb | note | REFERENCE DOCUMENTS: Letterdrop
b6308ad2-ee6a-5704-b5ac-d7d7f7e925e2 | note | INSPECTION/TEST METHOD: Visual Inspection
00620739-2eed-52e0-8591-a5e94331d76b | note | RECORD OF CONFORMITY: ITP Signed
6c6fa2df-b964-5e70-83dd-e4986f3fb968 | note | HP*
6565e29a-6150-5d70-a889-e43618bb4362 | note | RESPONSIBILITY: Site Engineer
ffb679e9-6907-5f99-833d-8641761cce6f | date | Date Completed:
| checkpoint | Final Inspection
9c2285d2-30fb-5a1c-9a07-c495b284ce6c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
e0a7525e-793c-5658-bdc3-a5ac0dfcc1a5 | textbox | Print Name:
4f6970ee-1664-5e7a-ba34-f8f2b914ce00 | textbox | Position:
55fe74c2-63c1-54f4-8992-1ff5579e62c5 | date | Date:
| checklist | ITP-002 - Stormwater Drainage Rev.3 | itp | ITP-002 - Stormwater Drainage |  | e488c9d4-fc8f-462c-b421-d81d3eb6e52b
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
878262a7-ba78-5284-9146-2ade51f2eba1 | note | FREQUENCY: Prior to commencing any activity
37e44d03-da34-5e24-b20f-2898aff4fc18 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are using the correct and complete set of IFC Drawings.
0caf2e34-0778-53cf-8169-0ec74d73871d | note | REFERENCE DOCUMENTS: IFC Drawings
7e5c811c-c15c-585c-a1b8-60286815fa3b | note | INSPECTION/TEST METHOD: Visual inspection
af593b87-7e0c-5052-9014-ec17a5315f3a | note | RECORD OF CONFORMITY: ITP Signed
64a1284f-0c38-5ca2-9695-ace3c6bbf735 | note | IHP
5882b175-a1a0-532f-aca2-9bda9246e6b3 | note | RESPONSIBILITY: Site Engineer / Site Foreman
390be23f-1a49-5839-ae37-2e92c5c0ebc0 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
8e442f4d-ec88-5619-a8ac-5ff15d8124da | note | FREQUENCY: Prior to commencing any activity
1ad9629f-4573-504b-8f17-6d92396c82cd | note | ACCEPTANCE CRITERIA: Ensure all relevant project documentation has been submitted and approved by Superintendent including SMP, PMP, EMP, QMP, TMP and SEQ documentation.
560c385f-d460-587e-832c-26e98f80912a | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP & SEQ
7594dcd7-aff0-57b2-9e81-0fdddc455d4e | note | INSPECTION/TEST METHOD: Visual Inspection
ec9736c3-6a27-5243-96a8-f944c5dadbc7 | note | RECORD OF CONFORMITY: ITP Signed
549e8783-bcbb-5a8e-969f-d18c85dc71b6 | note | HP
b7ab3519-eb71-5291-ab93-7e5862990091 | note | RESPONSIBILITY: Site Engineer/ Superintendent
dcf71b83-36a6-5340-a7c4-d7562aa9ff81 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.3 - Purchase and delivery of pre-cast drainage components
b33c383a-0c74-5829-9cc3-3f70230c2503 | note | FREQUENCY: Each Delivery
73ebc464-d047-549f-ac27-0d1d355344f6 | note | ACCEPTANCE CRITERIA: Precast materials to be used for construction have been inspected and are free from defects or damage.
80eac63b-dd60-5e03-9175-59bd81c79945 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.05
d89cfd19-c6e3-53e2-812b-d407649cde65 | note | INSPECTION/TEST METHOD: Visual Inspection
0fcbac55-dfaf-5961-94f6-2d57f6785754 | note | RECORD OF CONFORMITY: ITP Signed
f41a1be7-a953-538e-83c0-44cd9d61076d | note | WP
1cc1dda6-93c2-5f44-829c-5543b1980312 | note | RESPONSIBILITY: Site Engineer
c4a0bc4f-cca5-54e3-be2d-65043059a6c1 | date | Date Completed:
| checkpoint | 1.5 - Backfill material Classification
a6a94a7d-5cf6-5e2e-8783-dadc7a53e56d | note | FREQUENCY: Prior to start
10c80a2e-4df9-5050-99e2-de52d3530f76 | note | ACCEPTANCE CRITERIA: Approved compacted backfill within bedding zone to be 20mm Class 3 Fine Crushed Rock as nominated on the IFC Design Drawings
e66c41ae-f5cf-57d9-aa9d-674bfd6b8dc0 | note | REFERENCE DOCUMENTS: Dwg No. 2021-01 Sheet 1
527463b3-9d70-5ae8-a230-53c467d3687c | note | INSPECTION/TEST METHOD: Verify
23276c43-e3fe-5e84-b1ef-fdd67fad9020 | note | RECORD OF CONFORMITY: Test Reports from supplier
2242af65-9c23-572b-97af-8af0249e0f44 | note | TP
1dd8a55a-7a2b-547d-ac7e-8198aee263fa | note | RESPONSIBILITY: Site Engineer
5f0f0206-a0fa-5891-8b65-7d769cc8b37a | date | Date Completed:
| checkpoint | 1.6 - Mortar material classification
fea202ca-7721-5983-b981-2054953d8b51 | note | FREQUENCY: Prior to start
09800185-6387-5457-a08e-a4c7ebbebc34 | note | ACCEPTANCE CRITERIA: Mortar used in the laying of box culvert sections or as jointing for pipes shall comply with the requirements of clause 610.32.
a3743621-347e-59d5-89c1-0a63d6aac357 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.09 (e)
57aaad04-791b-5586-a10b-71b92001a190 | note | INSPECTION/TEST METHOD: Verify
ccacf927-5432-5109-a5d0-848c8176975f | note | RECORD OF CONFORMITY: Test Reports from supplier
86b12ff3-108f-586c-95e6-e93a481b1420 | note | TP
d5a3fcda-b7e1-5eff-8e44-a3e43f94856d | note | RESPONSIBILITY: Site Engineer
b6ec04f2-080a-52ec-bfd9-60e649ef4678 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Excavation Permit
902eca03-82ab-5141-9821-e9270d76e832 | note | FREQUENCY: Each lot
af18994d-83f9-5896-9fbc-873691bf27b8 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
793f7d26-7d89-5e33-87ea-927e6e8dcce9 | note | ○ Plant and equipment shall be appropriate for the task.
50ad6c45-5b68-5106-98b1-1082a84d9305 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation.
5cd697c9-1f47-5228-82ca-6b2b1cfc5fe8 | note | REFERENCE DOCUMENTS: Excavation permit
fbd101fe-4f53-50f8-beba-e26d8a1a30e7 | note | INSPECTION/TEST METHOD: Verify
fbbff0bb-0c54-5af4-8d22-dffe0890fca5 | note | RECORD OF CONFORMITY: ITP Signed
7d0aae82-afbf-5e92-9094-9be289b664d9 | note | IHP
0414c53d-90c2-535b-99ee-64a4bad6bd4e | note | RESPONSIBILITY: Site Engineer
8084f71a-cc77-5139-ad51-5fbeac745997 | date | Date Completed:
| checkpoint | 2.2 - Conformity with Drawings
8aa788c0-a789-5845-ac33-161a8a10a422 | note | FREQUENCY: Prior to Excavation
a97ed294-4407-5337-8a0b-5b1347c15439 | note | ACCEPTANCE CRITERIA: Prior to commencement of excavation for the pits and drainage lines the Contractor shall conﬁrm the position of all drainage components with the Superintendent.
77453e86-f2e0-5934-aa4b-19f1d7a50a44 | note | – Unless specified otherwise the tolerance on location of pipes compared to the design or a change to the design notified in accordance with this clause shall be:
249c4f55-6672-5e53-b499-2bcb098664fd | note | (a) offset of entry pits required to match lines of kerbs or barriers ±20 mm
6e7ca09d-46d4-5ee9-83c5-ec8865313450 | note | (b) plan location of pits other than offsets to kerb lines or barriers ±100 mm
b7b7a78f-68cb-5c9a-bfa3-b91aba1bf666 | note | (c) invert level of pipes at pits ±50 mm
5fbb873d-d2e7-5d5e-8d9f-583550443604 | note | (d) departure from design grade of pipe runs ±10 mm in 10 m provided minimum grade is not less than 1:200
2a85a98b-3e21-533e-8e0c-5ac36e213f44 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.09
3d0c98f5-ff9e-5b82-b9ec-401b75db9637 | note | INSPECTION/TEST METHOD: Visual Inspection
5d45a5b4-74f1-569c-807a-5fc6d6ab7394 | note | RECORD OF CONFORMITY: ITP Signed
09b86719-d57b-544f-a58c-1f4a638277f2 | note | HP
d0cfe3f4-08da-5664-841c-c9c57412574b | note | RESPONSIBILITY: Site Engineer/ Superintendent
ce446181-369f-593f-8f7e-b3fe7674d362 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.3 - Excavation
94d031a1-a4ca-5430-9969-b41ffa54c489 | note | FREQUENCY: Each Trench
54e30af3-ff22-5e84-b667-b8609cee2700 | note | ACCEPTANCE CRITERIA: For pipe culverts, the width of trench at and below the level of the top of the pipe shall be such that the horizontal clearance from the outside of the pipe to the wall of the trench is within the limits Min 300mm and Max. 600mm.
1bea3ccc-2aa0-5cfa-bb13-49bdd87a051c | note | REFERENCE DOCUMENTS: VicRoads Standard Section Table 701.151
8cb27d3e-4a9b-5bae-981f-1b3de24b94a0 | note | INSPECTION/TEST METHOD: Visual Inspection
07a3c851-3f73-5a2f-8007-52bb166b9e8c | note | RECORD OF CONFORMITY: ITP Signed
eaae2904-5ccc-5d41-ae6c-a4f6b32d1248 | note | HP
f7977e83-a5a5-592b-bdf8-a64dbc004d44 | note | RESPONSIBILITY: Site Engineer/ Superintendent
223ecfec-17c8-5e9b-af0f-3152ea619f18 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Compact base of trench
b9a20e12-1599-506b-8da5-1450e72ad784 | note | FREQUENCY: Each Trench
9c09e78e-6c37-5488-aefb-b54c5714f0aa | note | ACCEPTANCE CRITERIA: The base of the trench shall be compacted to refusal using mechanical plant.
a169e8dc-f622-5102-bc16-10f4a5b5a4c6 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.15
2e0ebaab-f1da-53d5-9b4d-012718d54295 | note | INSPECTION/TEST METHOD: Visual Inspection
fc9edd29-d57f-5792-803e-10dcbe9ba758 | note | RECORD OF CONFORMITY: ITP Signed
7d1fc4fb-0f00-58fa-849f-cba135cda36d | note | WP
46078206-f164-5b63-a05e-8e6307e80b3f | note | RESPONSIBILITY: Site Engineer
c13cc35e-26fb-5deb-8eb3-fa1f00e51e08 | date | Date Completed:
| checkpoint | 2.5 - Placement of Bedding Material
5341b554-5fde-57af-ad62-b859c1c76ac9 | note | FREQUENCY: Each Trench
e5825af1-dd7c-5bb2-91c9-ffe638b56cc4 | note | ACCEPTANCE CRITERIA: Bedding material shall be compacted to no less than the below thickness:
ed3d8890-f378-548b-9125-08502860b7d5 | note | ○ 100mm where D < 1500mm
5589d273-6c40-51d5-8bb8-1f99448aedb3 | note | ○ 150mm where D > 1500mm
4379da7d-9b8c-5367-9b0c-1a4eacd0ba0c | note | – where D is the nominal pipe diameter or culvert width.
56aecc30-3486-58f7-872d-97551fbba1e8 | note | REFERENCE DOCUMENTS: Dwg No. SD-D8-1 Sheet 5
67b5cc93-38b9-5917-b20f-a89d3d777ebf | note | INSPECTION/TEST METHOD: Visual Inspection
9fd47ff4-7831-5ff0-86f3-f6efbc9092ad | note | RECORD OF CONFORMITY: ITP Signed
abf54503-72bf-522a-8a76-d647ed1c1915 | note | WP
57813566-2afa-5796-85d3-d02018dcbbab | note | RESPONSIBILITY: Site Engineer
d873a21c-3155-5606-b385-40683dd81c47 | date | Date Completed:
| checkpoint | 2.6 - Laying of Pipes
ee2a6bdc-69a6-5556-9c37-76e160f0b77e | note | FREQUENCY: Each Line
162d4706-3a5f-562f-bace-d01bb6f7b1d3 | note | ACCEPTANCE CRITERIA: Laying of pipes shall not commence until the Contractor has verified that pipe bedding complies with the lines and levels of the design drawings and that pipes are not damaged and comply with the requirements of clause 701.04 and Clause 701.05 respectively.
2c9b409b-522e-55d2-91fd-8a5f31f2882d | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.17
7264edc4-8688-5689-b233-4d5c3207e6ce | note | INSPECTION/TEST METHOD: Visual Inspection
9d44814f-b76d-532a-b22c-327e94c97e3a | note | RECORD OF CONFORMITY: ITP Signed
abf5fd0e-0664-5072-8e41-c4d233f126e8 | note | IHP
30add7b4-bbd3-5dc4-b385-0185a09e6b91 | note | RESPONSIBILITY: Site Engineer
5f4c7324-e158-5abe-ade9-3352839ca45f | date | Date Completed:
| checkpoint | 2.7 - Jointing Pipe Sections
ed28a51b-67e2-5b76-8ffd-768d9542dd9e | note | FREQUENCY: Each Line
9256604d-33f9-52dc-9c29-942dbeec618c | note | ACCEPTANCE CRITERIA: Join pipes with rubber rings in accordance with manufacturer's instructions, check that the rings are clean and undisturbed. Any disturbed rings are to be cleaned and reassembled
a3464d1f-c1c3-5b47-b71c-ffc6319e58a8 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.18
d37bf20d-8c9e-5341-ae15-f3346e8e6d56 | note | INSPECTION/TEST METHOD: Visual Inspection
47276c0a-d7a1-530f-909c-d68c12a11835 | note | RECORD OF CONFORMITY: ITP Signed
7004e86f-705b-59e3-bc9d-780c93613af1 | note | WP
6e1a3b43-ec6b-5106-97cb-e286cb5c830f | note | RESPONSIBILITY: Site Engineer / Site Foreman
ca0e3b22-0d56-5bce-9b4a-d069128aa95a | date | Date Completed:
| checkpoint | 2.8 - Jointing to Pits
0452ffc9-eebb-5bde-8b2b-17ce90f26998 | note | FREQUENCY: Each Pit
50f6fc1c-1aac-566d-8b63-efd83697d8e4 | note | ACCEPTANCE CRITERIA: The joints between various components such as drainage pits, access chambers and pipes shall be made watertight using a cementitious mortar in accordance with the requirements of clause 610.33.
78ca3ee0-4419-5c1b-a422-c2d2185258a6 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.15
55ba6c0f-b162-5d81-a7bd-32a50f50412b | note | INSPECTION/TEST METHOD: Visual Inspection
787c2072-5856-547a-b144-5d8faaa28a22 | note | RECORD OF CONFORMITY: ITP Signed
57756f83-18f9-50b5-b336-9082cd2db719 | note | WP
25f48ce0-08d0-5d71-99f8-767dc5be11d9 | note | RESPONSIBILITY: Site Engineer / Site Foreman
e001a390-51ad-553b-bb73-dc6a70576cde | date | Date Completed:
| checkpoint | 2.9 - Place & compact backfill material over pipes
975f9016-2be7-5866-9774-ba5eedfb2dcb | note | FREQUENCY: Each Lot
58ea88b9-3839-56ff-9d11-aaa9c580038c | note | ACCEPTANCE CRITERIA: Unless the pipe is installed through an existing paved area, selected and ordinary backﬁll shall be placed as follows under, around, and above the culvert after the sections are bedded and compacted as speciﬁed in Clause 701.15.
78716c5d-f4e2-550f-bf2b-27904b34e63b | note | (i) Culvert Under Area not to be Paved: The trench shall be backﬁlled with selected backﬁll material to a level 0.3 m above the top of the culvert and with ordinary backﬁll material above that level.
1c072083-329f-5fcc-b8a7-966e3ad8076e | note | (ii) Culvert under area not to be paved: The trench shall be backfilled with selected backfill material to a level 0.3 m above the top of the culvert and with ordinary backfill material above that level.
45213fdb-5eb6-5d77-be55-9b37a8030517 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.19, Dwg No. SD-D8-1 Sheet 5
0bd8d0fa-42a3-5e22-a55a-9bd36977dd55 | note | INSPECTION/TEST METHOD: Visual Inspection
e0c6067a-c0b8-595b-b37e-24093ec51244 | note | RECORD OF CONFORMITY: ITP Signed
1a2344f5-d58c-5d01-8faf-e60510e1e372 | note | IHP
ef038b89-7c9c-5807-9295-d654bd91f5d2 | note | RESPONSIBILITY: Site Engineer / Site Foreman
94da6fa5-4b84-5644-b7e1-4bfae7672cb3 | date | Date Completed:
| checkpoint | 2.10 - Place & compact backfill material around pits
66a425a6-c423-5c75-9492-82daadee1ff7 | note | FREQUENCY: Each Pit
0d847b4f-bb27-5140-9e90-76bd1b2e9908 | note | ACCEPTANCE CRITERIA: Backfilling around drainage pits shall be placed in layers not exceeding 300 mm loose thickness and compacted to refusal using handheld mechanical equipment
92906a58-9f9a-567e-9354-c259be7548fb | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.18
e684f538-fd48-54b9-9bea-dd6991341de6 | note | INSPECTION/TEST METHOD: Visual Inspection
291234ee-bcb8-59ee-85ca-64639f8d3704 | note | RECORD OF CONFORMITY: ITP Signed
852dcbec-6b50-57e9-b597-6625ded568ad | note | WP
935d8f3f-7c10-58a3-8966-9da157aa0afb | note | RESPONSIBILITY: Site Engineer / Site Foreman
f589a928-b039-58c9-8642-7c8d067b6339 | date | Date Completed:
| checkpoint | 2.11 - Backfilling with 3% cement stabilised
4df3b031-e2bb-5993-a214-ed2eb2e46d87 | note | FREQUENCY: Each Trench
2400bd2b-9397-54eb-9eac-14b66d394998 | note | ACCEPTANCE CRITERIA: Where approval is given from superintendent, culverts in trenches may be backfilled to half the pipe diameter or box culvert height with 3% cement stabilised FCR with a water content sufficient to ensure penetration beneath the pipe or box culvert invert without leaving free surface water.
8f0f2e08-4ea5-567d-b735-42d561fbab86 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.19 (c)
1a37a0c8-5d7c-51a8-992d-cf4bce7d23e0 | note | INSPECTION/TEST METHOD: Visual Inspection
2211b506-faf4-5e5d-8db3-95f77406033c | note | RECORD OF CONFORMITY: ITP Signed
f57df8c6-1781-56e6-a391-bf871aebc8d4 | note | WP
08413c42-9fd4-5c4d-bfef-84c80f1fb81e | note | RESPONSIBILITY: Site Engineer / Site Foreman
d853be8f-df39-5770-a34c-1ed8c71529ca | date | Date Completed:
| checkpoint | 2.12 - Step Irons & Ladders
1f05cd78-06d6-5484-91d9-4565664a7177 | note | FREQUENCY: Each Pit
e67fcec0-1583-5942-91e6-ad09e9bb4765 | note | ACCEPTANCE CRITERIA: Drainage pits greater than 1.0 m deep shall be fitted with step irons or ladders in accordance with AS 1657 and this Section.
4792ed17-fcd4-5f53-9e32-51514062ce1b | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.12
2dcd84bf-088e-51a0-9897-773887625632 | note | INSPECTION/TEST METHOD: Visual Inspection
81b059ea-fd1b-56ce-be6b-1e17ed2d471b | note | RECORD OF CONFORMITY: ITP Signed
2f16b8f7-1238-55c8-8f9b-26a4729c3ac7 | note | WP
cd256ce1-64a8-5961-a954-d81c5f1ef332 | note | RESPONSIBILITY: Site Engineer / Site Foreman
c4720de7-a7c3-5687-8dcf-b5e2e4bfe16f | date | Date Completed:
| checkpoint | 2.13 - Construction Tolerances
1af997aa-0dc8-5abe-97a9-e4e7da8fe8be | note | FREQUENCY: Each Lot
58152be8-4bb0-5503-83d2-edf6433b8283 | note | ACCEPTANCE CRITERIA: The tolerances listed in Clause 610.47 are the allowable deviations of the finished product from the dimensions shown on the drawings. These tolerances will be a basis for acceptance of the work.
3ea073de-cfc7-55df-b9b2-fe9c211e7702 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 705.19
d1768480-19c3-5812-81e3-a7999679e244 | note | INSPECTION/TEST METHOD: Visual Inspection
d6f2c823-5405-5830-ab67-22df64390e0e | note | RECORD OF CONFORMITY: ITP Signed
887ebde1-7c83-520e-96c2-95ce7b6c154d | note | WP
1b6654ca-90c6-5a65-91be-9a1e21f447de | note | RESPONSIBILITY: Site Engineer / Site Foreman
d5ac1a17-825e-5159-95d0-6cd11614e5f4 | date | Date Completed:
| section | 3 - Testing & Completion
| checkpoint | 3.1 - Compaction and moisture content of backfill & bedding material
4f0b0322-4385-5971-aafa-92792e6fadef | note | FREQUENCY: Each Lot
ba4a677c-6595-58a6-bee8-47b740c1e398 | note | ACCEPTANCE CRITERIA: The Contractor shall test the bedding and backfill material at a frequency as shown in Table 701.291 to ensure that all materials comply with the specified requirements.
702b0913-0976-5a84-8ccd-79d3649b586f | note | REFERENCE DOCUMENTS: VicRoads Standard Section Table 701.291
ec918495-6c37-5701-a836-e4d5b355037f | note | INSPECTION/TEST METHOD: Verify
dc82a0fb-c033-53f6-91eb-1da905a9b734 | note | RECORD OF CONFORMITY: Test Reports
e775aac1-9d82-5f20-a47e-9b94f07e4156 | note | TP
82867338-f0bf-5f0f-804f-1bd36c1a2b55 | note | RESPONSIBILITY: Site Engineer
32ca3856-dfdb-5600-88ed-77758dd4e05e | date | Date Completed:
| checkpoint | 3.2 - CCTV inspection
c507e46f-398f-5644-acf5-a3bca9f02a97 | note | FREQUENCY: Each Lot
0cb91a91-88f9-59be-b488-352be0eac77e | note | ACCEPTANCE CRITERIA: Unless approved otherwise by the Superintendent, all drainage lines constructed beneath pavements shall be inspected, after completion of earthworks to subgrade level and prior to construction of pavement layers, by an independent testing organisation using closed circuit television (CCTV). Reporting of the CCTV inspections shall be in accordance with WSA 05 2013 – Conduit Inspection Reporting Code of Australia, published by Water Services Association of Australia.
479394b0-b468-5eb8-9d77-aa979176a268 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.3
0dcdad34-04b8-5543-b7f9-34345d1443f9 | note | INSPECTION/TEST METHOD: Visual inspection
262a6cda-5910-5dc6-a79c-160219267004 | note | RECORD OF CONFORMITY: CCTV Report
8039a369-682f-57a5-8289-1ead22b2563c | note | HP
f232c2a2-d350-5bc6-afef-58e4175c9879 | note | RESPONSIBILITY: Site Engineer/ Superintendent
69a68a92-663f-56d2-874d-e54178755cf5 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 3.3 - Repairs
44d4ec5a-a583-5e7b-ad29-b50cf3857cf3 | note | FREQUENCY: Each Lot
8ffbef96-c9d2-56ee-90b1-33b5f01ab55c | note | ACCEPTANCE CRITERIA: No repairs shall be undertaken without the Superintendent’s approval of the repair materials and procedures.
70c71141-18c6-5b7a-b648-b43ac8bd6163 | note | REFERENCE DOCUMENTS: VicRoads Standard Section 701.31
96ce90d8-f9e2-5656-8f83-3da4a5326325 | note | INSPECTION/TEST METHOD: Verify
6f4e9d68-8137-5b6f-9dca-e444b6990af4 | note | RECORD OF CONFORMITY: ITP Signed
189be06b-09b0-5df4-aaf7-1afeb1d19f02 | note | IP
a6cb5a63-2df4-5f31-9c4e-79cdd86f0889 | note | RESPONSIBILITY: Site Engineer/Superintendent
50fac880-48bc-501e-b455-7b4e34afd43c | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection
01d6c757-4946-5091-8a22-149c8caf344c | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
1f51fa99-4f0e-5bb0-ab9c-84a45dbebb49 | textbox | Print Name:
e65c7bad-7fab-5e27-978d-a99ec654b283 | textbox | Position:
0d2d05fb-a8c6-5aa5-a11f-2b5025f8b1db | date | Date:
| checklist | ITP-003 - Subgrade Preparation | itp | ITP-003 - Subgrade Preparation |  | a39b1a27-3c38-454b-ac5d-1d46cbf4419e
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
fd1b076f-da34-55e2-94f9-42e85d9993d9 | note | FREQUENCY: Prior to commencing any activity
9dd137fe-2cdf-5414-956a-68f17e05c805 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
c6f3a938-c055-5cd0-9f5a-eafdfd078652 | note | – using the correct and complete set of drawings
329ac690-43ff-525a-9f73-8ca31c78b98e | note | – all drawings are the latest revision
2f5fd915-6df9-54db-bf9f-adfa7bfed5fc | note | REFERENCE DOCUMENTS: Drawings and drawing registers
31284d07-85fa-5486-8b62-18f542519404 | note | INSPECTION/TEST METHOD: Visual inspection
d594abea-06e9-5485-bd2f-fed07d018e5b | note | RECORD OF CONFORMITY: This ITP signed off
54cae127-7abf-5076-bbea-bd91d98082d1 | note | HP*
3d123883-6eae-573a-8686-fe0d99b69937 | note | RESPONSIBILITY: Site Engineer / Site Foreman
fa484ef3-0104-525e-9d9e-fd17f8179e87 | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
98c7032e-8b67-5065-b6d4-1ee26a80f443 | note | FREQUENCY: Prior to commencing any activity
f2319650-508b-534d-a6c4-0437bc233265 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: PSP, EMP, TMP, JSEA, SWMS & WP
52f9331f-2fca-5e51-b339-abddb12c63bc | note | REFERENCE DOCUMENTS: PSP, EMP, TMP, JSEA, SWMS, WP
a4245cf8-2c97-5cdc-9311-264c006610af | note | INSPECTION/TEST METHOD: Visual Inspection
94b00314-5bd7-58b3-abdf-b43c254e2113 | note | RECORD OF CONFORMITY: This ITP signed off
9965fd42-be91-54c2-a091-02149cebbee1 | note | HP*
ed6d0f97-db3a-5c40-8070-3690fbaf34b9 | note | RESPONSIBILITY: Site Engineer / Site Foreman
41d72665-2d43-5310-9c41-747090d4fb26 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Survey Set-Out
122830c6-1a0e-5961-9126-e3d26d9f4d76 | note | FREQUENCY: Prior to commencement of excavation
ff894868-dce8-52b6-9203-2e35cab1771c | note | ACCEPTANCE CRITERIA: Area has been set out in accordance with the drawings
94452495-1547-51e3-9ad6-554155e05941 | note | REFERENCE DOCUMENTS: Work Procedure
57d36b2f-c4d1-55d3-a9da-0c2eb708dcda | note | INSPECTION/TEST METHOD: Verify
5c681e26-1fa3-5021-8a38-ab19792d1998 | note | RECORD OF CONFORMITY: This ITP signed
d2024e6f-4cee-534a-ac2f-228b493adbcb | note | IP
82363942-4b58-5bdd-bf68-2d5ca0437bfc | note | RESPONSIBILITY: Site Engineer/ Surveyor
a12a20a1-8a21-5960-9876-9a4132d6ee91 | date | Date Completed:
| checkpoint | 2.2 - Excavation Permit
b5b186e6-f007-5e24-8c87-4dc8837acdec | note | FREQUENCY: Each lot
1ea45578-2b7f-5e90-a360-22c9bd2f5c24 | note | ACCEPTANCE CRITERIA: An excavation permit must be issued prior to any excavation commencing.
bf733d03-486d-5fa3-a50c-2916c13b2ee9 | note | ○ Plant and equipment shall be appropriate for the task.
ab995707-74af-5079-82f3-a97e21f7af98 | note | ○ Excavation operations shall not disturb areas outside the limit of excavation
6cc125bf-a7e8-5641-9581-9a9f7b193bea | note | REFERENCE DOCUMENTS: Excavation permit
6e256e96-8e0a-56ba-b763-93d2a7fe6b5a | note | INSPECTION/TEST METHOD: Verify
52e0a5be-2875-5d26-9915-aa6ade6fd23e | note | RECORD OF CONFORMITY: This ITP Signed Off
9a8ea824-783b-5f63-b64c-17d7541b1e4c | note | HP*
c9e9e479-00c0-5efd-8408-534e5759575c | note | RESPONSIBILITY: Site Engineer / Site Supervisor
a3c77827-3982-5e67-8086-f66aee44766e | date | Date Completed:
| checkpoint | 2.3 - Subgrade Material Properties
8c295e02-3270-5291-b706-5c18d0099fb3 | note | FREQUENCY: Each Lot
9c2467c4-a906-5adf-b169-b6f673620383 | note | ACCEPTANCE CRITERIA: In situ material within 400mm of cut floor level to be consistent with Type B. i.e. CBR>assigned value (must be greater than 2), Swell < 2.5%.
02b64469-dbaf-51eb-b4e7-9cc4004f283e | note | ○ If parameter met rip and re compact 150mm. If parameters not met remove 400mm of material and replace with conforming type B.
debdc627-d543-5963-8754-de902dbf4118 | note | REFERENCE DOCUMENTS: Cl 204.06e
df5e1d40-ce5e-52eb-83d7-82522cda4b18 | note | INSPECTION/TEST METHOD: Test Point
ae6cb01a-cb82-55a6-9185-939d6e1f1922 | note | RECORD OF CONFORMITY: Test Reports
0128001d-8848-5a28-9573-49251ad0f2b9 | note | TP
809cad17-516e-59d2-98eb-953ec6602643 | note | RESPONSIBILITY: Site Engineer / Site Supervisor
8e32830d-4943-52e6-adb3-73429ce539fb | date | Date Completed:
| checkpoint | 2.4 - Inspection of Subgrade Material
0893c3d5-20c5-564e-bf51-c883c94ed432 | note | FREQUENCY: Each lot
b17cbbda-cfbc-57e1-87f3-34f8972e64ca | note | ACCEPTANCE CRITERIA: Prior to commencing excavation in any area and during excavation work, the Superintendent and the Contractor shall inspect each type of material encountered and subject to verification by appropriate laboratory testing, agree on the category of the material in accordance with Clause 204.04
3d7664a9-a574-51ca-9e8a-e0eb4b12afa5 | note | REFERENCE DOCUMENTS: Cl 204.06c
adcf61bc-21c4-530d-ada9-d437b7ed53d0 | note | INSPECTION/TEST METHOD: Verify
0acd8517-41ea-5bac-9db5-6607f8a8d848 | note | RECORD OF CONFORMITY: This ITP Signed Off
df5756f1-58f3-53b5-b0d4-9e1aeeea98e1 | note | HP
0c285d91-b64f-5096-be22-14afc05fe437 | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
ac31096d-5108-56c6-bc1e-2f432cf6c842 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.5 - Material classified as silt
6853a042-3235-5119-b77d-a08672f16aef | note | FREQUENCY: Prior to Commencing
2ba54d47-0a28-5fdb-8362-4d85e6c98b14 | note | ACCEPTANCE CRITERIA: Material classified as silt, either before or after compaction, is not acceptable as Type A material without stablisation to the satisfaction of the Superintendent
52b4a208-1adb-5502-b645-6d52c6fcb311 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.04(b)
e25ec8db-b8af-5d7c-9637-34c1bbe755d1 | note | INSPECTION/TEST METHOD: Document Review
13329f11-bd60-5b54-b409-1ee12ec08d29 | note | RECORD OF CONFORMITY: Superintendent satisfied with Stabilisation, Signed ITP/records
11d964a0-fa6a-5a50-b872-c8dcd27a1ae8 | note | HP
c8d1a168-f080-5a8e-82db-442422b73367 | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
217f03ca-bbda-510b-afff-a1a18a94c7d0 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.6 - Acceptance of Rock Subgrade (when applicable)
ac2123aa-4bb0-578b-855e-54e46a95c307 | note | FREQUENCY: Prior construction of the regulating layer
da123626-4c5a-5864-9c5a-5b79a9008575 | note | ACCEPTANCE CRITERIA: Prior to construction of the regulating layer, the areas of rock subgrade shall be presented to the Superintendent for acceptance.
c5476253-4247-5abb-b517-5ae34cb55b3f | note | ○ Any necessary amendments to the subsurface drainage design including transverse subsurface drainage at the interfaces shall be presented to Superintendent for review.
7da367c6-ab75-551a-a687-da6f12f003d2 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl. 204.06(f)
4239cbf5-ec9b-5656-85a6-eb0cab663a7b | note | INSPECTION/TEST METHOD: Site Inspection/ Document Review
acaaacc3-8f32-5f94-8d8f-7f748da35168 | note | RECORD OF CONFORMITY: Superintendent acceptance, Signed ITP
d3bb0ba4-cbd4-5cee-a65d-f5de04058125 | note | HP
15d97a3b-cb99-51f4-83f1-82918d70b74e | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
c59296d0-512d-5305-8830-19c81c75fe09 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.7 - Unsuitable Material
16fec5d9-9f8a-5217-bca4-f4905507388d | note | FREQUENCY: Each Lot
9d0b31e4-728b-56b5-8240-62dff51365b9 | note | ACCEPTANCE CRITERIA: Where Unsuitable material is encountered, proposed in-situ treatment must be submitted to the superintendent for review.
09fdbee9-c17f-53c5-b38c-958d14846b03 | note | – As per RFQ Section 200, Clause 200.3, the unsuitable material shall be jointly inspected by the Superintendent to determine the extent of the rehabilitation required.
2700ee40-2b20-5ab6-8cbd-b1c1caa88c78 | note | – Backfill of excavated area shall be with Type A material.
cac98c34-a078-550b-9f6a-c6eb6165ad11 | note | REFERENCE DOCUMENTS: 204.07(d), RFQ Section 200, Cl 200.3
a63cd787-da0b-59b4-b14d-c5f5910ea294 | note | INSPECTION/TEST METHOD: Visual Inspection
ba190829-54c0-5c9b-b8a1-fa0d4d18cd39 | note | RECORD OF CONFORMITY: This ITP Signed Off
517139d3-7052-5c17-af16-00636be3b71d | note | HP
728df4b5-3ba9-5685-b304-97c0416309e0 | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
93b795fe-9c71-5a46-a56a-800bdb1a718c | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.8 - Groundwater
c0a8cbeb-1e5a-5975-a4d8-a112f11e2d1c | note | FREQUENCY: Each Lot
cc564d03-377f-5942-8ca0-a5988eb98cf0 | note | ACCEPTANCE CRITERIA: Where groundwater is encountered the contractor shall notify the superintendent and submit proposed action for review.
d21c6dd2-6b0e-5e3f-9dcf-e9453af0fb2e | note | ○ The Contractor shall submit any necessary approvals from relevant authorities for the treatment and disposal of this groundwater
534f0da2-6788-5e81-aeaa-b011f26b9618 | note | REFERENCE DOCUMENTS: 204.06 (h)
c2d54b1b-b6fd-5bd0-b4b0-1d96050922f1 | note | INSPECTION/TEST METHOD: Visual inspection
b42dfe12-d0e7-5417-a802-919eea09cb93 | note | RECORD OF CONFORMITY: This ITP signed off
ffd65da1-72bf-5505-932e-c7d22eafa6e5 | note | HP
07ad17cd-faa5-5dfa-a6d1-660717727850 | note | RESPONSIBILITY: Site Engineer/ Superintendent
0a8b6b9e-5a3a-5e62-8563-ea4575df5c57 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 2.9 - Subgrade Level and Shape
b0524712-686c-5f97-bd25-204b90f77d11 | note | FREQUENCY:
c8d708e6-7cd9-5a0c-879a-4e15c6fb5505 | note | ACCEPTANCE CRITERIA: Level measurements shall be taken at random locations over the area of the lot in accordance with Section 173 – Examination and Testing of Materials and Work (Roadworks). The number of measurements taken within each lot shall not be less than the number specified in Table 204.031. Random level assessments of the surface shall be undertaken in lots not exceeding 4000 m2.
bde54877-8452-52c1-ad43-96e33a903573 | note | Scale B:
0f150037-6806-5a4c-8936-25abe7a6cffd | note | ○ Measurements per lot = 40
dd1fdbd2-b06b-5b24-90a9-80632f16ab6a | note | Surface level tolerances:
84f0a340-fd42-50c6-9e7a-5ddcd1e232d0 | note | ○ Range x = +5, -25mm
f7022469-8fd6-56f1-ac32-9a06c01b16ef | note | ○ Standard Deviation = 15mm
3c0f2f29-c68b-5c10-af7c-bf8aed3ca52f | note | REFERENCE DOCUMENTS: 204.03(g), Table 204.031
852265e2-341a-5e27-9c09-8dd359729463 | note | INSPECTION/TEST METHOD: Survey
66f85b22-cc90-5d31-aa92-e7d08248e681 | note | RECORD OF CONFORMITY: This ITP signed off; Survey Report
6d213c5f-29fb-5a2f-83da-a9b6cdb63d7c | note | SCP
83b9b619-7d36-5304-9cd3-68543b647900 | note | RESPONSIBILITY: Site Engineer / Surveyor
dfdc7820-f7b2-58b6-89d3-99c29f79d28f | date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Proof Rolling
a247ccc2-0473-5fbc-87f2-28780e47686f | note | FREQUENCY: Each Lot
8153b45e-a793-5d2e-931d-e588d583f1a0 | note | ACCEPTANCE CRITERIA: Proof rolls to be conducted in accordance with Section 173 of the VicRoads Standard Specification
af3da4c2-f48a-568d-a7ae-3731202a5a06 | note | REFERENCE DOCUMENTS: Section 173
39743c70-89df-5400-bfae-675991e7ecea | note | INSPECTION/TEST METHOD: Visual Inspection
df458ab0-6d5f-5350-99da-69dd920d87be | note | RECORD OF CONFORMITY: This ITP signed off
9affccc7-fa8a-5fff-8315-7a16ce8837ba | note | HP*, WP
edc4fd9c-a3e0-5e7f-b96d-75909a3b61ea | note | RESPONSIBILITY: Site Engineer / Site Supervisor / Superintendent
aef6e8fc-d1b4-5104-888b-b484f6bc1e26 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 3.2 - Compaction Testing
6ad446f4-7e5b-516c-bc71-a72aa197e47e | note | FREQUENCY: Each Lot
47764f60-d923-534c-8fa7-01058f527b4a | note | ACCEPTANCE CRITERIA: Scale B
219ddfe5-1d99-5ca7-8b1f-359bcdf08816 | note | ○ All Type A Material = minimum mean value of density ratio = 98%
54149603-2bdd-51b2-837c-46e5f1f4c30a | note | ○ Ripped and re-compacted material below Cut Floor Level = minimum mean value of density ratio = 98%
f44741d9-3e11-5be2-b19f-f22d404280c3 | note | REFERENCE DOCUMENTS: Table 204.131
cf0621f0-c9a2-5a10-9f71-9bb7932f8b8d | note | INSPECTION/TEST METHOD: Test Point
9c6571a0-6fa0-5a4c-a7e5-244f59dc175d | note | RECORD OF CONFORMITY: Test Records, Lot Register
d3580aec-e678-5175-9364-bd0910e2e22c | note | TP
17f524c7-85c0-51ae-ba64-c9199df880e7 | note | RESPONSIBILITY: Site Engineer
5ac338a0-aad7-5121-886f-0e4db375be26 | date | Date Completed:
| signoff | Signature Required
| checkpoint | Final Inspection
214e734b-94f0-5a66-bdfc-3b394f2fab57 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
34f95e1c-1573-5fe3-9de8-f5b8bb196010 | textbox | Print Name:
4f559ff1-cb4a-59fe-bbec-9ff1e630f63b | textbox | Position:
39b9b2b8-bcc3-5f07-a14c-b25e4395455a | date | Date:
| checklist | ITP-003a - Sub-Base Construction | itp | ITP-003a - Sub-Base Construction |  | fe91fae0-ceb5-4e8c-9547-b1f4ae59fba6
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
ce0d24f1-b6f4-57e4-b2b6-c23a1ffb645b | note | FREQUENCY: Prior to commencing any activity
a950ebe8-c9f0-5cc3-8817-def5c233207a | note | ACCEPTANCE CRITERIA: Ensure that the most recent copy of the design drawings are used and have been Issued for Construction (IFC).
5c7ec2a9-365d-5088-b185-99398d529b58 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
7eb2915e-b285-5667-84cc-4dd6b8ca9ace | note | INSPECTION/TEST METHOD: Visual inspection
15647d04-dc32-5a1c-9572-1820c4ee959e | note | RECORD OF CONFORMITY: This ITP signed
74047642-7e72-5b5b-969b-406f30c729e2 | note | WP
c72869b0-2ab5-5004-b1eb-11c10de2558e | note | RESPONSIBILITY: Site Engineer / Site Foreman
2a3c2870-a1eb-5731-aee1-2c82be566de5 | date | Date Completed:
| checkpoint | 1.2 - Material Mix Design
b1208f0e-da29-5b5a-9e8b-0f27c2af0f62 | note | FREQUENCY: Prior to commencing any activity
b998977d-8fc7-548b-be5a-a077debdc018 | note | ACCEPTANCE CRITERIA: Material proposed for import as sub-base material meets the requirements of VR Section 812. Obtain material compliance data from the supplier.
ae97b377-eca0-57ff-8e57-e88d0c931427 | note | REFERENCE DOCUMENTS: Cl 812.04, RC 500.02
156dcbbf-dc53-5e9b-9b0e-1617e0c08314 | note | INSPECTION/TEST METHOD: Document Review
9af1bd1e-9f3f-589d-9761-fad37fd740b2 | note | RECORD OF CONFORMITY: Mix Design VicRoads Approval
93b71dcc-a9f3-5a5a-88bf-cdd4d6a30dd6 | note | HP*
c443aa9f-7850-54ba-92d7-be5571bb6f71 | note | RESPONSIBILITY: Site Engineer
2b633278-083b-5a78-88ab-4f89f6519455 | date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
7586c4d2-9280-50e2-89b6-2f3a820e037a | note | FREQUENCY: Prior to commencing any activity
22417342-50db-500f-9528-ddc1b962df26 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
38966898-60f3-5386-8d7b-f02125e8ff17 | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
6c05e407-8ca4-54eb-a65d-adbca4a9acc3 | note | INSPECTION/TEST METHOD: Visual Inspection
99641113-2f03-5964-a6d3-030717fb703a | note | RECORD OF CONFORMITY: This ITP signed
df784342-b1ba-5f71-b3b7-e5cd61348a5d | note | HP*
d4ed3233-07ee-57da-8a8a-f1cc1b70f0de | note | RESPONSIBILITY: Site Engineer / Site Foreman
92c90a6a-7d23-58f7-9342-b4650420b31e | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Transverse Joints
993ed332-af9c-5b96-80bb-b98e68309861 | note | FREQUENCY: Check prior to placing material
7ae822c0-6a73-5ebc-83d5-3ac177c849fa | note | ACCEPTANCE CRITERIA: Material should be spread to minimize number of joints
d319c6ae-f678-58d9-9e6b-d1ae7eca50a4 | note | ○ Transverse joints shall be offset from one layer to next by not less than 2 metres
bbeca6ea-48cd-5be9-81fd-77004bea0341 | note | REFERENCE DOCUMENTS: Cl.304.08 (a),Cl.304.08 (c)
93ca8e1b-3634-5aa4-82b1-0acd91af3edd | note | INSPECTION/TEST METHOD: Visual Inspection
ae479608-e67a-542c-a2f4-1a132d3ea46b | note | RECORD OF CONFORMITY: This ITP signed off
5744958c-a44b-5cc4-86f0-91fc560ec406 | note | IP
d026de9d-a7df-558f-97be-7d0768474da7 | note | RESPONSIBILITY: Site Engineer / Site Foreman
98714f57-efa2-5977-aa1f-84998d8736bc | date | Date Completed:
| checkpoint | 2.2 - Longitudinal Joints
34b44696-f87c-5315-93f6-c8623c82a78e | note | FREQUENCY: Check prior to placing material
a293cca9-14d7-542e-b844-a3836d2c6da0 | note | ACCEPTANCE CRITERIA: Material should be spread to minimise number of joints
76c6cda6-10ac-5c72-988f-2f3289f909d3 | note | ○ Longitudinal joints offset from one layer to next by not less than 150mm Longitudinal joints to be located within 300mm from planned traffic lane lines or within 300 mm of the centre of a traffic lane.
9f5dd517-d7fa-5edd-870b-2979712aa919 | note | REFERENCE DOCUMENTS: Cl.304.07 (a), Cl.304.08 (d), Cl.304.08 (e)
fc58643a-233c-518d-ab7c-6d9ccf87a910 | note | INSPECTION/TEST METHOD: Visual Inspection
214ca9d5-bbfa-5d08-a05b-fceacb606f35 | note | RECORD OF CONFORMITY: This ITP signed off
cdebf260-659c-5c1c-89a0-62822b3970b9 | note | IP
3bc02613-1c41-57c5-a407-2762e5e5cdad | note | RESPONSIBILITY: Site Engineer / Site Foreman
fb4e89fc-1f6e-5bf7-a646-8623cd02fe41 | date | Date Completed:
| checkpoint | 2.3 - Lot Size
d02e5289-fd02-50a6-9f18-157afd7a8447 | note | FREQUENCY: Check prior to placing material
d453060e-8eaa-59ff-8794-7db25a33d95d | note | ACCEPTANCE CRITERIA: A single lot shall be considered a single layer of 4000m2 or one days production in a single layer, whichever is lesser.
345cbfd3-df00-5345-9ffe-94c3f94d4898 | note | REFERENCE DOCUMENTS: . Cl.304.09 (b)(ii), Table 304.121
76a5e8eb-6daa-5e0f-a524-06fb77699600 | note | INSPECTION/TEST METHOD: Site Inspection
05c843a3-ec41-5b41-b6ed-88c21552f79b | note | RECORD OF CONFORMITY: Signed ITP
fc9e4162-757f-57ad-be1a-24a5f399ed3c | note | IP
1d1bcff1-1100-5a89-a982-4ed0b7946d81 | note | RESPONSIBILITY: Site Engineer / Site Foreman
83764fdc-aba8-57ac-a427-6802ed8264e8 | date | Date Completed:
| checkpoint | 2.4 - Layer Thickness
6fab9c8e-a32c-5329-b40e-43f04874624f | note | FREQUENCY: Each Lot
8829c705-447e-5984-9c63-a8b3485ce397 | note | ACCEPTANCE CRITERIA: Sub-base shall be constructed to a maximum compacted thickness of 200mm and minimum thickness of 4 times the nominal size of the material.
2380317b-2f87-54f6-981d-34fe8dfe1d65 | note | REFERENCE DOCUMENTS: Cl 304.07b
4700c21d-c673-5f79-96e8-25eea2f1bf0a | note | INSPECTION/TEST METHOD: Site Inspection
d531652a-8fe8-5a5d-b274-6206858441e5 | note | RECORD OF CONFORMITY: Signed ITP
903be644-6c87-5809-88c7-c79ce0b9db30 | note | IP
63c90c34-0d2c-5335-a82e-74a15374ad46 | note | RESPONSIBILITY: Site Engineer
dbc7e2a0-cfef-5f3b-8892-dce1af17108e | date | Date Completed:
| checkpoint | 2.5 - Proof Rolling
16b041ab-7247-520a-bf39-a386d23a1fec | note | FREQUENCY: Proof Roll each layer
e6faba14-77df-5e7e-810c-246d0e156798 | note | ACCEPTANCE CRITERIA: No visible deformation or springing in presence of Superintendent's Rep.( Cl 173) Plant to comply with requirements of Cl 173.03.
20a82b0e-8bbc-5c82-96ae-a24bac4a2e26 | note | ○ Static > 12T
e03063e8-cac0-5a8f-ad93-1d4936d18d07 | note | ○ Pneumatic > 20T
327d8731-8ccb-59d0-ab70-b01aff2a576b | note | REFERENCE DOCUMENTS: 173.03
96626681-2028-516a-8506-7ce7f723fa7e | note | INSPECTION/TEST METHOD: Visual inspection
3fbb04c8-f816-56b8-b52f-83d201f72411 | note | RECORD OF CONFORMITY: This ITP signed off
2c979599-eec9-52a4-a8b6-1cdcc7ab01ee | note | HP/ WP
037c127d-c108-5947-acab-7aa9b8d1b97d | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
246d4297-62c0-5309-92e3-fda19365e2f5 | date | Date Completed:
| signoff | Signature Required
| section | 3 - Testing Requirements
| checkpoint | 3.1 - Determine Testing Scale & Initial testing frequency
2e0051d5-721c-518f-b60e-1afc9978f575 | note | FREQUENCY: Prior to Testing
219ad372-a9e3-5e30-a2a7-8f1827900bd8 | note | ACCEPTANCE CRITERIA: Initially test every lot until 3 consecutive lots of like material and/or work have achieved the standards specified in Clauses 304.09. and 304.12. If no failures, Reduced Frequency applies as specified in Table 304.121.
e0bb0de6-c822-5a21-ae11-a40a6c0ec291 | note | REFERENCE DOCUMENTS: Cl.304.09, Cl.304.12, Table 304.121
a135334b-871f-54be-b3ad-2eeb792ae4b0 | note | INSPECTION/TEST METHOD: Document Review/ Site Inspection
4a2c28ec-4252-50da-9892-b621e968034b | note | RECORD OF CONFORMITY: Signed ITP
8382cbb6-8c32-5580-814e-e47a0156e921 | note | AP
f5e2beb2-be1c-5e22-a034-97f47c9f2054 | note | RESPONSIBILITY: Project Engineer
06a59d58-0dc3-50c9-b8df-f03850b01344 | date | Date Completed:
| signoff | Signature Required
| checkpoint | 3.2 - Compaction Testing
f0bf42c4-f2c4-5196-b821-c93ea289a0f1 | note | FREQUENCY: Every Lot, Every second lot (reduced frequency)
18d84a08-981b-5826-8c9f-397743f672bb | note | ACCEPTANCE CRITERIA: Modified Maximum Density Ratio of not less than 97% & 98% for Class 3 FCR & Class 1 FCR respectively for road pavement as per Contract Drawings 2021-01 sheet 1
91de0818-74ff-5733-9dfa-850bacb84080 | note | REFERENCE DOCUMENTS: Contract Drawings (2021-01)
68315586-bcfa-575d-aed4-c58fe3ccaa84 | note | INSPECTION/TEST METHOD: Test point
98a711a6-ac7b-5f00-ae00-050ffa280094 | note | RECORD OF CONFORMITY: This ITP signed off; Test reports
44d790c5-fe23-57a0-a828-730c3cb80c75 | note | TP
aa118ca4-1b57-5986-a807-80ad944dcfcb | note | RESPONSIBILITY: Site Engineer
6c927dc8-6b59-52c4-a6b9-e9709a28624d | date | Date Completed:
| signoff | Signature Required
| checkpoint | Final Inspection
6d06fff7-2a6c-5640-8c48-9770d0b1d3ad | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
66ccda7f-3014-537f-9af1-dd291dc03025 | textbox | Print Name:
e169baf7-8f8a-5ee6-98a5-384d66688076 | textbox | Position:
15a66c70-703a-5fc8-add0-2d8bf7c0bd4a | date | Date:
| checklist | ITP-004 - Kerb and Channel | itp | ITP-004 - Kerb and Channel |  | b9072193-612f-4099-a382-1aa1c67b49e3
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
ae6de9f8-117a-5bf7-aec4-5c4dbd295378 | note | FREQUENCY: Prior to commencing any activity
3179c630-04a3-5740-a5eb-9fceaaea17f2 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
00d1f9ce-1375-5e8c-af7a-b23e6ce00b13 | note | – using the correct and complete set of drawings
25dea204-5e20-5ca6-b6e0-680887cb3808 | note | – all drawings are the latest revision
47b43ef7-8288-5b61-b48e-330d42592102 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
db9f3c1f-43d8-5dc0-a50d-f620ef6ccbe7 | note | INSPECTION/TEST METHOD: Visual inspection
9757cf13-f1e2-5c9b-af0b-27e7003a770e | note | RECORD OF CONFORMITY: ITP Signed
88ade27c-bb52-589e-89a3-1c558db3a1e2 | note | HP*
312f2a1e-0614-505d-92da-23329a6c2389 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
3d202252-413d-57e7-b85b-f2272a89828b | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
0ae0b1d4-89c2-577c-8f3a-f8a6f27fb2d2 | note | FREQUENCY: Prior to commencing any activity
d577d943-2f4e-5c30-a60c-4982f90a65e8 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
e9a172bd-a996-519f-8fd8-a4ced7a32c0a | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
65808d10-fdc0-558c-8003-7b6f63349fcb | note | INSPECTION/TEST METHOD: Visual inspection
f0062385-099e-51ba-90ee-de6554b1f4d4 | note | RECORD OF CONFORMITY: ITP Signed
f52cad99-f697-51ef-9458-4d45a4ef1ff2 | note | IP
533901f5-dfc1-5dde-a388-080011285c3f | note | RESPONSIBILITY: Site Engineer/ Site Foreman
094dceab-9cc5-51a4-a2f3-99da2a1c23a8 | date | Date Completed:
| checkpoint | 1.3 - Mix Design
aa40b2b8-06ce-53e8-94ac-e0f5ba662184 | note | FREQUENCY: Prior to commencing any activity
68493c40-071f-58a5-a062-433e5f01c236 | note | ACCEPTANCE CRITERIA: Approved VR mix design to be used. Details to be sent to the superintendent for approval prior to commencing works.
d964790a-fa12-5f5c-af6f-ef6668e232f3 | note | REFERENCE DOCUMENTS: AS 1379, Cl 703.07, 703.05, 703.23
2217d15d-9223-5694-8028-11c424aac0a4 | note | INSPECTION/TEST METHOD: Verify
9829ff77-d0d2-527f-8b92-618c1fa0da25 | note | RECORD OF CONFORMITY: ITP Signed, Mix design approval
932f29c0-8b87-59e1-86f1-cafb539c3151 | note | HP*/ WP
bdb5dc79-50de-53d6-afd0-d43a7fc053ec | note | RESPONSIBILITY: Site Engineer/ Superintendent
b4cb76ba-fc99-5548-8d3f-fdbf4fa83d89 | date | Date Completed:
| signoff | Request Signature
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
683cc676-d318-5a04-a911-c6afddd084fc | note | FREQUENCY: Prior to start
83f1fdb8-36c5-5477-99df-bf05cd520ce2 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
f352c2f5-3d20-5cc8-b33d-ffb915116659 | note | REFERENCE DOCUMENTS: Cl 703.17
faed1bb9-4735-5070-95d8-505219bd86bc | note | INSPECTION/TEST METHOD: Verify
a59cba6b-cb61-5a7d-8b71-1ffb95b384e5 | note | RECORD OF CONFORMITY: ITP Signed
69daa05e-2806-5872-8de2-8e1546114cfe | note | HP
1e826bf8-54a9-5410-9c79-9840a3911b85 | note | RESPONSIBILITY: Site Engineer/ Superintendent
56fb3841-b309-5a64-891d-7f60b458b94c | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Temporary Drainage Provisions
eed15d9a-18e4-5b9a-9e91-1f10699dc2ea | note | FREQUENCY: If Required
eff504b1-6ead-527d-a7ce-8717973e34d7 | note | ACCEPTANCE CRITERIA: If obstructing waterways, culverts or channels, temporary diversion of discharge of drainage and stormwater to be in place.
6bd3574b-59c1-592e-8640-1c8576ad1c86 | note | REFERENCE DOCUMENTS: Cl 703.18
de54ede5-517d-5d0d-bd91-df024b858ce2 | note | INSPECTION/TEST METHOD: Visual inspection
cf5a9c9b-cf12-5a04-9584-1b465044f13f | note | RECORD OF CONFORMITY: ITP Signed
6643c751-e5aa-5520-9104-3acb8cc9be49 | note | WP
f5821247-abb2-55a1-acd3-666e880cb61d | note | RESPONSIBILITY: Site Engineer/ Site Foreman
2eec9edd-25ba-5919-8b5f-1d2de97e26de | date | Date Completed:
| checkpoint | 2.3 - Bedding
ea0d8593-15a0-5346-80a7-956308e12490 | note | FREQUENCY: Each lot
844cce79-1d78-50c2-83bf-18681c3ea4e8 | note | ACCEPTANCE CRITERIA: All bedding material shall conform with the requirements of sections 812 or 820 for crushed rock and crushed concrete respectively.
9efae9da-e2c3-5d25-9c11-20f44bd9885c | note | ○ 20mm Class 3 shall be used and compacted to a thickness of not less than 100mm.
d5b2a94b-aea1-5216-8810-32ec438a3a4f | note | ○ Bedding shall be trimmed to appropriate levels, moistened as necessary, and be firmly compacted.
976b8a5c-acc0-504c-a163-5ab58ce29a65 | note | REFERENCE DOCUMENTS: Cl 703.21, IFC Drawing SD-K1 Sheet 06
6cb57ed0-1383-5417-9e83-184e1601bff2 | note | INSPECTION/TEST METHOD: Visual inspection
bc198ece-7c39-5ddf-b006-9213cf8ff6c3 | note | RECORD OF CONFORMITY: ITP Signed
75a4fe24-0406-5011-8fbc-4c98c8d674b7 | note | WP
ea721725-4afd-5da1-8e26-ccfc11a3501a | note | RESPONSIBILITY: Site Engineer/ Superintendent
fadb9aea-19a0-5785-821d-65658cc16fdb | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Pre-concrete check
c02395f2-8176-5d12-b3e2-dcb629434d6c | note | FREQUENCY: Each lot
73fc0766-23a1-5c37-a572-195cb3310c2c | note | ACCEPTANCE CRITERIA: Bedding shall be moist but shall have no free water on the surface.
04d24d54-94f8-5818-b63c-141c9759498c | note | ○ Concrete shall not be placed when the air temperature measured at the point of placement is >35°C or <5°C.
b8eddd65-e320-5fd0-9755-4a1f00cd6186 | note | ○ Temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
8e0ae3b9-959c-5fc1-9d81-6425b0b4e826 | note | ○ Formwork - Prior to placing concrete in an earth excavation, formwork shall be erected so that fresh concrete is not placed directly against the sides of the excavation.
dddac9bd-265c-54a5-ae1c-8939d8237eda | note | ○ Concrete extrusion machines have minimum cement content of 320kg/m3.
13d282af-c9e4-515e-bfdf-5d9198180fd5 | note | REFERENCE DOCUMENTS: Cl 703.08, 610.17(a)(b)(c), 703.12
be648c36-7778-55fa-bd08-7d2c25e14376 | note | INSPECTION/TEST METHOD: Verify
1940255a-1436-5299-bcdc-4caf963c8995 | note | RECORD OF CONFORMITY: ITP Signed
39667c00-03df-5cf2-9609-a25c01f1684d | textbox | Ambient Temperature |  |  | °C
cb5c1fea-045f-5507-9882-7d868d559d99 | textbox | Concrete Temperature |  |  | °C
9cc5d67a-5699-5728-a49e-1af4f2eb13bf | note | HP*/ WP
c2524293-3182-5507-9df7-82a7ec28b7db | note | RESPONSIBILITY: Site Engineer/ Superintendent
8d80fd8a-25ca-5cf3-a164-e028ad7db1a9 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.5 - Kerb Concrete Mixture/Strength
bcb2e3bb-8371-518a-8fb2-72a8261c7ba6 | note | FREQUENCY: Each Lot
f2546f1f-cc48-50b3-9717-34d571e99073 | note | ACCEPTANCE CRITERIA: Traffic Routes – a minimum of, or equivalent to, 320 kg of cementitious material or geopolymer binder per cubic metre of concrete
11a1c42f-c5c5-5200-be56-f18638ed71bb | note | ○ Local Streets – a minimum of, or equivalent to, 280 kg of cementitious material or geopolymer binder per cubic metre of concrete
91b4383c-1370-5249-b74c-d0481e15903c | note | REFERENCE DOCUMENTS: Cl 703.05(b)
29ca89be-8128-52d3-a463-c1c05c224add | note | INSPECTION/TEST METHOD: Verify
71d4c940-36f9-56fc-803a-cc92c7c15d81 | note | RECORD OF CONFORMITY: Test Record
1721d615-fb4e-5211-bedc-2c0f388b6ba9 | date | Date Completed:
| checkpoint | 2.5 - Concrete Placement
0a9a6f8e-1230-58d2-b1ff-97abbb1b2365 | note | FREQUENCY: Each lot
271e552d-38fc-5f35-bed7-4ab2d74bf859 | note | ACCEPTANCE CRITERIA: Concrete is to be fed to extrusion machine at a uniform rate. Concrete is to be satisfactorily compacted so that finished surfaces are free from surface pitting larger than 5mm diameter, honey combing or faulty patches
5e4c74ba-462c-5b0f-b297-fce9b5b8870c | note | REFERENCE DOCUMENTS: Cl 703.23
284f6511-184c-53cf-be3c-384c353648d2 | note | INSPECTION/TEST METHOD: Site Inspection
2bd769fe-bc4f-5eeb-b252-d30c0dfe2884 | note | RECORD OF CONFORMITY: ITP Signed
b4cf1b3f-8914-53db-a190-5ec1aaf6d9a1 | note | IP
74648b53-5cb2-5b33-9b20-fec3171fe84a | note | RESPONSIBILITY: Site Engineer
b3f80818-4c5e-5963-aa54-f3d976afd8f9 | date | Date Completed:
| checkpoint | 2.6 - Finish Surfaces
1ae32dc9-83e9-5a8d-97bc-d6223e218d62 | note | FREQUENCY: Each Lot
0fd55525-141f-5424-b59d-03511cba6ab3 | note | ACCEPTANCE CRITERIA: Edgings: rendered to a thickness not exceeding 3mm and trowel finished.
7e982836-97ec-508d-9763-0cc433d0fddb | note | ○ Concrete to have a neat appearance and uniform colour.
172c6cdc-c8e8-5847-91db-021888380cda | note | REFERENCE DOCUMENTS: Cl 703.25
af3d8d61-a043-541c-b769-5799c44d5635 | note | INSPECTION/TEST METHOD: Visual inspection
ce49acff-8bda-5014-a3b4-f3452f942969 | note | RECORD OF CONFORMITY: ITP Signed
9c0ca29e-4b1e-598e-a70b-efc00274d0eb | note | IP
4aeb4b38-74d0-58df-9cc1-7742dcca0145 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
b7a56d2c-49e7-58df-b18e-8b7b47dd92ac | date | Date Completed:
| checkpoint | 2.7 - Tolerances
c1864f54-eb8e-5c1b-ba25-627ad5c9e7f6 | note | FREQUENCY: Each Lot
9151e51d-33c6-5ce0-aa6a-b9b9ce24fcc6 | note | ACCEPTANCE CRITERIA: Match existing surfaces to within 5mm from dimensions shown on drawings. Section dimensions to be within 5mm and 15mm for width, for dimensions less than 25mm tolerance to be ± 3.
7bbfeae7-7fbc-51d8-9980-de2d5264a78a | note | ○ Kerb and channel shall be constructed to the level of the adjoining pavement with a tolerance of 0 to +10 mm. Except on curves or shaped areas, the deviation of the finished work from a 3 m straightedge shall not exceed 5 mm at any point.
ce0fe672-c4fe-57df-8135-78cbec656a8f | note | REFERENCE DOCUMENTS: Cl 703.15
912c6b70-96a3-5ca1-a03d-579a58a07209 | note | INSPECTION/TEST METHOD: Verify
15e17e0f-446c-5876-8bee-c7b622de210d | note | RECORD OF CONFORMITY: ITP Signed
9f223db0-1047-5592-acfd-7ef6bb75de61 | note | SCP
eafff1e5-e46b-506e-8c18-c552460ce779 | note | RESPONSIBILITY: Site Engineer/ Surveyor
499d2337-2410-53b0-ad9d-b07cf2db1112 | date | Date Completed:
| checkpoint | 2.8 - Joints
36103a43-4cfe-59b5-a984-af502019fac5 | note | FREQUENCY: Each joint
c484d253-8707-5428-a07b-2cc1e11fdabe | note | ACCEPTANCE CRITERIA: Transverse joints constructed at intervals not exceeding 2.5m.
50aa8b2b-b0c8-5ec6-827c-b7e91192ddbd | note | ○ Groove cut 20mm deep and > 5mm wide on exposed surfaces, with vertical cut made through the base of the groove (depth >50mm from surface of section).
b4b79a38-f5a8-569e-bff3-44d44d816df4 | note | ○ Prevent bonding between surfacing and edging either paint with bitumen or use a strip of bitumen
1fca0f52-0a9f-54ba-bd38-536b072d7892 | note | REFERENCE DOCUMENTS: Cl 703.26
d3bfcc80-d420-5309-af13-b754ceda0f13 | note | INSPECTION/TEST METHOD: Verify
748e9e2c-7c3c-59e1-aec9-19667a2b4a99 | note | RECORD OF CONFORMITY: ITP Signed
54112a18-21f3-5976-b067-59ec534a964f | note | IP
2efff1b3-e6ec-572f-a7fd-2c83e55c3f0b | note | RESPONSIBILITY: Site Engineer/ Site Foreman
83182e93-7432-539d-87fe-2ec4e9d4f09b | date | Date Completed:
| checkpoint | 2.9 - Curing
3c79497f-fd4d-5264-a278-3af13347e945 | note | FREQUENCY: Each Lot
776a1c11-b031-5b21-98df-3918916fef85 | note | ACCEPTANCE CRITERIA: The curing of exposed concrete surfaces shall commence immediately after finishing operations are progressively completed and shall continue uninterrupted for a period of not less than 7 days after placing the concrete, with the exception of concrete edgings which shall be cured for a period of not less than three days after placing the concrete.
9591a7ee-778b-5154-b32f-3c9c8c837fbd | note | ○ Concrete will be cured by method of wet hessian.
6af4f6a0-97f1-5177-8cd9-9aa7363c06ee | note | REFERENCE DOCUMENTS: Cl 703.1
2860fb3d-11d0-58de-b82c-1c491df1324d | note | INSPECTION/TEST METHOD: Verify
c49aa23b-3b38-5104-93d8-32387e76014e | note | RECORD OF CONFORMITY: ITP Signed
84e4e79f-bf8c-57ce-8367-62cede8e2ebe | note | IP
6a5235f4-8aa9-5081-aa92-154479ff6310 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
b09e8298-2b3d-5ca5-a54a-8eae035aa18c | date | Date Completed:
| checkpoint | 2.10 - Backfilling
d467ac58-ee32-510a-abff-4f3d49f0e5bb | note | FREQUENCY: Each Lot
94f470ea-243c-5cef-9187-218a8d1aa1dc | note | ACCEPTANCE CRITERIA: Not earlier than 3 days after casting.
1548aeb7-5074-538c-b520-2760ff1721ad | note | ○ Topsoil material free from perishable matter, lumps or balls of clay. Topsoil compacted behind the edging to a level of the top of the edging and to a width not less than 300mm unless otherwise specified.
6ea5c17f-791f-58ea-8b3c-c250a1abc5f6 | note | ○ Layers shall not exceed 150mm compacted depth.
41a0b120-f0dc-5145-acd2-c08373a20e7d | note | REFERENCE DOCUMENTS: Cl 703.29
bf8d726a-9d50-5203-8caa-819a7374a8e6 | note | INSPECTION/TEST METHOD: Verify
53926e90-eaee-533c-b506-cb9580fe79ab | note | RECORD OF CONFORMITY: ITP Signed
a2e966d3-226f-5f24-99b4-45256f16f533 | note | IP
41f010be-d6a3-58d2-8c10-c0b4cc3ab305 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
99fda7ee-bc6d-5d28-bfa3-0c989091ee20 | date | Date Completed:
| checkpoint | 2.11 - Cracking of Concrete
3f90c29c-3986-523f-a672-9c514da2048a | note | FREQUENCY: Following Completion
ac905170-7710-5f7c-b29f-0ab7f042568e | note | ACCEPTANCE CRITERIA: The concrete shall have no surface cracks at any stage after construction of width greater than 0.2 mm. Where such cracks exist, they shall be identified as a non-conformance.
039cea01-9e8c-51fd-8bb8-39c2061a81d1 | note | ○ Cracked sections of concrete shall be either removed and replaced, or repaired in accordance with Section 687 – Repair of Concrete Cracks, as directed by the Superintendent.
c02b59e7-3946-5b05-a839-eaad85f26195 | note | For damaged kerb and channel and edgings, a length of at least 1 m shall be removed and the replacement section shall be:
58ee430a-4ffa-5eb8-8afc-f969a008d904 | note | (a) constructed on compacted bedding;
c1f7e549-e7b8-530f-8707-5039bc9d3b6a | note | (b) dowelled into the adjoining sections with 12 mm diameter hot dip galvanised dowels embedded at least 100 mm each side of the joint; and
8f4c594c-07c9-5254-be39-107143d15b3e | note | (c) shaped and finished with curved trowels to match the profile and surface finish of adjoining sections.
b158e45b-20e7-56b6-b2af-68a1e6225cbf | note | REFERENCE DOCUMENTS: Cl 703.30, Section 687
8f2e9ab5-4897-5a8a-bd0c-e891f630cff9 | note | INSPECTION/TEST METHOD: Verify
75ec2c29-9d0f-59b2-bc4c-7b9f96b49dd0 | note | RECORD OF CONFORMITY: ITP Signed
74be7699-9535-5996-8dc0-a3992f54e12b | note | IP
b37b8c25-a5d9-503e-970a-7872f0345c77 | note | RESPONSIBILITY: Site Engineer
9eb63b10-3175-5d9c-abfc-8abdbe1abffa | date | Date Completed:
| section | 3 - Completion
| checkpoint | 3.1 - Survey data captured for as-built purposes
54915da1-d0db-50bd-9117-0bf60f8c60a8 | note | FREQUENCY: Completion of each lot
a61f8e93-3403-5a06-8308-7080a69c0940 | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
34dfc20e-e948-5297-b53e-6b49040dbc0f | note | REFERENCE DOCUMENTS: IFC Drawings / survey records
4f6d1b52-73cb-5a73-8561-90ec4554a6f2 | note | INSPECTION/TEST METHOD: Document review
a37dd267-8ca5-5026-a459-fcaa3f7db018 | note | RECORD OF CONFORMITY: As-built survey records
3db26df6-98c6-5e86-a8e9-b3b62eb9e7de | note | SCP
ab3d2252-9ad9-5870-a5d6-fc5f50ca05dd | note | RESPONSIBILITY: Project Engineer/ Surveyor
25992847-9029-5f36-81de-0c3869a2eb9a | date | Date Completed:
| checkpoint | Final Inspection
a4d81d44-ad70-51d8-8c58-40e3c72b7586 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
cd582911-0fe7-5581-9f69-adab9b938bf0 | textbox | Print Name:
c6b11dd5-4ec1-5e9c-9837-3dfbbb404d8d | textbox | Position:
5df35a0d-297d-5e3d-a711-c81c78dba241 | date | Date:
| checklist | ITP-005 - General Concrete Paving | itp | ITP-005 - General Concrete Paving |  | f2b8a46e-9472-408d-b8ac-99db5f4541ac
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Check for correct documentation
f2fbfa7e-79a5-572a-8aaf-99b35371b2b1 | note | FREQUENCY: Prior to commencing any activity
e28d9d84-adc9-5ba2-afd9-1c719f0bd99e | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
67276cc0-f7db-5744-9c41-1167118481ab | note | – using the correct and complete set of drawings
7d2bdb4a-1cc6-56d9-8975-b5a47552d406 | note | – all drawings are the latest revision
a47814f1-1d1a-505e-a360-1c88ff9a3bdf | note | REFERENCE DOCUMENTS: Drawings and drawing registers
68f070de-6a71-58f6-a7a0-53a68bca50eb | note | INSPECTION/TEST METHOD: Visual inspection
b816b580-3869-53d7-a175-64c14c374c77 | note | RECORD OF CONFORMITY: ITP Signed
856780fe-3c26-5dd3-9ac5-eee7b1f7caff | note | HP*
5bb659c8-b4f9-50ae-b643-f5fede671238 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
3a5378ba-592c-5a94-aa44-2466de3f2adc | date | Date Completed:
| checkpoint | 1.2 - Implementation of all measures and controls
a07435f2-adf6-5809-8a53-07f8ececbdcd | note | FREQUENCY: Prior to commencing any activity
d0d94383-a8b9-5e58-8375-dcddd0059ff5 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
b734aadc-cefd-562a-90c7-0037d4d8699f | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
4c82b5da-bd5d-5381-9183-d83d2fefcc8a | note | INSPECTION/TEST METHOD: Visual inspection
f17e31fc-fcaf-56f9-9356-d052d5c8ca79 | note | RECORD OF CONFORMITY: ITP Signed
ee2867cd-06b4-52c5-bb19-ea10a47e0a2c | note | IP
fe7b8141-af1e-50bf-b529-31388eef4e2a | note | RESPONSIBILITY: Site Engineer/ Site Foreman
6850e6a0-28b5-5dc4-b118-9f9f3d512780 | date | Date Completed:
| checkpoint | 1.3 - Survey and Set Out
3c9e0c25-b0d0-54ed-a25e-f2767d83fd33 | note | FREQUENCY: Prior to commencing any activity
54426e4e-0442-588a-9921-60019bea2f15 | note | ACCEPTANCE CRITERIA: Current design model available for machine control.
c4c9d727-706c-5655-bbf2-17ca4794c3ff | note | ○ Clearly mark limit of works, chainage, offsets, cut/fill level etc. (if required)
289c6857-1888-550c-b975-70a4f6849276 | note | ○ Design drawings must be IFC status
c6532ccb-d240-52e1-971f-5c0ec7645a90 | note | REFERENCE DOCUMENTS: IFC Drawings
e3d4bc40-26b7-532a-b77b-c2c692ce3c17 | note | INSPECTION/TEST METHOD: Verify
4ff9dfd0-822a-5efc-9391-4fc3ec0b64df | note | RECORD OF CONFORMITY: Site Inspection
3d63da21-e662-5eae-86df-4106ed4e5534 | note | HP*/ WP
5485812e-147c-5eb9-9014-08120763ec06 | note | RESPONSIBILITY: Site Engineer/ Superintendent
ec028712-1960-5f79-b398-3b45f62a8730 | date | Date Completed:
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
3d86dda1-3959-5fdd-abf6-d491628d52ed | note | FREQUENCY: Prior to start
17eac58e-0418-580f-be77-1d12d558f8d2 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
7af365d5-1e1d-5cf5-bde2-34f1b2d1f615 | note | REFERENCE DOCUMENTS: Cl 703.17
469fe868-3d49-5b5c-80ae-e1aa03932b1b | note | INSPECTION/TEST METHOD: Verify
beab295b-d069-585c-a5d5-b23fe412dfd1 | note | RECORD OF CONFORMITY: ITP Signed
d7e151da-18d4-527c-b9a6-69d268d966d4 | note | HP
da4a4728-d87a-5d39-89ba-2478ac1805ae | note | RESPONSIBILITY: Site Engineer/ Superintendent
4f6b94f8-b74c-57a1-807b-23302d8bda89 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Excavation and foundation
8ed2addd-4081-50e3-b838-724d0d96d565 | note | FREQUENCY: Each lot as required
ea2aca2c-68c9-57a1-ad5a-2d44bf5ad250 | note | ACCEPTANCE CRITERIA: Box out to a sufficient depth to allow for the required compacted thickness of bedding material under the full width of concrete paving. Where it is necessary to excavate existing pavement, the excavation shall not extend more than 150 mm from the edge of the adjacent face.
d16c4670-3bb8-5379-a5e2-fdfd21d38f2d | note | ○ Foundation true to grade and cross section as shown on the drawings by filling and excavating as necessary.
da28cf09-cd26-5932-9111-bad37fe384bf | note | REFERENCE DOCUMENTS: Cl 703.20, Cl703.21
08ff759e-8921-56c7-8338-8c149b3a1c88 | note | INSPECTION/TEST METHOD: Visual inspection
deb0f2f0-fbd8-5676-ab3a-d32cc60c3c91 | note | RECORD OF CONFORMITY: ITP Signed
e89d3935-126f-59cc-af15-9201022ed241 | note | WP
20ec99a8-b43b-5531-a10f-fdef1334baa2 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
e175d92b-d3ea-5886-a939-feedfa638fc4 | date | Date Completed:
| checkpoint | 2.3 - Bedding materials and compaction
2028dd64-5bb8-523b-9ba4-c1508a759385 | note | FREQUENCY: Each lot, Prior to concrete placement
1724ea96-5617-5888-9454-584cefcdc73d | note | ACCEPTANCE CRITERIA: Bedding material shall be compacted size 20mm Class 3 Crushed Rock or Class 3 crushed concrete.
33b9e6bf-a5d8-5c29-8131-7f2333ea718f | note | ○ Immediately before concrete is placed, bedding shall be moist but with no free water on the surface. Comply to Table 820.041, Table 820.071.
03ca625c-892e-5da3-af4f-7a7931bbe604 | note | REFERENCE DOCUMENTS: Cl 703.21, Table 820.041, Table 820.071, IFC Drawings - SD-K3-1
d5f674f0-9e39-5d93-bb34-dd6a7c9f9044 | note | INSPECTION/TEST METHOD: Visual inspection
7d596c29-0591-54cb-9a84-b15693b0c304 | note | RECORD OF CONFORMITY: ITP Signed
c80137e9-036a-5f4b-b1d6-dfb9975a49d0 | note | WP
be0ecb29-5926-58b4-8cf6-12529e5e2326 | note | RESPONSIBILITY: Site Engineer/ Superintendent
9347f3e4-19b8-5c2f-a85c-e752346a8783 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Bedding depths (compacted)
34603a32-484d-5aab-b225-10cdc7a86ac8 | note | FREQUENCY: Each lot
c91d5e2d-6f46-5edf-a2ab-471b62d635ac | note | ACCEPTANCE CRITERIA: 1. Edgings:
35e7ff91-eeed-587e-9fa4-4c1cc0ae67c0 | note | ○ When constructed over pavement layers, bedding shall be provided between the pavement layer and the underside of the edging, or the edging thickened to match the pavement layer.
7a33acd1-fb6d-54f7-aaea-625d4125157e | note | ○ When not constructed over pavement layers, bedding ≥ 100 mm compacted thickness.
412d3119-67c7-586d-842f-997008423040 | note | 2. Shared use paths:
18f76708-5e44-5b4f-89a7-ba39ba0bbf81 | note | ○ bedding ≥ 150 mm compacted thickness.
b8735900-ed2a-5ed8-8af8-4114bea1f540 | note | 3. Footpaths & Driveways:
d1be2306-ed62-5f62-b15c-b04ba49cec27 | note | ○ bedding ≥ 100 mm compacted thickness
e57feb96-3978-5377-afd5-d278de56839f | note | REFERENCE DOCUMENTS: Cl 703.21 (a), Cl703.21(b), Cl703.21(c),IFC drawings
81b8a517-f9cb-56e5-be7e-9ade6b00cf72 | note | INSPECTION/TEST METHOD: Visual inspection
b3518a2a-9572-5d3a-8d12-f69a41b7477b | note | RECORD OF CONFORMITY: ITP Signed
cb75f926-9a16-539c-bd0a-87be9f386b38 | note | HP*/ WP
65f670be-5214-58fd-a3cd-14569b7a1e45 | note | RESPONSIBILITY: Site Engineer/ Superintendent
19bb75cb-a4f6-517b-b325-9126d8d60591 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.5 - Ambient weather for concreting
5929b473-5eca-5179-86ce-805e2041a90a | note | FREQUENCY: Each Lot
da1344e7-62f6-5bb4-a6e8-8c1f2d95ced7 | note | ACCEPTANCE CRITERIA: Concreting operations shall comply with the requirements of Clauses 610.17(a), 610.17(b), 610.17(c) and 610.17(d) for Restrictions and treatments to be applied for concreting in hot, cold and wet weather.
7b7b7f8d-2e5a-5ce8-b6f4-22670938a328 | note | ○ The temperature of concrete, measured immediately prior to placing, shall not be less than 10°C or greater than 32°C.
d5751003-5e36-57a1-b12c-956c5a57bbc8 | note | ○ Ambient temperature not to be less than 5°C and no more than 35°C.
8e08bf70-6132-5d72-8d20-d4070de6c865 | note | REFERENCE DOCUMENTS: Cl 703.013, AS/NZS 4671, AS/NZS 4680
51b1525f-9a30-56c1-9699-49fdff12f255 | note | INSPECTION/TEST METHOD: All measures in accordance with relevant documentation
3194913e-369b-5f2c-b6e8-52228d9531f5 | note | RECORD OF CONFORMITY: Verify
28c1c313-3b16-50de-8150-fde046bcf01a | note | WP
80a55391-b6a6-5b4d-9ce7-d238a2b52551 | note | RESPONSIBILITY: Site Engineer
6924ced7-43a1-5302-87ef-ed07f391b9b7 | date | Date Completed:
| checkpoint | 2.5 - Steel reinforcing grade and placement
ba084f5b-e39a-51c7-86a8-ec5b59c23385 | note | FREQUENCY: Each lot
bdf58d84-88f9-5b72-b141-3f2417e8d0ec | note | ACCEPTANCE CRITERIA: 1. Steel reinforcement shall comply with the relevant requirements of AS/NZS 4671
29e0bb01-a058-5c71-b16c-5e6c225596c4 | note | 2. Concrete is to be reinforced by F72 mesh and with a cover of 40 mm as per the drawings SD-K3-1.
73a8287c-dbb2-5d23-9a62-83d873ab2d4d | note | 3. Support reinforcing using either concrete or plastic chairs.
5b1f87a3-f123-5efd-a8fc-bf6335e7c42e | note | 4. Wire chairs with or without plastic tips, bricks or pieces of timber or coarse aggregate shall not be used as support.
5bf3f83c-991f-5429-bb7b-09dee3fac473 | note | 5. Galvanising where specified shall be in accordance with the requirements of AS/NZS 4680.
4e8bac05-de20-573c-bc32-d3598dd1c812 | note | REFERENCE DOCUMENTS: Cl 703.013, AS/NZS 4671, AS/NZS 4680, IFC Drawing
93f957fb-ce1e-51f8-a178-1173f10a5499 | note | INSPECTION/TEST METHOD: Site Inspection
13d29e6d-478a-5bce-9dc3-b6b12e469e8e | note | RECORD OF CONFORMITY: ITP Signed
f6f84c89-ce46-5283-9a6f-3e1592620286 | note | WP
4e00a830-c120-51c2-988e-6c926134fa53 | note | RESPONSIBILITY: Site Engineer
9f413daa-9931-5012-b592-f61f6de9d6df | date | Date Completed:
| checkpoint | 2.6 - Formwork
441f2373-c3c1-5ef7-aedd-b5c2ebf52d5e | note | FREQUENCY: Each Lot
aa6f4904-36b0-5479-a7ca-30b87b7691c8 | note | ACCEPTANCE CRITERIA: Materials, design, construction and stripping of formwork shall comply with the relevant requirements of AS 3610. Joints in formwork shall be constructed such that loss of mortar is prevented.
f76ef33b-ccd5-5e66-a20d-08c3c3afff2f | note | Formwork shall not be stripped until the minimum times specified in AS 3610 Table 5.4.1 have elapsed from the time of completion of the placing of concrete. The minimum time shall also not be less than:
75bff631-ebc9-575b-ba69-15343e5361c5 | note | (a) 2 days for vertical formwork on external surfaces; and
da0e81db-1b02-5ea5-9246-e9023a15c0e6 | note | (b) 1 day for vertical forms on permanently hidden surfaces.
e790cbc6-ef3b-5588-9c9c-28b8e0e14ab8 | note | REFERENCE DOCUMENTS: Cl 703.12, AS3610
a7c45a20-3a94-54f6-afb9-6ca2943f9e98 | note | INSPECTION/TEST METHOD: Visual inspection
05906810-b764-5d7d-9383-20c6268d54bb | note | RECORD OF CONFORMITY: ITP Signed
991e4ea9-8d8f-5923-8e2b-f85e3f691969 | note | WP
f7e4a073-9055-5377-a6af-6c28cd4dc726 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
f5a5fdff-8dea-53d0-9a87-4d6a2ab633f0 | date | Date Completed:
| checkpoint | 2.7 - Concrete Placement and Compaction
16e5410f-c05f-5a23-a4b7-c45172635998 | note | FREQUENCY: Each Lot
27f6644d-2383-55b0-956c-4182054fe1aa | note | ACCEPTANCE CRITERIA: Concrete strength to comply with detail on IFC drawings and AS 1379
3699a717-0c88-56ac-95d9-b12c331dc0ca | note | ○ Concrete shall be thoroughly compacted by means of continuous tamping and internal vibration and shall be worked around any embedment’s and into corners of formwork or excavations to produce a dense concrete free from voids. Workable concrete mixes are exempt from vibration requirement. Concrete testing frequency in accordance with 610 requirements.
4b429e67-95f6-5bb7-8334-951e1a8c14ce | note | REFERENCE DOCUMENTS: IFC drawings, Cl 703.01, Cl 703.08, Cl 610.16, AS 1379
960e8e31-7999-5466-9566-e84ab3e64ab1 | note | INSPECTION/TEST METHOD: Visual inspection
0eee875b-97d0-5c1e-bd1c-048b3e7adc59 | note | RECORD OF CONFORMITY: ITP Signed
ff689309-a805-5bc5-86e5-175d6acad569 | note | WP
13504893-fd51-535b-8b63-335e3f5c92ec | note | RESPONSIBILITY: Site Engineer/ Site Foreman
29ac831c-c2ae-598b-a650-3fa2678f9425 | date | Date Completed:
| checkpoint | 2.8 - Surface Finish
a7c3a40e-439d-5a53-8ffa-d8a287ab21ee | note | FREQUENCY: Each Lot
b7191c46-8ac5-56a3-b567-1e70e8952d44 | note | ACCEPTANCE CRITERIA: Exposed surfaces shall be treated as follows:
d0518dc7-8cdb-58f8-9f3e-dc27d79cd0ca | note | a) Edgings
93af108e-5a3b-5414-b9dd-3080b7132282 | note | ○ All edgings rendered to a thickness ≤ 3 mm, within 30 minutes of placing or extruding concrete. Mortar shall consist of two parts of fine aggregate, one part of cement, and sufficient water to produce a mix of suitable consistency.
d9b60b65-e6d0-5893-958e-f15d7a26e0d9 | note | (b) Footpaths, other Surfacings and Shared Use Paths
804e460a-d894-5423-8eae-043c0aaeb10c | note | ○ Concrete compacted with internal vibration and worked until all the coarse aggregate is below the surface and the mortar comes to the top, struck off and finished to grade and cross section with a wooden float to produce a lightly textured non-skid surface.
93d4669b-ce99-5b9e-bee7-454bc000d8d6 | note | ○ All edges sharp and clean, and bullnoses regular and of uniform radius. All discoloured concrete shall be cleaned or replaced by the Contractor.
8c11370a-0144-5839-810a-e77ea748bf32 | note | ○ Permanently hidden concrete surfaces have a Class 4 surface finish.
ea6c3f56-f23c-5116-9e0d-9ead83d4916b | note | ○ All other concrete elements shall have a Class 3 surface finish for external surfaces and a Class 4 surface finish for permanently hidden surfaces.
00beed9b-1858-5624-9b67-e225b39fdbb6 | note | REFERENCE DOCUMENTS: Cl 703.25
fab982a4-9f7a-505a-96d9-6f070a8f8469 | note | INSPECTION/TEST METHOD: Visual inspection
a4d342bd-b42d-5fce-b16e-93055d054a83 | note | RECORD OF CONFORMITY: ITP Signed
c718e458-5f68-5011-b33d-3d156b41e2f0 | note | WP
940af0c5-7c86-5bbf-bcd5-f0dd9606f647 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
6bf80754-2a00-5476-8209-c2bfbc8461e4 | date | Date Completed:
| checkpoint | 2.9 - Joints
3bb6992e-41c0-55f2-b1fc-9daf675c2f70 | note | FREQUENCY: Each Lot
f1d89539-8f02-5db0-8576-b1a45980fcad | note | ACCEPTANCE CRITERIA: Transverse joints constructed at right angles to the back of edgings and the edge of footpaths and shared use paths. Joints in footpaths and shared use paths shall align with joints in adjacent edgings.
a1af7cd5-9bc9-5724-97e0-6f780b159af1 | note | a) Edgings
69703373-10f2-5fc2-a6ed-e5659436d3b7 | note | i) Traverse Joints – constructed at regular intervals ≤ 2.5m. Templates for edging using fixed forms shall be removed as soon as practical after finishing work. Resultant slot in edging shall be tooled to a depth of 20mm, and produce a groove ≥ 5 mm wide, following which a vertical cut shall be made through the base of the groove to a depth ≥ 50 mm from the surface.
70e60312-be41-592d-b97c-b2aa582dc334 | note | ii) Expansion Joints – placed at junctions with bridges, shall be 15 mm wide and filled with cork/bituminous impregnated particle board strip extending for the full width and depth of edging. Fill placed in position before concrete and held during placing of concrete.
9a9c9ebe-a4b8-5346-8972-2603c7f7b210 | note | b) Footpaths
6abc959d-633d-5a76-aaa9-658169f5ba76 | note | i) Expansion Joints
a9663584-3415-5ca2-9e4b-81261a61bbe3 | note | ○ Expansion joints placed at intervals ≤ 10 m. Expansion joint shall be 15 mm wide, filled with cork/bituminous impregnated particle board strip extending for full width and depth of paving. Filler shall be placed before concrete is placed and held in position during concreting.
50de86eb-5bd3-5878-95d0-941e6ae29b30 | note | ii) Control Joints
8d8ca57e-bfde-5706-9983-e8fdd490c81f | note | ○ Control joints at least 25% of paving thickness deep, 5 mm wide at 2.5 m intervals within 4 hours of placing concrete when air temperature is between 20 degrees and 35 degrees and within 24 hours when air temperature is < 20 degrees.
603e6718-0bd9-51e2-9ece-a55b2de8f4dd | note | c) Between concrete paving and shared use path
a7a72261-0689-5fdc-bae3-b0d280a4043b | note | ○ Except on narrow medians (< 2.0 m wide) surfaced full width, bonding between the concrete paving or shared use path and the edging prevented by painting the back of the edging with bitumen, or by a bituminous felt material between edging and concrete paving/shared use path.
ca3c6fbb-228f-5c06-9943-1305cd3f7833 | note | REFERENCE DOCUMENTS: Cl 703.26 (a), Cl 703.26 (b), Cl 703.26 (c)
454b1690-68f2-5302-bd57-28a7032674da | note | INSPECTION/TEST METHOD: Visual inspection
1106c800-e8d3-5dbb-9048-b4534996d7a5 | note | RECORD OF CONFORMITY: ITP Signed
30eb1f64-2ff2-5505-829b-fdfe2570380a | note | WP
bd93809c-2530-5f68-ae07-6eb7e770bc02 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
5c28c1c8-eb48-5c77-9074-fa52fa1df94c | date | Date Completed:
| checkpoint | 2.10 - Curing
6e1f64a0-2811-5008-877b-5b5249a28a8c | note | FREQUENCY: Each Lot
7fb319fa-bff7-5f89-a379-3bf8299b12ff | note | ACCEPTANCE CRITERIA: Match existing fixtures to within 5mm (pit covers, etc).
776eb273-2201-5795-841b-67ca40dddd44 | note | ○ Departure of line and level to design not to exceed 10mm at any point. Rate of change of deviation shall not exceed 10mm in 10m. For curves or shaped areas, the deviation of the finished work shall not exceed 5mm from a 3m straightedge at any point.
08f906f6-42dd-51fd-855b-1980a9db4c57 | note | ○ Section dimensions shall not deviate by more than 5mm except that overall width shall not exceed by more than 15mm. For dimensions less than 25mm the tolerance shall be +/- 3mm.
4d1320b4-3f45-546a-b57f-8957dbbdc4fd | note | ○ Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges
dd7caa0b-61b8-5256-80fc-9f4fbacc99ec | note | REFERENCE DOCUMENTS: Cl 703.10
ce01b8c5-f733-54cd-9fdc-d2454a8bf6bd | note | INSPECTION/TEST METHOD: Verify
fc4e7d16-66dc-55e7-acc6-c42837654c9a | note | RECORD OF CONFORMITY: ITP Signed
6b900eb0-5ea5-5128-a8da-6093dbad6b89 | note | IP
7590e470-2d82-54b1-8c85-15b9dec2f916 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
f7e54df9-7a05-5d6d-87db-1a57732d323e | date | Date Completed:
| checkpoint | 2.11 - Tolerances online, level and shape
ce06a51a-b7ab-5d21-87f9-7897c0c94dbe | note | FREQUENCY: Each Lot
926eb996-80e1-5ca0-87b7-4247bb85ad8a | note | ACCEPTANCE CRITERIA: Match existing fixtures to within 5mm (pit covers, etc). Departure of line and level to design not to exceed 10mm at any point. Rate of change of deviation shall not exceed 10mm in 10m. For curves or shaped areas, the deviation of the finished work shall not exceed 5mm from a 3m straightedge at any point.
361a0438-3bf0-56a5-b3f6-cdd639b1e7ea | note | ○ Section dimensions shall not deviate by more than 5mm except that overall width shall not exceed by more than 15mm. For dimensions less than 25mm the tolerance shall be +/- 3mm. Where median surfacings are to be constructed between edge sections of the same level, paving shall be crowned to produce a crossfall between 1% and 3% towards the edges.
cc40a727-a91c-56f5-8a96-525d9a839d03 | note | REFERENCE DOCUMENTS: Cl 703.15 (a), Cl 703.15 (b), Cl703.15 (c)
231fb284-dd07-5d8d-af63-e1b9ef86f55d | note | INSPECTION/TEST METHOD: Visual inspection
054bfb4a-942e-5231-b9e6-2890c1667433 | note | RECORD OF CONFORMITY: ITP Signed
b2fb0577-6cec-5fc7-9b78-401d723b9d36 | note | IP
84876b8d-848f-52ac-a076-25bb689efb6f | note | RESPONSIBILITY: Site Engineer
74eed070-1efe-5392-ae2b-2a093cf73c3a | date | Date Completed:
| checkpoint | 2.12 - Concrete repairs
4d1997cc-0c8d-51ed-9f00-ec4beecf8f56 | note | FREQUENCY: Each Lot
ce89abb1-5d39-5df5-8258-9970600584b5 | note | ACCEPTANCE CRITERIA: Any concrete repairs shall be carried out using a method and materials accepted by the Superintendent.
f1da1fa8-1e74-56fa-9a3f-49413c313a0a | note | REFERENCE DOCUMENTS: CL 703.08
241b3f23-d6e8-5a24-a933-cdbe9d4a235d | note | INSPECTION/TEST METHOD: Visual inspection
6df25503-6bf6-5587-a310-6eb3159fdb36 | note | RECORD OF CONFORMITY: ITP Signed
e5ed457a-b431-5b6d-8ba2-c1e2c58712cc | note | WP
270344f0-2848-5e2e-86de-f52751cf963d | note | RESPONSIBILITY: Site Engineer/ Superintendent
18689dcd-35d3-524f-babb-8e45c340d33b | date | Date Completed:
| signoff | Request Signature
| section | 3 - Completion
| checkpoint | 3.1 - Verification and Lot records complete
e0379a93-fbd9-5526-8874-b8c227720453 | note | FREQUENCY: Completion of each lot
c93c59d7-a256-5903-866e-020f276eeb06 | note | ACCEPTANCE CRITERIA: Completed work checklists, inspection and test results and contractor conformance records progressively and permanently saved and stored as soon as possible after they are received. Completed lot records are transferred to the Quality Team for final record verification prior to being closed
ad41d492-84d1-5324-bbc1-129a2e63f334 | note | REFERENCE DOCUMENTS: Test Certificates, QA Plan
6f5283aa-4840-5acc-b276-1a60db08001d | note | INSPECTION/TEST METHOD: Document review
df7e8e05-ca09-56f0-bc16-58390ec9dea6 | note | RECORD OF CONFORMITY: ITP Signed
4acd78e6-3b70-55e1-8238-4d23329caeb1 | note | TP
2b839e94-69e2-58cc-b4e4-d28025568aa3 | note | RESPONSIBILITY: Project Engineer/ Site Engineer
1b4b224f-0cb3-5a8d-8512-c9ecd3844437 | date | Date Completed:
| checkpoint | Final Inspection
4573e76e-203e-5c6e-b711-9c87637c77b1 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
5572a040-2a31-557d-8b3a-1c746cf2fd7b | textbox | Print Name:
190ae48d-94cc-5319-8b4f-e04f0c66a5b2 | textbox | Position:
e5f77401-1f7e-5cb8-bc3b-67f972cbcedf | date | Date:
| checklist | ITP-006 - Hot Mix Asphalt | itp | ITP-006 - Hot Mix Asphalt |  | 3bddd3a7-3304-4263-9f84-3523793118b9
| section | 1 - Construction Works
| checkpoint | 1.1 - Submission of Mix Design (Type Asphalt, mm Nominal Size)
0da9dd15-b928-5854-9b91-1710825aa908 | note | FREQUENCY: Prior to commencing paving
202be465-bfd6-5028-b92a-d568a9b4ee0c | note | ACCEPTANCE CRITERIA: Ensure this mix design has been registered and is reviewed by Superintendent prior to laying mix.
67d8ed42-d761-5ff5-a7fa-447b65a7e401 | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.06
0e66a5b7-5a1b-5168-ad6f-17ae1cf912f0 | note | INSPECTION/TEST METHOD: Correspondence of receipt of mix design
a77bcfcf-0463-5333-a611-39b0b370c563 | note | RECORD OF CONFORMITY: VR approval, Completed ITP
72e79d5a-c7aa-5470-9bcb-989a67629961 | note | HP
c52504fb-8bee-5c1b-ae48-5a2b006b4738 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
0802ee6f-bb2f-5328-9e99-094721e5081e | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.2 - Implementation of all measures and controls
0f3defc7-a28d-551b-be4f-9a5a5cfa90dc | note | FREQUENCY: Prior to commencing any activity
d38731b9-e5ed-5e03-b414-b26d96fd0c7c | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
7a942020-52f9-5b09-8b4f-ea742d8856fd | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
e36a3297-9b2a-54a9-96b9-8b51584b01c4 | note | INSPECTION/TEST METHOD: Visual Inspection
1f5718b3-12c0-5754-9598-8cc3ed502f3b | note | RECORD OF CONFORMITY: This ITP signed off
40e24211-164b-50fc-8473-3291369c678b | note | HP*
751475ca-39bc-54a2-9f7a-66a61619061f | note | RESPONSIBILITY: Site Engineer / Site Foreman
0cdd4ad4-aa99-5d77-b870-eb2aa153f004 | date | Date Completed:
| checkpoint | 1.3 - Site Inspection and Base Condition
4a7844d2-b646-535e-a017-2b24164f9a2f | note | FREQUENCY: Prior to commencing paving
1fc71db1-c4bc-5bfd-83a1-4b4b62a643b9 | note | ACCEPTANCE CRITERIA: Surface on which asphalt is to be placed is essentially dry and free from puddles and defects (holes, cracks, unstable material and edge irregularities) and loose materials.
e8654bf8-f5ee-58de-9a6b-ff2899ac4a38 | note | ○ Material and compaction test certificates conform for pavement
6f9a6d80-e07c-5f18-9121-262460e04e41 | note | REFERENCE DOCUMENTS: 407.14, AS2150 10.1, AS2150 10.3
aa98b063-248b-5e25-89ec-8e29e3efe673 | note | INSPECTION/TEST METHOD: Visual Inspection
c0cb2edc-bc34-5589-9100-0e7fa61b389d | note | RECORD OF CONFORMITY: ITP Signed, Test Certificates, Base Course Checklist
9311a750-050e-502c-869e-2d119ba6bebf | note | HP
d6ecafcf-3bfa-5725-8b2b-5f92d3d82b9c | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
0935cc3e-7d8e-59ce-9a22-dc149d8a7212 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.4 - Dryback
2c006a98-1896-5c30-9d00-7134f741bbf5 | note | FREQUENCY: Prior to commencing paving
c812f1bd-9953-5219-96ee-5f7b75543358 | note | ACCEPTANCE CRITERIA: Scale B Pavement Dryback and Embedment
5f211ec1-d26a-5292-91b4-99a03af11e13 | note | – 6 randomly selected test sites per lot required
fc494e3d-526d-540c-82cb-a9dc86a099f3 | note | – If Mean Moisture Ratio is < 60% & Maximum of any result is < 70% then Ball Penetration not required
b047b674-e377-52ab-a270-ae960c11020a | note | – If Mean Moisture Ratio is < 65% & Maximum of any result is < 70% then Ball Penetration Maximum individual result is 3mm
77be045d-7015-5296-b9e0-6c24c82ecd40 | note | – Testing schedule in accordance with 310.03 (c)
babc112b-add1-55e9-bd71-11f842a15501 | note | REFERENCE DOCUMENTS: 310.03(a), 310.03(b), Table 310.031, 310.03(c), Table 310.032
e67a878d-dc0f-54b3-a6ee-bd6b9c7a0122 | note | INSPECTION/TEST METHOD: Verify
9c57fe84-9bce-533d-9645-4b333d2e6b8d | note | RECORD OF CONFORMITY: ITP Signed off
ab5f6932-7a80-5455-8c65-d58ad8f7df19 | note | TP
694b0c38-b275-5acd-8fc7-65208cbb7dff | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor
35dba226-ce16-500e-b069-20353f31ecdf | date | Date Completed:
| checkpoint | 1.5 - Ambient Conditions for Placing
dad35083-f387-59bb-98d9-3c45a8edc7cd | note | FREQUENCY: Prior to commencing paving
ab3c69db-bd82-5469-a040-d2ffc362f35d | note | ACCEPTANCE CRITERIA: The majority of the surface area to be paved has a temperature greater than or equal to the following:
87b3ac2a-e3ad-54cd-b274-51cbcb129b19 | note | ○ Wearing Courses: 10°C for conventional binders or 15°C for PMBs
4bc614cb-c169-501e-8e64-2a04c8f5fb80 | note | REFERENCE DOCUMENTS: 407.17(a)
06ee7ff4-b13a-5b41-a800-b875c550fba0 | note | INSPECTION/TEST METHOD: Verify
370ede06-9137-54ba-b883-b2fd41c222c7 | note | RECORD OF CONFORMITY: Thermometer
48b9a8b7-84be-5a5e-bd70-396cbe2f6c5e | note | IP
66f7c64b-c638-5de2-9b3d-024431aab5fc | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
b046c4d7-351c-5cd2-a5d5-350dfb87d9c8 | date | Date Completed:
| checkpoint | 1.6 - Planning of Joints
5482e5a6-a4ed-5543-860b-9120bd5cf606 | note | FREQUENCY: Prior to commencing paving
614cc2b6-302c-5f0d-a9b1-25f5571404ab | note | ACCEPTANCE CRITERIA: Runs to be marked to ensure placement of joints satisfy the following unless otherwise approved by the Client:
7c369534-e7e0-59d7-81b9-cbbbe0162292 | note | ○ Transverse Joints Offset from layer to layer by at least 2m
64347da8-71b8-590e-92e7-29ad8c2d2f0f | note | ○ Longitudinal Joints Offset from layer to layer by at least
e588d21f-fa1c-5d19-ad08-25f4a78696d3 | note | ○ 150mm and be within 300mm of the lane line or centre of lane. Wearing course shall be on lane lines.
dd132533-139b-524d-bd82-0c154dec13c9 | note | REFERENCE DOCUMENTS: 407.21, IFC Drawings
4b431ff3-74c1-5198-9b65-9bd5fb1dedd9 | note | INSPECTION/TEST METHOD: Measure and mark out runs by tape measure or survey
91486e24-1fd2-5f31-b726-df6410135e94 | note | RECORD OF CONFORMITY: Paving Plan
36693100-9def-5d2d-9412-6a0cbc46c741 | note | WP
89c85b00-6c0d-51cb-bf62-f91523b1079e | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
a9d13f3a-c633-5138-b61e-a4433949dc15 | date | Date Completed:
| checkpoint | 1.7 - Longitudinal Joints with existing Pavement
56e0ef37-6286-57a8-a61c-8bd775a41a02 | note | FREQUENCY: Prior to commencing paving
69096dff-c6aa-5d6c-9896-d834669f137c | note | ACCEPTANCE CRITERIA: Where new pavement abuts an existing pavement, the existing pavement shall be removed in steps to achieve an offset from layer to layer of not less than 150mm.
f6966db5-71c7-58ab-9bf5-3eb196594035 | note | ○ Depth of step to be cut to the full depth of each indiviual layer.
24cf9e8c-ce1c-54f5-8e0f-2d6c6bf9dee4 | note | REFERENCE DOCUMENTS: 407.21 (c)
54382ce1-c376-5bfa-87a1-385248e613c8 | note | INSPECTION/TEST METHOD: Visual Inspection
56c7e62f-3b49-5ae4-9d8e-1598bafbef74 | note | RECORD OF CONFORMITY: ITP Signed
c44552a9-9465-5593-b0f1-098abaa63911 | note | WP
3a5ab7d6-56e8-528b-afbf-3b44403c9c10 | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
b2be3614-5f5d-5f26-bfa0-5c50c584f5cd | date | Date Completed:
| section | 2 - Asphalt Placement works
| checkpoint | 2.1 - Frequency of Inspection and Testing at the Mixing Plant
8d2a3f55-f6c2-55c1-83f8-e9799aed8c69 | note | FREQUENCY: As per Table 407.151
6cbbbf56-b811-512a-a6f6-d831c5edfea1 | note | ACCEPTANCE CRITERIA: The frequency shall not be less than that shown in Table 407.111, except that the Superintendent may agree to a lower frequency where the Contractor has implemented a system of statistical process control and can demonstrate that such lower frequency is adequate to assure the quality of the product.
05f5d652-bb98-5b18-8be6-0d9750352647 | note | REFERENCE DOCUMENTS: 407.151
5cc547fe-2257-5b1f-81a3-7f3d6fdbd7b6 | note | INSPECTION/TEST METHOD: Test Inspection
3395ef8f-cd02-5c6d-862d-38efd2bb1004 | note | RECORD OF CONFORMITY: ITP Signed
cf034219-02c1-5efa-a3db-b594e022a022 | note | TP
bee7693c-fcb5-51c6-bae3-a83dfb2979ad | note | RESPONSIBILITY: Project Engineer/ Asphalt Supervisor
b89a6bab-f69d-5f3b-baec-fed2cc10d561 | date | Date Completed:
| checkpoint | 2.2 - Tack Coat
3497ceaa-8e11-575b-8823-d4ee32c60de8 | note | FREQUENCY: Prior to commencing paving
3026a7a6-c058-5cf7-aeb1-66ef738965b5 | note | ACCEPTANCE CRITERIA: As per VicRoads Section 407.15, a tack coat shall be applied to cleaned/existing asphalt or a sealed surface on which fresh asphalt is to be placed unless the unsealed surface has been primed. Tack coat is not required on primed surfaces, on clean, freshly placed asphalt or when the layer to be placed exceeds 50mm.
8c2fb925-be57-59bc-94ca-81391044a00e | note | ○ Tack coat to be sprayed on existing asphalt joints.
b52c906c-315e-5582-963d-84e8ec760959 | note | ○ Tack coat must be allowed to turn from brown to black before paving.
c77f9077-3e67-5c89-8019-60bc662e2a19 | note | ○ If required, tack coat to be sprayed in a uniform film over the surface to be paved at a rate of 0.15-0.30 L/m2 of residual binder (60% bitumen )or 0.30 to 0.60 litres/m2 (30% bitumen content). This rate is to be doubled on joints and chases.
fb967a88-5634-5ae9-af19-003ecc61a90e | note | REFERENCE DOCUMENTS: 407.19, AS2150 11
8808b527-09b4-5f26-baf2-4805ac8df39a | note | INSPECTION/TEST METHOD: Visual Inspection
465d9234-3cde-5971-a5cc-d6c39a5ec236 | note | RECORD OF CONFORMITY: Spray area
b148f828-044a-5af3-9558-4df7d68de10f | note | WP
3a1d7180-45be-5121-96d2-a92bba64453d | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
40644933-4f09-501f-9e88-bdbc603d9bcd | date | Date Completed:
| checkpoint | 2.3 - Commencement of Placing
cd3d96f9-1e0c-57cb-98f0-aa6a7f44625e | note | FREQUENCY: Prior to commencing Paving
3901acfe-2845-51db-907f-f4578164cbed | note | ACCEPTANCE CRITERIA: The placement of asphalt on the sub-base or granular base for a new pavement or for an overlay of an existing bituminous surfaced pavement shall not commence until the consent to proceed is obtained from the Client.
9908e4ac-c802-5082-929e-b0cfc44f1535 | note | REFERENCE DOCUMENTS: 407.23
50d7dafd-203b-56ba-bbf1-17ce7a300208 | note | INSPECTION/TEST METHOD: Visual Inspection
9e642598-4275-5e6b-8cc9-dcbe2c0e101e | note | RECORD OF CONFORMITY: ITP Signed
ee500901-2fc6-53dc-aace-fedc3a02d3c3 | note | HP
2d04605b-7dab-5301-bb6e-23780bd2f50c | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor / Superintendent
2efb4d99-4fc2-55fe-94b7-875e458d2187 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.4 - Mix Design Confirmation
9c6343a8-7034-5121-a19e-33597406bbb2 | note | FREQUENCY: Each lot
be171d0d-c889-5ed5-827e-4332e971df13 | note | ACCEPTANCE CRITERIA: Check correct mix design as per pavement design has been delivered prior to laying mix.
7782e7a3-a8b0-5bef-938e-2cdf6f92473a | note | REFERENCE DOCUMENTS: VicRoads Spec. Cl.407.09
eff12b54-b160-5ff6-a7c2-5a49cb81045a | note | INSPECTION/TEST METHOD: Visual Inspection & Delivery Docket
981eb64a-f08c-5021-8d10-bcbe03191f46 | note | RECORD OF CONFORMITY: Delivery docket, Completed ITP
5b733ffb-7e88-5442-89fc-e9975a6dba2d | note | HP*
2a059b0b-8645-5f83-96bc-93fb73ab2d72 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
6661ac0e-9736-59f2-a5f4-6f19e4505c2b | date | Date Completed:
| checkpoint | 2.5 - Delivery of Mix
19120f91-3822-5501-b9b9-36d7347641f4 | note | FREQUENCY: Each load
1d369bc2-0a17-5710-80a6-ff573e3c213c | note | ACCEPTANCE CRITERIA: Asphalt is not segregated, binder is not separated or does not contain uncoated particles and the temperature from mixing plant is not more than 175°C.
e68e5e59-06a0-5eda-8372-b4530a50ab2e | note | REFERENCE DOCUMENTS: 407.11
9cab462b-34ec-54b7-a57e-acfbb751fc15 | note | INSPECTION/TEST METHOD: Visual Inspection
e8665bec-a8c0-5cf8-85bd-28850328a5d3 | note | RECORD OF CONFORMITY: Delivery Docket
f8ee1c8e-f30b-510f-afb9-012725d4f534 | note | WP
ae77a787-4f80-587c-8e82-184b6205183c | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
697a13e0-cda1-540a-a103-bc4c17b4a108 | date | Date Completed:
| checkpoint | 2.6 - Traceability
470a92c5-f27b-5f02-b6c8-7b0cee868884 | note | FREQUENCY: Each lot
387a55b9-3d41-50f2-b2d8-92ed7c6c522c | note | ACCEPTANCE CRITERIA: Ability to locate asphalt test results placed in three dimensions i.e. start/end chainage, offset/lane and layer
2083811b-b65a-5820-b562-cf63f9ce701d | note | REFERENCE DOCUMENTS: Fulton Hogan Quality Plan
df8caa68-f682-5c5a-b226-9dded1d5adb8 | note | INSPECTION/TEST METHOD: Verify
25e5279b-19fd-5ea8-830b-a854ec3c1a64 | note | RECORD OF CONFORMITY: Daily Lot Record
c59a0226-42ba-5ca5-8b1e-82ee62f431c0 | note | IP
87157674-ed44-53e8-83f5-015583f7872c | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
67a6e3b6-6f38-5609-8fa3-6ba69e623029 | date | Date Completed:
| checkpoint | 2.7 - Layer Thickness and Level Control
9cabad1c-86da-5d60-8b20-b4decbebe79e | note | FREQUENCY: Regularly during paving
d0cddcee-1806-580c-b0cf-f4d81549b093 | note | ACCEPTANCE CRITERIA: Thickness of asphalt layer conforms to asphalt thickness on drawings or specifications
df0d31f8-6417-5748-b6eb-2b430b4a55d1 | note | REFERENCE DOCUMENTS: IFC Drawings
4ca20e06-10ed-5edb-9fc3-49128c403a44 | note | INSPECTION/TEST METHOD: Verify
48ff0d49-8274-57aa-b8cb-fc5aa845bee4 | note | RECORD OF CONFORMITY: Dips using ruler or dip stick
c48e3321-3a75-59e5-86f7-3e845a18e500 | note | WP
970248a9-7de3-5957-9a02-0de35facbc54 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
fed78082-6b1b-5968-9eb5-38045f2e363b | date | Date Completed:
| checkpoint | 2.8 - Paver Stoppages
b122aa06-8fce-5bc8-b462-f31a6af063db | note | FREQUENCY: If paver stops
c993521f-fec5-5485-a6f1-25938d4641ab | note | ACCEPTANCE CRITERIA: A transverse joint shall be constructed if the asphalt in front of the screed cools to below 120°C
8d213f5e-7e32-5ff8-92c0-c9bb43f0c68e | note | REFERENCE DOCUMENTS: 407.25 (c)
bb444f84-7de1-5100-bcbc-6b2beb7195d9 | note | INSPECTION/TEST METHOD: Verify
f896bdc5-3405-5de1-bd97-83c9093cc62d | note | RECORD OF CONFORMITY: Thermometer
e2055d88-91a0-51f2-939d-b017f9b922ab | note | WP
5cfdc52b-bf88-549f-86c1-e4a784f0d1a5 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
055babdb-79e0-5834-8ba8-5d0dd69b4e7c | date | Date Completed:
| checkpoint | 2.9 - Surface Finish of Wearing Course
685dbc7f-eafe-5fe5-9b52-d559f81a62e2 | note | FREQUENCY: During paving and after final roll
e53e117b-52e2-504a-911c-f44b0aad03ed | note | ACCEPTANCE CRITERIA: The finished surface of asphalt wearing course shall be of uniform appearance, free of dragged areas, cracks, open textured patches and roller marks
d80d42d2-dadc-510f-90fb-0082a59a42a5 | note | REFERENCE DOCUMENTS: 407.29 (a)(i)
3573b470-da47-5d06-b96f-57daf3c1b9c2 | note | INSPECTION/TEST METHOD: Visual Inspection
1eed8855-6fa3-5dee-8c2c-1f9ddd0f09aa | note | RECORD OF CONFORMITY: ITP Signed
588c0b04-6c10-5ccc-b217-6f9bce107c4a | note | WP
c8a59ffb-23ae-5104-9d4f-b5b128a4e6c4 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
906bce33-63f5-524d-8a46-46f0245c25e1 | date | Date Completed:
| checkpoint | 2.10 - Kerb and Channel
6c954401-50e3-512f-a350-457f0398c73d | note | FREQUENCY: During paving and after final roll
c3446d17-5bab-5231-a904-6306915f72e5 | note | ACCEPTANCE CRITERIA: The edge of the wearing course shall be either flush with or not more than 5 mm above the lip of the channel unless otherwise specified
492d6024-18b0-541f-bb2f-99f1fd96e214 | note | REFERENCE DOCUMENTS: 407.29 (a)(ii)
47b5b1a2-0dcf-5102-bccb-3c2b021d49b9 | note | INSPECTION/TEST METHOD: Visual Inspection
d6fb25c2-b47f-5d84-be57-fd55e83a6f69 | note | RECORD OF CONFORMITY: ITP Signed
c263ef3d-ad82-55e1-a47b-15e09d47f1b0 | note | WP
49d4fc11-2c23-5a4c-9428-fd58bd46ddcd | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
47dc47ca-d91c-5116-b0fb-732c147e2ec9 | date | Date Completed:
| checkpoint | 2.11 - Alignment of layers not placed against concrete edge
21048502-a3fe-5b40-b31e-f11a4ef47eb7 | note | FREQUENCY: During paving and at completion of work
edc3694a-cb34-58b1-8e29-99263c030c54 | note | ACCEPTANCE CRITERIA: The edge of asphalt layers shall not be more than 50mm inside nor more than 100mm outside, the designed offset from centreline or design line.
8d6ce2cf-8301-522e-8723-982f0816368e | note | ○ The rate of change of offset of the edge of layer shall not be greater than 25mm in 10m
e7b209e9-5302-5127-a6c9-7f4d3e029720 | note | REFERENCE DOCUMENTS: 407.29 (a)(iv), Drawings
bd678957-5027-593d-84dc-eae62e09a209 | note | INSPECTION/TEST METHOD: Visual Inspection
838e8063-2485-5699-b667-38e362fcf48e | note | RECORD OF CONFORMITY: ITP Signed
448b6d6e-97b3-5e8c-b061-80344767ef85 | note | IP
ad0e4c07-4982-5b60-b8de-1ec79ca8a883 | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
5926f2e3-024f-5657-be5a-d923c5255920 | date | Date Completed:
| checkpoint | 2.12 - Width of layers not placed against concrete edge
a8dbf998-8f49-5ff9-9ef8-fa150fd6eece | note | FREQUENCY: During paving and at completion of work
760641ed-09bb-53e1-b29d-b1ea9920c471 | note | ACCEPTANCE CRITERIA: The width of asphalt layers shall not be less than the design or specified width of layer by more than 50mm or greater than the design or specified width by more than 100mm.
22d150ad-17e2-51de-9815-dea0c4a94618 | note | ○ The average width over any 300m shall not be less than the design or specified width
b60cbdac-2abf-5abf-9842-cdeda028c878 | note | REFERENCE DOCUMENTS: 407.29 (a)(v)
e7ec3820-b588-5033-bdd4-6da613908c39 | note | INSPECTION/TEST METHOD: Visual Inspection
a7df432a-e4e9-51cd-b0dd-8ceabe56b44b | note | RECORD OF CONFORMITY: ITP Signed
cac5eca6-ffe1-53a6-a891-a9dd20d0fb9a | note | IP
02a7b702-16b4-574e-95f6-aa9800efb2bb | note | RESPONSIBILITY: Site Engineer/ Asphalt Supervisor
5514f7b4-7292-5243-aa03-6cd89f5c401f | date | Date Completed:
| section | 3 - Testing
| checkpoint | 3.1 - Compaction
e7fa786b-5094-5ec3-a07a-8bedd89efea2 | note | FREQUENCY: Per Lot
f49585f9-d88d-5718-8e83-0a58d5f33f0d | note | ACCEPTANCE CRITERIA: For layers <50mm, if characteristic density ratio is:
14be7698-49a5-5093-b7ed-b9fb96a5ff24 | note | ○ 94.0% or greater Accept lot
db03d4f9-51a0-5f9d-951e-f5851a01ea1e | note | ○ 91.0% to 93.9% Lot may be accepted at reduced rate
d3b143ee-42e2-5495-a9da-cafc77f2777f | note | REFERENCE DOCUMENTS: Table 407.271
d9d25fd4-c72b-549a-8fe0-72c83ae497cd | note | INSPECTION/TEST METHOD: Verify
963729e4-3a12-57cf-a4dd-e6ceae4451e7 | note | RECORD OF CONFORMITY: Test Report
625bc982-25fa-5215-b50a-62beecaa4fb0 | note | TP
f161b7e9-2b41-5b90-ac2a-5d6a2184e5a3 | note | RESPONSIBILITY: Site Engineer/ Lab Technician
ae9d1fee-149b-5f8f-9550-8ed29decb95c | date | Date Completed:
| checkpoint | 3.2 - Level Conformance
f32e547d-f51e-59d9-b5ad-d6cde098ed86 | note | FREQUENCY: Per 4,000m2 at completion of work
c7eec371-4cc2-5b3d-aaad-5e29c09d3090 | note | ACCEPTANCE CRITERIA: Scale B: Individual departures from design not to exceed ±8mm with a standard deviation of no greater than 10mm
188fa2ae-1596-5a1d-9451-45f713865278 | note | ○ Minimum number of measurements per lot is 40
943f2765-ca87-52e5-8d04-c4117ea63b87 | note | (ii) Kerb and Channel: Refer to Item 2.10 of this ITP
c844f71c-c46d-502a-9791-e72d218071c7 | note | REFERENCE DOCUMENTS: Table 407.293, Table 407.292
d73d1862-2251-5e1a-a85a-fd9a3ec35bf9 | note | INSPECTION/TEST METHOD: Survey by VicRoads Section 173
f36ce4a1-876d-5adf-8130-f1623a7a37ad | note | RECORD OF CONFORMITY: Survey Conformance
9fed002c-deab-51fb-bfd1-7641a02e2892 | note | SCP
cfa6360f-5924-5432-a37e-cb153e186bf6 | note | RESPONSIBILITY: Site Engineer/ Surveyor
26bff980-f298-54c1-8abc-7e12a75781e4 | date | Date Completed:
| checkpoint | Final Inspection
f0712851-e7e8-57e3-bd56-6f1ce8d33c95 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
b4db3104-b5ec-5a49-b5b4-a152025b7e0a | textbox | Print Name:
c8f4f543-0343-52e9-8285-0bbc729addb3 | textbox | Position:
705c9389-778d-557a-b273-7ed1a7f2ce8e | date | Date:
| checklist | ITP-007 - Pavement Markings | itp | ITP-007 - Pavement Markings |  | d11e7e1a-edf3-496d-8f8f-21d7d4e603aa
| section | 1 - General
| checkpoint | 1.1 - Check for correct documentation
4ab8e107-c517-5ab2-a68b-1b38667a4ab4 | note | FREQUENCY: Prior to commencing any activity
a40054d9-1702-5a8f-85b4-eb78fcde4752 | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are:
2a19cab8-3fb4-5fc3-a5b5-36be09223b5b | note | – using the correct and complete set of drawings
315eec88-c372-5cd2-bbbf-2cbfd91970fe | note | – all drawings are the latest revision
9b10ad29-a8fd-5485-ba38-a0aae7cfc9f5 | note | REFERENCE DOCUMENTS: Drawings and drawing registers
9f8e524b-e0af-5fbc-aa8c-0c6931aac65b | note | INSPECTION/TEST METHOD: Visual inspection
77b26ffa-d2f4-594e-b0f6-79447d3a27ef | note | RECORD OF CONFORMITY: This ITP signed
e6c8062b-a5da-5007-a0d2-3c551f1c9a6d | note | HP*
64b49ee0-5910-5bfb-a978-cff368aebefb | note | RESPONSIBILITY: Site Engineer / Site Foreman
d0838d87-d536-5a03-a211-284a16b9b831 | date | Date Completed:
| checkpoint | 1.2 - Line marking conformance
00bd4c53-6a69-5cd6-85af-431881dccdea | note | FREQUENCY: Prior to commencing any activity
b0bc3f25-b04d-5d15-bcaa-078fdaf7feb1 | note | ACCEPTANCE CRITERIA: Materials to be used must conform with the specification
6e3c8f7f-555e-5997-ac4d-17e9c232b068 | note | REFERENCE DOCUMENTS: Cl 721.A05, IFC Drawing
a746d40f-dc95-5eae-a4db-9323741a88cb | note | INSPECTION/TEST METHOD: Record Review
9750f893-7b59-5bfc-a026-a2be5290d128 | note | RECORD OF CONFORMITY: This ITP signed
b53f95dc-fe1e-55e1-a1fb-92943684f8e2 | note | IP
5d713e9e-24b7-5ece-bd43-e6702e9ed4ff | note | RESPONSIBILITY: Contractor Representative
fa2178f1-c777-55ed-bc38-141698d1a861 | date | Date Completed:
| checkpoint | 1.3 - Site Preparation
b635c426-b7cd-574d-b97b-17cc0b7e312a | note | FREQUENCY: Prior to commencing any activity
98c4822d-18ef-5a74-a43e-64b818e16675 | note | ACCEPTANCE CRITERIA: Removal of any existing unsound, obsolete or redundant pavement markings
0cfbf3a8-62d6-552e-b8d8-8615557bfd3e | note | REFERENCE DOCUMENTS: Cl 721.A06
1fd5a15c-85f9-5755-b299-c15ce24e7591 | note | INSPECTION/TEST METHOD: Visual inspection
0587959b-0c27-5a5e-9e80-a06fb69f7558 | note | RECORD OF CONFORMITY: This ITP signed
f5cd6617-97ae-5dfa-ab27-f30440ba0e3c | note | IP
cbda5636-5243-5ca6-99a0-2d596a651226 | note | RESPONSIBILITY: Contractor Representative
7f6da263-6434-54d0-b0ad-481a72c8c977 | date | Date Completed:
| checkpoint | 1.4 - Set-out of Pavement Markings
b6d8dcf9-f496-5fb0-8705-ce957ebac3f5 | note | FREQUENCY: Prior to commencing any activity
3b3636ad-d046-5751-933d-69d87360cc2a | note | ACCEPTANCE CRITERIA: Pavement markings to set-out in accordance with IFC Drawings
82ceb3b0-b60f-5279-a870-94b6e911d646 | note | REFERENCE DOCUMENTS: Cl 721.A09
cfec81b1-8e0a-5a5a-b534-8d86c534144b | note | INSPECTION/TEST METHOD: Visual inspection
51b26ff1-db2b-5740-a349-17596a1d7551 | note | RECORD OF CONFORMITY: This ITP signed
6d07145a-eb71-553b-87df-bdd9ad44f000 | note | IP
b9aa712e-795d-581d-8daf-3cf9c0b5c5d2 | note | RESPONSIBILITY: Contractor Representative
d7ed9bb3-6026-5df2-8974-d7023fc71fe4 | date | Date Completed:
| section | 2 - Pavement Markings
| checkpoint | 2.1 - Acceptance of Work
0c0af253-8008-5cc9-90af-a380c634dbb4 | note | FREQUENCY: Each Lot as required
55cb169d-467e-536f-bd67-31b07384be4c | note | ACCEPTANCE CRITERIA: Where removal of unsuitable pavement marking is required, the method of removal shall be subject to the approval of the Superintendent before removal works commence.
1a2c1b4b-be9f-5e6e-b450-35de8add1120 | note | REFERENCE DOCUMENTS: 721.A12
e5e8cda0-57ca-5a72-a622-495d735b7a9f | note | INSPECTION/TEST METHOD: Visual Inspection
c1225745-4552-58c6-93f9-32cc2142b7c2 | note | RECORD OF CONFORMITY: This ITP signed
368aa4ff-3e57-5b12-8a88-0605d20fbbd4 | note | HP
f09bc8c4-5a11-5147-92b7-08a9a7020270 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
d6f93485-ac11-5727-9479-d6f331da3d1f | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Position of Markings
4770a150-aacb-5bde-9257-3471f3cfd780 | note | FREQUENCY: Each Lot as required
faa05356-5061-5683-9a24-6f46cb67c37a | note | ACCEPTANCE CRITERIA: All markings are to be set out in accordance with the dimensions and spacings as required by the appropriate standard in Clause 721.A03.
77200013-6b41-5ecd-8e02-927c5de0bd96 | note | ○ Painting/application of material shall not commence until the Superintendent has inspected the set out and given consent to proceed, unless an exemption has been granted in writing by the Superintendent.
666ee98c-b968-5c3e-b90c-809407eb9fc0 | note | REFERENCE DOCUMENTS: 721.B05
816388d6-85d6-5918-b9a8-6e6387bcc56b | note | INSPECTION/TEST METHOD: Visual Inspection
4c81928b-ae94-52dd-a6b2-d88f793ea6ba | note | RECORD OF CONFORMITY: This ITP Signed
86c530c6-6b14-589b-9bd3-a72701a3d63a | note | HP
d38bfa02-6ef7-5ec4-9626-c9b8dbcf293a | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
8f666a00-268f-5a53-bf70-a4b58b7a76f0 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.3 - Installation of Linemarking
84474bcb-eab2-5b1b-a61f-e947309a270d | note | FREQUENCY: During Construction
5ab1de76-f4bc-5861-bfee-cfc94ed1ddc5 | note | ACCEPTANCE CRITERIA: Line marking installed as per the IFC drawings
c9e80045-eff9-56c3-a9f8-866199465e54 | note | REFERENCE DOCUMENTS: IFC Drawings
ef282275-7f0a-5904-b9a1-1795c514ebcd | note | INSPECTION/TEST METHOD: Visual inspection
efd2df6e-a8da-5d77-a9a7-20246045ba88 | note | RECORD OF CONFORMITY: This ITP Signed
74d3ff0e-d447-5b0e-9ed1-1bf5f5f58963 | note | IP*
e10b608a-dcb0-5350-9f20-085c9fc626b6 | note | RESPONSIBILITY: Site Engineer / Site Foreman
28be19a2-7dcd-5708-9e44-9f5719d60e3d | date | Date Completed:
| section | 3 - Sign Installation
| checkpoint | 3.1 - Completion Inspection
d0dd5792-fab5-5ddf-8269-c1b91b51d7fd | note | FREQUENCY: Each Lot as required
be4dd93b-cb90-5a8e-ad89-b61de7e159b7 | note | ACCEPTANCE CRITERIA: Completed marking shall be uniform in appearance, texture, width and thickness and the surface shall be free from blister, air bubbles, tears, lumps, overlaps, unbeaded areas, tyre marks or other defects.
44b1c500-73b5-58d5-984a-a3cee4f83a0a | note | ○ Edges and cuts-offs shall be neat and sharp , and there shall be no visible run-off, overspray, dribbles, splash or spillage on to the surrounding area, or on to parked or passing vehicles.
5da189e7-8684-5f1d-be1b-7182fe62b44a | note | REFERENCE DOCUMENTS:
eb65a9e1-8633-51a2-8de8-632a4b5faa62 | note | INSPECTION/TEST METHOD: Visual inspection
becc4e91-e99f-51bd-a8c2-b4971f852a32 | note | RECORD OF CONFORMITY: This ITP Signed
b2e66858-148a-57ac-a811-1e4c2189e71e | note | WP
80c93943-484c-5744-b8c4-120f06e3edd0 | note | RESPONSIBILITY: Site Engineer / Site Foreman / Superintendent
1eeebec3-8cbd-5653-857f-cd95e7bb3af6 | date | Date Completed:
| signoff | Request Signature
| checkpoint | Final Inspection
6f0b249a-0797-525c-9fba-391036333a62 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
f20d1852-6f06-57ec-a077-7dbfec606b3f | textbox | Print Name:
54266283-270d-5992-8ae9-91e7affd9a47 | textbox | Position:
e7eef0d2-ba29-5f5b-85e4-4a0be63de837 | date | Date:
| checklist | ITP-008 - Landscaping - Irrigation | itp | ITP-008 - Landscaping - Irrigation |  | b3a8e7b4-7c0b-4e8a-a456-0ede1685027a
| section | 1 - Preliminary Works
| checkpoint | 1.1 - Pre-commencement meeting
ca6778de-8eee-5777-b3d8-e27fb43f9f48 | note | FREQUENCY: Prior to commencing any activity
a2a664de-9a12-5bb9-b364-279293bdf7bf | note | ACCEPTANCE CRITERIA: Hold a pre-commencement meeting with council's representative prior to commencing any landscaping activities
c1c04753-9556-575c-b0b1-862d152569c8 | note | REFERENCE DOCUMENTS: IFC Drawings
0472d9d4-7dc0-5c28-a2bd-4d5ddf19582d | note | INSPECTION/TEST METHOD: Verify
b9497992-c6b2-5b4c-a45d-9c41ba69a7fc | note | RECORD OF CONFORMITY: ITP Signed
43099775-71f8-5237-af22-d97d08a167e1 | note | HP
52ed50e3-96ac-59ba-9523-e415f2238b4b | note | RESPONSIBILITY: superintendent/ Site Engineer
d6a7ba0f-5525-5e41-8d3c-48922a9be07d | date | Date Completed:
| signoff | Request Signature
| checkpoint | 1.2 - Check for correct documentation
c91be041-a5be-5285-a26d-92f5f6ef6b5d | note | FREQUENCY: Prior to commencing any activity
93554083-3f18-5d0b-ac7f-4e3920ab66fb | note | ACCEPTANCE CRITERIA: Ensure that all employees and subcontractors are: - using the correct and complete set of drawings -all drawings are the latest revision
7605b547-78c4-56a3-ba5d-6c3da7609d1f | note | REFERENCE DOCUMENTS: Drawings and drawing registers
d154fe0d-5b75-5fc0-900f-65f439c5e85c | note | INSPECTION/TEST METHOD: Visual inspection
63cb55dc-6129-57ea-b2fa-c3a24350352e | note | RECORD OF CONFORMITY: ITP Signed
2e39d191-d6db-5185-9bd2-aae09f8fc38f | note | HP*
2f9f0361-1300-5867-b390-a2a32c2a50c8 | note | RESPONSIBILITY: Site Engineer /Site Foreman
7652b5e9-7f33-527e-90ba-cbcf13f6d28e | date | Date Completed:
| checkpoint | 1.3 - Implementation of all measures and controls
58279b71-8864-5e9e-ade6-9894169bcbd2 | note | FREQUENCY: Prior to commencing any activity
68932d70-f744-5d5b-88e4-a5bd42b7c1e8 | note | ACCEPTANCE CRITERIA: All necessary measures and controls are being implemented, that is: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
3d8266a7-ade5-5bc8-923a-1d2d3b733e6e | note | REFERENCE DOCUMENTS: SMP, PMP, EMP, QMP, TMP and SEQ documentation.
01b2ca78-433f-52f3-8907-590751452e62 | note | INSPECTION/TEST METHOD: Visual inspection
e6180111-7fa4-5e1f-9ab2-ea2ca7779b2d | note | RECORD OF CONFORMITY: ITP Signed
4ed07c9d-72dd-54f1-8255-1a8e544e13ed | note | IP
7d825657-1167-579d-b769-1010f8327d52 | note | RESPONSIBILITY: Site Engineer / Site Foreman
5c638b66-f28c-5ed1-8a01-ad08eeff8edc | date | Date Completed:
| checkpoint | 1.4 - Irrigation System
9af816aa-a07b-5ba3-bae3-5965f0356cdb | note | FREQUENCY: Prior to commencing any activity
2d1ffc1b-76e1-5aea-92dd-e5d7819f3857 | note | ACCEPTANCE CRITERIA: The contractor shall get the design approval from City of Ballarat on the irrigation system prior to commencing the activity
16c4696c-90d6-5058-9952-1806422f4df3 | note | REFERENCE DOCUMENTS: Landscape Specification Cl 7.1
723eee6b-e6d9-525e-832c-1f78a9e8cecc | note | INSPECTION/TEST METHOD: Verify
3d3b57f1-919c-586f-86ed-201fd820a5e3 | note | RECORD OF CONFORMITY: ITP Signed
c9cd5879-1e07-5257-8b4b-c15e6489aa74 | note | HP
f2c3b1fb-c4b4-5ea3-90d2-4e56603bacdd | note | RESPONSIBILITY: Superintendent/ Site Engineer
8bf50af0-a6ce-5057-b3dc-2c92c57fad8c | date | Date Completed:
| signoff | Request Signature
| section | 2 - Construction Works
| checkpoint | 2.1 - Setting Out
e7754ec4-3f13-5275-915f-b665d7c3396d | note | FREQUENCY: Prior to start
ffbfc6e4-60fc-5388-a690-e3b033adbf80 | note | ACCEPTANCE CRITERIA: Set out work in accordance with drawings. The superintendent will review and confirm set out. The alignment and survey/level pegs will be indicated to the Contractor on the Site by the Superintendent prior to the commencement of work. No survey/level pegs to be removed by any persons until completion of works.
394a5ac4-bc31-53a5-9608-c9dcd1136ee2 | note | REFERENCE DOCUMENTS: Cl 703.17
c641c725-8d6b-58f7-afd1-b624bfd70b5d | note | INSPECTION/TEST METHOD: Verify
38415601-7638-5af5-98b2-57e1fd35d4ed | note | RECORD OF CONFORMITY: ITP Signed
aa604bfc-31a0-5c89-b98e-22a68a7c05c4 | note | HP
690c6b48-60f8-58e5-b455-f400047f291d | note | RESPONSIBILITY: Site Engineer/ Superintendent
a6884b80-1287-530e-a1b5-681d3b550411 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.2 - Stripping of Topsoil
b346c3b8-5e5c-597f-af6c-a72dd79eabf2 | note | FREQUENCY: As required
098fb0e2-a0fe-5cd4-9777-742bf293c4f4 | note | ACCEPTANCE CRITERIA: Topsoil shall be stripped for the full width of the formation:
0636a2c0-c5ab-5108-b3f7-255a73d0ef50 | note | (a) defined by the line through batter points extended to include any rounding and any surface and catch drains;
b57f49d4-63d1-58d9-b8e8-69160d0f0788 | note | (b) by a means which avoids contamination with subsoil and does not increase the extent of unstable areas; and
6adfac30-dab6-56a8-86b7-b0491a10034e | note | (c) placed in stockpile or prepared areas.
703caa1a-0def-527e-b7fc-88764509c20f | note | ○ Unless there is an excess of topsoil to be removed from site, topsoil shall not be removed from the site.
03889f00-2163-5845-a04d-0353278be405 | note | ○ The Contractor shall treat and manage site topsoil before stripping, and after spreading, to remove and/or minimise the spread of weeds and other pathogens and pest organisms throughout the site.
ffa5adda-91a6-5e11-b7d3-973caab1d3e1 | note | ○ Stockpiles shall be maintained in a neat, well shaped state capable of shedding water. Topsoil shall be re spread as soon as practicable.
4d4f7c92-d4fd-5649-980a-eaf428f560a6 | note | ○ Stripped surfaces shall be graded to an even self draining surface.
0db3db04-b9ac-58e7-b35b-bda14a54088f | note | REFERENCE DOCUMENTS: Cl 204.05
2485e3d9-b2e2-53f7-a419-c612c11fd6d7 | note | INSPECTION/TEST METHOD: Visual inspection
e90c502d-7683-5735-b3bc-dd7884b93a6d | note | RECORD OF CONFORMITY: ITP Signed
a9b5cbd5-53bd-50a6-a60a-863232b09181 | note | IP
54d68c74-e7a9-5dae-9262-411f4516d953 | note | RESPONSIBILITY: Site Engineer/ Site Foreman
dd4daf8d-61ba-52c9-8461-a09341d897aa | date | Date Completed:
| checkpoint | 2.3 - Topsoiling
26e61e99-c18c-58aa-8eff-5d89f47e5040 | note | FREQUENCY: As Required
b07fe374-84a9-5c51-886c-c378416603c7 | note | ACCEPTANCE CRITERIA: Topsoiling shall not be placed over cut and fill areas until the Contractor has verified that such areas comply with the requirements in Clause 204.03
056aa46b-21e3-5fcf-a6b0-78eb0c5c7df9 | note | All unpaved cut and fill areas within the limits of the batters, including batter roundings but excluding cut batters steeper than 1.5 to 1 (horizontal to vertical), and any other area disturbed by the Contractor's operations, shall be topsoiled to the following thicknesses measured normal to the slope:
9fe3433c-c82d-5fd5-a1c3-e9fed50faf53 | note | (a) batters with slopes of 2 to 1 (horizontal to vertical) or steeper 50 mm minimum
7142948c-a498-5bd1-8c6b-d352c0dda4ad | note | (b) tree and shrub plantation bed areas other than (a) above - 100 mm minimum
060a033e-1069-506d-b330-f0f8c6eca1b2 | note | (c) verges: In areas without kerb and channel or concrete edging strips the depth of topsoil shall vary uniformly from 50 mm deep at the outside edge of verge to 20 mm deep within 100 mm of the edge of seal or asphalt surface treatment
eeb9e545-ddc7-550b-879a-0a7d71312b53 | note | (d) all other areas 75 mm minimum.
547b3de2-c4f0-52d8-9dd8-493c2f0c5d9e | note | ○ Topsoil shall be placed and levelled but not compacted except for verge areas, which shall be compacted. Topsoil on batters shall be placed so as to prevent rilling.
20db40d3-891b-5f72-ae13-7e16c02a9404 | note | ○ The surface level of topsoil shall match the finished surface level, or level of back of kerb or concrete edging, as appropriate.
8221af38-23fd-5b0c-9a1e-4d7cc4a0fe7d | note | REFERENCE DOCUMENTS: Cl 204.17
ca711253-2b7b-5294-ba74-ca9bf0deb24e | note | INSPECTION/TEST METHOD: Inspect
6c808852-a60a-5b0c-8d01-e4fb881c5795 | note | RECORD OF CONFORMITY: This ITP Signed
ce209ca4-f3fa-5c10-b40d-6125b9c697ee | note | IP
1a353958-8190-5e5a-86eb-28c6d258b1f0 | note | RESPONSIBILITY: Site Foreman
01f4ca5e-a714-5155-825a-c83e3d22fde3 | date | Date Completed:
| checkpoint | 2.4 - Tree Clearing
4928b21a-f52e-55b8-909b-e53552b7ef5a | note | FREQUENCY: As Required
06123a12-3e83-5f77-9eb3-fc872a3c2141 | note | ACCEPTANCE CRITERIA: The Contractor shall seek the Superintendent's approval prior to the removal of any tree. An inspection of the tree by the Superintendent or the Superintendent's environmental representative, along with the City of Ballarat is required.
fbf8a8c5-b3f0-51fd-ad3c-ede12e732985 | note | REFERENCE DOCUMENTS: Cl 200.1
358d0191-b723-55cf-a017-297db1e93f55 | note | INSPECTION/TEST METHOD: Verify
7da8a0d5-9f5f-5229-81d1-1c27f92be081 | note | RECORD OF CONFORMITY: This ITP Signed
d2dc2762-4575-54c2-b884-d1e654f7239c | note | HP*
c2449335-59a5-54d9-8ff9-0c2acdf482d9 | note | RESPONSIBILITY: Site Foreman / Site Engineer
abd46961-8cef-596e-b11a-c289ebf16558 | date | Date Completed:
| checkpoint | 2.5 - Hard infrastructure preparation
19a3f1f2-0623-5350-ab79-7ee7dbda0699 | note | FREQUENCY: Each Lot
1b699a52-3e7d-51e9-ba51-5236d794c657 | note | ACCEPTANCE CRITERIA: Footings excavation – Site excavation shall be excavation within the limits. The Contractor shall conduct its operations such that the area outside the limits of the excavation is not unduly disturbed. The Contractor shall not commence placing any fill on the prepared areas until the area has been reviewed by the Superintendent.
c7b99acf-624e-5ad1-93fe-1fcb7298913a | note | ○ Reinforcement for pavement/footing – All steel reinforcement shall be securely held during placing and compacting of the concrete.
6a47f16b-66da-577e-b092-32ed378293ad | note | REFERENCE DOCUMENTS: Cl 204.06 (d), Cl 204.10 (b), CL610.26 (a)
c836c437-f859-5fdd-b48c-305bf7959dce | note | INSPECTION/TEST METHOD: Site Inspection
3b59db02-6426-5450-ac25-3caf57d11cd5 | note | RECORD OF CONFORMITY: This ITP Signed
113756c1-79bf-52f2-a82f-061ed08891c2 | note | HP
10adf792-8464-537f-bb30-ba6fc0cbb423 | note | RESPONSIBILITY: Superintendent/ Site Engineer
3b5a8ef2-0d5c-5af7-8af8-0cfd11a7c6fe | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.5 - Soil Preparation
9950f557-69b0-51e3-becf-fca1530e591d | note | FREQUENCY: Each Lot
29fae3dc-1c8a-5625-80e7-8cfdc069405b | note | ACCEPTANCE CRITERIA: All the necessary soil/garden bed preparation shall be approved by the superintendent prior to planting.
8104f213-4dab-5ad5-ad34-744025e86d7b | note | ○ The planting soil should be prepared in accordance with the Tree Planting Detail and the landscape specification plan.
01b6b563-19eb-5df3-9027-8c99245c6799 | note | REFERENCE DOCUMENTS: Cl 720.10
ce8e4880-ad3c-5ca4-93d3-6584dc2fdee4 | note | INSPECTION/TEST METHOD: Site Inspection
e8bc2f41-9ca9-5be1-94ae-0a2aba641d4e | note | RECORD OF CONFORMITY: ITP Signed
355b7f78-a466-5247-8cef-084a20bba370 | note | HP
969c2248-d67d-56c7-a646-04d1cec704de | note | RESPONSIBILITY: Superintendent/ Site Engineer
efbea589-3d34-5c12-b710-ae26bd9ea448 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.6 - Plant Stock
fa9aa5ed-f582-52e6-92f4-f802d0d9d49e | note | FREQUENCY: Each Lot
b4884a99-e229-5fce-bd4c-9bf38617f970 | note | ACCEPTANCE CRITERIA: All of the trees and garden bed plants shall be inspected and approved by the council representative prior to plantation.At the nursery ensure that individual trees and batches are clearly labelled with the species name and cultivar / variety / provenance where appropriate
333dfd0d-07a2-53e9-993c-78be1d5e940b | note | ○ Hardwood stakes, as per details are to be installed immediately after planting.
ef6bfea9-9908-5498-8ac5-ed9b65dc5862 | note | ○ Stakes are to be driven 600mm into the ground or deep enough to ensure that the stake will remain stable and vertical.
b380fbab-837a-5cd5-887f-e6f5aae3fd1a | note | REFERENCE DOCUMENTS: Cl 720.04
aed963de-ddf5-59eb-827d-c54e8056d270 | note | INSPECTION/TEST METHOD: Visual inspection
e915131d-5781-5f7b-861b-28b0ddc7da89 | note | RECORD OF CONFORMITY: ITP Signed
48affc86-e5ad-5651-94b0-4fe2fef43aad | note | HP
dc013be9-b13f-57cf-8d30-3da571c47cb3 | note | RESPONSIBILITY: Superintendent/ Site Engineer
3f35751c-3eb3-5999-91e5-f617cf662119 | date | Date Completed:
| signoff | Request Signature
| checkpoint | 2.7 - Mulching
c685619c-02c0-509d-89ae-d69a37cea500 | note | FREQUENCY: Each Lot
9545f06e-5393-5eaa-b81f-e1ff8fbd9e14 | note | ACCEPTANCE CRITERIA: After topsoil placement and planting-out of the plant material in all garden beds, supply and spread mulch to an average compacted depth of 75mm. The mulch shall be free from soil clods, rocks and all other non-organic matter.
62ea13e3-f13d-5a1a-b30e-5a6feef94cc0 | note | REFERENCE DOCUMENTS: Cl 720.08
617930ab-c087-5e2a-b0b7-e30e62a66abc | note | INSPECTION/TEST METHOD: Visual inspection
79f61a40-4ab0-543f-b1a2-56e538397839 | note | RECORD OF CONFORMITY: ITP Signed
488b711d-f9f1-5099-b8d8-389e29a57eb9 | note | HP
57ea74de-83f1-5d52-b283-6e2d84c5773e | note | RESPONSIBILITY: Superintendent/ Site Engineer
8fcd0ea5-df27-5718-bad8-4aa63bd13409 | date | Date Completed:
| signoff | Request Signature
| section | 3 - Completion
| checkpoint | 3.1 - Practical Completion
455fc6b2-0a2f-5525-b8eb-52cf040e45e1 | note | FREQUENCY: Completion of each lot
d940fa18-eb51-5093-8b15-6c701ad80dc7 | note | ACCEPTANCE CRITERIA: Survey to ensure and validate that all works meet level and location requirements. Review of existing survey control marks and any additional control marks providing verification of conformity of as constructed features with design. As built survey recorded to confirm installation within tolerances in the latest IFC drawings.
9276ec14-b6de-5774-9ad5-6beb901e88a4 | note | REFERENCE DOCUMENTS: IFC Drawings / survey records
c30a0538-7ba9-5ce0-98aa-dc5da9678962 | note | INSPECTION/TEST METHOD: Document review
04e6e266-4384-5adc-b2fa-c18c948d0db6 | note | RECORD OF CONFORMITY: As-built survey records
9d574c93-4218-5ad3-881a-8cfdd8a964ed | note | SCP
ef036773-5049-5d2f-a663-e5e21cc324fb | note | RESPONSIBILITY: Project Engineer/ Surveyor
77ea5aaa-596a-526e-be7f-642b42e5361d | date | Date Completed:
| checkpoint | Final Inspection
ed7e3a14-7f12-57ed-9100-1de552e115ae | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
4b99d737-c801-5a33-8054-e09eb424a13c | textbox | Print Name:
fcc554ae-b5d1-515f-8f97-89c718f68707 | textbox | Position:
6b0642af-5b54-55bf-8fd2-3a5175c336ef | date | Date:
| checklist | ITP-009 - Spray Seal | itp | ITP-009 - Spray Seal |  | 91c91482-029d-404c-a235-044dd324036f
| section | 1 - Materials
| checkpoint | 1.1 - Bitumen
2baf5ad7-7f96-5a80-b019-f3aeebaa3a2d | note | FREQUENCY: Test cert upon request
7c8daaed-ee20-5bc7-9aeb-f4e746cabe3f | note | ACCEPTANCE CRITERIA: AS (Section 175) for residual bitumen for pavements
997c7d1f-d95f-5779-a042-5cebfa89b512 | note | REFERENCE DOCUMENTS: 408.08 (a)
91d3a3c6-50ef-5039-a4d8-b12e55525663 | note | INSPECTION/TEST METHOD: Verify
cfd17f89-336e-54d8-bcec-ca2b14cf14c2 | note | RECORD OF CONFORMITY: ITP Signed Off
64eaea1b-7bca-5dc3-87bc-39e7b1cc696b | note | IP
a8b61a54-c40b-56af-8a0c-c2eb0e16f79b | note | RESPONSIBILITY: Lab Manager
4518c909-71d8-5e4f-843d-2ff040740661 | date | Date Completed:
| checkpoint | 1.2 - Bitumen Emulsion
b0f756c5-293b-59ae-a45b-4fa5ad2270c5 | note | FREQUENCY: Test cert upon request
87c3189d-ccc3-5c19-af6c-1576e839b9ac | note | ACCEPTANCE CRITERIA: ARS or CRS comply with AS (Section 175) – Bitumen emulsions for the construction and maintenance of pavements
5390d161-e67b-5f8a-97b7-6959517024cd | note | REFERENCE DOCUMENTS: 408.08 (b)
c25f24b2-6d79-5895-bb1a-1b1395a2f14d | note | INSPECTION/TEST METHOD: Verify
fbb28087-886a-529a-a2a6-73ab53c91d66 | note | RECORD OF CONFORMITY: This ITP Sign off
8619bd63-1770-5cfe-bfa3-a798f554c39e | note | IP
d7422804-a765-5dcd-b1cf-f79d1893d08c | note | RESPONSIBILITY: Lab Manager
527c300a-6d31-5061-885d-0b325f4191f0 | date | Date Completed:
| checkpoint | 1.3 - PMB
00b1cca7-1d97-52a8-a6f0-cb267933d76c | note | FREQUENCY: Test cert upon request
9345a588-0076-59d1-9117-1d13007b4da7 | note | ACCEPTANCE CRITERIA: Austroads Specification Framework for Polymer Modified Binders and Multigrade Bitumen’s (AGPT/T190 - section 175) & table 408.161. Alternative PMB'S shall not be used without approval by Superintendent. Evidence of satisfactory field performance for 3 years required.
9515f41c-0a0d-5e9f-a42c-6dea014e64f0 | note | ○ (i) HSS - S10e,S35e,10Pts CR, or alternative approved by superintendent
7d546c70-3adf-52bf-ae2e-1b9ef3dd98e6 | note | ○ Field Produced CR - >5pts by mass of binder, Carrier oil <4Pts by volume of binder
d278bda1-16fa-534a-9f3f-3bbc85c5451c | note | ○ (ii) SAM - S45R,S20e,18Pts CR or alternative as approved by the superintendent
02ab93dd-1dac-5c2f-bbb8-ede024a23fa1 | note | ○ Field Produced CR - >18pts by mass of binder, Carrier oil <4Pts by volume of binder
86732d7b-53f2-5230-bc63-be11fe84566c | note | ○ (iii)SAMI - S25e,20PtsCR or alternative as approved by the superintendent
b7f25356-00e4-5478-a5de-cb85aa0375f0 | note | ○ Field Produced CR - >20pts by mass of binder, Carrier oil <4Pts by volume of binder
16e66046-11e3-5563-8dcc-32dd85ba0013 | note | ○ XSS treatments – Class S20E,S45R or S15RF or alternative as approved by the Superintendent.
7bd5af52-9be0-567d-a8dd-75100d108b95 | note | ○ XSS treatments are applied as a double/double application and the same binder shall be used for both applications.
156d81e9-f6ce-5581-90f4-410b8ad804e3 | note | REFERENCE DOCUMENTS: 408.08 (d)
d8362c4d-290a-513f-95f5-dd1ec88f72f7 | note | INSPECTION/TEST METHOD: Verify
029d7bbc-2aeb-5fc5-9ca5-a0e201cdf4f4 | note | RECORD OF CONFORMITY: ITP Signed Off
b837aa59-dc3d-56b4-a300-7db194556a4a | note | IP
88d6e71d-1cec-5337-aed2-784f4c74fc3a | note | RESPONSIBILITY: Lab Manager
40b7b9a3-00dd-5fca-92d2-75a307ded127 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 1.4 - Primer
fe770184-4b75-5edc-82ed-2e2058e41c19 | note | FREQUENCY: Test cert upon request
e615679b-bc1a-5a42-ba56-9d28ad2bc8c9 | note | ACCEPTANCE CRITERIA: Cutback bitumen only. NB: bitumen emulsion alternative acceptable upon providing evidence of its characteristics.
30d46a82-7d6a-5b1a-b47a-941fca931aca | note | REFERENCE DOCUMENTS: 408.08 (e)
dc00052e-5f5e-54b1-8e74-4ccbd28dd82a | note | INSPECTION/TEST METHOD: Verify
7e448935-cae5-550e-ac1f-96a0dde59f90 | note | RECORD OF CONFORMITY: ITP Signed Off
158436ae-9e60-5d15-8007-ab1211302024 | note | IP
9d88f36d-8f38-502c-8601-bd21857e05bd | note | RESPONSIBILITY: Lab Manager
bd68859a-a97e-5673-915d-508fe714eb32 | date | Date Completed:
| section | 2 - Aggregate
| checkpoint | 2.1 - Aggregate Specification
3ee40ab2-84c8-5038-b950-627143af7ec0 | note | FREQUENCY: Maximum lot size 350t of same class and size
57a627f8-b636-59c6-9c0a-5e81b55d53aa | note | ACCEPTANCE CRITERIA: VicRoads Standard Specification Sections:
5f8e4cc5-92c0-503a-b947-b1502c30becb | note | ○ 801 - Source Rock, 831 - Aggregate & 832 - Sands
37a7ffd5-5763-54b4-9872-fea1516e4729 | note | REFERENCE DOCUMENTS: 408.11 (a)
78e63798-23f8-57c2-ae12-a82ba3e6edd1 | note | INSPECTION/TEST METHOD: Verify
4e483eec-1891-5d92-a4a0-c5bee519f81d | note | RECORD OF CONFORMITY: ITP Signed Off
784dda9c-53f2-5835-8552-74db4b88634c | note | HP*
cc062d12-11a8-52a8-9db4-dc8b911a7a71 | note | RESPONSIBILITY: Lab Manager
8c978cdb-e5cf-54a0-a466-c8bfdfec5203 | date | Date Completed:
| checkpoint | 2.2 - Precoating
52f05830-f929-58fd-a4de-be00a2dd2e96 | note | FREQUENCY: All works carried out
70846e59-4172-58bb-af72-e3f6f4160580 | note | ACCEPTANCE CRITERIA: Supply plant precoated aggregate from supplier or field precoated aggregate from stacksite.
617eb4b8-3d6b-562e-b840-5cd59b5aac2c | note | ○ Aggregate shall be uniformly precoated to the satisfaction of the Superintendent.
281aa45b-12d5-5b20-b1ba-ea3f47ca906d | note | REFERENCE DOCUMENTS: 408.11 (b)
9fb0c050-cbdf-5eed-83c3-3c0bf4b13a39 | note | INSPECTION/TEST METHOD: Verify
fb471281-7dbb-5681-b005-653e1d722dff | note | RECORD OF CONFORMITY: ITP Signed Off
ff821126-a5fb-5fb5-818e-488e28c27f09 | note | IP
7a4ccb39-b389-5332-9811-cf6335db0f20 | note | RESPONSIBILITY: Supervisor
f1df5927-5306-5893-93bb-f56598b06fed | date | Date Completed:
| checkpoint | 2.3 - Removal of loose aggregate
18fc5b61-f829-5feb-84ef-61c7fd5146c1 | note | FREQUENCY: All works carried out
b118ed78-7bc7-553d-b0ea-6b1910f1abff | note | ACCEPTANCE CRITERIA: All areas – within 8 hours of sealing unless otherwise agreed with the Superintendent.
5823ec35-3c04-5e7d-9103-a0b152849891 | note | ○ NB: For seal of nominal size ≤ 7mm, < 60 loose stones/m2 to remain after.
10d5b921-0793-5fff-9efc-67e9e0c12d96 | note | REFERENCE DOCUMENTS: 408.14
393cf1ba-1b49-5ec3-8aed-c5be30a7bfe9 | note | INSPECTION/TEST METHOD: Verify
8ca87e1c-78d5-5108-95ff-7c28d44e1383 | note | RECORD OF CONFORMITY: ITP Signed Off
60354146-6083-5710-b499-268bd56cd5cf | note | IP
879b4e61-c885-5636-b90c-4b7c05f235af | note | RESPONSIBILITY: Supervisor
b0f83f32-2d59-526f-9cba-9881e5b8925c | date | Date Completed:
| checkpoint | 2.4 - Stack Site
5f7a6b3b-025a-5afe-92e8-2e0964a36d74 | note | FREQUENCY: Prior to commencing works
d1e23bd8-6d0d-58b3-ad4f-97b2fc1a2239 | note | ACCEPTANCE CRITERIA: Stack sites to be approved by Superintendent.
70791440-3eb8-5b3e-8075-140d11f34c8e | note | ○ Stack site to be at Kent Street where road is closed.
18289065-1e0e-5dcc-b603-c3ee1aaf8a94 | note | REFERENCE DOCUMENTS: 408.12
090158b2-c2b5-5582-a56c-b4ad10b94c7a | note | INSPECTION/TEST METHOD: Verify
211bbf3e-d177-5a28-9c3d-9f1fef1ff441 | note | RECORD OF CONFORMITY: ITP Signed Off
66b1c519-622d-5abf-9197-4b79d11aad25 | note | IP
87a0a230-de2c-5616-b451-fea4476343d9 | note | RESPONSIBILITY: Supervisor
6707e4f5-074c-5229-9488-3ac4374acbbe | date | Date Completed:
| section | 3 - Operation
| checkpoint | 3.1 - Rates of Application
5aace6d5-9824-51ec-9e52-030fcfc3e8fb | note | FREQUENCY: All works carried out
74060970-0583-5e06-818e-26d43649d7e1 | note | ACCEPTANCE CRITERIA: In accordance with the current Update of the Austroads Sprayed Seal Design Method (Section 175) rates of application - residual binder at 15 C
c2ca201d-44b7-59c3-bc8b-76ecb1afca76 | note | ○ Traffic Data and default rates -Table 3040.066 (Traffic Volumes)
b16a36a7-9e86-5c42-8d96-be709392fb81 | note | ○ 1 week prior, design rates of application, aggregate and rates for pre-treatment to be reviewed by Superintendent.
dff81e29-b1c4-5e04-9e6a-6f5d2091a152 | note | REFERENCE DOCUMENTS: 408.15 (a)
14528c34-da29-5010-97da-7ded23fabe2e | note | INSPECTION/TEST METHOD: Verify
c73d66cd-f0c9-5d04-b677-3f575d4e45f8 | note | RECORD OF CONFORMITY: ITP Signed Off
638d7426-efe9-58a7-8911-196c355c824e | note | HP
ba8c21be-b0ce-5454-9feb-8cf34a4e9897 | note | RESPONSIBILITY: Site/Project Engineer
e5220634-146c-5b88-9a80-b063fb83b2f0 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.2 - Surface Pre-treatment
6c9663b1-8719-59f1-9217-b10bbac0df57 | note | FREQUENCY: All works carried out
50ab4555-8217-5ed0-a45c-95380db61cfc | note | ACCEPTANCE CRITERIA: Refer Table 408.171, 408.132, 408.133
d37c3c6a-ff36-543c-9f5a-61b533abb5cd | note | REFERENCE DOCUMENTS: 408.13 (b)
263352ff-2372-59c0-9a85-ebd566d515b9 | note | INSPECTION/TEST METHOD: Verify
f08c214f-e2f8-519f-ad1b-b252aa6822f7 | note | RECORD OF CONFORMITY: ITP Signed Off
aad2d349-a3c8-5f47-be90-51a6e0bd5f6b | note | IP
fbf6cf1f-1287-5742-95db-fb017382e307 | note | RESPONSIBILITY: Supervisor
2501838a-5830-59af-a2ab-b82035e2fa81 | date | Date Completed:
| checkpoint | 3.3 - Calibration of Bitumen Sprayer
de42ce20-aad4-5450-8ec0-d201ac858411 | note | FREQUENCY: Prior to commencing works
bf449623-de35-5ed5-b2f0-1ae6689c08e8 | note | ACCEPTANCE CRITERIA: Calibration Certificate to be provided
e935d876-76ca-58ab-8f95-dae5e387b4b9 | note | REFERENCE DOCUMENTS: 408.07
0e5de3e1-b0ee-5559-866e-76783c49d130 | note | INSPECTION/TEST METHOD: Verify
d5b2b4e3-6a5a-5261-bbee-7b84191ab0b8 | note | RECORD OF CONFORMITY: ITP Signed Off
21159337-34e3-5052-b2ab-6feb656caeae | note | WP
404d30c3-d056-5823-9019-e14ab2faae27 | note | RESPONSIBILITY: Supervisor
6ea7cce9-54fc-5c28-9fef-9116eeadd434 | date | Date Completed:
| checkpoint | 3.4 - Commencement of works
ef061480-eaf3-5216-a8fc-ae3bbb9307c5 | note | FREQUENCY: Prior to commencing works
ba8da236-26b1-54a2-aa93-4e6eeeeccd96 | note | ACCEPTANCE CRITERIA: NB: Works shall not commence until the Contractor & Superintendent of works agree that the prepared surface is ready & fit for sealing. This includes a review of the material and evidence that the pavement passes compaction testing to Superintendents approval.
08c9a186-e366-5981-a3e8-a871f175caaf | note | ○ Primersealing shall not be carried out within 12 hours of forecast rain.
7792f5e7-4abd-55b0-8cff-a1998769f7e1 | note | REFERENCE DOCUMENTS: 408.04
c24592df-aae1-53c1-8fda-261773dd287c | note | INSPECTION/TEST METHOD: Verify
7be75b45-8ae0-591d-bdb9-de82c4ed8ae1 | note | RECORD OF CONFORMITY: ITP Signed Off, QD2190370 Sealing Checklist
628457b0-641c-524f-9e79-1f983058ed57 | note | HP
569dcd04-8487-54e2-9bf5-8f119c3706e1 | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor / Superintendent
ae88f82a-dbf4-5218-a7e6-bf73dd6af186 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.5 - Records
e3947d84-b1e8-5ec6-9108-be775714acca | note | FREQUENCY: Each Lot
f5439c0e-097a-5405-b40e-91c61d1d24f0 | note | ACCEPTANCE CRITERIA: Job completed within spec requirements.
c9050b98-12dc-5a8a-a134-ae55aa38229b | note | ○ Job completion report ,i.e. Spray Sheets to be submitted within 7 days of completion of sealing works
d5f456e4-418b-5688-a5a5-662aba12f2ec | note | REFERENCE DOCUMENTS: 408.17
a74c7066-5685-59aa-8877-055d1b3918b2 | note | INSPECTION/TEST METHOD: Verify
db973290-715b-5628-96af-6c94342a8c75 | note | RECORD OF CONFORMITY: ITP Signed Off, Spray Sheets, Section 408 Attachment A
c166aab7-dbe8-5d20-af76-8021a0eb8887 | note | WP
f7b41dce-434e-5668-bfa6-d78e64b6db19 | note | RESPONSIBILITY: Site/Project Engineer
ee297a7f-4fa8-5071-8640-0570b4ae4ebb | date | Date Completed:
| checkpoint | 3.6 - Acceptance of work- Binder rates
33a7e502-438b-5c06-a81d-ded63d829ceb | note | FREQUENCY: Each Lot
b471c799-4e8e-5434-9eba-6cc62c5b3d02 | note | ACCEPTANCE CRITERIA: Actual vs design rates. Variation between actual & design assessed by Table 408.121
e7f44aa3-688b-5716-948e-702aad70526d | note | ○ ie. Variation from the Design Rates of Application for Bituminous Material < 0.1 l/m² below the design rate of application
e011be00-0a88-5824-b2e7-1977a88f90df | note | REFERENCE DOCUMENTS: 408.15 (a)
93ab9906-1a0f-53ce-9825-8cc9edd3cb4a | note | INSPECTION/TEST METHOD: Verify
f3c9d980-cf2c-55e3-bc60-eba0e373abaa | note | RECORD OF CONFORMITY: ITP Signed Off
4ac293a7-6ec2-5733-a871-3d087bd8f4bf | note | IP
5ac66cf9-9aaf-5bcf-862e-e0412240797f | note | RESPONSIBILITY: Site/Project Engineer
7b01bd6e-cc5f-5f28-b377-4a8995d4a29e | date | Date Completed:
| checkpoint | 3.7 - Acceptance of work- Surface Texture
0f5bf1ba-7af6-5990-add5-2dfcd78633e0 | note | FREQUENCY: Each Lot
6660b5d6-2d5a-5013-89fe-83fecfbfcc0c | note | ACCEPTANCE CRITERIA: Acceptance - visual assessment or (where required) as per Table 408.122
f1efa418-c5cd-57ad-8052-2eeb81854e42 | note | ○ ie. 7mm Primerseal Mean Texture Depth between 1.0mm to 2.0mm
8d34573a-7197-5a62-bd57-9b94d5bced64 | note | REFERENCE DOCUMENTS: 408.15 (b)
d2891115-78ab-5270-a790-737504ffa811 | note | INSPECTION/TEST METHOD: Verify
af096020-5a2b-5f02-9af9-7c5cb8e0a90f | note | RECORD OF CONFORMITY: ITP Signed Off
a5552e44-d616-5cae-a0f6-cb3627a60bbd | note | IP
9911a020-9f04-5987-b67d-0b0e76cebf84 | note | RESPONSIBILITY: Site/Project Engineer
8c39f7b8-fd95-5435-910c-4dd2fccebc9b | date | Date Completed:
| checkpoint | 3.8 - Acceptance of work- Aggregate retention
4d4be63b-e88c-5bc4-919e-6c5085d8ddb8 | note | FREQUENCY: Each Lot
43edd592-d7b3-56dd-a086-cd9e5711526a | note | ACCEPTANCE CRITERIA: Acceptance -visual assessment or (where required) as per Table 408.123
605fa81a-d00b-5c77-85c8-c620745c0a6e | note | ○ Degree of Aggregate Stripping is 0 - 2
3a9a740c-1667-501a-a42b-0d21eea99eee | note | REFERENCE DOCUMENTS: 408.15 (c)
2e5218c2-f015-51f1-976b-6c4aae2abcc1 | note | INSPECTION/TEST METHOD: Verify
1bd9fcc9-ac64-5d46-91ae-24a5dc8d9323 | note | RECORD OF CONFORMITY: ITP Signed Off
e196a090-f736-5d6c-b72f-693415136bb4 | note | IP
226e9538-b98a-5356-81fc-53c273da2a98 | note | RESPONSIBILITY: Site/Project Engineer
79b8448e-4a8d-58d8-a0bb-36f249654795 | date | Date Completed:
| checkpoint | 3.9 - Acceptance of work- Visual Uniformity
276a2248-2592-5444-9b9e-3aece637bcc0 | note | FREQUENCY: Each Lot
f27c0806-703b-5584-b8d9-b1e58cc86b1b | note | ACCEPTANCE CRITERIA: Provide a surface with uniform colour, texture and consistent appearance
f5a96efd-b331-5b9f-a94e-1f64ae9e4fd2 | note | REFERENCE DOCUMENTS: 408.15 (d)
7db512a6-9a8f-5dee-9da2-7e5a46772457 | note | INSPECTION/TEST METHOD: Verify
d117c444-f7e1-585a-88f0-be5316918e66 | note | RECORD OF CONFORMITY: ITP Signed Off
8b88e472-4423-5a07-9600-b9e4719886a5 | note | IP
e16840ac-70b3-5d6a-8154-154cd3cbf875 | note | RESPONSIBILITY: Site/Project Engineer
dee8cdd5-086d-54ed-8e51-9ca2c5a247de | date | Date Completed:
| checkpoint | 3.10 - Maintenance of seals
c42973a6-a900-5c3b-885c-5320446ff2de | note | FREQUENCY: All works carried out
cc01006a-feeb-565f-896f-90b2b5244f97 | note | ACCEPTANCE CRITERIA: The contractor shall be responsible for the monitoring and maintenance of seals from the time of application until the end of the defects liability period.
400850ca-6e5e-5154-87fe-d52c1eba2b6d | note | ○ The Contractor shall advise the Superintendent in writing of the proposed treatment to effect the above work before undertaking the work.
d728aedb-445f-5cf7-ae83-ac4312b8310f | note | REFERENCE DOCUMENTS: 408.16
753ba7ee-fe8d-5fa3-95f6-f6f0c57ed650 | note | INSPECTION/TEST METHOD: Verify
1d3f73fe-a816-53ee-86c2-2b60c500ace4 | note | RECORD OF CONFORMITY: ITP Signed Off
101911dc-c51c-5c8b-b3c3-89235b8353bd | note | HP
6b1415e1-736c-5293-9597-ce7e7d121eda | note | RESPONSIBILITY: Site/Project Engineer, Superintendent
8d56ce0d-1a0b-5d12-959d-5e81af31f007 | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.11 - Maintenance of seals
d6b101cd-d1fa-5150-ba31-a954b2562206 | note | FREQUENCY: All works carried out
800ecca4-a416-5d41-8ba2-767fb8afc240 | note | ACCEPTANCE CRITERIA: Where the treatment for protection or repair of a seal involves the application of a further seal coat, the Contractor shall obtain the agreement of the Superintendent of the proposed treatment before undertaking the work.
da076616-6641-5d1f-a0ed-daca0dae84e2 | note | REFERENCE DOCUMENTS: 408.16
d2020a86-d814-5423-801e-0ff1a47cef62 | note | INSPECTION/TEST METHOD: Verify
5493c509-3b91-5e6e-a18c-9742e02aac51 | note | RECORD OF CONFORMITY: ITP Signed Off
c5b8a64a-7774-5bd1-b142-8d8a6564bc67 | note | HP
8c5572fd-acef-53bf-9ee2-0dee5500c768 | note | RESPONSIBILITY: Site/Project Engineer
44c7dc74-f281-546f-978f-399cb949fc8b | date | Date Completed:
| signoff | Request Signoff
| checkpoint | 3.12 - Defects Liability Period
f653a6b1-4507-5f69-947c-b0e8ee5c342e | note | FREQUENCY: All works carried out
46e7cda7-be81-52f1-b980-5b5903761b6e | note | ACCEPTANCE CRITERIA: All defects should be rectified six months prior to the conclusion of the Defects liability period. As stated in 408.15
fcc06d05-d1b4-5cf0-b234-10933ecbb764 | note | ○ The Contractor shall carry out at least two inspections of each job during the Defects Liability Period and provide a condition report to the Superintendent. The condition report shall detail the condition of the seal, any defects and the proposed corrective action.
ae07d712-6b0d-5c61-915f-9a2806b08bc6 | note | REFERENCE DOCUMENTS: 408.18
eb686aa1-7b6e-548e-8747-16e76e24ecee | note | INSPECTION/TEST METHOD: Verify
a764ceee-adb4-57e8-9428-1ac696bc8ad6 | note | RECORD OF CONFORMITY: ITP Signed off
ef67e13b-bc8a-533e-8b23-3353f065c3a4 | note | WP
3f2213b3-0c80-5f5e-b095-7f56531d4a32 | note | RESPONSIBILITY: Site/Project Engineer
1e022961-01f2-543b-9b02-27db6879f163 | date | Date Completed:
| checkpoint | 3.13 - Dryback
9481e36c-a544-5b4a-b2f0-c0ba129c8293 | note | FREQUENCY: Each Lot
0c88dc37-c7bb-5f2a-8cce-493316b4edfc | note | ACCEPTANCE CRITERIA: Scale B Pavement Dryback and Embedment
c85d3bae-f368-559f-9706-1718bfdb2217 | note | – 6 randomly selected test sites per lot required
30a8ae04-890f-5032-9cd1-2d0482caf466 | note | – If Mean Moisture Ratio is < 60% & Maximum of any result is < 70% then Ball Penetration not required
809f9828-192a-5c48-abbe-8d8e7032c6bc | note | – If Mean Moisture Ratio is < 65% & Maximum of any result is < 70% then Ball Penetration Maximum individual result is 3mm
6485019f-7694-5cf3-93c2-c1acf0672be0 | note | – Testing shall be undertaken no more than 24 hours before primersealing.
3e926735-b204-571a-a4af-7005cd2cb247 | note | – Testing schedule in accordance with 310.03 (c) and QD2190370 Sealing Checklist
43a6db51-7a7a-5b3b-abc0-0c9c72bafbe3 | note | REFERENCE DOCUMENTS: 310.03(a), 310.03(b), Table 310.031, 310.03(c), Table 310.032
0a5d71f5-61f9-5e15-a507-c9e0092a9f94 | note | INSPECTION/TEST METHOD: Verify
44c5f6b7-19fa-59fa-9363-552bc51e2885 | note | RECORD OF CONFORMITY: ITP Signed off
0de6895f-2f50-56ae-89a9-b5094b4d171f | note | TP
c3da66d0-37e4-5179-bb6a-7f59e1510528 | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor
89ec10a0-168d-5ecc-832c-4cf84adcaa79 | date | Date Completed:
| checkpoint | 3.14 - Ride Quality
1ef43aa8-4633-57c9-b568-d86c39d57161 | note | FREQUENCY: Each Lot
fc477829-1c1a-5add-9ae6-ac846f2add06 | note | ACCEPTANCE CRITERIA: Ride quality measurement shall be undertaken within 3 months of the completion of primerseal and prior to practical completion being awarded by the Superintendent.
bee8a5f3-0fea-549a-ad1a-fd87955fa71a | note | ○ The finished surface of the Primersealed pavement shall have a smooth longitudinal profile and comply with the minimum ride qaulity requirements of Scale C road as specified in Table 180.092.
e4bd1caf-b93f-5d6f-a389-3dc775bc3b1b | note | – Maximum Individual Lane Roughness Value for any 100 m Subsection = 2.70 m/km/lane
0ed50a84-73cd-53f9-a721-557797476467 | note | – Maximum Mean Lane Roughness Value for Lot = 2.00 n/km/lane
248a1572-f3c9-5f68-ab07-2f3799ef726f | note | – Maximum length of lot is 2km of continuous traffic lane
273f7f91-1180-5663-b159-381e3219fbdd | note | REFERENCE DOCUMENTS: 180.04, 180.092
f51ac608-0764-5c02-a756-fea9c969c035 | note | INSPECTION/TEST METHOD: Verify
7ba21260-f154-5cb7-9ae2-aad491392dc9 | note | RECORD OF CONFORMITY: ITP Signed off
904a6210-63d3-52c0-801c-3b4d350b3e2c | note | TP
5a2e80c5-9042-5132-ad6e-2110e2a1ab73 | note | RESPONSIBILITY: Site/Project Engineer/ Supervisor
4ee9bea4-c3b4-5424-bb46-15bc1114614b | date | Date Completed:
| checkpoint | Final Inspection
3636344f-6ffc-542a-a1cd-85de97eab330 | note | The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
9daeb411-57b9-5b04-9e48-3fa1a37bf4ca | textbox | Print Name:
122bfc9d-6398-5283-8861-14219bd84edf | textbox | Position:
88badc2c-e585-550b-9759-9670da98dfcf | date | Date: