## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Stage 3 - Library Exterior - South |  |  |  |  | Yes | Stage 3 - Library Exterior - South | 0ca3583b-eec3-450b-826f-21c48ec81c06
checkpoint-status |  |  | checkpoint | Remove Windows
checkpoint-status |  |  | checkpoint | Remove Existing Cladding
checkpoint-status |  |  | checkpoint | New Framing - New Bottom Plate DPC
checkpoint-status |  |  | checkpoint | New RWU - Proclima Self Adhesive
checkpoint-status |  |  | checkpoint | Install H3.2 Timber Plate with DPC
checkpoint-status |  |  | checkpoint | Install 1.2BMT Base flashing - 15Deg Slope
checkpoint-status |  |  | checkpoint | Install Cavity Closer
checkpoint-status |  |  | checkpoint | Install Easylap Cladding
checkpoint-status |  |  | checkpoint | Install Castellated Batten
checkpoint-status |  |  | checkpoint | Install 1.2 Aluminium Soffit Flashing
checkpoint-status |  |  | checkpoint | Paint Cladding
checklist-flat |  |  | checklist | Stage 3 - Tie Beams |  |  |  |  | Yes | Stage 3 - Tie Beams | 1d35558c-85c7-4eb1-87dc-fffa461217cc
checkpoint-status |  |  | checkpoint | 45x6 EA Tie Beam
checklist-flat |  |  | checklist | Block N & K South Elevation Infills |  |  |  |  | Yes | Block N & K South Elevation Infills | 2333b45b-a2b9-409f-9d5e-6619222f71e9
checkpoint-status |  |  | checkpoint | Remove Asbestos
checklist-flat |  |  | checklist | Phase 2 Block N &K - Lower R1 |  |  |  |  | Yes | Phase 2 Block N &K - Lower R1 | 235dc29a-e88e-4c9a-85d2-c76bed1339a6
checkpoint-status |  |  | checkpoint | Delap photos
checkpoint-status |  |  | checkpoint | Remove roofing iron
checkpoint-status |  |  | checkpoint | Remove existing cap flashings
checkpoint-status |  |  | checkpoint | Install new base deck
checkpoint-status |  |  | checkpoint | New 80mm PIR
checkpoint-status |  |  | checkpoint | New Fibretite Membrane
checkpoint-status |  |  | checkpoint | New Fascias
checkpoint-status |  |  | checkpoint | Parapet flashing
checkpoint-status |  |  | checkpoint | Gutters and Down pipes
checklist-flat |  |  | checklist | Weatherboard Replacement |  |  |  |  | Yes | Weatherboard Replacement | 2a993ab6-d284-4b65-8fd1-95bacdfb1e2a
checkpoint-status |  |  | checkpoint | Existing damaged weatherboard
checkpoint-status |  |  | checkpoint | New replacement
checkpoint-status |  |  | checkpoint | Paint
checklist-flat |  |  | checklist | Stage 3 - Duct Bracing |  |  |  |  | Yes | Stage 3 - Duct Bracing | 33a64b48-79c9-4c1b-84b4-78747f6c7408
checkpoint-status |  |  | checkpoint | Solid Blocking (200mm Long)
checkpoint-status |  |  | checkpoint | 4-12g Screws 150mm Long Each Side
checkpoint-status |  |  | checkpoint | Gripple GS19 Braces
checklist-flat |  |  | checklist | nAJ0 - Window |  |  |  |  | Yes | nAJ0 - Window | 3757d6b5-621b-4c4a-856b-9430adeb2cf9
checkpoint-status |  |  | checkpoint | Window removed
checkpoint-status |  |  | checkpoint | New Window Opening
checkpoint-status |  |  | checkpoint | Sill chamered to form Fall
checkpoint-status |  |  | checkpoint | Window Tape
checkpoint-status |  |  | checkpoint | Sill Flashing Installed
checkpoint-status |  |  | checkpoint | Cavity Batten Installed
checkpoint-status |  |  | checkpoint | Window Installed
checkpoint-status |  |  | checkpoint | Head Flashing Installed
checkpoint-status |  |  | checkpoint | Gib and Architraves
checkpoint-status |  |  | checkpoint | Window opener installed
checklist-flat |  |  | checklist | Phase 2 Block N &K - Upper Roof |  |  |  |  | Yes | Phase 2 Block N &K - Upper Roof | 498734f3-fe9d-488d-994a-c2959d9194b5
checkpoint-status |  |  | checkpoint | Delap photos
checkpoint-status |  |  | checkpoint | Clean roof
checkpoint-status |  |  | checkpoint | Remove existing cap flashings
checkpoint-status |  |  | checkpoint | Install screws to substrate
checkpoint-status |  |  | checkpoint | Install Trough Infill PIR
checkpoint-status |  |  | checkpoint | New Vapour Barrier
checkpoint-status |  |  | checkpoint | New 40mm PIR
checkpoint-status |  |  | checkpoint | New Fibretite Membrane
checkpoint-status |  |  | checkpoint | New Fascias
checkpoint-status |  |  | checkpoint | Parapet flashing
checkpoint-status |  |  | checkpoint | Gutters and Down pipes
checklist-flat |  |  | checklist | Stage 3 - Roof |  |  |  |  | Yes | Stage 3 - Roof | 5d98e3fa-7d48-4372-a32f-afc2989359f4
checkpoint-status |  |  | checkpoint | Remove Satellite Dish
checkpoint-status |  |  | checkpoint | Remove Existing Corrugated Iron
checkpoint-status |  |  | checkpoint | Remove Gutters & Down Pipes
checkpoint-status |  |  | checkpoint | Inspect Roof Rafters
checkpoint-status |  |  | checkpoint | Inspect Services
checkpoint-status |  |  | checkpoint | Install Roof Insulation - 25mm gap
checkpoint-status |  |  | checkpoint | Install Blocking between Existing Outriggers
checkpoint-status |  |  | checkpoint | Install Fascia
checkpoint-status |  |  | checkpoint | Paint Fascia
checkpoint-status |  |  | checkpoint | Install Drispace GN2500N Fascia Vent
checkpoint-status |  |  | checkpoint | Install VB20 Venting Batten
checkpoint-status |  |  | checkpoint | Install Eave Flashing
checkpoint-status |  |  | checkpoint | Install Wire netting
checkpoint-status |  |  | checkpoint | DRISTUD FRU38 Roof Underlay
checkpoint-status |  |  | checkpoint | Terminate at Top Batten
checkpoint-status |  |  | checkpoint | Install VB10 Venting Batten
checkpoint-status |  |  | checkpoint | Install Space Eaves Comb Filler G1275
checkpoint-status |  |  | checkpoint | Install Colorcote Magnaflow Roofing (Smokey)
checkpoint-status |  |  | checkpoint | Up Turn Stop Ends
checkpoint-status |  |  | checkpoint | 40mm Between Sheets at Ridge
checkpoint-status |  |  | checkpoint | Install Ridge Vent RV10DT
checkpoint-status |  |  | checkpoint | Install Ridge Flashing - 10mm Gap from Roof
checkpoint-status |  |  | checkpoint | Type 17 14G x 140mm Timbertite Screws
checkpoint-status |  |  | checkpoint | 125mm Box Colorcote Gutter on External Brackets 10mm Gap
checklist-flat |  |  | checklist | Phase 2 Block N &K - Lower Roof |  |  |  |  | Yes | Phase 2 Block N &K - Lower Roof | 5daf359f-3560-40a2-be82-0e4a2d571c98
checkpoint-status |  |  | checkpoint | Delap photos
checkpoint-status |  |  | checkpoint | Clean Roof
checkpoint-status |  |  | checkpoint | Remove existing cap flashings
checkpoint-status |  |  | checkpoint | Remove skylights
checkpoint-status |  |  | checkpoint | Install screws to substrate
checkpoint-status |  |  | checkpoint | Install Trough Infill PIR
checkpoint-status |  |  | checkpoint | New Vapour Barrier
checkpoint-status |  |  | checkpoint | New 40mm PIR
checkpoint-status |  |  | checkpoint | New Fibretite Membrane
checkpoint-status |  |  | checkpoint | New Fascias
checkpoint-status |  |  | checkpoint | Parapet flashing
checkpoint-status |  |  | checkpoint | Gutters and Down pipes
checklist-flat |  |  | checklist | Phase 3 Block N&K |  |  |  |  | Yes | Stage 3 Extension Block K&i | 62412db1-11a1-4761-9a58-c702eb27dd2f
checkpoint-status |  |  | checkpoint | Remove Existing Membrane roof
checkpoint-status |  |  | checkpoint | Delap photos
checkpoint-status |  |  | checkpoint | Clean roof
checkpoint-status |  |  | checkpoint | Remove Existing cap flashing
checkpoint-status |  |  | checkpoint | Install screws to substrate
checkpoint-status |  |  | checkpoint | Install through infill PIR
checkpoint-status |  |  | checkpoint | New Vapour Barrier
checkpoint-status |  |  | checkpoint | New 40mm PIR
checkpoint-status |  |  | checkpoint | New Fibertite Membrane
checkpoint-status |  |  | checkpoint | New Fascias
checkpoint-status |  |  | checkpoint | Frame Parapet
checkpoint-status |  |  | checkpoint | Parapet flashing
checkpoint-status |  |  | checkpoint | Gutters and Down pipies
checklist-flat |  |  | checklist | Phase 2 Block N &K - Cladding |  |  |  |  | Yes | Phase 2 Block N &K - Cladding | 65c58dc3-88c1-4f31-bd03-921be42c7bac
checkpoint-status |  |  | checkpoint | Remove Asbestos
checkpoint-status |  |  | checkpoint | Inspect timber framing
checkpoint-status |  |  | checkpoint | Install Rigid Wall Underlay
checkpoint-status |  |  | checkpoint | Membrane upstand
checkpoint-status |  |  | checkpoint | Install Cavity Battens
checkpoint-status |  |  | checkpoint | Install 9mm Fibre Cement board
checkpoint-status |  |  | checkpoint | Install Trims
checkpoint-status |  |  | checkpoint | Paint
checklist-flat |  |  | checklist | Roof |  |  |  |  | Yes | Stage 4 - Roof | 6d9ce565-415f-4b22-9161-42ac6d8dde10
checkpoint-status |  |  | checkpoint | Remove Roof Iron
checkpoint-status |  |  | checkpoint | Clean and encapsulate asbestos
checkpoint-status |  |  | checkpoint | New 140mm Rafters 600mm ctrs
checkpoint-status |  |  | checkpoint | New 140mm Outriggers
checkpoint-status |  |  | checkpoint | New 90x45 props to end of rafters
checkpoint-status |  |  | checkpoint | New 90x45 Mid span props
checkpoint-status |  |  | checkpoint | Extend wall to support 140mm rafters.
checkpoint-status |  |  | checkpoint | 2/90 x 3.15 skew nails + 2 wire dogs
checkpoint-status |  |  | checkpoint | Insulation
checkpoint-status |  |  | checkpoint | Intello to seal exterior
checkpoint-status |  |  | checkpoint | Roof bracing straps
checkpoint-status |  |  | checkpoint | Additonal purlins
checkpoint-status |  |  | checkpoint | Purlin Fixings Bugle 14 Guage
checkpoint-status |  |  | checkpoint | Fascia installed
checkpoint-status |  |  | checkpoint | Fascia painted - all four sides
checkpoint-status |  |  | checkpoint | 0.9BMT Colorcote Alugard eaves
checkpoint-status |  |  | checkpoint | Wire Netting
checkpoint-status |  |  | checkpoint | Vent Eave Combs Filler - G1275
checkpoint-status |  |  | checkpoint | Magnaflow 0.55 BMT Roofing
checkpoint-status |  |  | checkpoint | Vent Back Flashings
checkpoint-status |  |  | checkpoint | Apron Flashings
checkpoint-status |  |  | checkpoint | 300mm Box Gutter
checkpoint-status |  |  | checkpoint | Downpipes - brackets @800mm Crs
checklist-flat |  |  | checklist | Stage 3 - Library Interior -Careers Room |  |  |  |  | Yes | Stage 3 - Library Interior -Careers Room | 75579881-0cd0-4b00-a2d6-4ebeeaebf602
checkpoint-status |  |  | checkpoint | Remove Windows
checkpoint-status |  |  | checkpoint | Reframe Wall
checkpoint-status |  |  | checkpoint | Install Windows
checkpoint-status |  |  | checkpoint | Airseal Around Windows
checkpoint-status |  |  | checkpoint | Install Insulation
checkpoint-status |  |  | checkpoint | Install Structural Plywood
checkpoint-status |  |  | checkpoint | Install Skirtings
checkpoint-status |  |  | checkpoint | Install Architraves
checkpoint-status |  |  | checkpoint | Install Autex
checklist-flat |  |  | checklist | Stage 3 - Rafter to Ridge |  |  |  |  | Yes | Stage 3 - Rafter to Ridge | 814a5da2-edd7-4597-b873-d3f96d5c6ab1
checkpoint-status |  |  | checkpoint | 100 UC 15 Steel Frame
checkpoint-status |  |  | checkpoint | M16 x2 Bolts
checkpoint-status |  |  | checkpoint | 10mm thick Tee Brackets
checkpoint-status |  |  | checkpoint | 100 x6 EA Between Rafters
checkpoint-status |  |  | checkpoint | Double Timber Blocking up to Ridge
checkpoint-status |  |  | checkpoint | CPC80 Each side of Rafters
checkpoint-status |  |  | checkpoint | 2x Lumberlok Multistraps
checklist-flat |  |  | checklist | Northern Elevation |  |  |  |  | Yes | Northern Elevation | 85d0e381-eb48-4d68-abe7-fd7906f64396
checkpoint-status |  |  | checkpoint | Existing damaged weatherboard
checkpoint-status |  |  | checkpoint | New replacement
checkpoint-status |  |  | checkpoint | Paint
checklist-flat |  |  | checklist | Lower Roof |  |  |  |  | Yes | Lower Roof | 92c0ee06-cdc9-49d3-8ac5-eed59c311950
checkpoint-status |  |  | checkpoint | Delap photos
checkpoint-status |  |  | checkpoint | Clean Roof
checkpoint-status |  |  | checkpoint | Remove existing cap flashings
checkpoint-status |  |  | checkpoint | Install screws to substrate
checkpoint-status |  |  | checkpoint | Install Trough Infill PIR
checkpoint-status |  |  | checkpoint | New Vapour Barrier
checkpoint-status |  |  | checkpoint | New 40mm PIR
checkpoint-status |  |  | checkpoint | New Fibretite Membrane
checkpoint-status |  |  | checkpoint | New Fascias
checkpoint-status |  |  | checkpoint | Parapet flashing
checkpoint-status |  |  | checkpoint | Gutters and Down pipies
checklist-flat |  |  | checklist | Stage 3 - Plywood Brace Walls |  |  |  |  | Yes | Stage 3 - Plywood Brace Walls | 94ab479d-5443-4a58-98e1-75f9c204e79f
checkpoint-status |  |  | checkpoint | New Full Height Studs & Nogs
checkpoint-status |  |  | checkpoint | New Bottom Plate Fixing @ 600 Centres
checkpoint-status |  |  | checkpoint | Install Hold Down Brackets
checkpoint-status |  |  | checkpoint | 12G Timber Screws 125mm Long
checkpoint-status |  |  | checkpoint | M12 Bolts into SHS Post
checkpoint-status |  |  | checkpoint | New 12mm F8 Ply Bracing 125mm FH Nails
checklist-flat |  |  | checklist | Fibretite Roof |  |  |  |  | Yes | Stage 4 - Fibretite Roof | 9a4c08ae-0bf8-417e-b825-ef335c4662e1
checkpoint-status |  |  | checkpoint | Frame membrane roof - 400 centres
checkpoint-status |  |  | checkpoint | 19mm Plywood install
checkpoint-status |  |  | checkpoint | Vapour Barrier
checkpoint-status |  |  | checkpoint | PIR Board
checkpoint-status |  |  | checkpoint | Fibretite Membrane
checkpoint-status |  |  | checkpoint | Membrane Upstands
checkpoint-status |  |  | checkpoint | Diverters
checkpoint-status |  |  | checkpoint | Box gutter
checklist-flat |  |  | checklist | Easylap Cladding |  |  |  |  | Yes | Stage 4 - Easylap Cladding | a6c1c0df-8b50-4929-a035-2bb6425ec553
checkpoint-status |  |  | checkpoint | RAB Board - Adhero Wrap
checkpoint-status |  |  | checkpoint | Cavity Closer
checkpoint-status |  |  | checkpoint | CLD Battens - 400 crs
checkpoint-status |  |  | checkpoint | Easylap panels
checkpoint-status |  |  | checkpoint | Painting Completed
checklist-flat |  |  | checklist | Stage 3 - Library Interior - North, East & West |  |  |  |  | Yes | Stage 3 - Library Interior - North, East & West | b75c676f-e97a-4d72-873d-def549d7ea43
checkpoint-status |  |  | checkpoint | Remove Windows
checkpoint-status |  |  | checkpoint | Reframe Wall
checkpoint-status |  |  | checkpoint | Install Windows
checkpoint-status |  |  | checkpoint | Airseal Around Windows
checkpoint-status |  |  | checkpoint | Install Insulation
checkpoint-status |  |  | checkpoint | Install Structural Plywood
checkpoint-status |  |  | checkpoint | Install Skirtings
checkpoint-status |  |  | checkpoint | Install Architraves
checkpoint-status |  |  | checkpoint | Install Autex
checkpoint-status |  |  | checkpoint | Install Ceiling Flashing Trim
checklist-flat |  |  | checklist | Windows - AJ003 |  |  |  |  | Yes | Stage 4 - Windows - AJ003 | b8f827f6-2511-4a63-949f-28619ee1ade6
checkpoint-status |  |  | checkpoint | Remove Windows
checkpoint-status |  |  | checkpoint | Re frame new opening sizes
checkpoint-status |  |  | checkpoint | 100m SHS
checkpoint-status |  |  | checkpoint | Membrane dressed into sill
checkpoint-status |  |  | checkpoint | Sill Flashing
checkpoint-status |  |  | checkpoint | Flashing Tape
checkpoint-status |  |  | checkpoint | Cavity Batten
checkpoint-status |  |  | checkpoint | Window installed
checkpoint-status |  |  | checkpoint | Window winders
checklist-flat |  |  | checklist | Phase 3 Block M & L - Awning Roof |  |  |  |  | Yes | Phase 3 Block M & L - Awning Roof | bfbf2a7b-4f41-424c-8a4d-6525bba301bb
checkpoint-status |  |  | checkpoint | Remove Existing Clearlite
checkpoint-status |  |  | checkpoint | Install new Fibreglass Roofing
checkpoint-status |  |  | checkpoint | Install closed cell profiled foam strip
checkpoint-status |  |  | checkpoint | Install Apron Flashing
checkpoint-status |  |  | checkpoint | New Gutters and Down Pipes
checklist-flat |  |  | checklist | Weatherboard Cladding |  |  |  |  | Yes | Stage 4 - Weatherboard Cladding | c402e027-31d9-45ba-bdd2-d21e5b53eb3c
checkpoint-status |  |  | checkpoint | Apron Flashing Installed
checkpoint-status |  |  | checkpoint | RAB Board - Adhero Wrap
checkpoint-status |  |  | checkpoint | Cavity closer
checkpoint-status |  |  | checkpoint | Cavity Battens - 400mm Crs
checkpoint-status |  |  | checkpoint | Weatherboard Installed
checkpoint-status |  |  | checkpoint | Painting completed
checklist-flat |  |  | checklist | Stage 3 - Library Exterior - North |  |  |  |  | Yes | Stage 3 - Library Exterior - North | ce716b90-d0f1-4aec-b224-7a7adbee34f0
checkpoint-status |  |  | checkpoint | Remove Asbestos Soffits
checkpoint-status |  |  | checkpoint | Remove Existing Windows
checkpoint-status |  |  | checkpoint | Check Windows Openings Sizes
checkpoint-status |  |  | checkpoint | Install Jamb Battens
checkpoint-status |  |  | checkpoint | Install New Flashing Tape - 50mm lap onto Building Paper
checkpoint-status |  |  | checkpoint | Install New Weatherboard Below Windows
checkpoint-status |  |  | checkpoint | 0.9BMT Powder Coated Aluminium Sill Flashing
checkpoint-status |  |  | checkpoint | Install New Wall Underlay
checkpoint-status |  |  | checkpoint | Install New Weatherboards
checkpoint-status |  |  | checkpoint | Install New Windows
checkpoint-status |  |  | checkpoint | Install Fascia Between Windows
checkpoint-status |  |  | checkpoint | Install Scribers
checkpoint-status |  |  | checkpoint | Install H3.2 Soffit Blocking
checkpoint-status |  |  | checkpoint | Install Soffit Flashing
checkpoint-status |  |  | checkpoint | Install Villaboard Soffit
checkpoint-status |  |  | checkpoint | Paint Weatherboards
checkpoint-status |  |  | checkpoint | Paint Soffits
checklist-flat |  |  | checklist | Upper Roof |  |  |  |  | Yes | Upper Roof | d7fd38ac-84de-49f8-a504-899785a60c24
checkpoint-status |  |  | checkpoint | Delap photos
checkpoint-status |  |  | checkpoint | Clean roof
checkpoint-status |  |  | checkpoint | Remove existing cap flashings
checkpoint-status |  |  | checkpoint | Install screws to substrate
checkpoint-status |  |  | checkpoint | Install Trough Infill PIR
checkpoint-status |  |  | checkpoint | New Vapour Barrier
checkpoint-status |  |  | checkpoint | New 40mm PIR
checkpoint-status |  |  | checkpoint | New Fibretite Membrane
checkpoint-status |  |  | checkpoint | New Fascias
checkpoint-status |  |  | checkpoint | Parapet flashing
checkpoint-status |  |  | checkpoint | Gutters and Down pipies
checklist-flat |  |  | checklist | Stage 3 - Top Plate Fixing |  |  |  |  | Yes | Stage 3 - Top Plate Fixing | d8cb3fab-ea9a-46b4-9fc8-59a29718db27
checkpoint-status |  |  | checkpoint | 80x6 G300 Plate
checklist-flat |  |  | checklist | Fume Cupboards |  |  |  |  | Yes | Fume Cupboards | e57604b6-ac20-4bfe-a6f7-37f01d496099
checkpoint-status |  |  | checkpoint | Commissioned Results
checkpoint-status |  |  | checkpoint | Remove existing Fume Vents
checkpoint-status |  |  | checkpoint | Install Ply upstand
checkpoint-status |  |  | checkpoint | Membrane and Cricket
checkpoint-status |  |  | checkpoint | Install Fume Vent
checkpoint-status |  |  | checkpoint | Welded Aluminium Cap flashing
checkpoint-status |  |  | checkpoint | Boot Flashing and drive clamp
checkpoint-status |  |  | checkpoint | Recomissioned results
checklist-flat |  |  | checklist | Windows - AJ004 & AJ005 |  |  |  |  | Yes | Stage 4 - Windows - AJ004 & AJ005 | e8bf74b7-9778-4990-b4db-18e28fe72299
checkpoint-status |  |  | checkpoint | Remove Windows
checkpoint-status |  |  | checkpoint | Re frame new opening sizes
checkpoint-status |  |  | checkpoint | Membrane dressed onto sill
checkpoint-status |  |  | checkpoint | Sill Flashing
checkpoint-status |  |  | checkpoint | Flashing Tape
checkpoint-status |  |  | checkpoint | Cavity Batten
checkpoint-status |  |  | checkpoint | Window installed
checkpoint-status |  |  | checkpoint | Window winders
checklist-flat |  |  | checklist | Block N East Elevation 2 |  |  |  |  | Yes | Block N East Elevation 2 | ef36feec-5525-4402-8923-5cae67d90a63
checkpoint-status |  |  | checkpoint | Remove Asbestos
checkpoint-status |  |  | checkpoint | Inspect timber framing
checkpoint-status |  |  | checkpoint | Install Rigid Wall Underlay
checkpoint-status |  |  | checkpoint | Install Cavity Battens
checkpoint-status |  |  | checkpoint | Install 9mm Fibre Cement board
checkpoint-status |  |  | checkpoint | Install Trims
checkpoint-status |  |  | checkpoint | Paint
checklist-flat |  |  | checklist | Block N & K South Elevation Infills - Stage 2 |  |  |  |  | Yes | Block N & K South Elevation Infills - Stage 2 | f0b39514-69d6-41dd-8690-fab840721dca
checkpoint-status |  |  | checkpoint | Remove asbestos panels
checkpoint-status |  |  | checkpoint | Inspect Timber Framing
checkpoint-status |  |  | checkpoint | Install Rigid Wall Underlay
checkpoint-status |  |  | checkpoint | Install Flashing tape
checkpoint-status |  |  | checkpoint | Install Cavity Battens
checkpoint-status |  |  | checkpoint | Install Cavbat Battens
checkpoint-status |  |  | checkpoint | Install Powder Coated Aluminium Flashing
checklist-flat |  |  | checklist | Phase 3 Block M & L - Upper Roof |  |  |  |  | Yes | Phase 3 Block M & L - Upper Roof | f1fcb9b7-f9ec-48e5-b99b-13a513b7af5f
checkpoint-status |  |  | checkpoint | Delap photos
checkpoint-status |  |  | checkpoint | Clean roof
checkpoint-status |  |  | checkpoint | Remove existing cap flashings
checkpoint-status |  |  | checkpoint | Install screws to substrate
checkpoint-status |  |  | checkpoint | Install Trough Infill PIR
checkpoint-status |  |  | checkpoint | New Vapour Barrier
checkpoint-status |  |  | checkpoint | New 80mm PIR
checkpoint-status |  |  | checkpoint | Taper PIR closest to spouting
checkpoint-status |  |  | checkpoint | New Aluminium Drip Edge
checkpoint-status |  |  | checkpoint | New Fibretite Membrane
checkpoint-status |  |  | checkpoint | Penetration through roof
checkpoint-status |  |  | checkpoint | New Fascias
checkpoint-status |  |  | checkpoint | Install Pressure Bars
checkpoint-status |  |  | checkpoint | New Gutters and Down Pipes
checklist-flat |  |  | checklist | Stage 3 - Library Exterior - East & West |  |  |  |  | Yes | Stage 3 - Library Exterior - East & West | f34118cd-bc20-4538-a04e-3cb8d7410a2b
checkpoint-status |  |  | checkpoint | Remove Asbestos Soffit
checkpoint-status |  |  | checkpoint | Remove 3 Windows
checkpoint-status |  |  | checkpoint | Lap new Building Paper
checkpoint-status |  |  | checkpoint | Install new Weatherboards
checkpoint-status |  |  | checkpoint | Install Scribers
checkpoint-status |  |  | checkpoint | Install H3.2 Soffit Blocking
checkpoint-status |  |  | checkpoint | Install Soffit Flashing
checkpoint-status |  |  | checkpoint | Install Soffits
checkpoint-status |  |  | checkpoint | Paint Weatherboard
checkpoint-status |  |  | checkpoint | Paint Soffits
checklist-flat |  |  | checklist | Windows - AJ001 & AJ002 |  |  |  |  | Yes | Stage 4 - Windows - AJ001 & AJ002 | f7950aa6-aa59-41b0-8fa8-571c255e8c58
checkpoint-status |  |  | checkpoint | Remove Windows
checkpoint-status |  |  | checkpoint | Re frame new opening sizes
checkpoint-status |  |  | checkpoint | 100m SHS
checkpoint-status |  |  | checkpoint | WANZ Bar
checkpoint-status |  |  | checkpoint | Flashing Tape
checkpoint-status |  |  | checkpoint | Cavity Batten
checkpoint-status |  |  | checkpoint | Window installed
checkpoint-status |  |  | checkpoint | Window winders