## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-sectioned | e10ad774-73f1-4c74-bf7d-7eb8476bfecb |  | checklist | Viking Warmspan Checklist |  |  |  |  | Yes | Viking Warmspan Checklist | a6470979-6ee3-421a-ac19-7704836d4b25
checkpoint-group | 6ee57445-7670-4e50-8603-9d7a16ad980b |  | section | Prestart
checkpoint-status | a6136a16-a96f-4b32-85bd-81a3614c2886 |  | checkpoint | All workers inducted to site
checkpoint-status | e37cbeb1-1cc6-4c66-b648-436fe6b5d0d0 |  | checkpoint | Prestart safety meeting held
checkpoint-status | 02988180-5740-4da2-958f-38c0db44ef4a |  | checkpoint | Area Accessible
checkpoint-status | fb59594b-93d2-44c4-bc08-521bff08377b |  | checkpoint | Edge protection and safety installed
checkpoint-status | 1464d37f-5d36-4df1-a416-696eb6ed2e45 |  | checkpoint | Purlins in place
checkpoint-group | a60f06ae-ddae-4912-83b3-23d2bcdfdc8d |  | section | Warm Roof Metal deck substrate install
checkpoint-status | 8ace69aa-71fe-4084-a02f-c401e898888d |  | checkpoint | Pre-start o discuss details and execution of system
checkpoint-status | fce56655-d846-40d9-b2fc-1af5afcc2fd6 |  | checkpoint | Metal deck installed in accordance with Manufacturer’s recommendation.
checkpoint-status | a8debcec-a450-44fd-924b-b9a2e5b1c588 |  | checkpoint | Outlets are sufficiently sized for anticipated run-off.
checkpoint-status | 64a9e7d4-f648-4264-9874-af8be91dada4 |  | checkpoint | Metal roof edges overhanging into gutters are cut back and timber upstand installed at the height of PIR board.
checkpoint-status | 56f67eb8-4a7d-4d4e-aad6-3d0d2a6c2fbd |  | checkpoint | Metal surface satisfactory for installation of Duo membrane by Equus Applicator.
checkpoint-status | f0df4e49-a8fe-4abb-94a3-9ca4f0d1c8d8 |  | checkpoint | Sufficient and correct fixings installed
checkpoint-status | e9b66af2-2244-41c1-90d6-83e7dc0128ae |  | checkpoint | No metal edges protruding up high
checkpoint-status | db72d341-9dc6-442b-b674-f98ab2099906 |  | checkpoint | Flashings installed over hips/ridges and valleys
checkpoint-status | dcc2d79b-2899-40aa-87a0-a66ed498df1b |  | checkpoint | all swarf swept from roof
checkpoint-group | 28cd12b7-7888-49a0-b194-2aeb350aad13 |  | section | Vapour Barrier installation
checkpoint-status | 022b5958-ac3d-425c-83a8-3a89b2ec52d9 |  | checkpoint | Primer applied evenly and consistent to all surfaces and penetrations to the required height up upstands and parapets etc
checkpoint-status | eced6bd1-1800-4cc2-9c86-010da012a3d1 |  | checkpoint | Vapour barrier installed and carried up parapets a minimum 50mm past PIR Insulation board.
checkpoint-status | 7bb8fd18-5e05-47e9-8177-bf82c7833cbb |  | checkpoint | Correct side laps and end laps
checkpoint-status | 067cd70b-fa37-4e09-8136-1783a637f186 |  | checkpoint | Vapour barrier terminated correctly to ensure vapour layer continuity at roof openings, transitions and horizontal to vertical roof openings
checkpoint-status | 18f59676-5910-486d-8ba7-ae23f8246703 |  | checkpoint | Any damage to vapour layer to be repaired to 100 % continuous
checkpoint-group | 0d4f352f-8bed-4348-8c89-9e1421eeeeac |  | section | Insulation
checkpoint-status | 0580110c-ec19-4300-bb0b-e57386bf45b7 |  | checkpoint | Correct insulation delivered as per plans and specs
checkpoint-status | 2a6e77cc-523c-4ca6-987f-a574a37d8d65 |  | checkpoint | Insulation damage free no crushed edges etc
checkpoint-status | a3b66c3a-986f-46a0-b2ae-f1bec2cdf540 |  | checkpoint | Insulation has been kept dry out of weather at all times
checkpoint-status | c9c61d9b-b9f3-4afc-b629-d824e6e0c610 |  | checkpoint | Ends of insulation to be protected by a hard edge with timber or flashing
checkpoint-status | 2537bfbc-f30b-4f51-a3f5-7cbc27a60a7c |  | checkpoint | Insulation to be installed in a brick bond pattern
checkpoint-status | c77bfd76-8a9c-415c-8263-5e4ffb333308 |  | checkpoint | Correct fixing being used including the correct insulation plate or thermal plug or adhesive
checkpoint-status | 3d8c1830-0653-491c-ab47-8df135a3f13a |  | checkpoint | Correct fixing pattern used as per manufacturers specs or site specific wind uplift calculation
checkpoint-status | 0f40b6df-b6fb-4e7f-b8fc-1f617da09f24 |  | checkpoint | Evenly distributed weight if FAST adhesive used
checkpoint-status | cf50e869-d6df-4f6a-9acb-6fe97906911a |  | checkpoint | No edges protruding high
checkpoint-group | 7d46097d-cefa-46de-ab16-a371979a3702 |  | section | Coverboard
checkpoint-status | 3e7e0adc-dedf-4492-a658-23a58bfbb58c |  | checkpoint | Correct coverboard delivered as per plans and specs
checkpoint-status | 27bde908-b5f1-44b1-8236-b7e71f2bc98f |  | checkpoint | Any damaged insulation board to be cut out and replaced with new or not used (minimum repair 300 x 300mm)
checkpoint-status | e09094f5-deba-4a38-b552-c520e4f86bc2 |  | checkpoint | Correct fastening method ie glue or fixings
checkpoint-status | e44af369-0c9c-4075-bb39-53ee5ca92ad5 |  | checkpoint | Correct fixing pattern used as per manufacturers specs or site specific wind uplift calculation
checkpoint-group | 99c2db2f-b3aa-41f8-98ef-ae824dc99e35 |  | section | Viking Enviroclad installation
checkpoint-status | 02a7f631-eb27-422a-bbc5-76ff329e50db |  | checkpoint | Ensure substrate is completely free from debris, dust etc
checkpoint-status | ee5b5fe8-e445-4a24-a357-5fa98d0b667d |  | checkpoint | Taken into account ambient tempratures prior to installation beginning
checkpoint-status | eda8b55b-4e7c-4f52-88c5-52e8ed868a76 |  | checkpoint | Taken into account incoming weather prior to installation beginning
checkpoint-status | d25d1d91-1525-495c-9f75-fea62b350b2d |  | checkpoint | Adhesive applied as per specification (refer to relevant section in specification)
checkpoint-status | b59d0de3-7edb-4c39-a25d-fd9b31192225 |  | checkpoint | Membrane layout to the roof has been considered carefully
checkpoint-status | 90b9c46c-0cb5-412d-a699-5e4c8d24a50e |  | checkpoint | Membrane has been installed in the correct sequence, starting from the outlets up-to the highest point of the roof/deck or gutter
checkpoint-status | f1d3dc39-fe15-4b22-86d1-093aea19f4ff |  | checkpoint | Correct laps in Enviroclad overlapping edges a minimum of 50mm to provide for a minimum 40mm hot air weld.
checkpoint-status | 16526f3b-7cea-447d-84e2-5fd377f0d28f |  | checkpoint | Laps are cleaned prior to welding
checkpoint-status | 771c1700-cd6b-4ac8-9536-df1763e01cad |  | checkpoint | Membrane has been fully rolled to ensure a consistent bond
checkpoint-status | 56ec9d3d-aad6-486f-b55d-2af2611a303a |  | checkpoint | Terminations up walls, parapets etc to be completed as detailed or to minimum code requirements
checkpoint-status | c1108992-01c9-4a3c-a0c8-c536076ad151 |  | checkpoint | Terminations up walls, parapets etc to be mechanically fastened by flashing, fastening bar, TPO coated steel
checkpoint-status | fa17d114-519d-48a6-8fbc-96b6d6adb238 |  | checkpoint | Proprietary accessories have been used for all corners and terminations
checkpoint-status | b0f06770-4a45-466b-9f88-31aa24020676 |  | checkpoint | Proprietary accessories have been used for all penetrations ie Pourable pocket etc
checkpoint-status | 96b2adb9-931e-421e-827c-3a3978681367 |  | checkpoint | All welds seam probed and any inconsistencies in weld rectified
checkpoint-status | be2fa05a-ed12-4df7-bb9f-794b7b6f39e1 |  | checkpoint | Cut edges of membrane to be penny welded or lap seam primer installed
checkpoint-group | ad45bb02-ec3e-4394-a9fd-b074735434d8 |  | section | Flashings
checkpoint-status | 43cde2ec-7c2e-4190-9a62-46c6578531e1 |  | checkpoint | Flashings made in specified material/colour
checkpoint-status | f7ad195a-c4d2-4e6f-970f-7ffa13c877ec |  | checkpoint | Flashings installed neatly and fixed sufficiently
checkpoint-status | e8a6f7b7-ed78-4d8c-ba93-238baba5e50d |  | checkpoint | Flashings sealed with correct sealant
checkpoint-group | 1c42420d-659c-4ea2-b014-48392deb944b |  | section | Clean up
checkpoint-status | 74db9d20-7892-4e2e-b48e-2c97cb1e6b5e |  | checkpoint | All rubbish from all stages removed from site
checkpoint-status | 66b40714-28af-46a7-815d-9489d768cc7e |  | checkpoint | Roofs cleaned down
checkpoint-status | c5c3b4b9-b6f5-446a-b8c5-dc9bcf4a6ba3 |  | checkpoint | Scaffold checked on every level for rubbish
checkpoint-status | 73d2b0e9-37f5-4295-b1ad-2dc0eb969041 |  | checkpoint | Grounds checked for rubbish (under scaffold etc)
checkpoint-status | 680b9eb4-abf4-4fcd-ad0d-064aba993af8 |  | checkpoint | Site forman agrees site is clean
checklist-sectioned | 0ab8d4f7-050e-44a9-8f75-f90336aa9ec0 |  | checklist | TPO Concrete Checklist |  |  |  |  | Yes | Roofing QA - TPO Concrete Checklist | c0f6661e-242e-4a01-a85f-695744316812
checkpoint-group | 0a5276d2-9e6d-4420-a745-d0e864d272d0 |  | section | Substrate Check
checkpoint-status | 17c46294-b9b4-49f4-8acc-cb726ef2f18b |  | checkpoint | Concrete substrate has been allowed to fully cure - at least 28 days from pour
text | 83d107d2-1cb1-5f5d-b5c7-c0a523d0e573 |  | textbox | Concrete Pour date:
checkpoint-status | cb565a15-0c8a-4192-9fcf-771b7cea9275 |  | checkpoint | Fill hallows or holes with a cement plaster, or FLC
checkpoint-status | b3f7c929-f74c-45ca-92bf-acc36c3a2b5a |  | checkpoint | Surface smooth, clean, dry and free of debris or release agents
checkpoint-status | 31a5b93e-95ce-4f1f-961f-091379f6e0cf |  | checkpoint | Substrate venting installed as required
checkpoint-status | 1fe814da-64c9-4203-bc45-7eb6b13acb8f |  | checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
checkpoint-status | cb5009d0-2109-41dd-b4c5-8039b4e83e55 |  | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
checkpoint-group | 71bf0533-b51d-4631-bcc6-4899eb1769fd |  | section | TPO Horizontal & Vertical Application
checkpoint-status | 5c66c30d-1321-4b41-9acf-3175b4f01b19 |  | checkpoint | Conducted test weld on an off cut of membrane prior to installation?
checkpoint-status | 304dc290-75ce-45bf-98d1-d465f880dd39 |  | checkpoint | Ensure even coating of approved adhesive used on JM sheet as well as substrate
checkpoint-status | d236eebd-40f2-4163-a536-ff34d2d2093e |  | checkpoint | Ensure 40mm minimum sheet laps
checkpoint-status | 90ccf5d5-95ca-414a-8ab1-69e81f1e011f |  | checkpoint | Ensure all weld areas thoroughly cleaned with JMCLEAN membrane cleaner
checkpoint-status | 6a732944-e91e-4399-89ec-054e9d836b87 |  | checkpoint | Test all welds with a seam probe
checkpoint-status | fce8a021-1e20-467e-91ef-7306b77c8875 |  | checkpoint | Attach application photos (1 photo per 20m2)
checkpoint-group | 65544047-2ee5-4f0e-81fc-60c056ecfb30 |  | section | TPO Detailing (Gutters, Corners, Overflows)
checkpoint-status | 0d90d3f2-392f-4124-801a-5f8a24cb590d |  | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
button | f97f614b-44a8-5297-b7d6-9f491aa0a3d6 |  | button | Ensure the correct JM accessories are used? | Yes, No, N/A
boolean | 7e96e8a2-4cf5-5fc9-9816-a3d0c120861d |  | tickbox | Attach Photos (1 photo per drain/outlet )
checkpoint-status | 76d3517e-d1b3-4c0d-977d-b715ea5cb516 |  | checkpoint | Penetrations - appropriate detailing techniques used
button | dd9fa737-a8fb-5718-bb87-9b42290057eb |  | button | Ensure JM Single ply caulking is applied on appropriate areas? | Yes, No, N/A
button | b02779db-06d2-5e40-ad85-dd8d4da76204 |  | button | Ensure 200mm upstand extension over pipe penetrations, and 150 mm for vent and square post (deck) penetrations | Yes, No, N/A
boolean | 4d886059-3b59-5f6e-ad6e-c5f4653922a3 |  | tickbox | Attach Photo (1 photo per penetration)
checkpoint-status | f1b4dcc5-9ec0-4d5d-8973-afd30349459e |  | checkpoint | Transitions - appropriate detailing techniques used
button | 5108f476-ecaa-5def-a4f4-63b2835fd5f4 |  | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
boolean | fe20bbda-6024-5112-bbaa-e3fbac784a5d |  | tickbox | Application photos of transitions
checkpoint-status | fae1a3f3-7133-445c-888c-598eb4dfeaf9 |  | checkpoint | External & Internal Corners - appropriate detailing techniques used
button | 70315edb-9ac6-5816-8a19-055436d8b0a7 |  | button | Ensure appropriate JM corners accessories are used? | Yes, No, N/A
button | f7b60770-2c04-50e7-ac00-9ee34f62d8c6 |  | button | Ensure appropriate detailing techniques used? | Yes, No, N/A
button | aa7b6fc3-7518-5934-8e8b-aff06be50c1e |  | button | Ensure 40mm wield length on all sides and corner fully welded | Yes, No, N/A
boolean | 6b685fbd-f3f0-5b82-93ce-20f6b952f2ae |  | tickbox | Application photos of corners ( 1 per corner)
checkpoint-group | faf9a86d-9d37-442b-b83e-110ad76faa5f |  | section | TPO Concrete Termination
checkpoint-status | 85a2aea6-0010-45c4-a2cd-619fc662bcee |  | checkpoint | Ensure appropriate detailing used for termination?
checkpoint-status | f00f23db-4fde-414d-aa5d-751215c8ab4c |  | checkpoint | Ensure 40mm hot weld between TPO and steel folded flashing (if appropriate)
checkpoint-status | 692ba202-d8bf-44eb-bfd3-7b2f7007c726 |  | checkpoint | Application photos of terminations (1 photo per termination)
checklist-sectioned | 9db91ca0-99c1-4522-9435-93216f1527bb |  | checklist | Sweltite for Area: |  |  |  |  | Yes | Waterproofing QA - Sweltite Checklist | 7a9cbe6d-5f8b-4b67-ae9a-19538ea7bab5
checkpoint-group | 01f2112b-3174-490a-b14c-994bad1ef2e0 |  | section | Sweltite Area of Installation
checkpoint-status | 277604ae-9fe5-4ce3-9adf-028115d9c3ec |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | 1e8ed08f-80a0-5b0d-a678-e215d747965b |  | textbox | Description, grid sections, etc:
checkpoint-group | 04e4d099-be5b-4fff-af45-5b022cb83b37 |  | section | Sweltite Site & Substrate Prep
checkpoint-status | 8293854d-d51e-46b3-b2dc-eb22793ae7ed |  | checkpoint | Appropriate site conditions for installation
checkpoint-status | e4b9588d-2fc2-4fd1-bee9-b3d230cdecd3 |  | checkpoint | Appropriate water control in place
checkpoint-status | 27d3c552-6673-4a99-885a-1a6d78b2528f |  | checkpoint | Substrate photos taken
checkpoint-group | e3e1774e-92e3-4a3c-b49c-097299f0d871 |  | section | Sweltite - Foundation walls
checkpoint-status | f10d1a30-5622-449a-a20d-951f4daf6328 |  | checkpoint | Appropriate detailing done as per Allco specifications
checkpoint-status | b077bc2f-7be5-4d90-97da-8cc7715a97e5 |  | checkpoint | Ensure 100mm laps between membrane
checkpoint-status | f197622e-d5e1-4bd1-8917-c6e7267ada6c |  | checkpoint | All laps seam taped horizontally & vertically using Allco seam tape
checkpoint-status | 52aa348b-d37a-4ac6-b948-69367bf0c0af |  | checkpoint | Sweltite exceeds 150mm past F.F.L
checkpoint-status | 8302047e-86fd-409c-b425-7345ff6897b2 |  | checkpoint | Drainage coil has been placed 100mm from the floor/wall joint
checkpoint-group | c45272df-270a-4bae-937a-876272e9f985 |  | section | Sweltite Penetrations
checkpoint-status | 2536ead9-0d43-4ba7-af69-798c129bb267 |  | checkpoint | Penetrations detailed appropriately using appropriate accessory Volclay products
checkpoint-group | 53c52454-4c30-41b3-93a6-457daaa4dcd2 |  | section | Sweltite Termination
checkpoint-status | 8f0b8ab6-63e6-4530-9bf6-bfaf47b6d092 |  | checkpoint | Termination bar used on vertical & horizonal edges
checkpoint-status | 8253bee4-e8f3-43b4-9c28-9d4ef5a1d760 |  | checkpoint | Cetcoat applied at appropriate areas
checkpoint-status | 365ff4ff-9ecd-4b37-854e-b116ee5a8c19 |  | checkpoint | Termination sealed off correctly (i.e. M2000, Cetseal)
checkpoint-group | 5d0f334c-420e-4e7a-9480-05ed147ca8af |  | section | Sweltite Backfill & Protection
checkpoint-status | 10558d80-0c10-4f3f-8588-34c47747fe83 |  | checkpoint | Allguard has been installed as per Allco specifications
checkpoint-status | 2c34474a-d894-4d9e-89c2-2176feda778b |  | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
text | 12ea88f5-0476-56b6-96bd-fd5150dcce4d |  | textbox | Backfill date
checklist-sectioned | 4ee753fa-b026-46df-becf-857659828a07 |  | checklist | TPO Plywood Checklist |  |  |  |  | Yes | Roofing QA - TPO Plywood Checklist | 46783d8c-1b56-4340-868a-f426882ee396
checkpoint-group | 7b101946-7c62-49a5-beb5-b9de69a13bf7 |  | section | Substrate Check
checkpoint-status | e838d4d4-1fec-4a51-a22d-9cff6497fd4f |  | checkpoint | Framing supports at 400mm centres for 17.5m ply (in one direction). All plywood edges must also be supported.
checkpoint-status | 85bb9fc1-1a39-4e4a-8ab2-2c877862617e |  | checkpoint | Tongue and groove plywood NOT used
checkpoint-status | fa853cc8-8008-4157-96f6-39efbd6a99f9 |  | checkpoint | Framing supports at 600mm centres for 19.5m ply (in one direction). All plywood edges must also be supported.
checkpoint-status | 64cf4cee-93ad-4264-b090-df85052b7d65 |  | checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
checkpoint-status | caa73ff7-7d02-4a69-a14b-237575e4f217 |  | checkpoint | Minimum CD grade with the sanded C face upwards
checkpoint-status | 8bc1b614-fe39-43e8-8e8a-158107eda411 |  | checkpoint | Plywood to be laid at right angles (90 degrees) to supporting timber.
checkpoint-status | 8b46def0-373c-4c8b-b2be-904bd9908145 |  | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
checkpoint-status | c11bda70-df09-4eb7-9b84-3e6982d77f0d |  | checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
checkpoint-status | 3b9cd57c-f4ec-4a87-bbf9-f8c828d9634c |  | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
checkpoint-status | b9d04148-d231-434e-842c-d69a8ea8b656 |  | checkpoint | Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood to be at no more than 18%moisture content.
checkpoint-status | 1c5be848-0dd5-4358-a93c-9a32d672e322 |  | checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. - 1 vent for the first 40m2 and one for every 50m2 thereafter. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
checkpoint-status | 9f65ac5b-0cb2-4c7c-959c-d424be4167bc |  | checkpoint | All drains and outlets are membrane compatible. Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
checkpoint-status | d570db2e-3cee-4b0b-a93c-e83373399c0e |  | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
checkpoint-group | 804d8eef-aab2-43d5-9ca7-0e9ba306d28d |  | section | TPO Horizontal & Vertical Application
checkpoint-status | 6d7ad279-79d2-4640-91f8-3e544265b583 |  | checkpoint | Conducted test weld on an off cut of membrane prior to installation?
checkpoint-status | 69e0f0d4-aa95-4e72-be56-f925e3546f62 |  | checkpoint | Ensure even coating of approved adhesive used on JM sheet as well as substrate
checkpoint-status | 397f7f2d-84ea-4ff8-9a81-96cd38442d51 |  | checkpoint | Ensure 40mm minimum sheet laps
checkpoint-status | e73cf3d8-acd0-4929-b1fa-a09cb4cff688 |  | checkpoint | Ensure all weld areas thoroughly cleaned with JMCLEAN membrane cleaner
checkpoint-status | d12ed89a-9e70-4f28-a808-c2533edca866 |  | checkpoint | Test all welds with a seam probe
checkpoint-status | 933fc5a0-d147-43eb-a2cd-e9fbf0186bd0 |  | checkpoint | Attach application photos (1 photo per 20m2)
checkpoint-group | 296cbed0-b5ef-4d16-9cdf-0ab7f1fd506e |  | section | TPO Detailing (Gutters, Corners, Overflows)
checkpoint-status | 0f9f48af-a974-4347-8ed2-8623cd719290 |  | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
button | 55051658-0e82-50d7-957b-75c58c2ec217 |  | button | Ensure the correct JM accessories are used? | Yes, No, N/A
boolean | 76be6cf6-36b2-5ef7-be2e-2dc120961807 |  | tickbox | Attach Photos (1 photo per drain/outlet )
checkpoint-status | fa8e31fc-4002-4948-a353-566b303ebf1e |  | checkpoint | Penetrations - appropriate detailing techniques used
button | 5b081a9e-9f2b-5b34-99d9-33b80e5693a3 |  | button | Ensure JM Single ply caulking is applied on appropriate areas? | Yes, No, N/A
button | 8c2d69b7-4643-5eef-aa03-96593a9ea88f |  | button | Ensure 200mm upstand extension over pipe penetrations, and 150 mm for vent and square post (deck) penetrations | Yes, No, N/A
boolean | 5555c8d0-f50a-53b7-a241-1de820754033 |  | tickbox | Attach Photo (1 photo per penetration)
checkpoint-status | e9806f13-2522-4739-830b-c6dd2407ad6d |  | checkpoint | Transitions - appropriate detailing techniques used
button | 92349111-625a-5974-bcf0-9475f26cdc4b |  | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
boolean | de39d17b-09e9-5095-87ae-fde5e9e9929b |  | tickbox | Application photos of transitions
checkpoint-status | 6d8fb997-af06-409e-8e3d-b470312c4097 |  | checkpoint | External & Internal Corners - appropriate detailing techniques used
button | 99fb4c58-e97f-5425-8f41-43ea1400ced8 |  | button | Ensure appropriate JM corners accessories are used? | Yes, No, N/A
button | ed84b504-f598-5dba-b53c-977fc4c3842c |  | button | Ensure appropriate detailing techniques used? | Yes, No, N/A
button | b572370c-b744-5568-9747-7833ba749d60 |  | button | Ensure 40mm wield length on all sides and corner fully welded | Yes, No, N/A
boolean | 4d40a78e-f510-526f-ba42-814a44e94757 |  | tickbox | Application photos of corners ( 1 per corner)
checkpoint-group | 370559d2-9999-4bd5-b3f3-51bba851417d |  | section | TPO Plywood Termination
checkpoint-status | 8fa92dcd-139c-42f9-957b-3f4dd2372165 |  | checkpoint | Ensure appropriate detailing used for termination?
checkpoint-status | 06c5db5d-b9a1-4798-aba8-dd6341702177 |  | checkpoint | Ensure 40mm hot weld between TPO and steel folded flashing (if appropriate)
checkpoint-status | c687c58f-ab82-4df9-a548-0977847d161d |  | checkpoint | Application photos of terminations (1 photo per termination)
checklist-sectioned | a3825b2c-df0c-4253-ab36-8d3983216e2a |  | checklist | Voltex for Area: |  |  |  |  | Yes | Waterproofing QA - Voltex Checklist | c575fe41-ba7d-4516-aa1a-c358eb89d584
checkpoint-group | 20edd108-c87b-4115-b605-1b0ad912ec5e |  | section | Voltex Area of Installation
checkpoint-status | 8c5f7c7f-ec48-47b5-8830-bc80e2e16c56 |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | 345fe001-05ba-5e52-bc8e-d281f8fd964c |  | textbox | Description, grid sections, etc:
checkpoint-group | ec2928c3-46ab-417c-8b81-2a3625a9d1ee |  | section | Voltex Site & Substrate Prep
checkpoint-status | 859d9da9-03cc-4ff4-b2ea-980eef615e92 |  | checkpoint | Appropriate site conditions for installation
checkpoint-status | fab6781b-f22f-4962-aba5-95ae04feaa9b |  | checkpoint | Appropriate water control in place
text | 5af86c0a-73e9-59b9-b097-42759eeb694f |  | textbox | Concrete pour date
checkpoint-status | d9753dbe-84b1-40e4-a241-9c1b5a9ffc0d |  | checkpoint | Substrate photos taken
checkpoint-group | cbe0849a-6ac4-4db1-aff3-5d672f20adfe |  | section | Voltex Walls, Underslab and Footings
checkpoint-status | 28ff86f6-9c2f-4c12-a931-8bcbb2b0f82d |  | checkpoint | Membrane appropriately laid on substrate with dark grey (woven) side up
checkpoint-status | 47ea485b-7bdc-4b5d-a481-46d025a4940e |  | checkpoint | 100 mm overlap between each sheet, and stagger sheets end at a minimum of 300mm
checkpoint-status | 6751a0c0-0044-4582-852d-ad70713cfeec |  | checkpoint | Appropriate detailing done to external/internal corners
checkpoint-group | fdcd2b28-6101-4642-a8c6-b632a55eee75 |  | section | Voltex Penetrations
checkpoint-status | 7f5d8170-f436-4d22-a83e-4bec410431b7 |  | checkpoint | Penetrations detailed as per Allcos recommendations
checkpoint-group | d16e5558-1ff0-43d0-98bf-7fa98ca4d99c |  | section | Voltex Backfill & Protection
checkpoint-status | eef358bd-8a4b-4622-9dde-7630fa4196f4 |  | checkpoint | Allguard has been installed as per Allco specifications
checkpoint-status | 9c3e8769-9e67-4937-9632-f4bd2f7f75fa |  | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm
text | d0e82439-9d99-5db4-821d-a9d69c6c4400 |  | textbox | Backfill date
checklist-flat | 58d57f41-97b1-4d48-a8e2-71c3abde86be |  | checklist | Protection & Backfill for Area: |  |  |  |  | Yes | Waterproofing QA - Protection & Backfill Checklist | 59861e5f-15fd-4c96-9ad7-982e1f12764b
checkpoint-status | 50739d80-0144-4562-b22e-1f8d896422b4 |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | 59231477-162a-5580-aea2-dccab183f5b4 |  | textbox | Description, grid sections, etc:
checkpoint-status | d21e51dc-9387-40d2-bd43-7ee4c1d393a6 |  | checkpoint | Allguard has been installed as per Allco specifications?
checkpoint-status | cf9a872a-aa12-4f89-b1e1-50ca0014d9f6 |  | checkpoint | Hydrostatic Conditions - Backfill compacted every 400mm?
text | bba2a201-8152-58ce-8d6c-9ab9490030cb |  | textbox | Backfill date
checklist-flat | 101d6d51-f6a0-48bb-830b-d41b5ffcff80 |  | checklist | Site Visit date: |  |  |  |  | Yes | TA - Site Visit | 2d398eaa-3b48-40a7-a8ad-31e4b13c3d00
checkpoint-status | 3b44dfed-46ef-4f40-9c66-1e24d6db2236 |  | checkpoint | Site Details
text | 08b397d9-cae9-5704-baf4-41956f084809 |  | textbox | Project Name/Address:
text | 3dc2bb04-4a86-5107-a7ab-1967e5428834 |  | textbox | Contractor Name:
text | 4ed3981e-fbc0-5c33-a805-12a04216e7ff |  | textbox | Applicator Name:
button | d48eb27a-5dd5-54a6-8cdc-82ea9c48799f |  | button | System Warranty | Yes, No
checkpoint-status | e710f19d-57e3-4854-a72d-894def8af076 |  | checkpoint | Product(s) Used
boolean | 17b749b4-143a-5147-a691-99cb085b90cb |  | tickbox | Voltex
boolean | 7dd0d95c-ce61-5251-9892-9850820ec2a3 |  | tickbox | Voltex DS
boolean | 4e902ab6-63dd-5e80-9d82-ea34410c2c49 |  | tickbox | Voltex SWR
boolean | e48961ef-61a1-51bf-8ad8-c50a2c683ead |  | tickbox | Sweltite
boolean | 1caf4385-df75-55dd-94f0-c983b1d34624 |  | tickbox | Rx Waterstop 101
boolean | 0f3afd36-d654-539d-89e5-7d634e2a8bbd |  | tickbox | Rx Waterstop 102
boolean | e19ad193-1ed8-5f21-843a-a3096eb00916 |  | tickbox | Aquadrain
boolean | f127add9-4eba-527c-9a13-e9e5b5580602 |  | tickbox | Corflute
boolean | 1d234e03-3347-5411-8bca-892b98a53b9c |  | tickbox | Accessories
text | 4c251d93-ddfc-5023-9a8b-bafb1a65b446 |  | textbox | Other
checkpoint-status | f81ab4ae-aee2-495f-861e-0f9754b9e981 |  | checkpoint | Site Visit complete and NO REPAIRS REQUESTED
button | 2232c4fe-3e77-5264-aedb-de724743ce29 |  | button | Substrate acceptable | Yes, No
text | d6bcd1cf-db8c-5fcd-96b7-091868328b98 |  | textbox | Location or Grid Lines:
text | 5aa387f2-766e-54ee-80a1-5db918854e3c |  | textbox | Inspection Notes
checklist-sectioned | 901a99b7-bc4e-46ad-af2c-f39c16af286a |  | checklist | Hydrotech for Area: |  |  |  |  | Yes | Waterproofing QA - Hydrotech Checklist | 0734e24e-3cb8-4e83-ade6-15504357fb1e
checkpoint-group | 8adcb96b-baed-4145-bf89-9264f0ffd4c3 |  | section | Hydrotech Area of Installation
checkpoint-status | 9ac65781-fab5-445d-a2b7-bf8c13812549 |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | 2d3d4c20-fb70-5d83-96fd-207f0dd3a956 |  | textbox | Description, grid sections, etc:
checkpoint-group | 7cc8a01b-0988-42df-8f11-36e7682866cf |  | section | Hydrotech Site & Substrate Prep
checkpoint-status | cc28b9ae-176c-40eb-8901-cc95bce1ab08 |  | checkpoint | Wind uplift has been considered prior to installation
checkpoint-status | 7c058cb1-5fef-42e3-85a7-220393d2c906 |  | checkpoint | Ensure all drains and outlets are membrane compatible. Confirm with Allco rep if required
checkpoint-status | 2975547b-fad7-465e-9a20-b776f97641d4 |  | checkpoint | Concrete substrate has been allowed to fully cure with a minimum wood float finish
checkpoint-status | 8de8e338-34c9-4c27-aca2-82c9b160e43a |  | checkpoint | Substrate clean, dry and free of debris or release agents
checkpoint-status | c2a3c2a8-38fa-46a1-8f7d-cca61ac4ce13 |  | checkpoint | Substrate photos taken
checkpoint-group | 1caa264a-b3ae-4a18-9ef2-539115790946 |  | section | Hydrotech Horizontal & Vertical Application
checkpoint-status | d5b1ff75-1880-4b75-9caf-7b0f999cbdb3 |  | checkpoint | Test conducted to ensure membrane creates a mechanical bond to the substrate
label | 40874f5c-c1ce-5481-adc2-2f53299527a8 |  | note | Attach application photo (1 photo per 20m2 or separate area)
checkpoint-status | 1e99df68-a7ed-4a08-a1f7-664e18cf7df8 |  | checkpoint | First membrane layer applied at 3mm thickness
label | b04ecb4d-0965-5d27-b902-50ddb82afc51 |  | note | Attach application photos (1 photo per 20m2)
checkpoint-status | 8d4952e1-35a5-493b-9bef-155b5d4012b6 |  | checkpoint | Top coat of Hydrotech applied at 3mm thickness
label | 9546d650-1820-523e-be13-805dfef4cfcf |  | note | Attach application photos (1 photo per 20m2)
checkpoint-status | 6c4d4502-75f4-47bb-b6d5-3f72940bc834 |  | checkpoint | Photo proving total thickness of membrane system is 9mm (including protection layer)
checkpoint-status | 1c53b810-360b-449c-af5d-1e7eb1fffd73 |  | checkpoint | Photo of complete installation
checkpoint-group | aca8684d-842e-4d8f-8d1d-61c9453661d0 |  | section | Hydrotech Detailing
checkpoint-status | c4901fb1-3b61-4cbc-bad3-6cc549f75dac |  | checkpoint | All penetrations have detailed as per Allco specifications
checkpoint-group | f8f7671f-c3e1-4552-bdf4-530899b33d0d |  | section | Hydrotech Terminations
checkpoint-status | ae6308c2-7bbf-4783-a160-ad79c94c225d |  | checkpoint | Ensure the approved sealant or tape is used for termination
checklist-sectioned | b9db1e20-cd5f-477f-9465-6b75da1ac94d |  | checklist | Waterstop-RX for Area: |  |  |  |  | Yes | Waterproofing QA - Waterstop-RX Checklist | b405b6a1-2f9e-4e0a-9d12-b3dddaa5159d
checkpoint-group | 2b8bf332-68d0-4a6c-b20a-b05d576a52d9 |  | section | Waterstop-RX Area of Installation
checkpoint-status | 8690111c-79f6-4d8f-85c6-cd91b84cc375 |  | checkpoint | Checklist named with location or text box below or marked up drawing attached
text | 75d6dba4-47e4-50ec-bee6-387daf2d6af3 |  | textbox | Description, grid sections, etc:
checkpoint-group | 16830878-e2c7-4ca1-9a7e-00a8c862d69e |  | section | Waterstop-RX Site & Substrate Prep
checkpoint-status | 5bd055ab-d5b1-4f88-96cf-699a6c5c254a |  | checkpoint | Substrate is acceptable
checkpoint-status | 5f8c1e92-7115-4192-b1cf-fd520f5e1185 |  | checkpoint | Confirm appropriate Waterstop-RX is going to be used in relation to concrete thickness
text | bdde70d4-e30b-5c50-ac40-bf1df3880cae |  | textbox | Concrete pour date
checkpoint-status | 60209e19-d2be-478e-81e7-b85452ed019c |  | checkpoint | Substrate photos taken
checkpoint-group | 83086c8d-b95a-4953-8476-fe9884ae30c8 |  | section | Waterstop-RX Installation
checkpoint-status | ca3a7ab2-f2b1-44c1-aa5e-79f7da01b1bb |  | checkpoint | Waterstop-RX has been installed as per Allco specifications
checkpoint-status | 6a060df3-9bc0-44c4-84e6-d3e14c7de853 |  | checkpoint | All parties aware of Waterstop-RX requirements with exposure to climatic conditions
checklist-sectioned | 60f0fc44-2a87-4a26-a56e-3ed27cd34fc8 |  | checklist | Torch-On Concrete Checklist |  |  |  |  | Yes | Roofing QA - Torch-On Concrete Checklist | 26fe8013-d308-49e3-b466-4045bce5dfb8
checkpoint-group | a0a7d0ea-78b0-428b-a8cb-aa63ebfbabd5 |  | section | Substrate Check
checkpoint-status | c0b4a20d-39e3-47ed-930e-cc813464f5d3 |  | checkpoint | Concrete substrate has been allowed to fully cure - at least 28 days from pour
text | b38d2d6f-7d08-5827-890d-e0e4a8dd4b6a |  | textbox | Concrete Pour date:
checkpoint-status | 67131977-9b5e-43e0-b684-0d6a505c64b9 |  | checkpoint | Fill hallows or holes with a cement plaster, or FLC
checkpoint-status | 904eb277-bbe0-4141-b8fe-e3b1e70b072d |  | checkpoint | Surface smooth, clean, dry and free of debris or release agents
checkpoint-status | f320e300-ba2d-4d83-a8cf-ac39508dd31b |  | checkpoint | Substrate venting installed as required
checkpoint-status | 374a47be-0d52-4393-ac37-ef0b53989821 |  | checkpoint | Minimum 20mm triangular fillets at the base of upstands
checkpoint-status | ff8cd3ad-d340-4d5a-a237-795312c51ad2 |  | checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
checkpoint-status | 58d1c91a-5236-42c5-bf10-3ee5d562912e |  | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
checkpoint-group | 66230e6c-0aa1-4489-892b-251b16fe4703 |  | section | Torch-On Horizontal & Vertical Application
checkpoint-status | 4592d02b-5872-431e-a72e-8ec83fa292a1 |  | checkpoint | Check sheets are correctly aligned, unrolled completely and positioning them
checkpoint-status | 1c3cf6f1-4e26-4b69-a05c-9920dae5baea |  | checkpoint | Ensure side laps are at least 100mm and at head laps should be 150mm
checkpoint-status | 93997d1c-9d30-41b5-8552-bd28ba39aded |  | checkpoint | Ensure dermaprimer is used appropriately on the substrate
checkpoint-status | 8f7663d6-503e-426f-b4cd-ccf2527fe230 |  | checkpoint | The second layer fully bonded on to the first layer, staggering the side overlaps by 500mm and the head overlaps by half a roll
checkpoint-status | 5d56d67c-8b03-40bc-8702-ef85057ac204 |  | checkpoint | Ensure 150mm upstand height of membrane
checkpoint-status | 68643d72-fe63-43a1-883d-f28b6fbf0de7 |  | checkpoint | Attach application photos (1 photo per 20m2)
checkpoint-group | c7f9690e-99b7-40ac-8c03-321d9a822148 |  | section | Torch-On Detailing (Drains, Gutters, Joints, Overflows, Penetrations)
checkpoint-status | 58f3f19f-43aa-4e21-9b2d-dd4f4c7edd21 |  | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
boolean | ba888980-1c57-5f63-bb96-6a49662810b4 |  | tickbox | Attach Photos (1 photo per drain/outlet )
checkpoint-status | 064587d9-aaf3-4288-8d1d-13ea6afa9920 |  | checkpoint | Penetrations - appropriate detailing techniques used
button | f31a1b29-7078-5cb4-802f-414cb26d94de |  | button | Ensure 100mm extension from edge of penetration in all sides | Yes, No, N/A
button | 09992164-ec39-55a3-9a66-517abeed5338 |  | button | Ensure 100mm upstand extension over pipe | Yes, No, N/A
boolean | aefd8f5d-72ec-5fdb-98d3-c05353a6be32 |  | tickbox | Attach Photo (1 photo per penetration)
checkpoint-status | d45853cb-0434-4945-ad25-00f520b6c225 |  | checkpoint | Transitions - appropriate detailing techniques used
button | fd60130f-83c5-515d-93b2-9af3d5a1b265 |  | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
boolean | 802cbdb8-f708-5c6a-ae6b-13f57415558d |  | tickbox | Application photos of transitions
checkpoint-status | eecdf4e0-06fe-4ae0-a16d-58025b70a1e1 |  | checkpoint | Joints - appropriate detailing techniques used
button | 44af4e31-9771-563e-960d-0b2e9177136f |  | button | For expansion joints, ensure there is 150mm extension cover over the joint | Yes, No, N/A
boolean | cbcae9f4-ce8a-5819-a33c-83d0c10f49fe |  | tickbox | Application photos (1 photo per joint)
checkpoint-group | 013cdd1f-8b90-4024-a62c-3ba5a0492382 |  | section | Torch-On Terminations
checkpoint-status | b89c13c5-1d27-4cdc-b59e-c7e2a373215b |  | checkpoint | Ensure appropriate 100mm laps at transitions
checkpoint-status | 368a2b90-d3e6-4d2c-8e56-9dcb3ec3757f |  | checkpoint | Ensure appropriate detailing is used on terminations
checkpoint-status | 994e0e8f-180b-40dd-8b67-765d6f4ebfb1 |  | checkpoint | Application photos (1 photo per termination)
checklist-flat | a89ea8ab-d63c-4227-b0c8-fb0ce5e545f8 |  | checklist | Document: |  |  |  |  | Yes | Drawings attached | 5aa03855-5563-4fe9-bccf-e081f8585906
checkpoint-status | 700d5cd3-d75b-4707-b6f5-7eb22e64b1b2 |  | checkpoint | Document Attached
checklist-sectioned | 6b4400ab-0583-42d6-b125-f25d50b00cc1 |  | checklist | Coloursteel Roofing |  |  |  |  | Yes | Coloursteel Roofing | 64c23a21-604a-43ec-b35d-2c07fc268a89
checkpoint-group | a3b0a2e3-2918-4ff8-a1c0-257bf3dee0cc |  | section | Prestart
checkpoint-status | 305f7e79-84fb-4d83-887b-428c61a710d4 |  | checkpoint | Edge protection/scaffold in place
holdpoint | ec02f9d7-60ce-46ba-9dcd-2f4ccdb102ff |  | signoff | Raise remedial / request review
checkpoint-status | dd1b3012-efb2-4e6e-901b-65123af0bc70 |  | checkpoint | Safety nets installed
holdpoint | 7837907a-1236-423e-9161-23bf9e2d9c17 |  | signoff | Raise remedial / request review
checkpoint-status | 7d34d829-b9b1-499c-85c6-989178d2a912 |  | checkpoint | Purlins/battens & all necessary timberwork complete
holdpoint | ddfcffe9-bb3f-48d5-827c-3f39126d77cc |  | signoff | Raise remedial / request review
checkpoint-group | 15e35633-d3dd-4679-b2fa-fcc3c59532f9 |  | section | Substrate Checklist : Enviroclad Plywood
checkpoint-status | e32d13eb-eeb8-405d-bee7-f2be37504e86 |  | checkpoint | Framing supports at 400mm centres (in one direction). All plywood edges must also be supported.
label | f0db1618-2c16-50aa-9238-e0b7dd3358a9 |  | note | Do not use tongue and groove plywood. Viking Roofspec can accept the maximum support spacings provided in Table 15C of CHH Ecoply Specification Guide.
checkpoint-status | a8bf9405-4d83-4687-96b1-7db854aa13d5 |  | checkpoint | Minimum thickness 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
checkpoint-status | 9ceedeab-b902-46bd-b1e5-c81103c1df20 |  | checkpoint | Minimum CD grade with the sanded C face upwards.
checkpoint-status | f361cc0c-a4af-4315-b76d-b0a1ee347393 |  | checkpoint | Plywood laid with face grain at right angles to supports.
checkpoint-status | 68e0488f-32f7-44bb-a94a-d3a693ae57e7 |  | checkpoint | Plywood is to be laid with staggered joints in a brick bond pattern with a 3mm expansion gap between plywood sheet edges.
checkpoint-status | 5b8fc8bd-9ff9-4a24-95d0-ac07398ab199 |  | checkpoint | Plywood is screw-fixed with 10g x 50mm SS counter-sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
checkpoint-status | fe3bbb51-94f0-4817-9a29-ec468951a80d |  | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
label | cb7d24cd-b85c-5cd7-81d5-ee00761799af |  | note | *Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18%moisture content.
checkpoint-status | 45687ced-a80a-46d9-8c8b-f7ca2189b514 |  | checkpoint | For Roofs and Roof Decks over living spaces, all cavities must be ventilated and insulated in compliance with clause H1 NZBC. Cavity ventilation is not required for a Warm Roof system which meets or exceeds the minimum R value requirements.
checkpoint-status | e5bc4a53-5321-4ebc-984d-2ef258e7cfef |  | checkpoint | All drains and outlets are membrane compatible.
label | 0afca60d-3dc5-58d0-8cef-7a34ca9bb598 |  | note | Note that TPO membranes cannot be welded to Stainless Steel scuppers or sumps. Accessories must have Clamped Grates or be TPO weldable.
checkpoint-status | cc472b27-f57a-4346-9c75-5fca3c3bfde5 |  | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
checkpoint-group | 08159c01-f64d-48ff-9172-6143ba16ee5f |  | section | Roof QA
checkpoint-status | b4f148c3-1410-4dd8-811a-ee957965ecde |  | checkpoint | Fascia straight, cut in correctly
checkpoint-status | 92292faf-d73e-4c15-827d-ab6f6c0720c5 |  | checkpoint | Spouting installed with correct falls & outlets as per plans
checkpoint-status | 2b41dd4b-d39c-4b25-b00d-2718863d6aa5 |  | checkpoint | Underlay over fascia & trimmed neatly
checkpoint-status | 1680745d-8d51-4125-a77b-02de12439de9 |  | checkpoint | Valleys straight
checkpoint-status | 25fed7f2-afce-483a-9885-0ae84b2eec12 |  | checkpoint | Screws installed correctly & washers intact
checkpoint-status | 9d960cfb-21c2-4c8d-a643-454546105b4e |  | checkpoint | Roof clean from debris & swarf
checkpoint-status | 84b2f37d-6513-4984-a983-a6aaaa9158d8 |  | checkpoint | Flashing junctions tidy & sealed correctly
checkpoint-status | 7108bcdc-1dcd-4b56-bb34-b882312b11fe |  | checkpoint | Roof laid correctly & damage free
checkpoint-status | 6db0cd7d-87d2-4fa8-bfad-274f46475489 |  | checkpoint | Site clean, rubbish in bin or removed
checklist-sectioned | e301fef6-5031-475d-9f74-30dc5305d121 |  | checklist | Torch-On Plywood Checklist |  |  |  |  | Yes | Roofing QA - Torch-On Plywood Checklist | 001ba654-a384-4868-9258-e83c568d3901
checkpoint-group | 8d1e98d6-43b0-4194-8fd1-c6053271d91b |  | section | Substrate Check
checkpoint-status | 91e50886-febd-4b9c-8147-80a00011bbea |  | checkpoint | Framing supports at 400mm centres for 17.5m ply (in one direction). All plywood edges must also be supported.
checkpoint-status | 9822e387-181f-444a-9db9-1d6686266d9f |  | checkpoint | Framing supports at 600mm centres for 19.5m ply (in one direction). All edges must also be supported.
checkpoint-status | a3c7caba-c699-43ab-8fe5-02b9e1d38c7b |  | checkpoint | Minimum 17mm, F8, CCA H3.2 treated, structural plywood (not LOSP treated).
checkpoint-status | a9f25e63-c316-4a0f-b03d-dd9fc3a3c5f0 |  | checkpoint | Plywood screw-fixed with 10g x 50mm SS counter sunk screws at 150mm centres on all sheet edges and at 200mm centres through the body of the sheet. All screws to be counter sunk 1-2mm.
checkpoint-status | 32d6e7e6-99f9-4c8b-92c5-524be6e4b43f |  | checkpoint | Plywood laid with face grain at right angles to supports.
checkpoint-status | e89384f0-0918-4241-8f10-737bbbc64afa |  | checkpoint | Plywood is to be laid with staggered joints in a brick-bond pattern with a continuous bead of suitable construction adhesive on top of timber supports. Sheet edges to be carefully glued with a continuous bead of suitable construction adhesive (no spot gluing) and tight butt-jointed. Once sheets have been placed together remove any excess adhesive by scraping the joint with a chisel. Ensure joints and sheets are not walked on within 2 hours of application. When fully cured remove excess and sand off joints.
checkpoint-status | bfecf290-3f01-4038-b299-7f75f3e476bd |  | checkpoint | Provide min. 20mm timber fillets at the base of all upstands.
checkpoint-status | 5d8b7e6a-0d24-47e2-8c92-48ebad7c233a |  | checkpoint | Chamfer all external edges with a minimum radius of 5mm.
checkpoint-status | dd0ceb95-a30f-4208-9be9-e368d4865d7e |  | checkpoint | Plywood is to be laid with staggered joints in a brick-bond pattern with a continuous bead of suitable construction adhesive on top of timber supports. Sheet edges to be carefully glued with a continuous bead of suitable construction adhesive (no spot gluing) and tight butt-jointed. Once sheets have been placed together remove any excess adhesive by scraping the joint with a chisel.
checkpoint-status | 987da9ca-b404-45ca-80c5-9ed5e11b57a1 |  | checkpoint | Ensure joints and sheets are not walked on within 2 hours of application. When fully cured remove excess and sand off joints
checkpoint-status | e225d91c-9c1f-4269-b024-07dbaa6a826b |  | checkpoint | Plywood is to be kept dry at all times during construction. Blow/ torch drying the plywood surface prior to membrane application does not comply. Plywood and framing supports to be at no more than 18% moisture content.
checkpoint-status | e486ab2e-8e0f-46e6-8143-a1d560c028ba |  | checkpoint | Leave a 5mm minimum expansion gap around the perimeter of the plane. The fixing specification allows for a maximum 50m2 without expansion joints (dependant on design). 5mm expansion joints should be used on areas over 50m2 . For further information regarding placement of expansion joints for your design, please contact your Allco Representative .
checkpoint-status | 63f7aaca-dbd9-469a-a6e5-0d4e390df6a5 |  | checkpoint | Ensure minimum required falls are met. E2/AS1 2011 states 2° for roofs (-1:30 or 34mm/mt), 1.5° for decks (-1:40 or 25mm/mt) and 1:100 (10mm/mt) for internal gutters.
checkpoint-status | 2dbd927f-d007-46b5-88a8-576f2c62f167 |  | checkpoint | All drains and outlets are membrane compatible. Refer to your Allco Representative prior to installation if unsure.
checkpoint-group | fdcd5235-2805-43cb-8fde-813c38f7a7c0 |  | section | Torch-On Horizontal & Vertical Application
checkpoint-status | bac72a24-7916-49f7-af68-1346db9b9c9a |  | checkpoint | Check sheets are correctly aligned, unrolled completely and positioning them
checkpoint-status | 7a8a52a4-5afc-4296-8305-8160bd547b13 |  | checkpoint | Ensure side laps are at least 100mm and at head laps should be 150mm
checkpoint-status | 1f5d29a9-635a-4f93-82c3-1a8e2ea710d6 |  | checkpoint | Ensure dermaprimer is used appropriately on the substrate
checkpoint-status | 0c374dc0-b0ea-4fb0-b589-890c234ff6a7 |  | checkpoint | The second layer fully bonded on to the first layer, staggering the side overlaps by 500mm and the head overlaps by half a roll
checkpoint-status | 937f42c4-689d-472d-8677-75ec00e8ab50 |  | checkpoint | Ensure 150mm upstand height of membrane
checkpoint-status | 4173f0e1-c10e-4e4f-9af8-a81f79f27cad |  | checkpoint | Attach application photos (1 photo per 20m2)
checkpoint-group | 68d545ee-1d61-4a72-abb6-b50bc73a8bc7 |  | section | Torch-On Detailing (Drains, Gutters, Joints, Overflows, Penetrations)
checkpoint-status | b3023129-d61c-4b2f-af55-a3331efa1bc4 |  | checkpoint | Roof Drains & Outlets - appropriate detailing techniques used
boolean | 51b40b76-fa95-5722-a335-3774f53270e0 |  | tickbox | Attach Photos (1 photo per drain/outlet )
checkpoint-status | 20b1c39e-fa95-42af-8c24-d923177a57dd |  | checkpoint | Penetrations - appropriate detailing techniques used
button | 4627ef16-5959-5a0c-b96d-bc21a873a689 |  | button | Ensure 100mm extension from edge of penetration in all sides | Yes, No, N/A
button | ad1bf6be-1edf-510a-bc7f-03e5a26bc52d |  | button | Ensure 100mm upstand extension over pipe | Yes, No, N/A
boolean | fd5606fb-1140-5b4e-8ffe-460d48e94a41 |  | tickbox | Attach Photo (1 photo per penetration)
checkpoint-status | ce1d0f38-3989-4591-8e61-b74c63f681e5 |  | checkpoint | Transitions - appropriate detailing techniques used
button | 38843f71-4737-51b7-8200-1c122fb5e4d7 |  | button | All transitions sharply formed and having no irregular surfaces or edges | Yes, No, N/A
boolean | 8be7613c-5353-54bb-85a0-83cd00e30cc7 |  | tickbox | Application photos of transitions
checkpoint-status | b66a53b2-45f4-4cbb-bd1c-96a3046e2dda |  | checkpoint | Joints - appropriate detailing techniques used
button | 5ae4b605-ef23-585a-b46b-662a84b1913e |  | button | For expansion joints, ensure there is 150mm extension cover over the joint | Yes, No, N/A
boolean | e96c7424-4e02-5129-9539-94704d93f080 |  | tickbox | Application photos (1 photo per joint)
checkpoint-group | cdde9b48-f3c7-48d2-a98c-8384a6edbf72 |  | section | Torch-On Terminations
checkpoint-status | e1ee3865-867e-4755-8dff-b51348378b5c |  | checkpoint | Areas of installation input
text | 1a4141dc-ddf0-552b-924b-dcca1c0c56bf |  | textbox | Description, grid sections, etc
checkpoint-status | 24c9d016-fa9c-40fe-be01-1477e1e906d2 |  | checkpoint | Ensure appropriate 100mm laps at transitions
checkpoint-status | ce273bbd-6546-471b-95de-7f5d1a1cd70b |  | checkpoint | Ensure appropriate detailing is used on terminations
checkpoint-status | c294866b-13bf-4134-ace4-7d248eeeb6dd |  | checkpoint | Application photos (1 photo per termination)
checklist-flat | 12c653a0-db07-40fb-b81d-42401ab2fc45 |  | checklist | QA - Mohan TPO |  |  |  |  | Yes | QA - Mohan TPO | 85ba652f-7c3f-47fd-9dea-dadb98e1a595
checkpoint-no-status | 537cbd6c-359b-4475-a194-fb0a9238bf21 |  | checkpoint | Details
text | 8fe9586b-7ceb-5d99-ba57-0d1d60424327 |  | textbox | Work Area Covered by QC Sheet:
checkpoint-status | 54dd5f0f-0218-4d53-8c6e-324643421322 |  | checkpoint | Substrate clean, dry and free from foreign matter and sharp edges. If in doubt, check substrate moisture.
checkpoint-status | eed0f64a-6a82-4cc9-ab8c-d9824392fde8 |  | checkpoint | Movement joints identified and installed to approved specification/detail.
checkpoint-status | 52fe517d-40e7-49db-858f-706df2862163 |  | checkpoint | Underflashings installed to all corners and upstands.
checkpoint-status | 99ce7da8-f49b-4103-b4d0-c9a648b0f825 |  | checkpoint | All TPO seam-welded with complete lap integrity.
checkpoint-status | f8bf26dc-8142-4a36-81f6-ce099f508061 |  | checkpoint | Gutters correctly and neatly installed, particularly the internal corners - laps above roof line.
checkpoint-status | e23a81fa-e4af-4296-a8cd-67091fb41ed2 |  | checkpoint | Roof drains installed to specification and watertight.
checkpoint-status | df0bfa13-0910-4b1f-b853-2449fc1973e8 |  | checkpoint | Overflows installed to specification and local body requirements and watertight.
checkpoint-status | 29eceb1b-52cf-4b7d-b040-df216eae23a9 |  | checkpoint | Membrane termination completed to approved detail.
checkpoint-status | 138ef2a7-a806-4102-8973-393ca1629c6c |  | checkpoint | All penetration details completed to specification including under/overflashing.
checkpoint-status | 91338e8e-ffb1-4472-a980-139da42c1c80 |  | checkpoint | Overall installation free of wrinkles, creases and splits.
checkpoint-status | de99f566-b11b-494d-915d-e633b3daeb55 |  | checkpoint | Where practical flood test horizontal applications with a minimum 50mm depth of water for 24 hours. Make good any lack of water tightness when the surface is completely dry.
checkpoint-no-status | a0cddf3b-c2a1-4714-9f0c-e44b22ebac64 |  | checkpoint | Additional Notes
text | c01126b7-9f03-5bc7-9c4a-a36cb6a4338c |  | textbox | Issues to note or raised during installation:
text | fa49e097-154e-529d-9f36-a2982bf1c454 |  | textbox | Remedial action required:
text | 84a4009f-7030-5006-9ee5-65b8d3bfdcac |  | textbox | Note of damaged areas repaired:
button | d26dca60-145a-5c76-9583-70181b3e964c |  | button | Photographs taken | YES,NO
date | aea5d178-0eeb-5264-a9e2-4b101225ad3a |  | date | Date of completion
holdpoint | f8a187be-d725-4b73-8d55-ea955eeebb27 |  | signoff | Work Area Sign Off