## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist | INF-HSEQ CC0398-ITP Concrete Pile Cropping Rev A | itp |  |  |  |  | INF-HSEQ CC0398-ITP Concrete Pile Cropping Rev A
section | 1.0 Preliminaries
checkpoint | 1.1 - Starter Bars
label | Acceptance criteria - Are starter bars (if exposed) in suitable condition:
label | – Straight
label | – Free from excessive rust
label | – Correct height projections
button | Acceptance | Yes,No,N/A
label | Frequency - Once per Pile
label | Key - S
section | 2.0 Pile Cropping
checkpoint | 2.1 - Set out
label | Ref docs - DWG No. GRN-92002-030002 – 10
label | Acceptance criteria - Pile cut off has been marked by survey
button | Acceptance | Yes,No,N/A
label | Frequency - Once per pile
label | Key - W
checkpoint | 2.2 - Pre-Cutting (if required)
label | Acceptance criteria - Has the pile been pre-cut along survey marked level i.e. ring cut method
button | Acceptance | Yes,No,N/A
label | Frequency - Once per pile
label | Key - S
checkpoint | 2.3 - Irregular Concrete
label | Acceptance criteria - Large uneven/jagged concrete sections to be removed to create flat concrete cut off level
label | Frequency - Once per pile
label | Key - S
section | 3.0 Conformance check
checkpoint | 3.1 - Tolerance
label | Ref docs - DWG No. GRN-92002-030002 – 10, As per civil (235929) drawings
label | Acceptance criteria - Survey to check actual pile cut off level is within +-+-25mm of cut off level.
button | Acceptance | Yes,No,N/A
label | Frequency - Once per pile
label | Key - S
checkpoint | 3.2 - As Builts
label | Acceptance criteria - Survey to pick up cut off levels for as-builts
button | Acceptance | Yes,No,N/A
label | Frequency - Once per pile
label | Key - S