## checklist
148000 | checklist | S - S - Air conditioning
148001 | section | Pre-start checks
148002 | checkpoint | Area/base/wall ready for outdoor unit
148003 | checkpoint | Pipework route all clear, penetrations complete
148004 | checkpoint | Nogs/ply in place for indoor unit
148005 | checkpoint | Drain 1m from indoor unit location by plumber
148006 | section | First Fix
148007 | checkpoint | Complete length of pipework is insulated and acceptable
148008 | checkpoint | Drain installed and insulated
148009 | checkpoint | Supply cable installed correctly, protected and secured
148010 | checkpoint | Outdoor wall brackets in place
148011 | checkpoint | Interconnecting cables correctly installed and protected
148012 | checkpoint | Mechanical First Fix complete and acceptable
148013 | section | Second Fix
148014 | checkpoint | System pressure checked and still holding pressure and acceptable
148015 | checkpoint | Correct Indoor unit installed, level and tight to wall and acceptable
148016 | checkpoint | Correct Outdoor unit installed and secure
148017 | checkpoint | Indoor unit serial no. recorded
148018 | checkpoint | Outdoor Unit serial no. recorded
148019 | checkpoint | Indoor unit run, fan speeds, modes etc. are acceptable
148020 | checkpoint | Air conditioning Second Fix complete and acceptable
148021 | section | Commissioning
148022 | checkpoint | Installer confirmed commissioned and paperwork submitted
148023 | checkpoint | Commissioning paperwork reviewed and accepted by Project Manager
148024 | checkpoint | Electrical testing complete
148025 | checkpoint | Commissioning complete and acceptable
148026 | checkpoint | Inspections completed and issued to Foreman
148027 | holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
152000 | checklist | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
152001 | section | Pre-start checks
152002 | checkpoint | Area clear, access good, enough space for install
152003 | checkpoint | Duct Route clear, Penetrations completed
152004 | checkpoint | Nogs/Supports in place
152005 | section | First Fix
152006 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
152007 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations&)
152008 | checkpoint | Mechanical First Fix complete
152009 | section | Second Fix
152010 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
152011 | checkpoint | Mechanical Second Fix complete
152012 | section | Commissioning
152013 | checkpoint | Good access to all areas of building
152014 | checkpoint | Power live to Mechanical Plant
152015 | checkpoint | Mechanical Plant commissioned
152016 | checkpoint | Inspections completed and issued to Foreman
152017 | holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
150000 | checklist | S - S - Ventilation - Corridors Ventilation
150001 | section | Pre-start checks
150002 | checkpoint | Area clear, access good, enough space for install
150003 | checkpoint | Duct route clear, Penetrations complete
150004 | checkpoint | Nogs/Supports in place
150005 | section | First Fix
150006 | checkpoint | Access Panel requirements marked up on drawings and submitted to client
150007 | checkpoint | All works from builders or other trades to enable Mechanical First fix to be completed (e.g.. drains, framing, penetrations&)
150008 | checkpoint | Mechanical First Fix complete
150009 | section | Second Fix
150010 | checkpoint | All works from builders or other trades to enable Mechanical second fix to be completed (e.g.. painting, waterproofing...)
150011 | checkpoint | Mechanical Second Fix complete
150012 | section | Commissioning
150013 | checkpoint | Mechanical Plant commissioned
150014 | checkpoint | Inspections completed and issued to Foreman
150015 | holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
149000 | checklist | Apartment Ventilation
149001 | section | Pre-start checks
149002 | checkpoint | Penetrations done in floors and walls (if needed)
149003 | checkpoint | Space for ducting (no trades in the way)
149004 | checkpoint | Pipe through exterior wall installed by RHC to connect to
149005 | checkpoint | Drawings and work scope confirmed
149006 | section | First Fix
149007 | checkpoint | Ductwork run straight level and well supported
149008 | checkpoint | All ductwork joints sealed
149009 | checkpoint | All SAB joints sealed and taped
149010 | checkpoint | All flexible ducts cable tied and taped to duct
149011 | checkpoint | All seismic restraints in place (if needed)
149012 | checkpoint | Flexible ducts fixed in place to grille location
149013 | checkpoint | Grille locations/access panels marked on plans
149014 | checkpoint | Mechanical First Fix complete
149015 | section | Second Fix
149016 | checkpoint | Ceiling fans installed square and level
149017 | checkpoint | Kitchen range hood installed by RHC to connect to
149018 | checkpoint | Fingerprints removed from grilles/walls/ceilings
149019 | checkpoint | Fan plugged in before install to ceiling
149020 | checkpoint | External louver supplied by TSL, installed by RHC completed
149021 | checkpoint | Commissioning form completed & given to TSL
149022 | checkpoint | Mechanical Second Fix complete
149023 | section | Commissioning
149024 | checkpoint | Correct product used as per requirements
149025 | checkpoint | Correct design followed as per drawings
149026 | checkpoint | Mechanical Plant commissioned
149027 | checkpoint | Inspections completed and issued to Foreman
149028 | holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS
151000 | checklist | S - S - Kitch Extraction
151001 | section | Pre-start checks
151002 | checkpoint | Area clear, access good, enough space for install
151003 | checkpoint | Duct Route clear, Penetrations completed
151004 | checkpoint | Nogs/Supports in place
151005 | section | First Fix
151006 | checkpoint | Fan installed straight and level and correct orientation
151007 | checkpoint | Correct Fan installed
151008 | checkpoint | Fan seismically braced and vibration isolated
151009 | checkpoint | Inspections completed and issued to Foreman
151010 | holdpoint | CLICK AND SEND EMAIL TO FOREMAN TO SIGN FOR RECEIPT OF THE INSPECTION RESULTS

## breakdown
Keith Park(Thermal Solutions) | Tier 1 | Tier 2 | Tier 3 | Tier 4
Site QA
B07
Fitout
Basement
Stair Lobby
[6 empty] | Ventillation |  | Prepopulate | S - S - Ventilation - Corridors Ventilation
Lift Lobby
[6 empty] | Ventilation |  | Prepopulate | S - S - Ventilation - Corridors Ventilation
Carpark
[6 empty] | Jet Fans |  | Prepopulate | S - S - Ventilation - Carpark Ventilation - Jet Pulse Fan
Ground Floor
Common Area
Corridor
[7 empty] | Ventillation | Prepopulate | S - S - Ventilation - Corridors Ventilation
Storage
[7 empty] | Ventillation | Prepopulate | S - S - Ventilation - Corridors Ventilation
Service Area
Coms
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Corridoors Ventilation
Riser
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Corridoors Ventilation
Apartments
G50
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
G51
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
G52
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
G53
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
G54
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
G55
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
G56
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
G57
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
Level 1
Common Area
Corridor
[7 empty] | Ventillation | Prepopulate | S - S - Ventilation - Corridors Ventilation
Storage
[7 empty] | Ventillation | Prepopulate | S - S - Ventilation - Corridors Ventilation
Service Area
Coms
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Corridoors Ventilation
Riser
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Corridoors Ventilation
Appartments
150
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
151
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
152
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
153
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
154
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
155
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
156
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
157
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
Common Area
Corridor
[7 empty] | Ventillation | Prepopulate | S - S - Ventilation - Corridors Ventilation
Storage
[7 empty] | Ventillation | Prepopulate | S - S - Ventilation - Corridors Ventilation
Service Area
Coms
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Corridoors Ventilation
Riser
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Corridoors Ventilation
Level 2
Appartments
250
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
251
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
252
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
253
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
254
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
255
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
256
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
257
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
Level 3
Common Area
Corridor
[7 empty] | Ventillation | Prepopulate | S - S - Ventilation - Corridors Ventilation
Storage
[7 empty] | Ventillation | Prepopulate | S - S - Ventilation - Corridors Ventilation
Service Area
Coms
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Corridoors Ventilation
Riser
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Corridoors Ventilation
Appartments
350
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
351
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
352
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
353
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
354
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
355
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
356
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
357
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
Level 4
Common Area
Corridor
[7 empty] | Ventillation | Prepopulate | S - S - Ventilation - Corridors Ventilation
Storage
[7 empty] | Ventillation | Prepopulate | S - S - Ventilation - Corridors Ventilation
Service Area
Coms
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Corridoors Ventilation
Riser
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Corridoors Ventilation
Appartments
450
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
451
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
452
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
453
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
454
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
455
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
456
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning
457
[7 empty] | Ventilation | Prepopulate | S - S - Ventilation - Apartment Ventilation
[7 empty] | Extract Fan | Prepopulate | S - S - Kitch Extraction
[7 empty] | Air conditioning | Prepopulate | S - S - Air conditioning