## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
49f0dbee-1eee-5066-9e10-55f645b0d776 | checklist | Checkers Checklist |  | Checkers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
874016de-78a4-57f6-a2f9-02d7a2c46cf9 | checkpoint | Overall Measurements
8c05118a-72bf-5cc6-9db8-0357eb3df369 | checkpoint | Void Correct Position
db685d83-82de-508b-8d5d-fbddbaa7c92b | checkpoint | Ferrules - Measurements & Size - NS / FS
ead16306-b9a2-52f3-9418-abbf7b95e1b6 | checkpoint | Lifters Correct - Position, Size, Orientation
386fdee2-f5a2-549a-b489-12072dfa1511 | checkpoint | Fillet is Installed
5d2c77bf-d9b1-5dee-872f-d4f74be58779 | checkpoint | Check Concrete cover around Reo - 40mm
8fb5ae5c-0bb9-5e51-98a2-50ab5ee5ba60 | checkpoint | Panel Thickness confirmed - 200mm-340mm
25f3f42f-ad00-5039-b754-c9fe52db7e90 | checkpoint | Magnets are 100% Secure
98f353b7-0ef0-4bcb-a050-ad3e8876824c | checkpoint | Cure Applied
b9c2bd3a-17e5-5567-a17f-ecdf94a1c588 | checkpoint | Panel is Clean
ffda0709-ec2c-50eb-852b-5111a66a8781 | checkpoint | Photo Taken
18dc5f7a-230d-5da0-bdf6-853dbdf10694 | checklist | Installers Checklist |  | Installers Checklist
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
f4b76f1e-6cd9-562b-b108-5581201d776a | tickbox | 5T 120 Foot Anchors (2)
a252816a-2226-53e7-9141-b23aefffb327 | tickbox | 5T 170 Foot Anchors (2)
b992ca2c-08ae-51b3-9f09-fae3277b82c9 | tickbox | Ferrules - M20 (4)
7fcfb720-5337-583a-801e-134629bf7070 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
0d640038-1524-4f32-b06b-a98c855480f7 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
56aa3f1b-656d-5257-8224-050963a8196a | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
6b8a3aa0-7d81-5444-b750-bf645e309021 | checklist | Installers Checklist [extra ferules] |  | Installers Checklist [extra ferules]
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
109ae7d1-0278-5525-8bda-80da64a2b4cc | checkpoint | Complete Material "Bucket List"
af71741f-50ce-5e46-a31e-3b85b73f7c1d | tickbox | 5T Face Lifter (2)
600be304-2257-597a-9c69-928e96b36aa7 | tickbox | Ferrules - M20 (6)
c4ab563c-f1e9-5ae9-b40f-7b0ac3dc7507 | tickbox | ID Plate (1)
9eb8e239-00d9-5022-8c12-c351fa59e086 | checkpoint | Flick-out Panel Dimensions & DOUBLE CHECK
36c69184-1358-566a-b73c-b77f90cd15f1 | checkpoint | Apply bond breaker or wax 1 2 3
f475a17a-3961-536a-93e3-06338bd3a309 | checkpoint | Temporary Fix ID Plate to Formwork
0554993b-415c-5c70-b2c1-d97e4d3267ee | checkpoint | Use Aluminimum Formwork on Top Sides & Timber on Bottom Edge
bcef6a9d-826a-5a7a-bc2a-47f3ff147616 | checkpoint | Install Reo as-per Shop Drawing Plan
730fdf85-be2f-54f7-8ad5-1791c6f5dbf8 | checkpoint | Lifters to be Firm & Square against Formwork
ec154433-82f4-5131-8bbd-f038da7dd639 | checkpoint | Check Concrete cover around reo - 30mm
eeaa5eba-36d9-52ba-be11-0d77d59ebfdd | checkpoint | DOUBLE CHECK EVERYTHING
8ba55d3e-27aa-56d9-aef7-a4a04391c867 | checkpoint | Finish Required - GOOD as near face is outside face of building
d29b4c88-498d-4d81-82b8-4df4af67b940 | checkpoint | Apply Cure
cffb1cd8-bc46-59dd-ad38-bd733e35b4f5 | checkpoint | QA - Final Check of ALL measurerments & Photos
47d8ef19-23fb-53ec-bc0d-d72318ee54a1 | checkpoint | QA - Concrete Mix N40 Panel Mix
5d5e2ce3-2c4b-50e1-b811-24fd824d75f7 | checkpoint | QA - Check Concrete mix % before accepting. Allow enough mix time.
eb8dc484-15a1-5bb0-83fe-9542c3dccbd0 | checkpoint | CONCRETE TEST TAKEN
f0f6a7c6-7a3c-5a3c-beb6-26489991e1d4 | date | Pour Date
d557b6a5-e809-541e-b46b-9ca8a21aa575 | checkpoint | NOT TO BE POURED WITHOUT APPROVAL FROM ENGINEER
834014e9-84c1-5bd8-9a12-212cd800dd83 | checklist | Precast Components ITP |  | Precast Components ITP
6cd7eeb6-6eaa-576a-ba51-6df4cda0fddf | section | Manufacturing Documents
e96fec78-8ab7-5430-b7d8-cef12e74735e | checkpoint | Shop drawings reviewed and updated. Issued "As For Construction"
99f02884-0fc1-5dff-bb6a-45eb18afc632 | section | Pre-Pour Checks
49165423-2f41-5149-b81e-cbde87e49388 | checkpoint | Final Inspection - all placed in accordance with approved shop drawings
03360041-0315-5dbe-b399-5eaeea6b1f02 | tickbox | 5T 120 Foot Anchors (2)
8e5cbe99-5c90-5709-8ab4-da834c1ec03b | tickbox | 5T 170 Foot Anchors (2)
d51116b1-c894-53bf-a675-ce05e252b1dd | tickbox | Ferrules - M-20 (4)
799aa4a9-7b86-5d4c-bb9a-014374d8b3b7 | tickbox | Reinforcement
1d4cb2d3-ae8f-5b49-9e62-43e7b2288173 | tickbox | ID Plate (1)
ca9dd377-c97a-5393-ab69-1f5a93636ba2 | tickbox | 40 Panel Mix
1163715e-029e-58e9-abb1-0d7c465feeae | checkpoint | Upload sufficient number of photos pre pour
a614158b-31b9-5b16-a0ef-c7887449a5c9 | section | Concrete Pour Checks
ffb80e0b-4502-5f63-80b4-aeb30f63940f | checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
09176935-e4bb-556c-8462-fdf9b702c583 | tickbox | All Concrete Dockets Attached
e8adbc84-b448-5119-bc35-7edd8200d05f | section | Installation
8a65ca4c-14f0-57a0-b78a-e60252fa0ba4 | checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
9939c6bd-e771-5fc8-bb82-40e867acf0f9 | checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
2b06d77c-d942-57e5-bce4-a402092e6f0e | tickbox | Set out
a0fc461c-67eb-53d4-a516-2405db0d8b09 | tickbox | Core Holes
6ed43976-3868-5378-893d-ff231abb539a | tickbox | Install dowels
35962be0-c2f1-5298-ad20-b4dc89a5a6fd | checkpoint | Installation of precast panels including backpropping. Correct location, connections, finish confirmed against shop drawings.
f4245d08-5a41-52a0-82fd-3dc1f2509f8b | checkpoint | Grouting and sealing
f790cc3b-083a-5b9d-b491-f78676fc718e | checkpoint | Remove backpropping when instructed by consulting Engineers.
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | section | Final Inspection
862f87ce-dc9d-52f2-9938-dbec78456812 | checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
87e8f44c-9253-51bc-9912-f2c845459e9f | checklist | Precast Components ITP [extra ferules] |  | Precast Components ITP [extra ferules]
6cd7eeb6-6eaa-576a-ba51-6df4cda0fddf | section | Manufacturing Documents
e96fec78-8ab7-5430-b7d8-cef12e74735e | checkpoint | Shop drawings reviewed and updated. Issued "As For Construction"
99f02884-0fc1-5dff-bb6a-45eb18afc632 | section | Pre-Pour Checks
49165423-2f41-5149-b81e-cbde87e49388 | checkpoint | Final Inspection - all placed in accordance with approved shop drawings
cdfc1383-640f-5f5a-bdbe-27951fbf59be | tickbox | Face Lifter 5T (2)
9be97080-20f8-56ed-9f54-068bfadd6c4d | tickbox | Ferrules - M-20 (6)
dd41388d-49ec-528d-81ef-ae41e22448b3 | tickbox | Reinforcement
70840fc1-83cd-57a3-8cc6-c5d1cd4964fa | tickbox | ID Plate (1)
c4e0f11f-3e02-5dc6-a935-863479823a22 | tickbox | 40 Panel Mix
1163715e-029e-58e9-abb1-0d7c465feeae | checkpoint | Upload sufficient number of photos pre pour
a614158b-31b9-5b16-a0ef-c7887449a5c9 | section | Concrete Pour Checks
ffb80e0b-4502-5f63-80b4-aeb30f63940f | checkpoint | Concrete Strength correct as per Construction Sciences Concrete Compressive Strength Report
97cf5fe0-5d34-59bc-be35-f58d7c6429e7 | tickbox | All Concrete Dockets Attached
e8adbc84-b448-5119-bc35-7edd8200d05f | section | Installation
8a65ca4c-14f0-57a0-b78a-e60252fa0ba4 | checkpoint | All PPE and safety requirements in place. Machinery inspections complete.
9939c6bd-e771-5fc8-bb82-40e867acf0f9 | checkpoint | Notification of Inspection - all in accordance with approved shop drawings, correct size and location
2c2cbf8c-3c1d-5897-858d-8d1a8db2a9c1 | tickbox | Set out
a10b4b84-a985-5ebe-acee-e6cef59de502 | tickbox | Core Holes
baba1f7e-23f2-54d6-b100-eebdca9e4e68 | tickbox | Install dowels
35962be0-c2f1-5298-ad20-b4dc89a5a6fd | checkpoint | Installation of precast panels including backpropping. Correct location, connections, finish confirmed against shop drawings.
f4245d08-5a41-52a0-82fd-3dc1f2509f8b | checkpoint | Grouting and sealing
f790cc3b-083a-5b9d-b491-f78676fc718e | checkpoint | Remove backpropping when instructed by consulting Engineers.
e4df1e76-54d1-5b97-b96b-bf3da9d4c209 | section | Final Inspection
862f87ce-dc9d-52f2-9938-dbec78456812 | checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.