## LEVEL 0
Atlas Head Office
Level 0
Atlantic 48mm Seismic Windows
Atlantic 48mm | Atlantic 48mm | Atlantic 48mm | Atlantic 48mm | Atlantic 48mm | Atlantic 48mm | Atlantic 48mm | Atlantic 48mm
W001 | W002 | W003 | W004 | W005 | W006 | W007 | W008
159 Flush Glaze into Seismic
W009 | W010 | W011
159 Flush Glaze into Seismic
W012 | W013 | W014
Channel Glazing to Wind Lobby
WL01 | WL02 | WL03 | WL04

## LEVEL 1
Atlas Head Office
Level 1
Atlantic 48mm Seismic Windows
Atlantic 48mm
W101
159 Flush Glaze into Seismic
W102 | W103 | W104 | W105 | W106 | W07

## LEVEL 2
Atlas Head Office
Level 2
159 Flush Glaze into Seismic
W201
Atlantic 48mm Seismic Windows
Atlantic 48mm
W202 | W203 | W204 | W205

## ROOF
Atlas Head Office
Roof
Rooflight

## Checklists
type
checklist | Prestart | Once per level
checkpoint | Opening correct, rebates, drip grooves
checkpoint | Area clear, tidy and accessible
checkpoint | Building wrap correctly installed
checkpoint | Flashing tape correctly installed
checklist | Handover | Once per level
checkpoint | Item inspected and damage free
checkpoint | Area and item left clean and tidy
checkpoint | Protection tapes and films installed
checkpoint | Item inspected, all elements checked, correct, functioning and approved
checkpoint | Windows left clean
checkpoint | Remedial list completed
checklist | Atlantic Windows /Seismic Frames
Factory QA
checkpoint | Correct packings and sufficient at fixings
checkpoint | Reveal material correct size (TWT) and undamaged |  | Not Applicable
checkpoint | Reveal grooves correct size and location for linings |  | Not Applicable
checkpoint | Seismic frame installed, confirm correct fixings and oversealed
Insert frame installed correctly, and wedged off
checkpoint | Head flashing installed |  | Not Applicable
| WANZ Bars installed |  | Not Applicable
checkpoint | Openings correct and operational |  | Not Applicable
checkpoint | External - sealants and air seals installed correctly with perf rod
checkpoint | Internal - sealants and air seals installed correctly with perf rod
checkpoint | Hardware installed and operational |  | Not Applicable
checkpoint | Manifestation installed |  | Not Applicable
checkpoint | Glazing completed correct to specification including wedging
checkpoint | External head and jamb angles fited and sealed
checklist | Altantic Sliding Doors QA
checkpoint | Correct packings and sufficient at fixings |  | Not Applicable
checkpoint | Reveal material correct size (TWT) and undamaged |  | Not Applicable
checkpoint | Reveal grooves correct size and location for linings |  | Not Applicable
checkpoint | Frame installed correctly |  | Not Applicable
checkpoint | Head flashing installed |  | Not Applicable
| WANZ Bars installed |  | Not Applicable
checkpoint | Openings correct and operational |  | Not Applicable
checkpoint | Sealants and air seals installed correctly with Perf rod |  | Not Applicable
checkpoint | Hardware installed and operational |  | Not Applicable
checkpoint | Manifestation installed |  | Not Applicable
checkpoint | Glazing completed correct to specification including wedging |  | Not Applicable
159mm Flush Glaze / Seismic Frames
Factory QA
Correct packings and sufficient at fixings
| Reveal material correct size (TWT) and undamaged |  | Not Applicable
| Reveal grooves correct size and location for linings |  | Not Applicable
checkpoint | Seismic frame installed, confirm correct fixings and oversealed
Install 228157 sub sill into sismic sill tray. Main M14 sill fixings, and over seal. Install Gutter Sleeve with correct fixing and seals.
Check steel box stiffener (75 x 50 x 6mm) is inserted into mullions correctly
Check mullion hanger brackets are securly bolted to mullions and over sealed
Insert frame installed correctly, and wedged off
Install S/S head angle bracket to head at each mullion with M12 x 150 screwsand over seal
| Openings correct and operational |  | Not Applicable
checkpoint | External - sealants and air seals installed correctly with perf rod
checkpoint | Internal - sealants and air seals installed correctly with perf rod
Commercial Doors fited
Hardware installed and operational
Level 2 steel hanger brackets bolted to slab and alinginded correctely
Level 2 steel hanger bracket washers welded off and p[ainted
Upper level aluminium hanger brackets alingened correctly and fixed off
| Manifestation installed |  | Not Applicable
Glazing completed correct to specification including wedging were required
External flashings installed correctly with all fixings over sealed
Channel Glaziong to Lobby
Factory QA
Correct packings and sufficient at fixings
| Reveal material correct size (TWT) and undamaged |  | Not Applicable
| Reveal grooves correct size and location for linings |  | Not Applicable
Frame installed with correct fixings at correct centres. All fixings oversealed.
checkpoint | External - sealants and air seals installed correctly with perf rod
checkpoint | Internal - sealants and air seals installed correctly with perf rod
| Commercial Doors fited |  | Not Applicable
| Hardware installed and operational |  | Not Applicable
| Manifestation installed |  | Not Applicable
Glazing completed correct to specification including wedging
External flashings installed correctly with all fixings over sealed
Rooflight
Factory QA
Correct packings and sufficient at fixings
| Reveal material correct size (TWT) and undamaged |  | Not Applicable
| Reveal grooves correct size and location for linings |  | Not Applicable
Frame installed with correct fixings at correct centres. All fixings oversealed.
checkpoint | External - sealants and air seals installed correctly with perf rod
checkpoint | Internal - sealants and air seals installed correctly with perf rod |  | Not Applicable
| Commercial Doors fited |  | Not Applicable
| Hardware installed and operational |  | Not Applicable
| Manifestation installed |  | Not Applicable
Glazing completed correct to specification including wedging
External flashings installed correctly with all fixings over sealed