## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Prestart
section | Details
checkpoint | Opening correct, rebates, drip grooves
checkpoint | Area clear, tidy and accessible
checkpoint | Building wrap correctly installed
checkpoint | Flashing tape correctly installed
checklist | Handover
section | Details
checkpoint | Item inspected and damage free
checkpoint | Area and item left clean and tidy
checkpoint | Protection tapes and films installed
checkpoint | Item inspected, all elements checked, correct, functioning and approved
checkpoint | Windows left clean
checkpoint | Remedial list completed
checklist | Atlantic Windows / Seismic Frames
section | Details
checkpoint | Factory QA
checkpoint | Correct packings and sufficient at fixings
checkpoint | Seismic frame installed, confirm correct fixings and oversealed
checkpoint | Insert frame installed correctly, and wedged off
checkpoint | External - sealants and air seals installed correctly with perf rod
checkpoint | Internal - sealants and air seals installed correctly with perf rod
checkpoint | Glazing completed correct to specification including wedging
checkpoint | External head and jamb angles fited and sealed
checklist | 159mm Flush Glaze / Seismic Frames
section | Details
checkpoint | Factory QA
checkpoint | Correct packings and sufficient at fixings
checkpoint | Seismic frame installed, confirm correct fixings and oversealed
checkpoint | Install 228157 sub sill into sismic sill tray. Main M14 sill fixings, and over seal. Install Gutter Sleeve with correct fixing and seals.
checkpoint | Check steel box stiffener (75 x 50 x 6mm) is inserted into mullions correctly
checkpoint | Check mullion hanger brackets are securly bolted to mullions and over sealed
checkpoint | Insert frame installed correctly, and wedged off
checkpoint | Install S/S head angle bracket to head at each mullion with M12 x 150 screwsand over seal
checkpoint | External - sealants and air seals installed correctly with perf rod
checkpoint | Internal - sealants and air seals installed correctly with perf rod
checkpoint | Commercial Doors fited
checkpoint | Hardware installed and operational
checkpoint | Level 2 steel hanger brackets bolted to slab and alinginded correctely
checkpoint | Level 2 steel hanger bracket washers welded off and p[ainted
checkpoint | Upper level aluminium hanger brackets alingened correctly and fixed off
checkpoint | Glazing completed correct to specification including wedging were required
checkpoint | External flashings installed correctly with all fixings over sealed
checklist | Channel Glazing to Lobby
section | Details
checkpoint | Factory QA
checkpoint | Correct packings and sufficient at fixings
checkpoint | Frame installed with correct fixings at correct centres. All fixings oversealed.
checkpoint | External - sealants and air seals installed correctly with perf rod
checkpoint | Internal - sealants and air seals installed correctly with perf rod
checkpoint | Glazing completed correct to specification including wedging
checkpoint | External flashings installed correctly with all fixings over sealed
checklist | Rooflight
section | Details
checkpoint | Factory QA
checkpoint | Correct packings and sufficient at fixings
checkpoint | Frame installed with correct fixings at correct centres. All fixings oversealed.
checkpoint | External - sealants and air seals installed correctly with perf rod
checkpoint | Glazing completed correct to specification including wedging
checkpoint | External flashings installed correctly with all fixings over sealed