## ITP-xxx
|  |  | Inspection and Test Plan - Control and Supervision of the Works | [7 empty] | Document # ITP-029
[11 empty] | Revision : 00 | Date: 30/04/24
Client: |  | MRPA |  | Construction Process: |  | Prepared by: |  | Reviewed by : |  |  | Approved by :
Project: |  | Watergardens Carpark Project |  | TGSI Installation |  | Name: | Jake Cardillo | Name: | Patrick Fagan |  | Name: Shaun Kent
Contract No: |  | 7432000 |  | Specifications: Manufacturer Specification, AS1428
|  |  |  | Structure / Component: |  | Signed : |  | Signed : |  |  | Signed :
|  |  |  | Location: Watergardens Carpark |  | Date : 30/04/24 |  | Date : 30/04/24 |  |  | Date : 30/04/24
Lot No: |  |  | Lot Details: | [5 empty] | Lot Size/ Quantity:
Item | Task/Activity Description |  | Inspection / Controls and Verification Detail |  |  |  |  | HP/ WP/ AP/ IP/ TP/ SCP | Responsibility | Checked by:
No. |  |  | Frequency | Acceptance Criteria | Reference Documents | Inspection / Test Method | Record of conformity |  | Project Engineer Site Engineer Superintendent Surveyor Foreman | Client | Fulton Hogan | FH's Sub-contractor | Date
1 | Preliminary Works
1.1 | Check for Correct Documentation |  | Prior to Commencing Activity | •Ensure that employees and sub-contractors are using the most current and complete set of drawings | Contract Drawings and Registers | Visual Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.2 | Implementation of all measures and controls |  | Prior to Commencing Activity | •All necessary measures and controls are being implemented, including: EMP, TMP, SWMS and WP | EMP, TMP, SWMS, WP | Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
1.3 | Check Materials |  | Prior to Commencing Activity | •Inspect delivered materials for any chips, cracks or other visible damage. | Receivable Inspection List | Visual Inspection | This ITP Signed off | HP* | Fulton Hogan Engineer | N/A |  | N/A
1.4 | Setting out |  | Each Lot | •Line and level of reinstated bluestone kerbing shall be set out according to design levels. •Line and level of tactiles shall be set out according to design levels to suit new kerb height (if applicable). | Work Procedure | Inspection | This ITP Signed off | WP | Fulton Hogan Engineer, Client |  |  | N/A
2 | Construction of Access Ramp Bluestone Footpath
2.1 | Base preparation |  | Each lot | TGSI should be laid in accordance with the site specific application and applicable standards before fixing | IFC Drawings | Visual Inspection | This ITP signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
2.2 | Placement of TGSI |  | Each lot | Ensure the placement of the TGSI are in accordance with IFC drawings and are compliant to AS1428. | IFC Drawings | Visual Inspection | This ITP Signed off | HP | Fulton Hogan Engineer | N/A |  | N/A
3 | Completion
3.1 | Completion |  | Each lot | Ensure pavement area is free of debris and waste. | Visual Inspection | Visual Inspection | This ITP Signed off | IP | Fulton Hogan Engineer | N/A |  | N/A
Final Inspection
The signature below verifies that this ITP has been completed in accordance with the FH’s Quality system Procedures and verifies lot compliance with specifications.
| Print Name: |  | Position: |  | Signature: |  |  |  |  | Date: / /
Legend
HP | Hold Point | Work shall not proceed past the HP until released by the Superintendent |  |  | IP | Inspection point |  | Formal Inspection to be done and recorded
HP* | FH Hold Point | Work shall not proceed past the HP* until released by FH |  |  | TP | Test Point |  | Product compliance test to be undertaken and recorded/reported
WP | Witness Point | An inspection which must be witnessed by the Superintendent |  |  | SCP | Survey conformance point |  | A qualified surveyor to check product/section/structure and report
AP | Approval Point | Written or verbal approval given by the Superintendent
Note on K16: Rodrigo Anchico: Write "N/A" to disable the cell.