## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITC - Concrete Pour Record | [5 empty] | ITC - Concrete Pour Record
section | Preliminaries
checkpoint | Survey - Sufficient survey set out information is available.
checkpoint | Survey - Correct line and level for placement of concrete
checkpoint | Material Delivery - Items conform with the applicable Australian Standard/s
label | Comments / Records - Delivery Docket, Supplier’s Certificate of Compliance
checkpoint | Material Delivery - Items delivered with no visible signs of damage
label | Comments / Records - Delivery Docket, Supplier’s Certificate of Compliance
section | Pre-Pour Check (to be completed by Engineer or Supervisor)
checkpoint | Confirm Dimensions - Visual Check and Measure dimensions are correct for trench width or Thrust Block dimensions
label | Comments / Records - Measure onsite
checkpoint | Initial pour against ground - Surface free of water and soft spots
checkpoint | Initial pour against ground - Hardstand/ ground suitable for concrete pump location
checkpoint | Initial pour against ground - 50mm blinding UNO
checkpoint | Initial pour against ground - If for Thrust Block no loose Material
checkpoint | Construction joints & surfaces - Clean and free of laitance, scabble where required.
checkpoint | Reinforcement - Installed as per IFC drawings. Type, size, position, chairs, cover all as specified & within tolerance; laps and splices as specified. Extra tie wire on splice bars around construction joints and wedges fixed to support splice bars in stop end formwork.
label | Cover (mm):
bool | 50mm above obvert
bool | 75mm ground clearance
bool | Reo Count:
checkpoint | Cast-in items, block outs and hold down bolts - Type, quantity and location as per design.
checkpoint | Final inspection - Pour arrangements agreed and equipment adequate
checkpoint | Final inspection - Surface free of water, dust, debris and stains.
section | Concrete Pour (to be completed by Engineer or Supervisor)
checkpoint | Correct Batch / Grade of Concrete - Visual Acceptance of the docket prior to pouring
checkpoint | Concrete quality - Visual assessment of quality - note details of any loads rejected
checkpoint | Concrete Testing (Vertical Crest Thrust Block) - 3 sample Cylinder taken (7day and 2 X 28 day tests)
checkpoint | Concrete Testing (All Other Concrete Pours) - 3 sample Cylinder taken (7day and 2 X 28 day tests)
checkpoint | Compaction Method
bool | Pencil vibrators
textbox | 2 No
checkpoint | Signed: Engineer / Supervisor
holdpoint | Signed:
section | Post Pour Check (to be completed by Engineer or Supervisor)
checkpoint | Curing of exposed surfaces - Exposed surfaces cured
bool | Polyethylene sheeting (edges / laps sealed, 300mm min laps)
bool | Curing compound
bool | Water curing (continuous spraying, ponding, wet Hessian)
checkpoint-no-status | Location of embedment, hold down bolts and penetrations - All embedded items, hold down bolts and penetration located in accordance with drawings
label | Refer defects list below
label | Details of defects – cracking in slab pours and Inspection of repairs.
label | Finish concrete surfaces inspected by Supervisor. Within specification tolerances (≤ 0.2mm)
label | All defects repaired
bool | Cracks requiring repairs observed
bool | Refer to attached location plan
textbox | RFI
bool | Repairs in accordance with approved specification.
textbox | Comments / Records - Type of surface finish:
checkpoint | Witness Point
holdpoint | Engineer / Supervisor
checkpoint-no-status | Details of other defects
button | Defects listed and NCR raised | Yes,No
textbox | NCR #
checkpoint | Final inspection: All work completed accordance with applicable procedures, drawings, specifications and approved changes
signoff | Close out - Engineer
section | Concrete Pour Record
checkpoint-no-status | Details
textbox | CH Location
textbox | Mix (MPA)
date | Date
button | Concrete Pour Type | Thrust Block,Encasement
textbox | Truck Rego/ No.
textbox | Docket No.
textbox | Quantity (m3) - Truck
textbox | Quantity (m3) - Cum.
textbox | Batch Time
textbox | Finish Time
textbox | Discharge Time within 90mins
textbox | Measured Slump (mm) - 1
textbox | Measured Slump (mm) - 2
textbox | Cylinder Test No
textbox | Remarks
checkpoint | Signed: Engineer / Supervisor
signoff | Signed: