## Project Checklist Templates
Id | Type | Name | Values | Prompting Name
19eaed5f-9299-43de-aa83-48bc624939a2 | checklist | Ford St - Structural Rehab ITP | itp | Ford St - Structural Rehab ITP
a15f1540-4834-4927-b126-6d6fd40e1de3 | section | Subgrade
f5939035-785f-49de-901d-ebb79978a718 | checkpoint | 1.01 - Field
2ac28cb8-63d0-57db-acfc-0311804e1415 | note | Material Test Method Requirement - Scala Penetrometer, Cohesive soils only
eba18840-63ff-5e5e-b7da-b4d3155f8344 | note | Reference Documents - RITS Table 3-20
2bc35191-cce7-51f6-a6f7-8271d2061a69 | note | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
8881b0a9-e07f-5683-9141-8d7204dbe04f | note | Material Test Frequency - 1m inside of edge of seal and along centerline, Both lanes, at 10m spacing
383a30bb-7812-5c90-9482-8221fc217bb8 | note | ○ Minimum of 10 tests and/or at a frequency of 2 test per 10m chainage, whichever qty is greater
337cbf8b-2edf-5053-b09f-7dfb77510ea2 | note | Target Criteria - Confirm design assumptions - Scalar reaches minimum 2 blows/100mm
85f1b314-9368-5b33-808a-ff30e0d1612f | note | Action Point Records required - Test Record
6a23704f-ce35-5d2d-9544-9a34c6e5ce3c | note | Responsibility - QA / SE
54e9c2d5-dc0e-486d-a787-cca2f8766055 | checkpoint | 1.02 - Field
67358bae-608f-5fa5-a4bc-d188e06d671d | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
d0765a16-270a-520b-b58e-2ad0381947d6 | note | Reference Documents - RITS Table 3.24
e41babfd-9190-53c2-b989-81c732c96622 | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
e7a8d0de-9e78-5e63-a0ac-205505b4ba54 | note | Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency
1d93a08b-986f-5e13-8394-324202274ef3 | note | ○ Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
2251354b-80e8-5348-a35e-6bfd2d48544d | note | Target Criteria - +0mm/-30m from design or nominated level
c2364147-e31e-56ef-9ce1-4ec1e389086f | note | ○ No more than 15mm deviation from a 3m straight edge
0982b80f-74f7-5c9a-99c7-78916f48c58f | note | Action Point Records required - Survey record
b691d257-fa9f-5adb-8566-5c4f57250895 | note | Responsibility - QA / SE
d2c56014-2677-46ff-b1b8-a0ce5321ef0f | checkpoint | 1.03 - Field
1ceb4e56-6410-5fb3-a982-e979fb6a6fee | note | Material Test Method Requirement - Geogrid and Geofabric (cloth) installation
0353856e-e932-53c7-8f6a-ad48c4275b98 | note | Reference Documents - ISO:G 032 Version 2
379416d8-7415-5922-9862-8bd09fa45726 | note | Material Acceptance Criteria (Method) - Manufracture installation instructions
aa16e358-bea5-58fd-b7ef-3632a103772c | note | Material Test Frequency - 100% of Surface
1ff9a694-1adc-568b-9f93-6b51c458bc2c | note | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints.
3fb1a7cd-dfb7-5a55-b9cf-86003aa7b504 | note | ○ Geogrid and Geofabric shall be neatly installed without creases or folds.
fd9a4ea4-4dd0-559a-b9f6-4ec3f89f9fce | note | Action Point Records required - Site Record
e94e4a98-1171-5618-af63-bf6f686ee139 | note | Responsibility - QA / SE
a1b899cf-54b3-4116-9317-324fc5f1dffb | checkpoint | 1.04 - PE
7e96ed28-ae34-5eab-9f9f-7a056f1019cd | note | Material Test Method Requirement - Is the layer closed out ?
555eef89-a81b-527e-96e4-03f9475b3df6 | note | Reference Documents - See PQE
a2210085-673b-5b0f-ace5-758597e9b456 | note | Material Acceptance Criteria (Method) - See PQE
78f2bc5e-a07c-552e-adf8-7cfc4f3584a9 | note | Material Test Frequency - 100% of Surface Prior to placement of material
c9e7b0fc-f6b8-5436-ba37-8cab49211910 | note | Target Criteria - PQE Approval
e7db6443-08c8-5395-ac66-0502e81a5d07 | note | ○ All testing record & reviewed as compliant.
d165c685-566e-5b81-b821-2dc4d391dfe9 | note | Available Documents:
8e960d34-4f54-570a-ab12-9c14e302bf1c | note | ○ Test records
78a0475a-73e8-5f03-beb8-69b67cd9cae9 | note | ○ Survey records
7599fdd5-d2c5-5347-b144-45a7f5a7b3b5 | note | ○ Hold Point Records
f806f87a-41fa-5938-ac48-def45ab8872a | note | Action Point Records required - Hold Point
8e7bb529-a84d-50fc-999a-08b8eaea09d3 | note | Responsibility - PM
3e131c4c-ab1e-4069-b41e-ccc4472aa729 | signoff | AUTHORITY HOLDPOINT
16cdd789-56b2-4ced-b33f-89fd9f0a0d66 | section | Subbase
b9096a08-74fe-43ce-b0f9-f10aa33dcf4b | checkpoint | 2.01 - PE
51d56459-9aae-5b9e-84bc-f6918f93f230 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
aa66c009-0b74-5180-ac1d-4801cdc0da46 | note | Reference Documents - Insert Material Testing link
7c5260b0-3c43-506a-864f-645d4a61b56a | note | Material Acceptance Criteria (Method) - See PQE
a38d6ca6-0710-5005-8856-d3f0b91a6196 | note | Material Test Frequency - Prior to construction commencing
6144d017-899d-5799-b6ea-cb938e2db107 | note | Target Criteria - Material meets project requirements
7a44d965-2e51-5924-a069-53a6dde999b4 | note | Action Point Records required - Hold Point
fbd147f3-6e45-53e8-a2bf-53a63fc9a896 | note | Responsibility - QA / SE
3c745fe1-9c2f-4eac-8be7-cdd051c02337 | signoff | AUTHORITY HOLDPOINT
7f9910fd-df5c-4f7e-a274-e21e1e67d7e2 | checkpoint | 2.02 - Field
5a654d2b-6f2c-5e17-aff4-2e6487fa25e8 | note | Material Test Method Requirement - Plateau Density Test
1ea3e4d1-5616-596f-b559-f94d71f3e87e | note | Reference Documents - TNZ B/02: 2005
281be4c5-0f48-5f1c-9f48-a8d77466969b | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
2d850d9f-84d2-5fdb-9652-63611c43eef5 | note | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing
f5e183d6-8fec-5147-94c4-81dec37e7f64 | note | ○ Target to be approved by Engineer
849ad2dc-2100-5eb6-9875-fbc21299f057 | note | Target Criteria - N/A
71bd81eb-2d2b-5088-b3b9-e755b943ebfa | note | Action Point Records required - Hold Point Test Record
06839f98-9d60-55b9-b125-310658f64123 | note | Responsibility - QA / SE
c4221766-1037-4cf1-882b-186869ea18cc | signoff | AUTHORITY HOLDPOINT
98fd0a13-9766-4e27-ac6a-524df8a6c114 | checkpoint | 2.03 - Field
456a5dfd-3d66-5fea-8cf2-7b2529cfa117 | note | Material Test Method Requirement - Clegg Hammer
8dc40399-8102-5dfa-8535-4fe659f52301 | note | Reference Documents - RITS Table 3-21
30f29b04-6553-5c84-854d-1b215437e0b1 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
717268ba-5c09-5149-82b7-f41ea5226e37 | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
7602e34a-072d-5672-9708-ccf58822426a | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
35c8fb79-b1d7-53d1-9aa9-bdc85b32c9b1 | note | Target Criteria - CIV ≥ 35
6da4d157-987c-59c3-9b4e-e682b038e337 | note | Action Point Records required - Test Record
3a1e6df2-9706-5243-9d16-08e1ee500bc6 | note | Responsibility - QA / SE
46a12e92-2573-46fd-8d85-fe9993de93b1 | checkpoint | 2.04 - Field
ea68af16-3bd6-51d1-bf40-bf7a5e78121c | note | Material Test Method Requirement - Compaction NDM, Back Scatter
e38ad82b-edde-5bec-964c-d11361790961 | note | Reference Documents - RITS Table 3-22
dd7428ec-37aa-5ef9-8b04-992ed5cf1a1c | note | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
80cf4bba-941e-5557-bd85-53b675a0c793 | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
5eb63245-80b1-5cd8-9745-dd7f8c1c7cea | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
46a3a73e-ed7f-553e-b554-7359db9ada78 | note | Target Criteria - Mean ≥ 95 % MDD, Minimum ≥ 92% MDD
803c1be1-afd2-5380-bf00-eec1c6d455f6 | note | Action Point Records required - Test Record
043b1acb-efe1-5697-ae61-50db782ede0c | note | Responsibility - QA / SE
d1292ca0-9d58-47fd-9f2e-15dbcc90e273 | checkpoint | 2.05 - Field
35703013-0386-5feb-9496-78acc73664c3 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
f652228f-411f-5ada-ac1e-79650f4d2093 | note | Reference Documents - RITS Table 3.24
dd883b28-bf68-5cff-86ea-4d34301ffb36 | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
9b265ddd-ccdb-5db6-a088-90cde0e6b940 | note | Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency
e57ad1f5-5d37-58cf-9b71-76ce944dd7d3 | note | ○ Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
e978f430-ca2e-5a70-9681-fee8a1a723f9 | note | Target Criteria - +5mm/-25m from design or nominated level
c8ac6af0-b6b6-5ea3-8aa1-1a47f243e474 | note | ○ No more than 15mm deviation from a 3m straight edge
68bbbb13-4725-521e-8b0c-6d9637a0fb8c | note | Action Point Records required - Survey record
5cf207c9-84f0-5fe0-b6b9-1b20b8a18d01 | note | Responsibility - QA / SE
16bf12b7-2d1f-4297-bd4e-42967da545fc | checkpoint | 2.06 - PE
a32e568e-2fc2-54f9-b5d3-7501d44f94aa | note | Material Test Method Requirement - Is the layer closed out ?
1fa22697-42ed-5450-9cc3-3ea6ce2bfaca | note | Reference Documents - See PQE
c278c458-42f9-5c0a-ab02-205d36c203d6 | note | Material Acceptance Criteria (Method) - See PQE
00b1b789-2e29-5e68-aba9-7bcba6f55abd | note | Material Test Frequency - 100% of Surface Prior to placement of material
29a64912-4f08-50f9-b007-c0ac07811e92 | note | Target Criteria - PQE Approval
6af28046-d3bd-5d58-8bf4-95e6b76ce63c | note | ○ All testing record & reviewed as compliant.
ad504af5-b4d4-52ab-955d-9ddddfd02502 | note | Available Documents:
7cd517e7-6f9e-515a-bc08-e8fed6f816b6 | note | ○ Test records
c273381f-3b2c-50f3-a2fe-0432c566310c | note | ○ Survey records
4e62a1e6-c431-570f-8ad6-79d1c591ac90 | note | ○ Hold Point Records
ce3db904-d885-50c0-840f-ef3c3c31409b | note | Action Point Records required - Hold Point
98a53096-709b-53b3-bdbc-54ddeb940902 | note | Responsibility - PM
e6b30d3d-0fe0-47e1-848f-31c4b5157767 | signoff | AUTHORITY HOLDPOINT
054e5cac-815e-4c30-9252-215eb0f947cf | section | Membrane
91c50253-3b94-4e07-9633-1028b32d1824 | checkpoint | 3.01 - PE
0614af31-7bf8-5804-8ea5-d163c065634e | note | Material Test Method Requirement - Seal Design
ec4f6413-b195-5899-8aa2-302e49b7420c | note | Reference Documents - INSERT SEAL DESIGN
55626c97-ac4a-5c08-a18b-e0af6fd5dd6e | note | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
acdb3131-29c5-5cc8-99f7-d30028da0d89 | note | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
a41fa6f5-2b25-5532-a955-fd29a26cb226 | note | Target Criteria - Meets project requirements
f92329f7-7990-5c9d-ab32-52d16ba82b55 | note | Action Point Records required - Hold Point
013468b0-d510-5812-a51b-00943e5138cc | note | Responsibility - QA / SE
61424ebc-17d4-4717-8ae0-9abc6ac34017 | signoff | AUTHORITY HOLDPOINT
cefe6c68-6162-47a5-8a1c-47f03321130a | checkpoint | 3.02 - PE
184a7bb0-ccfe-5005-8df5-63d1a43004ec | note | Material Test Method Requirement - Bitumen Sprayer
11709a90-ba7d-5a79-a54f-cd2f56de50db | note | Reference Documents - TNZ P3
78e30eb6-5580-56be-be5d-4c2786867361 | note | Material Acceptance Criteria (Method) - Certification provided
d4151bf2-67cb-54ed-88c1-96a83be46c79 | note | Material Test Frequency - Prior to starting
a5f0e70a-9338-5248-9de7-d4223292a77b | note | Target Criteria - Current E/2 Certificate
9650c25b-f2a7-5392-8cd3-bc1e6974ce5c | note | Action Point Records required - Certificate Sheet
a230a137-e6eb-5964-a873-9962a9d2a763 | note | Responsibility - QA / SE
dbbe1684-6b76-4813-ac71-64771ddbaa27 | checkpoint | 3.03 - PE
56506a37-bc36-5366-b5e6-10aa8fd3088f | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
9e49c19f-848f-5e79-bc5e-23005faf6fbf | note | Reference Documents - Insert Material Testing
9d3f92b3-434b-56f5-94d9-5fa61b4b528f | note | Material Acceptance Criteria (Method) - See PQE
f3d544f3-bb83-5bbc-bc8e-6eb5d3b91082 | note | Material Test Frequency - Prior to construction commencing
c96eadf5-90ec-5817-ab03-dc1a6072f06e | note | Target Criteria - Material meets project requirements
cd4a20e2-de18-5b40-90e2-dec8f9a231ab | note | Action Point Records required - Hold Point
aa140275-1db8-5379-8e99-0116d56d54ed | note | Responsibility - QA / SE
c78e079a-e9a2-44b7-bd9d-ad590232a9bf | signoff | AUTHORITY HOLDPOINT
7aa8215c-decf-415a-8d78-5e37738e79b3 | checkpoint | 3.04 - Field
a01f4e99-d85c-5cbd-a1a7-1dbfb13dc04c | note | Material Test Method Requirement - Preseal Inspection
0e803bb2-903c-59fe-99c8-8bd9ca16bfa3 | note | Reference Documents - TNZ B/02: 2005
cb3bc309-0e70-5472-b263-f836368da7a9 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
27d71eb4-0362-5e9c-876e-ccbfd5d715b5 | note | Material Test Frequency - 100% of Surface Prior to sealing of surface
af385fe3-325f-5846-a369-994a9a2c5ca3 | note | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
8805de11-c2f7-5335-a734-4457194e4b01 | note | Action Point Records required - Test Record
fd36ee87-4550-50d7-a0c1-7c9142bf2a56 | note | Responsibility - QA / SE
e5d116cb-690f-48d2-9704-5b3089197890 | checkpoint | 3.05 - Field
f9dfba7b-ef5a-5483-83b1-ce84a64102ec | note | Material Test Method Requirement - GO/NO GO Survey
7835bc06-4afe-5e0d-81de-9740fa3c7126 | note | Reference Documents - Downers processes
0a6e8541-7154-5969-a944-ed379224bbf2 | note | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
9cd3f4c8-8b89-5015-80f8-b1a5e0021157 | note | Material Test Frequency - Prior to sealing on each site
e8b0b251-824d-554c-8d9d-30ebc118662b | note | Target Criteria - Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager
912a913e-1785-5d6d-aa39-128ea8e3c21a | note | Action Point Records required - Survey record
21fb04a9-2c41-555c-a892-844dfec8da1c | note | Responsibility - QA / SE
9a1c40b5-e705-4cc4-8a64-387dd1f93d8f | checkpoint | 3.06 - Field
ddb031e4-3655-51d2-ad74-1efe56e8b70a | note | Material Test Method Requirement - Application Rate
c1ce73ba-204c-513b-8603-774256b19169 | note | Reference Documents - TNZ P/3 : 1995.18
e2bc7437-ea20-5fdc-aec4-bef39ae26fd9 | note | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
1ecff04a-74ab-5dea-9399-89de90a771c4 | note | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
3bf901a5-5cb6-5553-bce6-0e79d072a897 | note | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
25e4cd0e-da4a-536d-86b9-7ecf9fb385d2 | note | Action Point Records required - Spray Sheet
0d14a811-3794-58d9-9769-3df4617abca3 | note | Responsibility - QA / SE
fff8d9b0-f3e3-49bb-8150-a683837dcf38 | checkpoint | 3.07 - Field
72fe9504-cb70-5720-9cb1-7bbb0f1b746a | note | Material Test Method Requirement - Post Seal Inspection
469b0343-63db-58ee-add5-2dd36322ad3b | note | Reference Documents - TNZ P3: 1995
ef661ffc-4855-586d-b301-edd3d364c183 | note | Material Acceptance Criteria (Method) - Engineers Inspection
a7206475-fefd-5089-b942-38f959990ab1 | note | Material Test Frequency - After sealing
1bca69e9-05a1-55cd-9cd0-94cfd313c1fa | note | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
6a2eeedb-b018-5c8f-8a8a-e0dbe2fe6c3c | note | Action Point Records required - Witness Point
b6f9aa5a-d357-5727-abd1-6cd096180cfe | note | Responsibility - QA / SE
f3e45114-e17d-4b33-a1b8-614cc8244e4f | section | EME2 Mix NZTA M32:2021
0a2d2b8a-547a-44fb-b538-abf80719dbfc | checkpoint | 4.01 - PE
779dd7b6-083c-57f0-8f89-43960e06e993 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
fc6f6df5-e88f-5568-8466-c9ab01c8a2a0 | note | Reference Documents - Insert Asphalt Design & Material Records NZTA -M32 Specification for high modulus asphalt EME 2)
13b17d32-9927-5cd1-8268-ee362600d6aa | note | Material Acceptance Criteria (Method) - Approved Treatment Design
6cb04279-c59f-5e55-b76d-6cc2fb6bb6d7 | note | Material Test Frequency - Prior to paving works commencing
f2443cff-4027-50c0-afba-bdc1ba4edd5b | note | Target Criteria - Treatment Design validation
5265deb0-97c3-5234-980a-11349204ad88 | note | Action Point Records required - Hold Point
1d01e1c9-6879-5d81-a3e8-f786d7692d8f | note | Responsibility - QA / SE
c2d56ff5-69f1-4ab6-ad35-77fe9c81ec0c | signoff | AUTHORITY HOLDPOINT
41b63c5b-e016-4c7a-86f0-fb54263a2fc9 | checkpoint | 4.02 - Lab
1494f3e4-d661-5cef-b750-fe294878e01e | note | Material Test Method Requirement - In-situ mat density calibration cores
81dbb4b9-87c8-5f6f-b772-478ebf95ff42 | note | Reference Documents - NZTA M32: 2021, 9.8.1
b6b87dc9-1c9e-54a9-8141-eaadd50fcb31 | note | Material Acceptance Criteria (Method) - ASTM D5361
01b84885-1400-5292-b80e-f0186bb0e140 | note | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot)
965d0ac3-107a-56ef-b905-907a65e86b49 | note | ○ 1 test per 100m per layer length (min 3 / Construction lot)
ca3cc5e9-f3a4-5894-9eca-beef84f30b00 | note | Target Criteria - Characteristic value - mix design air void +3% -2%
df3f941b-a26d-5087-943b-cf269f17d946 | note | Action Point Records required - Hold Point
c8a5c691-bb34-5af0-a73c-bffdca8b37e5 | note | Responsibility - QA / SE
0f05559a-96e1-4ddd-baf2-aa7e2cb56fab | signoff | AUTHORITY HOLDPOINT
2a02bd88-9e24-4eb6-98ba-b2b2a69028e0 | checkpoint | 4.03 - Lab
85c1a942-3690-5cb4-a238-80799eccd241 | note | Material Test Method Requirement - Grading (Particle Size Distribution)
b1af72f4-31d7-5ea5-94e1-cb1de814e51e | note | Reference Documents - NZTA M32: 2021, 5.3
792648fb-47b0-545c-8642-e50fcd7c9ec1 | note | Material Acceptance Criteria (Method) - NZS 4407:2015 test 3.8
c53925b0-c1ba-5491-9a34-99772eea8ad3 | note | Material Test Frequency - One test per 200 tonnes of production
1c13b277-ef35-5120-9889-c400df30e43f | note | Target Criteria - Tolerance from nominated JMF grading as per NZTA M32: 2021, Table 5.3
0d5c4d3e-ae21-5a48-960b-fb7bef3fd7b6 | note | Action Point Records required - Test record
39dc12ef-eed1-53da-ac96-add54e9633a9 | note | Responsibility - QA / SE
e28ff617-ce86-4603-8195-6c05be45d888 | checkpoint | 4.04 - Lab
e0557a55-25be-557e-bcf5-38f1ae8af3f0 | note | Material Test Method Requirement - Binder content
08f66288-677d-5c7d-89fe-56ef3e77cad1 | note | Reference Documents - NZTA M32: 2021, 5.3
c7769f1d-a0f5-5263-ba3c-1e89072136e8 | note | Material Acceptance Criteria (Method) - ASTM D2172
89323f47-913c-5e2b-95e6-80f83fa899f6 | note | Material Test Frequency - One test per 200 tonnes of production
7f2b70ca-00fa-5b98-9d25-a4adaab85431 | note | Target Criteria - Tolerance on JMF
82a60b0b-8c21-5293-bc78-acd023662931 | note | ○ Individual ±0.5
07711ce7-bc75-5ed9-9663-4a98fdb7c755 | note | ○ Rolling Average of 3 ±0.3%
f9f407c7-eda7-5fe2-8047-d003094f548a | note | Action Point Records required - Test record
15cd56bf-a611-5448-8e95-c101910ba7c3 | note | Responsibility - QA / SE
4de755cb-4d1d-49b4-883f-db4f3ff186f7 | checkpoint | 4.05 - Lab
eb61b398-5ed6-5cb5-89cb-d9a2f89de46b | note | Material Test Method Requirement - Maximum Theoratical Specific Gravity
3d34bd80-8c1c-56e9-a081-343038abb6c9 | note | Reference Documents - NZTA M32: 2021, 5.3
6fa0a056-b3c1-5e96-a23c-3fc6a2652db1 | note | Material Acceptance Criteria (Method) - ASTM D2041
d717dcb6-e622-522c-b467-37e479ca263d | note | Material Test Frequency - One test per 200 tonnes of production
5b588198-9346-58a9-acff-545416ae04cc | note | Target Criteria - Report Value
7f51e90f-7f18-5dd1-8d99-804d52c39c86 | note | Action Point Records required - Test record
58f8dd6f-7e93-52bf-9670-85482fff0d21 | note | Responsibility - QA / SE
e1a8c6b0-2fe1-4dcd-bacb-ae5d5c1b4311 | checkpoint | 4.06 - Lab
1b76d2c6-947f-530c-973f-067d36ada00a | note | Material Test Method Requirement - Air Voids
57d4802b-d79a-559a-b197-c4629fce2977 | note | Reference Documents - NZTA M32: 2021, 5.3
2d581c84-d319-5212-9cd5-70b8842e9bb7 | note | Material Acceptance Criteria (Method) - ASTM D3203-22
58d6d354-fdb4-550b-a34d-08fb26e94e2c | note | Material Test Frequency - One test per 600 tonnes of production
ce3dc65c-0b36-5c88-a992-272f5131a129 | note | Target Criteria - As specified for each mix type
48ab2628-e04d-521b-be0a-b906394a6b72 | note | Action Point Records required - Test record
e9578b4c-61c8-5828-b84f-f3ad3613dedb | note | Responsibility - QA / SE
fdc85e39-ab4a-465d-9032-28a3514e2495 | checkpoint | 4.07 - Field
ad3fef54-aee3-5876-9e72-4673dadcfc66 | note | Material Test Method Requirement - Load Locate
ec0fe7bf-c455-564d-ac5f-e3937560f9ef | note | Reference Documents - Downer Procedures
ad603681-4bec-5e09-8923-45d6ea83ce95 | note | Material Acceptance Criteria (Method) - Each load can be indentified to a location. Record includes:
bc04b32c-b1ae-581b-8d11-6ab0b979a1a0 | note | – Truck ID/Rego/Driver
17d21925-8d4b-56a3-ae8b-9a442a784caf | note | – Depart Plant Time
815cddf8-04ed-5771-8654-b73e93673e47 | note | – Arrive Site Time
9db16bd5-b5b4-59c5-971d-b2c0695e704e | note | – AC Temp on Arrival
84f7b02d-b81e-59ce-b961-a92f866f139e | note | – Ground Temp on Arrival
372fccd8-f07d-57f5-9272-bb618f4d6090 | note | – Tonnage
136dadd7-bcb7-5c9c-b108-7792d1a2b947 | note | – Run Width
f3eab985-7684-515d-892a-18726f016da3 | note | – Estimated Run Length
663e02f5-7b98-578a-af88-dea7d006c960 | note | – Calculated Area
553db5cf-956d-59e1-a964-a5771084267e | note | – Calculated Average Depth
ce566da9-aedc-5a95-8f14-9e555804318f | note | Material Test Frequency - Every Load
11bb5373-ae5b-5afd-a0e5-cac147a5b2bf | note | Target Criteria - All data is collected
a2c69b97-2236-5001-ba7b-ab27935e8ce6 | note | Action Point Records required - QA Sheet
c7c2ba98-967d-5d68-b8d9-796128ca9b6d | note | Responsibility - QA / SE
f746cb17-d77b-4c59-a514-6a644107d94e | checkpoint | 4.08 - Field
990efab6-1233-577e-9a9b-63571f0899be | note | Material Test Method Requirement - NDM Density Testing On-Site Mat and Joint
cd456fa4-8855-571a-9446-5dde0cf803cd | note | Reference Documents - NZTA M32: 2021, 9.8 Table 9.2
a9bb5574-f89e-56b1-b5dc-701395c5667a | note | Material Acceptance Criteria (Method) - ASTM D2950, ASTM D5361
7a18c7f8-4663-503d-a95e-26264ac3ebf3 | note | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot)
e888ab34-32bf-569a-b41c-714e1b7f0809 | note | ○ 1 test per 100m per layer length (min 3 / Construction lot)
63232454-fcb7-5987-9c01-4ad456774beb | note | Target Criteria - Mat: Mean air voids JMF +3,-2
64853529-217f-5fc0-bac7-b13ae8fdb16d | note | ○ Join: Mean air voids JMF +5,-2
2b7354f9-21ce-5ddc-a359-6e5465c7c3a1 | note | Action Point Records required - Test record
d9f6c61d-2bfb-5794-b0f5-2b3990ba63f9 | note | Responsibility - QA / SE
edb4c9a9-7545-4889-a744-9f905f869d4a | checkpoint | 4.09 - Field
0389c84d-cdf6-5132-822d-1069433a40a5 | note | Material Test Method Requirement - Plateau Density Test
5fbf05e2-4ec0-5ed1-827c-8cff1f2711c3 | note | Reference Documents - TNZ B/02: 2005
4de95dd2-74e7-5e9a-b599-e95ea45e6b82 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
2b69b839-59e0-5ec6-9214-7550ae464511 | note | Material Test Frequency - 1 test per site
0b115126-ec5a-52de-a815-4dd7a92826e1 | note | Target Criteria - N/A
28072cb7-15c2-5afb-ac35-027d619d7922 | note | Action Point Records required - Test Record
64447adf-09d5-5d78-bb4d-87ee3154b306 | note | Responsibility - QA / SE
88d8f4e0-dd4e-4ddf-92dc-85635d9b5df6 | checkpoint | 4.10 - Field
d3d6cadb-4b5d-5bac-927b-b2b94a085c3b | note | Material Test Method Requirement - Surface Level- Stringline checks for validation
06f381b2-04bd-5950-bec4-274d8ab96a23 | note | Reference Documents - NZTA M32:2021 10.2 and 10.3 Downer Procedures
08ed9e63-8a7d-5c98-9dfc-6a43a98e2649 | note | Material Acceptance Criteria (Method) - Contract Specifications
1c0ee76a-5f3d-5e91-8ebb-8ab6c79eea2e | note | Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency
3185468f-6ee9-519a-ae8e-c9ed37e65168 | note | ○ Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
f4287c74-a0f6-52ba-abd6-8afc593b02d9 | note | Target Criteria - +15mm/-5mm from design or nominated level
3ee386b9-b4d5-544e-b001-bd27d7fdc08d | note | ○ No more than 8mm deviaton from a 3m straight edge
46a0183f-31d1-5360-80e6-e84cea0e63cc | note | Action Point Records required - Survey record
c06c9b5d-8457-5d64-9a07-636343734039 | note | Responsibility - QA / SE
4c8d1120-8d7b-46b9-8519-0596fb7dbed0 | checkpoint | 4.11 - Field
075386c6-3615-59fa-a52b-bf15fe2828cd | note | Material Test Method Requirement - Post Surfacing Inspection
b893a213-072f-5118-9126-9463655729cb | note | Reference Documents - CCA Procedures
06c03cc5-2152-5236-b94c-229e9ee89dfc | note | Material Acceptance Criteria (Method) - Contract Specifications
7ae42963-01d2-565c-96bb-d911227e8a45 | note | Material Test Frequency - 100% of site After surfacing (within 5 days)
9059e901-cf71-573c-8561-64da9cd45767 | note | Target Criteria - Line marking has been reinstated
1b78ffa6-7b2d-5f9c-a5b3-f9a52173a130 | note | ○ All excess material has been removed from site
d2e61d6e-92a5-5a96-8edd-143da60ed9a3 | note | ○ All CPs are clear from filter fabric and any excess material removed from on top service covers
5b27086e-ab8c-577d-87a4-90c80e8c021b | note | Action Point Records required - Survey record
9dcb7feb-314a-5512-a132-57a1a3c9d60a | note | Responsibility - PM
c85fe63e-f929-4c17-8a7d-c0c714046c89 | section | First Coat Seal
101e0791-5960-4834-973f-dc35d1783451 | checkpoint | 5.01 - PE
c83c0b39-bf5d-5881-a32b-338bf8c72fed | note | Material Test Method Requirement - Seal Design
6b5c67b4-899c-5a32-82d6-9d360ff8422f | note | Reference Documents - INSERT SEAL DESIGN
09012ac4-20e9-5a03-a1aa-ca395c2263ea | note | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
dc93ae1f-44f1-5956-ac70-1c9db15994d8 | note | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
ab758008-2f2d-5d0e-8270-37c02b355ecc | note | Target Criteria - Meets project requirements
c9ed074c-40bd-5f38-b67a-2ca084f3573c | note | Action Point Records required - Hold Point
8003c5c0-d9d3-5432-9a73-211c0ac2c4ab | note | Responsibility - QA / SE
87fc1d93-eaa9-4fcf-971c-0a819f8b6d6b | signoff | AUTHORITY HOLDPOINT
3bc96619-1012-4285-92ce-dfa697c78101 | checkpoint | 5.02 - PE
b179b2e2-7163-53f7-8273-c743bf3ecdb3 | note | Material Test Method Requirement - Bitumen Sprayer
d6b7f4dd-c031-53f9-9d88-85abaf06c5cb | note | Reference Documents - TNZ P3
19fb6fa2-eb01-5c06-8270-11102c03be05 | note | Material Acceptance Criteria (Method) - Certification provided
32e1fd5b-e36d-5cd2-8cbb-51aa3419b533 | note | Material Test Frequency - Prior to starting
38a60019-cc1e-5228-9c91-836a1c20dd06 | note | Target Criteria - Current E/2 Certificate
c01a1f3d-8131-575f-a147-6680ee6f6ce9 | note | Action Point Records required - Certificate Sheet
4c7ffe9c-0279-57ce-bc77-b1fd73a0570b | note | Responsibility - QA / SE
e433196e-a7ba-4b78-af7d-6273aefaff4d | checkpoint | 5.03 - PE
72db1782-4d30-5a01-9d1d-eaf6c756ed98 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
aabc77b7-3587-528f-b5fb-c38e4c248721 | note | Reference Documents - Insert Material Testing
4ce7832d-701d-57d0-b9ee-be265edc7bce | note | Material Acceptance Criteria (Method) - See PQE
1209f9e2-8ac5-58fd-9739-757f3d279767 | note | Material Test Frequency - Prior to construction commencing
7b239ed3-d4d3-5eb8-a8ae-f4aa2ebfb544 | note | Target Criteria - Material meets project requirements
7e320d65-a831-5e0d-bebe-6c48a7cff8d7 | note | Action Point Records required - Hold Point
7b65f768-4108-5ad2-9a04-e34b42a97cdd | note | Responsibility - QA / SE
0a2b1183-2e3c-4dfc-973b-6ed15789639c | signoff | AUTHORITY HOLDPOINT
c340de6d-47d1-433b-a34e-f8547e38a101 | checkpoint | 5.04 - Field
a96b4ecb-267f-5c3d-a2fe-0f973aadd059 | note | Material Test Method Requirement - Preseal Inspection
5dbb1336-505f-59df-bdc2-5606d55efe5f | note | Reference Documents - TNZ B/02: 2005
1990f0df-5611-5ab0-b421-56d344d8f8d9 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
574286e7-d968-5cae-a950-fd8dac3427ed | note | Material Test Frequency - 100% of Surface Prior to sealing of surface
bbd8a8d3-27a5-5870-9d0b-9800c2b29691 | note | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
73a5c2d2-2b6f-5af7-8900-5a7000ac8701 | note | Action Point Records required - Test Record
af49fb13-9ca4-5e6d-8e59-00ce695f27bd | note | Responsibility - QA / SE
8dc1aee6-c9da-4e2c-a283-9d4e1dcb567c | checkpoint | 5.05 - Field
6b69b2cb-5648-5ea1-8aad-de7900dfb566 | note | Material Test Method Requirement - Degree of Saturaton
3fbd2035-5098-5a26-954b-02774a4f01ac | note | Reference Documents - TNZ B/02: 2005
7f87b005-915a-5aa5-bbd9-f7de1a2610c7 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
52718a2c-e617-5dda-aea8-2201f4472f29 | note | Material Test Frequency - 1 set of 5 per 1000m² - then 1 per 200m²
d878671e-f5ac-54d5-a5ed-dbc7cc9629df | note | Target Criteria - < 80 % Completed Max 48hrs before sealing
dcf0f8fb-f329-50e5-948e-6a6620d204cc | note | Action Point Records required - Test Record
8a56e0a6-6ad0-50cd-b587-6c6ed742a32a | note | Responsibility - QA / SE
15cde36a-7965-49d1-a2a4-3117ae50de56 | checkpoint | 5.06 - Field
082ac2ab-1393-5112-828c-207bedfbd631 | note | Material Test Method Requirement - GO/NO GO Survey
3558f5f3-985f-5409-911e-91a2f3263d19 | note | Reference Documents - Downers processes
f14fb069-a7b4-5c08-9e79-7d1bbb0d50ef | note | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
97abc601-53f9-520e-a084-063528bce132 | note | Material Test Frequency - Prior to sealing on each site
45592196-e1b0-569a-b67b-cd16be0b9bd6 | note | Target Criteria - Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager
f6b54833-3abf-5a65-a018-4ca7eaaf2c3d | note | Action Point Records required - Survey record
f2789860-f1b5-588d-aabf-6b56e286baf2 | note | Responsibility - QA / SE
fd53327f-19ee-45b6-9754-e8a988351b9b | checkpoint | 5.07 - Field
5ef92c93-f893-5e18-9653-42a99bba1eec | note | Material Test Method Requirement - Road temp
16b19c0e-3457-5668-92c8-698e78eb222e | note | Reference Documents - TNZ P3:1995.18
09ed2327-69aa-5d15-a215-850bede2722f | note | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
ce43355e-ceff-524e-a9da-4f5e72dde24d | note | Material Test Frequency - Once per day of sealing prior to sealing commencing
330c5861-ffd1-5fcb-bf1c-21e64b78a870 | note | Target Criteria - Air temp >10°C
cc6cf1e1-9cb5-54cc-9505-432fc5e75e6b | note | Action Point Records required - Spray sheet
7efdbb1b-4639-55f1-8eb7-04a5e4a4a80a | note | Responsibility - QA / SE
e1e3b43f-0198-4cb6-bb85-06b06daa82dd | checkpoint | 5.08 - Field
f2d2d184-3aed-5948-9e16-32be0c59675e | note | Material Test Method Requirement - Application Rate
7399cb23-a159-58ad-b600-de0ea5e2a7fd | note | Reference Documents - TNZ P/3 : 1995.18
181d1197-24c7-5953-abed-cc9f5f6e05d6 | note | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
739e553f-46a3-5cb2-9773-debad63fdca2 | note | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
c19fb685-84fe-5439-b6d6-89ee87154e07 | note | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
35d2ee1c-5b35-5840-bb9b-0a3ae3d9f8b2 | note | Action Point Records required - Spray Sheet
0243f1ce-1381-5bdc-ae9b-528f7b142e48 | note | Responsibility - QA / SE
50f1e102-4f10-4d81-9e0f-399168833529 | checkpoint | 5.09 - Field
628c670f-c3b0-580f-b931-5f082f348887 | note | Material Test Method Requirement - Chip spread rate
8e09d66c-388c-5bc3-a772-340218ef11e7 | note | Reference Documents - TNZ P3: 1995.21
e5f9cc6e-8b5f-56ab-bbb7-d9653d78f0c5 | note | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3)
a3cb5dc4-9c6a-53b9-99a8-c5e1a9918fce | note | ○ Chipsealing in New Zealand (pg 435)
79b05c2c-96f7-5991-bf6e-29aaad3a44c5 | note | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
3a5aced7-1b31-540c-b9e5-ea2a75f6eedf | note | Target Criteria - Visual checks meets seal design requirements
eebd865b-c984-5b46-974a-8b1d0b782053 | note | Action Point Records required - Witness Point/Spray sheet
3a303faf-7f15-5b38-afc1-2e2baf0f5918 | note | Responsibility - QA / SE
4754d1e1-eab0-434e-b010-c4103675efbf | checkpoint | 5.10 - Field
e2027f69-5621-5ca0-9ea3-5d96395c27ca | note | Material Test Method Requirement - Rolling Checks
a2e6c444-d3f1-5358-b701-40fa200beebe | note | Reference Documents - TNZ P3: 1995.22
5f267205-e206-5589-8cbb-75ba9fbcd98f | note | Material Acceptance Criteria (Method) - Sealing Record
1895bfa4-f250-5cd8-af88-d382b57b33f1 | note | Material Test Frequency - for each sealing site per day
2d9e76f9-5286-557b-b5e9-d9ea6f8ae1a5 | note | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
dabd22e4-b746-5efc-b173-8dafe135d116 | note | Action Point Records required - Witness Point/Spray sheet
ce76d9d0-88de-5af9-b46b-2648dbb383d4 | note | Responsibility - QA / SE
88626f7c-c85c-47f4-a4c4-e4b5c8927eae | checkpoint | 5.11 - Field
b005490c-0330-5d83-a64e-ccfa1e1fb7fb | note | Material Test Method Requirement - Post Seal Inspection
dd4c28be-139c-5eb2-85df-954da679fca8 | note | Reference Documents - TNZ P3: 1995
86d0bfd7-2f50-5207-bff8-19897b23d171 | note | Material Acceptance Criteria (Method) - Engineers Inspection
c377f6aa-b514-5101-87df-a4969781edd5 | note | Material Test Frequency - After sealing
39da5fdb-06be-5a9c-b1a8-6cd0cd686c2e | note | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
6a0d8865-2f0c-5194-bb2c-62ca98a5f62f | note | Action Point Records required - Witness Point
5474e7e0-a20d-5ae5-9efc-7ff95fe26540 | note | Responsibility - QA / SE
3998c6c2-2543-4967-b63f-1e8989b0200d | section | Post Construction
8cc242cd-0a1e-4231-a003-79f86445a578 | checkpoint | 6.01 - PE
032ae967-efb8-5737-869d-01f14b54b39f | note | Material Test Method Requirement - Asbuilt and RAMM Data
b6c010b2-9cba-5f83-afaa-daea99ba4c4b | note | Reference Documents - RAMM Update sheet
ebad1e6f-d03b-5315-bd80-965514398add | note | Material Acceptance Criteria (Method) - Asset Management Information Plan
dafb1d5e-2fbf-5f86-a5be-818d56fec77e | note | Material Test Frequency - After works complete
95569b20-706e-5d34-ad95-3981fdfe56b7 | note | Target Criteria - RAMM sheet 100% complete and accurate .
109d9d74-dc00-594f-a910-9b316acc062e | note | Action Point Records required - RAMM Asset Update sheet
2faa7b13-4427-5dea-b3bd-35774bdaa1aa | note | Responsibility - PM
256dd6a9-1057-4b38-a56f-820677cebb70 | checkpoint | 6.02 - Field
98fd5fe8-e066-5866-95f6-67697d6a8b4a | note | Material Test Method Requirement - Site Safety Audit
eef95b9e-b2da-52ff-b4ad-1656f2f93531 | note | Action Point Records required - Test Record
81a8be94-6230-5984-83c7-c0eaffa438df | note | Responsibility - PM
a6a4bd03-9b92-4889-9ac6-f7bfea9fbad7 | checklist | ITP - Chipseal Surfacing | itp | ITP - Chipseal Surfacing
ae33bc86-15c9-4622-9910-1766cf900ffc | section | Design
77885afd-b89d-4f1e-ae12-92d3c42d24fd | checkpoint | Treatment Selection
b8bac416-3ddd-5c3d-b85d-151c0429ab82 | note | VERIFICATION ACTIVITY - Physical / Site video/photographic record
b10d49bf-6fda-5dc1-8f29-890621070ada | note | METHODS OR REFERENCE - Asset Team - Base Preservation
a865c83c-1e5b-5930-a75b-1bcf16130cf8 | note | FREQUENCY - Annually Pre-reseal
e91b13de-7645-5ab4-9645-373575abbae5 | note | ACCEPTANCE CRITERIA - Documented approval from at time of Tender -Team/Client
6e364dfe-e39e-5492-ac9d-172fc0578849 | note | HOLD / WITNESS POINT - Mandatory HOLD POINT - Client Approval
fecc251a-e28b-53b2-ad13-e5624044e1a5 | note | RECORDS - Approved Seal Designs
7900daf3-eabc-568e-b26e-294de13c8d24 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
e712f751-18d0-481e-9d8b-94cc5b27bde0 | signoff | AUTHORITY HOLDPOINT
f77ebbcc-1e61-4a94-971d-dc2f4c02f219 | checkpoint | Chipseal Design
32125593-e49a-56a9-82d6-3a16526d4915 | note | VERIFICATION ACTIVITY - Peer review by Authorised Seal Design Approver
5d9ff096-a346-52f6-aadc-00d04b4bed4f | note | METHODS OR REFERENCE - Chipsealing in NZ
3d0a53ad-054f-5794-a334-86db72bb408d | note | FREQUENCY - One per design prior to commencing onsite
5b96cc67-f61a-5c1f-a1aa-6069f69fc78d | note | ACCEPTANCE CRITERIA - Design meets requirements of P17
1bcf2598-49cd-54a3-be59-63475ef59ec9 | note | HOLD / WITNESS POINT - Mandatory HOLD POINT - Seal Design peer Reviwer - Client Approval
e12e15e2-af08-5358-8c8a-eef0dc16791b | note | RECORDS - Peer Reviewed Seal Designs
0109c951-c53d-57f2-9143-a5a7e8f9f5df | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
f604e18e-1b87-47d9-8985-21cfd9b0f4bf | signoff | AUTHORITY HOLDPOINT
6c387542-cee7-467a-8586-c9a3aaa1c208 | section | Materials Testing
5a0616b4-d95b-4cc3-8526-70d744231674 | checkpoint | Size (Grades 2-5) & Shape (Grades 2-4)
6a8116cf-f838-5d22-92d3-24ff0752bf3a | note | VERIFICATION ACTIVITY - Lab Test
37cc380c-eedc-58a6-91eb-d2897e1dcc04 | note | METHODS OR REFERENCE - NZTA M/6
c00c0cfb-aa59-5190-8aea-9ff8b7c25efd | note | FREQUENCY - 1/500m3
07558025-0a6a-5c23-8cc4-a31d5d83c997 | note | ACCEPTANCE CRITERIA -
12935f30-9322-57ce-963f-325da05ce100 | note | Size (ald mm)
11782103-ef3a-5a8f-a289-2508532300dd | note | – G2 9.5-12.0
44e94c5e-3b44-5a61-82a0-eece3915e7e6 | note | – G3 7.5-10.0
1984cea0-5da7-55d6-bc7c-d8c86fcbaf72 | note | – G4 5.5-8.0
768d4c03-0d11-567e-b6e8-dd7fe9db02fb | note | – G5 Report
15e70cfb-aca9-5484-98ce-9eec0479b405 | note | Shape
f82cb0bc-d62f-5776-9daa-8438b46d5f8d | note | – AGD/ALD Ratio G2,3,4 = 2.25 max
60db0a4c-da63-588c-8928-ebf4b803f4cb | note | – G2,3,4 = min 98% with 2+ broken faces
8f78423a-f9a9-5514-b4e9-cc4ba38493a6 | note | HOLD / WITNESS POINT - Witness Point
98d6e4b3-0e9b-54b4-bf17-855a1dd511db | note | RECORDS - IANZ Lab Reports
7b023df4-94dc-57ff-a3f4-858833416993 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
ebf10891-fe7f-46c4-b36d-51c2afdc292d | checkpoint | Cleanliness (Grades 2-6)
7c65619b-65fd-546e-97d6-c64e48fa6574 | note | VERIFICATION ACTIVITY - Lab Test
03cb8793-2c69-59f8-aa27-01c7322eeb9f | note | METHODS OR REFERENCE - NZTA M/6
f0d46b0c-f384-51f7-a755-491981f4c5e5 | note | FREQUENCY - 1/500m3
f4b6fd92-59a5-54bc-8cff-289d4609caf1 | note | ACCEPTANCE CRITERIA -
ea51d4b4-42dc-51dc-8197-cee3300339cc | note | Cleanness value
b634aae2-db61-5847-a018-63f409d69af9 | note | ○ G2 = 89
85dfed76-b499-52ed-bfcb-845fb0cedd93 | note | ○ G3 = 87
528e97a9-bb34-55f8-ac68-fd90683a3b2a | note | ○ G4 = 85
657b1b6b-fced-5fc1-99dc-60f57a9027a4 | note | ○ G5 & G6 Report only
6006450c-969a-58d1-b3d3-d2cb8d3bf52f | note | HOLD / WITNESS POINT - Witness Point
a21ec498-cd5b-5f5a-a408-18c601a27747 | note | RECORDS - IANZ Lab Reports
90dca6c4-0511-576f-9d3d-288e1dd6d6d6 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
e73f616d-11c0-48f8-8920-2ea42b3d2115 | checkpoint | Compatibility (Multi Layered seals)
7e980c5b-8c39-5506-9747-9f03ad988d3e | note | VERIFICATION ACTIVITY - Comparison Of Chip ALD
d42a813a-c218-58bc-93e5-91181537e85f | note | METHODS OR REFERENCE - Chipsealing in New Zealand NZTA (NZTA 2005)
a2e97d79-8129-51ac-a0c4-5773358452b7 | note | FREQUENCY - 11.5, 7.2
dbecd8af-2e82-5b25-9b9a-a389539c430a | note | ACCEPTANCE CRITERIA - Two Coat Seal Aggregate Compatibility
162099d7-f4fa-565a-8138-ffce32955bfd | note | HOLD / WITNESS POINT - Witness Point
e9f39998-31a2-5895-b7e3-37b642a9c3c1 | note | RECORDS - IANZ Lab Reports
bcb04773-0f56-5c76-bca4-d4a320dfe836 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
7e8be982-f558-474e-9030-9dba08db4079 | checkpoint | Bitumen Distributor
b9c09588-6755-58f1-821e-b4be36e85557 | note | VERIFICATION ACTIVITY - IANZ Lab E/2 Results
f51d60af-7a34-5ba7-81a3-aa89a369a9bf | note | METHODS OR REFERENCE - Code of Compliance
734c7a04-c061-5da9-bcc0-2c3f8d1d34e3 | note | FREQUENCY - Annual
b24f8268-6ce7-5549-a12d-14448fb19c42 | note | ACCEPTANCE CRITERIA - Speed Test(+-3% over 100m), Dipstick Test (+-50L over 2000L), Matt Test (app rate within 0.10L/m2, longitudinal within 10%, thirds within 5%, transverse within 20%)
5af5fa4d-a247-5238-a0a8-d90c5bf19cf9 | note | HOLD / WITNESS POINT - Mandatory HOLD POINT - Client - Engineer Witness
45751f62-b184-5307-b90d-bc2a76a0694e | note | RECORDS - RNZ E2 Certificate
ff0e155b-5666-5962-94ed-7b23928fc6be | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
970dd462-0f35-44ed-bf41-365807315c95 | signoff | AUTHORITY HOLDPOINT
462e4f08-9eda-47b0-aaf6-2262cd721c3a | checkpoint | Emulsion/PME Testing
6aeb0a91-de9a-57b2-bef9-2d079e0b0b7f | note | VERIFICATION ACTIVITY - Lab Testing
4fdffbba-77fd-5056-96d5-93ef86fa01e6 | note | METHODS OR REFERENCE - Manufacture Specification
7c8684ce-c6fb-5994-9b25-3ec764d8b3c8 | note | FREQUENCY - Per Emulsion/Bitumen Production Batch
8a87d516-97f8-5fa4-8e56-975f88db6e60 | note | ACCEPTANCE CRITERIA - Bitumen Content, ITM 11-01, Viscosity, ITM 10-02, PH ITM-08-02
680283bb-a734-5b34-bd05-1ee8ef0f5980 | note | HOLD / WITNESS POINT - Witness Point
577891d2-3c9e-5313-83df-b25405ed50f0 | note | RECORDS - IANZ Lab Reports
cd7eefc1-d5f1-51d4-9f87-81bc48bf496d | note | RESPONSIBLE PERSON - Road Science
17667d39-1862-4d4c-8671-01f35ef354b2 | section | Surface Inspection
7db94019-5321-40fe-8dfe-df4da62bfb80 | checkpoint | Surface Texture - Measurement
ea6a9301-f759-5538-bb9b-5a25c100807b | note | VERIFICATION ACTIVITY - Sandcircle Measurement
9710ae19-37b9-5d3b-83c4-1f94ead71953 | note | ○ ARRB Hawkeye or NZTA HSD
857bb0a6-e14f-5fee-a7d5-476eee1307da | note | METHODS OR REFERENCE - NZTA T/3
7852b2aa-23a4-5c29-afa5-faf365ece545 | note | FREQUENCY - At time of Seal Inspection
ff3fbaa6-5e79-5363-9a5a-9aab093639d8 | note | ACCEPTANCE CRITERIA - Texture evaluation for each site complete to validate design texture assumption, where differs application altered to meet on-site texture
29fff669-1952-51ed-b07f-3002b9a0ea2e | note | HOLD / WITNESS POINT - Witness Point
234ca677-0ab6-5851-a175-42b913ed011a | note | RECORDS - Sandcircle Data
3fcebe63-1480-57fa-b0e0-fe2d549486ff | note | ○ Hawkeye Data
0b1587ce-5b5d-5457-b98b-0722f656240d | note | ○ High Speed Data
8ea2742e-7b0e-5026-b615-c14d80674efd | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
1819cda9-a9ca-477f-a96d-ccc856dd6b4c | checkpoint | Pre Seal Survey
fac6283d-08f6-5237-a0e3-c73938d3c026 | note | VERIFICATION ACTIVITY - Downer Survey or MS Forms Pre Reseal Inspection
56870af1-ed29-54d7-9dbc-b089e75c9043 | note | METHODS OR REFERENCE - Downer Survey or MS Forms Pre Reseal Inspection
d94ab634-9a6e-5abc-b5eb-c7d901b6f571 | note | FREQUENCY - At time of Seal Inspection
dd569752-feef-5d06-939a-cf9e519a9678 | note | ACCEPTANCE CRITERIA - Record & any noted issues / Client
78edf02d-ec62-53c3-bc49-88066950b248 | note | HOLD / WITNESS POINT - Witness Point
4fe26d9d-2452-5522-ad29-3bbe54fbc22e | note | RECORDS - Lucidity
2cc5fbd2-a42c-5335-95c5-aa005d992c78 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
4372a70b-8302-4050-a6f1-f734ac6161d8 | checkpoint | Construction Compliance testing
1eb04db5-34e4-5660-8519-a27246e365d6 | note | FREQUENCY - 24 hours in advance of seal construction commencement
00128c60-89a1-5ef7-98a8-ea71c05746b7 | note | ACCEPTANCE CRITERIA - Confirmation from renewals manager all testing has met requirements
cb9be670-7972-5074-aa8b-2b740c270d04 | note | HOLD / WITNESS POINT - Hold Point
4bd9901d-850f-583d-b411-582a00974f33 | note | RECORDS - Email Confirmation
39ba154c-acfd-57ba-b427-0399e387d28f | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
a64a768e-3aac-4358-bd06-d57cc1265c82 | signoff | AUTHORITY HOLDPOINT
54663e06-af7e-4621-802d-dc02121496a4 | section | Seal Construction
a16174cc-a798-4e72-8ad6-ee61a563ab5c | checkpoint | Go/No Go Survey
baa43280-b6bb-5490-85c3-5de56231da02 | note | VERIFICATION ACTIVITY - Visual, Zeus, Iris
82523af8-10de-561c-b149-ce1e2eccf94d | note | METHODS OR REFERENCE - Downer Survey Sealing Go / No Go, Road Science Zeus app & Downer Iris app
56d7125e-7f44-51d5-bd96-3a088c2c6f12 | note | FREQUENCY - Prior to sealing on each site
e541738a-772c-5f14-872e-e0c231aa0705 | note | ACCEPTANCE CRITERIA - Pass on Go / No Go, Marginal & discussion with Contract Manager or written approval from Rehab Manager
8c0acbc3-d424-5831-83e4-87a9390b3549 | note | HOLD / WITNESS POINT - Witness Point
16fd627a-f3d9-5575-bd0d-e97f7cb2ab5b | note | RECORDS - Lucidity
4bf36fe5-114d-58be-a02a-7f8c4d758797 | note | RESPONSIBLE PERSON - Supervisor / Foreperson / QA
b957b463-c3f9-41af-98fb-1b22935eaf2b | checkpoint | Pavement Markings/RRPMs
cbb7d398-86f0-5256-942f-c612f8f09515 | note | VERIFICATION ACTIVITY - Tagging of existing Pavement Markings, Removal of RRPMs
6b30baea-2447-5bf4-b915-e39265eff001 | note | METHODS OR REFERENCE - Pavement Marking Set Out Sheet, CBP
ba42138a-cd85-5c99-baf2-c534cd73b0bc | note | FREQUENCY - Prior to sealing on each site
fe740cdf-b21d-5165-8264-8a2fc52052b8 | note | ACCEPTANCE CRITERIA - All raised pavement markers to be removed (1st & 2nd Coat Seal surfaces excluded) and existing line marking "tagged". Check for any new markings required
351f7d9e-dc59-51ee-9060-19d2e6adc6e8 | note | HOLD / WITNESS POINT - Witness Point
11b33926-9666-51d5-b10b-34a8aef87bad | note | RECORDS - None
4cdbef59-ed90-5ad8-ac8f-fafa099e3672 | note | RESPONSIBLE PERSON - Foreperson / QA
3094e6d0-176c-4649-8114-1c3fb17f1f20 | checkpoint | Road Furniture & Sumps protected
5a4eccc8-cd0f-5a02-8f30-fb5a5e459358 | note | VERIFICATION ACTIVITY - Visual Inspection
42f1e396-c0d9-5a43-a2be-3b5681da6290 | note | METHODS OR REFERENCE - Crew Breifing Plan / Visual
f55a0dea-2d4a-55f5-8d4d-62868983ffe6 | note | FREQUENCY - Prior to sealing on each site
5a6f89ce-3c63-527f-8693-07bc20deeb55 | note | ACCEPTANCE CRITERIA - Protect all road furniture in accordance with Crew Breifing Plan. Fabric & protect all sumps.
cb1d391b-896a-5f33-a6fb-f809c43b7646 | note | HOLD / WITNESS POINT - Witness Point
2d34c56c-94bc-57f2-b569-51f269f4e39c | note | RECORDS - None
da727d5d-e3f2-55fa-8dce-2bb068923fe6 | note | RESPONSIBLE PERSON - Foreperson
f897cef3-5616-464e-9856-ec315f28c12d | checkpoint | Surface Condition/Temp
60f26011-38d8-5390-9319-7b11e4ec5e68 | note | VERIFICATION ACTIVITY - Physical / Visual Inspection
39ee4605-b53a-5fda-a349-c1aa4ab55889 | note | METHODS OR REFERENCE - Visual / NZTA T/3
9eb6c39f-5839-5ed3-a8ce-17c8c8630567 | note | FREQUENCY - Prior to sealing on each site
5b88cb74-bd2d-5eb4-8aac-e410c548cacd | note | ACCEPTANCE CRITERIA - Surface area shall be dry and free from any loose chip, dust, dirt, vegetation. Temperature recorded on site prior to sealing commencing
d33d06be-a844-528e-9ed2-f474fbda815e | note | HOLD / WITNESS POINT - Witness Point
7e13a1e0-da36-54e9-a169-c57461e797da | note | RECORDS - None
102c8bba-6366-5ca0-9120-14e74d93b64f | note | RESPONSIBLE PERSON - Foreperson / QA
cda8a75b-ddfb-491f-85c6-d3554869ca14 | checkpoint | Stockpiles
b529c606-7062-5642-977a-a8d91dbfbbd6 | note | VERIFICATION ACTIVITY - Visual Inspection
388ff826-4743-5308-baba-1581300c31e7 | note | METHODS OR REFERENCE - CBP
31554d94-64a8-58e4-82a8-1febc7b3c3ac | note | FREQUENCY - Each Stockpile
d9397fe2-ec8e-5784-bf1c-a7907b3ec982 | note | ACCEPTANCE CRITERIA - Correct Source, Grade and quantity. Uniquely Identified.
ca9591c0-b738-53e5-ac7b-5aba50e6c791 | note | HOLD / WITNESS POINT - Witness Point
f2eb0657-ee6b-5ad9-a7fd-91840a2f9ef9 | note | RECORDS - Sealing Data Docket
adf162fa-a504-5c56-8ad7-d89194018bc1 | note | RESPONSIBLE PERSON - Foreperson
89177b2d-3a56-4676-a19b-acc65dc30c14 | checkpoint | Spraying
56106492-10be-5ce8-bc53-6b987d8f3ba5 | note | VERIFICATION ACTIVITY - Paper Start and Finish all runs
1f8d9ef6-cc59-5265-b113-c5d942bcbbb7 | note | METHODS OR REFERENCE - Spray Runs
4939c459-3960-54bc-b5b3-b33dfbe1855f | note | FREQUENCY - All Runs
01216aaa-eb01-51d6-ad6d-3005082fe42a | note | ACCEPTANCE CRITERIA - Mark out start / Finish
b1c88459-58c3-5726-8fa8-ef7c8695271e | note | HOLD / WITNESS POINT - Witness Point
08f57fe8-0561-5f41-a290-d3a131d9c101 | note | RESPONSIBLE PERSON - Sealing Contract Engineer / QA
0ff66321-2bdd-4e6e-8f3e-418c851cdd78 | checkpoint | Sealing
18218745-f65a-53ba-a97b-bdb075a5af89 | note | VERIFICATION ACTIVITY - Longitudinal Joints out side of wheel tracks
1f42b9d7-d4aa-5565-b6fb-ad2b13404775 | note | METHODS OR REFERENCE - Spray Runs
1adfdd88-26c6-51cb-87b7-2fddadfc878c | note | FREQUENCY - All Runs
e598842b-7989-5a14-b255-0823df67cb9b | note | ACCEPTANCE CRITERIA - Mark out lane lines by construction team
e61df316-2f7a-5b8d-be66-bb7bd438d813 | note | HOLD / WITNESS POINT - Witness Point
371f534e-3cfe-5d18-8d6f-581789578ad8 | note | RESPONSIBLE PERSON - Sealing Contract Engineer / QA
920d94bb-8684-4007-9851-15b273195585 | checkpoint | Binder Application Rate
10dd4742-d07f-56b6-91b7-8339538910cd | note | VERIFICATION ACTIVITY - Tank Level dips prior to and after spray run
1dc07a81-5409-56fe-9571-531d2de1e2d1 | note | METHODS OR REFERENCE - Dipstick
48059586-5d48-538d-a517-d458937b210f | note | FREQUENCY - At Beginning of the day
049dc32a-90f0-502f-a33c-d53faf908311 | note | ○ After 1st spray run of site
9d1eb934-ca1c-52eb-bcee-3076161ba4bc | note | ○ After last spray run of site
4011c2a5-d693-508c-8607-e96c30700956 | note | ○ At end of tank prior to loading
7440e263-839b-55d1-8745-5251e4779785 | note | ACCEPTANCE CRITERIA - Quantities used to be within the desired tolerance of design Spray Rate
1eb285e7-9c90-574f-a02a-ace6bacba525 | note | HOLD / WITNESS POINT - Mandatory HOLD POINT
50c91244-1a85-52a7-9f2f-7bd8bc3374ee | note | RECORDS - Spray Sheets
78502455-b481-59f0-a404-a015a3c07804 | note | RESPONSIBLE PERSON - QA
788d4a20-7658-4f10-bbb1-f91c1c8df471 | signoff | AUTHORITY HOLDPOINT
8e93cf7a-eb6e-46a2-bab3-46b3fcc2cc54 | checkpoint | Chip Spread Rate
f6a3da0d-9889-5b49-b149-aae2ecd3c087 | note | VERIFICATION ACTIVITY - Visual
958a4cd9-f1dd-52bb-9b45-debaffb1c1e4 | note | METHODS OR REFERENCE - Crew Briefing Plan/Visual
f5b55ba5-5c6e-5245-b8f1-e808e95dab1d | note | FREQUENCY - On going whilst seal being constructed
56ee706b-283c-541c-a3e7-6ab9faaab8c5 | note | ACCEPTANCE CRITERIA - Chip is applied in accordance with the appropriate coverage as specified in the Crew Briefing Plan
53e439d7-7b5b-572b-b3bc-01526d2620b3 | note | HOLD / WITNESS POINT - Witness Point
ac2c9fec-3e01-588c-9626-3c1bdd4f6f6f | note | RECORDS - Data Docket
97bf4280-9ac6-5ce1-8801-ab3811cfcbf8 | note | RESPONSIBLE PERSON - QA/Foreperson
6e41cbfa-200c-492d-9550-fdf5f4252afc | checkpoint | Removal of Surplus Chip
1a09f4bd-0665-5431-829d-19f43b4d168d | note | VERIFICATION ACTIVITY - Physical / Visual
e1e375a4-d845-5326-b867-964ff8e9a5e8 | note | METHODS OR REFERENCE - Front Mounted Broom / Suction Truck, Downer Survey or MS Forms Post Seal Inspection
3e8fbe8c-292c-5fa2-b642-c2e940e34e67 | note | FREQUENCY - At conclusion of positive traffication within 48 hours
3de16c8e-16bd-51c7-9606-14b21c24c644 | note | ACCEPTANCE CRITERIA - All sump and road furniture protection removed. Meets requirements of P/17 Table 2.
d43d4a0c-4b77-56c0-9d06-7a25a97007a7 | note | HOLD / WITNESS POINT - Witness Point
6b5af8f2-189e-5527-b869-a0e2c07b68e5 | note | RECORDS - Post Seal Inspection
52be7210-9bbf-57a0-ae5a-404a732bcee2 | note | RESPONSIBLE PERSON - Sealing Contract Engineer / QA
a11901b1-48ac-4811-88e4-22d764d0494f | section | Post Seal Construction
6077e2f0-884a-4171-97c2-d562cead7296 | checkpoint | Post Seal Traffic Management
bb2983c0-0360-5d1e-a3cc-4e050dac6722 | note | VERIFICATION ACTIVITY - Physical / Visual
01c83253-e5e7-5578-919e-6e488c6997b1 | note | METHODS OR REFERENCE - As per TMP
d1a0a5bd-9a7e-5878-98ac-a04367bb1896 | note | FREQUENCY - Full length and width of carriageway
bac4151b-4024-50c3-a393-958e8d74cae8 | note | ACCEPTANCE CRITERIA - Minimum of 48 hours under normal traffic flow. If rain forecast within 48 hours, traffication recommences until clear weather window of at least 48 hours
0818d570-deb3-5dcc-aaed-a100a0238bba | note | HOLD / WITNESS POINT - Hold Point
bf34ccde-38b5-5c9f-affa-9d009371cd95 | note | RECORDS - Zeus or suitable recorded weather data
4664ad1d-8eac-5034-ab25-943130eb6747 | note | RESPONSIBLE PERSON - Sealing Contract Manager / Engineer
236b056c-58d0-4362-9c6e-7d0e240ed7b0 | signoff | AUTHORITY HOLDPOINT
0c9a4237-0062-43a3-ae72-dfaf4261c886 | checkpoint | Post Seal Inspection
066c9566-5b0f-515e-a393-214cc6d42a3e | note | VERIFICATION ACTIVITY - On Site Visual
aed14217-3aa6-5cf5-b7fd-cd912a6aca77 | note | METHODS OR REFERENCE - Lucidity Post Seal Inpsection
595c5426-6a89-5938-9230-4cbb578f15e1 | note | FREQUENCY - After sealing is complete
825082a7-a947-553a-93aa-4dbf3aa7e3f6 | note | ACCEPTANCE CRITERIA - Engineers requirements. Any defects identified, repairs programmed and costs estimated
bd831730-f430-53af-9691-25380d7c4759 | note | HOLD / WITNESS POINT - Witness Point
f1f9e735-43ae-553f-b84b-4eb74c883340 | note | RECORDS - Post Seal Inpsection
092923c3-0cb1-5820-9a6e-a64424b342b4 | note | RESPONSIBLE PERSON - Sealing Contract Engineer / Manager / QA
18fb86a2-a2f2-4346-a543-559b13a7d97a | checkpoint | Asbuilts and RAMM data
1861c79a-1a9c-58da-beca-415acba11db0 | note | VERIFICATION ACTIVITY - RAMM Update Sheet
5bee76e2-cfca-55f2-b786-d2789dcfb01d | note | METHODS OR REFERENCE - RAMM Database
1ec043cf-baa5-55be-a090-8bd8616db9e6 | note | FREQUENCY - After sealing is complete
b2776b25-f423-50bf-a1af-edbacb2291d2 | note | ACCEPTANCE CRITERIA - RAMM update sheet 100% complete and accurate, note data provided for RAMM update to be uploaded by others. As Built Drawing Complete.
51aff0d1-38c1-540e-bcb9-895343e2e169 | note | HOLD / WITNESS POINT - Witness Point
a6387424-cf66-5156-97bb-e498e3f1e069 | note | RECORDS - As built information / RAMM Update Sheet
eec144d8-1215-5f78-a741-a1f9abb6e653 | note | RESPONSIBLE PERSON - Sealing Contract Manager/ QA/QE
ec5dda9d-0860-4ea5-b0ec-d715252426d4 | checklist | ITP - GRANULAR REHAB INSPECTION TESTING PLAN Rev 1 | itp | ITP - GRANULAR REHAB INSPECTION TESTING PLAN
4a53e1ff-f0dc-47e7-9a1e-cbe79b2d4d1f | section | Subgrade
833a9c54-1516-47f3-a985-a2b77ba0cd24 | checkpoint | 1.01 - Field
217c5661-52f7-552b-a7ab-a5a90f6909ef | note | Material Test Method Requirement - Scala Penetrometer Cohesive soils only
3a65fdda-d08c-50f0-af6b-8a8e1d6dd4c0 | note | Reference Documents - RITS Table 3-20
133e5ec1-a90b-5583-b99d-ddd18d80a640 | note | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
7802ce43-eda7-5df5-a9ae-7ddfda0dfaf6 | note | Material Test Frequency - 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests)
46cc95f5-2963-5366-a384-28e51fa23d03 | note | ○ Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
2fdbc726-0ca9-51fc-a66d-28d8647cc7dd | note | Target Criteria - Confirm design assumptions - Scalar reaches minimum 2 blows/100mm
bff3ab40-b400-594e-886c-d7655d64c207 | note | Action Point Records Required - Test Record
9fd66279-5859-519f-9073-dd2a21c24c2e | note | Responsibility - QA / SE / PE
cee436d5-3e83-4280-8773-6d564c0c2a90 | checkpoint | 1.02 - Field
4da70fcc-7525-53db-9778-98dd519de912 | note | Material Test Method Requirement - Clegg Hammer Aggregate fill only where subgrade undercut or trench backfilled
fa1197f3-3226-58c7-9810-84d0197c4154 | note | Reference Documents - RITS Table 3-21
d8f05b8b-cbeb-559d-a0e6-809fc70de94c | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
f9fba30a-986a-5511-b004-c3c484204bb8 | note | Material Test Frequency - In centre of undercut or trench, Minimum of 1 test per undercut location
99177218-9f58-5063-946f-15058d750d23 | note | Target Criteria - CIV ≥ 15 or CBR of 20
22ab9787-a494-5022-8aeb-ef5d8454c99b | note | Action Point Records Required - Test Record
a1280a49-e622-5738-a646-f92f08eea303 | note | Responsibility - QA / SE / PE
b192725d-7c62-4542-ab98-63fcafedef5d | checkpoint | 1.03 - Field
8076f805-8775-5018-9627-10381b293b95 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
59a028f6-cd8c-5b79-b701-63d760caa071 | note | Reference Documents - RITS Table 3.24
225e2ba0-e5be-5752-9b11-20c6d8b5fffd | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
5ba26114-b3de-5845-891e-f6e3b4fdf545 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
ba4d9ade-1f23-5319-9ce1-a8d58737781a | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
7f22a1e6-6d6a-56b5-afc3-cd3e03d032da | note | Target Criteria - +0mm/-30m from design or nominated level
bc5bf8b8-25c6-5e47-b943-d374e460e63c | note | ○ No more than 15mm deviation from a 3m straight edge
d0e8e422-eebc-5e6f-a5c2-5aa632ee39c0 | note | Action Point Records Required - Survey record
44e73bf1-4759-5d82-a8d4-9125f088699e | note | Responsibility - QA / SE / PE
d8354076-7ff9-42c6-ae5a-01ed10a41a62 | checkpoint | 1.04 - Field
4ba8327e-d6e3-53b9-8c07-e8569bddc636 | note | Material Test Method Requirement - Tenser Triaxial Geogrid and Geofabric (cloth) installation
776e8d66-53a2-5ac0-b785-348fa908a026 | note | Reference Documents - Tensar construction sequence CS_TriAx/30.04.08
b1977f3b-775f-556a-9d1b-e9fb4ad0bb50 | note | Material Acceptance Criteria (Method) - Manufracture installation instructions
192439ae-aff8-5d75-ad84-858077eae986 | note | Material Test Frequency - 100% of Surface
74c5ab3f-aadd-533c-9791-25e1766c191a | note | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints.
ef61f35b-cc25-577e-a84f-6bb115d14cd5 | note | ○ Geogrid and Geofabric shall be neatly installed without creases or folds.
04eac2e0-38de-51b3-a298-e33d318cc6b1 | note | Action Point Records Required - Site Record
12eddcc3-4f6e-555a-a5c8-055a7872039f | note | Responsibility - QA / SE / PE
193100aa-64d0-4bb9-9a23-cf433515c84f | checkpoint | 1.05 - PQE
dfc1f7f7-7272-5839-8256-b2a6e2cfc245 | note | Material Test Method Requirement - Is the layer closed out?
af97ccbe-8dad-5e19-9367-e8665e611ae3 | note | Reference Documents - See PQE
475b2664-5e89-5a50-b7fa-b98e005952ef | note | Material Acceptance Criteria (Method) - See PQE
4027b42e-d650-5003-9c3a-07d71202b3cc | note | Material Test Frequency - 100% of Surface Prior to placement of material
02afbcf8-9035-5f8c-a837-ea8aed4da809 | note | Target Criteria - PQE Approval
f6d999d3-4262-599d-a764-5e78f437cf91 | note | ○ All testing record & reviewed as compliant.
6ef92a32-9ce2-5289-b63f-7e1a7296c25b | note | Available Documents:
0b1df901-e115-5587-86da-88da8de2d880 | note | ○ Test records
2fc702d2-3fe4-5804-bfae-27c4d1628b13 | note | ○ Survey records
177b54cf-79e5-51b3-9516-3e109b5b4ad9 | note | ○ Hold Point Records
bc7746a1-2c80-5328-9056-a9b6e020444a | note | Action Point Records Required - Hold Point
6ecb63a7-4788-5326-8b6d-67c0739d3a90 | note | Responsibility - SE / PE / PM / PQE
ea7637d9-d328-452a-99f4-47cb4daccad1 | signoff | AUTHORITY HOLDPOINT
09f00d49-f20e-400a-ac3c-554cabd17433 | section | Subbase
824f1692-c02a-4662-b0ca-40ca77f21aad | checkpoint | 2.01 - PQE
4e17b1ac-0e6c-5612-b1a2-c859db4c2c95 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
a1d01ca8-c4df-5e1d-9be7-59e5207a058f | note | Reference Documents - Insert Material Testing link
43a93335-8969-5841-b990-616de0075df6 | note | Material Acceptance Criteria (Method) - See PQE
8b55a06a-85db-5e89-a02f-bb5d54077ed2 | note | Material Test Frequency - Prior to construction commencing
49e30b3c-2d72-581f-a5fd-2e9651a12bda | note | Target Criteria - Material meets project requirements
9d8cd007-1f60-5f88-a075-83fc8c6173c7 | note | Action Point Records Required - Hold Point
3b7138fc-4818-5554-91d6-178db1867a85 | note | Responsibility - SE / PE / PM / PQE
1a7e6be5-6345-425c-9eb9-2b5340cc91a9 | signoff | AUTHORITY HOLDPOINT
81292115-f3ce-424f-a231-48c552055864 | checkpoint | 2.02 - Field
17612ea0-406c-5ca2-988a-f21a01188a08 | note | Material Test Method Requirement - Plateau Density Test
f5d4e46c-bac7-5c1a-bac6-b1231894b293 | note | Reference Documents - TNZ B/02: 2005
ec154a61-db3a-59a6-b7ec-35e2fb367ef5 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
3d9cf93a-d25e-50f3-90d5-99f746d59b7b | note | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing
53980568-45dd-5dce-8101-32374a313787 | note | ○ Target to be approved by Engineer
de7a4797-91b2-5828-986c-a00ad3240a5d | note | Target Criteria - N/A
54641c7b-c6b0-5588-81ab-2f4f8413dd81 | note | Action Point Records Required - Hold Point, Test Record
55ac252f-cf45-5103-b919-dc907a2b1526 | note | Responsibility - SE / PE / PM / PQE
cdaec728-0f73-4816-a5c4-7d033b54ca3b | signoff | AUTHORITY HOLDPOINT
9255d1d7-e612-458d-8c11-9172faa9f5bc | checkpoint | 2.03 - Field
2f62eb67-6927-5981-85da-9fe62505948e | note | Material Test Method Requirement - Clegg Hammer
dafe8cf0-4f8e-5408-bc00-1e843ad44045 | note | Reference Documents - RITS Table 3-21
a57c0813-5009-5942-87c9-9f4fb2e61bce | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
0a8904c6-432a-598f-8e39-ff96fdcbd0d0 | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
af16604e-49b8-54fc-ba4a-0e60b374ce28 | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
50e45a78-d000-5e33-aa0e-6dbeeb7bfe2e | note | Target Criteria - CIV ≥ 25
aec72f6b-d942-524e-9307-c7bb75b97c7b | note | Action Point Records Required - Test Record
507c570b-c473-55cf-a6c4-180b1415fb15 | note | Responsibility - QA / SE / PE
9cfb2c8e-643b-480d-a6ed-63c08a76c1b7 | checkpoint | 2.04 - Field
55cd34b5-e8e0-5c76-ac21-099599e61940 | note | Material Test Method Requirement - Compaction NDM Back Scatter
24b1889e-1a8b-591e-97c2-fef5dab1dec2 | note | Reference Documents - RITS Table 3-22
5739aecb-0001-5010-b6ec-4aada27b1540 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
2416baa1-627d-5eda-b0a7-dede97b2abc3 | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
77d54de2-a490-5510-9b3b-ccf7310aeea9 | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
fad2497c-62e2-58d2-a7ef-8c8467d478d4 | note | Target Criteria - Mean ≥ 95 % MDD
4b87e9b4-7cdc-58fc-aad9-a3603b29fc5b | note | ○ Minimum ≥ 92% MDD
b94ba9ce-ca36-59f0-a291-63486a70fce3 | note | Action Point Records Required - Test Record
db71aa11-d97b-56f5-8dfa-d08c35810b21 | note | Responsibility - QA / SE / PE
419e3731-9916-4002-8700-16dd875bc1c0 | checkpoint | 2.05 - Field
2461d8a1-2853-5b8c-8025-0ef0e9a41931 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
f9d1bc7c-be01-50a3-8a0f-3b09a4ab3cf3 | note | Reference Documents - RITS Table 3.24
256104bc-683c-5056-a2a5-4a161c812f7f | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
e8c5af2d-7e98-565c-b021-ab2d023e0380 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
6a483674-1b54-575f-b57f-71fc44a7537b | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
7c720fb2-ad5d-5502-a862-f1e351d49f62 | note | Target Criteria - +5mm/-25m from design or nominated level
9cd91d47-5290-51ed-8be1-251389ebc3c8 | note | ○ No more than 15mm deviation from a 3m straight edge
ff69ed24-a19e-54cc-85fa-10f1cd61794d | note | Action Point Records Required - Survey record
727b94e9-cbdc-543e-9e04-aa4d4db88200 | note | Responsibility - QA / SE / PE
6a31d294-738b-4e88-9227-88e3a9bcac30 | checkpoint | 2.06 - PQE
51aba292-d103-54b2-b5f3-987f90cbb452 | note | Material Test Method Requirement - Is the layer closed out ?
867ecb5b-1b55-52d5-9468-7f792c168f2e | note | Reference Documents - See PQE
62da9652-cc87-532d-bcba-156aba5ca1c9 | note | Material Acceptance Criteria (Method) - See PQE
8a4e3b41-5cd6-5d46-877c-8f3b46a91ba4 | note | Material Test Frequency - 100% of Surface Prior to placement of material
c0ac5202-6a89-5bb6-ac2f-e27199f3644a | note | Target Criteria - PQE Approval
bd913970-ce2c-56c5-bc4f-6901d92e0c39 | note | ○ All testing record & reviewed as compliant.
418155dd-cfb2-5b43-93ef-29d1c2292807 | note | Available Documents:
7300ffca-a510-5db4-bec1-fdb715909978 | note | ○ Test records
e1d84957-ca31-528b-9ef8-dc7d0c47304d | note | ○ Survey records
3165f9ff-0825-53a0-a093-cc5ad70113c5 | note | ○ Hold Point Records
55c09936-04d6-596b-bc65-577081b612e2 | note | Action Point Records Required - Hold Point
cc9a8145-6597-5b88-8df7-17c52704c2f2 | note | Responsibility - SE / PE / PM / PQE
12c97a93-326a-4806-b1ce-4dccec36e011 | signoff | AUTHORITY HOLDPOINT
bbc4dca2-dca8-4195-82fd-63bea379a723 | section | Basecourse
fa58b4ef-564f-4019-b5a4-4f1f7906102c | checkpoint | 3.01 - PQE
d89b9fd0-390c-5a4f-9ebd-af6416da7b32 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
11591ee0-5257-5bb9-9d3d-09e420021ce4 | note | Reference Documents - See PQE
0e160e31-dce9-5bb3-acfd-c8cdd11dfdb7 | note | Material Acceptance Criteria (Method) - See PQE
473a5e87-8f04-556a-9443-418988173346 | note | Material Test Frequency - Prior to construction commencing
753f9814-1f41-51a8-9cfe-82c958ffc466 | note | Target Criteria - Material meets project requirements
e18366fd-8422-5c52-a973-01ed37acbba6 | note | Action Point Records Required - Hold Point
5ac12076-488d-5ea4-b876-0e08c923ff77 | note | Responsibility - SE / PE / PM / PQE
3f4a1013-4ee4-42d0-bf8c-8e8a192df1c5 | signoff | AUTHORITY HOLDPOINT
d4d3109a-2d17-4e34-9296-f14e993d8781 | checkpoint | 3.02 - Field
5dd3f8d4-04d8-58c6-90b7-307d35dd5fa7 | note | Material Test Method Requirement - Cement application Mat test
f1d05917-8a28-5b24-897c-316826012acb | note | Reference Documents - TNZ B/5:2008
5db59e49-c1b3-58d8-93fd-753a58179c7f | note | Material Acceptance Criteria (Method) - TNZ B/5:2008
9c5d86fe-2806-58c7-9786-c294ab3fc986 | note | Material Test Frequency - 1 test per 400m² (minimum 1 per run)
e34469de-a6dc-5ae2-9708-c4db8acd1112 | note | Target Criteria - ±0.50kg/m² of specified rate
44944e70-a036-5651-9729-7bed04d17dee | note | Action Point Records Required - Stabilisation QA sheet
ce82c926-dc5d-52c7-ac4a-62a12ef6d108 | note | Responsibility - QA / SE / PE
6624ce3b-92e5-45cb-8c79-952fc0d973eb | checkpoint | 3.03 - Field
c60e5753-965f-5306-899a-ad6023cd49eb | note | Material Test Method Requirement - Stabilisation Depth
21b07c92-448f-5d58-a871-4f1b38af4b23 | note | Reference Documents - TNZ B/5:2008
34483f54-d26c-5e01-9d23-f409db9b4d88 | note | Material Acceptance Criteria (Method) - TNZ B/5:2008
860c0023-58f7-5184-b7ef-d17b5f898d6c | note | Material Test Frequency - 2 test per 400m² (minimum 1 per run)
08c336c3-6572-5a19-8008-f97594ad2b9f | note | Target Criteria - Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer
f31a62f0-dac9-5a5c-b634-4de1ba1d77a4 | note | Action Point Records Required - Stabilisation QA sheet
2aaa9f8a-8007-5530-85dc-d1aa7b4613fd | note | Responsibility - QA / SE / PE
e43e22df-4e18-4bd7-842e-22bfaac40124 | checkpoint | 3.04 - Field
e9d0b731-92ae-560c-9a3f-516254aa59a4 | note | Material Test Method Requirement - Plateau Density Test
dd87ffc1-b24c-5e5d-9d7e-b14196d72b64 | note | Reference Documents - TNZ B/02: 2005
6cd7dd11-43de-5417-b234-241a1b174b7d | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
65bc1887-c7e5-5d26-8d9a-dfb55a0c1ff6 | note | Material Test Frequency - 1 test per site
0a476c8c-6f92-598d-8509-9baec6159e4f | note | Target Criteria - N/A
fa2dc0b2-dea4-5478-a6c7-eb7fb1d4d5c4 | note | Action Point Records Required - Test Record
039e5309-b7fd-5152-9383-ba590f1ffe2f | note | Responsibility - SE / PE / PM / PQE
6d406241-86d7-4ffe-8ec2-9d678da10f00 | checkpoint | 3.05 - Field
c0e6d9e2-86b0-59c7-ae60-e1ca150c5f4a | note | Material Test Method Requirement - Clegg Hammer
c1af60b6-fb74-5f88-b6cc-c7e5b63f18ba | note | Reference Documents - RITS Table 3-21
5aa0d380-71e7-5445-a835-40ceeeb27cd7 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
87ac84c8-8380-5f45-881f-1faa6e947822 | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
1fcc8f37-32d9-5fde-b41a-f3c101ad2528 | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
f3b71b40-5464-547b-abbf-49d9c7cc99ee | note | Target Criteria - CIV ≥ 40
33f5ad8d-22d0-50d9-a290-3b7ca6efdd39 | note | Action Point Records Required - Test Record
23657f1e-dd33-512d-bd86-f5f498fec3a8 | note | Responsibility - QA / SE / PE
a0e7b3a4-e0b9-4874-a0f7-55d75e29eaec | checkpoint | 3.06 - Lab
b286bf9d-4a5f-5ea1-aa67-56dc816a2e66 | note | Material Test Method Requirement - Compaction NDM Back Scatter
8ab6dc35-0705-5963-9be8-4d3031f2b7a8 | note | Reference Documents - RITS Table 3-22
4fabbf8c-0259-5d78-b54c-3836b34b2c8a | note | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
4e260b44-d17e-56b6-91ee-c6f780f53d34 | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
1d305402-96a2-587b-8cee-d7b5ba17adcc | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
08502657-3607-5633-a3bf-6cbaa26f59c5 | note | Target Criteria - Mean ≥ 98 % MDD
285bb911-afa3-54a7-8dd7-900bb45dab76 | note | ○ Minimum ≥ 95% MDD
993e302a-6e44-5ce7-880d-a2429ebbc4f6 | note | Action Point Records Required - Test Record
f38ced75-9069-566b-baa2-2b446c3fd186 | note | Responsibility - QA / SE / PE
5f96699c-1b9c-4c42-a382-eb79c32b9b0e | checkpoint | 3.07 - Lab
0b4f2dbc-ebc9-50cc-a818-57c057f0c779 | note | Material Test Method Requirement - Benkelmen Beam Deflection Testing
9e1136cf-ebec-59e4-9fcc-eb185f28bd16 | note | Reference Documents - RITS Table 3-23
e29ab170-055b-5b27-ab1e-5a84f3f44556 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.5, ASTM D5874-16
23f12a18-9134-5b34-8ec7-8d1dfcd049af | note | Material Test Frequency - 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests)
85bb246c-c73d-5453-a34d-51e1792ef34c | note | ○ Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
8360afee-f16c-5e91-81f5-ab7d4479c1eb | note | Target Criteria - Max deflection allowed: 1.83mm
d2bfde77-f9b7-5a77-abc7-bfca8a7245de | note | ○ From design report - due to non-RITs compliant Subgrade CBR
bf080c70-0a74-588b-8026-bc7a52e94d1e | note | Action Point Records Required - Test Record
c881c64f-8672-5269-854a-b91892516da2 | note | Responsibility - QA / SE / PE
5504906a-b934-41de-91ed-e0f91a03632b | checkpoint | 3.08 - Field
fbc4b6a1-2917-530e-b17f-ee6da4ff873e | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
2a8ceb4d-386a-5b65-8a05-012a9d25ba27 | note | Reference Documents - RITS Table 3.24
e58e894f-5e40-58e0-98ac-4506e9c66f27 | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
6fafd489-d9d9-51e0-b23a-2ba8d7596d0d | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
1b8a4d8d-b30e-543c-8437-dd57675a2138 | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
143ff4a3-6ff7-5e72-8032-ee038a11ca14 | note | Target Criteria - +10mm/-0mm from design or nominated level
9a1e64df-c4c0-51d4-94f2-99e3468fcd58 | note | ○ No more than 12mm deviation from a 3m straight edge
dcaccffa-ce94-57c8-94b8-abfb32138237 | note | Action Point Records Required - Survey record
786943df-1e2d-5040-9e6e-2e60d14b4d7a | note | Responsibility - QA / SE / PE
d5c7f0dc-8d70-47f5-90a8-a53ab4f672ef | checkpoint | 3.09 - Field
d7cb7000-8fc5-522f-88d3-4e89c6cd3fef | note | Material Test Method Requirement - Visual Inspection of Basecourse Surface
3fdbaa6f-5376-5874-b9e1-3338717a6b94 | note | Reference Documents - TNZ B/02: 2005 7.8
c723dd8e-4f67-5133-a078-d9f0202e5ef5 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005 7.8
8bbc1d23-a12d-55eb-830c-5ac4a653b09e | note | Material Test Frequency - 100% of Surface Prior to sealing of surface
18c01434-e1e2-5c51-8ac3-196d987b407e | note | Target Criteria - Engineers Approval (The larger aggregate is held in place by with a matrix of smaller aggregates, the smaller aggregate is held firmly in place by fine material, and the matrix does not displace under normal trafficking or sweeping No evidence of rutting in surface)
44084d4b-0cee-5a5d-84ce-7cb6df73b5ba | note | Action Point Records Required - Hold Point
99de7704-b5ea-5aff-899f-7c1d521fcb27 | note | Responsibility - SE / PE / PM / PQE / ER
698878bd-a650-407e-8a95-a21eec1e7280 | signoff | AUTHORITY HOLDPOINT
0371f60c-3bba-41c7-af0a-814dd67a7670 | checkpoint | 3.10 - PQE
a5649b61-eb6c-5deb-a88c-22453df7b9ef | note | Material Test Method Requirement - Is the layer closed out ?
75a2432e-419e-5f6c-ab32-5da24dcff6ea | note | Reference Documents - See PQE
52e8b236-579b-5be8-866d-aa90a0671e49 | note | Material Acceptance Criteria (Method) - See PQE
da34bcfd-9d55-51c1-8883-e1e2d04ac1cb | note | Material Test Frequency - 100% of Surface Prior to sealing of surface
598cef2d-cf75-58c4-9103-d268905865a7 | note | Target Criteria - Engineers Approval
4812bbfa-f9d6-5377-a8be-bc6a3fa44f4e | note | ○ All testing record & reviewed as comliant.
ac8e2aa8-5af0-5505-ab41-11ead8e2e9e5 | note | Available Documents:
7b2ef9f7-55f2-50cc-ac01-a38151082f83 | note | ○ Test records
5b4f9d0c-5945-598b-bf1d-6e9dacf74e04 | note | ○ Survey records
75eecdc4-1920-5d93-a2a4-e64bf986b29a | note | ○ Hold Point Records
36ee847e-9da0-5014-b92d-2f42bb967c6e | note | Action Point Records Required - Hold Point
ccecc880-dbea-5b9d-8524-92e138a545b0 | note | Responsibility - SE / PE / PM / PQE / ER
a2ce9bbf-7703-4468-94fa-16ef2984a8bd | signoff | AUTHORITY HOLDPOINT
c9f5d6ed-04ce-4589-95cd-20998e550750 | section | Membrane or First Coat Seal
c87c0384-79d7-4a11-866f-12e1a206ffe3 | checkpoint | 4.01 - PQE
41ce1379-6134-5e8d-aac9-e5ecace1c190 | note | Material Test Method Requirement - Seal Design
70ef40bd-e452-5103-b7e5-cc3f8b6cac6d | note | Reference Documents - INSERT SEAL DESIGN
f1e10dc2-d103-59d8-91d6-9174361d0366 | note | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
94a02d35-418a-5739-8769-23050648fb49 | note | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
12d56daf-82ca-57f8-8906-ff6e248d7a3e | note | Target Criteria - Meets project requirements
6a4118fa-cbac-52b5-b8c0-2c31e7c0a711 | note | Action Point Records Required - Hold Point
1fa47671-537a-5309-83bd-3e378bb583bb | note | Responsibility - SE / PE / PM / PQE / ER
e6beebda-227e-4010-86a5-74751e774afe | signoff | AUTHORITY HOLDPOINT
f52e49df-a1e1-4108-bf8e-30c0e78769bd | checkpoint | 4.02 - PQE
be365c2e-5fc7-5108-b195-7e4407502aa2 | note | Material Test Method Requirement - Bitumen Sprayer
3a4df9eb-52b5-5050-a816-40453de118eb | note | Reference Documents - TNZ P3
3ea963ec-43b9-59c9-aecc-b2f2a1492fb6 | note | Material Acceptance Criteria (Method) - Certification provided
a90d80ef-bd47-548b-a089-94341a9fc6c7 | note | Material Test Frequency - Prior to starting
176c992e-f692-55ba-b233-b446df7b4704 | note | Target Criteria - Current E/2 Certificate
6f5a5165-ac24-5302-88a1-fea9a01560ba | note | Action Point Records Required - Certificate Sheet
afd8424c-8ccf-5def-bb1e-a9ee14af8810 | note | Responsibility - SE / PE / PM / PQE / ER
7e3f6728-288d-4db1-bb9d-80ce8b85e4a8 | checkpoint | 4.03 - PQE
8875da92-7d31-5d67-aea1-7d6ad0ec427e | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
cd73aec3-88e2-5b30-bd70-0059cdbc503d | note | Reference Documents - Insert Material Testing
6101360e-4f2c-5e33-96de-48906f65d10a | note | Material Acceptance Criteria (Method) - See PQE
1994c5fe-ee3d-57f2-b99b-9afe29e11cc8 | note | Material Test Frequency - Prior to construction commencing
d2f9d746-bcf6-53f0-89f6-b044699d8e35 | note | Target Criteria - Material meets project requirements
2c5ffbd1-38aa-538d-bc92-3fd73c4ac65e | note | Action Point Records Required - Hold Point
98d1f77e-c544-5868-a3a9-15b9a3da7679 | note | Responsibility - SE / PE / PM / PQE
ff25151a-1cf4-4048-99b3-bc31a3201356 | signoff | AUTHORITY HOLDPOINT
52cb18a1-caf9-41ae-b1ab-20635c432ed1 | checkpoint | 4.04 - Field
9337bdc2-855d-5fb4-b9e9-904ad65b091a | note | Material Test Method Requirement - Preseal Inspection
392617a4-7b02-546b-8632-c6585bfa609f | note | Reference Documents - TNZ B/02: 2005
bf8a7d3f-059b-59dd-a468-c064eefc5950 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
c7b20a21-eb7f-586f-b2c8-d306fefbada4 | note | Material Test Frequency - 100% of Surface Prior to sealing of surface
a16589c9-a040-5ab6-af40-d19436cbe45f | note | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
982ca5a1-1785-5acb-8006-22959e8d36c3 | note | Action Point Records Required - Test Record
909321db-6de9-55d5-9c06-ee741acfb48d | note | Responsibility - FM /QA / SE / PE
8d3ef751-8293-4431-a953-120f59ab9913 | checkpoint | 4.05 - Field
43395f88-cc7b-5268-ab63-0dd844797380 | note | Material Test Method Requirement - Degree of Saturaton
0b5cf5ec-8bc1-5f5e-8ba2-e4ebc277ae6c | note | Reference Documents - TNZ B/02: 2005
e47e1254-ebbb-53fb-bf15-de2521b56ee9 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
eec30acc-984d-57b5-90a8-b1993647bed3 | note | Material Test Frequency - 1 set of 5 per 1000m² - then 1 per 200m²
4eeb90e8-b2cf-5171-9983-eb3990a95a04 | note | Target Criteria - < 80 % Completed Max 48hrs before sealing
294f2947-cdfc-5351-9e50-85e77eb58d71 | note | Action Point Records Required - Test Record
aeffbe2a-a7e6-5005-858e-7f7c2fcc1f93 | note | Responsibility - QA / SE / PE
ccd95ac4-5471-46af-8f75-934c6dabe64c | checkpoint | 4.06 - Field
f0055c25-3c12-5969-8e0f-e88baba3bd10 | note | Material Test Method Requirement - GO/NO GO Survey
487f1283-7984-5c48-b3e6-c05d8ed22938 | note | Reference Documents - Downers processes
b941304e-f89c-5ef5-8099-3282b5480953 | note | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
76180cf3-3f8d-529f-bff0-50b82c03c2fa | note | Material Test Frequency - Prior to sealing on each site
54fbb06e-8f7f-5275-9120-7ff77ce564cd | note | Target Criteria - Pass on GO/NO GO, Marginal & discussion with contract Manager or Written approval from Rehab manager
d9aa6425-cf7c-5cb5-85d0-a79a159ef17c | note | Action Point Records Required - Survey record
46514b4a-1fdb-503a-9b80-2c3f9d212c92 | note | Responsibility - QA / SE / PE
e2e83c43-1ca3-4637-803f-ab682fdfc820 | checkpoint | 4.07 - Field
7a135c46-629b-5820-a2ff-a3245a7b4202 | note | Material Test Method Requirement - Road temp
3ac80d12-ae6b-5f2c-93b1-7c5800b61b6e | note | Reference Documents - TNZ P3:1995.18
8fc698ec-76e7-5355-836d-2ed059f11158 | note | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
2469b369-fbcf-5eb7-a020-fe489f5c350c | note | Material Test Frequency - Once per day of sealing prior to sealing commencing
8fd3a21d-8554-5da7-acbd-4bc352dc9b02 | note | Target Criteria - Air temp >10°C
cc7d61dd-f81e-5642-bf3d-bbef158a4c64 | note | Action Point Records Required - Spray sheet
157fc9aa-492e-5ea4-8075-34d63e83a809 | note | Responsibility - QA / SE / PE
a83ea12b-9caa-4734-801f-4af57a119854 | checkpoint | 4.08 - Field
bdaa1955-9d8c-5bb8-9e7e-d1e8b7c77351 | note | Material Test Method Requirement - Application Rate
aa725496-7e7b-5e4b-be9a-a7bf865fcba1 | note | Reference Documents - TNZ P/3 : 1995.18
09448168-a52d-5079-ad59-ef395aa53814 | note | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
f73cd632-85d9-57ef-8946-b1cd668a2d42 | note | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
9881e53f-9dea-54b2-a2db-62655264074a | note | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
d167f5a6-cb56-5dbe-b762-92d78de90b65 | note | Action Point Records Required - Spray Sheet
d8759027-e115-5aae-9847-5e6ab5f51aaf | note | Responsibility - QA / SE / PE
27ad8de6-8d55-4b83-99bc-bad5ab18432b | checkpoint | 4.09 - Field
56978a08-56c2-5c9f-9bef-5bc646d8b076 | note | Material Test Method Requirement - Chip spread rate
02a5ab45-3923-5f4e-ba45-11c750b14a09 | note | Reference Documents - TNZ P3: 1995.21
ab0fbfa3-e25d-5bec-9c6f-9c1bec7754a0 | note | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
442a4db2-e2be-5b12-9010-25efdca8b1f2 | note | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
be57aef9-a295-5e09-900f-1cd1a203a8f8 | note | Target Criteria - Visual checks meets seal design requirements
cb0ae1da-6619-5e41-971e-d7275a77e27a | note | Action Point Records Required - Witness Point/Spray sheet
1e69589f-2d8d-5754-9a2c-f7f92a1dcf7b | note | Responsibility - QA / SE / PE
0b1656b1-cdd0-4e62-b083-c8db27801250 | checkpoint | 4.10 - Field
d391db62-d282-527e-81fa-a2e03055fb75 | note | Material Test Method Requirement - Rolling Checks
8bc85263-68f0-5c8c-af1b-dcdfaef87fd9 | note | Reference Documents - TNZ P3: 1995.22
4b15e85e-1174-52dc-a966-e15f60b63e11 | note | Material Acceptance Criteria (Method) - Sealing Record
bfaed682-a215-5af1-aa5f-68f24aafd871 | note | Material Test Frequency - for each sealing site per day
00c39a84-270f-5159-ac47-dc857e7cf715 | note | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
fdc8b082-4046-5513-9278-660c66573a3c | note | Action Point Records Required - Witness Point/Spray sheet
170e2039-f457-5c9e-8fc8-abea08dd7481 | note | Responsibility - QA / SE / PE
b17bef5a-b03f-4efd-9ba6-c9421db8b76f | checkpoint | 4.11 - Field
5412f4b2-5e6f-5d6a-b338-8607f98b5824 | note | Material Test Method Requirement - Post Seal Inspection
72ce7dbf-8387-5a94-a649-8a173305fc82 | note | Reference Documents - TNZ P3: 1995
37d54f49-d378-5cad-a714-1c3bf78b3410 | note | Material Acceptance Criteria (Method) - Engineers Inspection
4d75cd0f-2093-574e-8a5c-a3aea63381d6 | note | Material Test Frequency - After sealing
9c103069-96c9-514a-8147-82fb279af508 | note | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
7bc3005e-ec81-513b-84b3-76715deef1d9 | note | ○ Line marking has been reinstated
3540f5f6-f945-53bb-9653-aa9dc731826b | note | ○ All excess chip has been removed from site
d356802f-2926-57df-8bab-735a336e1eb5 | note | ○ All CPs are clear from filter fabric and excess chip and any excess material removed from on top service covers.
06f4260d-1527-5607-9a94-4abf9636934c | note | Action Point Records Required - Hold Point
6a513f12-6b0f-52be-a9c0-427897495ba5 | note | Responsibility - QA / SE / PE
9dbf2c11-6f60-43ba-97dc-50aa0a1dd61f | signoff | AUTHORITY HOLDPOINT
69364a53-2226-4365-b90a-95db596666c6 | section | Post Construction
99e1def4-ca59-43f1-a8cb-f5dec0f2fd0b | checkpoint | 5.01 - PQE
d0f35973-bf8f-52a1-a824-9d37004c6267 | note | Material Test Method Requirement - Asbuilt and RAMM Data
1090b273-c9f5-5d0f-9537-6042b57cac06 | note | Reference Documents - RAMM Update sheet
bc9bc198-ae79-5f9e-a679-a200de1ef063 | note | Material Acceptance Criteria (Method) - Asset Management Information Plan
f79655bf-f5a4-5bfd-a4b5-2dbd8d339ded | note | Material Test Frequency - After works complete
9829020b-afbc-52e1-b469-61122eb669dc | note | Target Criteria - RAMM sheet 100% complete and accurate .
56c7e62e-8a19-5778-b4f7-1c87146b3402 | note | Action Point Records Required - RAMM Asset Update sheet
24532aa0-0c2f-5110-ba9a-323b7027ef2f | note | Responsibility - site engineer / Project Engineer/PQE
b5bee41f-b361-484c-8c2c-dff0c3663947 | checkpoint | 5.02 - Lab
39960cf4-5076-52fc-be10-b1b0978d9f36 | note | Material Test Method Requirement - High speed Rutting - Road Roughness
7f72cada-6816-5ff5-aa49-4ef1b56a8828 | note | Reference Documents - CCA DOC
3d53d405-edb6-5445-b2b4-612a9ac36f42 | note | Material Acceptance Criteria (Method) - Laser Profilometer Survey
53bca1be-65bf-59ed-8845-bc36b8a6eaa5 | note | Material Test Frequency - After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability
741c5def-2719-5cb4-9a2e-da25948d5b44 | note | ○ All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths
5b3c3025-4dd0-556d-85e1-703875d056ae | note | Target Criteria - High Speed Rutting: > 5mm Report to Designer
52a6f1ad-442a-5719-b127-c8d20469361b | note | Action Point Records Required - Test Record
be4bfb58-7cec-55ef-8234-ab35003709ea | note | Responsibility - site engineer / Project Engineer/PQE
a432b6be-8ad8-4a22-b213-47c4e299bbd0 | checklist | ITP - STRUCTURAL REHAB INSPECTION TESTING PLAN Rev 1 | itp | ITP - STRUCTURAL REHAB INSPECTION TESTING PLAN
ed2f1c1c-0c72-43e7-869b-c962a807c4ec | section | Subgrade
9f9eb795-3e32-424c-9805-5e2f7e383d76 | checkpoint | 1.01 - Field
83dd20eb-d88d-5cca-9a26-1a35b7431106 | note | Material Test Method Requirement - Scala Penetrometer Cohesive soils only
d7fec1b2-f63c-5e24-9998-ea9d6ae9de08 | note | Reference Documents - RITS Table 3-20
e5b0912b-5edc-5154-88df-2fa571823835 | note | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
e380152b-ceac-52ee-ae96-d321f79e7ade | note | Material Test Frequency - 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests)
abf12906-d37d-509d-a431-21cce82c1c23 | note | ○ Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
68729cd6-be26-5338-88ef-5a04f650121c | note | Target Criteria - Confirm design assumptions - Scalar reaches minimum 7 blows/300mm
c86ddecf-f3b4-59de-8f8f-351c88d00dfd | note | Action Point Records Required - Test Record
d7640c3d-951b-57cd-9b88-61d72038490a | note | Responsibility - QA / SE / PE
2d06ac0e-1dad-487e-ae3f-6fa72309abb2 | checkpoint | 1.02 - Field
1e7ab05a-46d4-5e56-b438-b269b7bd0459 | note | Material Test Method Requirement - Clegg Hammer Aggregate fill only where subgrade undercut or trench backfilled
ad2aaad3-fbbb-564f-91fd-de2629bd00ee | note | Reference Documents - RITS Table 3-21
ea6e231b-43a3-5a38-b5cf-4be7d15b2bd1 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
a4bbaed3-50c5-584a-a5d2-ee34e01189b7 | note | Material Test Frequency - In centre of undercut or trench Minimum of 1 test per undercut location
bb70b9eb-38c3-56df-a4ee-6bf5ce5976d1 | note | Target Criteria - CIV ≥ 15 or CBR of 20
437eaf52-9bda-5f41-a800-1ebd36ddeb0a | note | Action Point Records Required - Test Record
e89d3361-c686-5036-8991-900d78d9f0d3 | note | Responsibility - QA / SE / PE
4f06fc0a-7392-4c6e-b381-aa5a6086ceb5 | checkpoint | 1.03 - Field
fb7bf29d-3d8f-5073-b0ac-181540de1c68 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
9a72360e-2450-5c09-b14b-bf2ee2c19f66 | note | Reference Documents - RITS Table 3.24
a346496c-67ec-5614-9c7f-d370a061e9e7 | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
f8ffc8e8-f876-5da1-86c8-d565f14c9f44 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
a8548cc7-00f5-56d5-a3c9-1f8025d4dedd | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
72a0244b-d623-5155-a787-914fd3e43318 | note | Target Criteria - +0mm/-30m from design or nominated level
db47f28f-5779-575a-a33b-bae4b67b3521 | note | ○ No more than 15mm deviation from a 3m straight edge
4a3524e2-3cb9-522c-a11c-32c5f8785e45 | note | Action Point Records Required - Survey record
610a7e85-942a-52c4-8bcc-2834b66f993c | note | Responsibility - QA / SE / PE
782def2c-3436-4036-9f34-57d16e80f2e5 | checkpoint | 1.04 - Field
6444c82e-1657-557b-88ab-66a6e1d6ffc1 | note | Material Test Method Requirement - Tenser Triaxial Geogrid and Geofabric (cloth) installation
7978ee5c-6ee8-56ab-83f0-caf5a7d963a1 | note | Reference Documents - Tensar construction sequence CS_TriAx/30.04.08
fd9f1c38-95da-5f6d-98d2-12c75f68d1ce | note | Material Acceptance Criteria (Method) - Manufacturer installation instructions
d3e620fd-5d77-52c0-b69d-7bb2cdcee57f | note | Material Test Frequency - 100% of Surface
f01ad8fe-8dc1-5c8d-8deb-26de06319f86 | note | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints.
31ceeba8-10d4-5e46-8f7d-41dafd03f9b0 | note | ○ Geogrid and Geofabric shall be neatly installed without creases or folds.
b78c8054-5e6b-5d39-a602-389f4f282c92 | note | Action Point Records Required - Site Record
e925d51a-78b1-5df3-98ab-90f1955232cd | note | Responsibility - QA / SE / PE
7595520e-1d13-47b0-b2a4-ff628b0b6e07 | checkpoint | 1.05 - PQE
408513dd-2693-5790-a61d-dcf6509e556b | note | Material Test Method Requirement - Is the layer closed out?
f7336156-6d4a-5792-9e3b-129e604eac8f | note | Reference Documents - See PQE
0944a583-edc0-5cd6-abe1-9f1a84420820 | note | Material Acceptance Criteria (Method) - See PQE
b0a9b218-b9d7-5b6f-be3c-be7f8488b99c | note | Material Test Frequency - 100% of Surface Prior to placement of material
9124b237-6f47-503f-9eb1-dafba5559857 | note | Target Criteria - PQE Approval
52049364-bb1c-55a3-b523-149984b67a51 | note | ○ All testing record & reviewed as compliant.
f87bf984-58a5-5184-8106-a241a59d6a82 | note | Available Documents:
b92cb638-5127-5d06-8646-7a99c00176a8 | note | ○ Test records
db124d70-023c-5a2f-9ce7-6cc815bee769 | note | ○ Survey records
868007fc-6be4-5abb-a731-be1eaf06e4c4 | note | ○ Hold Point Records
a3d3c43b-578f-520e-ad2f-2936889bb82a | note | Action Point Records Required - Hold Point
4b208ca8-f3ba-5c31-aeab-3a1872cf2a1d | note | Responsibility - SE / PE / PM / PQE
e70dc611-cf89-4b5f-b245-50037ed809fa | signoff | AUTHORITY HOLDPOINT
425b2afd-789c-4183-93dd-83d43ab27697 | section | Subbase
5456715f-f02c-43e2-8d44-68b43100f5ab | checkpoint | 2.01 - PQE
f39b84ed-d56f-5475-a326-5e23ebc854d3 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
e702bd3c-a3a3-5a0b-a4dd-3e245aade11c | note | Reference Documents - Insert Material Testing link
78b0dfa0-085d-5569-935d-1aa8969be135 | note | Material Acceptance Criteria (Method) - See PQE
8dddd834-3b81-5445-a90c-148e96e09b56 | note | Material Test Frequency - Prior to construction commencing
17942e98-3028-5ecd-a4d0-38a609180a16 | note | Target Criteria - Material meets project requirements
0f735402-85b2-52c5-8280-d16bc2334a09 | note | Action Point Records Required - Hold Point
be997440-b8ce-5977-a737-94efe7da529e | note | Responsibility - SE / PE / PM / PQE
cea3c451-5eab-4029-ba9c-41bd4acab313 | signoff | AUTHORITY HOLDPOINT
0b935037-2c8b-48bc-a743-5b553cae0262 | checkpoint | 2.02 - Field
fe437cb5-0b5a-5a37-b7b7-9a267eb20d2c | note | Material Test Method Requirement - Plateau Density Test
3d9bff9f-9010-54d7-bec0-624af08eb4a2 | note | Reference Documents - TNZ B/02: 2005
3449acb9-02c4-5a7f-a146-53f9e00fef23 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
ce739100-9655-57a8-b730-d2b7f4531e90 | note | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer
d6d44070-a443-5b0b-8aa6-e317b881501f | note | Target Criteria - N/A
95e47d95-37c4-5dc8-ba72-7616f35dcb7f | note | Action Point Records Required - Hold Point, Test Record
e47a4c89-8ab4-5479-9b07-bb03869cc768 | note | Responsibility - SE / PE / PM / PQE
44131022-14ae-4e95-b161-0cec3f9193de | signoff | AUTHORITY HOLDPOINT
da2f7e2c-05c5-4431-9990-cd8d01a36bb0 | checkpoint | 2.03 - Field
c4bba904-07bd-59a3-ac20-85c0d8278e40 | note | Material Test Method Requirement - Clegg Hammer
6da8dbcd-ed8e-5dde-b491-73be485d9ff4 | note | Reference Documents - RITS Table 3-21
ba3182e0-5157-5673-8706-cc632b9c02dd | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
7a1dfb6c-0e29-5423-a00d-08160a86abad | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
858ba4ec-090d-57da-be04-b66dd6e43476 | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
0a49bce7-8f56-535d-850e-a5f7de783c1e | note | Target Criteria - CIV ≥ 25
5c4ef9b8-36dd-5150-826b-e204b9b9ea0d | note | Action Point Records Required - Test Record
530775b3-4e90-500c-9542-787bccfea5e5 | note | Responsibility - QA / SE / PE
c829c3b2-34ef-41cf-9584-f1d451e639b0 | checkpoint | 2.04 - Field
8ac03dbd-dd94-553b-923d-b85bf8c241e8 | note | Material Test Method Requirement - Compaction NDM Back Scatter
bec9dc1a-98ae-5530-a3c2-354391ae8015 | note | Reference Documents - RITS Table 3-22
1cd50b59-3351-56bc-8459-ac8528cce809 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
208c94ab-7af2-55f9-8534-f6b900d5cf7e | note | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
a5f04211-0bf8-5093-be97-9bcb5fab281d | note | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
ec4c4467-690d-51d7-9d46-425badbd717d | note | Target Criteria - Mean ≥ 95 % MDD
52e62f4d-d4bb-53ec-86d5-1a0e278e077f | note | ○ Minimum ≥ 92% MDD
ad0ed00f-e8cf-5f6b-93a0-133b395c4b2d | note | Action Point Records Required - Test Record
de6b53b2-6d82-5f8a-8f02-219a0a289723 | note | Responsibility - QA / SE / PE
d0819259-ea6c-47bd-87f0-587c87dd4df7 | checkpoint | 2.05 - Field
43ef66f2-04c7-5e07-8d51-aa30dff9ee04 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
42629ad7-f119-55b8-baef-4bb2dcf9a383 | note | Reference Documents - RITS Table 3.24
69ac5100-6b33-5127-90a9-436723342f43 | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
eb3c0327-f1d9-5a04-b7be-aeef70c041d9 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
fc87979f-ca9b-54fe-9463-8c5e76009e2d | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
0a6bb718-2046-54c7-98c1-04114e2e2a33 | note | Target Criteria - +5mm/-25m from design or nominated level
2dcf72a5-da0c-5e00-b9fb-065d32019736 | note | ○ No more than 15mm deviation from a 3m straight edge
596d7d2b-a181-58f1-9868-4e6692fdd5a3 | note | Action Point Records Required - Survey record
7d8c89f6-f8ee-5ef8-a8a9-c6cd0c614b86 | note | Responsibility - QA / SE / PE
edac930a-3913-41c6-bfa4-ae7bc6eeb24b | checkpoint | 2.06 - PQE
6ff6404e-794d-5cb9-9894-6b15acf7a1f2 | note | Material Test Method Requirement - Is the layer closed out?
e6ed3098-2650-590e-aa69-3bb91f5b40f3 | note | Reference Documents - See PQE
cd0f387c-77c0-5652-8b38-c9bb4f84ce31 | note | Material Acceptance Criteria (Method) - See PQE
d91a534f-f662-5ce7-998c-13b769171479 | note | Material Test Frequency - 100% of Surface Prior to placement of material
a0aaad04-9ed2-5676-b639-67ec2e24d7f0 | note | Target Criteria - PQE Approval
a123d0cb-291c-5f8a-a417-1df986637bcb | note | ○ All testing record & reviewed as compliant.
fdf8007a-2095-5391-bb96-0d7095d96357 | note | Available Documents:
488f7cb5-e622-5db2-b3f2-07c60d3df7df | note | ○ Test records
6141ee7e-9b0d-517c-ad6c-36fd1a1f271d | note | ○ Survey records
0f3ddd01-c70e-5945-8bc3-e30c9c1cf5d0 | note | ○ Hold Point Records
7f82ec50-4ba2-5483-acbf-5b5b7853aa1d | note | Action Point Records Required - Hold Point
44fe665e-5f8e-5478-bd79-b6e95d087157 | note | Responsibility - SE / PE / PM / PQE
e2b9a67d-1f4f-4ac8-910f-2efe129b69bd | signoff | AUTHORITY HOLDPOINT
9ca32040-50ea-458d-b78f-2415f98424a4 | section | Membrane or First Coat Seal
eaaee871-5189-49b4-8e9b-2deaafdea006 | checkpoint | 3.01 - PQE.
829f6a4b-86db-5a27-af40-eea65ee117f1 | note | Material Test Method Requirement - Seal Design
9ed8ad2d-8ee5-5283-9cbe-8fc77093f601 | note | Reference Documents - INSERT SEAL DESIGN
8bf8800c-4299-5b62-9921-b64c8e89f21c | note | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
8b23908d-5926-5796-b7a5-067fb00ffd70 | note | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
649eef1e-f6fb-5b93-941f-3df1ae9a650f | note | Target Criteria - Meets project requirements
cab5c74d-58b8-5b67-945d-21cb24635e00 | note | Action Point Records Required - Hold Point
64dd4c67-0377-5bf2-8217-131d9efc4d45 | note | Responsibility - SE / PE / PM / PQE / ER
4abb4d0b-7cb0-4b2a-a8fa-8e6f5ad1f929 | signoff | AUTHORITY HOLDPOINT
e432ad2a-0b38-4f24-9ebe-403e664fff16 | checkpoint | 3.02 - PQE
95447a1b-8147-5520-ab33-6b3ad5b6c951 | note | Material Test Method Requirement - Bitumen Sprayer
e46bba72-c4df-58ab-9c85-0331eb693e01 | note | Reference Documents - TNZ P3
65395671-aae0-51c2-8ad1-57fcd12fd05b | note | Material Acceptance Criteria (Method) - Certification provided
bdee1325-51f0-5635-ba61-b57c548443c8 | note | Material Test Frequency - Prior to starting
e82a07a3-3014-59e2-9e02-d3fb335dddf2 | note | Target Criteria - Current E/2 Certificate
1e6169a5-214b-5d80-8ec3-8816b028995f | note | Action Point Records Required - Certificate Sheet
e511e1b3-f838-5317-909a-d074c70c0e3a | note | Responsibility - SE / PE / PM / PQE / Era
2419210d-1321-47c6-a719-36d9ea30e0ea | checkpoint | 3.03 - PQE
a5242764-6ea7-5917-aa17-778da73cdbba | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
5fcdb352-3b2a-5d9d-838e-3b5f90cae371 | note | Reference Documents - Insert Material Testing
0727c617-b7c8-5651-a363-e5369c254735 | note | Material Acceptance Criteria (Method) - See PQE
7f50c619-1db5-55e4-945f-2122688cf992 | note | Material Test Frequency - Prior to construction commencing
b0a47dd6-2ef9-5ee6-abef-71a870ca7e4e | note | Target Criteria - Material meets project requirements
13b67c3f-ed21-5fce-a783-597a7422572e | note | Action Point Records Required - Hold Point
5525912a-a183-5ec3-95f8-807089426e43 | note | Responsibility - SE / PE / PM / PQE
a81bdc02-fc94-47c8-af24-0d6e352fc6b8 | signoff | AUTHORITY HOLDPOINT
c95407b9-e857-411b-9ff6-b3ba4e25c163 | checkpoint | 3.04 - Field
db05c041-a4f7-54bf-ad01-ae50dd18936c | note | Material Test Method Requirement - Preseal Inspection
9a25afdb-5e62-5f1d-aff0-5dc32fd9f138 | note | Reference Documents - TNZ B/02: 2005
40cffd30-bedb-5264-8c73-722f11b701ea | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
4f228b03-6f49-504b-ade2-115a971df52f | note | Material Test Frequency - 100% of Surface Prior to sealing of surface
4c828742-0603-5646-a944-b9b69ea4b2aa | note | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
5b170bed-0e45-5808-97bb-eabcf5c5c8ba | note | Action Point Records Required - Test Record
c2846382-0350-5b53-8c74-da278ff34af4 | note | Responsibility - FM /QA / SE / PE
0f747620-5f62-416e-9e54-f99f4a969111 | checkpoint | 3.05 - Field
6816269e-f098-5d16-a80d-a8150c56c473 | note | Material Test Method Requirement - Degree of Saturaton
c42d3424-ff07-5d3f-90d8-68e505ba1c09 | note | Reference Documents - TNZ B/02: 2005
64501425-62ca-58aa-9048-18f2a6fbfe4b | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
eb1a163e-0f72-5c39-a13b-5282cd91f33b | note | Material Test Frequency - 1 set of 5 per 1000m² - then 1 per 200m²
a526c021-ea2f-5100-9100-5c46dd88a474 | note | Target Criteria - < 80 % Completed Max 48hrs before sealing
d5985ecc-6e4b-5e2f-bb3b-ad04cb4ad937 | note | Action Point Records Required - Test Record
8a91fec9-503f-5996-95c2-23ff192baab0 | note | Responsibility - QA / SE / PE
2af63280-a66d-4483-943f-3de0882ba2b5 | checkpoint | 3.06 - Field
0f770f35-41de-581c-bb24-1b492b4286ff | note | Material Test Method Requirement - GO/NO GO Survey
8776e696-d184-567c-9552-15320a949307 | note | Reference Documents - Downers processes
ea542827-4ff5-555b-ae1c-78b7ec2851c8 | note | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
bd290bb4-ce40-5406-abda-95283939a036 | note | Material Test Frequency - Prior to sealing on each site
1e5352f1-db09-56e4-beb9-3cf948f09ad5 | note | Target Criteria - Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager
e3cf381e-642d-53d0-a9f8-2fbc2cbd8ab8 | note | Action Point Records Required - Survey record
17b85a33-a940-542a-84e2-4208971c822e | note | Responsibility - QA / SE / PE
800b3b3e-b349-4ad7-81a8-07b32aa014cc | checkpoint | 3.07 - Field
1c06b392-9215-5f99-abcb-916696b6fef7 | note | Material Test Method Requirement - Road temp
79e84a91-b784-5c97-bc36-72133bc9765d | note | Reference Documents - TNZ P3:1995.18
4c04e2b0-0e85-5386-b81d-713c4c8ca855 | note | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
027bc837-2e19-5c08-8518-0ed31588a5d6 | note | Material Test Frequency - Once per day of sealing prior to sealing commencing
eda8a95e-0855-50f0-92b8-9ea17bbf95b0 | note | Target Criteria - Air temp >10°C
e3cf7935-bf2e-5ae0-8aba-9525d02b8c58 | note | Action Point Records Required - Spray sheet
9ae2d44c-3f90-5e3f-89db-0fd80aa0b1b7 | note | Responsibility - QA / SE / PE
f411d882-e91a-4a92-847a-896e4d76dc17 | checkpoint | 3.08 - Field
11a6b816-5487-592a-9d9b-0baea9622b31 | note | Material Test Method Requirement - Application Rate
7c0fdbfe-2fd8-52e7-9f51-24de45b5519d | note | Reference Documents - TNZ P/3 : 1995.18
440598d8-88d3-5716-a5f2-d57a5414f1c6 | note | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
565b240f-5598-5055-8bfe-1ff2b19adfcd | note | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
1ff48aa3-7c33-52e0-84c9-89b6559c0b6f | note | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
e75ddb50-2a70-5764-9bfa-baa6ac4ba899 | note | Action Point Records Required - Spray Sheet
33474055-c7b4-51d6-8701-ffef804d7c12 | note | Responsibility - QA / SE / PE
38869e7a-1c83-455e-8c7a-7391cdc12047 | checkpoint | 3.09 - Field
249422b6-5cd3-5e32-938b-98ba0d543ef0 | note | Material Test Method Requirement - Chip spread rate
298f15e2-166f-532b-844d-0688bf709a1f | note | Reference Documents - TNZ P3: 1995.21
a717ae2f-5262-5bf5-92d6-2bb46c28131c | note | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3), Chipsealing in New Zealand (pg 435)
d28a4e6d-6875-55cf-8308-51baa7182f4e | note | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
23149d55-6246-510b-96a6-102221922550 | note | Target Criteria - Visual checks meets seal design requirements
b1ae87d4-45ca-571a-8ebb-5e793dce4bd4 | note | Action Point Records Required - Witness Point/Spray sheet
8e3cb14f-4d34-5ac5-a4d7-e4ef11559226 | note | Responsibility - QA / SE / PE
a948f589-5c6f-402c-8f2b-73efca3b4b9d | checkpoint | 3.10 - Field
4655f788-ed72-5638-9f77-e90e93beb65e | note | Material Test Method Requirement - Rolling Checks
cb0672d2-c3fc-54e7-9986-f05a7cbf06c1 | note | Reference Documents - TNZ P3: 1995.22
32dc68b1-523c-5dce-859f-8504c490998f | note | Material Acceptance Criteria (Method) - Sealing Record
c76d2fd3-98d1-5eba-a074-30017d37ebba | note | Material Test Frequency - for each sealing site per day
926ac038-6b3e-5b5c-b834-bcbe44f2792d | note | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
103bdd56-de3d-5648-9d61-639fd3d535cd | note | Action Point Records Required - Witness Point/Spray sheet
4f4caccc-c454-5f1b-b6e6-6f063351cd11 | note | Responsibility - QA / SE / PE
a178d55d-98cd-493a-8f75-fd0a09cb7919 | checkpoint | 3.11 - Field
ef7525a4-0afb-5db2-a3dc-4941cdb85a0a | note | Material Test Method Requirement - Post Seal Inspection
d39e484a-05e4-5afd-92be-6ca2bf78a622 | note | Reference Documents - TNZ P3: 1995
aac293e9-f2a5-5e97-9bb5-cdaeea9322d0 | note | Material Acceptance Criteria (Method) - Engineers Inspection
67202766-d85d-5b63-a457-3bbde14a9872 | note | Material Test Frequency - After sealing
12054c9f-c12c-5bd1-b91b-11a31e462749 | note | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
61b0f736-2bdc-55d6-b197-5d87fd465e59 | note | Action Point Records Required - Witness Point
5ad7eeb3-fd0c-50c6-84d6-bb0b0ca1ffed | note | Responsibility - QA / SE / PE
d8513920-839d-4b11-8331-944878bdb532 | section | DG and AC Mixes NZTA M10:2020, SMA Mixes NZTA M27:2020, PA Mixes TNZ P/11
cc4cd08d-90a2-45fc-9690-c4900b1330c9 | checkpoint | 4.01 - PQE
03ab5605-7885-554e-a201-e6d618c40a28 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
b617fda2-60d2-5061-8e58-0ba4a4f5327e | note | Reference Documents - Insert Asphalt Design & Material Records NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines
a5eab962-4425-54cd-93ee-5cbf4a66d1c2 | note | Material Acceptance Criteria (Method) - Approved Treatment Design
295f55cd-7474-564d-bf6f-f98e4da5e3c1 | note | Material Test Frequency - Prior to paving works commencing
d87a73da-759b-5418-a927-9089f4c08ace | note | Target Criteria - Treatment Design validation
5e2e04b3-3abc-5297-a5c3-a53af64495fe | note | Action Point Records Required - Hold Point
c2b11687-7b32-5c61-8e0b-2d1a3a9618c5 | note | Responsibility - SE / PE / PM / PQE
92d5b945-eb63-42d7-b67d-ac0ffb9aa9a4 | signoff | AUTHORITY HOLDPOINT
f2dc4bcf-6ae9-4824-9039-4ad569f18586 | checkpoint | 4.02 - Lab
db23a61d-2cd5-5a85-99bb-22580314fa24 | note | Material Test Method Requirement - In-situ mat density calibration cores
f5899597-053c-580d-a588-24fc320ab027 | note | Reference Documents - NZTA M10:2020 9.9.1, NZTA M27:2020 9.9.1
4ec42ec8-3ad4-5df4-b102-4e14484b2973 | note | Material Acceptance Criteria (Method) - ASTM D5361
a9625ac0-4146-5a3d-a801-3e5250fd578d | note | Material Test Frequency - One test per 900 t of asphalt plant production
26a770ae-db1a-53b9-b70d-eac3359aa69d | note | Target Criteria - Characteristic value - mix design air void +3% -2%
63bfa68b-e5c5-58e9-8f0c-8050b3fb8454 | note | Action Point Records Required - Hold Point
3d3ce661-0272-5422-86ad-44c9da122e7e | note | Responsibility - SE / PE / PM / PQE
bc8ae5a4-cf0e-417f-921a-d6795049a475 | signoff | AUTHORITY HOLDPOINT
d722bca6-2ad7-46d0-866a-df7b4ee19016 | checkpoint | 4.03 - Lab
87b9a9d5-348b-5de8-986b-0656d2569407 | note | Material Test Method Requirement - Grading (Particle Size Distribution)
9df70da6-06ce-50db-bc0f-748b4bde2095 | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
204fc621-f770-5fc6-9435-d918e3bcd6bb | note | Material Acceptance Criteria (Method) - NZS 4407:2015 test 3.8
a2140b49-2157-5faa-923f-690d38c46664 | note | Material Test Frequency - One test per 900 t of asphalt plant production
9c2ec068-edfb-5229-8ffd-b44227c12431 | note | Target Criteria - Tolerance from nominated JMF grading as per
62204bf0-886d-542d-909c-dfea9890bb0d | note | ○ NZTA M10 Table 5.3
e1e9d656-7e1b-5429-84e5-9652a70f4b8b | note | ○ NZTA M27 Table 5.3
6eff57b3-71d8-5fb4-9e9a-06af5d36cb5c | note | ○ TNZ P/11 Table 7.1
591587bc-6572-55d7-a872-22cfb2a6d890 | note | Action Point Records Required - Test record
c337748a-7293-526e-b681-cbf53673c81d | note | Responsibility - SE / PE / PM / PQE
201da1c4-2703-4b7f-9fb5-dbc046b78dcc | checkpoint | 4.04 - Lab
b0aec730-5203-5723-918e-8b643d1c7e8b | note | Material Test Method Requirement - Binder content
8765b322-50ee-5146-9418-c1184db1c76f | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
39e0d41c-78f5-5ad9-8089-4a27a9229593 | note | Material Acceptance Criteria (Method) - ASTM D2172
9280f8ce-d8c4-5665-9eaf-ef6c7a462c44 | note | Material Test Frequency - One test per 900 t of asphalt plant production
c02a3560-da84-5e57-8c93-ffb8dbe48598 | note | Target Criteria - Tolerance on JMF
07381507-3617-5c8f-8811-c61db14c5635 | note | ○ Individual ±0.5 (All)
6dc63d23-9c08-5f95-b77e-ea0136f9330f | note | ○ Rolling Average of 3 ±0.3% (DG, AC, SMA)
cd7d297f-ee2b-5799-99e3-01488fe61b7c | note | ○ Rolling Average of 3 ±0.4% (PA)
931d136e-e743-58c9-b518-594a9227fc64 | note | Action Point Records Required - Test record
c2a57365-48a4-5fb2-bec2-0aac63ef1b12 | note | Responsibility - SE / PE / PM / PQE
b2e22d94-771c-4cfa-b719-191e2977bb1e | checkpoint | 4.05 - Lab
7188c1f2-0cf9-554b-ae02-772b8b4d98d5 | note | Material Test Method Requirement - Air Voids
326b7412-27b8-558b-9918-fe9b5f710ac1 | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
6fe197c2-74d5-5f08-a971-3ccbcb9e6faf | note | Material Acceptance Criteria (Method) - ASTM D3203-22
35f8d412-e184-5d15-90da-a22197199620 | note | Material Test Frequency - One test per 900 t of asphalt plant production
b5b9c78d-ef46-5293-9924-83f0293b8785 | note | Target Criteria - As specified for each mix type
f74061a8-cfe2-5d26-a066-face8f9cc51a | note | Action Point Records Required - Test record
366c71ac-d0c6-5b53-87d1-384b965cb91f | note | Responsibility - SE / PE / PM / PQE
95c8e71f-98ee-49a8-b64f-013b7c0bc45c | checkpoint | 4.06 - Lab
6a0582ec-3f3f-57c8-92e5-529e84bb1650 | note | Material Test Method Requirement - Maximum Theoretical Specific Gravity
decbf91b-bf49-5061-ba65-a89aecbfa08e | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
1a2d1159-2be1-50cd-9ec0-cb45d6710f66 | note | Material Acceptance Criteria (Method) - ASTM D2041
48147a46-ab8c-513e-bb00-7a6b324cae32 | note | Material Test Frequency - One test per 900 t of asphalt plant production
694ec183-8c9d-5377-81bb-6919fc54d39c | note | Target Criteria - Report Value
cdbd5e73-ddda-52e3-87f4-1d65ebc51666 | note | Action Point Records Required - Test record
419a830c-da46-55b8-9c46-c224fc0b873a | note | Responsibility - SE / PE / PM / PQE
c20845c3-ccbd-4bd3-9d97-a96cceddedf7 | checkpoint | 4.07 - Field
88bee2ec-f686-54cb-8a21-a710eaea4f4d | note | Material Test Method Requirement - Load Locate
e83eba02-76ae-525e-8a42-4fe8593bb43b | note | Reference Documents - Downer Procedures
a7e5c555-c3e3-5656-97ab-e5211354f01a | note | Material Acceptance Criteria (Method) - Each load can be indentified to a location. Record includes:
c2b61529-84fe-5dd1-9489-f757f3fbbd52 | note | – Truck ID/Rego/Driver
3d12f4f6-6c51-500b-9e90-2b088e75b8e1 | note | – Depart Plant Time
f3a4200f-35a4-5681-843a-169e0c04c2ea | note | – Arrive Site Time
fa30dfe7-fe8b-5376-a222-ab03afb05b92 | note | – AC Temp on Arrival
3889a381-b014-5791-b01d-a3654851c667 | note | – Ground Temp on Arrival
f35f0789-dd6f-5b7f-aaba-c803240f27d9 | note | – Tonnage
6ff753f6-f608-5fef-981d-e7b58e895527 | note | – Run Width
e264a5a6-9e3e-51ee-8841-b4cef5c660d7 | note | – Estimated Run Length
76ef0a28-cf11-5c30-952b-3cc4a25996d3 | note | – Calculated Area
86e1ecfd-0888-5a58-8502-c15e5a9b62d6 | note | – Calculated Average Depth
957999f9-3a71-5c95-9845-12ea76885e71 | note | Material Test Frequency - Every Load
a1471619-d002-5875-b006-275c904c152f | note | Target Criteria - All data is collected
43c7f9b4-f67a-5128-b3a1-071fdfca0200 | note | Action Point Records Required - QA Sheet
205820a2-fcfb-52cd-a7f2-e154e377c5e6 | note | Responsibility - QA / SE / PE
25ec27a4-bf7e-498e-8e2b-597462d6a7d3 | checkpoint | 4.08 - Field
e8c1e572-1a70-5a7e-9436-0fe9fe0ef28d | note | Material Test Method Requirement - NDM Density Testing On-Site Mat and Joint
9e12e809-737c-5b16-abde-69391e490242 | note | Reference Documents - NZTA M10:2020 9.9.1 and 9.9.2, NZTA M27:2020 9.9.1 and 9.9.2
f537e9b1-a296-5a99-b389-b69f67601a59 | note | Material Acceptance Criteria (Method) - ASTM D2950, ASTM D5361
a75f5fac-3e0f-561a-96ad-731ae697b75b | note | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot)
6ac0d290-5410-5171-b58b-fe7f24d5a874 | note | ○ 1 test per 100m per layer length (min 3 / Construction lot)
13840120-5fbf-54e2-9ec1-b3262cc2fb46 | note | Target Criteria - Mat: Mean air voids JMF +3,-2
c10ad175-511d-5405-ba93-c7fb2826e663 | note | ○ Join: Mean air voids JMF +5,-2
9dbd1423-58b6-5e74-bfeb-6eba536ee02b | note | Action Point Records Required - Test record
ee87f9cb-9d28-5739-a3a9-74ab564d6f49 | note | Responsibility - QA / SE / PE
b09cb4f3-be47-4a9f-bcb9-fde89e0ca7ba | checkpoint | 4.09 - Field
4b79e4ff-d168-5290-a19f-a264ef9c3ea3 | note | Material Test Method Requirement - Surface Level- Stringline checks for validation
21f96f03-d5b4-5727-92ab-a473ffe927e1 | note | Reference Documents - NZTA M10:2020 10.2, NZTA M27: 2020 10.2 Downer Procedures
494c2550-74a3-5fcd-99c1-070a451f219b | note | Material Acceptance Criteria (Method) - NZTA M/10
b9ba6700-f771-576e-a527-d1b03f1f2af5 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
ed803c8b-e6b2-5876-9a53-0fea451e1fd5 | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
9852a97f-de06-5a8f-9630-1fe235326d55 | note | Target Criteria - +15mm/-5mm from design or nominated level
5596f386-d448-525c-80bc-6c9b3e75bd23 | note | ○ No more than 8mm deviaton from a 3m straight edge
d417b127-4357-51bb-856b-9dbaa11b94b5 | note | Action Point Records Required - Survey record
35e5a2b6-9096-5983-966a-30cf63cbdf13 | note | Responsibility - QA / SE / PE
ca405c39-9409-418c-b38a-d4a8b43c5e39 | checkpoint | 4.10 - Field
cafb8d5f-a482-5f82-bf97-dd530aeff262 | note | Material Test Method Requirement - Post Surfacing Inspection
181f69eb-413d-5164-bf56-126f9a93d99e | note | Reference Documents - CCA Procedures
b3f7922c-5628-5ece-8b2d-80b6dfdb9b6d | note | Material Acceptance Criteria (Method) - Contract Specifications
6b440ce3-7e2d-575d-8ce8-cef9907b6ad9 | note | Material Test Frequency - 100% of site After surfacing (within 5 days)
06b1c1cd-72de-513a-86df-bfad1b259621 | note | Target Criteria - Line marking has been reinstated
575702c4-97df-5b3e-bbb6-405d5b5d1607 | note | ○ All excess material has been removed from site
d7b9f9f6-2d4c-5511-991b-f4e1f580e09f | note | ○ All CPs are clear from filter fabric and any excess material removed from on top service covers
05fa6542-c271-58ff-acdc-126e992cc261 | note | Action Point Records Required - Hold Point
92106a43-6019-5f14-ac9a-668b98c858df | note | Responsibility - QA / SE / PE
90cd4623-96f7-49ac-b580-25c47c133a01 | signoff | AUTHORITY HOLDPOINT
1480edf6-8491-4f4b-810a-acc2c2e7a22b | section | Post Construction
ea79340e-bbeb-4705-90db-3922df072186 | checkpoint | 5.01 - PQE
200b8d7f-eb52-555e-81a6-14a8ef9c2ecd | note | Material Test Method Requirement - Asbuilt and RAMM Data
f72a5a35-5a9d-5fa3-ac08-785c2b3e34dd | note | Reference Documents - RAMM Update sheet
997e9c06-cb09-5010-8a31-762138fe1cdf | note | Material Acceptance Criteria (Method) - Asset Management Information Plan
103e55de-c1be-56b9-b5c6-e26003c8fe64 | note | Material Test Frequency - After works complete
568fd26e-add3-5183-abc8-4a569e24df97 | note | Target Criteria - RAMM sheet 100% complete and accurate .
ad4ccd32-1e54-5272-816c-573b6b01e7de | note | Action Point Records Required - RAMM Asset Update sheet
80e4faf6-3e0e-5e5b-9ed1-4802167fa8c4 | note | Responsibility - site engineer / Project Engineer/PQE
60220e8c-2f9c-42db-8b9f-eb5ac4c1f963 | checkpoint | 5.02 - Lab
cf2bd284-6073-5252-b705-00215da3e177 | note | Material Test Method Requirement - High speed Rutting - Road Roughness
86568a45-4e7c-55aa-a3ab-d6c3536961d4 | note | Reference Documents - CCA DOC
8ff5ad7a-f279-571f-9157-60693a2714b1 | note | Material Acceptance Criteria (Method) - Laser Profilometer Survey
dd2c5e16-d01e-5d20-87c5-e837b0c2ddae | note | Material Test Frequency - After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability
22c10ade-f858-5b6f-874f-bc9a2866cbe0 | note | ○ All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths
5595abbd-9639-57c2-8ab0-86d03629d0f6 | note | Target Criteria - High Speed Rutting: > 5mm Report to Designer
c175a12d-8a11-57fd-a3b9-2d52c5a47819 | note | Action Point Records Required - Test Record
b1c3ecc6-3fc1-5cd3-8dbc-83f33c2eaa6b | note | Responsibility - site engineer / Project Engineer/PQE
9a911928-9827-4c3e-a4ac-b457581d55cd | checklist | ITP - TAC Renewal | itp | ITP - TAC Renewal
e04be66a-348f-4316-ae2b-1646366ff188 | section | Details
f4926249-1624-49cc-9673-a89dabe507a3 | checkpoint | Office
8ee91b88-276e-53e2-ad57-04badb148bef | note | Material Test Method Requirement - Weather
e7df02ea-3e71-5bdc-954d-a2ec769ef7ec | note | Material Acceptance Criteria (Method) - Consistent dry weather with no significant rainfall.
cdf4be2d-e33f-52a2-92c1-89314da47d37 | note | Material Test Frequency - Prior to construction commencing
87337665-b722-56e0-85b5-9359d80a48b7 | note | Target Criteria - Ground temperature 5˚C min for structural asphalt. 10˚C min for wearing course.
8f63d7a3-91bb-517f-9244-3713525e6a91 | note | Action Point Records required - Hold Point
0bc30df3-1e7e-555b-be37-150d2b15f9c6 | note | Responsibility - Downer Contract Engineer
8817fa8a-521a-4adf-a02f-a11ee85f1180 | signoff | AUTHORITY HOLDPOINT
ffa5bdd1-4146-4f25-981e-c726394c7606 | section | 2.00 - Milling
dee9f5a5-cf4b-4877-95fa-577829865489 | checkpoint | 1.01 - Field
70bdfb34-b9cd-52ca-9904-e765413bedc9 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
cceb9250-913a-54c9-8d6d-eaac51dd5d77 | note | Reference Documents - RITS Table 3.24, NZTA M10:2020 10.1
fc6d4b69-5d35-5179-b269-bea387625c4f | note | Material Acceptance Criteria (Method) - String line or GPS rover
bd18e143-42c0-58d6-b650-34366f83bd45 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
01fc649e-675d-5b86-a454-808559afac92 | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
ba8d6fe3-4044-57cd-a384-07ee640e5a49 | note | Target Criteria - +15mm/-5mm from design or nominated level
70c58f8a-3fd0-5661-972c-7c055af5f924 | note | ○ No more than 8mm deviaton from a 3m straight edge
29c59a47-54b5-5a79-af1d-87153aea6e0c | note | Action Point Records required - QA Sheet
d9794eed-e349-5dbf-bf7c-e4d9e459e610 | note | Responsibility - Supervisor
18d640a9-6d72-4dfd-951d-3e75743af296 | checkpoint | 1.02 - Field
0b3ff5a3-3d08-5424-85f1-1014c8b6ff1d | note | Material Test Method Requirement - Surface Inspection
c5001b51-477c-5cb2-9e4d-a83b4c7d6502 | note | Reference Documents - NZTA M10:2020 9.2
4d477a69-a79b-5240-a8c5-2e6a259cc525 | note | Material Acceptance Criteria (Method) - Visual Inspection
32ec48d4-3af1-561f-b1fb-dc4b8c21c158 | note | Material Test Frequency - 100% of Surface, Prior to paving
826183a9-3d3c-5fa1-9b20-2e4c1d2cc37e | note | Target Criteria - The surface on which the paving is to be laid shall be free from standing water, and any loose material, dust, clay or foreign matter shall be removed by sweeping.
c2730032-c0bb-5630-bdc7-0f3cae2f49f8 | note | Action Point Records required - Hold Point
5c2e38fa-d4b1-5a03-bb65-80a02b85e788 | note | Responsibility - Supervisor
06056102-4e9f-4f9c-bf17-6ce479590c30 | signoff | AUTHORITY HOLDPOINT
4070d105-315d-4ed3-b4c1-79fe7832eb02 | checkpoint | 1.03 - Field
6caee2e4-7f38-52a8-97ab-1f84d4a331af | note | Material Test Method Requirement - Does the surface pre-treatment meet project requirments?
7ff72507-c589-5898-81e0-dfa0ac3543a9 | note | Reference Documents - NZTA M27:2020 9.3, NZTA M10:2020 9.2, NZTA SP-M-032
3de0d123-0138-5bc2-8b22-6ff29caf3285 | note | Material Acceptance Criteria (Method) - Design requirements
875ea3d6-684b-5317-9d83-69c6a1672002 | note | ○ Visual confirmation after milling
50915996-26ee-5e27-9d6f-bf0ca01f55d2 | note | ○ NZTA SP-M-032: Step 4 Bond and Seal
c677223d-185f-5700-8f85-64a39120566a | note | Material Test Frequency - 100% of Surface, Prior to paving
b4ec7237-e2f8-5c02-b634-28f907f3d2c3 | note | Target Criteria - Is the suggested surface pre-treatment still suitable after inspectiing the milled surface?
7a6792c9-a63d-5da3-9bea-bfa3ac777ddc | note | Action Point Records required - Hold Point
71c671ee-1346-54eb-a94f-23a8678cd02c | note | Responsibility - Supervisor
7877b210-abd0-4181-b60c-0b4493427f96 | signoff | AUTHORITY HOLDPOINT
1787a463-db49-463d-842f-f34280226573 | section | 3.00 - Surface pre-treatment Membrane or Chipseal
bbd65626-f413-4ae4-a817-fec7aa5d73e2 | checkpoint | 2.01 - PQE
41312b79-8262-55e6-8614-acb22ebc70a3 | note | Material Test Method Requirement - Seal Design
e22de0fa-bf7a-5a53-92f8-e311f2619a77 | note | Reference Documents - NZTA M27:2020 9.3, NZTA M10:2020 9.2, NZTA SP-M-032
f59efe04-c7c8-53e7-9a73-fcf059dc7d17 | note | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
d43846b6-33a8-5f50-80d5-b97a3abfb27e | note | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
228f4d26-bc5f-5895-b00f-cc893b1f007a | note | Target Criteria - Meets project requirements
b26f3371-f5c5-5cbe-b2c5-295ea6560557 | note | Action Point Records required - Hold Point
5a07d45e-0ebe-59f1-a4e3-c1b75014d11a | note | Responsibility - CCA Project Engineer
0833ff7d-827d-4cf8-921a-df34c9c028c5 | signoff | AUTHORITY HOLDPOINT
194b950c-d9c0-4f91-8876-591b7e32c642 | checkpoint | 2.02 - PQE
7b234ffc-2ede-5f6f-8c7a-b95c21aca957 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
6ecb18c4-5a0c-515f-af89-411f49467f8e | note | Reference Documents - Insert Material Testing
b1beef31-7666-5542-b9e7-4c2d00637b54 | note | Material Acceptance Criteria (Method) - See PE
9de69bb1-ff0f-55f4-b4ff-3e6d976159f5 | note | Material Test Frequency - Prior to construction commencing
66347bea-01b7-583a-9c53-8cf7db1fefe7 | note | Target Criteria - Material meets project requirements
d59d00f3-29d4-56eb-b7e5-86597e4b466c | note | Action Point Records required - Hold Point
54607e7f-ee4f-51ba-b343-b4443c66ca61 | note | Responsibility - CCA Project Engineer
77376e9b-daeb-4efd-9bbc-7cad1d81299e | signoff | AUTHORITY HOLDPOINT
17963075-5f78-4119-9345-ecfbbcf174a2 | checkpoint | 2.03 - Field (1)
36b2cb36-01fb-509d-a61b-b4ee5f213aac | note | Material Test Method Requirement - Preseal Inspection
71fda52e-a1f3-5f5c-98d6-aa665dd03843 | note | Reference Documents - TNZ B/02: 2005
cbf1d0de-bc70-5542-865f-b7da9bf0982f | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
65f7c6de-954f-5b8d-aa6a-f1b20a59842c | note | Material Test Frequency - 100% of Surface, Prior to sealing of surface
c19494da-1032-5257-80cd-8911987ad917 | note | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
679c063e-b25e-50a3-9bcd-a081bc109113 | note | Action Point Records required - Test Record
73db7d84-74a5-5c65-be7f-d973680ffa85 | note | Responsibility - Supervisor
371689ff-d250-4b2e-b6c7-f01e19dbeb9f | checkpoint | 2.03 - Field (2)
c0a240f1-daa3-570e-8f51-ff31eddfcb2e | note | Material Test Method Requirement - Road temp
af8d475b-ca4f-52aa-afde-0b1f8fdd24f7 | note | Reference Documents - TNZ P3:1995.18
07c6d6a7-daac-5b9d-9657-522c0b772e1a | note | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
68dc80d0-e897-527f-a44a-9b41c05c4ce0 | note | Material Test Frequency - Once per day of sealing prior to sealing commencing
4a7cec92-d588-5cd5-a701-e2c90a10161e | note | Target Criteria - Air temp >10°C
873bc365-2ad6-5c69-a9b5-94c68ddfe96c | note | Action Point Records required - Spray sheet
817c1eab-439f-57c7-ab82-ccd597ba123e | note | Responsibility - Supervisor
24cafd7e-43d5-4000-aea8-3524d4648351 | checkpoint | 2.03 - Field (3)
5a05c05d-fe35-514a-b138-fa4c08bbeb92 | note | Material Test Method Requirement - Application Rate
7b370a75-7d16-583f-8be9-73899185f2fb | note | Reference Documents - TNZ P/3 : 1995.18
832d0d8d-0554-520e-845a-0d3a50ce17d7 | note | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
dbac3175-e2af-5eb2-8951-8b304884e5d2 | note | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
a9b80857-b1b4-5ef1-88fa-52a6831e26f7 | note | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
ca58ad43-4edb-540d-a33c-95659d8accd4 | note | Action Point Records required - Spray Sheet
bb706290-5cc5-5fa2-a5aa-8a2fa1b856db | note | Responsibility - Supervisor
1cdf7209-af42-4400-9309-7e0f5d7d49d8 | checkpoint | 2.03 - Field (4)
070bd473-8749-54b3-b035-c3257f3bdc95 | note | Material Test Method Requirement - Chip spread rate
c91a7b15-45c9-5c77-8cdb-1c1607ea8f58 | note | Reference Documents - TNZ P3: 1995.21
96ce2b1d-8ea9-535f-b6ad-1a48d4f435b1 | note | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3)
35af36ae-44c3-5bec-a464-098934d92f97 | note | ○ Chipsealing in New Zealand (pg 435)
9fb6227e-d813-530e-8158-f30025f37e53 | note | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
5f8514a8-ddca-5a33-b4f3-403886086648 | note | Target Criteria - Visual checks meets seal design requirements
7341526b-7f1a-535f-bbcb-22493caaf992 | note | Action Point Records required - Witness Point/Spray sheet
cceacc53-cfe5-50a8-8c46-2af5f9e3f3fb | note | Responsibility - Supervisor
8439baed-411c-4e0c-a409-af3ae656a67d | checkpoint | 2.04 - Field
34fbd1af-fe15-5435-abe3-02765c21a7c5 | note | Material Test Method Requirement - Post Seal Inspection
99472524-eaee-53db-8ad3-839210b81394 | note | Reference Documents - TNZ P3: 1995
a6329da5-f4b4-5f53-9e08-ffa103442b08 | note | Material Acceptance Criteria (Method) - Engineers Inspection
80ef79a3-2497-525c-a38a-437ed3cc163f | note | Material Test Frequency - After sealing
4a592916-f853-5e84-bb47-a7adc3fffd90 | note | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
b0f81ff9-2b28-523a-b036-4b344a0ab73f | note | Action Point Records required - Witness Point
d8be4432-b236-5eac-94c0-c4927dea47d3 | note | Responsibility - Downer Contract Engineer
e7e3272f-8960-4d8b-9ba5-c6490a4ea582 | section | 4.00 - DG and AC Mixes NZTA M10:2020, SMA Mixes NZTA M27:2020, PA Mixes TNZ P/11
bc3b0a5b-af1b-4131-9651-eff59e6782bc | checkpoint | 3.01 - PQE
94d3c4cc-b523-5a9e-8359-608f480a6328 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
c5bb8b68-716c-545c-82ce-2536fd28183e | note | Reference Documents - Insert Asphalt Design & Material Records
d5e8726c-5b8d-5378-bb50-955d4a56122d | note | ○ NZTA SP-M-032 Asphalt Surfacing Treatment selection Guidelines
0bc2ac08-f398-52b2-b6a9-20111c658328 | note | Material Acceptance Criteria (Method) - Approved Treatment Design
dea2faf3-a934-5b7d-91b3-f065b6557677 | note | Material Test Frequency - Prior to paving works commencing
4c494a1f-8c6a-5d12-8456-2eb0adca91e6 | note | Target Criteria - Treatment Design validation
aec21f6e-7132-53b2-9c62-7ff7024d41ea | note | Action Point Records required - Hold Point
e5f6d5e6-ec12-5f65-a9a1-50b17348ee07 | note | Responsibility - CCA Project Engineer
4e6e3cda-7f2e-42e5-80e3-7bf4f735e2e0 | signoff | AUTHORITY HOLDPOINT
3ca395d6-f62c-4249-85cd-10d1bdfce134 | checkpoint | 3.02 - Lab
474c0392-4cac-5f4e-94cf-05a5abe39420 | note | Material Test Method Requirement - In-situ mat density calibration cores
7fc704d4-800e-538f-a230-b448949b1448 | note | Reference Documents - NZTA M10:2020 9.9.1, NZTA M27:2020 9.9.1
0b7df810-0341-52d9-a09e-8b4f20f4222a | note | Material Acceptance Criteria (Method) - ASTM D5361
16c1fc29-54b9-53b0-bf9c-78d7c9d184c1 | note | Material Test Frequency - One test per 900 t of asphalt plant production
a6c7f832-23d7-54cc-8106-c547601044a3 | note | Target Criteria - Characteristic value - mix design air void +3% -2%
55acc125-aa51-5733-8b1f-54e75e97a0fe | note | ○ Thickness as per specified nominal depth
fa6bc172-0f7c-5b76-aae3-634deda04a9e | note | Action Point Records required - Hold Point
3c52cd92-c3e0-5f60-98b1-b96c955c3d76 | note | Responsibility - Downer Contract Engineer
1ca215de-0519-4a63-9b7b-9c277b15d21a | signoff | AUTHORITY HOLDPOINT
c020628f-cc9d-44c0-bd06-cba4c791e033 | checkpoint | 3.03 - Lab (1)
f4bccfd8-b2ac-524a-8ff8-f9ebc8878fae | note | Material Test Method Requirement - Grading (Particle Size Distribution)
26a0d436-8e69-5a6f-8535-0ac45998c7d1 | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
e40b5b7e-c77b-5975-af3a-1b794fe8116f | note | Material Acceptance Criteria (Method) - NZS 4407:2015 test 3.8
e54bc3b1-db47-58e8-9b47-8ccf19a9b12f | note | Material Test Frequency - One test per 900 t of asphalt plant production
24563d05-0089-5703-8bca-4a75fe5cdc8e | note | Target Criteria - Tolerance from nominated JMF grading as per NZTA M10 Table 5.3, NZTA M27 Table 5.3, TNZ P/11 Table 7.1
e2223d80-fbef-55db-8369-c6133665fa83 | note | Action Point Records required - Test record
c882f111-4adc-548f-9fb1-7584e4e0b555 | note | Responsibility - Downer Contract Engineer
bb42ead7-af62-483a-90f0-4b3b1694a8ca | checkpoint | 3.03 - Lab (2)
3cec6dbf-a4d9-56ee-9b2e-0905a8cdee3a | note | Material Test Method Requirement - Binder content
41794b1c-7603-5e07-a64b-90e57f7e76c0 | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
d621ff61-fe34-5702-b4b7-7a096300b235 | note | Material Acceptance Criteria (Method) - ASTM D2172
7206e528-6a1d-5fa5-968f-7d2943ca3f2e | note | Material Test Frequency - One test per 900 t of asphalt plant production
dc3738ff-cef3-57c8-8487-193241721999 | note | Target Criteria - Tolerance on JMF
10d92d07-e0dd-58b7-bd9b-57619fa06d2a | note | Action Point Records required - Test record
c850bd73-f2e5-59ed-bf24-6a9eaa3d0203 | note | Responsibility - Downer Contract Engineer
acdabff3-be85-4f6b-a9ce-fa3239caebc1 | checkpoint | 3.03 - Lab (3)
449a0d52-1b97-5876-b6e2-55e4ad0295c7 | note | Material Test Method Requirement - Air Voids
f8dc6b56-9019-570a-843e-72c8714f7113 | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
99e519dc-7d86-550d-a3c8-d71afad5920a | note | Material Acceptance Criteria (Method) - ASTM D3203-22
ed54cd7c-fa44-5865-866d-a9773421236c | note | Material Test Frequency - One test per 900 t of asphalt plant production
06e2bb13-2f33-5e0d-b079-8308141515b3 | note | Target Criteria - As specified for each mix type
67b84221-31a0-5aa8-ac70-ae9fe3bc7f97 | note | Action Point Records required - Test record
22f1bbe5-c6cf-5a24-a57b-23dfdd1a0be9 | note | Responsibility - Downer Contract Engineer
929e398f-c401-4233-b32c-7fc6de8877d5 | checkpoint | 3.03 - Lab (4)
aa85f780-7ea4-5dba-b6da-a127154cb39e | note | Material Test Method Requirement - Maximum Theoratical Specific Gravity
ea5b0da5-62b8-5173-b446-9cdb14324b13 | note | Reference Documents - NZTA M10: 2020 Table 5.2, NZTA M27:2020 Table 5.2, TNZ P/11:2007 Table 7.1
48f7f99e-29ef-500c-8f03-f2fdad238309 | note | Material Acceptance Criteria (Method) - ASTM D2041
6731c9c6-47ed-5fa2-8ff2-e6656ca6bcde | note | Material Test Frequency - One test per 900 t of asphalt plant production
b8dd544a-2186-5024-9fb4-0d6ce1131303 | note | Target Criteria - Report Value
9a6ca816-2605-576a-a5a6-e79ea9d14caf | note | Action Point Records required - Test record
13e31661-22b1-55cc-a30d-ea4d2febf3d3 | note | Responsibility - Downer Contract Engineer
ae8c33a4-667b-432d-a1cd-36d2c5f2b223 | checkpoint | 3.07 - Field
c5d21c2d-885a-51ab-bf40-e1c6a83ec999 | note | Material Test Method Requirement - Load Locate
e7327806-2151-5d39-bb6e-ef95729881f7 | note | Reference Documents - Downer Procedures
7ee4a2a3-bb79-573e-945c-7a4e47dbe529 | note | Material Acceptance Criteria (Method) - Each load can be indentified to a location. Record includes:
9a01143d-d73f-5e5a-b85f-da220bdd26be | note | – Truck ID/Rego/Driver
43131813-319e-5bb8-92f0-6f2bf5cbcdda | note | – Depart Plant Time
91e17fbf-53eb-53aa-9a4d-d15428816944 | note | – Arrive Site Time
df15c935-bc17-5796-8074-54ba85ee7a31 | note | – AC Temp on Arrival
a5869bfd-2ecc-5d8c-9bdf-f4b4e5f81463 | note | – Ground Temp on Arrival
be293647-0013-59d1-9bad-a7d807743a33 | note | – Tonnage
0085b298-1ce3-510f-9003-10277fe3f34d | note | – Run Width
59dd9c13-45b2-58b0-b06d-452111c592bb | note | – Estimated Run Length
125ac8da-0c37-5a53-8a3c-1026bbcf01f5 | note | – Calculated Area
14666393-4739-5426-a3a6-5ee51d7e1608 | note | – Calculated Average Depth
55294085-ade2-5b32-9055-03db712c903b | note | Material Test Frequency - Every Load
6914963d-396a-5e0b-ad2e-abbf521d6c0d | note | Target Criteria - All data is collected
862bdfb0-a65a-5e03-9259-69d5b777ed58 | note | Action Point Records required - QA Sheet
fc97ad6b-434e-5929-bec8-0edabda6df36 | note | Responsibility - Supervisor
fd8750db-8d73-46ca-86ea-a2e7e497010d | checkpoint | 3.08 -
f198f95f-1616-525a-ac3a-b92d19d1e45a | note | Material Test Method Requirement - Plateau Density Test
8a32a488-8439-5727-94d9-3b69f57af5c4 | note | Reference Documents - TNZ B/02: 2005
c6a57503-8347-5d9e-a073-8996d8b8137e | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
63c93128-5923-592a-80eb-11b2506e7eaa | note | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing
0a1ede04-10fa-5976-aec4-f1acbc7c7f94 | note | ○ Target to be approved by Engineer
0c256234-033d-558f-8a83-f61015e4ce0a | note | Target Criteria - N/A
66f0f379-b865-5400-9360-a1726ba5a25d | note | Action Point Records required - Hold Point
62f14fd4-8162-548c-a40d-f71a4f7212e9 | note | Responsibility - Downer Contract Engineer
3ee32d4d-ce2d-4d58-ad3c-e83a869ac937 | signoff | AUTHORITY HOLDPOINT
66a2826a-84cb-4ca9-a047-19cdb4a93f49 | checkpoint | 3.09 - Field
df642754-e24c-566e-8fe7-e9c8c68718a4 | note | Material Test Method Requirement - NDM Density Testing On-Site, Mat and Joint
8c6303ec-9c72-54f9-b08d-ec12580b636b | note | Reference Documents - NZTA M10:2020 9.9.1 and 9.9.2, NZTA M27:2020 9.9.1 and 9.9.2
e82d31ce-20b6-50bd-b53f-0d6b9d7e1b7a | note | Material Acceptance Criteria (Method) - ASTM D2950, ASTM D5361
d0f38e00-00f9-5815-b4e1-e2d1d3ce38ee | note | Material Test Frequency - 1 test per 300m² per layer (Min 8 / Construction lot)
bb9f35be-a567-568c-8274-ea7e77bfeb3c | note | ○ 1 test per 100m per layer length (min 3 / Construction lot)
1563b922-ebc5-5e55-b30d-34e8fc55a6a3 | note | Target Criteria - Mat: Mean air voids JMF +3,-2
45bcdeac-2715-59f4-85c6-a45e9e474829 | note | ○ Join: Mean air voids JMF +5,-2
e0dc80d4-7b37-51f7-8bcb-afa2b86fdd91 | note | Action Point Records required - Test Record
910af8bc-c2bc-5645-a6ca-449bab112573 | note | Responsibility - Supervisor
4b8f5cce-9b3d-44c1-abb5-c8d94700162d | checkpoint | 3.10 - Field
bfee19f2-9cfd-58f0-b8ff-61c8c7695db1 | note | Material Test Method Requirement - Straight Edge
3a77e9ca-1273-5355-ae7e-b35619c13c27 | note | Reference Documents - NZTA M10:2020 10.2, NZTA M27: 2020 10.2, Downer Procedures
48eeaff8-b0f0-5853-bb3f-e1b89b15f543 | note | Material Acceptance Criteria (Method) - NZTA M/10
397c6505-587a-546b-b557-e0acb427b718 | note | Material Test Frequency - 5 Points across full width of carriageway at 10m frequency
31c48753-0b3e-57df-bc29-45b3b8e34c22 | note | ○ Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
8d9cc1b9-424a-58e3-97fb-eec38a0d7c57 | note | Target Criteria - No more than 5mm deviation from a 3m straight edge
3043db52-7ad3-5b02-a301-352747b51246 | note | Action Point Records required - Survey record
10a80a26-464a-5848-8a70-d07aedae2077 | note | Responsibility - Downer Contract Engineer
9442a211-c143-46e6-aa9f-f904a44a105a | checkpoint | 3.11 - Field
4a9ff8e5-d2a8-53a2-af06-34453260c6a2 | note | Material Test Method Requirement - Post Surfacing Inspection and Safety Audit
33c1bec9-9e49-5e8e-85b1-6d3a3c3abb05 | note | Reference Documents - CCA Procedures
75de739f-3ce0-50d2-b670-778d72536bb6 | note | Material Acceptance Criteria (Method) - Contract Specifications
15a286cd-dffa-5127-9e01-30bdf443377d | note | Material Test Frequency - 100% of site, After surfacing (within 5 days)
1af56ddb-bec0-5942-a494-82497531f332 | note | Target Criteria - Line marking has been reinstated
c57a1a04-f85d-5594-8b1d-433a33147adb | note | ○ All excess material has been removed from site
f8a2157d-3105-5e72-b2c9-90e319470114 | note | ○ All CPs are clear from filter fabric and any excess material removed from on top service covers
f8ee17b2-75e7-5110-9350-5c9d612edc4e | note | Action Point Records required - Survey record
4186f8e5-358f-5ffa-bd3c-7650f1768c00 | note | Responsibility - CCA Engineer / Downer Contract Engineer
2580c2e1-291b-4287-8e92-b02c3974f236 | section | 5.00 - Post Construction
855701fb-9972-4629-9d46-4d854d27d5c1 | checkpoint | 4.01 - PQE
809a0458-237f-5e91-a7c9-a3cb19804e45 | note | Material Test Method Requirement - Asbuilt and RAMM Data
a7f2f925-9383-5292-8678-977f1544a499 | note | Reference Documents - RAMM Update sheet
f4bcb743-1996-56e2-93f4-f982a288a404 | note | Material Acceptance Criteria (Method) - Asset Management Information Plan
d76cee9e-f1d0-5a25-82ef-9a66b59c9c4a | note | Material Test Frequency - After works complete
deeb1e0f-d5a3-53dd-8e2e-51b521294aad | note | Target Criteria - RAMM sheet 100% complete and accurate .
60f5f2a0-6501-5da8-91db-f409ef3e9a83 | note | Action Point Records required - RAMM Asset Update sheet
60b20976-abb4-530f-a9a7-c25d27e70f3b | note | Responsibility - Downer Contract Engineer
3ed42109-8dbc-4782-b4af-dcdb9432a7d3 | checklist | Kakanui Ave - Granular Rehab ITP |  | Kakanui Ave - Granular Rehab ITP
4b0fc3ce-fd0a-46bb-9b1a-046266ffad91 | section | 1.00 Subgrade
2ef5e854-e563-4cdd-8a6e-4e4aacbf12fa | checkpoint | 1.01
00a63b49-f085-59b9-a576-e2879ce6e828 | note | Lab, PQE or Field, PE - Field
71f9ec59-8545-515e-b535-a739036b1a6f | note | Material Test Method Requirement - Scala Penetrometer Cohesive soils only
6332b832-2ab1-5541-a3ef-4acf10dde008 | note | Reference Documents - RITS Table 3-20
79abcd9e-686c-5189-a30f-17e919defa71 | note | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
0c786328-4881-5f42-a455-6edd2ea644ed | note | Material Test Frequency* - 1m inside of edge of seal and along centerline, both lanes, at 10m spacing Minimum of 10 tests and/or at a frequency of 2 test per 10m chainage, whichever qty is greater
66d521fd-7caa-52e2-9f09-e6f31def1d92 | note | Target Criteria - 2 blows per 100mm, average over 900mm
3834c66c-d019-58ff-9f5c-d23c50b9960d | note | Action Point Records required - Test Record
0227da4b-89b7-50f3-81ea-f03bcb15d5a9 | note | Responsibility - QA / SE
b52a21b5-697c-4307-b447-b8b1d48610da | checkpoint | 1.02
6db3dd0a-4f65-5eff-9135-eb4daf6e9727 | note | Lab, PQE or Field, PE - Field
53254324-ef91-5882-a94f-2039c12ef2fc | note | Material Test Method Requirement - Clegg Hammer Aggregate fill only where subgrade undercut or trench backfilled
07e0ac5b-ab56-5dab-ae99-5579a63cb972 | note | Reference Documents - RITS Table 3-21
b7640ebb-8eac-5a10-9b7f-53e25b803574 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3 ASTM D5874-16
1a15f1f9-69f2-5893-8dcd-cff1d236f99e | note | Material Test Frequency* - In centre of undercut or trench Minimum of 1 test per undercut location
953bbaf5-ee7e-5d95-b603-50e9a6eefcd7 | note | Target Criteria - CIV ≥ 15 or CBR of 20
247b614d-f7bd-54a3-a560-efbc71a9aa3c | note | Action Point Records required - Test Record
e64baab9-faaa-5fb8-9835-dbb87e8db4c7 | note | Responsibility - QA / SE
66f50159-594c-4dc2-afa1-25a15f2f6cbe | checkpoint | 1.03
cd6563dd-af37-5a2e-93bb-ccb924438a58 | note | Lab, PQE or Field, PE - Field
b4eaa422-e65d-5344-b096-b8660ab5fa0c | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
49aa0561-e73f-554d-97a3-67150e67237a | note | Reference Documents - RITS Table 3.24
27c1cff3-3974-5f69-b6a0-eb311d00c713 | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
8b4cba89-75ea-5c97-b7c0-1f26bc44d9a6 | note | Material Test Frequency* - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
dabfb8b6-5753-56e4-9e80-57e8703bbbcc | note | Target Criteria - +0mm/-30m from design or nominated level No more than 15mm deviation from a 3m straight edge
55b72b90-4320-56eb-8176-056b8532acac | note | Action Point Records required - Survey record
debd9168-1102-513b-9424-47992f9e0e46 | note | Responsibility - QA / SE
38a04d78-f641-4f93-a16f-843d09f0ff17 | checkpoint | 1.04
7759ed12-1d74-5826-b81c-08713254f4f4 | note | Lab, PQE or Field, PE - Field
d162fa0b-c4ac-524c-a76f-c6170f2e5299 | note | Material Test Method Requirement - Tenser Triaxial Geogrid and Geofabric (cloth) installation
07bb68b0-5d16-5b00-95da-ac59fd59e24d | note | Reference Documents - Tensar construction sequence CS_TriAx/30.04.08
da44b74e-a668-5052-b2b4-a34561e546b8 | note | Material Acceptance Criteria (Method) - Manufacturer installation instructions
fd3c9fb9-8172-5894-ba7d-8647ae770c09 | note | Material Test Frequency* - 100% of Surface
cccbe6bf-98eb-5033-8b66-0679698b507b | note | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints. Geogrid and Geofabric shall be neatly installed without creases or folds.
e79d1579-dc15-57d4-bb09-f9e68a0a2422 | note | Action Point Records required - Site Record
dbdbcddf-ea13-5187-a897-6f0b73408971 | note | Responsibility - QA / SE
d207aa10-407d-4f77-91e0-2a45a73636a0 | checkpoint | Compliance - 1.05
db4918df-f70c-5331-8efe-0a213e8d3de4 | note | Lab, PQE or Field, PE - PE
542f245d-7be2-5ad5-afb7-8e8d2aa146ef | note | Material Test Method Requirement - Is the layer closed out ?
086e4236-4e0a-5c5e-a8b4-85a862267b0a | note | Reference Documents - See PQE
9b3e60fc-c0e7-585c-88b0-65e220d07aa3 | note | Material Acceptance Criteria (Method) - See PQE
5dc0ffda-11da-54ef-abce-df033296be65 | note | Material Test Frequency* - 100% of Surface Prior to placement of material
791c44d9-47e9-530e-8098-8ead49f13f28 | note | Target Criteria - PE Approval All testing record & reviewed as compliant. Available Documents: Test records Survey records Hold Point Records
477dbe83-8984-58c6-9fc2-3353f80a67e0 | note | Action Point Records required - Hold Point
e1201ec9-6444-55f7-9dbc-a3d54c0d031a | note | Responsibility - PM
5282553e-a96d-447b-9cd5-54d3f19dd60f | signoff | AUTHORITY HOLDPOINT
61ee7496-e263-4f80-942b-6238da46f195 | section | 2.00 Subbase
d9f85edd-4409-4b96-8827-e519fdc7e683 | checkpoint | Compliance - 2.01
5d6f52ed-af47-5090-89e3-167e47a72db8 | note | Lab, PQE or Field, PE - PE
d7970e49-7449-5ecd-847f-565713763bc9 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
06533706-8f31-5eb8-afa0-5deb127be0ec | note | Reference Documents - Insert Material Testing link
25e4a620-6441-5982-be8f-6bca36cb8876 | note | Material Acceptance Criteria (Method) - See PQE
eee47d95-d220-5b84-9753-9f2695b717e5 | note | Material Test Frequency* - Prior to construction commencing
d7e0ad15-fb0a-5321-bf59-ee9272c978e1 | note | Target Criteria - Material meets project requirements
6d0bf117-e7a1-588b-b1e6-e20790a4e13b | note | Action Point Records required - Hold Point
ca1822cd-1e0e-58a0-ba9b-f9a51fa3db82 | note | Responsibility - PM
c46c25d1-ca6b-455b-81eb-b14dcfb98e5c | signoff | AUTHORITY HOLDPOINT
06e89ec8-21af-425b-b8a8-24b20a66129b | checkpoint | 2.02
80c04bd5-4039-50b5-a1c6-d43d350bbf42 | note | Lab, PQE or Field, PE - Field
2105f80c-2317-5aec-8e45-53bedc3613cc | note | Material Test Method Requirement - Plateau Density Test
bdf59334-742a-5993-8fc9-170edf1678d0 | note | Reference Documents - TNZ B/02: 2005
6c352a2f-5dd8-59ac-8eb7-852a45320334 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
131c690c-b442-5904-b9e3-137e17c2b635 | note | Material Test Frequency* - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer
5803f53e-cc49-578f-9c8a-0f25553c8b5f | note | Target Criteria - N/A
cd220cae-07cd-5aeb-a194-acef83457c36 | note | Action Point Records required - Hold Point Test Record
2952fc43-e8d2-5232-bc76-7138fd1bb964 | note | Responsibility - PM
89074dfe-fbb5-4fba-aa92-c1d0894e988f | signoff | AUTHORITY HOLDPOINT
2fc2c09c-f6fa-47a8-b70d-e1fc55e532df | checkpoint | 2.03
9b1c2e17-a4aa-5ac6-822a-a7ff130fb3ab | note | Lab, PQE or Field, PE - Field
ebe5171e-fd7a-516f-9678-406360c6c4e5 | note | Material Test Method Requirement - Clegg Hammer
4b521321-f937-5914-8088-0e604b4c4140 | note | Reference Documents - RITS Table 3-21
e1e894a7-75d3-515a-9864-49f0524e0966 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3 ASTM D5874-16
73d1fa84-456c-5ab4-b19e-e6a569a1b669 | note | Material Test Frequency* - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
9d1a7678-7afd-57ac-bedc-a7427f251e1a | note | Target Criteria - CIV ≥ 35
6ebeba03-20a7-5b7f-bc03-96c30fe74d25 | note | Action Point Records required - Test Record
2d06f1e9-6f94-55ae-88f9-ec4eda41a543 | note | Responsibility - QA / SE
9f33ebc0-8be8-4151-ba4f-b72cb530203e | checkpoint | 2.04
f9ebc4c3-9209-50f4-b90f-899005b283fe | note | Lab, PQE or Field, PE - Field
07e8516f-4e96-5d9c-b899-d1cad251eb4d | note | Material Test Method Requirement - Compaction NDM Back Scatter
7d7c27a0-9beb-59aa-96d0-b5d849c57e7c | note | Reference Documents - RITS Table 3-22
45af1d55-a22e-59b7-ac9d-15a306e3dd99 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.4 4407:2015 test 4.3
48d84142-0b7c-5627-bd12-0b048bdb6bfd | note | Material Test Frequency* - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
95be2d71-b3d8-59a5-b335-1c65e1e490b6 | note | Target Criteria - Mean ≥ 95 % MDD Minimum ≥ 92% MDD
4ff5d83a-06cb-5d60-9be1-e523b6e808b0 | note | Action Point Records required - Test Record
e79195c2-1b00-5d92-a21a-04b366490d7e | note | Responsibility - QA / SE
88aafdc7-3451-4475-8a2d-9f83ed1a23e0 | checkpoint | 2.05
16ee68b6-45c3-59cf-98cd-6a5a6a922ff7 | note | Lab, PQE or Field, PE - Field
6022a64b-08c5-59d7-9838-f42314e39f02 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
693dc70f-4dc2-56b2-a600-424bf64577cd | note | Reference Documents - RITS Table 3.24
519ffc22-b7ce-590e-8f67-9a2899bed674 | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
1b639b2d-34a3-53ad-a37f-910d1843753f | note | Material Test Frequency* - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
60397701-f883-5728-81d3-311274c259f7 | note | Target Criteria - #ERROR!
87e93a83-d1ce-5189-bea0-5aa4577b2e1f | note | Action Point Records required - Survey record
d62e577f-e2de-5664-8ab8-3e5c1282d1df | note | Responsibility - QA / SE
24b44b84-304a-4d4a-9095-35c3fa23f3ab | checkpoint | Compliance - 2.06
009c5be0-13fe-55ae-a5b6-3b34d34d6c29 | note | Lab, PQE or Field, PE - PE
b0dd139e-fe9b-503c-b9c6-0faa5622e50d | note | Material Test Method Requirement - Is the layer closed out ?
ffa64241-ea22-5188-9767-a4023ee1c95d | note | Reference Documents - See PQE
dee5031a-aafd-5693-8ef2-59ddcf9dd4bf | note | Material Acceptance Criteria (Method) - See PQE
7da9090c-5d36-5412-ab05-c817b9a6841e | note | Material Test Frequency* - 100% of Surface Prior to placement of material
3eda1206-9501-5a64-bd97-c146e2b9dd15 | note | Target Criteria - PQE Approval All testing record & reviewed as compliant. Available Documents: Test records Survey records Hold Point Records
5b506731-6f3a-5d57-88d2-1655b928939a | note | Action Point Records required - Hold Point
ecc489d4-1ae9-59d2-9fc1-05e1791bfe76 | note | Responsibility - PM
01a8fbf5-8e20-4d90-8b7f-7d688fbd38fe | signoff | AUTHORITY HOLDPOINT
efb17a87-ae02-4485-b35b-136b5f06b8f9 | section | 3.00 Basecourse
c520b744-342f-4858-8e82-cfc56bf09666 | checkpoint | Compliance - 3.01
3fb593b4-bfbb-530e-93e0-c775f3f485fc | note | Lab, PQE or Field, PE - PE
8547153a-d81e-5e7b-878f-61caf0ff52fb | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
403c3f88-0c12-561b-96ef-a863137ee07b | note | Reference Documents - See PQE
fb1a5cb5-6e67-5501-ad9f-feb19577bb54 | note | Material Acceptance Criteria (Method) - See PQE
fde6ecb1-8f74-500f-b7fd-6b8c06109550 | note | Material Test Frequency* - Prior to construction commencing
e156c923-225a-5ead-8ba8-b45b171011ad | note | Target Criteria - Material meets project requirements
d5d4c57b-1f2e-5e4f-9f7a-71e04d9bba6a | note | Action Point Records required - Hold Point
d1b1dfa7-86b4-5865-9ae4-6314fad14edf | note | Responsibility - PM
d9020090-0ea9-4871-8fa6-1cf7871ea6a7 | signoff | AUTHORITY HOLDPOINT
6486af72-e492-4f14-9636-c7e994207f27 | checkpoint | Stabilisation Delete if Not Required - 3.02
8f31ec09-1c04-54df-9a04-f7b54481d124 | note | Lab, PQE or Field, PE - Field
1e82489d-3b14-556e-a4cb-226928b1f7e0 | note | Material Test Method Requirement - Cement application Mat test
7375690b-9e6c-519e-b864-450f77a5e8fe | note | Reference Documents - TNZ B/5:2008
498d642d-f7fa-5a36-b5fd-987e2f239d7d | note | Material Acceptance Criteria (Method) - TNZ B/5:2008
02669006-eaa6-5247-9d01-d85bb5adc43e | note | Material Test Frequency* - 1 test per 400m² (minimum 1 per run)
ffb4b839-acf8-578b-a8b6-caf693cb26e5 | note | Target Criteria - ±0.50kg/m² of specified rate
30e53783-e292-5f1d-98c6-d1b4705eb383 | note | Responsibility - QA / SE
666fae27-1503-4673-9e4c-88de60450e10 | checkpoint | Stabilisation Delete if Not Required - 3.03
e142da3e-8ecd-59a9-b902-6389c698c777 | note | Lab, PQE or Field, PE - Field
420bd1a8-441e-5338-b968-22117e0ee98a | note | Material Test Method Requirement - Stabilisation Depth
48ae6575-8884-5012-95c0-70a87755a079 | note | Reference Documents - TNZ B/5:2008
afa5a324-f564-522d-b732-917f7134705d | note | Material Acceptance Criteria (Method) - TNZ B/5:2008
7c3d33da-88e1-5b03-9809-e359ef63db01 | note | Material Test Frequency* - 2 test per 400m² (minimum 1 per run)
97a846e7-7c47-5b5a-8f31-8586d263db08 | note | Target Criteria - Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer
83e410a0-f020-50e2-8365-11917dc40b16 | note | Responsibility - QA / SE
86c4bc93-68d0-4f26-8bf9-833125fdabd9 | checkpoint | 3.04
a65fd198-19cf-5ab3-b5b6-d1d4c43eb791 | note | Lab, PQE or Field, PE - Field
684b388d-2b14-5eb5-9cf0-70f89059f3af | note | Material Test Method Requirement - Plateau Density Test
0b94780a-36d5-5d70-94e0-2fc13610fc4b | note | Reference Documents - TNZ B/02: 2005
628ac345-7df7-55d7-8867-9c3e439128b9 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
afa15f37-af65-5cde-94aa-0e6a49264c28 | note | Material Test Frequency* - 1 test per site
c32f5934-3a3a-544a-a5b5-03b8accc06ff | note | Target Criteria - N/A
bea22ed7-7d64-599a-b209-e3921a974c9f | note | Action Point Records required - Test Record
666599fc-2457-5ca1-9013-f57233d195e3 | note | Responsibility - QA / SE
3dec8bfc-5619-42e1-8f57-6a7d8a14f6d2 | checkpoint | 3.05
6c46e706-9030-5f3d-a565-e28b820215fe | note | Lab, PQE or Field, PE - Field
856ed93f-9fec-58c8-b92a-35ab1f34d23f | note | Material Test Method Requirement - Clegg Hammer
b46375ba-2a6a-51b1-b2a8-9512bad23ad4 | note | Reference Documents - RITS Table 3-21
69a9ea43-78e6-547e-9963-8ccf846f4eb5 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3 ASTM D5874-16
82404458-441c-576c-b186-45ec24c1695e | note | Material Test Frequency* - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
419bb836-ccb1-58aa-8c9b-6b0e0301f04a | note | Target Criteria - CIV ≥ 40
4e05f0a6-1198-5935-9af1-3a820445d252 | note | Action Point Records required - Test Record
794d7013-d670-5148-8808-77b8b82a38c4 | note | Responsibility - QA / SE
55af0782-0296-4063-a4b1-b5f6c9fdb5e1 | checkpoint | 3.06
a54e8b7d-b47c-588e-beb7-bb3e383a17a6 | note | Lab, PQE or Field, PE - Lab
90f0988f-5513-5884-8a94-8ad94c94b972 | note | Material Test Method Requirement - Compaction NDM Back Scatter
0e3662c4-a2d9-5293-bd7c-2cd6141607e7 | note | Reference Documents - RITS Table 3-22
451ae765-a726-5f0c-94db-a8126b05aa12 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.4 4407:2015 test 4.3
7de64dc0-1d38-5065-a082-49e7129cace9 | note | Material Test Frequency* - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
b73c9def-e2e5-5186-8182-01838cfcf71c | note | Target Criteria - Mean ≥ 98 % MDD Minimum ≥ 95% MDD
a84b5775-379a-58c2-b541-797a2f4b2b9e | note | Action Point Records required - Test Record
add50e27-1cd1-513b-941b-14a53ce54ccb | note | Responsibility - QA / SE
2f8768e1-8f85-4740-ad38-2bf1a062e090 | checkpoint | 3.07
5dae00e1-229e-57c3-b7b0-dd1011f13e14 | note | Lab, PQE or Field, PE - Lab
91bd219d-f525-5f37-99d8-90aa92ee97f6 | note | Material Test Method Requirement - Benkelmen Beam Deflection Testing
62bb516d-a7a2-589f-a9d0-ea878fea25cc | note | Reference Documents - RITS Table 3-23
992ace98-3ff3-5a4f-a18c-af1b0a94d8c2 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.5 ASTM D5874-16
871d731e-98e2-5669-8d38-fd64ca8c8123 | note | Material Test Frequency* - 1m inside of edge of seal and along centerline, staggered across lanes, at 10m spacing (no greater than 20m between tests) Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
dad4ed16-d334-5226-9650-b0461b8f1e9d | note | Target Criteria - Max deflection allowed: 2.37mm From design report - due to non-RITs compliant Subgrade CBR
9cbaec5d-1350-5c58-a30a-ce0dbff43637 | note | Action Point Records required - Test Record
2d526e9a-3960-50f1-b9d9-2465ddea1562 | note | Responsibility - QA / SE
d30fdb5d-78b9-4eaa-befd-5d8ac84de69c | checkpoint | 3.08
cd12af74-857a-51c2-9a38-c6ac9238c1e5 | note | Lab, PQE or Field, PE - Field
2e404cf1-a47d-583d-9b6e-edc728de66d3 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
9ba62d37-3021-53b2-b4b9-f9d4fbc886d2 | note | Reference Documents - RITS Table 3.24
416c9199-e52b-5264-8fe7-99fec9692cd6 | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
872ba7ff-36ba-5e13-9dc8-2344f4d68344 | note | Material Test Frequency* - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
b52c1b26-caa6-5137-83d8-d6b7f03e5b06 | note | Target Criteria - +10mm/-0mm from design or nominated level No more than 12mm deviation from a 3m straight edge
3506d579-0b99-56f9-896d-933010f86f5e | note | Action Point Records required - Survey record
841ca3f6-5eaa-58d9-8845-5cd80aa49bc8 | note | Responsibility - QA / SE
97d62f5e-4f08-4fbb-b7d7-9f1b9568c19d | checkpoint | 3.09
2d598802-bf1d-5677-bc7a-7a19c9a38943 | note | Lab, PQE or Field, PE - Field
9014d60b-e15d-5c7e-a5ef-0365997ffe55 | note | Material Test Method Requirement - Visual Inspection of Basecourse Surface
eaf0af5c-f622-5083-9bf9-f5eb1cfd8b6c | note | Reference Documents - TNZ B/02: 2005 7.8
d445864b-b566-507b-adb0-d7cea617e45a | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005 7.8
8c54c84c-768f-5f03-a72f-867495d10e4d | note | Material Test Frequency* - 100% of Surface Prior to sealing of surface
3fab935a-0fbd-5d4c-a8f3-a1873989684a | note | Target Criteria - Engineers Approval (The larger aggregate is held in place by with a matrix of smaller aggregates, the smaller aggregate is held firmly in place by fine material, and the matrix does not displace under normal trafficking or sweeping No evidence of rutting in surface)
22de362d-4c98-5fbb-a307-1f4bbf0ea52d | note | Action Point Records required - Hold Point
eb5b23da-727d-5c20-8cd8-987ccc5df766 | note | Responsibility - PM
d627aa87-f5a4-48b2-af8e-d78c396d3381 | signoff | AUTHORITY HOLDPOINT
7b60a5c0-2f12-4a25-960b-f0c1a33f029e | checkpoint | Compliance - 3.10
8aabd115-4012-5065-bace-935f817cf9e2 | note | Lab, PQE or Field, PE - PE
209d82a8-7ced-53b3-8a16-0f065b9362c8 | note | Material Test Method Requirement - Is the layer closed out ?
1b8e6b5b-e496-54c6-881b-0a2180be82bc | note | Reference Documents - See PQE
c52d2bdb-8c5d-5d68-868e-1625a1342553 | note | Material Acceptance Criteria (Method) - See PQE
8e601f35-fed0-5c58-9d89-c7f086a0f488 | note | Material Test Frequency* - 100% of Surface Prior to sealing of surface
3491c310-0bdd-5f35-a57b-2958483e4c9e | note | Target Criteria - Engineers Approval All testing record & reviewed as compliant. Available Documents: Test records Survey records Hold Point Records
010c623a-d0f7-5272-82b9-a03d165936fc | note | Action Point Records required - Hold Point
db7d6d55-d7e5-5e08-b292-9b23954fb79a | note | Responsibility - PM
0f817051-5785-4fcf-a806-3bccad86462d | signoff | AUTHORITY HOLDPOINT
5a76b381-95db-41ac-8c8d-3c430ec766cc | section | 4.00 Membrane or First Coat Seal
a4bc2f5d-2059-4b39-8a95-de4692df8b0c | checkpoint | Compliance - 4.01
b7dd093f-6169-506a-83ba-b7885b176870 | note | Lab, PQE or Field, PE - PE
cdd65f64-9984-550d-a65b-21cb833db5af | note | Material Test Method Requirement - Seal Design
50aa4a0c-424e-5e6a-b8ff-457f5faca6c0 | note | Reference Documents - INSERT SEAL DESIGN
dc8c901d-1600-534a-a5c8-21fe32d82f10 | note | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
07933ffa-53ba-51b2-a8b7-ec0aec404c3e | note | Material Test Frequency* - Prior to sealing commencing (Minimum 1 week prior to application)
d6fadf07-8104-5b88-9ee9-e2ed22f7f8a3 | note | Target Criteria - Meets project requirements
4d65cfb1-5bc3-5a15-ae51-37c7646cab47 | note | Action Point Records required - Hold Point
27f6b826-0085-5505-9f17-9c9a58b8709e | note | Responsibility - PM
55760ab2-0c9b-4ebb-ac03-aceec5fede84 | signoff | AUTHORITY HOLDPOINT
c22a1e88-4e57-450c-9381-411b33661f4d | checkpoint | Compliance - 4.02
1e78265f-7b38-5249-9d2a-6c2aa6438a39 | note | Lab, PQE or Field, PE - PE
188c6083-b5be-549d-865b-9ddb27401a3d | note | Material Test Method Requirement - Bitumen Sprayer
1cecaabd-4565-5071-94df-88e332c82071 | note | Reference Documents - TNZ P3
a39e4921-593e-56e4-ab18-c9727efbdccc | note | Material Acceptance Criteria (Method) - Certification provided
49627651-d710-5e46-95ee-e0a8e52000f3 | note | Material Test Frequency* - Prior to starting
0212a6cd-72ce-596b-9079-da4f3a2efcd4 | note | Target Criteria - Current E/2 Certificate
7799335c-e35e-5da1-b3ec-4711e944c96e | note | Action Point Records required - Certificate Sheet
188895e6-91bf-5ea8-8341-15971898b271 | note | Responsibility - QA / SE
297e4561-6471-44d9-9259-36834d469043 | checkpoint | Compliance - 4.03
74449947-4d5c-5418-94ec-2ef2d148aaef | note | Lab, PQE or Field, PE - PE
2ab39c75-8a3c-5fbf-a4b9-3d86326e7df4 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
3daa66e0-0a4c-5e89-a10b-eaa50563fdbe | note | Reference Documents - Insert Material Testing
1e1ae61d-5d30-5508-a517-0bc6f63e775b | note | Material Acceptance Criteria (Method) - See PQE
fd59d425-e672-5b3e-a6fb-91ab4db8add5 | note | Material Test Frequency* - Prior to construction commencing
df1a539a-50c8-511c-9f47-bc9b4800d6af | note | Target Criteria - Material meets project requirements
9ad0f61f-a94e-5b55-874a-3439a517050d | note | Action Point Records required - Hold Point
ddcab2c7-3e16-5fb4-9901-ddfd2ef20906 | note | Responsibility - PM
55f91c4c-4da9-4b0d-b967-d100f0d992a5 | signoff | AUTHORITY HOLDPOINT
178a484b-c683-46a5-b85b-bd3702361d40 | checkpoint | 4.04
742767c2-8ef3-5cf4-9487-5089c80ffaab | note | Lab, PQE or Field, PE - Field
3f03f996-d628-5a69-8b1c-4bbd30a58424 | note | Material Test Method Requirement - Preseal Inspection
0af4bb31-d28f-5a00-a50a-9c3a47a5c32b | note | Reference Documents - TNZ B/02: 2005
bee81f3c-da8e-5a4d-b090-cdb566d454b2 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
c159c9fd-ce08-5424-bc9c-63df99f4fd80 | note | Material Test Frequency* - 100% of Surface Prior to sealing of surface
e7aa1c33-e4ee-5d2d-8761-556fa48f903f | note | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
b1eb2f1a-daba-5322-be33-f5179bfeac33 | note | Action Point Records required - Test Record
7d7d2389-89b9-5e66-9d50-fec46de0ce47 | note | Responsibility - QA / SE
88477183-417b-43db-a012-243d35c520f3 | checkpoint | 4.05
cc9a49a9-e8ac-5cde-9bf9-a1346328a52a | note | Lab, PQE or Field, PE - Field
baf0dc62-95d2-509b-9b2d-4eefbb7a2156 | note | Material Test Method Requirement - Degree of Saturaton
2c380b4a-8994-5a56-ae80-a02d535e2537 | note | Reference Documents - TNZ B/02: 2005
7064b340-db83-5811-84ad-a1df6eb1ef0b | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
b85c736c-4b08-52af-83f1-befee327c4a5 | note | Material Test Frequency* - 1 set of 5 per 1000m² - then 1 per 200m²
b1bbc9df-672d-5773-97d7-47f0957d9b13 | note | Target Criteria - < 80 % Completed Max 48hrs before sealing
884298ec-0ee1-5dd5-aa4e-174cd61aca34 | note | Action Point Records required - Test Record
cbacc2f5-0e69-5170-aef3-6814c34fc66d | note | Responsibility - QA / SE
ae142da7-00d9-4ee6-8382-9ec2eda477f5 | checkpoint | 4.06
844ec3dd-6b45-5429-8c74-0511ceab6c79 | note | Lab, PQE or Field, PE - Field
51c52b40-5344-56e9-850c-057adfa86c7f | note | Material Test Method Requirement - GO/NO GO Survey
fe046b28-c925-5074-8c5c-720276f02a27 | note | Reference Documents - Downers processes
eb2d1ea4-9e54-5812-964c-5816edca62ef | note | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
7d5c9523-e53a-5534-a6ba-870141afd03a | note | Material Test Frequency* - Prior to sealing on each site
4fbe49d2-4b7b-5088-b672-c65319d671fc | note | Target Criteria - Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager
5654c426-c01b-5108-9ea4-ec7eac524b59 | note | Action Point Records required - Survey record
4505a3a5-ff1a-5a72-ba97-82602705becf | note | Responsibility - QA / SE
c05251a5-8abf-4b27-850a-0a96a379dfc8 | checkpoint | 4.07
7e11c171-499f-5adc-97f7-b3b5df2013e7 | note | Lab, PQE or Field, PE - Field
a3202811-0331-5fbb-ac80-7a164ac7d346 | note | Material Test Method Requirement - Road temp
a5d0ec52-11bb-5578-b4be-2df035de6d66 | note | Reference Documents - TNZ P3:1995.18
683c7446-e0cc-54ee-8bee-82bb3e6bab2b | note | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
fd855582-dc9c-5475-b1bf-5ae0ebbf853b | note | Material Test Frequency* - Once per day of sealing prior to sealing commencing
e8f171c4-829a-59a7-9afa-85899e6ef331 | note | Target Criteria - Air temp >10°C
e1c3a6b3-1a0c-5d16-9e0a-2ba079f62624 | note | Action Point Records required - Spray sheet
5e0b713b-73cc-53dd-81b5-13a025bb06ba | note | Responsibility - QA / SE
ae508965-acea-4e48-99ef-f632ef3a3754 | checkpoint | 4.08
27643fcc-a5d6-5d21-83c0-d063a7e63d26 | note | Lab, PQE or Field, PE - Field
61f5f5d0-2d72-58e1-bd6c-6dcea8e4cef5 | note | Material Test Method Requirement - Application Rate
e854436b-507b-52e1-8b1b-621c0bd7836b | note | Reference Documents - TNZ P/3 : 1995.18
63ffded8-1559-5da6-83af-e97122eb1b98 | note | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fitted to sprayer
69701988-0342-51c3-b34f-3c33ce06ac3d | note | Material Test Frequency* - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
383b2eba-d04f-5f41-b480-0b2fd162c754 | note | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
c78b07ec-f5b0-5956-8e2f-185df00392df | note | Action Point Records required - Spray Sheet
d614b39b-8138-5ded-83ea-77b5f0437cef | note | Responsibility - QA / SE
3f93fcb4-9f15-4a96-9eee-caa35ce883ac | checkpoint | 4.09
8041e120-4d0e-530e-9414-ed17816d1c12 | note | Lab, PQE or Field, PE - Field
fc5447e7-7a2f-5482-8f8e-59db09b721e9 | note | Material Test Method Requirement - Chip spread rate
f8454671-c324-54fc-a296-b36373ad70e5 | note | Reference Documents - TNZ P3: 1995.21
134d0374-a848-5166-a91a-b1343762b9bd | note | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435)
92283386-b32d-530a-831b-f4d2e411bec8 | note | Material Test Frequency* - Total amount of chip used to be calculated at end of days sealing
b025fb35-587d-5e74-be87-959ac2a304dc | note | Target Criteria - Visual checks meets seal design requirements
de5879ea-bb43-5e9a-8f3c-92684e93ed97 | note | Action Point Records required - Witness Point/Spray sheet
aace4f04-cdb8-56c8-b97f-4686c9d1e2cb | note | Responsibility - QA / SE
2e5f02f6-0977-44f7-a693-adf7ada155a8 | checkpoint | 4.1
800aef8f-287c-5a93-b138-e6c3845e9236 | note | Lab, PQE or Field, PE - Field
c4407925-a2ad-5de5-bffd-aee586de87b7 | note | Material Test Method Requirement - Rolling Checks
f12b2b4b-b064-554c-9918-7773a19c4d18 | note | Reference Documents - TNZ P3: 1995.22
09a2d9bb-20cc-5cbb-b77b-51c9072021e1 | note | Material Acceptance Criteria (Method) - Sealing Record
3114f65d-c4f7-56b4-b563-18164ba70d6d | note | Material Test Frequency* - for each sealing site per day
f127bad6-5317-5a00-8a24-7f0523aec0c3 | note | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
a951f907-06f1-5c93-b868-daa290024f1b | note | Action Point Records required - Witness Point/Spray sheet
ec7a5380-8b44-5a9a-9e2c-cf5fecd4a736 | note | Responsibility - QA / SE
933685c5-8efb-4a16-87fb-1de4e834dd5d | checkpoint | 4.11
51101139-59cd-534a-ba64-eaf71bfec1ac | note | Lab, PQE or Field, PE - Field
e9ab05d2-38ba-5686-80b3-35eff4b77290 | note | Material Test Method Requirement - Post Seal Inspection
ef4c8c91-8c6e-55ff-9ee8-b23c9790247e | note | Reference Documents - TNZ P3: 1995
b4a8f96f-67ae-5573-aecb-fe45ccf11c70 | note | Material Acceptance Criteria (Method) - Engineers Inspection
311bad5b-156b-55fd-90cd-06f0928d5d86 | note | Material Test Frequency* - After sealing
99408849-f263-5c94-bf6c-35c7b47834c7 | note | Target Criteria - The chip is embedded, uniformly placed and chipseal is fit for purpose
cd3b937c-6992-57f1-99a8-6037da69e6cd | note | Action Point Records required - Witness Point
2cd812e8-47fb-5886-93e2-9f3315ed62f2 | note | Responsibility - PM / SE
d5ed9572-3b51-4c2d-ab50-65bfbbaa9744 | section | 5.00 Post Construction
901f4b97-f979-4b24-af89-21ad19ad229b | checkpoint | Compliance - 5.01
2a914f6d-fd8a-509b-98e1-6282aba5b0c1 | note | Lab, PQE or Field, PE - PE
18c85856-05ae-5bd2-a93e-580ba5cadaa2 | note | Material Test Method Requirement - Asbuilt and RAMM Data
10890ce0-47f5-524d-ac3d-09ae1325235f | note | Reference Documents - RAMM Update sheet
5a0ce04e-f5a7-5b40-8e1d-77f1ec114869 | note | Material Acceptance Criteria (Method) - Asset Management Information Plan
d3f18fc5-1e42-52c4-87fe-c2ae74b06bde | note | Material Test Frequency* - After works complete
7f4c1e8b-420a-5a17-ab20-eb7d80f4f111 | note | Target Criteria - RAMM sheet 100% complete and accurate .
a5728426-94b3-56d4-9208-9a2d4da166ec | note | Action Point Records required - RAMM Asset Update sheet
0cf436ac-52f7-5a09-9cad-adc81ed43768 | note | Responsibility - Project Engineer
3840300a-4d68-426d-8bc0-aeb3be7e13d9 | checkpoint | Compliance - 5.02
ea9afabf-eb0f-5501-b7f1-de9b55ef2076 | note | Lab, PQE or Field, PE - Lab
ab3f3599-4059-5651-b868-98e3e6008501 | note | Material Test Method Requirement - Site Safety Audit
5e3764da-8cfc-538e-9299-55cd262282dc | note | Action Point Records required - Test Record
2b54f563-d720-5698-ae4f-4c7d9ff5e2ef | note | Responsibility - PM
99dd8a12-55fe-4093-821d-7216593af43f | checklist | Paul Cres - Granular Rehab ITP |  | Paul Cres - Granular Rehab ITP
5a2d5bc5-5988-4702-a8de-551868724419 | section | 1.00 Subgrade
c72a7284-4611-4636-adc2-84dbf641229c | checkpoint | 1.01
13eec248-a512-52c1-af78-13ac31510be3 | note | Lab, PE or Field - Field
6183796e-70c1-5554-ba12-ef2ec0c9cc16 | note | Material Test Method Requirement - Scala Penetrometer Cohesive soils only
21b7ffc8-9ddd-5e1f-83ad-851782af6744 | note | Reference Documents - RITS Table 3-20
551f0eef-ab2c-5b59-b09a-5790e92e4fec | note | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
8a42e90d-094a-5014-bc18-fe7e3321154a | note | Material Test Frequency* - 1m inside of edge of seal, on both lanes, at 10m spacing Minimum of 10 tests and/or at a frequency of 2 test per 10m chainage, whichever qty is greater
859ad091-80f4-5000-9645-a149127cf3f0 | note | Target Criteria - 2 Blow per 100mm ,average over 900mm depth
d9d5c6df-9c6b-5571-9934-8349785160af | note | Action Point Records required - Test Record
89264ad5-1601-51e8-aa95-cc2429cbbab6 | note | Responsibility - QA / SE
4a140857-6b3b-41a6-baf5-fe0b120e498e | checkpoint | 1.02
d2e92396-52ba-5b59-b289-4985a458e96b | note | Lab, PE or Field - Field
07742c25-16e4-51e1-b7af-731921b89a6e | note | Material Test Method Requirement - Clegg Hammer Aggregate fill only where subgrade undercut or trench backfilled
5fd32638-516f-55d3-9c8a-9a1d17887d72 | note | Reference Documents - RITS Table 3-21
0d6ecaa8-89a3-5f62-b19d-e1234cf7f5b5 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3 ASTM D5874-16
e0183631-1a63-5500-97d4-182f69aae858 | note | Material Test Frequency* - In centre of undercut or trench Minimum of 1 test per undercut location
69f215eb-5af0-5e98-8c94-997995904140 | note | Target Criteria - CIV ≥ 15 or CBR of 20
1809034c-8e22-5c03-a52f-ec68e8ed6fda | note | Action Point Records required - Test Record
9a9b713d-211b-5175-8cf3-d329ffb8cb35 | note | Responsibility - QA / SE
81da39a2-f3be-4322-be26-2126728a679e | checkpoint | 1.03
abe25f7a-6646-5f59-bc07-b254999860d3 | note | Lab, PE or Field - Field
49170e1b-f7d3-517f-8586-c1283aec0517 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
3b31aba1-d40c-5d27-9df9-09d984d89522 | note | Reference Documents - RITS Table 3.24
a3e1d185-296c-5ce1-966a-68f29e16e66c | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
86b536ce-d65f-5bad-9b07-6d2af3f1aebf | note | Material Test Frequency* - 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
dffcefb8-436f-57f2-a4db-71a0b102803b | note | Target Criteria - +0mm/-30m from design or nominated level No more than 15mm deviation from a 3m straight edge
a8c08abf-fe29-5061-a108-772b503aa105 | note | Action Point Records required - Survey record
ffb2e967-fde5-5f95-8a4b-b3b0a01f258f | note | Responsibility - QA / SE
f1fb94bc-36ca-4290-ae5c-146b2a69d337 | checkpoint | 1.04
f3d7b95a-e797-5e9c-97ca-ab0944ca72c8 | note | Lab, PE or Field - Field
d2904e89-f709-55f9-a028-3a80bb2e4884 | note | Material Test Method Requirement - Geogrid and Geofabric (cloth) installation
6f111720-7586-53bb-8a21-49518a8ea813 | note | Reference Documents - Geogrid
177c6256-a290-5049-a401-e2a96aa71a56 | note | Material Acceptance Criteria (Method) - Manufacturer installation instructions
b72a4ccf-9076-5813-80a0-a717cc1d7e29 | note | Material Test Frequency* - 100% of Surface
8aa8b189-cb61-52d1-b3cf-19251d180bf9 | note | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints. Geogrid and Geofabric shall be neatly installed without creases or folds.
13d82281-03b4-5962-85bf-805e45f7c747 | note | Action Point Records required - Site Record
462f635b-be1d-505d-a4c9-e66c483d3b10 | note | Responsibility - QA / SE
c6eca931-6069-4498-b3cf-1052e16cfb0f | checkpoint | Compliance - 1.05
3b938235-9884-5b3e-a93e-6e7d026a54ed | note | Lab, PE or Field - PE
4b0404f7-85c4-54ac-8722-affb8d51782a | note | Material Test Method Requirement - Is the layer closed out ?
6887c125-7ccd-52a4-adc3-4e0464fd660e | note | Reference Documents - See PQE
983f6c8f-ac94-5d5b-9cc3-9cd403bd0f05 | note | Material Acceptance Criteria (Method) - See PQE
b2814491-4d1d-50b2-99c0-c817067d4499 | note | Material Test Frequency* - 100% of Surface Prior to placement of material
82745c5d-46cb-598f-b67f-eab4316671df | note | Target Criteria - PQE Approval All testing record & reviewed as compliant. Available Documents: Test records Survey records Hold Point Records
5cbaef80-f0ee-5513-b03b-874e605398fe | note | Action Point Records required - Hold Point
3fc1b029-c3db-50e1-bf63-615c5adad468 | note | Responsibility - PM
347e51a6-23e0-46ba-970f-285902240d69 | signoff | AUTHORITY HOLDPOINT
0c3da57a-03ab-410c-91f2-c6f851dd3165 | section | 2.00 Subbase
51dd8b78-423c-4106-bbce-3727f2ecdbac | checkpoint | Compliance - 2.01
165970c9-1574-58d2-9f8c-0618d8f08034 | note | Lab, PE or Field - PE
510f8f2f-88cb-5bc7-8039-0f93806f7832 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
d3821ceb-97ea-5c1c-a706-44970a000609 | note | Reference Documents - Insert Material Testing link
6f50f8b6-0c31-5cba-b641-57f291cb1037 | note | Material Acceptance Criteria (Method) - See PQE
f95d7954-0323-53de-bc37-339bfb3fe350 | note | Material Test Frequency* - Prior to construction commencing
006800d7-5fc1-5af6-9e19-233ede0b6adc | note | Target Criteria - Material meets project requirements
c4965a89-0c25-5392-a45c-5829cc6eec86 | note | Action Point Records required - Hold Point
77beca6c-920b-5dcb-b963-9e5201f3bc0e | note | Responsibility - PM
9cd8e91d-55e5-498e-8a64-3f59516f3666 | signoff | AUTHORITY HOLDPOINT
63556e65-9669-4704-a738-29411431466c | checkpoint | Stabilisation Delete if Not Required - 2.02
f75a7bdb-397c-5685-be5e-0c1c6226915e | note | Lab, PE or Field - Field
d9d081e7-90ab-5915-a9f6-45782a10614e | note | Material Test Method Requirement - Cement application Mat test
e6d58954-131d-55f0-9f26-bd5346c0315f | note | Reference Documents - TNZ B/5:2008
b0a1a775-e5ed-54dc-b490-a822c55da405 | note | Material Acceptance Criteria (Method) - TNZ B/5:2008
3acd1405-f6f4-54cd-94d5-43ba23b96e63 | note | Material Test Frequency* - 1 test per 400m² (minimum 1 per run)
f104fee6-8175-5450-9b1c-f62ad0aba19e | note | Target Criteria - ±0.50kg/m² of specified rate
fd30001a-5538-5101-9ccf-5fb850ff2a29 | note | Action Point Records required - Stabilisation QA sheet
637ae63c-9361-5f79-afb6-ca9e4b17e71c | note | Responsibility - QA / SE
edc7cee0-2422-49d0-857a-dafe3b083cde | checkpoint | Stabilisation Delete if Not Required - 2.03
d399c289-01c7-5411-a8bf-09a7e72b3650 | note | Lab, PE or Field - Field
4edb0010-f6b1-54b3-8dc1-2f7c589d73ff | note | Material Test Method Requirement - Stabilisation Depth
55713d1b-f161-554b-8735-c1ece7cdf189 | note | Reference Documents - TNZ B/5:2008
2611d50b-6e5b-5411-9975-2ec871903d58 | note | Material Acceptance Criteria (Method) - TNZ B/5:2008
47ac6ad2-303c-5738-abbb-0401fc38be50 | note | Material Test Frequency* - 2 test per 400m² (minimum 1 per run)
d053b5e0-acca-5b7f-b204-9a60137b0c5b | note | Target Criteria - Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer
4cb271f5-95d3-59aa-a664-a15d5a9fdc31 | note | Action Point Records required - Stabilisation QA sheet
74dc152f-3bec-5150-8f84-611f8a8a9c29 | note | Responsibility - QA / SE
79f0df98-b055-444f-9243-b8931add5df3 | checkpoint | 2.04
8165b2cc-e7fe-5c33-b021-bd435dea7185 | note | Lab, PE or Field - Field
52e4af2b-1aa4-5adf-9e0f-9a7ddfa53852 | note | Material Test Method Requirement - Plateau Density Test
14da305f-90ac-5f9e-b772-a446b2d18149 | note | Reference Documents - TNZ B/02: 2005
fd4fb09f-7b46-5a08-b2fe-d0a1ec43b2e9 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
a48d4030-11fd-5b85-b583-63fa383d5654 | note | Material Test Frequency* - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer
56b3fad3-2fbc-58b8-ac61-3ddb8e2113ec | note | Target Criteria - N/A
f8aaa1cd-3aaa-5da0-93de-15a6c3564f72 | note | Action Point Records required - Hold Point Test Record
014f01f6-b4f8-5851-8d26-2f87ee0696f6 | note | Responsibility - PM
8116423f-00ce-4fe7-b5f9-1d815e188fa5 | signoff | AUTHORITY HOLDPOINT
60906226-0be2-4e32-870e-c67090060bca | checkpoint | 2.05
de2dc4d1-a62b-559d-bcb5-856422c10252 | note | Lab, PE or Field - Field
48765872-aa77-59da-81dc-00bf67e3ea4b | note | Material Test Method Requirement - Clegg Hammer
7aed1d5d-7a3a-548d-881a-2b18183ad0ec | note | Reference Documents - RITS Table 3-21
be438677-ec08-5c6c-815b-17a695ca8879 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3 ASTM D5874-16
37f6a0b6-e33b-575d-b203-b16e58f43b96 | note | Material Test Frequency* - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
1a985e12-5a50-5049-9751-185e463a3d45 | note | Target Criteria - CIV ≥ 35
c32c6849-b4b6-521f-b46c-5e613778f823 | note | Action Point Records required - Test Record
b3d41211-9a0f-5ef1-8e9d-a8bda08d978b | note | Responsibility - QA / SE
776c9d98-feef-41ad-b9a5-648676e08a04 | checkpoint | 2.06
ad1978d1-1fe2-596d-be21-1a68bfffff21 | note | Lab, PE or Field - Field
fd6a8515-ba66-58d3-8de5-5abc9e7eb28c | note | Material Test Method Requirement - Compaction NDM Back Scatter
3c629d73-fb97-5cfb-8395-574cb3888650 | note | Reference Documents - RITS Table 3-22
9fdc32b1-7180-5f7e-ae76-e208ec089fdb | note | Material Acceptance Criteria (Method) - RITS 3.8.3.4 4407:2015 test 4.3
fa835e95-d77c-5529-8fa4-7017441261c0 | note | Material Test Frequency* - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
00b3080a-ee2d-5c4f-97c4-7b4118c5e070 | note | Target Criteria - Mean ≥ 95 % MDD Minimum ≥ 92% MDD
f92c98b0-54e2-5f30-93a1-71d72da22dcb | note | Action Point Records required - Test Record
077702a7-29f4-5eaf-b8f9-2900be717a05 | note | Responsibility - QA / SE
500273f6-84bf-4a61-98e2-05c192e37ff7 | checkpoint | 2.07
b73921bc-06c8-5588-abfe-e334b4fd104a | note | Lab, PE or Field - Field
528195c6-b616-5df3-9b5a-75783a11e981 | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
7d2b4937-79aa-5e08-9797-015394b902c1 | note | Reference Documents - RITS Table 3.24
907b55fc-758c-54eb-9873-ee891ccbcfaa | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
df83f971-7840-541f-803b-4997d3f1a702 | note | Material Test Frequency* - 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
f1d34b44-4964-52b2-8aab-32209963c05e | note | Target Criteria - +5mm/-25m from design or nominated level No more than 15mm deviation from a 3m straight edge
20dcf0b6-865b-502b-9f26-7e5bb1f1e177 | note | Action Point Records required - Survey record
e7a196c4-b7eb-5813-aeca-b28b9833a488 | note | Responsibility - QA / SE
d0a3136d-9262-4aa7-bc0c-f0adac76e029 | checkpoint | Compliance - 2.08
4ae1d04e-aee3-5201-bc56-0a5300de1cf3 | note | Lab, PE or Field - PE
9e4de299-df6c-5c12-8f60-e838d7191062 | note | Material Test Method Requirement - Is the layer closed out ?
370484e7-80bd-54d4-bfa4-d310b007b7a7 | note | Reference Documents - See PQE
2c849f04-36a2-5ce4-830e-c798b5b349d6 | note | Material Acceptance Criteria (Method) - See PQE
08f02cd4-372b-5392-8888-ae6707ed7927 | note | Material Test Frequency* - 100% of Surface Prior to placement of material
ed6e4f34-ad71-5b7c-98ea-ed1b637e5922 | note | Target Criteria - PQE Approval All testing record & reviewed as compliant. Available Documents: Test records Survey records Hold Point Records
1fd7435e-2ea7-5c0c-b622-505cd02ef14b | note | Action Point Records required - Hold Point
8b9eed31-ba15-54f5-b524-5be8ddd9537e | note | Responsibility - PM
146b864e-d72c-4467-b981-8d326f840f3f | signoff | AUTHORITY HOLDPOINT
fb1ff8f1-b51d-4951-a15b-c2a60ff47941 | section | 3.00 Basecourse
61adc1fe-31c2-4a7e-8293-744f6bc70ef4 | checkpoint | Compliance - 3.01
03178c89-34f6-5fd9-a003-5fc7f9ce5e44 | note | Lab, PE or Field - PE
3b49aa8d-0666-5b8a-9494-a71278408687 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
5d0afc2c-d251-574b-9ecd-17ac8ef601bb | note | Reference Documents - See PQE
d5c3ea19-45b0-5cd5-ab35-98e1cea58d2d | note | Material Acceptance Criteria (Method) - See PQE
cb9103e2-a518-51d2-9d3b-8763f9da2343 | note | Material Test Frequency* - Prior to construction commencing
bd70de33-e2fa-5770-bb59-fa1cea54c1e8 | note | Target Criteria - Material meets project requirements
febb7aa2-6080-55d1-9b27-53cbf8c31aad | note | Action Point Records required - Hold Point
41c2e0ed-7f73-5595-bf20-6250f53f74e5 | note | Responsibility - PM
a8e085b0-b8d8-453f-a43d-a8b95d588c5a | signoff | AUTHORITY HOLDPOINT
b7144902-4246-4aa9-9ddc-aee0882d9e8a | checkpoint | 3.02
b1f40414-96be-5e7a-b482-6aa02303aa32 | note | Lab, PE or Field - Field
ee46ba4a-0a03-5672-b72c-b92e5737ece4 | note | Material Test Method Requirement - Plateau Density Test
555c76a8-3faf-5e41-b353-89ce033e1a8d | note | Reference Documents - TNZ B/02: 2005
314d47b0-536f-597a-baaf-3c3a67d95720 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
8c084d5d-ef3d-5824-b71a-1ef21a3143ae | note | Material Test Frequency* - 1 test per site
74cbdc1d-77d2-57f2-8696-baa216956eac | note | Target Criteria - N/A
c8e9eb13-9582-5ff1-9ad4-7983232e29e5 | note | Action Point Records required - Test Record
0df9f63c-b2cb-5515-a330-6be788eb827b | note | Responsibility - QA / SE
110a3ec5-52ff-4ebe-afaf-02e1c7de742c | checkpoint | 3.03
1e74adab-4fbb-5cf0-9833-bc2c0ee38753 | note | Lab, PE or Field - Field
c8d01ff0-596e-5b27-81c6-5ae812aa4d40 | note | Material Test Method Requirement - Clegg Hammer
5c8fb220-3a1a-5c3a-a981-d5500d3d770a | note | Reference Documents - RITS Table 3-21
005ef584-94fe-5643-9b16-70081cfd9132 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.3 ASTM D5874-16
5f21bf40-04b0-5453-b79a-5f1fb716175b | note | Material Test Frequency* - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
883873b4-740d-5463-b634-1785b4c3d488 | note | Target Criteria - CIV ≥ 40
19b1d3d8-e620-5adc-a773-fc16f683d148 | note | Action Point Records required - Test Record
64b5019d-edba-5e90-89d8-714fdb08c2b9 | note | Responsibility - QA / SE
7cb4a27b-325f-4113-bc63-37c1c977b0ad | checkpoint | 3.04
6976a289-1904-5b5b-9ce7-9e86cedeeafb | note | Lab, PE or Field - Lab
5186bf32-7b42-5fc8-923d-d6e5ab538f37 | note | Material Test Method Requirement - Compaction NDM Back Scatter
f119a131-a9e0-5114-b53e-826881c111cb | note | Reference Documents - RITS Table 3-22
aa035417-e3d0-511f-88e5-e73d5574b138 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.4 4407:2015 test 4.3
47f522ef-4fc2-54ba-baee-5c3fc86a02c4 | note | Material Test Frequency* - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
99132e72-ebf5-59d9-8de9-33ac9906f092 | note | Target Criteria - Mean ≥ 98 % MDD Minimum ≥ 95% MDD
781edb22-bd1a-5593-a7b4-652a7ad3b2de | note | Action Point Records required - Test Record
64a8a452-e1cf-5f54-8378-3746dd03b44f | note | Responsibility - QA / SE
832accef-5a7a-4093-b042-6beec4e903e9 | checkpoint | 3.05
e64be859-ef57-5b96-9656-0f3c2a28139e | note | Lab, PE or Field - Lab
6611ab92-5bea-5424-8043-34adde242b30 | note | Material Test Method Requirement - Benkelmen Beam Deflection Testing
426ef476-bcd2-5106-a905-2106ad5800f8 | note | Reference Documents - RITS Table 3-23
5eb2b994-5387-52a7-8f7b-5e38665e54d0 | note | Material Acceptance Criteria (Method) - RITS 3.8.3.5 ASTM D5874-16
1f2aa5c9-8635-599e-a9e4-3ca36bf54918 | note | Material Test Frequency* - 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests) Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater
68d0af4a-29ae-5d74-8e0f-012359e85666 | note | Target Criteria - Max deflection allowed: 1.45mm From design report - due to non-RITs compliant Subgrade CBR
e81fd55c-5d7a-53e1-b3f0-0b27b3f917af | note | Action Point Records required - Test Record
3f6b5a73-22cd-59a3-bc4a-1a729df4daf4 | note | Responsibility - QA / SE
ec509d41-03a1-46e0-88dc-c31f4969d3ef | checkpoint | 3.06
088191a4-0091-5be6-9446-e3d8fe94ba70 | note | Lab, PE or Field - Field
ed103827-6046-5c8a-8eb0-4f16b899397a | note | Material Test Method Requirement - Surface Level, Shape, and crossfall
2ea1c26a-900d-58b4-8597-c2515e0881f6 | note | Reference Documents - RITS Table 3.24
e1b99ef9-e5da-5615-8b58-cd74e2468cbb | note | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
0b8f953f-eae0-577b-bfd5-99f2277f8ca3 | note | Material Test Frequency* - 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
fca8db46-5622-5580-9f29-93fd756cd3e9 | note | Target Criteria - +10mm/-0mm from design or nominated level No more than 12mm deviation from a 3m straight edge","+15mm/-5mm from design or nominated level
73945289-81bd-5e2c-af0c-de61c3e95957 | note | Action Point Records required - Survey record
b4f48be9-045c-56d4-a09f-6a8c364d3323 | note | Responsibility - QA / SE
4101cae4-2d4c-4d86-ae08-4f54ea2fee12 | checkpoint | 3.07
e00458ca-3fd3-56ee-831c-32340c6becac | note | Lab, PE or Field - Field
c7cdac3e-68e1-5833-a5f9-5768f116687b | note | Material Test Method Requirement - Visual Inspection of Basecourse Surface
e8d0f013-5a1c-5936-99eb-b48617a54586 | note | Reference Documents - TNZ B/02: 2005 7.8
c066eee7-f9fc-5d2c-8991-d097e9bdbffb | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005 7.8
9ac600a6-51f5-5ac1-bd09-b6cb48aec762 | note | Material Test Frequency* - 100% of Surface Prior to sealing of surface
43ee5458-8a24-5885-8d87-74e663727acf | note | Target Criteria - Engineers Approval (The larger aggregate is held in place by with a matrix of smaller aggregates, the smaller aggregate is held firmly in place by fine material, and the matrix does not displace under normal trafficking or sweeping No evidence of rutting in surface)
453c31a2-3b81-57a3-8cfe-e60325d228ef | note | Action Point Records required - Hold Point
b94c42b4-19e9-51b3-bf0c-b737f25e89e2 | note | Responsibility - PM
238aa789-1ae9-41c8-93b5-3b06c5f82e54 | signoff | AUTHORITY HOLDPOINT
4f2b5883-5981-4dc4-9958-a7bca22d761f | checkpoint | Compliance - 3.08
7e535ebc-79bd-5df8-96f9-1ff869e45c3c | note | Lab, PE or Field - PE
b058d0e4-6ff4-5e71-b858-5870774683be | note | Material Test Method Requirement - Is the layer closed out ?
29ba01d3-1fbb-5475-a764-442bf230b773 | note | Reference Documents - See PQE
35db46bb-0c37-5087-a5e9-124396281c79 | note | Material Acceptance Criteria (Method) - See PQE
29c435e7-9b3d-5d83-a944-537eaa8a99ae | note | Material Test Frequency* - 100% of Surface Prior to sealing of surface
a355ff25-c76e-5885-99c2-b64350ee5538 | note | Target Criteria - Engineers Approval All testing record & reviewed as compliant. Available Documents: Test records Survey records Hold Point Records
635e504b-deb2-5a38-9cf6-ae9d5e244bde | note | Action Point Records required - Hold Point
1e46da5f-79b7-5d51-b501-8bd919275029 | note | Responsibility - PM
2a7afef0-969f-4df9-b18b-e3da52a3c528 | signoff | AUTHORITY HOLDPOINT
800e5864-6885-40f8-a2cb-ce83389ad994 | section | 4.00 Membrane or First Coat Seal
33dbfdc1-9726-4e8c-b2d0-56c7add49ac6 | checkpoint | Compliance - 4.01
9df3c2c1-ee10-59a3-90d9-ecc14cb942fa | note | Lab, PE or Field - PE
71560fb4-5d9a-5cf2-b6d2-02d1cc54e896 | note | Material Test Method Requirement - Seal Design
5cb3aeb5-9a25-5e68-a6bc-d7473c259edd | note | Reference Documents - INSERT SEAL DESIGN
1a59600f-e6f1-5cf4-b11b-cd11d7368431 | note | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
a9a84d0a-6272-5774-913d-d9f8ee9728cb | note | Material Test Frequency* - Prior to sealing commencing (Minimum 1 week prior to application)
5d8199a9-1c92-50c3-8786-286d2c19b57e | note | Target Criteria - Meets project requirements
5d4726f3-c619-5832-8e86-b17b1d269b51 | note | Action Point Records required - Hold Point
ea2d2b72-f1e1-5316-ba21-af6ebd4593e8 | note | Responsibility - PM/ SE
6f862e59-7b25-4bbf-98a9-750c5d679618 | signoff | AUTHORITY HOLDPOINT
5ea30588-b1f6-49c2-a64a-e3f1f3306f7b | checkpoint | Compliance - 4.02
787da9d7-eab0-5e91-a4f2-1fdfcc5b6b55 | note | Lab, PE or Field - PE
9564208b-a363-5771-972c-38c6aba75b45 | note | Material Test Method Requirement - Bitumen Sprayer
a31911a2-c1d7-5d6a-bf51-983df80f7bad | note | Reference Documents - TNZ P3
88c1ae42-b50a-5d9d-80bb-34660de86b61 | note | Material Acceptance Criteria (Method) - Certification provided
614eeb88-c282-5daf-a5c2-d701e2cee8f6 | note | Material Test Frequency* - Prior to starting
83918da0-369a-51a7-9fce-c2e4529f9d24 | note | Target Criteria - Current E/2 Certificate
0c65c0b4-fff7-5c72-8af0-788be81ce3e6 | note | Action Point Records required - Certificate Sheet
c824812d-b56a-53be-92dc-115e246ecbb4 | note | Responsibility - QA / SE
570ca531-8dec-4231-b3eb-e51a0475ca12 | checkpoint | Compliance - 4.03
376377db-4e56-578e-8bae-407764b84f8c | note | Lab, PE or Field - PE
860f909d-5a57-574d-ab3b-efdee802f6f4 | note | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
a306c09f-b655-5ebc-8732-4f29cbb9cda0 | note | Reference Documents - Insert Material Testing
66809c47-b288-573d-bbfa-6652f36f53f0 | note | Material Acceptance Criteria (Method) - See PQE
250afb13-666e-5025-9c72-c91a095f9452 | note | Material Test Frequency* - Prior to construction commencing
993cf121-1b53-5425-9d04-6ac35ce4ef3a | note | Target Criteria - Material meets project requirements
ec892b02-813e-56da-a7a5-2bddd99b5179 | note | Action Point Records required - Hold Point
814583c7-42fa-55c8-a602-9908001110fd | note | Responsibility - PM/ SE
69fae025-aa4b-4179-940c-85d89fb194c6 | signoff | AUTHORITY HOLDPOINT
95f9f455-8c3c-4b2f-9847-d10d745281bd | checkpoint | 4.04
05f40ee7-0807-5ba7-a6c8-f96b84001496 | note | Lab, PE or Field - Field
0be03b4c-3b4f-52ce-af90-f0e3a22bd76b | note | Material Test Method Requirement - Preseal Inspection
51135a22-4769-53e5-bd28-36d71d89b041 | note | Reference Documents - TNZ B/02: 2005
d3f13dc4-910d-5a24-9943-97905433c381 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
466d1de2-984c-5459-8419-9c0505f68dd7 | note | Material Test Frequency* - 100% of Surface Prior to sealing of surface
c6f70e89-bd14-50a5-9fa6-43743eaa7832 | note | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
7de2d571-dcad-530d-b9f6-8ddbeb1c4f3b | note | Action Point Records required - Test Record
0cea0853-0bcf-5e4b-ba4c-d45c3e07c6ce | note | Responsibility - QA / SE
78f4d8ff-be0c-46ac-846a-efe0cf177980 | checkpoint | 4.05
31fe4bce-fdd1-5b17-a11f-ea79e62d068a | note | Lab, PE or Field - Field
2c2dd765-78f0-537c-9f56-82a4b33795a0 | note | Material Test Method Requirement - Degree of Saturaton
5e20c2fb-41b9-52ca-8ec5-97b8abc5dbea | note | Reference Documents - TNZ B/02: 2005
431ccd80-3961-5882-bee9-6d87daacb0a2 | note | Material Acceptance Criteria (Method) - TNZ B/02: 2005
f518ade9-9211-57f4-9e23-bfd607d7dd4b | note | Material Test Frequency* - 1 set of 5 per 1000m² - then 1 per 200m²
7f6b2da7-d641-50e8-8dab-d4aa533bdde6 | note | Target Criteria - < 80 % Completed Max 48hrs before sealing
5d7d0f10-8d18-5fa8-9c89-427e70893363 | note | Action Point Records required - Test Record
4710f8d5-c145-52ea-a593-637b6211932e | note | Responsibility - QA / SE
c0b850b4-ad4b-44d2-a300-f1d0e52e4d0c | checkpoint | 4.06
53f15443-8127-5901-ad57-89b1110e81d8 | note | Lab, PE or Field - Field
e8632f7f-d9ee-5820-9722-872a2105e8a1 | note | Material Test Method Requirement - GO/NO GO Survey
83c2476e-3b7f-5dc3-b242-ee45b027e8e4 | note | Reference Documents - Downers processes
95bf39d2-5604-59d7-ae45-3c6efcb2ac2e | note | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
24bd2e42-72d7-5140-9c0d-2fab232d1071 | note | Material Test Frequency* - Prior to sealing on each site
dbfe0380-cfad-5c8e-afba-286547702cba | note | Target Criteria - Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager
bd1fe742-7638-5c33-bf73-84c9b5b66865 | note | Action Point Records required - Survey record
42bfdaa4-2efe-5ca0-90f9-2ea89dfeac79 | note | Responsibility - QA / SE
a175b658-c6ef-46f6-b782-0f5db61bccb1 | checkpoint | 4.07
c677b336-d469-56c0-abc1-9d408194c0f0 | note | Lab, PE or Field - Field
94336e2f-f8be-53e9-b02d-f6c6218688ec | note | Material Test Method Requirement - Road temp
1f8140c1-d80e-5af8-9cb2-954f55466dd7 | note | Reference Documents - TNZ P3:1995.18
c838d5f1-56e2-58bf-b3a1-a082d0200012 | note | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
1dad5f66-068b-54ce-806c-d3063c146027 | note | Material Test Frequency* - Once per day of sealing prior to sealing commencing
8e4c546e-df32-5fca-bc22-1554827507a5 | note | Target Criteria - Air temp >10°C
b1d34ce3-5d32-5de8-b236-84d17c2daa25 | note | Action Point Records required - Spray sheet
598b0627-647e-56ff-a9f8-c598ee2f7e00 | note | Responsibility - QA / SE
6bafff2f-11f7-4481-bd96-86222a7b28db | checkpoint | 4.08
3dfba68e-7cd7-57b2-88c2-d8b1e7443a4b | note | Lab, PE or Field - Field
aeebe961-8e1e-57c4-90cb-8f49f484a1cd | note | Material Test Method Requirement - Application Rate
b4daffe0-30b8-505c-b554-f64a03f5934c | note | Reference Documents - TNZ P/3 : 1995.18
a914757b-5d73-5b9c-a5a2-56b20a84dddd | note | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fitted to sprayer
4f6af59d-f319-5e3a-b427-104771e0fc08 | note | Material Test Frequency* - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
f2d66d7b-38df-561a-8062-aa3769e937c9 | note | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
f4ea3d8e-1d41-5679-9da5-d3ca4a3da11b | note | Action Point Records required - Spray Sheet
e08f8c1f-753e-585c-bf87-8cc4e8638b35 | note | Responsibility - QA / SE
877d6a90-79b4-4dc0-a501-b201feae728f | checkpoint | 4.09
7ab36ebb-a5fe-50cd-bf47-ecf81b8807e5 | note | Lab, PE or Field - Field
5318f9de-6b0b-5bb4-b456-ab6d78d6f1c2 | note | Material Test Method Requirement - Chip spread rate
45b112a5-815a-5fdf-94a7-d082281fd4e7 | note | Reference Documents - TNZ P3: 1995.21
b84b730e-081c-54b6-a880-6195f991d07f | note | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435)
f168bc51-8536-5527-9862-0689d1d878d9 | note | Material Test Frequency* - Total amount of chip used to be calculated at end of days sealing
5920e48d-f7e8-5a1d-9f0b-9e911a7a26be | note | Target Criteria - Visual checks meets seal design requirements
a1d81f95-c5f3-5b58-b45c-85d9c2c8fe3c | note | Action Point Records required - Witness Point/Spray sheet
b2947482-a1d0-5c05-8aa7-d6bae4a9c242 | note | Responsibility - QA / SE
3a36c474-c7bc-4a63-8a7a-c214a17d9897 | checkpoint | 4.1
1e997f76-652f-5bdf-8f34-66d4c0a581b7 | note | Lab, PE or Field - Field
6997551d-e28a-5385-ab9c-576b83e994d9 | note | Material Test Method Requirement - Rolling Checks
666cbfbc-c2a7-5d57-ab5e-98d0a7cee869 | note | Reference Documents - TNZ P3: 1995.22
b4d098bb-fb30-51bc-9171-558a740bacb7 | note | Material Acceptance Criteria (Method) - Sealing Record
778b30a4-914f-563a-826b-e3d970cabac3 | note | Material Test Frequency* - for each sealing site per day
c1e52175-54e8-52fe-a528-e29168dd0740 | note | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
306b0217-9e45-55d2-995b-3bf078e375b7 | note | Action Point Records required - Witness Point/Spray sheet
4835ffa1-5b33-5eb5-af4a-e874157b8790 | note | Responsibility - QA / SE
b66d0bb3-69f5-4e18-966e-ff0df9450d94 | checkpoint | 4.11
8ad2977e-5ed0-5c12-adcd-dd79c067002d | note | Lab, PE or Field - Field
7d11ad75-5ec4-50b8-8f51-11c80bc3c347 | note | Material Test Method Requirement - Post Seal Inspection
ef611833-a55e-576a-9708-01965cd6ee53 | note | Reference Documents - TNZ P3: 1995
af4936b1-d5bb-57be-ac21-d011434bde3d | note | Material Acceptance Criteria (Method) - Engineers Inspection
2a942471-ff3b-5633-b7a9-9cbbed4ab9fc | note | Material Test Frequency* - After sealing
06284e85-7cb7-5ce2-b34b-aaa4d7018bde | note | Target Criteria - The chip is embedded, uniformly placed and chipseal is fit for purpose
ae083ebc-3c88-5081-8e6d-81d20b34710d | note | Action Point Records required - Witness Point
1b3a310c-fc48-5a96-af48-77717c12c6f4 | note | Responsibility - PM/ SE
3776067d-e0cf-4d09-9241-8abfd05a8833 | section | 5.00 Post Construction
a7020d79-cafd-4784-bf7d-54fb77f70662 | checkpoint | Compliance - 5.01
2736d22f-8184-5fc2-8f84-fb3fc4ddc9e5 | note | Lab, PE or Field - PE
d4a20254-fd19-5df4-8bb9-be1a07c34c9d | note | Material Test Method Requirement - Asbuilt and RAMM Data
b3e95c6a-905e-522f-9704-574d72a63e70 | note | Reference Documents - RAMM Update sheet
7cc7f594-36e0-5863-a368-8ef94862f459 | note | Material Acceptance Criteria (Method) - Asset Management Information Plan
ac8006e2-e6df-526f-8058-5b495544df81 | note | Material Test Frequency* - After works complete
61f0e20e-72a5-5a32-a9fa-f9bdc1dc542d | note | Target Criteria - RAMM sheet 100% complete and accurate .
24dbdc70-cd67-5fa7-a2f8-0dee7c701bea | note | Action Point Records required - RAMM Asset Update sheet
548a9091-56f7-5984-a3b5-30c26d5e70a0 | note | Responsibility - Project Engineer
4e6f7c21-d690-455c-972e-f5e823ba8e57 | checkpoint | Compliance - 5.02
bf545ae2-3339-51c5-9a9c-b86c8b3ea6ce | note | Lab, PE or Field - Field
04aa6ba1-3dbb-56f2-a2bb-0a715d9dee61 | note | Material Test Method Requirement - Site Safety Audit
bf803f4c-9ace-5651-ac01-dcbf1471349e | note | Action Point Records required - Test Record
06be78db-e6c7-5f23-8c75-7360286d5af8 | note | Responsibility - PM
3e8a2ff9-ff65-4fd2-8e58-bf93474d7193 | checklist | Prelim Checks - Chipseal: |  | Prelim Checks - Chipseal:
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
8be18d95-bde5-44b1-849f-5c55ec66a862 | checkpoint-no-value | a) Seal Design
a0065bbb-b88c-46dc-bd37-8c1e242ee56b | checkpoint-no-value | b) TCE
e96ac780-af2b-48cb-b5dc-1562d250d4c4 | checklist | Prelim Checks - Rehabs: |  | Prelim Checks - Rehabs:
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
a6f10e8d-74de-481d-b162-74015236a1c8 | checkpoint-no-value | a) Design Reports
1bbb8065-7fa2-41f8-9636-2ac51f53f7ac | checkpoint-no-value | b) NPV
3cd6fbaf-d716-4717-913f-6adaf62ca014 | checkpoint-no-value | c) Final Treatment
51895e00-fdb3-4a17-912b-d2041e3a25aa | checkpoint-no-value | d) TCE
d14b914a-ffb9-447e-a121-58f098b9d602 | checklist | Prelim Checks - Thin Asphalt: |  | Prelim Checks - Thin Asphalt:
45e8814a-82cf-423b-a9fd-c3a56e777229 | section | Details
3c5a423d-3440-4f85-b942-71095cc29389 | checkpoint-no-value | a) Optionering Report
01a3c2bf-2117-4450-8756-68c4b6922e80 | checkpoint-no-value | b) TAC Assessments
be66fd57-1b07-4e1d-bd6e-c96894b29c4d | checkpoint-no-value | c) TCE
ccf1af12-4346-4b55-ac32-1b05fe634ab5 | checkpoint-no-value | d) Validated Mix