## Rehab ITP
| Site Name | Hukanui Rd | [6 empty] | Development Date:
| Carriageway width (m) | 18.5 |  |  | Target CBR value for subgrade | 3 |  |  | Role | Name |  | Acronym
| Surfacing Type | Chipseal |  |  | Scala - Minimum blows per 100mm | 2 |  |  | Foreman | Phillip |  | FM
| Kerb and Channel | Yes |  |  | Scala - Minimum blows per 300mm | 6 |  |  | Quality Technician | WSP |  | QA
| ESA (Million ESA) | 1.55 |  |  | Clegg - Minimum CIV value | 15 |  |  | Site Engineer | Stephen Makiri |  | SE
|  | From design report |  |  | Material used for Subbase | WHAP65 |  |  | Site Supervisor | Mike Graham |  | SS
| Does design align with RITs standards | No |  |  | Target MDD value for subbase | 2.24 (5.5% OMC) | from lab report |  | Project Engineer | Pratibha Metha |  | PE
| Theoretical max deflection on Basecourse (mm) | 1.7 |  |  | Material used for Basecourse | TNZ AP40 |  |  | Project Manager | George Issac/Brody Brown |  | PM
[5 empty] | Target MDD value for basecourse | 2.26 (5.5% OMC) | from lab report |  | Designer | Jordan Rae |  | DE
[9 empty] | Engineers Representative | n/a |  | ER
GRANULAR REHAB INSPECTION TESTING PLAN Rev 1
Item No | Material Type | Typical Use | Item ID | Lab, PQE or Field, PE | Material Properties Required for Acceptability for Permanent Works |  |  |  |  | link | Action Point Records required | Responsibility
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptance Criteria (Method) | Material Test Frequency* | Target Criteria
1 | Subgrade |  | 1.01 | Field | Scala Penetrometer Sand and Cohesive soils only | RITS Table 3-20 | NZS 4402.6.5.2:1988 | 1m inside of edge of seal and along centerline, both lanes, at 10m spacing | 3 blows per 100mm, to a depth of 500mm |  | Test Record | QA / SE
|  |  | 1.02 | Field | Clegg Hammer Aggregate fill/Subgrade or where subgrade undercut or trench backfilled | RITS Table 3-21 | RITS 3.8.3.3 ASTM D5874-16 | 1m inside of edge of seal and along centerline, both lanes, at 10m spacing and/or Minimum of 1 test per undercut location | CIV ≥ 15 or CBR of 20 |  | Test Record | QA / SE
|  |  | 1.03 | Field | Light Weight Deflectometer | Design Review Correspondence |  | 1m inside of edge of seal and along centerline, both lanes, at 10m spacing | Information only to confirm consistancy of in Situ SIL/Subgrade layer. Targe threshold of 30Mpa |  | Test Record | QA / SE / DE
|  |  | 1.04 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | +0mm/-30m from design or nominated level No more than 15mm deviation from a 3m straight edge |  | Survey record | QA / SE
|  |  | 1.05 | Field | Geogrid Installation | DuraGrid X & GridTex INSTALLATION GUIDELINES: BASE REINFORCEMENT APPLICATIONS AND STABILISATION | Manufracture installation instructions | 100% of Surface | Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints. Geogrid and Geofabric shall be neatly installed without creases or folds. |  | Site Record | QA / SE
|  | Compliance | 1.06 | PE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to placement of material | PE Approval All testing record & reviewed as compliant. Available Documents: Test records Survey records Hold Point Records |  | Hold Point | PM
2 | Subbase | Compliance | 2.01 | PE | Has the material used in this layer been formally accepted for use? | Insert Material Testing link | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | PM
|  | Stabilisation Delete if Not Required | TBC | Field | Cement application Mat test | TNZ B/5:2008 | TNZ B/5:2008 | 1 test per 400m² (minimum 1 per run) | ±0.50kg/m² of specified rate |  | Stabilisation QA sheet | QA / SE / PE
|  | Stabilisation Delete if Not Required | TBC | Field | Stabilisation Depth | TNZ B/5:2008 | TNZ B/5:2008 | 2 test per 400m² (minimum 1 per run) | Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer |  | Stabilisation QA sheet | QA / SE / PE
|  |  | 2.02 | Field | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing Target to be approved by Engineer | N/A |  | Hold Point Test Record | PM
|  |  | 2.03 | Field | Clegg Hammer | RITS Table 3-21 | RITS 3.8.3.3 ASTM D5874-16 | 1m inside of edge of seal and along centerline, both lanes, at 10m spacing | CIV ≥ 35 |  | Test Record | QA / SE
|  |  | 2.04 | Field | Compaction NDM Back Scatter | RITS Table 3-22 | RITS 3.8.3.4 4407:2015 test 4.3 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | Mean ≥ 95 % MDD Minimum ≥ 92% MDD |  | Test Record | QA / SE
|  |  | 3.07 | Lab | Benkelmen Beam Deflection Testing | RITS Table 3-23 | RITS 3.8.3.5 ASTM D5874-16 | Along wheelpaths - 1m inside of edge line and 1m from centerline, staggered across lanes, @ 10m spacing (no greater than 20m between tests) Minimum of 10 tests per lane, and/or at a frequency of 1 test per 10m chainage, whichever qty is greater. | 90th% < 1.5mm no value over 1.75mm |  | Test Record | QA / SE
|  |  | 2.05 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | +5mm/-25m from design or nominated level No more than 15mm deviation from a 3m straight edge |  | Survey record | QA / SE
|  | Compliance | 2.06 | PE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to placement of material | PQE Approval All testing record & reviewed as comliant. Available Documents: Test records Survey records Hold Point Records |  | Hold Point | PM
3 | Basecourse | Compliance | 3.01 | PE | Has the material used in this layer been formally accepted for use? | See PQE | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | PM
|  | Stabilisation Delete if Not Required | TBC | Field | Cement application Mat test | TNZ B/5:2008 | TNZ B/5:2008 | 1 test per 400m² (minimum 1 per run) | ±0.50kg/m² of specified rate |  | Stabilisation QA sheet | QA / SE / PE
|  | Stabilisation Delete if Not Required | TBC | Field | Stabilisation Depth | TNZ B/5:2008 | TNZ B/5:2008 | 2 test per 400m² (minimum 1 per run) | Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer |  | Stabilisation QA sheet | QA / SE / PE
|  |  | 3.04 | Field | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | 1 test per site | N/A |  | Test Record | QA / SE
|  |  | 3.05 | Field | Clegg Hammer | RITS Table 3-21 | RITS 3.8.3.3 ASTM D5874-16 | 1m inside of edge of seal and along centerline, both lanes, at 10m spacing | CIV ≥ 40 |  | Test Record | QA / SE
|  |  | 3.06 | Lab | Compaction NDM Back Scatter | RITS Table 3-22 | RITS 3.8.3.4 4407:2015 test 4.3 | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | Mean ≥ 98 % MDD Minimum ≥ 95% MDD |  | Test Record | QA / SE
|  |  | 3.07 | Lab | Benkelmen Beam Deflection Testing | RITS Table 3-23 | RITS 3.8.3.5 ASTM D5874-16 | 1m inside of edge of seal and along centerline, both lanes, at 10m spacing | Max deflection allowed: 1.7mm From design report - due to non-RITs compliant Subgrade CBR |  | Test Record | QA / SE
|  |  | 3.08 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal | +10mm/-0mm from design or nominated level No more than 12mm deviation from a 3m straight edge |  | Survey record | QA / SE
|  |  | 3.09 | Field | Visual Inspection of Basecourse Surface | TNZ B/02: 2005 7.8 | TNZ B/02: 2005 7.8 | 100% of Surface Prior to sealing of surface | Engineers Approval (The larger aggregate is held in place by with a matrix of smaller aggregates, the smaller aggregate is held firmly in place by fine material, and the matrix does not displace under normal trafficking or sweeping No evidence of rutting in surface) |  | Hold Point | PM
|  | Compliance | 3.1 | PE | Is the layer closed out ? | See PQE | See PQE | 100% of Surface Prior to sealing of surface | Engineers Approval All testing record & reviewed as compliant. Available Documents: Test records Survey records Hold Point Records |  | Hold Point | PM
4 | Membrane or First Coat Seal | Compliance | 4.01 | PE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | PM
|  | Compliance | 4.02 | PE | Bitumen Sprayer | TNZ P3 | Certification provided | Prior to starting | Current E/2 Certificate |  | Certificate Sheet | QA / SE
|  | Compliance | 4.03 | PE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | PM
|  |  | 4.04 | Field | Preseal Inspection | TNZ B/02: 2005 | TNZ B/02: 2005 | 100% of Surface Prior to sealing of surface | All loose aggregate, dirt, dust, silt and deleterious matter has been removed. |  | Test Record | QA / SE
|  |  | 4.05 | Field | Degree of Saturaton | TNZ B/02: 2005 | TNZ B/02: 2005 | 1 set of 5 per 1000m² - then 1 per 200m² | < 80 % Completed Max 48hrs before sealing |  | Test Record | QA / SE
|  |  | 4.06 | Field | GO/NO GO Survey | Downers processes | Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app | Prior to sealing on each site | Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager |  | Survey record | QA / SE
|  |  | 4.07 | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C |  | Spray sheet | QA / SE
|  |  | 4.08 | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray Sheet | QA / SE
|  |  | 4.09 | Field | Chip spread rate | TNZ P3: 1995.21 | area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Total amount of chip used to be calculated at end of days sealing | Visual checks meets seal design requirements |  | Witness Point/Spray sheet | QA / SE
|  |  | 4.1 | Field | Rolling Checks | TNZ P3: 1995.22 | Sealing Record | for each sealing site per day | As per rolling requirements defined in TNZ P3: 1995.22. |  | Witness Point/Spray sheet | QA / SE
|  |  | 4.11 | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose |  | Witness Point | PM / SE
5 | Post Construction | Compliance | 5.01 | PE | Asbuilt and RAMM Data | RAMM Update sheet | Asset Management Information Plan | After works complete | RAMM sheet 100% complete and accurate . |  | RAMM Asset Update sheet | Project Engineer
|  | Compliance | 5.02 | Lab | Site Safity Audit | [5 empty] | Test Record | PM

## Full ITP (hidden)
REHAB INSPECTION TESTING PLAN
Item No | Material Type | Typical Use | Item ID | CEA Lab, Supplier or Field | Material Properties Required for Acceptability for Permanent Works | [7 empty] | NOTES
[5 empty] | Material Test Method Requirement | Reference Documents | Material Acceptance Criteria (Method) | Material Test Frequency* | Target Criteria | link | Action Point Records required | Responsibility
1 | sub grade layer | Onsite Testing | 1.01 | Field | checking for CBR | RITS Table 3.20 | NZS 4402.6.5.2:1988 | at every 10m alternating or staggered intervals depending on the width of carriageway | 3 minimum blows/100mm or CBR 7 |  | Survey record | site engineer / Project Engineer/PQE
|  |  | 1.02 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 Section 5 Fig 1 | 5 points every 10 m | Tolerence -30 to 0 mm |  | Survey record | site engineer / Project Engineer/PQE
|  |  | 1.03 | Field | Tenser Triaxial Geogrid and Geofabric (cloth) installation | Tensar construction sequence CS_TriAx/30.04.08 | Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints. Geogrid and Geofabric shall be neatly installed without creases or folds. | For full length pavement. |  |  |  | site engineer / Project Engineer/PQE
2 | sub base testing | Compliance | 2.01 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing link | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | site engineer / Project Engineer/PQE
|  | Onsite Testing | 2.02 | Lab | Plateau Density Test | TNZ B/02: 2005 | TNZ B/02: 2005 | 1 test per 5,000m² | N/A |  | Test record | site engineer / Project Engineer/PQE
|  |  | 2.03 | Field | Surface Level, Shape, and crossfall | RITS Table 3.24 | TNZ B/02:2005 | 2 points (per shoulder and median) at a 20m frequency | tolerence -25 to +5 mm |  | Survey record | site engineer / Project Engineer/PQE
3 | Basecourse Placement | Compliance | 3.01 | PQE | Has the material used in this layer been formally accepted for use? | See PQE | See PQE | Prior to construction commencing | Material meets project requirements |  | Test record | site engineer / Project Engineer/PQE
4 | stabilized basecourse | Onsite Testing | 4.01 | Field | Visual Inspection of previous layer | See PQE | See PQE | 100% of Surface Prior to placement of material | Engineers Approval (The larger aggregate is held in place by with a matrix of smaller aggregates, the smaller aggregate is held firmly in place by cemented fine material, and the matrix does not displace under normal trafficking or sweeping No evidence of rutting in surface of Hi Lab) |  | Hold Point | site engineer / Project Engineer/PQE
|  |  | 4.02 | Field | Stinging for basecourse layer | RITS : Table 3.24 | See PQE | at every 10m alternating or staggered intervals depending on the width of carriageway | Tolerence -5mm to +15mm |  |  | site engineer / Project Engineer/PQE
|  |  | 4.03 | Field | Plateau Test | To achieve the OWC and MDD of the basecourse | TRANSIT TNZ B/5: 2008 7.7 | once for specified material | N/A |  |  | site engineer / Project Engineer/PQE
|  |  | 4.04 | Field | Clegg Hammer | RITS Table 3.21 | RITS 3.8.3.3 | At 10 m Alternating or staggered intervals depending on the width of carriageway | For clegg 40 CIV minimum |  |  | site engineer / Project Engineer/PQE
|  |  | 4.05 | Field | NDM | RITS Table 3.22 | 4407:2015 test 4.3 | At 10 m Alternating or staggered intervals depending on the width of carriageway | NDM minimum 92% MDD and 95% MDD average |  |  | site engineer / Project Engineer/PQE
|  |  | 4.06 | Field | BEAMS | RITS Table 3.23 | TNZ T/1 June 1977 | At 10 m Alternating or staggered intervals depending on the width of carriageway | depending on traffic |  |  | site engineer / Project Engineer/PQE
5 | Stabilisation | Onsite Testing | 5.01 | Field | Cement application Mat test | TNZ B/5:2008 | TNZ B/5:2008 | 1 test per 400m² (minimum 2 per run) | ±0.50kg/m² of specified rate |  | Stabilisation QA sheet | site engineer / Project Engineer/PQE
|  |  | 5.02 | Field | Stabilisation Depth | TNZ B/5:2008 | TNZ B/5:2008 | 1 test hole every 50m staggered between left-and right-hand edges of the run | Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer |  | Stabilisation QA sheet | site engineer / Project Engineer/PQE
|  |  | 5.03 | Field | Surface Level, Shape, and Crossfall | RITS table 3-24 | TNZ B/5:2008 | 5 points per 2 lanes (+1 point per add. Lane) at a 20m frequency | +15mm/-5mm no point in the surface varies more than 12 mm from a 3.0m straight edge placed on the road |  | Survey record | site engineer / Project Engineer/PQE
6 | pre seal inspection | Compliance | 6.01 | PQE | Has the Basecourse been given Approval to Proceed | Insert Approval to Proceed Documents Number | Approval to Proceed process | 1 document per lot | Available Documents: Test records Survey records Site Obs records Witness Points |  | Hold Point | site engineer / Project Engineer/PQE
|  |  | 6.02 | PQE | stone mosaic | TNZ B/2 | NZTA Chapter -07 Preseal preaparation Cl 7.2.1 | Throughout the surface | Clean stone mosaic surface that will not ravel as a result of sweeping |  |  | site engineer / Project Engineer/PQE
|  |  | 6.03 | PQE | straight edge | RITS Table 3-24 | within 12mm deviation from 3m staight edge | Throughout the surface |  |  |  | site engineer / Project Engineer/PQE
|  |  | 6.04 |  | client approval |  | Complaince with item ID 6.01, 6.02, 6.03 |  |  |  |  | site engineer / Project Engineer/PQE
7 | wearing surface First Coat Application | For Compliance | 7.01 | PQE | Seal Design | INSERT SEAL DESIGN | TNZ M/1 Table 1 Tests | Prior to sealing commencing (Minimum 1 week prior to application) | Meets project requirements |  | Hold Point | site engineer / Project Engineer/PQE
|  |  | 7.02 | PQE | Has the material used in this layer been formally accepted for use? | Insert Material Testing | See PQE | Prior to construction commencing | Material meets project requirements |  | Hold Point | site engineer / Project Engineer/PQE
|  |  | 7.03 |  | GO/NO GO Survey | Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app |  | Prior to sealing on each site | Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager |  |  | site engineer / Project Engineer/PQE
|  | On Site Testing | 7.04 | Field | Road temp | TNZ P3:1995.18 | Temperature recorded on site prior to sealing commencing | Once per day of sealing prior to sealing commencing | Air temp >10°C |  | Spray Sheet | site engineer / Project Engineer/PQE
|  |  | 7.05 | Field | Application Rate | TNZ P/3 : 1995.18 | Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer | Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling | binder application rate is +/-50ltrs + 4% of the application rate |  | Spray Sheet | site engineer / Project Engineer/PQE
|  |  | 7.06 | Field | Chip spread rate | TNZ P3: 1995.21 | area sealed (m2) to be divided by the volume of chip spread (m3) Chipsealing in New Zealand (pg 435) | Total amount of chip used to be calculated at end of days sealing | Visual checks meets seal design requirements |  | Witness Point/Spray sheet | site engineer / Project Engineer/PQE
|  |  | 7.07 | Field | Rolling Checks | TNZ P3: 1995.22 | Sealing Record | for each sealing site per day | As per rolling requirements defined in TNZ P3: 1995.22. |  | Witness Point/Spray sheet | site engineer / Project Engineer/PQE
|  |  | 7.08 | Field | Post Seal Inspection | TNZ P3: 1995 | Engineers Inspection | After sealing | The chip is embedded, uniformily placed and chipseal is fit for purpose |  | Witness Point | site engineer / Project Engineer/PQE
|  |  | 7.09 |  | High speed Rutting & NAASRA - Road Roughness | CCA DOC | Laser Profilometer Survey | After first coat sealing and prior to final surfacing with either EMOGPA, OGPA, SMA, or second coat sealing; After 12 months of trafficking; End of defects liability All lanes at 20m intervals in each wheel path and staggered by 10m between wheel paths | High Speed Rutting: > 5mm Report to Designer NAASRA reading:Shall not exceed 70 counts/km as a 95th percentile value |  | Test Record | site engineer / Project Engineer/PQE
8

## Sheet1
Yes
No
Frequency
|  | CBR and Deflection testing | Compaction testing | Surface Level, Shape, and crossfall
| Carriageway 4.0m wide and less | Along centerline, at 15m spacing (no greater than 30m between tests) Minimum of 10 tests and/or at a frequency of 1 test per 15m chainage, whichever qty is greater | Scattered across carriageway width, at 30m spacing (no greater than 60m between tests, no closer than 15m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | 3 Points across full width of carriageway at 10m frequency Edge of Seal, Centerline, Edge of Seal
| Carriageways between 4.0m and 8.0m | 1m inside of edge of seal, on alternating lanes, at 10m spacing (no greater than 20m between tests) Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | 5 Points across full width of carriageway at 10m frequency Edge of Seal, Centre of Lane, Centerline, Centre of Lane, Edge of Seal
| Carriageways greater than 8.0m in width | 1m inside of edge of seal and along centerline, staggered across lanes, at 10m spacing (no greater than 20m between tests) Minimum of 10 tests and/or at a frequency of 1 test per 10m chainage, whichever qty is greater | Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m) Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater | 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
|  | Chipseal | Asphalt
| Residential cul-de-sacs and private ways <40 units | Average: 1.50mm 90th %ile: 1.80mm Max: 2.40mm | Average: 1.30mm 90th %ile: 1.60mm Max: 2.10mm
| Carriageways less than a million ESAs | Average: 1.25mm 90th %ile: 1.50mm Max: 1.80mm | Average: 1.10mm 90th %ile: 1.35mm Max: 1.80mm
| Carriageways greater than a million ESAs | Average: 1.00mm 90th %ile: 1.20mm Max: 1.60mm | Average: 1.00mm 90th %ile: 1.20mm Max: 1.60mm
| Cohesive Soils |  |  | Granular
CBR | Penetration per blow (mm) | Min blows/100mm | Min blows/300mm | CIV
1 | 109.5 | n/a | 3 | n/a
2 | 65 | n/a | 5 | n/a
3 | 47.2 | n/a | 7 | n/a
4 | 36 | n/a | 9 | n/a
5 | 30.5 | n/a | 10 | n/a
6 | 27.5 | n/a | 11 | n/a
7 | 24.6 | n/a | 13 | n/a
8 | 22 | n/a | 14 | n/a
9 | 20 | n/a | 15 | n/a
10 | 18.7 | 6 | n/a | n/a
11 | 17 | 6 | n/a | n/a
12 | 17.5 | 6 | n/a | n/a
13 | 16.7 | 6 | n/a | n/a
14 | 15.5 | 7 | n/a | n/a
15 | 13.7 | 8 | n/a | 15
20 | 11 | 10 | n/a | 28
30 | 8.5 | 12 | n/a | 63
40 | 7 | 15 | n/a | 112
50 | 5.5 | 19 | n/a | 175