## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Hukanui Rd - Granular Rehab ITP | itp |  |  |  |  | Hukanui Rd - Granular Rehab ITP
section | Subgrade
checkpoint | 1.01 - Field
label | Material Test Method Requirement - Scala Penetrometer, Sand and Cohesive soils only
label | Reference Documents - RITS Table 3-20
label | Material Acceptance Criteria (Method) - NZS 4402.6.5.2:1988
label | Material Test Frequency - 1m inside of edge of seal and along centerline, both lanes, at 10m spacing
label | Target Criteria - 3 blows per 100mm, to a depth of 500mm
label | Action Point Records required - Test Record
label | Responsibility - QA / SE
checkpoint | 1.02 - Field
label | Material Test Method Requirement - Clegg Hammer, Aggregate fill/Subgrade or where subgrade undercut or trench backfilled
label | Reference Documents - RITS Table 3-21
label | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
label | Material Test Frequency - 1m inside of edge of seal and along centerline, both lanes, at 10m spacing and/or Minimum of 1 test per undercut location
label | Target Criteria - CIV ≥ 15 or CBR of 20
label | Action Point Records required - Test Record
label | Responsibility - QA / SE
checkpoint | 1.03 - Field
label | Material Test Method Requirement - Light Weight Deflectometer
label | Reference Documents - Design Review Correspondence
label | Material Acceptance Criteria (Method) -
label | Material Test Frequency - 1m inside of edge of seal and along centerline, both lanes, at 10m spacing
label | Target Criteria - Information only to confirm consistancy of in Situ SIL/Subgrade layer.
label | ○ Target threshold of 30Mpa
label | Action Point Records required - Test Record
label | Responsibility - QA / SE / DE
checkpoint | 1.04 - Field
label | Material Test Method Requirement - Surface Level, Shape, and crossfall
label | Reference Documents - RITS Table 3.24
label | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
label | Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency
label | ○ Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
label | Target Criteria - +0mm/-30m from design or nominated level
label | ○ No more than 15mm deviation from a 3m straight edge
label | Action Point Records required - Survey record
label | Responsibility - QA / SE
checkpoint | 1.05 - Field
label | Material Test Method Requirement - Geogrid Installation
label | Reference Documents - DuraGrid X & GridTex INSTALLATION GUIDELINES: BASE REINFORCEMENT APPLICATIONS AND STABILISATION
label | Material Acceptance Criteria (Method) - Manufracture installation instructions
label | Material Test Frequency - 100% of Surface
label | Target Criteria - Maintain minimum 300mm overlap between each roll on longitudinal and transverse joints.
label | ○ Geogrid and Geofabric shall be neatly installed without creases or folds.
label | Action Point Records required - Site Record
label | Responsibility - QA / SE
checkpoint | 1.06 - PE
label | Material Test Method Requirement - Is the layer closed out ?
label | Reference Documents - See PQE
label | Material Acceptance Criteria (Method) - See PQE
label | Material Test Frequency - 100% of Surface, Prior to placement of material
label | Target Criteria - PE Approval
label | ○ All testing record & reviewed as compliant.
label | Available Documents:
label | ○ Test records
label | ○ Survey records
label | ○ Hold Point Records
label | Action Point Records required - Hold Point
label | Responsibility - PM
holdpoint | AUTHORITY HOLDPOINT
section | Subbase
checkpoint | 2.01 - PE
label | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
label | Reference Documents - Insert Material Testing link
label | Material Acceptance Criteria (Method) - See PQE
label | Material Test Frequency - Prior to construction commencing
label | Target Criteria - Material meets project requirements
label | Action Point Records required - Hold Point
label | Responsibility - PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | TBC - Field (1)
label | Material Test Method Requirement - Cement application Mat test
label | Reference Documents - TNZ B/5:2008
label | Material Acceptance Criteria (Method) - TNZ B/5:2008
label | Material Test Frequency - 1 test per 400m² (minimum 1 per run)
label | Target Criteria - ±0.50kg/m² of specified rate
label | Action Point Records required - Stabilisation QA sheet
label | Responsibility - QA / SE / PE
checkpoint | TBC - Field (2)
label | Material Test Method Requirement - Stabilisation Depth
label | Reference Documents - TNZ B/5:2008
label | Material Acceptance Criteria (Method) - TNZ B/5:2008
label | Material Test Frequency - 2 test per 400m² (minimum 1 per run)
label | Target Criteria - Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer
label | Action Point Records required - Stabilisation QA sheet
label | Responsibility - QA / SE / PE
checkpoint | 2.02 - Field
label | Material Test Method Requirement - Plateau Density Test
label | Reference Documents - TNZ B/02: 2005
label | Material Acceptance Criteria (Method) - TNZ B/02: 2005
label | Material Test Frequency - Minimum of 1 test per to determine obtainable MDD target for Compliance NDM testing
label | ○ Target to be approved by Engineer
label | Target Criteria - N/A
label | Action Point Records required - Hold Point, Test Record
label | Responsibility - PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.03 - Field
label | Material Test Method Requirement - Clegg Hammer
label | Reference Documents - RITS Table 3-21
label | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
label | Material Test Frequency - 1m inside of edge of seal and along centerline, both lanes, at 10m spacing
label | Target Criteria - CIV ≥ 35
label | Action Point Records required - Test Record
label | Responsibility - QA / SE
checkpoint | 2.04 - Field
label | Material Test Method Requirement - Compaction NDM, Back Scatter
label | Reference Documents - RITS Table 3-22
label | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
label | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
label | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
label | Target Criteria - Mean ≥ 95 % MDD, Minimum ≥ 92% MDD
label | Action Point Records required - Test Record
label | Responsibility - QA / SE
checkpoint | 3.07 - Lab
label | Material Test Method Requirement - Benkelmen Beam Deflection Testing
label | Reference Documents - RITS Table 3-23
label | Material Acceptance Criteria (Method) - RITS 3.8.3.5, ASTM D5874-16
label | Material Test Frequency - Along wheelpaths - 1m inside of edge line and 1m from centerline, staggered across lanes, @ 10m spacing (no greater than 20m between tests)
label | ○ Minimum of 10 tests per lane, and/or at a frequency of 1 test per 10m chainage, whichever qty is greater.
label | Target Criteria - 90th% < 1.5mm, no value over 1.75mm
label | Action Point Records required - Test Record
label | Responsibility - QA / SE
checkpoint | 2.05 - Field
label | Material Test Method Requirement - Surface Level, Shape, and crossfall
label | Reference Documents - RITS Table 3.24
label | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
label | Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency
label | ○ Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
label | Target Criteria - +5mm/-25m from design or nominated level
label | ○ No more than 15mm deviation from a 3m straight edge
label | Action Point Records required - Survey record
label | Responsibility - QA / SE
checkpoint | 2.06 - PE
label | Material Test Method Requirement - Is the layer closed out ?
label | Reference Documents - See PQE
label | Material Acceptance Criteria (Method) - See PQE
label | Material Test Frequency - 100% of Surface, Prior to placement of material
label | Target Criteria - PQE Approval
label | ○ All testing record & reviewed as compliant.
label | Available Documents:
label | ○ Test records
label | ○ Survey records
label | ○ Hold Point Records
label | Action Point Records required - Hold Point
label | Responsibility - PM
holdpoint | AUTHORITY HOLDPOINT
section | Basecourse
checkpoint | 3.01 - PE
label | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
label | Reference Documents - See PQE
label | Material Acceptance Criteria (Method) - See PQE
label | Material Test Frequency - Prior to construction commencing
label | Target Criteria - Material meets project requirements
label | Action Point Records required - Hold Point
label | Responsibility - PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | TBC - Field (1)
label | Material Test Method Requirement - Cement application Mat test
label | Reference Documents - TNZ B/5:2008
label | Material Acceptance Criteria (Method) - TNZ B/5:2008
label | Material Test Frequency - 1 test per 400m² (minimum 1 per run)
label | Target Criteria - ±0.50kg/m² of specified rate
label | Action Point Records required - Stabilisation QA sheet
label | Responsibility - QA / SE / PE
checkpoint | TBC - Field (2)
label | Material Test Method Requirement - Stabilisation Depth
label | Reference Documents - TNZ B/5:2008
label | Material Acceptance Criteria (Method) - TNZ B/5:2008
label | Material Test Frequency - 2 test per 400m² (minimum 1 per run)
label | Target Criteria - Visual check to confirm that cement has been mixed to the correct depth, and as near as possible to full depth without mixing into the previous layer
label | Action Point Records required - Stabilisation QA sheet
label | Responsibility - QA / SE / PE
checkpoint | 3.04 - Field
label | Material Test Method Requirement - Plateau Density Test
label | Reference Documents - TNZ B/02: 2005
label | Material Acceptance Criteria (Method) - TNZ B/02: 2005
label | Material Test Frequency - 1 test per site
label | Target Criteria - N/A
label | Action Point Records required - Test Record
label | Responsibility - QA / SE
checkpoint | 3.05 - Field
label | Material Test Method Requirement - Clegg Hammer
label | Reference Documents - RITS Table 3-21
label | Material Acceptance Criteria (Method) - RITS 3.8.3.3, ASTM D5874-16
label | Material Test Frequency - 1m inside of edge of seal and along centerline, both lanes, at 10m spacing
label | Target Criteria - CIV ≥ 40
label | Action Point Records required - Test Record
label | Responsibility - QA / SE
checkpoint | 3.06 - Lab
label | Material Test Method Requirement - Compaction NDM, Back Scatter
label | Reference Documents - RITS Table 3-22
label | Material Acceptance Criteria (Method) - RITS 3.8.3.4, 4407:2015 test 4.3
label | Material Test Frequency - Scattered across carriageway width, at 20m spacing (no greater than 40m between tests, no closer than 10m)
label | ○ Minimum of 5 tests and/or at a frequency of 1 test per 200m², whichever qty is greater
label | Target Criteria - Mean ≥ 98 % MDD, Minimum ≥ 95% MDD
label | Action Point Records required - Test Record
label | Responsibility - QA / SE
checkpoint | 3.07 - Lab
label | Material Test Method Requirement - Benkelmen Beam Deflection Testing
label | Reference Documents - RITS Table 3-23
label | Material Acceptance Criteria (Method) - RITS 3.8.3.5, ASTM D5874-16
label | Material Test Frequency - 1m inside of edge of seal and along centerline, both lanes, at 10m spacing
label | Target Criteria - Max deflection allowed: 1.7mm
label | ○ From design report - due to non-RITs compliant Subgrade CBR
label | Action Point Records required - Test Record
label | Responsibility - QA / SE
checkpoint | 3.08 - Field
label | Material Test Method Requirement - Surface Level, Shape, and crossfall
label | Reference Documents - RITS Table 3.24
label | Material Acceptance Criteria (Method) - TNZ B/02:2005 Section 5 Fig 1
label | Material Test Frequency - 5 Points (+1 point for each additional lane) across full width of carriageway at 10m frequency
label | ○ Edge of Seals, Centre of each Lane, Centreline, Centre of each Lane, Edge of Seal
label | Target Criteria - +10mm/-0mm from design or nominated level
label | ○ No more than 12mm deviation from a 3m straight edge
label | Action Point Records required - Survey record
label | Responsibility - QA / SE
checkpoint | 3.09 - Field
label | Material Test Method Requirement - Visual Inspection of Basecourse Surface
label | Reference Documents - TNZ B/02: 2005 7.8
label | Material Acceptance Criteria (Method) - TNZ B/02: 2005 7.8
label | Material Test Frequency - 100% of Surface, Prior to sealing of surface
label | Target Criteria - Engineers Approval (The larger aggregate is held in place by with a matrix of smaller aggregates, the smaller aggregate is held firmly in place by fine material, and the matrix does not displace under normal trafficking or sweeping No evidence of rutting in surface)
label | Action Point Records required - Hold Point
label | Responsibility - PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3.10 - PE
label | Material Test Method Requirement - Is the layer closed out ?
label | Reference Documents - See PQE
label | Material Acceptance Criteria (Method) - See PQE
label | Material Test Frequency - 100% of Surface, Prior to sealing of surface
label | Target Criteria - Engineers Approval
label | ○ All testing record & reviewed as compliant.
label | Available Documents:
label | ○ Test records
label | ○ Survey records
label | ○ Hold Point Records
label | Action Point Records required - Hold Point
label | Responsibility - PM
holdpoint | AUTHORITY HOLDPOINT
section | Membrane or First Coat Seal
checkpoint | 4.01 - PE
label | Material Test Method Requirement - Seal Design
label | Reference Documents - INSERT SEAL DESIGN
label | Material Acceptance Criteria (Method) - TNZ M/1 Table 1 Tests
label | Material Test Frequency - Prior to sealing commencing (Minimum 1 week prior to application)
label | Target Criteria - Meets project requirements
label | Action Point Records required - Hold Point
label | Responsibility - PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.02 - PE
label | Material Test Method Requirement - Bitumen Sprayer
label | Reference Documents - TNZ P3
label | Material Acceptance Criteria (Method) - Certification provided
label | Material Test Frequency - Prior to starting
label | Target Criteria - Current E/2 Certificate
label | Action Point Records required - Certificate Sheet
label | Responsibility - QA / SE
checkpoint | 4.03 - PE
label | Material Test Method Requirement - Has the material used in this layer been formally accepted for use?
label | Reference Documents - Insert Material Testing
label | Material Acceptance Criteria (Method) - See PQE
label | Material Test Frequency - Prior to construction commencing
label | Target Criteria - Material meets project requirements
label | Action Point Records required - Hold Point
label | Responsibility - PM
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4.04 - Field
label | Material Test Method Requirement - Preseal Inspection
label | Reference Documents - TNZ B/02: 2005
label | Material Acceptance Criteria (Method) - TNZ B/02: 2005
label | Material Test Frequency - 100% of Surface, Prior to sealing of surface
label | Target Criteria - All loose aggregate, dirt, dust, silt and deleterious matter has been removed.
label | Action Point Records required - Test Record
label | Responsibility - QA / SE
checkpoint | 4.05 - Field
label | Material Test Method Requirement - Degree of Saturaton
label | Reference Documents - TNZ B/02: 2005
label | Material Acceptance Criteria (Method) - TNZ B/02: 2005
label | Material Test Frequency - 1 set of 5 per 1000m² - then 1 per 200m²
label | Target Criteria - < 80 % Completed Max 48hrs before sealing
label | Action Point Records required - Test Record
label | Responsibility - QA / SE
checkpoint | 4.06 - Field
label | Material Test Method Requirement - GO/NO GO Survey
label | Reference Documents - Downers processes
label | Material Acceptance Criteria (Method) - Downer survey sealing GO/NO GO,Road science Zeus app & Downer Iris app
label | Material Test Frequency - Prior to sealing on each site
label | Target Criteria - Pass on GO/NO GO ,Marginal & discussion with contract Manager or Written approval from Rehab manager
label | Action Point Records required - Survey record
label | Responsibility - QA / SE
checkpoint | 4.07 - Field
label | Material Test Method Requirement - Road temp
label | Reference Documents - TNZ P3:1995.18
label | Material Acceptance Criteria (Method) - Temperature recorded on site prior to sealing commencing
label | Material Test Frequency - Once per day of sealing prior to sealing commencing
label | Target Criteria - Air temp >10°C
label | Action Point Records required - Spray sheet
label | Responsibility - QA / SE
checkpoint | 4.08 - Field
label | Material Test Method Requirement - Application Rate
label | Reference Documents - TNZ P/3 : 1995.18
label | Material Acceptance Criteria (Method) - Quantity of binder sprayed in any spray run measured by dipstick reading or a calibrated accumulating rev counter fiited to sprayer
label | Material Test Frequency - Dipstick measurements before spraying is commenced from tank and after the last spray from the tank or prior to it's refilling
label | Target Criteria - binder application rate is +/-50ltrs + 4% of the application rate
label | Action Point Records required - Spray Sheet
label | Responsibility - QA / SE
checkpoint | 4.09 - Field
label | Material Test Method Requirement - Chip spread rate
label | Reference Documents - TNZ P3: 1995.21
label | Material Acceptance Criteria (Method) - area sealed (m2) to be divided by the volume of chip spread (m3)
label | ○ Chipsealing in New Zealand (pg 435)
label | Material Test Frequency - Total amount of chip used to be calculated at end of days sealing
label | Target Criteria - Visual checks meets seal design requirements
label | Action Point Records required - Witness Point/Spray sheet
label | Responsibility - QA / SE
checkpoint | 4.10 - Field
label | Material Test Method Requirement - Rolling Checks
label | Reference Documents - TNZ P3: 1995.22
label | Material Acceptance Criteria (Method) - Sealing Record
label | Material Test Frequency - for each sealing site per day
label | Target Criteria - As per rolling requirements defined in TNZ P3: 1995.22.
label | Action Point Records required - Witness Point/Spray sheet
label | Responsibility - QA / SE
checkpoint | 4.11 - Field
label | Material Test Method Requirement - Post Seal Inspection
label | Reference Documents - TNZ P3: 1995
label | Material Acceptance Criteria (Method) - Engineers Inspection
label | Material Test Frequency - After sealing
label | Target Criteria - The chip is embedded, uniformily placed and chipseal is fit for purpose
label | Action Point Records required - Witness Point
label | Responsibility - PM / SE
section | Post Construction
checkpoint | 5.01 - PE
label | Material Test Method Requirement - Asbuilt and RAMM Data
label | Reference Documents - RAMM Update sheet
label | Material Acceptance Criteria (Method) - Asset Management Information Plan
label | Material Test Frequency - After works complete
label | Target Criteria - RAMM sheet 100% complete and accurate .
label | Action Point Records required - RAMM Asset Update sheet
label | Responsibility - Project Engineer
checkpoint | 5.02 - Lab
label | Material Test Method Requirement - Site Safity Audit
label | Reference Documents -
label | Material Acceptance Criteria (Method) -
label | Material Test Frequency -
label | Target Criteria -
label | Action Point Records required - Test Record
label | Responsibility - PM