## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | Precast Components ITP
section | Job Approval Documents/Construction Documents
checkpoint | Received Construction drawing from Client
checkpoint | Shop drawings Prepared, reviewed and updated. Issued "As For Construction"
label | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
section | Pre-Pour Check Approvals
checkpoint-no-status | Formwork
checkpoint-no-status | Reinforcement (Reo)
checkpoint-no-status | Embedded Items and their placement
checkpoint-no-status | Lift Procedure
checkpoint-no-status | Concreting (mix design)
section | Test on Concrete (requests and approvals)
checkpoint-no-status | Request From Client
checkpoint-no-status | Test schedule and Test Results
section | Transport 01
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 02
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 03
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Transport 04
checkpoint | Any Lifting, Loading, Transport Instructions from Client
checkpoint | Transport Vehicle Approvals
checkpoint | Ensure loads are glutted correctly and chains are over gluts.
section | Other Documentations
checkpoint-no-status | Special Instructions
checkpoint-no-status | Other
section | Final Inspection
checkpoint | All approvals, certificates, data warranties, guarantees, manuals, as-built drawings collected.
checklist | Checkers Checklist | [5 empty] | Checkers Checklist (Panel A)
section | Checkers Checklist
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Ferrules -M20x96 - Position, Size, Orientation - NS / FS - 18Nos
checkpoint | Embedded Item - Ferrules -M24x96 - Position, Size, Orientation - NS / FS - 12Nos
checkpoint | Embedded Item - FF, NF Lifters Correct - Position, Size, Orientation - Pinhead Lifter Galvanised 5Ton x 170mm
dropdown | Embedded Item: | 10,other
checkpoint | Embedded Item - Fillet / Chamfer installation
checkpoint | Concrete cover check (As per the drawing)
checkpoint | Panel Thickness check, alignment check
checkpoint | Panel (Max) length check, alignment check
textbox | Length:
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
checkpoint-no-status | Overall Measurements (-250mm, +750mm) height
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Formwork Check - Double check the measurement with Diagonal check
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Reinforcement Check - Reo placement -adjacent to ferrules
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist | [5 empty] | Installers Checklist (Panel A)
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing
checkpoint | Complete Material "Bucket List"
checkpoint | Eye Anchor - Pinhead Lifter Galvanised 5Ton x 180mm (LA05180)
checkpoint | Embedded Item - Ferrules -M20x96 - Position, Size, Orientation - NS / FS - 18Nos
checkpoint | Embedded Item - Ferrules -M24x96 - Position, Size, Orientation - NS / FS - 12Nos
checkpoint | Embedded Item - FF, NF Lifters Correct - Position, Size, Orientation - Pinhead Lifter Galvanised 5Ton x 170mm
dropdown | Embedded Item | 10,other
checkpoint-no-status | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Required Mould, Supports, Ties (-250mm, +750mm) height
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Reinforcement Check - Reo placement -adjacent to ferrules
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check
checkpoint | Concrete cover check (As per the drawing)
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
checkpoint | QA - Concrete N40 20mm Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Off Form)
checkpoint | Curing Procedure arranged
checklist | Checkers Checklist | [5 empty] | Checkers Checklist (Panel B)
section | Checkers Checklist
checkpoint | Site Safety / Workers Safety
checkpoint | Availability of updated shop drawing
checkpoint | Overall Measurements of construction Element
checkpoint | Embedded Item - Ferrules -M20x96 - Position, Size, Orientation - NS / FS - 18Nos
checkpoint | Embedded Item - Ferrules -M24x96 - Position, Size, Orientation - NS / FS - 12Nos
checkpoint | Embedded Item - FF, NF Lifters Correct - Position, Size, Orientation - Pinhead Lifter Galvanised 5Ton x 170mm
dropdown | Embedded Item: | 10,other
checkpoint | Embedded Item - Fillet / Chamfer installation
checkpoint | Concrete cover check (As per the drawing)
checkpoint | Panel Thickness check, alignment check
checkpoint | Panel (Max) length check, alignment check
textbox | Length:
checkpoint | Formwork Check - Magnets are 100% Secure, All supports, Ties, Bracing
checkpoint | Formwork Check - Flatness, Levelness, Panel is clean
checkpoint | Formwork Check - Double check the measurement with Diagonal check
checkpoint-no-status | Overall Measurements (-500,+750mm ) height
checkpoint | Reinforcement (Reo) placed, cleaned, tightened
checkpoint | Reinforcement Check - Reo placement -adjacent to ferrules
checkpoint | Curing Procedure arranged
checkpoint | Photo Taken
checklist | Installers Checklist | [5 empty] | Installers Checklist (Panel B)
section | Job Approval Documents/Construction Documents
checkpoint | Availability of updated shop drawing
checkpoint | Complete Material "Bucket List"
checkpoint | Eye Anchor - Pinhead Lifter Galvanised 5Ton x 180mm (LA05180)
checkpoint | Embedded Item - Ferrules -M20x96 - Position, Size, Orientation - NS / FS - 06 Nos
checkpoint | Embedded Item - Ferrules -M20x70 - Position, Size, Orientation - NS / FS - 01Nos
checkpoint | Embedded Item - FF, NF Lifters Correct - Position, Size, Orientation - Pinhead Lifter Galvanised 5Ton x 170mm
dropdown | Embedded Item: | 10,other
checkpoint-no-status | ID Plate
textbox | ID:
section | Pre-Pour Check Approvals
checkpoint | Formwork Check -Panel Dimensions & DOUBLE CHECK
checkpoint | Apply Debonding agents -bond breaker or wax (1/2/3/ Coats)
checkpoint | Temporary Fix ID Plate to Formwork
checkpoint | Use Required Mould, Supports, Ties (-500,+750mm ) height
checkpoint | Reinforcement Check - Reo as-per Shop Drawing
checkpoint | Reinforcement Check - Reo placement -adjacent to ferrules
checkpoint | Lifters, Ferrules, Tubes Fixed Firm & aligned -Check
checkpoint | Concrete cover check (As per the drawing)
section | Quality Assurance
checkpoint | QA - Final Check of ALL measurements & Diagonals
checkpoint | QA - Concrete N40 20mm Panel Mix - Special Adjustments
checkpoint | QA - Concrete mix design ,variations%, adjustments%, mix time
checkpoint | QA - All main & other requirement to do Concreting -DOUBLE CHECK
date | Pour Date
checkpoint | CONCRETE TEST Procedure
checkpoint | APPROVAL FROM ENGINEER
section | Other Arrangements
checkpoint | Concrete surface Finish Requirement arranged (Off Form)
checkpoint | Curing Procedure arranged