## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Roundabout | itp |  |  |  |  | Generic - ITP - Roundabout
section | Materials
checkpoint | 1 - Kerb
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 1 - Survey Setout
label | VERIFICATION ACTIVITY: Survey
label | METHODS OR REFERENCE: Roundabout shape and heights to be set-out by the surveyor
label | FREQUENCY: Prior to commencement.
label | ACCEPTANCE CRITERIA: Survey
label | HOLD POINT: In process Inspection
label | RECORDS: Survey Receipt.
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 2 - Roundabout Apron
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: Construction Drawings
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Chamfer shape to be handformed in-situ concrete pour with with two layers of 65 mesh with minimum 50mm cover.
label | ○ 200mm thickness with broom finish NO OXIDE
label | ○ CIV > 25
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 3A - Precast Kerb & Nib
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: Kerb to be laid using precast hand-laid on compacted basecourse. Gaps between kerbs shall be no larger that 10mm
label | ○ CIV > 25
label | HOLD POINT: In process Inspection
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Concrete Infill
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards - IS0001 & IS0002
label | FREQUENCY: Each Site
label | ACCEPTANCE CRITERIA: 180mm depth of 20MPa Concrete
label | ○ 6kg/m3 red oxide broom finish
label | ○ On minimum 150mm of GAP65
label | ○ CIV >25
label | HOLD POINT: In process Inspection
label | RECORDS: FH Concrete QA sheet. Concrete Delivery Dockets
label | ONSITE RESPONSIBILITY: Site Engineer
section | As-builts
checkpoint | 5 - As built information
label | VERIFICATION ACTIVITY: Drawings
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
checkpoint | 6 - RAMM DATA
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE: As-builts to be in accordance with Chapter 24, clause 24.3 of ATCOP.
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: RAMM SHEET
label | HOLD POINT: In Process Inspection
label | RECORDS: As-built records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | Prepared by:
textbox | Approving Delegate:
checklist | ITP - Concrete Raised Crossing | itp |  |  |  |  | Generic - ITP - Concrete Raised Crossing
section | Concrete Raised Crossing
checkpoint | 1 - Permits
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Obtain Permits
label | FREQUENCY: As required
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Control Checklist - Fall Prevention (if applicable). Notify Worksafe NZ if required. Ensure all necessary Permit to Works & Controlled Checklists are in place
label | RECORDS: Permit attached or permit number noted
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Sub-Contract and Supplier Agreements are signed
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Signed Subcontractor and Supplier Agreements
label | RECORDS: Subcontract and Supplier Agreements
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.1 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure TMP is approved and check that the requirements are correctly interpreted and understood by the STMS
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: TMP is approved by CAR manager for each site and works are only completed within the approved dates..
label | RECORDS: TMP on MyWorksites/On Site
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2.2 - Pre-construction sign offs
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all Sub-Contractors and Suppliers go through FH induction
label | FREQUENCY: On site daily
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Induction
label | CONFORMANCE CRITERIA: Supplier's and Subcontractor's signatures on hazard ID and pre-start documentation
label | RECORDS: Hazard ID and Pre-starts to safety team
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Design
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Design is approved and Drawings are of the latest revision. Drawings to be 'ISSUED FOR CONSTRUCTION' status. HOLD POINT of not issued to IFC.
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: IFC drawings have been received by Contractor
label | RECORDS: Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 - Installation of Erosion and Sediment Controls
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure that Erosion & Sediment Control in place
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Territorial Authority has approved the asbuilts for the ESC controls constructed onsite and gives approval for construction to commence
label | RECORDS: Environmental Controls Audit
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Survey Setout
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Set out design features as per For Construction drawings (Cast in items, Ducting, Penetrations)
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Survey + Smart Level
label | CONFORMANCE CRITERIA: Consistency with Construction Drawing
label | RECORDS: Site Photos post surveying
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Locate Existing Services by Hand Digging
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Ensure all services conflicting with the line of trench has been exposed by hand digging
label | FREQUENCY: Prior to commencement
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Potholing
label | CONFORMANCE CRITERIA: All conflicts have been located. New services and/or conflicts to be advised to Project Engineer. Asbuilt all services
label | RECORDS: Digging and excavation checklist, service planes,As-Built Drawings Doc. Review
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: LESA dowels to be used at all construction joints at 600mm clearance
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.1 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 0.25mm polythene layer placed across all surface area at bottom of raised table
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection, Document Review
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Delivery Dockets / Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.2 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 30mm thick compacted layer of AP20 aggregate placed underneath polyethene layer.
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: CIV >15
label | RECORDS: Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.3 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Two layers of 663 mesh 50mm cover from top and bottom to be placed inside with 70mm plastic chairs seperating.
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | RECORDS: Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7.4 - Material Compliance
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: All concrete delivered to site shall have 40MPa 28 day compressive strength.
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Concrete Delivery Dockets
label | CONFORMANCE CRITERIA: Delivery Docket added to QA folder
label | RECORDS: Concrete Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Formwork to be set to correct line and level
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 8.1 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised table formwork to be 75mm above existing road level and be 300mm in depth and gradients respectively of entry (1:15) and exit ramps (1:20)
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.2 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to have 225mm depth at entry point and tie into 300mm depth to meet raised table
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.3 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to be 1.125m across for entry and 1.5m for departure ramp.Toe to be 500mm across for both entry and departure with 50mm asphaltic wearing course
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect formation level
label | RECORDS: Site photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.4 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Raised Table ramps to be 1:15 gradient for ramps at entry and exit ramps to be 1:20 relative to the road
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Designer to inspect gradient level
label | RECORDS: Site photos / Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8.5 - Temporary Works (Formwork)
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: The Site Engineer and MSQA Engineer must sign off the formwork prior to concrete being poured
label | FREQUENCY: Prior to concrete pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Reinforcing
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: All construction joints are to contain 2 rows of LESA dowels or similar approved dowels .Dowell system 50mm w/ Black 300*50*6mm plates @400 centres placed across the construction joint
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Site photos/Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Concreting
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: The MSQA Engineer shall be advised at least 24 working hours before the proposed time for concreting that a pre-pour inspection is required
label | FREQUENCY: Prior to concrete pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Engineer will be notified via email/SMS at least 24 hours before required for inspection
label | RECORDS: Email / SMS
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10.1 - Concreting
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Vibrator to be used throughout concrete pour
label | FREQUENCY: When pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual Inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 10.2 - Concreting
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Concrete surfaces shall be U5 broomed finish for ramps, and Broom finish for table top.
label | FREQUENCY: At completion of pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Curing
label | ACTION (Hold, Monitor, Witness): M
label | DETAIL: Concrete will be left for 48 hours minimum to cure before traffic is allowed on it.
label | FREQUENCY: Post Pour
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Monitoring the time allowed for curing
label | CONFORMANCE CRITERIA: 48 hours minimum have passed
label | RECORDS: Concrete Formwork Checklist
checkpoint | 12 - Remove formwork
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Remove formwork after 48 hours
label | FREQUENCY: Post Curing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Concrete Inspection Record
label | RECORDS: Concrete Formwork Checklist
checkpoint | 13 - Asphalt- Concrete extension slab/ Toe
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Two rows of Lesa diamond placed mid depth @600 C/C along construction joint as per TDM TC003
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
label | RECORDS: Site photos,delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.1 - Asphalt- Concrete extension slab/ Toe
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: 200mm thick 40MPa Concrete with two layers of 663 mesh
label | FREQUENCY: Prior to pouring concrete
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Pre pour Inspection Checklist, Concrete Inspection records
label | RECORDS: Site photos,delivery dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13.2 - Asphalt- Concrete extension slab/ Toe
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Tack Coat between AC and Concrete slab
label | FREQUENCY: Post Curing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Visual inspection
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Site photos
checkpoint | 13.3 - Asphalt- Concrete extension slab/ Toe
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: 50mm thick DG10 / Mix 7
label | FREQUENCY: Post Curing
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Measurement
label | CONFORMANCE CRITERIA: Photos + Delivery Docket added to QA folder
label | RECORDS: Site photos,delivery dockets
checkpoint | 14 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Ensure all QA Records,site photos and incident cases (OFIs) are closed and included within QA file
label | FREQUENCY: At completion of Lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: All QA files compiled and sumbitted to client
label | RECORDS: QA records
checkpoint | 14.1 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness): W
label | DETAIL: Delivery Dockets to be included in QA file
label | FREQUENCY: At completion of Lot
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Document Review
label | CONFORMANCE CRITERIA: Delivery Dockets to be included in QA file
label | RECORDS: QA records
checkpoint | 15 - As-builts
label | ACTION (Hold, Monitor, Witness): H
label | DETAIL: Red pen mark up drawings to be included in QA file
label | FREQUENCY: At the completion of the Lot of work
label | INSPECTION / TEST METHOD (Submission, Visual Inspection, Testing, Measurement, Review): Drawings
label | RECORDS: Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | QA checked By Quality Manager:
textbox | Accepted By Engineers Rep:
checklist | ITP - ACO Drain | itp |  |  |  |  | Generic - ITP - ACO Drain
section | Site Set Out
checkpoint | 1 - Site Set out
label | VERIFICATION ACTIVITY: Surveyor
label | METHODS OR REFERENCE: Surveyor
label | FREQUENCY: Everysite
label | ACCEPTANCE CRITERIA: Site Set out as per construction plan provided with GPS location and 3D model provided by designers. Site set out inspected with designers/MSQA and client ensure criteria is acceptable.
label | ○ Alternatively like for like
label | HOLD POINT: Mandatory HOLD POINT -
label | RECORDS: Survey Receipt
label | ONSITE RESPONSIBILITY: Site Engineer
holdpoint | AUTHORITY HOLDPOINT
section | Materials
checkpoint | 2 - Aco Drain K300
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: All the block and the grate should be inspected before installation.
label | HOLD POINT: Inprocess Inspection
label | RECORDS: Dockets
label | ONSITE RESPONSIBILITY: Site Engineer
section | Construction
checkpoint | 3 - Prep and Level Check
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each block
label | ACCEPTANCE CRITERIA: Subgrade -(CBR > 3)
label | ○ Base course - 100mm min. thickness GAP40
label | ○ Clegg CIV > 12
label | ○ water flow check
label | HOLD POINT: Inprocess Inspection - Engnieer to check
label | RECORDS: Depth check photos, fall check photos
label | ONSITE RESPONSIBILITY: Site Engineer
checkpoint | 4 - Lay Kerb Drain
label | VERIFICATION ACTIVITY: QA FORM
label | METHODS OR REFERENCE: TDM Technical Standards
label | FREQUENCY: Each Block
label | ACCEPTANCE CRITERIA: Boxing to be done along the aco drain
label | ○ Surfacing - Concrete 150mm and 25 MPa @ 28 days.
label | ○ Side Haunching for 150mm thickness
label | ○ Vibrator to be used to avoid voids
label | ○ Finished level of concrete to match with the grate
label | HOLD POINT: Inprocess Inspection - Engnieer to check
label | RECORDS: FH concrete QA sheet. Concrete delivery Dockets kept as record, Photos
label | ONSITE RESPONSIBILITY: Site Engineer
section | Asbuilts
checkpoint | 5 - As built information
label | VERIFICATION ACTIVITY: RAMM DATA SHEET
label | METHODS OR REFERENCE:
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: As built drawings and Ramm Sheets Completed
label | HOLD POINT: In Process Inspection
label | RECORDS: Asbuilt records
label | ONSITE RESPONSIBILITY: Supervisor and Engineer
section | ITP APPROVAL
checkpoint | ITP Approval
textbox | Prepared by:
textbox | Approving Delegate: