## Table 1
Pavement - Structural Asphalt on Concrete
Project Name: |  | Weymouth RAB: Roscommon Road and Weymouth East | [6 empty] | Design Report . |  | Weymouth Construction
ITP Prepared By: |  | AA - FH |  | Date: |  | 2024-12-17 |  |  | Peer Review By: |  | SS - FH – initial version only |  |  |  | Date: 18/12/2024
No. | ACTIVITY DESCRIPTION | VERIFICATION ACTIVITY | METHODS OR REFERENCE | FREQUENCY |  | ACCEPTANCE CRITERIA |  |  | TYPE |  | RECORDS (Responsibility) |  | ONSITE RESPONSIBILITY |  | SIGNOFF
Milling/Excavation
1 | Identification and location of services | Service plans and GPR Markouts | Trained contractor staff | Full Pavement Extent |  | Services sufficiently deep to avoid damage. |  |  | Mandatory HOLD POINT Engineer Signoff Required |  | Photos and Report |  | Project Engineer |  | MSQA Signoff
2 | Milling / Cut to Waste (350mm at Weymouth and 400mm at Roscommon) | Stringline | Dip from stringline or survey as- built | 5m each lane |  | +0 / -20mm to design level |  |  | Mandatory HOLD POINT Engineer Signoff Required |  | Stringline Sheet |  | Project Engineer |  | MSQA Signoff
3 | Subgrade | No unacceptable subgrade materials after excavation | Visual Inspection | NA |  | Free of detritius and loose material. Subgrade Treatment may Required |  |  | Inprocess Inspection |  | Site diary |  | Project Engineer
Subgrade Treatment
4 | Subgrade Testing and Treatment | Testing, Scala Penetrometer Testing, Shear Vane testing, and Proof rolling | Design Report | At 10m intervals staggered in each wheel path |  | For, Subgrade CBR > 3%, Scala < 50mm per blow, shear vane >= 60kPa and no visual movement under static roller. - No Undercut required |  |  | Mandatory HOLD POINT Designer Signoff Required |  | Testing results, QA and video of proof rolling. |  | Project Engineer |  | MSQA Signoff
5 | Subgrade Testing and Treatment | Testing, Scala Penetrometer Testing, Shear Vane testing, and Proof rolling | Design Report | At 10m intervals staggered in each wheel path |  | For, Subgrade CBR 2 - 3%, Scala 50 - 100mm per blow, shear vane 40 - 60kPa and visual movement under static roller. - No Undercut required at Weymouth East and Geotextile to remain at bottom of concrete subbase. - 150mm undercut required at Roscommon Road and geotextile placed before backfilling with granular |  |  | Mandatory HOLD POINT Designer Signoff Required |  | Testing results, QA and video of proof rolling. |  | Project Engineer |  | MSQA Signoff
6 | Subgrade Testing and Treatment | Testing, Scala Penetrometer Testing, Shear Vane testing, and Proof rolling | Design Report | At 10m intervals staggered in each wheel path |  | For, Subgrade CBR 1 - 2%, Scala >= 100mm per blow, shear vane 20 - 40kPa and visual movement under static roller. - 200mm Undercut required at Weymouth East and geotextile placed before backfilling with granular. - - 250mm undercut required and geotextile placed before backfilling with granular |  |  | Mandatory HOLD POINT Designer Signoff Required |  | Testing results, QA and video of proof rolling. |  | Project Engineer |  | MSQA Signoff
AP40 Layer (Subgrade improvement layer)
7 | 150mm or 200mm or 250mm Excavation | Stringline | Dip from string line | 10m each lane |  | +0 / -20mm No trafficking of the excavated subgrade |  |  | Mandatory HOLD POINT Designer Signoff Required |  | Marked up drawing |  | Project Engineer |  | MSQA Signoff
8 | Class C Geotextile | N/A | NZTA F/7 | NA |  | Geotextile material and construction in accordance with NZTA F/7 Placed as per subgrade treatment |  |  | In process Inspection and Contractor Records |  | Testing Results |  | Project Engineer
9 | ATAP40 (material) | No non-compliant results | Material test results | Once |  | Compliance with AT Series 800 Specification for the Supply of Aggregates |  |  | Contractor Records |  | Testing Results |  | Project Engineer
10 | ATAP40 (Compaction) | Compaction | CIV | Every 10m in each lane |  | CIV>=35 |  |  | Contractor Records |  | Testing Results |  | Project Engineer
11 | ATAP40 (Level Tolerance) | Stringline | Dip from string line | 10m each lane |  | +5 / -25mm No trafficking of the excavated subgrade |  |  | Contractor Records |  | Testing Results |  | Project Engineer
12 | ATAP40 (Surface finish) | N/A | Visual Inspection | NA |  | Free of detritius and loose material |  |  | Inprocess Inspection |  | Site diary |  | Project Engineer
New Pavement Joint
13 | Transverse Tie In To existing pavement | Pavement Joint | Visual Inspection | Each Subsection |  |  |  |  | Mandatory HOLD POINT Designer Signoff Required |  | Photos and Report |  | Project Engineer |  | MSQA Signoff
14 | Longitudinal Tie In To existing pavement | Pavement Joint | Visual Inspection | Each Subsection |  |  |  |  | Mandatory HOLD POINT Designer Signoff Required |  | Photos and Report |  | Project Engineer |  | MSQA Signoff
Concrete Subbase
15 | Concrete Subbase | Strength and slump | Concrete dockets | each pour |  | Strength = 20MPa Slump = 130mm pump mix Pump mix being used hence cannot specify slump. Shape of the concrete to be closely monitored due to fluidity nature of pump mix on graded surface |  |  | Inprocess Testing |  | Docket |  | Project Engineer
16 | Concrete Subbase | Levels / thickness | Dip from stringline or survey as- built to top of subbase (Surveyor to provide set-out information prior to concrete pour) | 10m each lane |  | For Weymouth Road, Target Depth = 150mm below design surface -0 / +10mm For Roscommon Road, Target Depth = 200mm below design surface -0 / +10mm |  |  | Mandatory HOLD POINT Designer Signoff Required |  | Stringline Sheet |  | Project Engineer |  | MSQA Signoff
17 | Concrete Subbase | Rough trowel surface finish | Visual Inspection | NA |  | Rough surface verified over 100% of surface area |  |  | Inprocess Inspection |  | Production Recurs |  | Project Engineer
18 | Concrete Joint – if two different pours | Joints | Visual Inspection | Each Subsection |  |  |  |  | Mandatory HOLD POINT Designer Signoff Required |  | Photos and Report |  | Project Engineer |  | MSQA Signoff
19 | Crack Bandage if crack occurs | Cracks | Visual Inspection | Each Subsection |  |  |  |  | Mandatory HOLD POINT Designer Signoff Required |  | Photos and Report |  | Project Engineer |  | MSQA Signoff
Emulsion – Tack and Blind (Concrete and AC layer)
20 | Emulsion tack coat | CAT60 cationic emulsion or approved alternative | Visual Inspection |  | each lot |  | Hand spray tack coat emulsion | Inprocess Testing |  | Photos |  | Project Engineer
Structural Asphalt (AC20 – 160mm in two lifts 80mm each)
21 | AC20 | Check weather reports | Forecast and thermometer |  | Daily |  | No fog, rain or wet surface. Base temp ≥ 7o C | Inprocess Testing |  | AC check sheet |  | Project Engineer
22 | AC20 | Ensure previous layer is broomed clean | Visual |  | Prior to starting |  | Free of detritius and loose material | Inprocess Testing |  | AC check sheet |  | Project Engineer
23 | AC20 | Production tests | Grading, binder content, max density, temp |  | As per M/10 |  | NZTA M/10 | Inprocess Testing |  | Lab test |  | Project Engineer
24 | AC20 | Surface finish inspection | Visual inspection by the Engineer |  | Each lot |  | Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate. | Inprocess Testing |  | Inspection sheet |  | Project Engineer
25 | AC20 | Density testing | NDM |  | Every 30m2 |  | Air voids (4% - 6%) | Inprocess Testing |  | Inspection sheet |  | Project Engineer |  | MSQA Signoff
26 | AC20 | As-built layer | Stringline |  | Each lot |  | First layer = 60mm +/- 10mm | Inprocess Testing |  | As-build drawings & stringline measures |  | Project Engineer
27 | AC20 | As-built layer | Stringline |  | Each lot |  | Second layer = 60mm +/- 10mm | Inprocess Testing |  | As-build drawings & stringline measures |  | Project Engineer
28 | Joint Inspection | Visual | Design Report |  | Each Subsection |  |  | Mandatory HOLD POINT Auckland Transport Signoff Required |  |  |  | Project Engineer |  | MSQA Signoff
No Cores on AC20
29 | AC20 | Density testing | Cores (Random testing plan to be agreed with client) |  | 1/300m2 or min 4 no. |  | Air voids to meet NZTA M/10:2020 | Mandatory HOLD POINT Auckland Transport Signoff Required |  | RFI response |  | Project Engineer |  | MSQA Signoff
30 | AC20 | Thickness | Cores depth (Random testing standard) |  | 1/300m2 or min 4 no. |  | - Target depth 160mm | Mandatory HOLD POINT Auckland Transport Signoff Required |  | Core test report |  | Project Engineer |  | MSQA Signoff
Hatelit grid to be laid in between asphalt layers
31 | Hatelit C40/17 | Length direction grid overlap | Visual inspection |  | Ongoing during install |  | Min. 250mm | Inprocess Testing |  | Photo / diary note / check sheet |  | Project Engineer
32 | Hatelit C40/17 | Cross direction grid overlap | Visual inspection |  | Ongoing during install |  | Min. 150mm | Inprocess Testing |  | Photo / diary note / check sheet |  | Project Engineer
33 | Hatelit C40/17 | Tack coat | Visual inspection |  | Ongoing during install |  | 0.5 lt / m2, residual bitumen emulsion (depending on surface condition) | Inprocess Testing |  | Photo / diary note / check sheet |  | Project Engineer
34 | Hatelit C40/17 | Emulsion on overlaps | Visual inspection |  | Ongoing during install |  | 0.5 lt / m2 if required | Inprocess Testing |  | Photo / diary note / check sheet |  | Project Engineer
35 | Hatelit C40/17 | Evenly laid grid | Visual inspection |  | Ongoing during install |  | Minimal air voids in grid, grid pulled tight | Inprocess Testing |  | Photo / diary note / check sheet |  | Project Engineer
Asphalt Surfacing 40mm – AC10
36 | Rougness of Road | Insitu | Contract Spec 4415 |  | Every 100m |  | The new pavement shall have an average dynamic roughness, when measured over a length of 100m, of less than 60 NAASRA counts/km for any three consecutive results and no individual value greater than 70 | Inprocess Inspection |  | NAASRA count |  | Project Engineer
37 | Shape of road | 3m straight edge | NZTA M/10 spec |  | At joints and any other areas of concern |  | Irregularities < 5mm under straight edge | Inprocess Inspection |  | Check sheet |  | Project Engineer
38 | Temperature Limitations | Temperature | Contract Spec / M10 Spec |  | Every Site |  | Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 120 Degree | Inprocess Inspection |  | Asphalt QA |  | Project Engineer
39 | Surface Preparation | Visual | NZTA M/10 spec |  | Every Site |  | Swept clean; all necessary measures to prevent ponding prior to any surfacing | Inprocess Inspection |  | Visual |  | Project Engineer
40 | Asphalt Production Tests for AC10 | Production Tests | Grading, binder content, max density, temp |  | As per M/10 |  | NZTA M/10 | Laboratory Testing |  | IANZ Lab |  | Project Engineer
41 | Joint Placement | Paving Plan |  |  | Every Site |  | Paving Plan to be completed for every site with dimensions. Joint sealing shall be applied between new and existing surfacing. Joints off-set 150mm | Inprocess Inspection |  | Nil |  | Project Engineer
42 | AC10 - Layer thickness – 40mm compacted depth | Insitu | Contract Spec / NZTA M10 Spec |  | Continuous |  | 40 mm minimum and 45 mm maximum compacted depth | Mandatory HOLD POINT Auckland Transport Signoff Required |  | Asphalt QA |  | Project Engineer |  | MSQA Signoff
43 | AC10 | Density testing | NDM |  | Every 30m2 |  | NZTA M/10 | Mandatory HOLD POINT Auckland Transport Signoff Required |  | RFI response |  | Project Engineer |  | MSQA Signoff
44 | Reinstatement of Linemarking and RRPM's | Visual | NZTA M7 approved (Class B or C as required for anticipated traffic level) |  | Every site |  | *Carried out within 12 hours of each shift completed and as per the existing markings * Suitable Traffic Control to remain in place until pavement markings have been reinstated | Inprocess Inspection |  | Linemarking Records |  | Project Engineer
APPROVALS
Approved by Project Engineer : |  | TBC |  |  | Signature: |  |  | Date:
Approved by Contract Manager : |  | TBC |  |  | Signature: |  |  | Date:
Approved by Client Rep : |  | TBC |  |  | Signature: |  |  | Date: