## res
type | name | values | prefix | postfix | usage count | user addable | template name | Resource Id
checklist | ITP - Pavement - Structural Asphalt on Concrete | itp |  |  |  |  | Weymouth Construction - Stage 7 - Pavement Construction - ITP - Pavement - Structural Asphalt on Concrete
section | Milling/Excavation
checkpoint | 1 - Identification and location of services
label | VERIFICATION ACTIVITY: Service plans and GPR Markouts
label | METHODS OR REFERENCE: Trained contractor staff
label | FREQUENCY: Full Pavement Extent
label | ACCEPTANCE CRITERIA: Services sufficiently deep to avoid damage.
label | TYPE: Mandatory HOLD POINT Engineer Signoff Required
label | RECORDS: Photos and Report
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Milling / Cut to Waste (350mm at Weymouth and 400mm at Roscommon)
label | VERIFICATION ACTIVITY: Stringline
label | METHODS OR REFERENCE: Dip from stringline or survey as- built
label | FREQUENCY: 5m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm to design level
label | TYPE: Mandatory HOLD POINT Engineer Signoff Required
label | RECORDS: Stringline Sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Subgrade
label | VERIFICATION ACTIVITY: No unacceptable subgrade materials after excavation
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Free of detritius and loose material. Subgrade Treatment may Required
label | TYPE: Inprocess Inspection
label | RECORDS: Site diary
label | ONSITE RESPONSIBILITY: Project Engineer
section | Subgrade Treatment
checkpoint | 4 - Subgrade Testing and Treatment
label | VERIFICATION ACTIVITY: Testing, Scala Penetrometer Testing, Shear Vane testing, and Proof rolling
label | METHODS OR REFERENCE: Design Report
label | FREQUENCY: At 10m intervals staggered in each wheel path
label | ACCEPTANCE CRITERIA: For,
label | ○ Subgrade CBR > 3%, Scala < 50mm per blow, shear vane >= 60kPa and no visual movement under static roller.
label | – No Undercut required
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS: Testing results, QA and video of proof rolling.
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Subgrade Testing and Treatment
label | VERIFICATION ACTIVITY: Testing, Scala Penetrometer Testing, Shear Vane testing, and Proof rolling
label | METHODS OR REFERENCE: Design Report
label | FREQUENCY: At 10m intervals staggered in each wheel path
label | ACCEPTANCE CRITERIA: For,
label | ○ Subgrade CBR 2 - 3%, Scala 50 - 100mm per blow, shear vane 40 - 60kPa and visual movement under static roller.
label | – No Undercut required at Weymouth East and Geotextile to remain at bottom of concrete subbase.
label | – 150mm undercut required at Roscommon Road and geotextile placed before backfilling with granular
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS: Testing results, QA and video of proof rolling.
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 6 - Subgrade Testing and Treatment
label | VERIFICATION ACTIVITY: Testing, Scala Penetrometer Testing, Shear Vane testing, and Proof rolling
label | METHODS OR REFERENCE: Design Report
label | FREQUENCY: At 10m intervals staggered in each wheel path
label | ACCEPTANCE CRITERIA: For,
label | ○ Subgrade CBR 1 - 2%, Scala >= 100mm per blow, shear vane 20 - 40kPa and visual movement under static roller.
label | – 200mm Undercut required at Weymouth East and geotextile placed before backfilling with granular.
label | – 250mm undercut required and geotextile placed before backfilling with granular
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS: Testing results, QA and video of proof rolling.
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
section | AP40 Layer (Subgrade improvement layer)
checkpoint | 7 - 150mm or 200mm or 250mm Excavation
label | VERIFICATION ACTIVITY: Stringline
label | METHODS OR REFERENCE: Dip from string line
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +0 / -20mm
label | ○ No trafficking of the excavated subgrade
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS: Marked up drawing
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 8 - Class C Geotextile
label | VERIFICATION ACTIVITY: N/A
label | METHODS OR REFERENCE: NZTA F/7
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Geotextile material and construction in accordance with NZTA F/7 Placed as per subgrade treatment
label | TYPE: In process Inspection and Contractor Records
label | RECORDS: Testing Results
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 9 - ATAP40 (material)
label | VERIFICATION ACTIVITY: No non-compliant results
label | METHODS OR REFERENCE: Material test results
label | FREQUENCY: Once
label | ACCEPTANCE CRITERIA: Compliance with AT Series 800 Specification for the Supply of Aggregates
label | TYPE: Contractor Records
label | RECORDS: Testing Results
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 10 - ATAP40 (Compaction)
label | VERIFICATION ACTIVITY: Compaction
label | METHODS OR REFERENCE: CIV
label | FREQUENCY: Every 10m in each lane
label | ACCEPTANCE CRITERIA: CIV>=35
label | TYPE: Contractor Records
label | RECORDS: Testing Results
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 11 - ATAP40 (Level Tolerance)
label | VERIFICATION ACTIVITY: Stringline
label | METHODS OR REFERENCE: Dip from string line
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: +5 / -25mm
label | ○ No trafficking of the excavated subgrade
label | TYPE: Contractor Records
label | RECORDS: Testing Results
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 12 - ATAP40 (Surface finish)
label | VERIFICATION ACTIVITY: N/A
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Inspection
label | RECORDS: Site diary
label | ONSITE RESPONSIBILITY: Project Engineer
section | New Pavement Joint
checkpoint | 13 - Transverse Tie In To existing pavement
label | VERIFICATION ACTIVITY: Pavement Joint
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: Each Subsection
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS: Photos and Report
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Longitudinal Tie In To existing pavement
label | VERIFICATION ACTIVITY: Pavement Joint
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: Each Subsection
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS: Photos and Report
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
section | Concrete Subbase
checkpoint | 15 - Concrete Subbase
label | VERIFICATION ACTIVITY: Strength and slump
label | METHODS OR REFERENCE: Concrete dockets
label | FREQUENCY: each pour
label | ACCEPTANCE CRITERIA: Strength = 20MPa Slump = 130mm pump mix
label | ○ Pump mix being used hence cannot specify slump. Shape of the concrete to be closely monitored due to fluidity nature of pump mix on graded surface
label | TYPE: Inprocess Testing
label | RECORDS: Docket
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 16 - Concrete Subbase
label | VERIFICATION ACTIVITY: Levels / thickness
label | METHODS OR REFERENCE: Dip from stringline or survey as- built to top of subbase (Surveyor to provide set-out information prior to concrete pour)
label | FREQUENCY: 10m each lane
label | ACCEPTANCE CRITERIA: For Weymouth Road,
label | ○ Target Depth = 150mm below design surface
label | ○ -0 / +10mm
label | For Roscommon Road,
label | ○ Target Depth = 200mm below design surface
label | ○ -0 / +10mm
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS: Stringline Sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 17 - Concrete Subbase
label | VERIFICATION ACTIVITY: Rough trowel surface finish
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: NA
label | ACCEPTANCE CRITERIA: Rough surface verified over 100% of surface area
label | TYPE: Inprocess Inspection
label | RECORDS: Production Recurs
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 18 - Concrete Joint – if two different pours
label | VERIFICATION ACTIVITY: Joints
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: Each Subsection
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS: Photos and Report
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 19 - Crack Bandage if crack occurs
label | VERIFICATION ACTIVITY: Cracks
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: Each Subsection
label | TYPE: Mandatory HOLD POINT Designer Signoff Required
label | RECORDS: Photos and Report
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
section | Emulsion – Tack and Blind (Concrete and AC layer)
checkpoint | 20 - Emulsion tack coat
label | VERIFICATION ACTIVITY: CAT60 cationic emulsion or approved alternative
label | METHODS OR REFERENCE: Visual Inspection
label | FREQUENCY: each lot
label | ACCEPTANCE CRITERIA: Hand spray tack coat emulsion
label | TYPE: Inprocess Testing
label | RECORDS: Photos
label | ONSITE RESPONSIBILITY: Project Engineer
section | Structural Asphalt (AC20 – 160mm in two lifts 80mm each)
checkpoint | 21 - AC20
label | VERIFICATION ACTIVITY: Check weather reports
label | METHODS OR REFERENCE: Forecast and thermometer
label | FREQUENCY: Daily
label | ACCEPTANCE CRITERIA: No fog, rain or wet surface. Base temp ≥ 7o C
label | TYPE: Inprocess Testing
label | RECORDS: AC check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 22 - AC20
label | VERIFICATION ACTIVITY: Ensure previous layer is broomed clean
label | METHODS OR REFERENCE: Visual
label | FREQUENCY: Prior to starting
label | ACCEPTANCE CRITERIA: Free of detritius and loose material
label | TYPE: Inprocess Testing
label | RECORDS: AC check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 23 - AC20
label | VERIFICATION ACTIVITY: Production tests
label | METHODS OR REFERENCE: Grading, binder content, max density, temp
label | FREQUENCY: As per M/10
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Inprocess Testing
label | RECORDS: Lab test
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 24 - AC20
label | VERIFICATION ACTIVITY: Surface finish inspection
label | METHODS OR REFERENCE: Visual inspection by the Engineer
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Uniform texture, no roller marks, no bleeding, cracking or shoving, no crushing of the aggregate.
label | TYPE: Inprocess Testing
label | RECORDS: Inspection sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 25 - AC20
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: NDM
label | FREQUENCY: Every 30m2
label | ACCEPTANCE CRITERIA: Air voids (4% - 6%)
label | TYPE: Inprocess Testing
label | RECORDS: Inspection sheet
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
checkpoint | 26 - AC20
label | VERIFICATION ACTIVITY: As-built layer
label | METHODS OR REFERENCE: Stringline
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: First layer = 60mm +/- 10mm
label | TYPE: Inprocess Testing
label | RECORDS: As-build drawings & stringline measures
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 27 - AC20
label | VERIFICATION ACTIVITY: As-built layer
label | METHODS OR REFERENCE: Stringline
label | FREQUENCY: Each lot
label | ACCEPTANCE CRITERIA: Second layer = 60mm +/- 10mm
label | TYPE: Inprocess Testing
label | RECORDS: As-build drawings & stringline measures
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 28 - Joint Inspection
label | VERIFICATION ACTIVITY: Joint Inspection
label | METHODS OR REFERENCE: Design Report
label | FREQUENCY: Each Subsection
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
section | No Cores on AC20
checkpoint | 29 - AC20
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: Cores (Random testing plan to be agreed with client)
label | FREQUENCY: 1/300m2 or min 4 no.
label | ACCEPTANCE CRITERIA: Air voids to meet NZTA M/10:2020
label | TYPE: Air voids to meet NZTA M/10:2020
label | RECORDS: RFI response
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
checkpoint | 30 - AC20
label | VERIFICATION ACTIVITY: Thickness
label | METHODS OR REFERENCE: Cores depth (Random testing standard)
label | FREQUENCY: 1/300m2 or min 4 no.
label | ACCEPTANCE CRITERIA: Target depth 160mm
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS: Core test report
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
section | Hatelit grid to be laid in between asphalt layers
checkpoint | 31 - Hatelit C40/17
label | VERIFICATION ACTIVITY: Length direction grid overlap
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Ongoing during install
label | ACCEPTANCE CRITERIA: Min. 250mm
label | TYPE: Inprocess Testing
label | RECORDS: Photo / diary note / check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 32 - Hatelit C40/17
label | VERIFICATION ACTIVITY: Cross direction grid overlap
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Ongoing during install
label | ACCEPTANCE CRITERIA: Min. 150mm
label | TYPE: Inprocess Testing
label | RECORDS: Photo / diary note / check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 33 - Hatelit C40/17
label | VERIFICATION ACTIVITY: Tack coat
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Ongoing during install
label | ACCEPTANCE CRITERIA: 0.5 lt / m2, residual bitumen emulsion (depending on surface condition)
label | TYPE: Inprocess Testing
label | RECORDS: Photo / diary note / check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 34 - Hatelit C40/17
label | VERIFICATION ACTIVITY: Emulsion on overlaps
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Visual inspection
label | ACCEPTANCE CRITERIA: 0.5 lt / m2 if required
label | TYPE: Inprocess Testing
label | RECORDS: Photo / diary note / check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 35 - Hatelit C40/17
label | VERIFICATION ACTIVITY: Evenly laid grid
label | METHODS OR REFERENCE: Visual inspection
label | FREQUENCY: Ongoing during install
label | ACCEPTANCE CRITERIA: Minimal air voids in grid, grid pulled tight
label | TYPE: Inprocess Testing
label | RECORDS: Photo / diary note / check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
section | Asphalt Surfacing 40mm – AC10
checkpoint | 36 - Rougness of Road
label | VERIFICATION ACTIVITY: Insitu
label | METHODS OR REFERENCE: Contract Spec 4415
label | FREQUENCY: Every 100m
label | ACCEPTANCE CRITERIA: The new pavement shall have an average dynamic roughness, when measured over a length of 100m, of less than 60 NAASRA counts/km for any three consecutive results and no individual value greater than 70
label | TYPE: Inprocess Inspection
label | RECORDS: NAASRA count
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 37 - Shape of road
label | VERIFICATION ACTIVITY: 3m straight edge
label | METHODS OR REFERENCE: NZTA M/10 spec
label | FREQUENCY: At joints and any other areas of concern
label | ACCEPTANCE CRITERIA: Irregularities < 5mm under straight edge
label | TYPE: Inprocess Inspection
label | RECORDS: Check sheet
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 38 - Temperature Limitations
label | VERIFICATION ACTIVITY: Temperature
label | METHODS OR REFERENCE: Contract Spec / M10 Spec
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Asphalt not to be paved when foggy or raining, or placed on a wet surface or when temperature is below the base temperature limitations of 120 Degree
label | TYPE: Inprocess Inspection
label | RECORDS: Asphalt QA
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 39 - Surface Preparation
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA M/10 spec
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Swept clean; all necessary measures to prevent ponding prior to any surfacing
label | TYPE: Inprocess Inspection
label | RECORDS: Visual
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 40 - Asphalt Production Tests for AC10
label | VERIFICATION ACTIVITY: Production Tests
label | METHODS OR REFERENCE: Grading, binder content, max density, temp
label | FREQUENCY: As per M/10
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Laboratory Testing
label | RECORDS: IANZ Lab
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 41 - Joint Placement
label | VERIFICATION ACTIVITY: Paving Plan
label | FREQUENCY: Every Site
label | ACCEPTANCE CRITERIA: Paving Plan to be completed for every site with dimensions. Joint sealing shall be applied between new and existing surfacing. Joints off-set 150mm
label | TYPE: Inprocess Inspection
label | RECORDS: Nil
label | ONSITE RESPONSIBILITY: Project Engineer
checkpoint | 42 - AC10 - Layer thickness – 40mm compacted depth
label | VERIFICATION ACTIVITY: Insitu
label | METHODS OR REFERENCE: Contract Spec / NZTA M10 Spec
label | FREQUENCY: Continuous
label | ACCEPTANCE CRITERIA: 40 mm minimum and 45 mm maximum compacted depth
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS: Asphalt QA
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 43 - AC10
label | VERIFICATION ACTIVITY: Density testing
label | METHODS OR REFERENCE: NDM
label | FREQUENCY: Every 30m2
label | ACCEPTANCE CRITERIA: NZTA M/10
label | TYPE: Mandatory HOLD POINT Auckland Transport Signoff Required
label | RECORDS: RFI response
label | ONSITE RESPONSIBILITY: Project Engineer
label | SIGNOFF: MSQA Signoff
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 44 - Reinstatement of Linemarking and RRPM's
label | VERIFICATION ACTIVITY: Visual
label | METHODS OR REFERENCE: NZTA M7 approved (Class B or C as required for anticipated traffic level)
label | FREQUENCY: Every site
label | ACCEPTANCE CRITERIA: Carried out within 12 hours of each shift completed and as per the existing markings
label | ○ Suitable Traffic Control to remain in place until pavement markings have been reinstated
label | TYPE: Inprocess Inspection
label | RECORDS: Linemarking Records
label | ONSITE RESPONSIBILITY: Project Engineer
section | APPROVALS
checkpoint | Approvals
textbox | Approved by Project Engineer:
textbox | Approved by Contract Manager:
textbox | Approved by Client Rep: