## Ground Improvements
|  |  |  | Inspection Test Plan |  | ****** | Approved |  | Signature |  | BLIC
| {Logo} |  |  | Contract Name: | C1001A Concrete Pile Underslip |  | Engineer
|  |  |  | Procedure: | Ground Improvements (Wick Drains) |  | Quality Manager
Inspection & Test Plan / Checklist
Lot No: C1001A Drainage |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-CS-7003 |  | Compliance with Work Instructions and Specifications
Detailed Location:
Chainage:
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Design | H | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review |  | Check Drawing Register | Site Engineer
2 | Survey Setout | H | Setout locations of wicks in accordance with design | Prior to commencement | Measurement |  | Survey receipt | Site Engineer
3 | Material Compliance | H | Prefabricated wick drains shall consist of a 100mm wide drainage core | Each roll | Visual Inspection / Certification | Vertical Wick Drains Specification | Manufacturer Certificate | Site Engineer
4 |  | H | Ensure all wick drains are free from defects, rips, hole and flaws | Each roll | Visual Inspection / Checksheet |  | Photos | Site Engineer
5 | Wick Drain Installation | W | Wick drains shall be installed vertically, within a tolerance of not more than 20mm per 1000m. | Daily | Visual inspection / measurement | Contractor to check for plumb as per Vertical Wick Drains Specification | Sub-Contractor Records | Site Engineer
6 |  |  | Depth achieved. Min of 500mm wick protruding from the ground | Each Wick | Visual inspection |  | Sub-Contractor Records | Site Engineer
7 |  | W | Splices or connections shall be done in a professional manner that ensures continuity of the drain without diminishing the flow characteristics of the wick material | Each joint | Visual inspection | Vertical Wick Drains Specification | Sub-Contractor Records | Site Engineer
8 |  | H | Design Engineer Inspection prior to backfilling |  | Visual inspection |  |  | Site Engineer | Design Engineer
9 | Survey Asbuilt | H | Extents of wick drain area to be As Built surveyed |  | Survey |  | Survey Receipt | Site Engineer
10 | Lot Number QA File | W | Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into CONQA/Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
11 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | Asbuilt Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: