## Keystone Retaining Wall
|  |  |  | TREC - INSPECTION TEST PLAN - MASS BLOCK (MAGNUM STONE) RETAINING WALL |  |  | Approved |  | Signature
| (insert Alliance logo here) |  |  | Contract Name: | B1101a - TE NGARUE BRIDGE SCOUR |  | Engineer
|  |  |  | Procedure: | Mass Block (Magnum Stone) Retaining Wall |  | Quality Manager
Inspection & Test Plan / Checklist
Lot No: n/a |  |  |  | Corresponding Work Instruction: |  | B1101 |  | Compliance with Work Instructions and Specifications
Detailed Location: Te Ngarue Stream Bridge
Chainage: SH2 626/0.00 Road True Left Hand Side
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Survey Setout | W | Set out base of wall to 1m offset. Setout and mark all known services along the line of the Retaining Wall. | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer
2 | Mass Block & Extenders Compliance | H | All blocks that are delivered are to be approved to use and are compliant with the Specifications | Prior to commencement | Document Review | Compliance with suppliers specifications | Delivery Dockets | Site Engineer
3 | Base and Backfill Material Compliance | H | Material to meet specifications dependant on material type selected | Each material used | Document Review | Compliance with specification (a clean well graded gravel) | Bulk Fill Earthworks Record (check sheet) | Site Engineer
4 |  | W | Fill Construction Material | 1 test per 1000m3 | Lab Testing - Wet Sieve NZS4407:2015 Test 3.8.1 | For AP65 65mm 100%, 19mm 45-65%, 75um 0-15%. For AP20 25mm 100%, 19mm 100-75%, 4.75 0-10%, 300um 0-5%. | Lab Test Report | Site Engineer
5 |  | W | Fill Construction Material | 1 test per 1000m3 | Lab Testing - Plasticity index NZS4407:2015 Test 3.3 | PI<20 | Lab Test Report
6 |  | W | Fill Construction Material | 1 test per 1000m3 | Lab Testing - NZ Std compaction NZS4402:1986 Test 4.1.1 | n/a (for NDM) | Lab Test Report
7 |  | W | Fill Construction Material | 1 set of tests (1 point per 5 linear m (min 2 per set)) - Foundation base, ~1/2 height, full height | Site Testing - NDM NZS4407:2015 Test 4.3 | 95% of MDD +-2%OMC | Lab Test Report
8 | Mass Block Fill Material Compliance | H | Material to meet specifications dependant on material type selected | Each material used | Document Review | Compliance with drawing requirements | Bulk Fill Earthworks Record (check sheet) | Site Engineer
9 |  | W | Drainage Aggregate - Garding, Crushing Resistance and Weathering Index | One per source prior to installation | Lab Testing - TNZ F/6:2003 | Grading - 20/40 Drainage Aggregate no more than 5% passing a 75µm sieve Crushing resistance - Not less than 100kN. Weathering index - AA,AB,AC,BA,BB,BC,CA | Lab Test Report | Site Engineer
10 | Excavate Base of Wall | H | Excavate footprint of the wall area to the correct line and level and ensure area safe to work in. | As required | Survey |  | Survey Receipt | Site Engineer
11 |  | H | Base of excavation to be checked by Geotech engineer / Design Engineer | As required | Visual |  | Subgrade Approval Checksheet | Site Engineer | Design Engineer
12 |  | H | Test the base of the excavation to ensure it meets Specification. | Staggered in respect of wall width, every 2 linear m | Site Testing - Scala NZS 4402 Test 6.5.2:1988 | 3 blows /100mm to 1m | Lab test result dockets | Site Engineer | Design Engineer
13 | Subsoil Drainage | H | If subsoil drainage is required for this wall construction then follow the TREC ITP for Subsoil Drainage | Prior to construction of wall | Document Review |  | TREC ITP Subsoil Drainage | Site Engineer | Design Engineer
14 | Construct Wall | H | If a concrete foundation is required for the wall then install as per specifications/drawings | Prior to construction of wall | Document Review | Concrete to meet the specifications , if concrete testing required then compression cylinders taken, collect all delivery dockets and include with this lot | Delivery Dockets | Site Engineer
15 |  | H | A Permit to Lift has been issued to the contractor carrying out the works and there is a Lift Plan available | Prior to construction of wall | Document Review |  | Permit to Lift | Site Engineer
16 |  | W | Install Mass Blocks as per Manufacturers specs along the front face of layers to ensure correct line and level. | As required | Visual |  | TREC MSE Wall Geogrid Checksheet and Photo's | Site Engineer | Design Engineer
17 |  | W | Install grid or extender layers as per drawings and have Design Engineer signs off each layer. | As required | Visual / Survey |  | Survey Receipt and TREC MSE Wall Geogrid Checksheet | Site Engineer | Design Engineer
18 |  | W | Place fill material on grid or extender layers as per drawings and compact to MSE Wall specifications and test. | as required | Lab Testing | 95% MDD or whatever is called for in the specification | TREC Bulk Fill Earthworks checksheet | Site Engineer
19 |  | W | Ensure line and level of front face is as per design | Each Lift | Visual |  |  | Site Engineer
20 | Survey As Built | H | Ensure all works comply with design prior to carrying on with next construction process | At completion of sub soil drainage line | Survey |  | Survey receipt | Site Engineer
21 | Confirm testing requirements met | H | Ensure correct no. of test sets performed for fill testing | At completion of Lot | Document Review | A) No. of days worked:_______ B) No. of 250mm lifts:_________ C) How many XXXm3 fill: ______ Require greater of A or B, and not less than C. | Test results and calculations of fill volume | Site Engineer | Design Engineer
22 | Lot Number QA File | W | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into CONQA/Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
23 | As-builts | H | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: