## Rock Armouring
|  |  |  | Inspection Test Plan |  |  | Approved |  | Signature
| (insert Alliance logo here) |  |  | Contract Name: | B1101A Te Ngarue Bridge Scour Repairs |  | Engineer
|  |  |  | Procedure: | Rock Armouring |  | Quality Manager
Inspection & Test Plan / Checklist
Project No: B1101 ID302 |  |  |  | Corresponding Work Instruction: |  | (insert contract suffix here)-CS-7057 |  | Compliance with Work Instructions and Specifications
Detailed Location: Te Ngarue Stream Bridge
Chainage: SH2 RP 626/0.00
No: | Inspection / Test Point | ACTION (Hold, Monitor, Witness) | Detail | Frequency | Inspection / Test Method submission, visual inspection, testing, measure, review | Conformance Criteria | Records | Initials | Design Engineer Initials (Grey if not required) | Date(s)
1 | Design | W | Ensure that Design is approved and Drawings are of the latest revision | Prior to commencement | Document Review | IFC Drawings to be provided for uploading to this ITP | Check Drawing Register | Site Engineer
2 | Survey Setout | W | Set out extents and check against design drawings | Prior to commencement | Survey | Consistency with Construction Drawing | Survey receipt | Site Engineer
3 | Topsoil Strip | M | Once all ESC controls have been installed & the Tree Felling & Vegetation Clearance has been carried out | Prior to commencement | Document Review | ITP for Tree Felling & Vegetation Clearance to be used | TREC - Tree Felling & Vegetation Clearance ITP | Site Engineer
4 | Foundations | H | Inspect fill foundation, rip rap foundation, as appropriate | Per area as required | Inspection by the Design Engineer | Foundation must be approved, in writing, before filling commences | TREC - Subgrade Approval Checksheet | Site Engineer | Design Engineer
5 |  | H | Inspect gabion wall foundation | Scala penetrometer readings along bottom row at 4m ctrs or min 2 Scala penetrometer readings per area whichever is greater | Inspection by Design Engineer | Scala penetrometer reading of ≥3 blows per 100mm. Foundation must be approved, in writing, before gabion construction commences | ? | Site Engineer | Design Engineer
6 | Gabion/Reno Baskets | W | All baskets are to be ordered in accordance with the specifications & drawings | Prior to commencement | Document Review | Any defective baskets are NOT to be used in the wall construction - return to the supplier immediately | Delivery Dockets | Site Engineer
5 | Material Compliance Testing | W | Material to meet specifications dependant on material type selected | Each material used | Document Review | D50 1000 rock rip rap: 100% pass 1500mm, 80% pass 1250mm, 50% pass 1000mm, 20% pass 750mm AP65: 100% pass 65mm, 5% pass 75μm | Photos to demonstrate process has been carried out | Site Engineer
6 |  | H | Rock Construction Material | Prior to commencement: At quarry - Confirmation of acceptability by Geotech Engineer from each source unless rock property changes are evident, in which case additional approval required | Visual, geological hammer testing or scraping of rock as required by Geotechnical Engineer | Confirmation of acceptability by Geotechnical Engineer - Hard, durable stone with the size conforming to that shown on the drawings - Rock shape to be as cubical as possible with limiting ratio of least dimension to greatest dimension 1:3 - Long, thin or slabby shapes are not acceptable | Inspection and sign off by Geotechnical Engineer | Site Engineer | Design Engineer
7 |  | M | Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bedim A49 and Tencate PES 1000/Tencate PES 2000 | Prior to commencement of placement | Visual Inspection | Conformance with Specification | Delivery Dockets/ Material Cert | Site Engineer
8 | Construction of Engineered Fill Embankment | W | Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap | Compaction testing from ~0.5m above typical WL. Sets of NDM (~5/test area) at <~1.5m vertical spacing with final test at FL. Clegg Impact Value tests at ~0.6m lifts (every 2nd layer) | Site testing to TNZ F/1, NDMs and Cleggs (CIV) for calibration. | Min 95% Standard Proctor density |  | Site Engineer
9 | Geotextile Placement | W | Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps. | Daily visual check | Visual inspection |  | Photographs | Site Engineer
10 | Riprap Placement | H | Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material | Daily visual check | Visual inspection | Specification | Photographs | Site Engineer | Design Engineer
11 | Gabion/Reno Baskets | W | Install the baskets as per Manufacturers specs to ensure correct line and level. | As required | Visual |  | Photo's | Site Engineer
12 |  | W | Place Gabion material into baskets ensuring the outside facing the flat side of the bigger stones are placed by hand to ensure that the baskets are kept square | Every basket | Visual |  | Photo's | Site Engineer
13 |  | W | Tie lids on basket as per Manufacturers spec with the correct tie materials or staples | Every basket | Visual |  | Photo's | Site Engineer
11 | Survey As Built | W | Ensure rock slopes comply with design prior to next process taking place | At completion of Lot | Measurement |  | Survey receipt | Site Engineer
12 | Lot Number QA File | M | Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File | At completion of Lot | Document Review | Ensure all QA is uploaded into CONQA/Procore | Delivery Dockets, Test Reports, Lab Testing Register | Site Engineer
13 | As-builts | M | Red pen mark up drawings to be included in QA file | At the completion of the Lot of work | Drawings |  | As-built Drawing | Site Engineer
Comments:
IFC Drawings used for Construction incl. Rev numbers:
Reference Documentation (Notices/NCRs etc.):
QA Compiled By : |  |  |  |  | Signature: |  |  | Date:
QA checked By Discipline Manager: |  |  |  |  | Signature: |  |  | Date:
QA checked By Quality Manager: |  |  |  |  | Signature: |  |  | Date:
Accepted By Design Engineer: |  |  |  |  | Signature: |  |  | Date: