## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | ITP - Ground Improvements (Wick Drains) C1001A - Concrete Pile Underslip | itp |  |  |  |  | ITP - Ground Improvements (Wick Drains) C1001A - Concrete Pile Underslip
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Check Drawing Register
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Setout locations of wicks in accordance with design
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Prefabricated wick drains shall consist of a 100mm wide drainage core
label | Frequency - Each roll
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection / Certification
label | Conformance Criteria - Vertical Wick Drains Specification
label | Records - Manufacturer Certificate
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure all wick drains are free from defects, rips, hole and flaws
label | Frequency - Each roll
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection / Checksheet
label | Records - Photos
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Wick Drain Installation
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Wick drains shall be installed vertically, within a tolerance of not more than 20mm per 1000m.
label | Frequency - Daily
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection / measurement
label | Conformance Criteria - Contractor to check for plumb as per Vertical Wick Drains Specification
label | Records - Sub-Contractor Records
checkpoint | 6 -
label | Detail - Depth achieved. Min of 500mm wick protruding from the ground
label | Frequency - Each Wick
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Sub-Contractor Records
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Splices or connections shall be done in a professional manner that ensures continuity of the drain without diminishing the flow characteristics of the wick material
label | Frequency - Each joint
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Vertical Wick Drains Specification
label | Records - Sub-Contractor Records
checkpoint | 8 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Design Engineer Inspection prior to backfilling
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 - Survey Asbuilt
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Extents of wick drain area to be As Built surveyed
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey Receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 10 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all OFIs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into CONQA/Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 11 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - Asbuilt Drawing
holdpoint | AUTHORITY HOLDPOINT