## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | TREC ITP - Mass Block (Magnum Stone) Retaining Wall - B1101a - TE NGARUE BRIDGE SCOUR | itp |  |  |  |  | TREC ITP - Mass Block (Magnum Stone) Retaining Wall - B1101a - TE NGARUE BRIDGE SCOUR
checkpoint | 1 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out base of wall to 1m offset. Setout and mark all known services along the line of the Retaining Wall.
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
checkpoint | 2 - Mass Block & Extenders Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - All blocks that are delivered are to be approved to use and are compliant with the Specifications
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Compliance with suppliers specifications
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 3 - Base and Backfill Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Compliance with specification (a clean well graded gravel)
label | Records - Bulk Fill Earthworks Record (check sheet)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 4 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill Construction Material
label | Frequency - 1 test per 1000m3
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - Wet Sieve NZS4407:2015 Test 3.8.1
label | Conformance Criteria - For AP65 65mm 100%, 19mm 45-65%, 75um 0-15%. For AP20 25mm 100%, 19mm 100-75%, 4.75 0-10%, 300um 0-5%.
label | Records - Lab Test Report
checkpoint | 5 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill Construction Material
label | Frequency - 1 test per 1000m3
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - Plasticity index NZS4407:2015 Test 3.3
label | Conformance Criteria - PI<20
label | Records - Lab Test Report
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill Construction Material
label | Frequency - 1 test per 1000m3
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - NZ Std compaction NZS4402:1986 Test 4.1.1
label | Conformance Criteria - n/a (for NDM)
label | Records - Lab Test Report
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Fill Construction Material
label | Frequency - 1 set of tests (1 point per 5 linear m (min 2 per set)) - Foundation base, ~1/2 height, full height
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Testing - NDM NZS4407:2015 Test 4.3
label | Conformance Criteria - 95% of MDD +-2%OMC
label | Records - Lab Test Report
checkpoint | 8 - Mass Block Fill Material Compliance
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Compliance with drawing requirements
label | Records - Bulk Fill Earthworks Record (check sheet)
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 9 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Drainage Aggregate - Garding, Crushing Resistance and Weathering Index
label | Frequency - One per source prior to installation
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing - TNZ F/6:2003
label | Conformance Criteria - Grading - 20/40 Drainage Aggregate no more than 5% passing a 75µm sieve
label | ○ Crushing resistance - Not less than 100kN.
label | ○ Weathering index - AA,AB,AC,BA,BB,BC,CA
label | Records - Lab Test Report
checkpoint | 10 - Excavate Base of Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Excavate footprint of the wall area to the correct line and level and ensure area safe to work in.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey Receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Base of excavation to be checked by Geotech engineer / Design Engineer
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - Subgrade Approval Checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 12 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Test the base of the excavation to ensure it meets Specification.
label | Frequency - Staggered in respect of wall width, every 2 linear m
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Site Testing - Scala NZS 4402 Test 6.5.2:1988
label | Conformance Criteria - 3 blows /100mm to 1m
label | Records - Lab test result dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 13 - Subsoil Drainage
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - If subsoil drainage is required for this wall construction then follow the TREC ITP for Subsoil Drainage
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - TREC ITP Subsoil Drainage
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 14 - Construct Wall
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - If a concrete foundation is required for the wall then install as per specifications/drawings
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Concrete to meet the specifications , if concrete testing required then compression cylinders taken, collect all delivery dockets and include with this lot
label | Records - Delivery Dockets
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 15 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - A Permit to Lift has been issued to the contractor carrying out the works and there is a Lift Plan available
label | Frequency - Prior to construction of wall
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Records - Permit to Lift
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 16 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install Mass Blocks as per Manufacturers specs along the front face of layers to ensure correct line and level.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
label | Records - TREC MSE Wall Geogrid Checksheet and Photo's
checkpoint | 17 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Install grid or extender layers as per drawings and have Design Engineer signs off each layer.
label | Frequency - As required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual / Survey
label | Records - Survey Receipt and TREC MSE Wall Geogrid Checksheet
checkpoint | 18 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Place fill material on grid or extender layers as per drawings and compact to MSE Wall specifications and test.
label | Frequency - as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Lab Testing
label | Conformance Criteria - 95% MDD or whatever is called for in the specification
label | Records - TREC Bulk Fill Earthworks checksheet
checkpoint | 19 -
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure line and level of front face is as per design
label | Frequency - Each Lift
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual
checkpoint | 20 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure all works comply with design prior to carrying on with next construction process
label | Frequency - At completion of sub soil drainage line
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Records - Survey receipt
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 21 - Confirm testing requirements met
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure correct no. of test sets performed for fill testing
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria -
textbox | A) No. of days worked:
textbox | B) No. of 250mm lifts:
textbox | C) How many XXXm3 fill:
label | Require greater of A or B, and not less than C.
label | Records - Test results and calculations of fill volume
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 22 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into CONQA/Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 23 - As-builts
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing
holdpoint | AUTHORITY HOLDPOINT