## res
type | name | values | prefix | postfix | usage count | user addable | template name
checklist-flat | TREC ITP - Rock Armouring - B1101A Te Ngarue Bridge Scour Repairs | itp |  |  |  |  | TREC ITP - Rock Armouring - B1101A Te Ngarue Bridge Scour Repairs
checkpoint | 1 - Design
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that Design is approved and Drawings are of the latest revision
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - IFC Drawings to be provided for uploading to this ITP
label | Records - Check Drawing Register
checkpoint | 2 - Survey Setout
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Set out extents and check against design drawings
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Survey
label | Conformance Criteria - Consistency with Construction Drawing
label | Records - Survey receipt
checkpoint | 3 - Topsoil Strip
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Once all ESC controls have been installed & the Tree Felling & Vegetation Clearance has been carried out
label | Frequency - Prior to commencement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - ITP for Tree Felling & Vegetation Clearance to be used
label | Records - TREC - Tree Felling & Vegetation Clearance ITP
checkpoint | 4 - Foundations
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Inspect fill foundation, rip rap foundation, as appropriate
label | Frequency - Per area as required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Inspection by the Design Engineer
label | Conformance Criteria - Foundation must be approved, in writing, before filling commences
label | Records - TREC - Subgrade Approval Checksheet
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 5 - Material Compliance Testing
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Material to meet specifications dependant on material type selected
label | Frequency - Each material used
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - D50 1000 rock rip rap: 100% pass 1500mm, 80% pass 1250mm, 50% pass 1000mm, 20% pass 750mm
label | ○ AP65: 100% pass 65mm, 5% pass 75μm
label | Records - Photos to demonstrate process has been carried out
checkpoint | 6 -
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Rock Construction Material
label | Frequency - Prior to commencement: At quarry - Confirmation of acceptability by Geotech Engineer from each source unless rock property changes are evident, in which case additional approval required
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual, geological hammer testing or scraping of rock as required by Geotechnical Engineer
label | Conformance Criteria - Confirmation of acceptability by Geotechnical Engineer
label | – Hard, durable stone with the size conforming to that shown on the drawings
label | – Rock shape to be as cubical as possible with limiting ratio of least dimension to greatest dimension 1:3
label | – Long, thin or slabby shapes are not acceptable
label | Records - Inspection and sign off by Geotechnical Engineer
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 7 -
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Geotextile - Rolls delivered and delivery dockets gathered. Compliant with Bedim A49 and Tencate PES 1000/Tencate PES 2000
label | Frequency - Prior to commencement of placement
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual Inspection
label | Conformance Criteria - Conformance with Specification
label | Records - Delivery Dockets/ Material Cert
checkpoint | 8 - Construction of Engineered Fill Embankment
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that the Engineered fill embankment is constructed to at least the finished height of the embankment protection rip rap
label | Frequency - Compaction testing from ~0.5m above typical WL. Sets of NDM (~5/test area) at <~1.5m vertical spacing with final test at FL. Clegg Impact Value tests at ~0.6m lifts (every 2nd layer)
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Site testing to TNZ F/1, NDMs and Cleggs (CIV) for calibration.
label | Conformance Criteria - Min 95% Standard Proctor density
checkpoint | 9 - Geotextile Placement
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure that geotextile is placed as detailed in Specifications/Drawings with the required laps.
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Records - Photographs
checkpoint | 10 - Riprap Placement
label | ACTION (Hold, Monitor, Witness) - H
label | Detail - Ensure that placement of rock material is placed in such a manner to minimise segregation and avoid displacement of underlying materials. Oversize rock to be placed such to minimise voids. Design Engineer given notice to visually inspect initial placement of riprap material
label | Frequency - Daily visual check
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Visual inspection
label | Conformance Criteria - Specification
label | Records - Photographs
holdpoint | AUTHORITY HOLDPOINT
checkpoint | 11 - Survey As Built
label | ACTION (Hold, Monitor, Witness) - W
label | Detail - Ensure rock slopes comply with design prior to next process taking place
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Measurement
label | Records - Survey receipt
checkpoint | 12 - Lot Number QA File
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Ensure all NCRs are closed and included within QA file, Delivery Dockets and Lab Testing Spreadsheet and Test Reports to be included in QA File
label | Frequency - At completion of Lot
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Document Review
label | Conformance Criteria - Ensure all QA is uploaded into CONQA/Procore
label | Records - Delivery Dockets, Test Reports, Lab Testing Register
checkpoint | 13 - As-builts
label | ACTION (Hold, Monitor, Witness) - M
label | Detail - Red pen mark up drawings to be included in QA file
label | Frequency - At the completion of the Lot of work
label | Inspection / Test Method submission, visual inspection, testing, measure, review - Drawings
label | Records - As-built Drawing