## Resources
Rich Type | Id | Warnings | type | name | values | prefix | postfix | Usage Count | User Addable | Template Name | Template Id
checklist-flat |  |  | checklist | Production and Testing ITPs |  |  |  |  | Yes | Production and Testing ITPs | 03ba6713-33d2-4f0e-8fee-0e534bf8e297
checkpoint-status |  |  | checkpoint | Production and Testing ITPs
checklist-sectioned |  |  | checklist | 3. HB AWPT ITP - McKenzies |  |  |  |  | Yes | 3. HB AWPT ITP - McKenzies | 075f4a39-0f25-41c9-8310-dc747431bb18
checkpoint-group |  |  | section | Preliminary / Estabilishment
checkpoint-status |  |  | checkpoint | Establish TTM
label | af850ef5-71f8-5e03-ae49-e28dfceb8f86 |  | note | Test Required - Visual Inspection
label | 3f33bba9-2d5f-5ff9-a684-bf6fdaccdf8f |  | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | 1efced5c-40ff-56ed-abb5-bc1a11ccb6bf |  | note | Task Assigned To - STMS/Site Foreman
label | 4a93c0f8-5cd4-558e-b7e5-ce59e59ba513 |  | note | Measuring Devices or Method - Visual
label | ea208df8-9f50-5662-b7ab-565150acb570 |  | note | Criteria - As per TMP and ensure TMC advised in advance of works.
label | 8afeb445-6451-5ee4-8fa5-4baa31a0894e |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Permits
label | 9fe94df4-08cd-5661-9e51-79c90303034a |  | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | 33f81939-c267-5126-b91f-efa221a2c4e1 |  | note | Test Required - Document Review
label | 5614bc98-17f0-53d5-8ad9-141122358840 |  | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | c1bcc6f8-9d73-5727-ad2e-5c2c8793b7bd |  | note | Task Assigned To - Site Foreman
label | d53f8a9a-eeb9-56ae-83e6-fc503ab043e1 |  | note | Measuring Devices or Method - Visual
label | 06d69ccf-800c-5b5e-800a-a8adbe43b7c3 |  | note | Criteria - Obtain permits and mark outs prior to construction
label | f11573b0-f6bd-5b1b-abba-b1a25fb0202a |  | note | QA Form - Copy of Permit on site
checkpoint-status |  |  | checkpoint | Clear-Shoulder and Side drain
label | f4e28b61-ec31-5247-bd21-429f09e04fc9 |  | note | Test Required - Visual Inspection
label | fc6ab4cc-bedf-5eff-8da3-2e3232251c03 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 6ffa6631-5df8-526b-b9c8-88c6e6ca9bed |  | note | Measuring Devices or Method - Visual
label | 3d886d97-4707-56ee-8396-ee89393ac9d9 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Digout Failed Areas
label | a4b695e0-0729-5f6d-ad64-1b1b0a34ab6b |  | note | Specification Reference - Refer to Design Report for required depth based on Scala results
label | fb02f0d6-269e-55e6-b69a-eab11d9f7d37 |  | note | Test Required - Visual Inspection
label | 226a8373-d9a1-5bac-9d62-677f1924073a |  | note | Task Timing / Minimum Task Frequency - Prior to Pavement Rehabilitation Construction
label | 7aed6ab6-0919-5c0c-9744-fa67469fa263 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 3e7b08fb-3c10-5f52-a45e-124b2f78ca70 |  | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | 2fa44150-9af8-5b41-8a4a-e9d67cd0015c |  | note | Criteria - Backfill with Pavement Aggregate
label | 1e283d0a-9811-5aea-8290-160e692c0c37 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint-status |  |  | checkpoint | Cement for stabilisation
label | 08decc68-69e1-5034-b586-cd6609d5b03c |  | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | 5f514f79-2497-5c59-8af9-f798ce7b99d0 |  | note | Test Required - Certified in accordance with NZS 3122
label | d58e6344-b8be-5fda-a40f-f461d05e54b1 |  | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint-status |  |  | checkpoint | Production plan
label | a1ee1ad8-2132-52b8-8d37-2fb2bba0e6ac |  | note | Specification Reference - NZTA B/5:2008, 7.2.2
label | 55254d6f-df3c-548d-b394-db195dc23c00 |  | note | Task Timing / Minimum Task Frequency - 1 per site
checkpoint-status |  |  | checkpoint | Stabilisation mix properties (including cement):
label | d386e0c4-3085-57c9-b15b-2480204abb1b |  | note | – Maximum dry density (MDD)
label | 1be1b594-3edf-5b6f-8e9e-7e272f02984d |  | note | – Optimum water conent (OWC)
label | 33e55ac0-03e9-52af-9ebb-635a93af0123 |  | note | – Solid density (SD)
label | 47d8813f-5e7f-52c6-84ac-c10ad55a9e3b |  | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | ac83b3b6-73ca-5a25-9e8d-8ca957db7cb1 |  | note | Test Required - Material properties for compaction verification
label | 705fa293-41b7-5ab2-a90a-5335805e1d51 |  | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | 4ee7ed93-edd0-5466-9514-99774fba91ab |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | d391cf4d-d43c-5a1c-a5e6-4814d4acd1e4 |  | note | QA Form - QA Measurement Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | In-situ moisture content of existing pavement aggregate
label | 3aaac256-503b-5feb-96fa-926d36b37a53 |  | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | e7af630b-742a-564e-865f-867692c37b38 |  | note | Test Required - In-situ moisture content Between 90% to 100% of OWC
label | 384c0c34-a0b8-55c4-a4ee-bb42a398c29e |  | note | Task Timing / Minimum Task Frequency - As required
label | 69564ecc-ad0c-5dc3-b5b9-9f536fc42a01 |  | note | Task Assigned To - Inspection - Lab
label | 5ad645fe-1468-50fe-b40e-953eab53a1d4 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Top-up metal
label | 939a5f60-55e7-50b7-8d18-43e92e6f4bf2 |  | note | Specification Reference - TNZ M/4 Table 4
label | 18632f55-231f-5bea-9c3a-d6551013290b |  | note | Test Required - Placed to required depth and design levels
label | 263a91cf-d801-5c0a-9f32-11a1b4fe0e72 |  | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | cb4f7626-274e-519b-ae8c-a4a802845a77 |  | note | Task Assigned To - Site Foreman
label | c194cee0-dfa5-557c-a808-3b06d03474f0 |  | note | Measuring Devices or Method - Stringing, Tape measure and or survey
label | 5024f357-eec5-5860-8d62-5d4ed3d6bc36 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Cement spreading
label | e865f898-960c-5d42-9669-52cac2b17a37 |  | note | Specification Reference - NZTA B/5:2008, 7.3
label | d2c400e8-35c9-592a-9415-b3ddf698285b |  | note | – Mat test (1m2 canvas mat)
label | 8aba7ac8-f5e0-5bb2-b58f-8ebd31fec825 |  | note | – Average usage test
label | 1f64b22f-0b97-52cb-8b8e-c5c83feff079 |  | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | d5ece7ae-af58-5d5a-891e-7edca6bfd4aa |  | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
label | 0a50671b-b91e-5e95-b597-d1c980cfe26a |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 0ff82b5a-54cc-521c-8ab1-80c582f51456 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | In-situ mixing - Cut depth
label | ace093aa-5c19-5da7-96e2-94c781e19b8c |  | note | Specification Reference - NZTA B/5:2008, 7.6.1
label | 77d6d018-daec-518f-9324-14d8bd9be08d |  | note | Test Required - Maximum variation -5mm and +15mm
label | 99c0b945-999d-5662-b3c5-81bab74c8258 |  | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | aa6ccd86-45f0-5752-b547-5f85b26445d1 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 44f02253-7330-5198-b0e2-dfdafb6e939c |  | note | Measuring Devices or Method - 250mm Depth
label | 2fed62e1-0c51-515f-bd9b-1847e2bad73d |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 5c0eedcc-c594-590c-85c3-374e66345818 |  | note | Specification Reference - NZTA B/5:2008, 7.7.1 NZS 4402 Test 41.3
label | f69eb0b6-e4af-5481-914b-5660cfe623d5 |  | note | Test Required - Plateau testing
label | 5809ad45-13c4-5457-b780-3b66855a1c71 |  | note | ○ Mean value ≥ 98% of MDD
label | 5357c9ac-696b-5d00-b435-5700810d27c0 |  | note | ○ Minimum value ≥ 95% of MDD
label | 358d9aad-3b96-5aff-bd03-4505d5b72db6 |  | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | c876f753-efee-5da5-ae63-b8314ee385e3 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 89fac70e-d089-594a-af3d-49a769a88d66 |  | note | Measuring Devices or Method - Nuclear Densometer
label | 10809696-9ae5-541b-8d30-af318352cf74 |  | note | Criteria - Minimum value 95% of MDD
label | d386147d-de86-5282-87bd-d8ad5265b2b5 |  | note | QA Form - Test Reports
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape
label | 97fefc29-7a3c-51e5-8357-f6d915623504 |  | note | Specification Reference - NZTA B/5:2008, 7.8
label | 32e6542d-6455-55e4-9fb2-e4a9b6057878 |  | note | Test Required - ≤10mm from 3-metre straight edge
label | edbed1a6-a8c9-55b5-b3c1-fee7a45a8eb7 |  | note | – No depression
label | e293933d-cc8c-56a1-9efd-f07f5897a89b |  | note | – Vertical variations -5 + 15mm
label | 99b8d382-3e4e-5269-809a-786985789240 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 93f5dcde-d4ce-5dac-b615-a2c6ec67abbf |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 645515fb-3923-5157-89c1-fd26f4fe2c09 |  | note | Measuring Devices or Method - Stringing, Tape measure and or survey
label | 8b4ec6e9-fc9b-52a7-a70d-65a7a2200ad9 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Crossfall
label | a7b3d6c4-06a4-5d79-afb4-1d3a2f25824c |  | note | Specification Reference - NZTA B/5:2008, 7.9
label | bbf35a9f-1db3-51fb-9b6f-13e03deccc57 |  | note | Test Required - Not less than exisitng crossfall at the start of construction
label | e9fbcd6e-2940-5481-b57c-3e67422ccaf9 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 355cd3d3-a6ab-5c01-8a46-c9b7ed64660e |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 3ef9730f-e3c4-5525-86f4-45280dd37ecc |  | note | Measuring Devices or Method - Stringing, Tape measure and or survey
label | 39f4440b-d2bc-5f45-95f6-08975ce3a8f9 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Surface finish
label | 90a0f73f-e0d1-5a84-9fa4-445af336062e |  | note | Specification Reference - NZTA B/5:2008, 7.10
label | 5845613c-c752-556b-9d10-a93978a4c226 |  | note | Test Required - See clause
label | 0f1d96e4-2bf4-5512-89cc-53a0952b0bb9 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 4d86d6c3-47ab-5691-824a-940f9759c10f |  | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | bbbdaf3a-d52a-5911-ba9b-318de62cb638 |  | note | Measuring Devices or Method - Visual
checkpoint-no-status |  |  | checkpoint | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
checkpoint-no-status |  |  | checkpoint | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
checkpoint-group |  |  | section | Chipseal Construction (NZTA P29)
checkpoint-status |  |  | checkpoint | Ensure appropriate TMP used
label | e731b267-e1b2-5b8b-b606-a9c36a4e1555 |  | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint-status |  |  | checkpoint | Seal design
label | 5df487f7-cc46-57ec-947e-962d803acd0f |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | b5157884-f8d9-5acf-bdd5-9be9ec805c19 |  | note | Task Assigned To - Project Engineer
label | f198e064-b636-5e1e-a8d4-2ec2c9502791 |  | note | Criteria - Seal design to be reviewed prior to surfacing
label | 2e0e5360-10f7-5613-a477-77b482f95172 |  | note | QA Form - Seal design template
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Location/Size Confirmation
label | 5ca3117b-c84a-5a36-b32f-fbefdde540e4 |  | note | Test Required - Mark up extent of chipseal
label | ea1975cb-dc3d-5fa3-9b36-dcc71b634f3c |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing
label | b413b96f-0de1-53a0-94de-4f5f627f3731 |  | note | Task Assigned To - Project Engineer
label | 9e094f44-5bce-58f4-92b6-66380ca61a2d |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Surface Cleanliness
label | a6c489a9-22f2-5145-a319-ef4e2669248f |  | note | Test Required - Visual Inspection
label | 090c7f25-eda3-5549-b582-ec81f0e8cb37 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder
label | c01ef9f2-f5eb-5b04-bf40-04a50c6995e3 |  | note | Task Assigned To - Site Foreman
label | d1e269ca-8154-5cc4-8e56-4f3580984e5e |  | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | 7fc09843-0816-5fc4-a105-ac36f1be19b3 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Plant Resource
label | 8ae15dca-a91e-5e1a-a066-21e5e188dbb3 |  | note | Test Required - Visual Inspection
label | a54c1408-936e-5982-81bf-d8110e2fe4c4 |  | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | 5bb74e72-e582-50ee-ac9c-192f1b583dc0 |  | note | Task Assigned To - Site Foreman
label | 8f8bac14-b4e5-50e7-bf12-b3ffbfe41994 |  | note | Measuring Devices or Method - Visual
label | d51b766e-3f6d-5b10-a90e-31911a3ef9eb |  | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | 2d1a4f04-9309-581e-af24-6ed610e1e68b |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Binder Application
label | 61dc46de-484e-5498-b0cf-ccfc1d4b50a7 |  | note | Test Required - Binder type, Cutback, Temp, Application rates
label | 0cd2023e-3187-5b4d-938b-6407f331fecb |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | 600ccf86-a002-50ee-8709-96760de57202 |  | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | 9e60668b-2c80-578f-b3cf-e2f583604309 |  | note | Measuring Devices or Method - Visual
label | 85594e38-4a9b-5630-a9cb-7d3eed85579e |  | note | Criteria - Binder Type = 180/200.
label | a5aadf71-8bd3-5383-8b4a-3656478b1a8d |  | note | ○ Cutback to suit 1st coat seal 4pph kero max.
label | 3f5cb0ad-817c-559f-a528-8ed4d0f49ecb |  | note | ○ Temp = 150deg celcius min
label | 5059775d-a529-558b-a851-47b4d4726381 |  | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
label | aaf29903-8016-54d4-a8f9-c4efb80295cb |  | note | QA Form - Bitumen Spray Sheets
checkpoint-status |  |  | checkpoint | Chip Application
label | c0bbbb20-ad5b-5b4b-81a8-ee6887977f42 |  | note | Test Required - Chip type, Chip Application
label | 4cf7593f-5d73-5e3c-904f-8b82f6124c3f |  | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | 8f5f5122-0178-5496-9c5f-70c3440da440 |  | note | Task Assigned To - Site Foreman
label | ea6e3f77-d3d5-5a53-90d1-b6fa8b021fe0 |  | note | Measuring Devices or Method - Visual
label | 2f6df7f0-649b-505e-ba73-cf4e3536bf06 |  | note | Criteria - Trucks loaded with correct chip.
label | 76159247-55f3-580d-836d-aa12f822855e |  | note | ○ Chip clean. (G4/6 Racked example)
label | 8e5d4975-7e8e-5c8d-8d05-d25ec6abfb31 |  | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | 0e7ab8d2-fd14-5430-aef6-9f19b6150599 |  | note | ○ G6 application = Enough to just fill the voids around the G4.
label | f4aa000d-d9da-50ee-a1fe-0e53071130c1 |  | note | QA Form - 'QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | e0de6630-93f0-5975-b2d9-d45375034b76 |  | note | Test Required - Visual
label | 1c3bfae1-f07b-5162-a6ff-4a77da73656e |  | note | Task Timing / Minimum Task Frequency - At completion of rolling
label | 8dc3286a-c27b-55e5-8b1f-c3fbdf6108cb |  | note | Task Assigned To - Site Foreman
label | fca54f7d-ae26-5814-8291-ae9b84e6ba74 |  | note | Measuring Devices or Method - Visual
label | 1415af99-78e2-5c7a-9109-55cf08d3f346 |  | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 675d02a5-193a-541e-b96c-c75f8686de9f |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Site Measure
label | a695fdb2-1b82-5acc-b16c-300edf5b9fb8 |  | note | Test Required - Record final site measure
label | 5d49a707-e6c1-5af7-8fdb-f48b5d14f38a |  | note | Task Timing / Minimum Task Frequency - Completion of works
label | 5e2188c7-f367-51ff-af40-3ad4bd917fbf |  | note | Task Assigned To - Site Foreman
label | 824c2535-31fe-5a6a-ab56-924aa4616bf2 |  | note | Measuring Devices or Method - Measuring Wheel or Tape
label | 5eef4fae-ce19-57ad-a6b5-6342086ce818 |  | note | Criteria - Sketch and record seal area and QA detail
label | e339b1ac-ffa2-5430-8c56-2874a7da14b0 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Post Seal Care
label | d4eff21f-3fa6-5acc-85c5-f0a9a6e654f2 |  | note | Test Required - Visual inspection
label | b29d08a5-ce41-543e-a057-c49fa962ea25 |  | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | d2d87c04-d8e0-5998-b683-4fa887326653 |  | note | Task Assigned To - Site Foreman
label | 69431531-c812-5403-b2d6-b469235d69d9 |  | note | Measuring Devices or Method - Visual
label | d02dde0f-e000-5565-97cb-e7f05c5e7ea4 |  | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | 1a336b44-0ab0-5abc-baef-ce313fb0514b |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Chip Removal, Pavement Marking, Traffic Services
checkpoint-status |  |  | checkpoint | Removal of excess chip
label | 43bf1fbc-dfbe-5a7e-ba1f-de33d1d2deaf |  | note | Test Required - Visual Inspection
label | bfc8f627-8b47-5f21-b544-5e57566a2342 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 51b2d957-c7a2-5c68-98a6-efa46155b2bf |  | note | Task Assigned To - Project Engineers/Site Foreman
label | b3c8fb70-582e-5465-8ff4-8bc4c36678ab |  | note | Measuring Devices or Method - Visual
label | 1fd8b6cd-933e-58e9-b894-46ed329fba14 |  | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 2a2be0f7-9497-59f5-a2e4-daa61e972f50 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Pavement Marking
label | 11d30969-9e7e-5443-9d97-9cf65d668f40 |  | note | Test Required - Visual Inspection
label | 56741978-e3a0-5abc-92a5-d6d37496e847 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | f1216e3d-95c4-548c-8732-22db5a6b5507 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 8c462110-3af0-55e7-9778-60afe6da6fd8 |  | note | Measuring Devices or Method - Visual
label | ce178b24-ebc3-5041-994e-8a39ab70c705 |  | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | 1573c25f-0612-5589-b183-7e3b1fd82a52 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Removal of TTM
label | d2acd26e-7b93-5ac1-baa3-af6b4518cc52 |  | note | Test Required - Visual Inspection
label | 81ce1205-e6d2-5209-a684-ee88f30dedcd |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | fbb7fffb-d56e-5a76-8cd4-a8fd13c95a91 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | dcaf27a4-2318-577f-a16e-2287f8a2f927 |  | note | Measuring Devices or Method - Visual
label | 175ca669-7543-5d88-9baf-394f47e8a27b |  | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | 3d095f05-bc9c-5e47-ae76-c79ac2923365 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Traffic Services
label | e75d0643-65f8-52b2-883f-310fa3e83ec1 |  | note | Test Required - Visual Inspection
label | 6d340f4a-9c9b-554d-bd29-ee2f73c9823e |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 55adf4c1-d7c7-5438-ba04-6e65c55950f8 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 4a68e499-f45c-5657-9974-21f20d950c41 |  | note | Measuring Devices or Method - Visual
label | 9f2e2102-06a6-5e77-9b39-ab31e3688095 |  | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | 6cf5ce19-8783-532f-a602-ecfcfb5235ae |  | note | QA Form - Daily Diary
checklist-flat |  |  | checklist | Approved JMF |  |  |  |  | Yes | Approved JMF | 0f230045-6516-4dd6-932c-88e32a125c5d
checkpoint-status |  |  | checkpoint | Approved JMF
checklist-sectioned |  |  | checklist | 5. HB AWPT ITP - Snee Rd II |  |  |  |  | Yes | 5. HB AWPT ITP - Snee Rd II | 1035b024-fbf6-4740-a368-468169a8d46f
checkpoint-group |  |  | section | Preliminary / Establishment
checkpoint-status |  |  | checkpoint | Establish TTM
label | 5fb862be-9ce3-54a8-bad0-d7f8990c8d93 |  | note | Test Required - Visual Inspection
label | 4bebd3d5-0878-5652-a879-0ecf932c28f9 |  | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | 262420ab-a12c-5c78-9ea7-65bfe9e16a1b |  | note | Task Assigned To - STMS/Site Foreman
label | 349d9718-39d7-58d1-8e9e-70fda974490b |  | note | Measuring Devices or Method - Visual
label | 5b1b0ac1-fe26-5e9b-a2d8-70c71de8f3b2 |  | note | Criteria - As per TMP and ensure TMC advised in advance of works.
label | f9ed209f-e50f-5d59-bac0-c5b8b23b93f8 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Permits
label | bf6fadf2-98a6-51e6-86d0-406c2b00db43 |  | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | f0b3bd95-732a-5fb8-a04a-771b1772ba6d |  | note | Test Required - Document Review
label | 2a42d632-e47c-5146-a6e2-7ac1999f7310 |  | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | e017bff7-62b0-54de-b94a-8137ad89b72d |  | note | Task Assigned To - Site Foreman
label | 03442ec9-5ef6-52ee-b4d0-bdc9ab4bebd0 |  | note | Measuring Devices or Method - Visual
label | c5e4b60e-892d-52e7-ad8a-755258ef1a9d |  | note | Criteria - Obtain permits and mark outs prior to construction
label | 9d8a93d1-31e9-50f6-aa15-0491b7ecc4ef |  | note | QA Form - Copy of Permit on site
checkpoint-status |  |  | checkpoint | Clear-Shoulder and Side drain
label | 82ebda7f-436c-56bd-8b71-ed6ebb672dbf |  | note | Test Required - Visual Inspection
label | 3b84ebac-cdcc-588b-988f-c5dbc8693523 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 44dc7e4c-2069-58b9-a789-b180b98b90b7 |  | note | Measuring Devices or Method - Visual
label | 23aa44b3-ed84-5954-8af0-fafbbfdf561e |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Digout Failed Areas
label | 44a6d330-b0f1-5093-acb4-069b837dd72d |  | note | Test Required - Visual Inspection
label | e237dab7-9fb9-598f-9fd3-9582afa2774c |  | note | Task Timing / Minimum Task Frequency - As Requested
label | 55bd27a7-6bfa-5b22-8024-a75dbe721705 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | e8fe65de-1646-53c7-b8da-c37ddcf99d97 |  | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | 5a8ce62d-89a9-516e-82bc-e46c2cea62d6 |  | note | Criteria - Backfill with Basecourse
label | a4b22c29-8bd2-52d4-9d97-04a25836ba38 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint-status |  |  | checkpoint | Cement for stabilisation
label | aebb764f-bff9-5b0b-8493-5a802b6b5dec |  | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | 9e805c77-c118-51a8-a205-467286734232 |  | note | Test Required - Certified in accordance with NZS 3122
label | 51a89581-afc3-5bd9-bc35-69299ac6ff2f |  | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint-status |  |  | checkpoint | Production plan
label | 53e7cf42-c4c7-5ef5-b5ce-ba1f208a2cf5 |  | note | Specification Reference - NZTA B/5:2008, 7.2.2
label | 478397b9-120e-5931-8338-f99c9557f0fd |  | note | Task Timing / Minimum Task Frequency - 1 per site
checkpoint-status |  |  | checkpoint | Stabilisation mix properties (including cement):
label | 41c8810b-ce97-5216-9bee-71d8081ebd09 |  | note | – Maximum dry density (MDD)
label | 51d32042-8558-5948-9fea-4b1ebd40f6ba |  | note | – Optimum water conent (OWC)
label | 3603ceb9-daaa-5044-bb0f-59a41cfdedad |  | note | – Solid density (SD)
label | f7fbfeda-eceb-545b-8e70-42590746f37c |  | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | f2d070fe-8c51-5c25-9237-1e6b51275027 |  | note | Test Required - Material properties for compaction verification
label | fe44a267-71c9-52fe-a1af-4c9cf404d8ca |  | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | b08db3d6-708f-56df-8a3e-116fdedb3430 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | e00fef26-53fd-5351-ba28-437ce37e929c |  | note | QA Form - QA Measurement Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | In-situ moisture content of existing pavement aggregate
label | 93c9e9ee-808f-5b03-9d0a-09d6f2deedf3 |  | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | 4cd77759-4281-55a4-802c-6bccfda9e274 |  | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
label | ffbafcc8-bbdc-50e2-9b58-d132992f23f5 |  | note | Task Timing / Minimum Task Frequency - As required
label | ebdc325d-e1b6-5a76-aa72-69ef993caec1 |  | note | Task Assigned To - Inspection - Lab
label | 317d2896-7b38-5665-9180-3834ba6b76fd |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Top-up metal
label | 4ff31d20-9bc2-5c1f-b8a1-1d4f76790554 |  | note | Specification Reference - TNZ M/4 Table 4
label | d6ddd36a-1a28-5d75-8487-3d872e7a26a8 |  | note | Test Required - Placed to required depth and design levels
label | 851a90b1-817f-5fa8-a749-fe1b91eecc52 |  | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | 874aee0c-9699-565b-9de5-ae7a61169a84 |  | note | Task Assigned To - Site Foreman
label | 17b8a7ae-1ba4-5456-ac6e-8b71ab63ff83 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Cement spreading
label | f48953f3-7037-5ed8-8eee-7aa91bfdf7ba |  | note | Specification Reference - NZTA B/5:2008, 7.3
label | 9951362b-c4ef-54db-bbfc-27c5bb3a607d |  | note | – Mat test (1m2 canvas mat)
label | 3cf6f084-6e05-547e-9a4d-c4d1de4c30d6 |  | note | – Average usage test
label | 4a71d46b-f42d-592f-bd88-c90211139970 |  | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | e69c5dc0-4bb6-52ee-98e0-8e4126ec5b0b |  | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
label | 1c8712e8-f8dc-5524-b4a5-ef6cd815e640 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 1be1197b-7870-527b-8fef-dfbdda2709ba |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | In-situ mixing - Cut depth
label | 92dd9b9e-e5a0-5787-acd1-b01e3975454c |  | note | Specification Reference - NZTA B/5:2008, 7.6.1
label | 9e720c70-0b9d-5d23-9e85-9c9601cc8d81 |  | note | Test Required - Maximum variation -5mm and +15mm
label | 481e4ffb-7c33-5e74-be14-69c2d1e862ce |  | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | f164cc6f-f56a-56f4-8cd2-ca60b68a2418 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 550d228c-3ba6-51d6-a31d-8f2ec4a4da32 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 1d47be70-6bb3-5de3-a6da-451652f17239 |  | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
label | bf09f076-b687-59c9-ae1f-7c4de6e3d7c3 |  | note | Test Required - Plateau testing
label | b7c8b8d1-481f-5589-95a9-7b900eeb96ed |  | note | ○ Mean value ≥ 98% of MDD
label | 3c9055fd-a2a8-5469-820b-e0e5d01987bd |  | note | ○ Minimum value ≥ 95% of MDD
label | df917caa-d608-5328-9341-7507672e0eb6 |  | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | 130cbcda-ef40-5d9a-b1aa-8aec64b50a8a |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | d0c33c84-936c-5469-b018-66fc77533e5c |  | note | Measuring Devices or Method - Nuclear Densometer
label | 260c1b34-0333-5080-8193-61edb22f3781 |  | note | Criteria - Minimum value 95% of MDD
label | b6a932df-f2c1-5ccb-9a60-3268cc67a981 |  | note | QA Form - Test Reports
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape
label | d9f9bc18-f3ee-5b6b-934f-37c18fe882a0 |  | note | Specification Reference - NZTA B/5:2008, 7.8
label | 6895f197-27e0-5d12-ac3c-fef5435d0910 |  | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
label | 4ce13567-a48c-5cc1-b8d6-aae891dd33f7 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 4c77cc91-5bb6-53b3-8298-308d257e4791 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 7f62a0a3-b55f-5a1a-8592-20d3c2e8b779 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | 9d5801e3-7ce3-5525-a528-28386f2b363e |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Crossfall
label | 6eb025a0-7003-59b5-8ade-89b527b199dd |  | note | Specification Reference - NZTA B/5:2008, 7.9
label | e73563a3-02f5-50ea-ac89-2334372b0771 |  | note | Test Required - Not less than exisitng crossfall at the start of construction
label | 7e9d671d-1b2a-574c-9c81-a7fa5962c6a1 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | e5ec48a5-ca6b-577c-959c-a09f628372aa |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 602851d9-c4a5-5a41-a7e1-188ffd5ea5a3 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | 9b87c1ea-ca24-5723-9a08-8a26c3351b9a |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Surface finish
label | 36fb6d18-fdf7-5f90-b30b-5299a94da29b |  | note | Specification Reference - NZTA B/5:2008, 7.10
label | 095debb0-51b6-5535-9264-172864361177 |  | note | Test Required - See clause
label | 08f25850-b878-50d8-92dd-3393d1d0a6af |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | a158e552-2eba-56a7-9b78-5d25930d76a4 |  | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | 25ebef81-c28e-593a-831c-0b8223c335e6 |  | note | Measuring Devices or Method - Visual
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
checkpoint-no-status |  |  | checkpoint | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
checkpoint-group |  |  | section | Chipseal Construction (NZTA P29)
checkpoint-status |  |  | checkpoint | Ensure appropriate TMP used
label | 275769cf-a68b-5c69-a788-fa9bf07729cf |  | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint-status |  |  | checkpoint | Seal design
label | 833ec145-eb43-58ba-82ba-f40e6a1e2bce |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | d9b8011f-daa6-5d43-8fd7-f1b98a52f505 |  | note | Task Assigned To - Project Engineer
label | bd831281-09b7-5a85-a7ba-f8636fffea2b |  | note | Criteria - Seal design to be reviewed prior to surfacing
label | 97d3aab9-133e-5b90-a44f-36409076455a |  | note | QA Form - Seal design template
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Location/Size Confirmation
label | 02a1b64c-8be5-5a54-ae5f-49cba0c401ec |  | note | Specification Reference - Mark up extent of chipseal
label | 9e8c2dfe-67e6-5480-9666-c0485faa1c1a |  | note | Test Required - Prior to surfacing
label | a41743b9-ec2f-5dfb-8304-723b06d7df6e |  | note | Task Timing / Minimum Task Frequency - Project Engineer
label | f5f0ad31-49f5-5389-a162-04bb1dd5a019 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Surface Cleanliness
label | a449b7b0-4cb4-5d1d-97d3-8471f3ab5b7f |  | note | Test Required - Visual Inspection
label | a47b508e-4972-5be9-848b-64a5c94bf079 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder
label | 450814d1-05d1-566e-a7e4-9d22f096cdde |  | note | Task Assigned To - Site Foreman
label | 658cd04e-78b9-5d9f-a3db-af17129952e8 |  | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | 835fa6e1-463e-5b0f-9ac7-c83d6a702d15 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Plant Resource
label | 80910abb-ac87-5301-a282-c4682cb3e21c |  | note | Test Required - Visual Inspection
label | e8ad88f3-fc48-572e-af37-be0e5066b1d2 |  | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | de996be6-6ca8-59c6-99cc-d11fd8060adb |  | note | Task Assigned To - Site Foreman
label | 88b12ae1-3f6f-5580-bdfd-801b6179ae10 |  | note | Measuring Devices or Method - Visual
label | 9da2428b-5ab1-532f-b969-14f854dbf7ee |  | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | 9ffa929b-e37d-5a74-8842-f0078ccff996 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Binder Application
label | 588ea8e5-34f8-5c31-a211-e72529b4dd93 |  | note | Test Required - Binder type, Cutback, Temp, Application rates
label | ff2fc897-1282-5206-bc02-9178e34a8768 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | 731da5b5-149b-5f05-b721-9dd1c07625a1 |  | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | 14c2f34b-bd51-54fe-96c2-56ce0463d720 |  | note | Measuring Devices or Method - Visual
label | dd4270eb-1016-5fd0-9167-ccce2a67f5b9 |  | note | Criteria - Binder Type = 180/200.
label | b89b45bf-0f69-5ea7-a4ac-0624d7a02427 |  | note | ○ Cutback to suit 1st coat seal 4pph kero max.
label | d2a74fcd-3c3b-549f-b4e3-b67c2a21f98b |  | note | ○ Temp = 150deg celcius min
label | d5f0552e-20c1-5066-a597-045c65739ff4 |  | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
label | 2315168a-9f38-59c3-aeee-9f1cd5e11ffc |  | note | QA Form - Bitumen Spray Sheets
checkpoint-status |  |  | checkpoint | Chip Application
label | d1528ab9-f370-577b-b8a1-b25e13d8c57d |  | note | Test Required - Chip type, Chip Application
label | 913316af-aa30-5ae1-a97e-ec29645b3590 |  | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | ced241d1-966f-545b-adee-c11ae5ec53bb |  | note | Task Assigned To - Site Foreman
label | 8cc0bcec-3c15-5047-9c26-b29aa131e28a |  | note | Measuring Devices or Method - Visual
label | d5481c18-2d50-5e4a-84be-5d54d8a766ad |  | note | Criteria - Trucks loaded with correct chip.
label | 5c3ccfa5-bed8-5a31-929a-941a075a7291 |  | note | ○ Chip clean. (G4/6 Racked example)
label | 70124bce-03a2-5b47-8ce6-e131f9829ac3 |  | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | 83c7c9d4-2158-5061-81ef-1f07f289578d |  | note | ○ G6 application = Enough to just fill the voids around the G4.
label | 897a8fe7-ebb0-5760-ac56-c310cace84c7 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 3c631c03-73a2-56bc-8b47-db3a3cd2a117 |  | note | Test Required - Visual
label | 17664467-c75c-549f-a8f6-0e2fab89047f |  | note | Task Timing / Minimum Task Frequency - At completion of rolling
label | b7ab78dd-5c14-52bf-9903-670fea2fb22b |  | note | Task Assigned To - Site Foreman
label | 91f88405-32ed-5370-b181-b9f828667a74 |  | note | Measuring Devices or Method - Visual
label | fb22ab97-560e-59bf-b64b-a7910b2a3ff4 |  | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | ae7384f7-60c7-5f5e-922d-ddb5ce33da52 |  | note | QA Form - 'QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Site Measure
label | b0b5a0d6-8a09-58f6-9357-cc8cff5fca62 |  | note | Test Required - Record final site measure
label | 78d69b08-4771-5e22-94cc-944a8a21a057 |  | note | Task Timing / Minimum Task Frequency - Completion of works
label | 77a036f7-ea0f-5170-bb84-7a7682c74aa1 |  | note | Task Assigned To - Site Foreman
label | 1dc4d556-49c7-52bb-88da-debaecee95b2 |  | note | Measuring Devices or Method - Measuring Wheel or Tape
label | 4c95b3a2-4d52-5eb0-8994-20636cd574e1 |  | note | Criteria - Sketch and record seal area and QA detail
label | 98bceb82-33c8-5e29-a1d3-e200d67b824f |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Post Seal Care
label | c6ed3776-2d22-5b01-8f4f-a52897951eaf |  | note | Test Required - Visual inspection
label | ba2d6d7b-6b36-5aff-b5db-a57ca34558f0 |  | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | 14019db0-3088-5312-8da8-d78d51b85a9c |  | note | Task Assigned To - Site Foreman
label | 564248e7-ed7a-5f15-8392-3f9ee53a1157 |  | note | Measuring Devices or Method - Visual
label | d7676ef1-a9be-5af8-84e8-a0dca3f80519 |  | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | 67119314-415a-5a38-897d-da4310ec6e61 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Chip Removal, Pavement Marking, Traffic Services
checkpoint-status |  |  | checkpoint | Removal of excess chip
label | 3cf120cf-791a-5f72-97b2-8024c2c55571 |  | note | Test Required - Visual Inspection
label | 328b6a72-3e50-59cd-8f8e-59a222e8023d |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 9d73e507-3617-5d65-98a1-d4f966e9e68f |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 782445b9-9c47-520f-986e-b1f10eef0fce |  | note | Measuring Devices or Method - Visual
label | 60e06e5b-d7ba-54de-b61d-f4842146e0f4 |  | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | c4f3ff7a-cd4b-5063-b4cc-80dfff1d083a |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Pavement Marking
label | 3bb830e2-953e-54bb-b7de-ac8b08fd5e12 |  | note | Test Required - Visual Inspection
label | 16920172-9eac-5c8a-a297-5c1f4f57bc22 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 352cd3a6-8f77-5ea3-96fa-20a5e3005592 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 64344400-d63a-56fc-8091-a3c1b3c5fede |  | note | Measuring Devices or Method - Visual
label | f75a6688-deaa-568c-bf64-e66f934cc2f6 |  | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | 4febb4d8-cb23-572e-9c1c-cf2df71c6d2b |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Removal of TTM
label | 01f43b0b-3305-586d-bff9-3cb82910aa6a |  | note | Test Required - Visual Inspection
label | 2bd5e1cb-1438-5638-85d3-dab742295b06 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | f457cf51-fcb3-5ef8-978c-6c1ccba99097 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 6eb9ceab-cf85-5ba4-83b9-6cc7370fa54d |  | note | Measuring Devices or Method - Visual
label | 803d126a-38b0-5b95-b106-21c292776318 |  | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | df8b71fa-3b9d-5bf4-9eff-c1308d33e271 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Traffic Services
label | 150d2d54-682f-51ea-99ce-94c31ac44ba6 |  | note | Test Required - Visual Inspection
label | b5bdec19-05ed-5409-bb36-63d2b61f86a0 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 7b8f908e-b1e9-5877-9c05-88c10708e659 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 4587dde2-5108-59ae-b1cb-91bee594b060 |  | note | Measuring Devices or Method - Visual
label | cfe0c9bd-a78c-542b-920e-1bd2fe961838 |  | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | 1ca12b25-9c65-545e-97bb-6658bc8e1bf8 |  | note | QA Form - Daily Diary
checklist-sectioned |  |  | checklist | 8. HB AWPT ITP - Clarkesons Hill A |  |  |  |  | Yes | 8. HB AWPT ITP - Clarkesons Hill A | 10b56f46-5432-4199-a4c7-2f4d29bc53ad
checkpoint-group |  |  | section | Preliminary / Establishment
checkpoint-status |  |  | checkpoint | Establish TTM
label | 9f9615f6-5fe9-54f1-832c-805bf92b797a |  | note | Test Required - Visual Inspection
label | c099eb00-f713-5f18-9774-88b6e6a2f409 |  | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | 35c3b9fe-2ba0-5e60-80f3-841815d4f156 |  | note | Task Assigned To - STMS/Site Foreman
label | a8a5d54e-81c5-5328-b4cc-c313ba02074e |  | note | Measuring Devices or Method - Visual
label | 32b51d6f-802e-5d7d-8bdc-1d7c18b89dbc |  | note | Criteria - As per TMP and ensure TMC advised in advance of works.
label | d48832c8-b3bf-587c-bb92-94a0617ae2ef |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Permits
label | 789ad237-ac22-5605-b570-377ff7504ff2 |  | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | f0f47384-7a04-5666-ae21-076ed746cf0b |  | note | Test Required - Document Review
label | 3f122113-17d7-5ead-a736-cbaf94748893 |  | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | a7cacdff-c3e8-5d76-9b11-3d02efcf7718 |  | note | Task Assigned To - Site Foreman
label | 7363c45f-f74c-5790-b494-8262eef0082f |  | note | Measuring Devices or Method - Visual
label | b6825292-bc87-55d7-8c75-efcba5a4baa2 |  | note | Criteria - Obtain permits and mark outs prior to construction
label | 518eda35-edff-509f-8fdc-3626d35a13ed |  | note | QA Form - Copy of Permit on site
checkpoint-status |  |  | checkpoint | Clear-Shoulder and Side drain
label | 6b9a14bd-385c-5e95-9a66-8c8cd04792bf |  | note | Test Required - Visual Inspection
label | 1e3fb442-4458-52e6-8f00-80e5b0aaab8b |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 878a5f2a-afa3-57c2-83eb-2123a6adc15c |  | note | Measuring Devices or Method - Visual
label | b86fd4dc-922a-5697-880d-d8d1d39d7bb1 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Digout Failed Areas
label | 9e8c04da-9938-5fa5-b0b7-3a666691ee38 |  | note | Test Required - Visual Inspection
label | 73f31b00-f7f5-5fcf-b6c4-bd28fd6ff6e5 |  | note | Task Timing / Minimum Task Frequency - As Requested
label | 93203692-c8b1-554a-9637-753a9536ebcd |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 9937a9c9-4c25-559b-bb1e-5dc83f0ac081 |  | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | 4adc9165-71cd-5667-8a1e-c478b6d349d5 |  | note | Criteria - Backfill with Basecourse
label | 227e378c-21b3-5f0a-957d-974d440ba9b5 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Kerb Construction
checkpoint-status |  |  | checkpoint | Basecourse layer construction (1)
label | 89f89651-c326-5a0f-ab9f-dbe74d748d63 |  | note | Specification Reference - TNZ B/2
label | 4f11a46a-72e1-5beb-9395-6fcacd2e6ed4 |  | note | Test Required - Level and alignment
label | ad070208-ff9e-58c9-8083-614d9c749411 |  | note | Task Timing / Minimum Task Frequency - Every 20m
label | 3aecab4b-5be2-5e27-b532-b10ec6382b53 |  | note | Task Assigned To - Project Engineer
checkpoint-status |  |  | checkpoint | Basecourse layer construction (2)
label | 078c50cf-38c8-5edb-898e-cf4963f0a68c |  | note | Specification Reference - TNZ B/2
label | a41bb285-b126-5630-9c0a-f8691894949f |  | note | Test Required - Compaction
label | e34aff7b-bda8-55b1-b04f-68675e87a419 |  | note | Task Timing / Minimum Task Frequency - Every 20m
label | 71152df4-484b-5b77-9c83-fd94e40c5bbb |  | note | Task Assigned To - Project Engineer
label | 8669bef6-e636-521f-8059-fb962cec9572 |  | note | Criteria - 25min on the 4th drop
label | 47b85271-43d9-53a5-aa38-4e2822e0c7d7 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Kerbing
label | 04c1a518-b17f-5b7d-a983-a2b4f65d53b3 |  | note | Test Required - Set-out level and alignment
label | c78906b0-a00c-5225-b2d5-c858bf1c6b57 |  | note | Task Timing / Minimum Task Frequency - after base construction and prior to placement of concrete
label | cea67277-a8a5-5ac8-86da-f572e6b882e1 |  | note | Measuring Devices or Method - survey check
label | b16914ca-5ad7-5e37-bdfc-f277b5373ce0 |  | note | Criteria - Horizontal: ± 20mm, Vertical: ± 5mm
checkpoint-status |  |  | checkpoint | Concrete Works
label | ab256e45-a3b7-5629-b212-5e98397c10a4 |  | note | Test Required - 20MPa
label | 05d2cfe2-a940-5979-8d0e-849bdc903487 |  | note | Measuring Devices or Method - Copy of delivery docket
label | f08b2a70-f25f-59a4-a8f8-c93053c41139 |  | note | Criteria - 20MPa, 28days
checkpoint-group |  |  | section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint-status |  |  | checkpoint | Cement for stabilisation
label | 52789124-7328-5295-a5fc-307a286ca159 |  | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | 4cc99be6-7498-5d1c-9ac0-a3bab12e2a0a |  | note | Test Required - Certified in accordance with NZS 3122
label | 0ec41559-40b3-53fe-ac8f-27a8fc4a4b0a |  | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint-status |  |  | checkpoint | Production plan
label | e14f0f17-155f-5227-8957-d8d65fc9d62d |  | note | Specification Reference - NZTA B/5:2008, 7.2.2
label | 59fa78cf-ec86-5ded-bcf0-c76e58af88b0 |  | note | Task Timing / Minimum Task Frequency - 1 per site
checkpoint-status |  |  | checkpoint | Stabilisation mix properties (including cement):
label | 6fedc27a-bbd6-59d3-af12-8024e5029fd2 |  | note | – Maximum dry density (MDD)
label | c6d41be6-6f37-5543-aec6-ab5e2e80a80a |  | note | – Optimum water conent (OWC)
label | b4561958-d7c3-593a-9133-0a04fe104f43 |  | note | – Solid density (SD)
label | c0f8f601-4167-5916-9c99-a426c2157036 |  | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | ff17db8f-4305-558b-9ce9-6b15095e2277 |  | note | Test Required - Material properties for compaction verification
label | 271a6cea-7681-5f52-a316-46b853a951ed |  | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | 243b771f-1c2f-52ef-8ccf-f983a9902962 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 6d435f75-8dbb-59e2-9697-29dc35ea68de |  | note | QA Form - QA Measurement Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | In-situ moisture content of existing pavement aggregate
label | 09f89974-2cc3-529f-abe8-cb424696d370 |  | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | ca5a4331-0b26-5d6f-bffb-cbb2f45d2f7a |  | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
label | f4e2edc8-2ca7-55ea-92f4-315faf0f7ea1 |  | note | Task Timing / Minimum Task Frequency - As required
label | c8ea393b-4762-5ec2-a9d1-67e3f32095a8 |  | note | Task Assigned To - Inspection - Lab
label | a0dbd5f8-e8de-50c7-a74e-5344e4468b45 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Top-up metal
label | 542b2963-e6fb-5c02-b826-0b73fcd216de |  | note | Specification Reference - TNZ M/4 Table 4
label | 01b465f4-92c1-5856-a605-1ca14b625daa |  | note | Test Required - Placed to required depth and design levels
label | 8ec48b85-6482-5b41-ab90-05eecc099248 |  | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | af45abe8-b734-5f5d-a9db-beffe40aae66 |  | note | Task Assigned To - Site Foreman
label | f77051d2-1838-58c8-b6e2-14f5c234a97b |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Cement spreading
label | d580969a-c604-51de-a639-dc4f7c5ed289 |  | note | Specification Reference - NZTA B/5:2008, 7.3
label | 2d56eeb4-1084-5acf-bf21-66d7b99fd593 |  | note | – Mat test (1m2 canvas mat)
label | 00c1f01c-0f8b-5c53-a4ec-ff4a8a23dde9 |  | note | – Average usage test
label | 40077438-b495-5034-b9f8-b1cced70a464 |  | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | 9ce535a9-1801-5a24-b243-b7fdead3142b |  | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
label | 3b7af9da-3869-50ff-a966-84adc3627d90 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 2a1b5e72-3635-5775-83d2-97729833bd4d |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | In-situ mixing - Cut depth
label | 87f7b815-2ee5-56ef-8d89-2ab140f4ccf2 |  | note | Specification Reference - NZTA B/5:2008, 7.6.1
label | a0f1c177-8a83-5b80-8bb2-1f6c4f6b522c |  | note | Test Required - Maximum variation -5mm and +15mm
label | 98341e5e-0340-565b-aa7f-027deb2a1b0a |  | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | 8f46e5e4-f69e-5a9e-a31b-e990cd4ce356 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | a8f76f1b-f83d-50cd-9bd4-5b5cf5d76cfd |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 67fdb6ed-02a8-56c1-92e6-39af7880fe78 |  | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
label | 3bd7be8d-2688-562f-b2dd-48b06d31b0ec |  | note | Test Required - Plateau testing
label | 579abd4d-4a09-52df-937e-20c1c49452ca |  | note | ○ Mean value ≥ 98% of MDD
label | c7ed232b-8b45-538b-ad38-6f816e0174ff |  | note | ○ Minimum value ≥ 95% of MDD
label | cf0e48aa-e193-58a8-a0ca-493aa285b5fb |  | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | d3747ac7-31f0-593b-89cb-603ff001403a |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | d6c45cc7-197a-509e-86be-f44b4158d877 |  | note | Measuring Devices or Method - Nuclear Densometer
label | b9b84758-a8ad-5876-82c6-79a7cbd16551 |  | note | Criteria - Minimum value 95% of MDD
label | 0c15783b-ea85-5e69-9d62-cb58435b120f |  | note | QA Form - Test Reports
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape
label | 5726e7b0-790a-5b70-8b2a-b3025e55e643 |  | note | Specification Reference - NZTA B/5:2008, 7.8
label | 5588a1d8-6076-59de-9728-3ee3a6202f34 |  | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
label | 67157436-ba52-50c7-8bec-9f2873fe516d |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | c50c2623-ef09-5200-a01d-2b7426cbd35a |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 33a2e2f9-2881-529c-b45c-24d3a9b967f1 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | ed84ffe1-7548-5a95-a1a8-6586955620aa |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Crossfall
label | 51a6fcf1-4a87-5f2e-8a56-b3876265ac79 |  | note | Specification Reference - NZTA B/5:2008, 7.9
label | 80556c65-371e-5520-bff8-1b7a3713aaa1 |  | note | Test Required - Not less than exisitng crossfall at the start of construction
label | 1ab420ef-a48f-56b9-81f1-299e322a372a |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | dc906c92-03d8-59a1-b59e-931d35ff99e5 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 87495094-110d-5458-9862-8593fd9fa3bb |  | note | Measuring Devices or Method - Stringing, Tape measure
label | b2c23006-f25c-5505-8b1e-965b6e9b2bf7 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Surface finish
label | de6165fb-4ab2-5c4a-b251-47e8ddc45abf |  | note | Specification Reference - NZTA B/5:2008, 7.10
label | d26739eb-e00b-5cb9-a602-4f3f42852e52 |  | note | Test Required - See clause
label | ad6879ce-f1a7-5fb4-ab86-88e34ad0712a |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 83b781ba-951c-510c-ae61-3e256041a63c |  | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | a2b01da0-3af3-5e2c-8f1b-469be3add62e |  | note | Measuring Devices or Method - Visual
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
checkpoint-no-status |  |  | checkpoint | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
checkpoint-group |  |  | section | Chipseal Construction (NZTA P29)
checkpoint-status |  |  | checkpoint | Ensure appropriate TMP used
label | 2146abda-5e3e-5833-8dc0-a60dde1cee00 |  | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint-status |  |  | checkpoint | Seal design
label | de864163-0592-595c-9ba1-42e07fc0eb18 |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | dfd1a5a4-c782-5bcf-8a9f-a6ef5256c167 |  | note | Task Assigned To - Project Engineer
label | c8cb05dc-fd9f-5eb8-a735-2c09867cc3ca |  | note | Criteria - Seal design to be reviewed prior to surfacing
label | 81ed2747-6e19-52d8-b34f-209f76934b4d |  | note | QA Form - Seal design template
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Location/Size Confirmation
label | c27aa341-412d-5116-b57d-32ba6be352bf |  | note | Specification Reference - Mark up extent of chipseal
label | fdd52201-3dd9-580e-8f1f-964d33f497b7 |  | note | Test Required - Prior to surfacing
label | b3451788-d922-587b-8fc0-a409d5dba38a |  | note | Task Timing / Minimum Task Frequency - Project Engineer
label | a78d289b-e18a-5417-bef8-18e9d4a34da7 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Surface Cleanliness
label | 1d9d21d3-54ce-5efe-92c0-efd96471f1f1 |  | note | Test Required - Visual Inspection
label | e9518a19-e67c-5dd3-9181-4486a869eb79 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder
label | 2d03562c-3681-5a7d-9c90-f16e09c4541a |  | note | Task Assigned To - Site Foreman
label | ad746014-fdee-5539-81fd-ecac4d4f9631 |  | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | 0ca43e9f-ea99-5639-80bc-9a19c221b560 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Plant Resource
label | 93a16345-13c0-5a3d-af25-38bba297a2e6 |  | note | Test Required - Visual Inspection
label | da556196-4f6e-5943-a9cd-9e539389036b |  | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | eeb77bc2-d784-5a97-9017-8f6f2e74c128 |  | note | Task Assigned To - Site Foreman
label | dd277c7e-7042-513f-a94f-b8b5c23b2694 |  | note | Measuring Devices or Method - Visual
label | 3e2938e1-216b-5f86-8e8c-46640ed269cb |  | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | 3fd31a18-d5ce-54a7-9c8f-05b76146499f |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Binder Application
label | e003997c-edb4-5353-9c24-6b241d08093f |  | note | Test Required - Binder type, Cutback, Temp, Application rates
label | 9b5bfa33-37d3-549c-bbad-3b89b39505aa |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | 77a431cb-0edd-5af2-9d37-3e22e55a8b37 |  | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | ae9fa691-1fc1-589b-9bfb-d83a6311d934 |  | note | Measuring Devices or Method - Visual
label | 34128450-3c8d-51a2-a115-e5db8c72d0be |  | note | Criteria - Binder Type = 180/200.
label | 5edb08d7-5a38-5e03-96f5-d35aee2cadf2 |  | note | ○ Cutback to suit 1st coat seal 4pph kero max.
label | 8c67bcbb-1a90-5e68-8995-900e15873f15 |  | note | ○ Temp = 150deg celcius min
label | 572bbeeb-ca3e-5391-bdf2-4e1a6509d7cb |  | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
label | cc6a0100-9e76-506a-bb27-c6d4e6063be5 |  | note | QA Form - Bitumen Spray Sheets
checkpoint-status |  |  | checkpoint | Chip Application
label | 36f3c615-452e-5cce-81a1-49cdbf6b516b |  | note | Test Required - Chip type, Chip Application
label | 3a4f2716-0452-5ce8-aa81-fbe32293aa6e |  | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | 1fe48731-3d48-5b73-bab6-54342dbaea4b |  | note | Task Assigned To - Site Foreman
label | 324e4d1b-f478-518e-92a7-4fc52bc31711 |  | note | Measuring Devices or Method - Visual
label | 50490e24-906a-5bcf-bab6-2fcf92ee1e6b |  | note | Criteria - Trucks loaded with correct chip.
label | 09da1baa-36b0-597c-b822-3960dd28f5b5 |  | note | ○ Chip clean. (G4/6 Racked example)
label | ca001fd1-a151-5146-bc34-e6c2b530b3f9 |  | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | f45225cf-5cd0-502c-a1dd-f40498abbfea |  | note | ○ G6 application = Enough to just fill the voids around the G4.
label | ed9ae10e-be48-5cbf-8dc2-f545d1382e66 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 7ae03ee1-4d24-5d45-add7-d1b17155c513 |  | note | Test Required - Visual
label | 9f3e2039-717b-5df1-a462-aebc22bbfef3 |  | note | Task Timing / Minimum Task Frequency - At completion of rolling
label | f98b3b2d-1af0-52c2-b7ac-3a22461c4a6c |  | note | Task Assigned To - Site Foreman
label | 2e3ccb98-e74a-55af-ba31-d31b7a1341ba |  | note | Measuring Devices or Method - Visual
label | 860a0677-66f0-5e99-b92b-38e38fb3803f |  | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 23b2c3b2-62dc-5f63-9eb7-1068abafb490 |  | note | QA Form - 'QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Site Measure
label | ff7b7667-b59f-5cef-88c3-5fa05bbb9414 |  | note | Test Required - Record final site measure
label | ec08eb82-baeb-54c2-9302-2bebabb34918 |  | note | Task Timing / Minimum Task Frequency - Completion of works
label | ce21673d-83de-52a7-b467-64a6990b65b5 |  | note | Task Assigned To - Site Foreman
label | 30cfd6da-961c-563b-b8be-3367177ee57f |  | note | Measuring Devices or Method - Measuring Wheel or Tape
label | b53a3264-a650-564c-95bd-aaed90039460 |  | note | Criteria - Sketch and record seal area and QA detail
label | f0de65c0-c15f-5b34-b31c-40107aacb82a |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Post Seal Care
label | 77f6d138-a5ce-54e9-8c41-787916c56f1d |  | note | Test Required - Visual inspection
label | 1c370494-fadc-5c61-8e93-69913acf8e1e |  | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | 3bd7336b-3e26-5ca9-877f-41b532c0ff72 |  | note | Task Assigned To - Site Foreman
label | 8a937b3d-0b92-51ed-b566-d93f39e10dd1 |  | note | Measuring Devices or Method - Visual
label | 523e9f5d-ce3f-56a9-9dd6-96941a7cc0ce |  | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | 87e3f05b-2bbb-5532-acf3-2bd74711117f |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Chip Removal, Pavement Marking, Traffic Services
checkpoint-status |  |  | checkpoint | Removal of excess chip
label | 6a2c5d23-b527-5474-8591-bbff12384482 |  | note | Test Required - Visual Inspection
label | eb889dfd-92d9-5568-bc2c-2267ae032ae5 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 2b0d87a0-5d50-5de1-babe-315d332cb16d |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 1bc321ad-a13e-5f24-826b-2ea0e648ec8d |  | note | Measuring Devices or Method - Visual
label | 38aa8270-3fcc-5a2d-9eb2-d8c53ce4c337 |  | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 486e487b-46b5-5824-88fb-85b764abef23 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Pavement Marking
label | f35e2458-3c43-512e-97ab-8cd96fd64eac |  | note | Test Required - Visual Inspection
label | 60e036a4-b110-5eb7-aaa6-5ea06cf3906f |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | b98114fd-0b99-5301-8065-faa092b1e81f |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 447ef6ce-e718-52a7-8e3e-ea5eaaca830e |  | note | Measuring Devices or Method - Visual
label | afe0daaf-597a-555c-9312-11292b6d326b |  | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | 4844ad4b-5549-5e4c-8e49-e4c52b96bdc2 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Removal of TTM
label | 024ed583-2ed8-5ea3-9396-c5d1105c4a78 |  | note | Test Required - Visual Inspection
label | eecca2e9-b120-57e8-a9f6-bab96c4eaba8 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 83fb1299-c7b5-5029-90d3-a8938327472a |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 7ea5adc0-f6c1-5efe-aa58-61be1b487f9f |  | note | Measuring Devices or Method - Visual
label | f5f31f81-2176-5d74-9c8f-1b5ce057df12 |  | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | e11ce5e1-8ae4-571d-852a-18c527317426 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Traffic Services
label | c6912911-6e0c-5814-b02a-95f4da573499 |  | note | Test Required - Visual Inspection
label | 72df5ee2-b260-52ca-bcd9-d4f65effdb4a |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | cbd67f70-9bcd-56fb-942e-e4047fbf94e8 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | c959752f-d752-5b9d-a683-97ae93dd94c2 |  | note | Measuring Devices or Method - Visual
label | 2c236bd7-df83-5e19-8b5f-354524cadd9e |  | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | 34fdcc20-6fc6-5ae2-b218-54bd8a50de70 |  | note | QA Form - Daily Diary
checklist-sectioned |  |  | checklist | 9. HB AWPT ITP - Clarkesons Hill B |  |  |  |  | Yes | 9. HB AWPT ITP - Clarkesons Hill B | 1befbfab-ae0f-4f03-97c8-c117516162f3
checkpoint-group |  |  | section | Preliminary / Establishment
checkpoint-status |  |  | checkpoint | Establish TTM
label | b1ee275f-d68c-5a15-8b4f-9eb843baaa97 |  | note | Test Required - Visual Inspection
label | cc45ea55-b359-50a5-b25f-c6e3cda87c5c |  | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | c9b857aa-78c7-5057-9da9-0a30104a1e01 |  | note | Task Assigned To - STMS/Site Foreman
label | a19d51b3-7f5d-56e1-b416-7dfe7a04daa0 |  | note | Measuring Devices or Method - Visual
label | 26c4e8ff-3660-5076-89c6-ffd587d46736 |  | note | Criteria - As per TMP and ensure TMC advised in advance of works.
label | a73d15a9-718c-550f-ad1d-90b4fb2774f7 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Permits
label | 797d8d37-ae6a-5d48-a890-d62a4ec628e4 |  | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | 34b45fc5-4a92-589d-a0b2-a92c3f7bc28e |  | note | Test Required - Document Review
label | ce9a748b-69d3-5b72-a8b3-e5fa33b0f2e3 |  | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | 06001c79-ad87-5b6f-a0f3-c8c79987924e |  | note | Task Assigned To - Site Foreman
label | 779601ea-8775-5dd3-a6e6-6d033ec28906 |  | note | Measuring Devices or Method - Visual
label | e4fd2055-ba90-5a23-9ae2-fbf19b6ff110 |  | note | Criteria - Obtain permits and mark outs prior to construction
label | 5615b212-298c-5436-a622-32b2bdf00307 |  | note | QA Form - Copy of Permit on site
checkpoint-status |  |  | checkpoint | Clear-Shoulder and Side drain
label | 31f0ba43-8185-5365-8fa5-8c7d6742b90d |  | note | Test Required - Visual Inspection
label | 1f6baeca-1b21-5dd3-8a69-dc440c92b783 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | c3d039a8-6ac7-5a11-9feb-eeea2b4f1bf3 |  | note | Measuring Devices or Method - Visual
label | 3833a2ae-0b20-573f-979a-9ca4fe23615a |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Digout Failed Areas
label | 330b1799-cf26-57c1-89b5-7e5588d21faf |  | note | Test Required - Visual Inspection
label | 7140b887-51b9-523a-8bfb-0e26b7ae631c |  | note | Task Timing / Minimum Task Frequency - As Requested
label | 2e36ec08-03f4-5f59-842f-1659c10179a2 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | ccca1dcf-5684-5cf8-8d54-831bbbf9b404 |  | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | fd0e0abb-74b4-514f-ab73-d6eaaf1efe6d |  | note | Criteria - Backfill with Basecourse
label | 86817d81-4732-58b5-a492-14166a58c6c1 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Kerb Construction
checkpoint-status |  |  | checkpoint | Basecourse layer construction (1)
label | 51786667-4add-5489-a0f9-2b329bada835 |  | note | Specification Reference - TNZ B/2
label | bef97d1d-5047-58f0-a827-8ae0d82cece8 |  | note | Test Required - Level and alignment
label | 0a83f13f-25e7-5e01-bd23-e7041e0a7f9e |  | note | Task Timing / Minimum Task Frequency - Every 20m
label | 41dbf942-adfb-55ce-8ebc-c9a6eb7fa172 |  | note | Task Assigned To - Project Engineer
checkpoint-status |  |  | checkpoint | Basecourse layer construction (2)
label | 730f58fa-c9ef-5520-bc30-8f282dc6ec6b |  | note | Specification Reference - TNZ B/2
label | afa09493-08c2-5b12-b9c6-7bb93f387912 |  | note | Test Required - Compaction
label | 06005127-32af-51d2-b286-bdb402f20e7a |  | note | Task Timing / Minimum Task Frequency - Every 20m
label | 17596aed-cc4f-5473-ab86-a6c47a0ae320 |  | note | Task Assigned To - Project Engineer
label | 5a86da7b-0c3c-58df-b021-631b5028e1bc |  | note | Criteria - 25min on the 4th drop
label | d1db1b61-eed6-5170-81e6-6122ff0c805c |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Kerbing
label | 54ebaeff-9c0b-57c9-8ee9-c6cd56a1524e |  | note | Test Required - Set-out level and alignment
label | 2211e0dc-9454-5d86-808f-da74fbe877a9 |  | note | Task Timing / Minimum Task Frequency - after base construction and prior to placement of concrete
label | a08633de-a222-5ace-ac0f-dfb516deac6f |  | note | Measuring Devices or Method - survey check
label | a614b784-39a2-58f6-9641-3fcdce81faf3 |  | note | Criteria - Horizontal: ± 20mm, Vertical: ± 5mm
checkpoint-status |  |  | checkpoint | Concrete Works
label | 433d5c21-7396-58eb-8f80-d491a344a8ea |  | note | Test Required - 20MPa
label | e0197a9e-23d2-52f4-8af5-b21bf1fbcce4 |  | note | Measuring Devices or Method - Copy of delivery docket
label | fc9bf63a-258c-5ee4-9db7-1d9bb5116e7d |  | note | Criteria - 20MPa, 28days
checkpoint-group |  |  | section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint-status |  |  | checkpoint | Cement for stabilisation
label | 2ad08ba9-b80b-5024-b7da-fa5ed7aa758b |  | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | 0fd58c7a-9f02-526e-b431-a00cb6dc672c |  | note | Test Required - Certified in accordance with NZS 3122
label | 15b8e0d8-cddb-592d-8ca0-31a40277bc1c |  | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint-status |  |  | checkpoint | Production plan
label | 679f0f4a-4f4d-5a03-80b1-c0531698b56c |  | note | Specification Reference - NZTA B/5:2008, 7.2.2
label | 1d89444e-5f42-502f-9296-417724bcee7a |  | note | Task Timing / Minimum Task Frequency - 1 per site
checkpoint-status |  |  | checkpoint | Stabilisation mix properties (including cement):
label | a3b9bdc9-373f-586c-a3e6-31f3feb547ab |  | note | – Maximum dry density (MDD)
label | ee2936d2-ace9-51da-b537-1985402c1c20 |  | note | – Optimum water conent (OWC)
label | a3ac339f-c315-50bf-9cc0-2a79d1312fc1 |  | note | – Solid density (SD)
label | 0f7fe82e-04f0-58b7-bde9-6e39f35ee745 |  | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | d202e947-3c80-536d-9633-c65dcbb7d0a3 |  | note | Test Required - Material properties for compaction verification
label | 20c1ab2a-0aef-56af-8565-08598239b9c8 |  | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | 9015b414-c465-5876-9d3b-ff0c21c7f6a0 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 9b20592f-af19-5b3e-b430-a919f4572f22 |  | note | QA Form - QA Measurement Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | In-situ moisture content of existing pavement aggregate
label | 3cf8e55f-7dc0-545e-b358-bbc10ef44b71 |  | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | e0f27768-9cbc-5304-9154-9902d012742a |  | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
label | 8e4e9390-dbe3-5293-856a-4c71f8673a17 |  | note | Task Timing / Minimum Task Frequency - As required
label | eaedc41a-8a78-5c73-8880-02c8db7d5579 |  | note | Task Assigned To - Inspection - Lab
label | 17643378-7b0f-5ce2-a7f0-fc0c2ce2e113 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Top-up metal
label | 10d31154-a15e-5527-b033-74fbf70df0af |  | note | Specification Reference - TNZ M/4 Table 4
label | a117fd17-8687-5f8d-8b82-ec4d5c46f3f9 |  | note | Test Required - Placed to required depth and design levels
label | 34b0c081-33a5-55cc-a2fc-9365b64202f5 |  | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | e023d2bd-71b1-51a9-b715-1bdc8f10c3f8 |  | note | Task Assigned To - Site Foreman
label | 58e0fa60-f098-5741-b034-a50aafd8a62e |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Cement spreading
label | a82b0bd0-3c92-5351-b7b5-33a3fb0026b0 |  | note | Specification Reference - NZTA B/5:2008, 7.3
label | 8b6eab63-8584-5676-86a1-6eb8d9721a7b |  | note | – Mat test (1m2 canvas mat)
label | 4f3516a9-e9c1-50be-bafc-82d4610453ff |  | note | – Average usage test
label | 20a1cf54-1782-593e-a685-fa5145bc653d |  | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | a95af12b-2c3e-5df5-b815-81c7ae745bc7 |  | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
label | 51469bc9-5f52-5948-9597-d4a07ed7b36c |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 588b3de1-e86a-5e72-8dda-eedf907cf6d7 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | In-situ mixing - Cut depth
label | ebfbd6f4-0fc8-548f-ab12-4dd6a654e730 |  | note | Specification Reference - NZTA B/5:2008, 7.6.1
label | 8d6a15d4-aef7-5501-9a77-d0379392f281 |  | note | Test Required - Maximum variation -5mm and +15mm
label | 47a513d4-05ce-5219-89da-74c7692a5e1d |  | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | 493aef0c-1731-5bda-a079-d760057587d9 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 3755a873-ff39-5727-8b30-0693eea84db2 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 2098663b-00c0-563d-846c-b7857cb11793 |  | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
label | e76824cc-334b-51e8-b70a-70001cf6536e |  | note | Test Required - Plateau testing
label | 21a097fc-5d9f-5a90-a7c7-dcbe80d1fca3 |  | note | ○ Mean value ≥ 98% of MDD
label | e222b39c-4cbf-5c79-bbed-d24cd99242a7 |  | note | ○ Minimum value ≥ 95% of MDD
label | 2eea8749-be22-5bad-b19c-5d761c5b2a6f |  | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | 06e9407c-5a15-56db-a0e0-0d89a28621fd |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 7ec2146e-5b79-5598-bfc9-d78e4d6fecb8 |  | note | Measuring Devices or Method - Nuclear Densometer
label | 0e6ae2a8-425c-562d-bc7c-735745441370 |  | note | Criteria - Minimum value 95% of MDD
label | f61d0771-f266-5b82-b8a7-ebe0b850035b |  | note | QA Form - Test Reports
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape
label | f0544342-d1ff-58df-b842-0a77bd3d88ef |  | note | Specification Reference - NZTA B/5:2008, 7.8
label | 92f9b985-2423-5356-bfd6-1ec23b8dc1ab |  | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
label | 49dfa3d5-123e-5d7f-baab-c75c89079c40 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 48f292f2-f89b-53e0-b3fa-196faa13cd95 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 9733c92b-8e73-5a18-8693-3842f2135243 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | 90581362-fd2f-5e4f-a3ae-c2fb919e7b8c |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Crossfall
label | f2736107-f4be-58d4-9eba-5bc77fdcf12a |  | note | Specification Reference - NZTA B/5:2008, 7.9
label | e60bb7ce-b31b-5190-a7e8-6446b453ba17 |  | note | Test Required - Not less than exisitng crossfall at the start of construction
label | 2cf47544-4a0b-53fc-ba28-67a76f0c48b3 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | fdbc0f02-d785-5a6d-9476-a76a79dc256f |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 1229e09f-c197-52f3-8e4b-725315bfc538 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | 58376b49-4a1f-5dcb-a190-14db3fef263d |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Surface finish
label | fba67fa2-7f68-5a74-9846-142d37bacf40 |  | note | Specification Reference - NZTA B/5:2008, 7.10
label | d2fc8324-4850-530e-9053-2c87f0eea876 |  | note | Test Required - See clause
label | 3578229c-1b1e-528a-bc52-422eb824eb7b |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 60c62e4c-b913-52d0-86ae-71f36c896613 |  | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | fe13580b-e6cb-5e21-ab43-b62f2312327f |  | note | Measuring Devices or Method - Visual
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
checkpoint-no-status |  |  | checkpoint | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
checkpoint-group |  |  | section | Chipseal Construction (NZTA P29)
checkpoint-status |  |  | checkpoint | Ensure appropriate TMP used
label | fe34aa32-7fe0-5c3f-9bab-814b73aacb22 |  | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint-status |  |  | checkpoint | Seal design
label | dc4d656f-0d64-539d-bd53-856923aae1ef |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | 8b7917e3-9bdd-59f5-a345-c8a0b2ead699 |  | note | Task Assigned To - Project Engineer
label | 05d80574-2915-538b-a05b-eb543df0e497 |  | note | Criteria - Seal design to be reviewed prior to surfacing
label | adcce0a0-bb40-5a5b-8502-3b68b609bb81 |  | note | QA Form - Seal design template
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Location/Size Confirmation
label | d1359f13-8d85-54a2-8033-e5e4632410a6 |  | note | Specification Reference - Mark up extent of chipseal
label | cc681d30-14d1-5119-8824-f29edd484898 |  | note | Test Required - Prior to surfacing
label | b0f13e91-54dc-5818-9e7f-e180b00c4a71 |  | note | Task Timing / Minimum Task Frequency - Project Engineer
label | 70480d72-0c4c-53bc-8868-665f55e11b49 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Surface Cleanliness
label | dab9deb3-ee10-510c-9ef0-5a9fa933f292 |  | note | Test Required - Visual Inspection
label | b56bd97c-206a-5448-90b4-ed2f71b5f71e |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder
label | 25a63ad9-772a-5d1c-bff8-6038971c80b3 |  | note | Task Assigned To - Site Foreman
label | 91fe74e3-751e-520a-a006-1cd02a79df63 |  | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | 463cca6d-ecb6-5e9a-a624-822e4990cd3d |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Plant Resource
label | 07e4c6fc-ee8e-528e-a3bf-e1661cf2caa5 |  | note | Test Required - Visual Inspection
label | 986f3681-791b-506c-83e4-1a5d386908f5 |  | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | 2f5ad221-6d72-5d6d-8676-afe0bf6d7e75 |  | note | Task Assigned To - Site Foreman
label | 51306215-6156-5988-aeca-65e0b0d3a073 |  | note | Measuring Devices or Method - Visual
label | 03c96a4d-5453-5e15-9919-10f4b2f412fb |  | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | 11e2de61-6acc-5b5f-ae06-14323df95a36 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Binder Application
label | c3d6a0e5-c5dc-5063-af4a-e70b53e5f46b |  | note | Test Required - Binder type, Cutback, Temp, Application rates
label | c88a08b8-393b-518e-bbc5-8c0d755dbdf1 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | 3a0ea77d-fd15-5428-bc94-6e1a49bf1ee6 |  | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | ee855ee6-0d0d-50f7-9723-7dd15d268952 |  | note | Measuring Devices or Method - Visual
label | 9e54687b-e4cb-52a9-9feb-a583a7a0bf6d |  | note | Criteria - Binder Type = 180/200.
label | 40f2a9ed-2c71-524f-a4f7-b0c4d6ad97fc |  | note | ○ Cutback to suit 1st coat seal 4pph kero max.
label | 4de4c0d0-f31c-5e68-b0f0-5522a99160d7 |  | note | ○ Temp = 150deg celcius min
label | 6ddecb33-eaf5-5f68-966a-7c76dabde708 |  | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
label | 8e37cdff-8aca-5223-b328-f3c2f9a409bb |  | note | QA Form - Bitumen Spray Sheets
checkpoint-status |  |  | checkpoint | Chip Application
label | c0daf26c-9d4f-56dd-80da-0093965b6fc3 |  | note | Test Required - Chip type, Chip Application
label | 12af4c35-9566-50b6-b12a-7b192a09cce8 |  | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | 4ac622c9-0e59-5436-a30b-2a5386f33a19 |  | note | Task Assigned To - Site Foreman
label | c304d81a-bc65-5363-9a4b-d819b5298bc6 |  | note | Measuring Devices or Method - Visual
label | cc60b74a-f4ad-5ab1-a5c2-8112a61642a7 |  | note | Criteria - Trucks loaded with correct chip.
label | 2e7755df-9c49-52ee-80ac-23618ad936fa |  | note | ○ Chip clean. (G4/6 Racked example)
label | 6e4903f7-21b5-5d7f-a364-d92329e86f96 |  | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | bacda8ee-b51b-535a-98f0-cee412ccf278 |  | note | ○ G6 application = Enough to just fill the voids around the G4.
label | a3428f22-8328-5b68-9520-758f83d7fe22 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 34b83295-6d7a-51a2-94dd-43924dd3068a |  | note | Test Required - Visual
label | 73d28dd0-4399-579e-bfbb-17d8f633515d |  | note | Task Timing / Minimum Task Frequency - At completion of rolling
label | 5f00c11c-e8e2-5443-ac40-e03850d5047e |  | note | Task Assigned To - Site Foreman
label | 5f80a280-9a55-503d-b119-7fd27a7d5092 |  | note | Measuring Devices or Method - Visual
label | ad17ebcd-dfc0-5353-aa49-2a83b9a88d9c |  | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 66b62776-4004-5fd3-92e1-06d4e72a38bf |  | note | QA Form - 'QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Site Measure
label | f45bc688-dde1-539d-a849-e0a7d8a9cf84 |  | note | Test Required - Record final site measure
label | 8733bfe5-7d4c-5ae2-a79a-011b80a56c81 |  | note | Task Timing / Minimum Task Frequency - Completion of works
label | e6119e66-1b70-5e20-851f-f4dc6e66b55b |  | note | Task Assigned To - Site Foreman
label | da74d426-6f9d-50ac-a009-54ddec84bb53 |  | note | Measuring Devices or Method - Measuring Wheel or Tape
label | 3e5333bf-986a-5064-a1f0-4031c0d02fe0 |  | note | Criteria - Sketch and record seal area and QA detail
label | f5743024-b44a-532d-b33a-1f714a239894 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Post Seal Care
label | 3467dda1-e3cc-5e8f-9656-af460d01c1a0 |  | note | Test Required - Visual inspection
label | fbb02145-c28e-55cd-bdd2-82a6aac0cd06 |  | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | 2a74346d-7989-56fc-9e71-f627b9c5b6d4 |  | note | Task Assigned To - Site Foreman
label | 15456b4c-123f-5362-9324-3d0139abbd99 |  | note | Measuring Devices or Method - Visual
label | 9d250803-2ef4-58e3-b68a-5c5bcbab0eaf |  | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | a021b707-3530-5243-9f85-33bba6062cf4 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Chip Removal, Pavement Marking, Traffic Services
checkpoint-status |  |  | checkpoint | Removal of excess chip
label | 9eaf77ff-9a8d-5641-a8b6-59559d7ae3a7 |  | note | Test Required - Visual Inspection
label | 2281c306-59c2-5f52-b2b2-4e266cc73b51 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 0302a3f1-0bf8-50ef-a139-9086088bcf74 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | edf6f64d-f442-597a-a177-7e221abdc87d |  | note | Measuring Devices or Method - Visual
label | 20cb17dd-1061-50b2-aebc-753ba326d4b8 |  | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 4a47c2d2-0745-59b2-bde3-3ca31b0e1169 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Pavement Marking
label | 72a3dde1-a6c8-5946-8c24-f029a3ded53a |  | note | Test Required - Visual Inspection
label | b1c22dd5-66a8-585a-9916-6ca2584bb982 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 3fdc306f-c62a-56f2-8538-418ad570145b |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 31edeb95-d7d2-5169-895a-6a915baf16dc |  | note | Measuring Devices or Method - Visual
label | 84b58c17-ab98-516e-a69d-bdf4ca542585 |  | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | 7a434c10-3a22-5ea2-a7ff-78240231150c |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Removal of TTM
label | 5db4ba89-93d6-5cfc-aae1-d6698e06d034 |  | note | Test Required - Visual Inspection
label | 611fe62c-413f-5b38-91f5-30d85dab5656 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 2a31521f-5f9b-556b-a783-81e120ef9e59 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 658f1e06-71ca-5149-b4bd-869bb5d52ee9 |  | note | Measuring Devices or Method - Visual
label | 3edccdf4-748b-5b88-8aca-8860753e91fb |  | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | 5b983245-49c2-51a2-8dcd-328d10dfaff7 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Traffic Services
label | 9d424ffc-5e5d-5f60-9d18-7870edec8a34 |  | note | Test Required - Visual Inspection
label | 20b11828-4bc3-5e10-a11e-1d57f27ea3b4 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 0e347011-bc30-5905-87fe-1335971216af |  | note | Task Assigned To - Project Engineers/Site Foreman
label | daf241bb-bc55-5433-bdf4-9afbda5bc7f7 |  | note | Measuring Devices or Method - Visual
label | b31d95b0-794b-5252-ab40-9c3c713d7145 |  | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | 8ee6cd32-acdc-560c-8a41-1a108ecc8f68 |  | note | QA Form - Daily Diary
checklist-flat |  |  | checklist | Verified Program |  |  |  |  | Yes | Verified Program | 4031e91b-ef8c-473e-8e03-e3b98a769670
checkpoint-status |  |  | checkpoint | Verified Program
checklist-sectioned |  |  | checklist | 1. HB AWPT ITP - Nth Rakaipaka |  |  |  |  | Yes | 1. HB AWPT ITP - Nth Rakaipaka | 5229d904-5dd5-414a-940f-1ceeb7f613d6
checkpoint-group |  |  | section | Preliminary / Establishment
checkpoint-status |  |  | checkpoint | Establish TTM
label | 2346e8e4-c7fb-5b41-afb3-de1f177ed1e4 |  | note | Test Required - Visual Inspection
label | f9a34cc8-c9ba-5681-a603-e15c7c5155ca |  | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | 07e3ffa5-c8cf-5127-bcfc-63ec4e00f690 |  | note | Task Assigned To - STMS/Site Foreman
label | 04209cc9-5caa-59ee-b666-92f2bf7fdf2a |  | note | Measuring Devices or Method - Visual
label | 4dec6e74-ebeb-50b7-bca2-dea1483513ee |  | note | Criteria - As per TMP and ensure TMC advised in advance of works.
label | e4a44636-9b69-5c5e-8c93-e20d144379df |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Permits
label | 509533f9-3b95-58b6-b4eb-d1fa8bcdf108 |  | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | 6100b311-96ca-5347-8af2-5e0874cc1c6b |  | note | Test Required - Document Review
label | 8c5ab6e3-cb0c-5312-bbb8-fbcbc6e6c1ad |  | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | e9589a34-2639-519e-90ea-00243c515515 |  | note | Task Assigned To - Site Foreman
label | 80e1c81a-78b1-5fa8-a80e-40ff6c0e947b |  | note | Measuring Devices or Method - Visual
label | 9a0138bd-fcc2-58d9-8708-c26635d641b7 |  | note | Criteria - Obtain permits and mark outs prior to construction
label | 1597436b-2d87-59af-b416-d94dcef3b74f |  | note | QA Form - Copy of Permit on site
checkpoint-status |  |  | checkpoint | Clear-Shoulder and Side drain
label | c185533d-fe02-58cd-a94d-1c1d927f04e1 |  | note | Test Required - Visual Inspection
label | adab292e-d0d9-547d-911e-663da7cb4a7e |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 1d93f184-5cd0-5876-bf27-4e219c6b4363 |  | note | Measuring Devices or Method - Visual
label | 8fdc9879-3a5d-5bc9-abc9-397a93012c78 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Digout Failed Areas
label | 542c5bf1-af60-5a0f-89c4-80341ec7fff6 |  | note | Test Required - Visual Inspection
label | eb8e03f7-c1de-59b2-ba83-a4aff1d458eb |  | note | Task Timing / Minimum Task Frequency - As Requested
label | cfa993b8-56f5-5892-91d3-f529435f083b |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 0029a368-4ffc-5af1-bcaa-d61790420b4c |  | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | 62245261-9e82-548d-adcf-028af1f68616 |  | note | Criteria - Backfill with Basecourse
label | b0cb6e09-acd8-56c6-ab5d-a969f223a2c1 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint-status |  |  | checkpoint | Cement for stabilisation
label | 2d3c0755-008f-58a2-9bb4-f4f9ca5547da |  | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | d05ae5b7-0350-5579-b20b-ac8fa1560a11 |  | note | Test Required - Certified in accordance with NZS 3122
label | a9cf6809-6da5-5861-8144-9b5af8f503a1 |  | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint-status |  |  | checkpoint | Production plan
label | 3859bc1f-e976-5f94-8dd7-5bf8f6d16c6f |  | note | Specification Reference - NZTA B/5:2008, 7.2.2
label | bd00eeba-6c7f-59c8-8456-5470471fe6fa |  | note | Task Timing / Minimum Task Frequency - 1 per site
checkpoint-status |  |  | checkpoint | Stabilisation mix properties (including cement):
label | 932b13e7-c0af-5457-81e8-c5ae834749b6 |  | note | – Maximum dry density (MDD)
label | f16b471a-86ae-5ab9-98b1-962cb2b0701d |  | note | – Optimum water conent (OWC)
label | 8a94ae39-86d0-5f40-9052-e0a2c6b2616c |  | note | – Solid density (SD)
label | 333716e0-dc14-5610-b118-22f8ae7ad7f3 |  | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | 43dae03b-b69e-5011-81a1-58dfdf2ca1b4 |  | note | Test Required - Material properties for compaction verification
label | 5e5d5d19-bbb7-5f08-8582-81957852db6e |  | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | 743feb28-8864-50ba-85b3-3c8e73a91513 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 407d4ee8-3e8f-5c95-b7ee-67a59104574a |  | note | QA Form - QA Measurement Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | In-situ moisture content of existing pavement aggregate
label | 33678cc3-f3b8-50b2-a1c3-5c708710d585 |  | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | 1807703f-1866-5660-8a5f-eaf977f1e191 |  | note | Test Required - In-situ moisture content Between 90% to 100% of OWC
label | 7f71072f-581a-5682-97ed-a15241f3be90 |  | note | Task Timing / Minimum Task Frequency - As required
label | df47c37d-d585-56ee-a7ee-33241209d343 |  | note | Task Assigned To - Inspection - Lab
label | d4252f1f-39aa-575e-9cb1-45f080d8f0f2 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Top-up metal
label | e8c9707b-89e7-5ad6-8280-8636e3dce2d9 |  | note | Specification Reference - TNZ M/4 Table 4
label | 1426a3a0-d141-593d-852d-1b5e53a408f0 |  | note | Test Required - Placed to required depth and design levels
label | 82c97a50-690d-50b0-9f5e-bcbb8ed4940c |  | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | db47c239-9591-5f96-9a34-88d7f1c17c2b |  | note | Task Assigned To - Site Foreman
label | db3114ed-6acb-505f-9444-f0c45c45f63a |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Cement spreading
label | 3b13c9f5-2af0-5c1e-be38-b41b9a4383c9 |  | note | Specification Reference - NZTA B/5:2008, 7.3
label | 605f4392-2a1e-5a5d-96e7-fffb389ca39f |  | note | – Mat test (1m2 canvas mat)
label | c7695b9a-dc64-59c4-aed9-52bf2d60d3ef |  | note | – Average usage test
label | 04aef123-aaab-5164-b65e-392646551efc |  | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | 1e167dff-44ea-585b-86b5-b1c95bc2d46b |  | note | Task Timing / Minimum Task Frequency - Inspection & sign off by Site Supervisor
label | b62e5c1b-b233-5851-be6c-776632478cdd |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 2662eafd-e94e-5c11-8547-b6010766428c |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | In-situ mixing - Cut depth
label | d806b182-88cb-51a7-a807-da5ce03bd164 |  | note | Specification Reference - NZTA B/5:2008, 7.6.1
label | 50bc4b34-dd24-598b-8958-63d6cea4e225 |  | note | Test Required - Maximum variation -5mm and +15mm
label | 7f1b3697-1778-5d6e-b3d2-85fca075131c |  | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | bd591b59-1f93-5163-bbff-df869bc3ca9f |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | f2661985-3f6b-5b29-ae64-523b8b4c8b77 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 0963015f-c6c8-5e2c-9d47-fe16fbedc568 |  | note | Specification Reference - NZTA B/5:2008, 7.7.1 NZS 4402 Test 41.3
label | 264eccbd-bbe2-5c73-9e5c-60a378c7299f |  | note | Test Required - Plateau testing
label | a200c8fa-bb86-5919-944c-68b58bf793ec |  | note | ○ Mean value ≥ 98% of MDD
label | fd1173c5-492f-5b28-b49f-71aa27bb6d51 |  | note | ○ Minimum value ≥ 95% of MDD
label | 8e28baf1-0cab-55ff-8635-7eee6cf5e3a3 |  | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | e40d9ce9-b575-55dc-90a4-b1749351ef5d |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | b29fd211-211a-55a9-86da-a53f189fad03 |  | note | Measuring Devices or Method - Nuclear Densometer
label | 532ff4da-7519-5d73-9ab7-ec93d7c9c5de |  | note | Criteria - Minimum value 95% of MDD
label | 90f99efe-8590-5307-bcc7-66bbfa12e340 |  | note | QA Form - Test Reports
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape
label | cbef2b1a-3a06-5102-9ded-0809a638a7c2 |  | note | Specification Reference - NZTA B/5:2008, 7.8
label | a30a3ce0-677f-537f-bda1-7fda4160df2b |  | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
label | 88e919b1-f8ba-54fd-a888-274293d4e6e9 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 644c7dfc-9195-5f85-a6ff-7a5e1bb09a75 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | b54f7e08-4ea3-557f-bd03-eac8610fef71 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | ffe779a9-99cd-5bf8-8472-f0249a46cad7 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Crossfall
label | 56d3a123-4161-5321-ae4d-1b0722f0df1d |  | note | Specification Reference - NZTA B/5:2008, 7.9
label | 5c16cecf-20e4-57e8-8a97-d2ad01f98496 |  | note | Test Required - Not less than exisitng crossfall at the start of construction
label | b5cfe9fe-dae2-5865-97a7-33c1b9b94e57 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 864b1392-84a9-5295-9be9-6a6819350b7b |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 7e5dd190-566c-5c05-a0d7-019959ae9be6 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | 8159318d-6ba1-5315-9088-7a37f023a107 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Surface finish
label | 38de163d-1adf-5aeb-9601-62e4c045a1d1 |  | note | Specification Reference - NZTA B/5:2008, 7.10
label | bebc45cc-f73d-5107-8442-c5d617de3ba3 |  | note | Test Required - See clause
label | a548da74-2fe1-5fd2-87ea-4e8f18a3d9fc |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 19ad890b-bf15-52bb-87b1-bd2a9040111e |  | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | a505d190-1e43-55a9-be24-a481eed833a5 |  | note | Measuring Devices or Method - Visual
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
checkpoint-no-status |  |  | checkpoint | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
checkpoint-group |  |  | section | Chipseal Construction (NZTA P29)
checkpoint-status |  |  | checkpoint | Ensure appropriate TMP used
label | b5df889d-6ce7-591a-aefa-a3e8fe3973cd |  | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint-status |  |  | checkpoint | Seal design
label | 932f78d5-11dd-58cb-a65f-5e14597bee16 |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | aec675aa-e450-56bc-bab2-5a1b4d34ebb9 |  | note | Task Assigned To - Project Engineer
label | 023c01b3-ffcb-5770-ab2b-a9aaa3925bed |  | note | Criteria - Seal design to be reviewed prior to surfacing
label | 1ef0ddc2-320a-56a8-9cbb-b5f49e6bbc88 |  | note | QA Form - Seal design template
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Location/Size Confirmation
label | d815ab07-9ee0-57ac-b2c8-a4f1e3b8c151 |  | note | Test Required - Mark up extent of chipseal
label | 4cf920f9-921b-54f1-a481-78a2ae40a1b1 |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing
label | 35a49727-7162-5d88-a243-1d49f005e998 |  | note | Task Assigned To - Project Engineer
label | f5b201e2-2644-57aa-8d6f-cb5507ac7ff1 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Surface Cleanliness
label | eb53f897-d775-5f8c-b95d-40029d97f96f |  | note | Test Required - Visual Inspection
label | a852a750-81b1-5a2f-9b36-9c6de2487139 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder
label | 8d226232-5668-50bd-a8ac-d7d8f45f8fe0 |  | note | Task Assigned To - Site Foreman
label | 21a2187a-1740-58fe-8e17-bb780e4640f6 |  | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | 7df651f5-6a55-5ca5-a9b4-29abaaa8bcae |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Plant Resource
label | 36a1f0d3-39c9-58c2-88bf-656a3454280b |  | note | Test Required - Visual Inspection
label | 7fcc09ff-cb36-5db2-b95d-0df375a1c799 |  | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | 25b9b0d9-16be-5d66-8aee-c2920a3c8a55 |  | note | Task Assigned To - Site Foreman
label | 23913796-c0ea-5bc5-aeb0-26e656a04c3a |  | note | Measuring Devices or Method - Visual
label | 0d405182-a9cb-57b7-a008-ac19e0ba68e6 |  | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | 0683dd3f-7464-5ca8-8edd-f7eae01955f9 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Binder Application
label | 0bd41cc1-45c3-5396-9663-4a48d9037b4b |  | note | Test Required - Binder type, Cutback, Temp, Application rates
label | 3392ddaa-0b9e-53e5-8149-c15b6b398139 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | bd24ee15-4c32-5fde-8e2f-f894d5722994 |  | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | ffd31dcb-4912-5924-a1c8-0df92da3cacb |  | note | Measuring Devices or Method - Visual
label | 8692977a-4c6b-5d04-abaa-460168dd7876 |  | note | Criteria - Binder Type = 180/200. Cutback to suit 1st coat seal 4pph kero max. Temp = 150deg celcius min, Application = Design l/m2, +/- 0.1 l/m2.
label | 16d2a7b7-8e33-5c13-9d9a-c32528cf4d43 |  | note | QA Form - Bitumen Spray Sheets
checkpoint-status |  |  | checkpoint | Chip Application
label | 82d0a6ea-e3b3-5da3-954b-82abfc2522f0 |  | note | Test Required - Chip type, Chip Application
label | 69cdf642-1788-50bf-ac68-8a40ce8b2c8b |  | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | 79ab55ac-3b00-532d-9314-5215bfa964df |  | note | Task Assigned To - Site Foreman
label | 8b3a75d0-c2fb-56cf-bc8e-304ad7e499b5 |  | note | Measuring Devices or Method - Visual
label | 96354846-e730-55cd-b35f-906cb3f1c3ad |  | note | Criteria - Trucks loaded with correct chip.
label | 98cc0c9b-7ae5-5501-9bc7-231749971228 |  | note | ○ Chip clean. (G4/6 Racked example)
label | 89e5234d-1ea3-5882-8859-abe4e6b6fbe7 |  | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | 763345c1-c5f9-5dd9-ae90-e05929715cdc |  | note | ○ G6 application = Enough to just fill the voids around the G4.
label | 09ec7806-0258-5de2-8a6e-e7e9ae5c8cbb |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | d88dfdab-b3ed-5541-b141-3d86d767ac58 |  | note | Test Required - Visual
label | 1a591eca-fd2e-5c83-9149-53497430cb3c |  | note | Task Timing / Minimum Task Frequency - At completion of rolling
label | 7bb589fb-095f-55ad-8393-b45258e0324e |  | note | Task Assigned To - Site Foreman
label | 4dd35467-3e80-5343-b2d8-4bacce5c2fef |  | note | Measuring Devices or Method - Visual
label | 84fb1976-59e4-582a-9a77-6d1dcda63b88 |  | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 28ab5d1f-ce52-56c8-aa81-b66130d2fb8a |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Site Measure
label | 2521a57a-066e-5e33-969f-a6e5001b2537 |  | note | Test Required - Record final site measure
label | e8ce2965-dc27-5ffb-8592-c8ff649dcb7e |  | note | Task Timing / Minimum Task Frequency - Completion of works
label | 3244e567-6cb1-5dd7-ada6-54adbe6e2326 |  | note | Task Assigned To - Site Foreman
label | bd32e130-b935-51ef-a226-9e7e47911732 |  | note | Measuring Devices or Method - Measuring Wheel or Tape
label | d863103d-da95-5365-85b6-a18b80f13f72 |  | note | Criteria - Sketch and record seal area and QA detail
label | 16d0b647-9476-58e8-b788-f76385b1f6e0 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Post Seal Care
label | a63f63eb-ec6c-5ade-93b4-5b3e6bf7bf58 |  | note | Test Required - Visual inspection
label | de203a03-4f85-56f3-925f-45e40a72d315 |  | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | ee5c2a90-ea46-58b4-af05-2863fbd33f8a |  | note | Task Assigned To - Site Foreman
label | 33d4803a-ebb4-5e6b-bf8a-2ad08135573c |  | note | Measuring Devices or Method - Visual
label | 5368a926-78e2-5167-88b4-74fada5fd994 |  | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | cd4e02cc-2c48-5f42-a9ac-d5ce5523570a |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Chip Removal, Pavement Marking, Traffic Services
checkpoint-status |  |  | checkpoint | Removal of excess chip
label | 72b3381f-1a06-5a86-ae48-207cddff1906 |  | note | Test Required - Visual Inspection
label | 08c61188-cb2d-5351-bdca-61137efa4bdc |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 4b98b978-1df2-5d77-ac5d-6af3b7723222 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 650563e2-d19c-5c1c-87dc-48520a10c474 |  | note | Measuring Devices or Method - Visual
label | be0399f1-514b-50f2-bfe4-fce800aab142 |  | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 4d449fbb-f0bd-5506-9146-9ab81755b85a |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Pavement Marking
label | e916876f-24f9-5c73-a6ea-19f238d117fb |  | note | Test Required - Visual Inspection
label | 7916175f-93b6-5b99-beb3-8185f5e9dedc |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | fa1e8f6d-2638-50ea-bfab-49655da2cd04 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 6c497c2d-0772-5af7-8e50-0654b7a60472 |  | note | Measuring Devices or Method - Visual
label | a696641e-9ce4-5f74-a8d7-61ee0992c715 |  | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | 00afd4a4-f0d8-5b7e-93af-de89d9e57f9a |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Removal of TTM
label | dabee641-5b3c-5133-be2a-6e62601a55f3 |  | note | Test Required - Visual Inspection
label | 36ebfc46-e74e-533f-896e-badec09d4f3b |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 2814bb41-d20e-5753-a29b-ee808efb0214 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 3bb7b767-1710-5c67-9744-27d9a10e9c9c |  | note | Measuring Devices or Method - Visual
label | f2ae9bb6-2811-54ff-890c-be5cff4704c8 |  | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | 13842ba9-e3e2-5868-9a87-05bf259d6820 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Traffic Services
label | e2784b90-dd4b-5be3-8e61-da315cadb3d0 |  | note | Test Required - Visual Inspection
label | f706ad98-3802-5b2b-a510-c180c43675c5 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | f9f87f9f-9006-555f-8edb-c7b42acc8ef8 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | cc2cb8dc-66ac-50cb-9b30-05399192bfe9 |  | note | Measuring Devices or Method - Visual
label | be518738-34e4-58d9-b66a-819507f2b14b |  | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | 28066207-6c35-5856-8759-825ad8bfa8a1 |  | note | QA Form - Daily Diary
checklist-sectioned |  |  | checklist | 6. HB AWPT ITP - Nth of Waione Bridge |  |  |  |  | Yes | 6. HB AWPT ITP - Nth of Waione Bridge | 54adc08f-bf54-4de4-8154-ae208e12713d
checkpoint-group |  |  | section | Preliminary / Establishment
checkpoint-status |  |  | checkpoint | Establish TTM
label | 38d9a751-bb54-534e-b8d5-c63aeb68ee3a |  | note | Test Required - Visual Inspection
label | ed8fe355-b711-5b30-8fcb-df3ba0df4033 |  | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | eeea2cb5-6a24-5000-8f5a-c88d1f0e23b6 |  | note | Task Assigned To - STMS/Site Foreman
label | 3c7b36c2-9cce-5564-8bdd-ba439606a2a1 |  | note | Measuring Devices or Method - Visual
label | ef04f272-1fd0-51a6-8bbb-b9e2409da624 |  | note | Criteria - As per TMP and ensure TMC advised in advance of works.
label | 3c46f11a-68ac-5a06-affc-ff826fe932ac |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Permits
label | 6d20d895-3d12-5283-97ea-23802ef7d9dd |  | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | 62d65d6e-ab09-5688-8c85-588968de595d |  | note | Test Required - Document Review
label | e844dc36-6786-5102-91bd-ff5e3a13cbe5 |  | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | 21786bd6-6b5c-5203-b606-7e55c6041472 |  | note | Task Assigned To - Site Foreman
label | 31e0de35-0a91-5e55-9b29-265f9b77a079 |  | note | Measuring Devices or Method - Visual
label | d8d52c64-79d5-5567-9f8f-3a16694a6a11 |  | note | Criteria - Obtain permits and mark outs prior to construction
label | 4c28e2e7-2deb-5e5b-a40b-9690846e0eaa |  | note | QA Form - Copy of Permit on site
checkpoint-status |  |  | checkpoint | Clear-Shoulder and Side drain
label | 5778fbe3-c6ac-5552-942b-54a92ae00b9c |  | note | Test Required - Visual Inspection
label | 1d31aff9-3b90-5d99-80ea-3a91d242e443 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | eb2be1ea-d2c9-5e3f-aeea-eb2fd56adb00 |  | note | Measuring Devices or Method - Visual
label | 6a29dd35-9901-5fb1-acf4-9abdbb8a8486 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Digout Failed Areas
label | ce29fc28-570c-5f04-9871-93e152d9b129 |  | note | Test Required - Visual Inspection
label | fee47c67-b1e3-5931-b055-4f5290613ab0 |  | note | Task Timing / Minimum Task Frequency - As Requested
label | 83ea561a-a11e-56be-9eff-fbfd0930f239 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 25bd2da9-656f-538f-8c78-623354f67665 |  | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | 830ff297-abf6-5c62-9093-c60d92b3cab6 |  | note | Criteria - Backfill with Basecourse
label | c89e998f-e980-5c7a-a99e-683cce6b0c56 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint-status |  |  | checkpoint | Cement for stabilisation
label | 53430fa4-7f77-50f8-85c7-0d37fb39e9c5 |  | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | 0dcd4ed0-c426-5e33-bd79-366820f3dd2d |  | note | Test Required - Certified in accordance with NZS 3122
label | a678e196-abc9-52f0-9ee3-1bbe425f86cc |  | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint-status |  |  | checkpoint | Production plan
label | 26140ea8-7985-5fd4-8114-a32d98ffbf5c |  | note | Specification Reference - NZTA B/5:2008, 7.2.2
label | adc08a4f-95ca-5c01-a58d-8d124fc8edc1 |  | note | Task Timing / Minimum Task Frequency - 1 per site
checkpoint-status |  |  | checkpoint | Stabilisation mix properties (including cement):
label | 35c9d167-448b-5979-b548-0c32c52c1d81 |  | note | – Maximum dry density (MDD)
label | cf3783b6-ab21-5bf5-a783-d1d6ef370607 |  | note | – Optimum water conent (OWC)
label | eefd2679-41de-5823-8cfe-82cc645a803d |  | note | – Solid density (SD)
label | aa2ff381-eed7-50a4-a5d7-06c6a9840be1 |  | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | 9ac6296f-53b8-513e-87b2-9f4086569b69 |  | note | Test Required - Material properties for compaction verification
label | ea8e9578-4433-5b7e-b737-dce0bd3687bc |  | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | f28f717a-d1d9-5817-8583-7d1d40a6019d |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | e4ce7070-8e67-543e-88ba-dadec32270e5 |  | note | QA Form - QA Measurement Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | In-situ moisture content of existing pavement aggregate
label | 7247f360-89ee-5655-8cbe-39b225ce226c |  | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | 8cc10f80-948a-5734-9cb0-b14fe3b27141 |  | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
label | bc10c98a-95e5-5688-aad9-cda64322aaf7 |  | note | Task Timing / Minimum Task Frequency - As required
label | 91f58eb3-409a-5a82-a636-03f48160b967 |  | note | Task Assigned To - Inspection - Lab
label | 77614e93-241e-5c36-a822-7c663ebada4d |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Top-up metal
label | 0ccbed2b-c0e1-51c5-b5d1-18f80c210d97 |  | note | Specification Reference - TNZ M/4 Table 4
label | f89beff0-624f-5894-b365-7706e43eeacd |  | note | Test Required - Placed to required depth and design levels
label | 9a7dde5f-d167-518d-9c21-69b8096fb8cd |  | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | 07f89223-29df-5d6e-9f91-757af2498567 |  | note | Task Assigned To - Site Foreman
label | 74e67f79-7d75-51c5-8ced-5a8c9357ed7e |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Cement spreading
label | 7d34751e-d72b-5fb8-8238-6c54b0a28688 |  | note | Specification Reference - NZTA B/5:2008, 7.3
label | 3208117e-9bf7-584c-9a76-2cbf2f89ac43 |  | note | – Mat test (1m2 canvas mat)
label | 1fbac610-74ac-5b47-9501-9b511b30c5a2 |  | note | – Average usage test
label | 1946b65b-0160-5580-b215-a7a28620c92e |  | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | 37478768-39ac-5c71-ad35-099fe76f1849 |  | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
label | 6d17fb88-edf8-5c1b-8d53-6393536c04de |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | e19e75db-d5c2-57f5-93bb-e7610d2556c1 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | In-situ mixing - Cut depth
label | 65f11e5c-0e8c-5fb3-953f-d7d51d7098ac |  | note | Specification Reference - NZTA B/5:2008, 7.6.1
label | ad0a933a-0e1f-5bcc-ba1d-05b37a097fa7 |  | note | Test Required - Maximum variation -5mm and +15mm
label | ceae56f6-7df0-57e3-8059-5447b68073b1 |  | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | a6231344-03d5-5ee3-b0dc-1725bf824367 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | e3afb3db-292e-5060-9e5b-8d92bc989e83 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 5a301811-7790-59f5-a5a3-526dd24eedd9 |  | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
label | eeb6323b-8d45-5dc7-9af2-16648679fdc2 |  | note | Test Required - Plateau testing
label | dc26cc31-ddaa-5045-a70c-8a7341d2245b |  | note | ○ Mean value ≥ 98% of MDD
label | edb485cf-78c7-5b37-9912-08756d50d3a4 |  | note | ○ Minimum value ≥ 95% of MDD
label | b49d5b1c-540d-52bc-aa9e-195569022eeb |  | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | 1360da9c-aa8a-51b1-9466-4a3f6bd4def5 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | bbf325ae-515e-5d3b-990b-e6ec1ddc737e |  | note | Measuring Devices or Method - Nuclear Densometer
label | 3fcd3648-5278-5a2e-a773-c3634126eaaa |  | note | Criteria - Minimum value 95% of MDD
label | dcfab9b8-b540-5f2e-b6b4-540053b14e82 |  | note | QA Form - Test Reports
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape
label | 1c5f9c0d-680c-5c62-ace6-392d948ae546 |  | note | Specification Reference - NZTA B/5:2008, 7.8
label | ec4238b5-02e8-596e-9a76-271b087b4a08 |  | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
label | 0afd0d70-cdd4-5b41-bf0e-89c85fa51ab9 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 3a3ba271-c201-52ca-a5be-64e651878b83 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | fe47eb8d-9f35-57cd-9023-6493f260a712 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | ff0d3795-6a0b-514b-b164-688af956af27 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Crossfall
label | 3b9de9e4-50c8-5549-b1d4-40b9148ed0f1 |  | note | Specification Reference - NZTA B/5:2008, 7.9
label | a9bdfb51-028b-58b2-bfb9-8f5ecf163652 |  | note | Test Required - Not less than exisitng crossfall at the start of construction
label | 297ee8a1-c393-5993-b2d6-e3920126cd50 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 4aa45d2e-05ce-5346-9823-328c8cc26d8a |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 011b0f29-4b57-596d-bb70-5187fad27266 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | 4890b899-572f-5571-83c4-67710206f13f |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Surface finish
label | 9ea988dc-4c01-5be3-b035-36235fb5f07a |  | note | Specification Reference - NZTA B/5:2008, 7.10
label | 36c2a529-5f61-5d1a-8e74-26b86eb2f97b |  | note | Test Required - See clause
label | 5baaeff9-fb66-5018-9052-9465caca2331 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | d34d2fd3-3ff5-5d2b-9450-ddddbd4c34b7 |  | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | d9e2db30-4bb9-5488-a084-c521460b2b42 |  | note | Measuring Devices or Method - Visual
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
checkpoint-no-status |  |  | checkpoint | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
checkpoint-group |  |  | section | Chipseal Construction (NZTA P29)
checkpoint-status |  |  | checkpoint | Ensure appropriate TMP used
label | 84f51587-3292-5a95-b118-f432d4fad642 |  | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint-status |  |  | checkpoint | Seal design
label | 57b89ce8-4957-53a5-a05d-286ce3b9cc79 |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | 46e37d65-67e2-5888-839c-ef766cd7b03d |  | note | Task Assigned To - Project Engineer
label | 2fb7259e-0012-5d1e-9014-ca3ade8d2b88 |  | note | Criteria - Seal design to be reviewed prior to surfacing
label | 60084855-19d1-57dc-acb6-443acc1d2d06 |  | note | QA Form - Seal design template
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Location/Size Confirmation
label | 3247cd18-5d89-5512-803e-0cae8649db73 |  | note | Specification Reference - Mark up extent of chipseal
label | a5cc1917-8312-5901-8f19-d998bd80ffe7 |  | note | Test Required - Prior to surfacing
label | ce3f9973-00c9-5a39-878d-9c3151215421 |  | note | Task Timing / Minimum Task Frequency - Project Engineer
label | 1278892d-9274-5d29-8ac2-59ec026767f3 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Surface Cleanliness
label | 5bfe132b-14b7-50f4-a8eb-540dc80dddd7 |  | note | Test Required - Visual Inspection
label | 9443a80f-30f3-58dc-97a6-218de27646a8 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder
label | 7ac9813a-7c00-5fd7-95cf-c8cb65ecfdbe |  | note | Task Assigned To - Site Foreman
label | 0569fcb4-9410-5d6a-9bc8-72218593f7ba |  | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | f79cf4f5-7c7d-5956-a09c-758f77da6ec8 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Plant Resource
label | 320ceb20-ab7a-538c-9956-bd39f28cdc0e |  | note | Test Required - Visual Inspection
label | 0d7a1c3a-bac3-5058-9b61-de7098a1bb6e |  | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | e2de6435-cea9-5ceb-b0d6-32b29f99e779 |  | note | Task Assigned To - Site Foreman
label | 4a24acd1-82a4-5e32-b7bc-591c4c302f9c |  | note | Measuring Devices or Method - Visual
label | 9fb33ce8-8f5c-5502-b8e7-d80303883100 |  | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | 67577120-da7c-5413-9539-d2fd7ff4d5a7 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Binder Application
label | bdcce479-ab53-5253-bf3e-ccea91f82f8f |  | note | Test Required - Binder type, Cutback, Temp, Application rates
label | 7a31b4a6-a7dc-51c5-ae6b-1bcf2f8e7806 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | 9202987b-e12c-5cfb-8111-412dd065c181 |  | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | b17c3ff7-2575-530b-a9d9-fa1854522952 |  | note | Measuring Devices or Method - Visual
label | fa96ba39-78a9-52dd-9460-f68c519507bd |  | note | Criteria - Binder Type = 180/200.
label | 0b8f03a0-c84d-5003-bb8d-0ad76f45a8ca |  | note | ○ Cutback to suit 1st coat seal 4pph kero max.
label | e0dd6147-e262-5954-9a94-89b24e8cb66c |  | note | ○ Temp = 150deg celcius min
label | 9311d1c2-3734-5516-9adc-94f81a0039c6 |  | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
label | 6381c34e-fd59-5574-968a-5a1c95d7f894 |  | note | QA Form - Bitumen Spray Sheets
checkpoint-status |  |  | checkpoint | Chip Application
label | 1d942dcc-5a48-5255-90fc-7c9828b1b169 |  | note | Test Required - Chip type, Chip Application
label | 75563529-6155-5143-9b25-e91f9a929c80 |  | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | 897a98b4-5e47-59ae-941e-2c702d1e7b66 |  | note | Task Assigned To - Site Foreman
label | f721e793-5d54-56f7-96c8-fef5e789e518 |  | note | Measuring Devices or Method - Visual
label | bb79996f-8a9c-5a84-8617-bf1edb56335c |  | note | Criteria - Trucks loaded with correct chip.
label | cffa1cc1-48f2-511d-b522-9cdd44589276 |  | note | ○ Chip clean. (G4/6 Racked example)
label | 0a063d3c-0a91-5283-bb9d-6c6451ffde0a |  | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | 7bde1a68-6473-5d3b-af2f-d2c5802aa8e3 |  | note | ○ G6 application = Enough to just fill the voids around the G4.
label | 96595aa6-5062-55ff-a6ac-1ce4e9aa6eec |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 14a66912-dda8-54f8-a023-40e09cba41e7 |  | note | Test Required - Visual
label | 288d6889-2dd1-5973-a0af-e19d1954b51d |  | note | Task Timing / Minimum Task Frequency - At completion of rolling
label | 1138f4a4-21f3-5893-a82b-b009cb13bbe8 |  | note | Task Assigned To - Site Foreman
label | 11c1df9e-bdf0-59bc-b912-31a5ce2663a0 |  | note | Measuring Devices or Method - Visual
label | 91d1b185-aa2a-5519-91b7-ee2760226f19 |  | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 85a1a6fa-80e4-50a9-8cdc-65031f8fb053 |  | note | QA Form - 'QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Site Measure
label | 9e9089d4-8939-5076-b268-b015f84013b2 |  | note | Test Required - Record final site measure
label | c711cb7a-5da6-5003-9cee-a32f1c942263 |  | note | Task Timing / Minimum Task Frequency - Completion of works
label | 0b23aa7a-6a18-546e-882d-b25aa55536a9 |  | note | Task Assigned To - Site Foreman
label | a006b963-0bfd-5c7c-9c45-fd90a2451d9d |  | note | Measuring Devices or Method - Measuring Wheel or Tape
label | fba6e9ab-fa37-595a-8b2c-df46fdd16cf4 |  | note | Criteria - Sketch and record seal area and QA detail
label | 8a597c6b-001c-5d0c-a09a-c7e3017036ce |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Post Seal Care
label | ec5bddbc-ea9f-5588-bdc1-807b99d0c3ee |  | note | Test Required - Visual inspection
label | 4405e873-0f03-5dbe-91c8-db6900ff6098 |  | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | 25da6529-5275-5fe8-bf3b-e80ecedce2f7 |  | note | Task Assigned To - Site Foreman
label | 702c69e1-b0c6-5fd0-813e-9556a8a0ece2 |  | note | Measuring Devices or Method - Visual
label | c515a892-da8d-5f03-b1c3-d9d941bdd260 |  | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | 4c35fa18-4771-554d-944c-2243d60ba1af |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Chip Removal, Pavement Marking, Traffic Services
checkpoint-status |  |  | checkpoint | Removal of excess chip
label | e5c51db8-7dbc-51f1-ae9d-bc53cc6e44c3 |  | note | Test Required - Visual Inspection
label | c2cdad7f-155b-5622-89af-fbc6c5c845d5 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 05ec0b81-812e-5caf-a04e-230e415a3b12 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 7727649b-628a-5512-b75e-c82c56ffcb5a |  | note | Measuring Devices or Method - Visual
label | 05b27c11-6499-566e-9919-41c8091608c4 |  | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | a4366244-d03a-500b-a104-6213ef3c0189 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Pavement Marking
label | 39417e24-e4d2-538d-9e66-2514c242794a |  | note | Test Required - Visual Inspection
label | a3a620b0-c2ed-53af-b7aa-904da73f2b5b |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | c7581edd-37ea-5d2e-bc14-04875ac7826a |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 7e0da1b2-6f50-5837-8298-d83464cc594e |  | note | Measuring Devices or Method - Visual
label | b1c46ad4-6df0-5dda-ad69-0f2ad9c01fe0 |  | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | 25f9b1c3-b46a-5385-8fb6-fe71190dada7 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Removal of TTM
label | 4d6ec002-ea5c-51ed-9792-17c972f8ef69 |  | note | Test Required - Visual Inspection
label | 58697d87-c5f9-58fb-8459-a842a1545416 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 23a1c201-cdf3-5f1f-b363-68a84aa0e819 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 20de402a-12f2-51c3-abd1-006bc83af8be |  | note | Measuring Devices or Method - Visual
label | cc5a3294-7c46-51a7-bba5-ab4a54ab3776 |  | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | 6e71cb8e-bdff-544f-b506-42635565853e |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Traffic Services
label | 000fe201-64e4-546a-a804-c4ca2f95aae8 |  | note | Test Required - Visual Inspection
label | ffde1824-f216-5100-9387-1bf1ff960c75 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 98a1f0ba-d851-5afb-bd6b-daec4b80eab1 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 1e281de1-3c70-5891-bd00-93d7d019637f |  | note | Measuring Devices or Method - Visual
label | a0726351-caa2-5590-ae0d-e26d4b11a75a |  | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | 931cef85-90ea-5014-9929-4f023ced4b19 |  | note | QA Form - Daily Diary
checklist-sectioned |  |  | checklist | 0. HB AWPT ITP - Material testing |  |  |  |  | Yes | 0. HB AWPT ITP - Material testing | 6f0eff6d-fb94-4996-883c-3e6cf7dfade8
checkpoint-group |  |  | section | Basecourse Material Testing
checkpoint-status |  |  | checkpoint | Approved Aggregate
label | c017c45e-8ae3-5af5-ae1e-0ba4fe6c4834 |  | note | Specification Reference - TNZ M/4 Table 4
label | 3cf95b2d-a775-538f-894a-e3ad1c3a29de |  | note | Test Required - Grading
label | 0b9a8f3d-a9fb-5e76-a67f-411bcc12e27f |  | note | Task Timing / Minimum Task Frequency - 1 independent test per 500m3, prior to basecourse placement
label | b2dab19f-01f1-5f43-a7c0-a7cc1a45d702 |  | note | Task Assigned To - IANZ accredited laboratory
label | 9150971a-6824-5833-9051-f1e70cd69df8 |  | note | Measuring Devices or Method - NZS 4407:2015, Test 3.8
label | f5ee4eed-1783-50cf-b656-592431211b12 |  | note | Criteria - Napier River Gravel
label | 654a2ea8-5799-5f66-8b5b-e336ece54d02 |  | note | ○ 78-100% 26.5mm
label | ae9a531c-b73b-5437-9f04-721b42a602ef |  | note | ○ 13-25% passing 1.18mm
label | 9c3e6dd2-c614-5207-af63-2db46e1a4e33 |  | note | ○ 10-19% passing 600µm
label | 14fd0390-c81e-5426-b543-321b503d4ed1 |  | note | ○ 7-14% passing 300µm
label | 32347d23-dcec-565f-b0d7-4076567cd0e4 |  | note | ○ 5-11% passing 150µm
label | 824581e9-8ffc-52d1-ad73-1b5a5a613739 |  | note | ○ 3-8% passing 75µm
label | 6f1f7e98-3e0e-58a3-8645-225987bfe26e |  | note | QA Form - QA Measurement Sheet
checkpoint-group |  |  | section | Bitumen Manufacture
checkpoint-no-status |  |  | checkpoint | Note: These tests are reproduced from NZTA M/1 for information only. A copy of current approval letter will be required for each grade and source of binder used on the project to verify the binder is approved.
checkpoint-status |  |  | checkpoint | Penetration
label | 6179c817-5d35-5341-aaff-ead72d577e1f |  | note | Specification Reference - NZTA M/1 Table 1
label | 346928ac-ff67-5c8d-9775-f3bd34bb8ab2 |  | note | Test Required - Penetration at 25°C, 100g, five seconds
label | 25d5ac43-893f-5e92-928a-ae106beb2e43 |  | note | Task Assigned To - IANZ accredited laboratory
label | 9c3508e2-35c2-52de-b1da-f342a54b9022 |  | note | Measuring Devices or Method - ASTM D5
checkpoint-status |  |  | checkpoint | Viscosity (1)
label | 360b0a5b-72e2-5b50-af96-360bb42e5d2a |  | note | Specification Reference - NZTA M/1 Table 1
label | 522e6d56-3f25-581d-aa36-1c3e31b17190 |  | note | Test Required - Viscosity PaS at 60°C
label | f3df050f-d6f4-54e0-8405-f48d4d5e0013 |  | note | Task Assigned To - IANZ accredited laboratory
label | ef06f4b8-a792-5a10-b392-602648c4040e |  | note | Measuring Devices or Method - AS 2341.2 or ASM D2171
label | 6d614ecc-0d5e-5dc2-8384-3d8117e058a1 |  | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
checkpoint-status |  |  | checkpoint | Viscosity (2)
label | 7c625f0f-2628-5a45-848a-bab9d875ae16 |  | note | Specification Reference - NZTA M/1 Table 1
label | b5811269-afaa-541f-b3de-3d942a9ff1bc |  | note | Test Required - Viscosity mm2/s at 135°C
label | 5a95aede-b5c1-54a2-9654-5a759b5aefda |  | note | Task Assigned To - IANZ accredited laboratory
label | 0eaefcf1-efef-5161-b609-64f2b9bf4c75 |  | note | Measuring Devices or Method - AS 2341.3 or ASM D2170
label | b749a0f5-1b28-5d9f-b275-f2fc86690cf9 |  | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
checkpoint-status |  |  | checkpoint | Flash Point
label | 31fcb9d1-7eea-54d5-8d6a-6d24ef18c644 |  | note | Specification Reference - NZTA M/1 Table 1
label | 530fe060-2820-51b1-a009-aa105b443b7b |  | note | Test Required - Flash point (Cleveland open cup), °C
label | 90186177-0247-5b24-b563-f5da709ec26e |  | note | Task Assigned To - IANZ accredited laboratory
label | 9a65d397-2f20-5bd0-a943-571839ade8d2 |  | note | Measuring Devices or Method - ASTM D92
label | 8f44496e-ba26-5edf-bdcf-00c1a4f78f08 |  | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
checkpoint-status |  |  | checkpoint | Solubility
label | c4505d32-4a0d-5a47-9e43-83891bfb4abe |  | note | Specification Reference - NZTA M/1 Table 1
label | e571232a-6f95-51d0-8668-fb3dbbfaceed |  | note | Test Required - Solubility in Trichloroethlyene, % or Solubility in Toluene, %
label | fde38550-1b9c-5bad-a265-e29bdc597786 |  | note | Task Assigned To - IANZ accredited laboratory
label | ea69d6c9-d14a-5b0e-9e3e-5cf4e895ff49 |  | note | Measuring Devices or Method - ASTM D2042, AS 2341.8
label | 44913f61-54fa-5b1b-859b-ec9fecaaa363 |  | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
checkpoint-status |  |  | checkpoint | Penetration
label | d549c673-aefd-5b44-95b9-a9a90276f114 |  | note | Specification Reference - NZTA M/1 Table 1
label | 994fa4b5-506e-5e04-9526-2d2840b75e77 |  | note | Test Required - Penetration of residue, at 25°C, 100g, five seconds, % of original.
label | b1a62323-5111-52e3-8336-0e0e3a8695de |  | note | Task Assigned To - IANZ accredited laboratory
label | 425e7f7e-c965-54c0-b38f-4d7d499c1def |  | note | Measuring Devices or Method - ASTM D5
label | 52de6447-eda0-5b0c-99b6-c30abcbd4e60 |  | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
checkpoint-status |  |  | checkpoint | NZTA Approved
label | 1f589101-c5d2-53de-8269-e1d50e5ded41 |  | note | Specification Reference - NZTA M/1 5
label | ec289500-b296-5ced-9de8-77fd7c09fa6e |  | note | Test Required - Letter from NZTA
label | 135576f0-197d-5981-ac17-6edd1031bac1 |  | note | Task Timing / Minimum Task Frequency - 1 per source and grade of binder used
label | 4f80bb70-152f-50ea-bddb-b614e5a1ee9c |  | note | Task Assigned To - NZTA
label | 973f7b92-83cc-5dbd-934d-b8c58b356a5d |  | note | Criteria - Complies with requirements for penetration grade as per TNZ M/01 Table 1.
checkpoint-group |  |  | section | Sealing Chip Material Testing
checkpoint-status |  |  | checkpoint | Crushing Strength
label | 4f71f51f-e5d0-54e2-92c6-c819adb96843 |  | note | Specification Reference - NZTA M/6 3.2
label | b0a57ef5-b46a-5262-a4af-18442a8c26e7 |  | note | Test Required - Crushing Resistance Test
label | a934d8fa-1873-55c3-a041-dab8b3cdeb68 |  | note | Task Timing / Minimum Task Frequency - Once per year - 1 test
label | f4c62ad8-b3be-5ad6-8400-27aee43c6329 |  | note | Task Assigned To - IANZ accredited laboratory
label | 10200ec6-aee5-5029-a411-8950cbfd654d |  | note | Measuring Devices or Method - NZS 4407:2015, Test 3.10
label | 36cc1bcc-c0c8-5a44-8206-459b397a3106 |  | note | Criteria - <10% fines passing 2.36mm under 230kN load
checkpoint-status |  |  | checkpoint | Weathering Quality
label | 60532d02-2e0a-5a50-af48-6c8025311518 |  | note | Specification Reference - NZTA M/6 3.3
label | c4fe07af-440a-5c7d-998e-47b45c127ca8 |  | note | Test Required - Weathering Quality Index Test
label | 5e915326-569e-525c-8845-795039e55933 |  | note | Task Timing / Minimum Task Frequency - Once per year - 1 test
label | f1d3f483-db53-596a-9e8c-cff8da332d15 |  | note | Task Assigned To - IANZ accredited laboratory
label | c37de08c-1a07-5fdb-a730-9ccd74ff57f3 |  | note | Measuring Devices or Method - NZS 4407:2015, Test 3.11
label | 02a94bc5-4584-5bd7-8fcd-04ad00e8fdc4 |  | note | Criteria - AA or BA
checkpoint-status |  |  | checkpoint | Weak Particles Test
label | af28feb1-b9fd-5d80-be2a-2b8b6d442533 |  | note | Specification Reference - NZTA M/6 3.4
label | 9db43972-2677-5d5c-a7b4-91d032dae678 |  | note | Test Required - Australian Weak Particles Test
label | b9a0bab2-91f7-595d-a3ef-53cc30f3ad06 |  | note | Task Timing / Minimum Task Frequency - Only undertaken in case of dispute.
label | 69711a32-2ec4-5a40-b27c-1d7d5545c93c |  | note | Task Assigned To - IANZ accredited laboratory
label | ff50e7ce-7dd6-5246-b24e-e33d0e810ccd |  | note | Measuring Devices or Method - AS 1141.32-1995
label | 1829a69c-77f6-5ea3-b5e0-1dc4dc4a912a |  | note | Criteria - Maximum of 1%
checkpoint-status |  |  | checkpoint | Polished Stone Value
label | d3e4b7d1-c2f8-5f08-bd66-67fcff080de4 |  | note | Specification Reference - NZTA M/6 3.5
label | 3a83d399-ab91-5a24-ba4e-e8d1d31210d9 |  | note | Test Required - Polished Stone Value Test
label | 8ee42d69-43b4-5f19-b9c1-d4099000fe8d |  | note | Task Timing / Minimum Task Frequency - Once per year - 1 test
label | f8fcc0ca-cf13-5139-8db8-d9aba33d4226 |  | note | Task Assigned To - Accredited PSV Testing Agency
label | abc34548-a397-5ae6-8c86-2f8a160647ee |  | note | Measuring Devices or Method - BS 812 : Part 114
label | ff3f84b8-f6ff-51ad-99b3-61c4dfb8e54e |  | note | Criteria - PSV Required = 53
checkpoint-status |  |  | checkpoint | Cleanliness
label | c5c4da20-4665-577b-864e-69de67a09f7d |  | note | Specification Reference - NZTA M/6 4.1.1.
label | 09612193-458a-54e4-be93-9ef4921326b2 |  | note | Test Required - Cleanliness Test
label | ef2b9ef3-1596-5cbd-8f86-2e61996d788b |  | note | Task Timing / Minimum Task Frequency - 1 test per 500m3
label | 8706c9b2-8b10-5465-822c-4076b34bdfc8 |  | note | Task Assigned To - IANZ accredited laboratory
label | 2f65b834-f1b9-5c29-b2ea-005955d72060 |  | note | Measuring Devices or Method - NZS 4407:2015, Test 3.9
label | 8328f7e4-678c-53f3-98dd-ab012624fd36 |  | note | Criteria - Grade 3 - 87 min, Grade 5 - clean & free of soft, weathered, disintegrated or deleterious material
checkpoint-status |  |  | checkpoint | Size & Shape
label | 0e83be57-01a1-51fc-a3c8-0e356e2dc6ed |  | note | Specification Reference - NZTA M/6 4.1.2.
label | c4424ee7-128e-5b65-9ce1-987c8237a252 |  | note | Test Required - Size & Shape
label | 6aaf5de2-2868-5f15-af86-a9ec1ddde554 |  | note | Task Timing / Minimum Task Frequency - 1 test per 500m3
label | bed06d01-3201-5e7c-acea-7e7905698bf6 |  | note | Task Assigned To - IANZ accredited laboratory
label | d370c5ce-86f6-5024-8f95-d44a4600b00e |  | note | Measuring Devices or Method - NZS 4407:2015, Test 3.13
label | aeb7f533-fcf6-5800-8154-bf8fed924ec1 |  | note | Criteria - Grade 3 - ALD 7.5 - 10.0, 70%Min within 2.5% ALD
checkpoint-status |  |  | checkpoint | Broken Faces
label | bb4753e0-13a2-5929-a0dc-61496f4f9778 |  | note | Specification Reference - NZTA M/6 4.1.2.
label | b325156b-430a-50fc-95a5-4bf292cd78bf |  | note | Test Required - Broken Faces Test
label | b1f2d179-7537-57c6-b2b5-d7347c9f833a |  | note | Task Timing / Minimum Task Frequency - 1 test per 500m3
label | 928b259d-29f5-5871-91df-3ddb1ff43e3b |  | note | Task Assigned To - IANZ accredited laboratory
label | 9f8afcb3-aed5-5027-b42b-e78df0852083 |  | note | Measuring Devices or Method - NZS 4407:2015, Test 3.14
label | 27188844-b216-5a01-85f1-db3beb158c9e |  | note | Criteria - 98% with minimum two broken faces
checkpoint-status |  |  | checkpoint | Grading
label | 76e2708d-ed78-592e-91b4-0080c1da5a3c |  | note | Specification Reference - NZTA M/6 4.2.2.
label | d59a2369-8015-5537-88f3-1d1a1dedfaf5 |  | note | Test Required - Grading
label | cbf3bb47-9933-5b22-9f64-545cbe5e6c55 |  | note | Task Timing / Minimum Task Frequency - 1 test per 500m3
label | dddccb3d-5835-50c1-be6e-6ea2aa27174b |  | note | Task Assigned To - IANZ accredited laboratory
label | 18978e38-c1f8-5cdf-92df-9fa28e961540 |  | note | Measuring Devices or Method - NZS 4407:2015, Test 3.8
label | e6f92b91-b0d0-5164-b094-232186d7a3c1 |  | note | Criteria - Grade 5: 95-100% passing 9.5mm, 0-8% passing 4.75mm, 0-2% passing 2.36mm
checklist-sectioned |  |  | checklist | 7. HB AWPT ITP - Maori Gully II |  |  |  |  | Yes | 7. HB AWPT ITP - Maori Gully II | 73315b14-924f-4dab-8cf6-f73620b4e06d
checkpoint-group |  |  | section | Preliminary / Establishment
checkpoint-status |  |  | checkpoint | Establish TTM
label | 9e727d69-e6d0-5c15-b5fd-32fcc6e88d29 |  | note | Test Required - Visual Inspection
label | 452927ff-e8eb-5e11-a1d0-70b1bfaded73 |  | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | 9bb146c0-d2af-5eea-b19e-e79b7ee5516f |  | note | Task Assigned To - STMS/Site Foreman
label | 8a97edbb-0d75-5f94-aa75-4de275df4514 |  | note | Measuring Devices or Method - Visual
label | 1f53a997-cf46-523d-9437-7cde01b6ca99 |  | note | Criteria - As per TMP and ensure TMC advised in advance of works.
label | a0a1915d-6a1e-5b1e-be6c-3f521f5cb894 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Permits
label | 214e6942-2a7d-5f71-ab32-c2845937d59a |  | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | c49ea305-78eb-50a1-a761-40ff3874554f |  | note | Test Required - Document Review
label | c98e7472-20ce-55ed-b78c-2a26ae11074d |  | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | 5f2665ee-89c4-53af-b7be-178c0bfee858 |  | note | Task Assigned To - Site Foreman
label | b76679a4-4be6-57ea-a258-ca93fa370a6a |  | note | Measuring Devices or Method - Visual
label | f3c7b250-ca60-5b21-a484-15507719d077 |  | note | Criteria - Obtain permits and mark outs prior to construction
label | 63375072-db9d-523e-ab86-3bdda92b775e |  | note | QA Form - Copy of Permit on site
checkpoint-status |  |  | checkpoint | Clear-Shoulder and Side drain
label | 495d8504-de5f-5153-9f3d-9dcd19b85617 |  | note | Test Required - Visual Inspection
label | cce986d6-8585-5307-aa70-3ad7e33ea4ea |  | note | Task Assigned To - Project Engineers/Site Foreman
label | ccdb8f73-c74e-51cb-95dd-334a095e1853 |  | note | Measuring Devices or Method - Visual
label | fdfb7bea-ef97-5ebf-9ed3-f9d7b43fc54d |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Digout Failed Areas
label | 2942f81e-a0f1-50bd-a35f-6c872dbf8e19 |  | note | Test Required - Visual Inspection
label | 198cd783-5947-5c57-96cb-0169fa92c855 |  | note | Task Timing / Minimum Task Frequency - As Requested
label | a3bbd18b-5d75-5ebc-9aaf-7f3a8eab56a9 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 3049eb92-a325-5be7-b3fc-940a8797a536 |  | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | 53592d48-d13f-5a64-a83f-8d6d3941cb23 |  | note | Criteria - Backfill with Basecourse
label | 7024b36d-ec57-5ee8-80f1-cf428e46dbc2 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint-status |  |  | checkpoint | Cement for stabilisation
label | d6d75fef-8d13-555e-9c4c-aedd8790dc4d |  | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | f736fd03-5735-5e51-93e5-8ac54d245f5c |  | note | Test Required - Certified in accordance with NZS 3122
label | 657601a3-a596-5415-92eb-cb473a6a9c15 |  | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint-status |  |  | checkpoint | Production plan
label | 4499221e-d0ec-5e33-8de4-07bcbaff3fec |  | note | Specification Reference - NZTA B/5:2008, 7.2.2
label | 6fa55405-2b10-5392-93a6-50166813138f |  | note | Task Timing / Minimum Task Frequency - 1 per site
checkpoint-status |  |  | checkpoint | Stabilisation mix properties (including cement):
label | 3e6b7318-01b3-5ee5-94c5-285d40514d16 |  | note | – Maximum dry density (MDD)
label | 4136c32c-1c66-580c-8001-61d16c858b1d |  | note | – Optimum water conent (OWC)
label | 5cb7d2ff-145c-51a3-92f1-b986cdd8f508 |  | note | – Solid density (SD)
label | 5e8d775c-da37-574c-88e5-f83f33ab0649 |  | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | f1cf27d6-dcff-5779-9e2f-4dd28248306d |  | note | Test Required - Material properties for compaction verification
label | 71e2ec38-36f6-59cb-ad3b-511be806fc17 |  | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | ac73eaae-fbcb-5794-b0ef-1bb05fc1c8ad |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 9175c801-d476-525a-9a98-4b42e37a26a1 |  | note | QA Form - QA Measurement Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | In-situ moisture content of existing pavement aggregate
label | 9e66b795-eb9d-50c3-a83e-881ac67cee09 |  | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | a3711edf-8cea-53a9-85cf-b99f3f8d5b47 |  | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
label | 033c3441-9cb9-5111-8c1c-402ff81dd258 |  | note | Task Timing / Minimum Task Frequency - As required
label | 9b99a7da-63e4-563c-b884-726e151162a8 |  | note | Task Assigned To - Inspection - Lab
label | bd09d86b-148f-5386-b91c-d2b5bcdeee17 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Top-up metal
label | 9a8a3828-9d10-5048-be36-ae1c0d83bf84 |  | note | Specification Reference - TNZ M/4 Table 4
label | cd81896c-1f2b-552f-8316-2a532d7e34ed |  | note | Test Required - Placed to required depth and design levels
label | 5a12cb64-d970-5c6a-bb6d-1d6c1212cd25 |  | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | e7e0cfa9-d265-56f7-8dd2-fdd25854652a |  | note | Task Assigned To - Site Foreman
label | 5fc938e6-22de-5608-ae00-0aff594e5d7f |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Cement spreading
label | 627bf848-56fc-5f2b-9597-37afc94e2a04 |  | note | Specification Reference - NZTA B/5:2008, 7.3
label | a36ace53-ddda-52a0-acd2-861dfe9d1cda |  | note | – Mat test (1m2 canvas mat)
label | e6d03b99-eab8-5d9e-8944-798041b3ece5 |  | note | – Average usage test
label | 456bcdb4-6387-53ce-9487-b44722016805 |  | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | 663c2c92-e950-52bc-a8d6-d394a5c51f40 |  | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
label | 5d9dff98-931b-5ec2-a6ab-0ae4c5660b00 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 6b12f254-c937-57aa-a443-37310fe2b7df |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | In-situ mixing - Cut depth
label | a52fafa3-6132-5e1e-82f4-f9a160fdf074 |  | note | Specification Reference - NZTA B/5:2008, 7.6.1
label | d04e632d-a535-53f8-a3b8-f36d672dc60d |  | note | Test Required - Maximum variation -5mm and +15mm
label | 98ece1fb-ec29-5af4-b451-faec88f0d7a5 |  | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | 5c28fb65-8abb-5251-927a-2daec1984e5f |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | d059b241-4acb-569d-ad63-42b4945f5d6b |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | b5181747-d69f-55b0-bc44-f61c87e002fe |  | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
label | 01e80b6a-59e6-5fa2-86cc-3caa21e7cf18 |  | note | Test Required - Plateau testing
label | a5551f41-8b46-52da-9b28-4ae814d54b75 |  | note | ○ Mean value ≥ 98% of MDD
label | f8064a62-b66b-55b2-a2a9-1707c0da7139 |  | note | ○ Minimum value ≥ 95% of MDD
label | a026ece9-14b7-583c-91ff-7b34a84ea363 |  | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | 97d287f2-a93f-51a7-9357-3e4fcfd9b2e4 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 637606ee-9c8f-5041-a476-ac676e1d1bf4 |  | note | Measuring Devices or Method - Nuclear Densometer
label | ae5003d5-eb80-5e96-b233-af607447320a |  | note | Criteria - Minimum value 95% of MDD
label | e63f2b45-f4cd-58ac-8712-e1613cc8a396 |  | note | QA Form - Test Reports
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape
label | 27f5add4-837b-553b-8018-cc8f7987e957 |  | note | Specification Reference - NZTA B/5:2008, 7.8
label | 34652781-8c57-5e9b-a5b6-96c9906fd827 |  | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
label | 2ef8eaf6-0bb4-59c5-8d1f-62c563c68272 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | e0abb821-55df-5f89-a9dd-d2304bd048b5 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 485ab4c9-0e8a-5e67-8bbd-88469c24c9f0 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | 4a6cebdf-49df-52dc-92e9-0814a4853de6 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Crossfall
label | 36a030f6-0dc8-5256-8cc5-3763fa9d2430 |  | note | Specification Reference - NZTA B/5:2008, 7.9
label | fad195eb-8c5e-5da8-a60c-0e6fbd393a15 |  | note | Test Required - Not less than exisitng crossfall at the start of construction
label | 8e634981-6ef9-5475-89a0-5791c95f2f1f |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | a28a0011-3e7e-5eab-a3af-a72727f7eaa2 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | dbee86bf-a2ad-5053-87ad-22d646a5845d |  | note | Measuring Devices or Method - Stringing, Tape measure
label | 6b61478e-9dd6-565d-b815-1bfbf80aad49 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Surface finish
label | cc0b0195-d04d-559e-ba26-205962c78d4c |  | note | Specification Reference - NZTA B/5:2008, 7.10
label | 4783037a-0de5-503f-ab36-5f1d3f328ca1 |  | note | Test Required - See clause
label | 75cce73b-8daf-5ef0-821e-4e46668c6872 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | a5075f49-de10-5f2f-ad11-6f48023a8c2a |  | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | 5017875c-faf7-55bd-b1fd-b65a394aa0f1 |  | note | Measuring Devices or Method - Visual
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
checkpoint-no-status |  |  | checkpoint | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
checkpoint-group |  |  | section | Chipseal Construction (NZTA P29)
checkpoint-status |  |  | checkpoint | Ensure appropriate TMP used
label | fbbc7485-7643-59f4-b998-d2cebeac3a9f |  | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint-status |  |  | checkpoint | Seal design
label | 2573347e-06a6-5011-bd4a-1fcfdb9159fb |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | 28036359-c695-5611-8074-35379b8b8f14 |  | note | Task Assigned To - Project Engineer
label | 31f19ff0-e08b-5b6e-9dae-74e4aad625c2 |  | note | Criteria - Seal design to be reviewed prior to surfacing
label | 966d3014-7d93-5977-a6d2-45c813533173 |  | note | QA Form - Seal design template
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Location/Size Confirmation
label | 0d5a0481-1d89-50ef-baab-b2468f3afe8f |  | note | Specification Reference - Mark up extent of chipseal
label | 8f995ebb-7321-5f3b-9568-e5e37c56af13 |  | note | Test Required - Prior to surfacing
label | 63e51689-d220-55d2-81bb-9e87babbaa4a |  | note | Task Timing / Minimum Task Frequency - Project Engineer
label | cb9a5507-7699-569b-80bf-3ce464de022a |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Surface Cleanliness
label | 1c04d82d-4be2-5857-b363-6dd8cd2da193 |  | note | Test Required - Visual Inspection
label | 7f737f98-2796-5858-b6f5-bd25c106fdc2 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder
label | 1363f441-7599-5974-a55b-d6158900a264 |  | note | Task Assigned To - Site Foreman
label | 2fb9765d-c893-5e94-a460-d8e9b66cc961 |  | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | adf72013-6fd8-5ffb-a44b-c838cadeb0d8 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Plant Resource
label | 939237e9-ab87-579e-a9af-dedd46195fb6 |  | note | Test Required - Visual Inspection
label | 15f9fcf7-7594-5feb-b119-0e5a75196d2a |  | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | 2bb543bc-bbdc-5433-a1c6-7f8113536ae6 |  | note | Task Assigned To - Site Foreman
label | 3db8641b-502d-5aae-b08d-0bf5a0df88d3 |  | note | Measuring Devices or Method - Visual
label | 40b037e1-9a02-5d2c-b144-735ac6599e8c |  | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | 15e622ed-d484-5720-87d2-7cf8019b2433 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Binder Application
label | 5c56c43a-fc02-5724-9e30-c7d936fd8c33 |  | note | Test Required - Binder type, Cutback, Temp, Application rates
label | 0df12f9e-c318-5b86-abea-bf96c2759486 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | e6ea6ea9-c077-574c-897a-dc2550d58528 |  | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | 86f6f219-6b0c-5a94-85e2-db2971b55ef5 |  | note | Measuring Devices or Method - Visual
label | 806767c3-e5c6-5d7d-9b7c-2e2a9d691503 |  | note | Criteria - Binder Type = 180/200.
label | d9f93319-d9dc-5034-a098-91d522de6dab |  | note | ○ Cutback to suit 1st coat seal 4pph kero max.
label | 4014c17c-70d5-52cf-ad39-dfac0cac043f |  | note | ○ Temp = 150deg celcius min
label | bc426ef9-0e1f-526f-9f7c-abf31430c811 |  | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
label | c05868dd-3d0f-5265-bfef-6ad24189d9f0 |  | note | QA Form - Bitumen Spray Sheets
checkpoint-status |  |  | checkpoint | Chip Application
label | 1df9dc25-75e6-5613-a2a7-48f3418a9d88 |  | note | Test Required - Chip type, Chip Application
label | 356b3d1e-4975-54f1-8eed-b5712dbf5285 |  | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | f06aa4c7-c436-5c2c-a066-624048b90b91 |  | note | Task Assigned To - Site Foreman
label | 5003c798-298e-5539-97f0-b0e850c71e30 |  | note | Measuring Devices or Method - Visual
label | 5923bc20-70d6-5372-aeb6-5a03cc85c53e |  | note | Criteria - Trucks loaded with correct chip.
label | ce974590-6d4a-5bc6-aa0c-3ced9b8dd640 |  | note | ○ Chip clean. (G4/6 Racked example)
label | 7a4bf8fc-0cd8-5e42-9ca6-6b35f3993693 |  | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | 52de6216-cc84-59ca-b738-8d62fd01b1bc |  | note | ○ G6 application = Enough to just fill the voids around the G4.
label | 7344bc79-e1b7-5c6e-a72a-e920f86dc204 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 593cbbac-829b-5356-9cf9-8e607bfb8ef7 |  | note | Test Required - Visual
label | 1ab853bf-acf7-51ae-af51-ef61e0a489f2 |  | note | Task Timing / Minimum Task Frequency - At completion of rolling
label | 922363ca-6595-56f5-b03d-80d493364e9b |  | note | Task Assigned To - Site Foreman
label | 8e7c05ba-8767-5f6d-9ccc-935ae6ffd30f |  | note | Measuring Devices or Method - Visual
label | 2ed203e4-75d2-5598-ae78-103cce1cb439 |  | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 19635c5e-4bec-50e2-b600-1578ea03dba3 |  | note | QA Form - 'QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Site Measure
label | 09fd2aeb-b1a2-5a9d-a13e-0117a3b61f3e |  | note | Test Required - Record final site measure
label | 2ddcab13-cbfe-5bb3-bee5-b0965a161e45 |  | note | Task Timing / Minimum Task Frequency - Completion of works
label | f345c4e1-8b18-575f-8add-3083f8921a0d |  | note | Task Assigned To - Site Foreman
label | 1d1b797c-0d94-5d75-9f85-09a8603c10f3 |  | note | Measuring Devices or Method - Measuring Wheel or Tape
label | a009fe3b-18b0-5d9f-a76c-87254ae92f2c |  | note | Criteria - Sketch and record seal area and QA detail
label | c78b3a92-f166-5776-a12e-edb4365e5b76 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Post Seal Care
label | 7c59cf82-c427-5376-9b2f-a8e5e0deffb8 |  | note | Test Required - Visual inspection
label | 0634009b-283c-5ac8-8f1d-37bc0d9ea2d8 |  | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | c733ede8-e930-52d8-898e-22855779b1e1 |  | note | Task Assigned To - Site Foreman
label | 2dde7978-ae49-55c1-8107-c6d8b4b97a02 |  | note | Measuring Devices or Method - Visual
label | ef8ab778-a954-5d26-8d71-68aae3c37ecc |  | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | f4d5bd94-2aaf-53a5-a751-b6008980e4ad |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Chip Removal, Pavement Marking, Traffic Services
checkpoint-status |  |  | checkpoint | Removal of excess chip
label | 1fcf4fb8-9360-5755-a0b9-d04d338c2af5 |  | note | Test Required - Visual Inspection
label | 8bb92c22-31af-5d4d-abc9-7c9fd153c12f |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 484dd708-cee1-5d48-a366-12f3aa47cd74 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | a0f69bc6-aa7e-5aff-8cfd-e91abd6f3389 |  | note | Measuring Devices or Method - Visual
label | 226280d7-0bda-563b-af95-daf1e0e8be83 |  | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 08da7270-287b-5742-942b-2f95f07f3a29 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Pavement Marking
label | 8d95e559-f323-57cb-bdda-fac204878608 |  | note | Test Required - Visual Inspection
label | d00a3088-80e4-564e-a674-c408e8ac7aa8 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | f8f9f20c-6909-5a22-95a9-5e1d1208d396 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 8bc79abf-cf78-5f6e-a0a1-5768dfb507f5 |  | note | Measuring Devices or Method - Visual
label | 67dc97da-84b1-5ef2-9b8e-9da717911419 |  | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | 56003cce-5966-5dda-aff5-e7c173ad72cd |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Removal of TTM
label | 2296148e-864c-58ee-8c5e-ed0af3fe2595 |  | note | Test Required - Visual Inspection
label | a23c0043-c28f-59c0-994f-c46b419aa57f |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | ae9fcdc8-ec7c-53b7-8760-a02a3e8d0b4d |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 8bfe5d89-bc95-5c27-b25b-5904cb726d99 |  | note | Measuring Devices or Method - Visual
label | f0b38261-f912-5223-8288-49054065ce46 |  | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | 2fa112bd-e9b1-52be-9dbd-e6cdfa05a7e1 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Traffic Services
label | 55fc42b2-585f-50ae-9a59-cee05f7e8b4b |  | note | Test Required - Visual Inspection
label | 7256f138-bbcb-5f0e-933d-9c552738a577 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | eee0b414-8897-5293-bfdd-f44fa5a40c2c |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 76f07081-288c-5211-a9c3-0657593f7862 |  | note | Measuring Devices or Method - Visual
label | 02930075-490d-57ee-9b36-b8f759f3ea5d |  | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | 199f7453-0671-5d5e-9cb8-2260e6143427 |  | note | QA Form - Daily Diary
checklist-sectioned |  |  | checklist | 11. HB AWPT ITP - Sth Tikokino Rd |  |  |  |  | Yes | 11. HB AWPT ITP - Sth Tikokino Rd | 7929ccbc-0397-45df-8ab4-538fafe9a307
checkpoint-group |  |  | section | Preliminary / Establishment
checkpoint-status |  |  | checkpoint | Establish TTM
label | 91538060-9873-51ce-9dfb-9c9de2525f7c |  | note | Test Required - Visual Inspection
label | 5798a19d-73cd-5dc1-852b-9ae794401101 |  | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | 5afa72c8-e1dc-5019-acee-c4cd2fc34d61 |  | note | Task Assigned To - STMS/Site Foreman
label | 0df74b12-33d6-5f6f-88ec-b2a45aa01e6a |  | note | Measuring Devices or Method - Visual
label | 3d38c849-9b27-5f5a-b2f7-324854be76d1 |  | note | Criteria - As per TMP and ensure TMC advised in advance of works.
label | ba3b834c-3243-5ad5-9229-101262c0d174 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Permits
label | ddc0e0ff-ae1f-51b5-aff8-27ed63ffda1c |  | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | 405be179-e028-5a88-9e73-f2e6f33b171b |  | note | Test Required - Document Review
label | e0ebc954-f416-5e41-9992-7abffb9fc375 |  | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | 071d5a18-afb6-5e79-b265-00101462f84a |  | note | Task Assigned To - Site Foreman
label | dd028f6d-25c2-5d4f-b390-4d675f9452f0 |  | note | Measuring Devices or Method - Visual
label | 741261fd-893d-501a-aa49-ca1bd2df89ed |  | note | Criteria - Obtain permits and mark outs prior to construction
label | 62892809-c874-5b44-9bfc-e899484d3b18 |  | note | QA Form - Copy of Permit on site
checkpoint-status |  |  | checkpoint | Clear-Shoulder and Side drain
label | 0cb0f75a-fa50-594f-8baf-410c6c41cbcd |  | note | Test Required - Visual Inspection
label | 111eb40c-0aae-5ce2-a281-de8e16a26025 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | aa940636-a7c4-524f-bbca-3eaea59019c9 |  | note | Measuring Devices or Method - Visual
label | 14808c72-5018-5707-ab34-8f12607801b8 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Digout Failed Areas
label | 2aa37540-a08a-52b3-8a08-0fbf294bda40 |  | note | Test Required - Visual Inspection
label | d5fabe2b-96cf-563b-9d9e-1b6c4897cda3 |  | note | Task Timing / Minimum Task Frequency - As Requested
label | 5804d450-bd44-596d-9d79-9a491b3ffaca |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 6c6b2da0-1ea7-5618-a561-f424b3609ee2 |  | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | a0aa6791-3a2d-54bb-8e95-1eccabd85851 |  | note | Criteria - Backfill with Basecourse
label | 6f5b1150-abaf-50a2-854b-83ac3abe0a39 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint-status |  |  | checkpoint | Cement for stabilisation
label | e505fca6-aa87-5d8e-8334-984fafb4dc7b |  | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | 01afbe2a-5110-57ea-ba76-2e281c986789 |  | note | Test Required - Certified in accordance with NZS 3122
label | dbc7d379-1d91-5603-a2cf-440a5d2a0979 |  | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint-status |  |  | checkpoint | Production plan
label | 17149eda-a01d-5d4d-b400-09a14d0de478 |  | note | Specification Reference - NZTA B/5:2008, 7.2.2
label | e1a4ee0e-1bee-5b1e-845f-0f0edda7706d |  | note | Task Timing / Minimum Task Frequency - 1 per site
checkpoint-status |  |  | checkpoint | Stabilisation mix properties (including cement):
label | bdeca950-d630-5fd4-8656-0e7d40da6940 |  | note | – Maximum dry density (MDD)
label | de1e53db-d690-524c-bfd1-e94044ca024d |  | note | – Optimum water conent (OWC)
label | 76f10a16-1977-5638-9103-14202c42b748 |  | note | – Solid density (SD)
label | d7b6e2e1-0be0-5558-a50d-a0eb757e8f85 |  | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | 0746165d-a493-5821-8643-64a99ab5187e |  | note | Test Required - Material properties for compaction verification
label | 08a1441a-a8fa-5cba-8e4c-1954da2dc906 |  | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | 35cd3f68-14ee-5088-83c7-574d40adac42 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | cdaa17e3-8336-5b91-9bd8-a49f58bcf899 |  | note | QA Form - QA Measurement Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | In-situ moisture content of existing pavement aggregate
label | 697bf1ea-be28-5d3a-94f8-f63d891f1c89 |  | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | 5a3f6503-0bf2-52b9-be53-5215516ce5aa |  | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
label | d9c60a67-938c-5865-934a-b60d134ae8a7 |  | note | Task Timing / Minimum Task Frequency - As required
label | a3393fca-ce4d-5cf3-9ec9-7f5d855e29da |  | note | Task Assigned To - Inspection - Lab
label | b768d9d9-98b4-57fc-80fe-2cd4a87e1653 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Top-up metal
label | 64c3aab4-d2a8-5ddf-8cf3-611ef6019d79 |  | note | Specification Reference - TNZ M/4 Table 4
label | ceb7e4df-03fb-54ce-8970-21c43ff71248 |  | note | Test Required - Placed to required depth and design levels
label | 9cf81f28-a394-5e28-b562-31d44cf00952 |  | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | 5217ed14-ffff-5ece-be71-d4310e34369b |  | note | Task Assigned To - Site Foreman
label | afa32026-ab03-5fd4-bdab-b8d0b93c62c8 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Cement spreading
label | b7b303a3-6daa-5c6b-b43b-d3487b2175dd |  | note | Specification Reference - NZTA B/5:2008, 7.3
label | 9107eb25-b71d-53cd-9782-0d8bb4eb30d7 |  | note | – Mat test (1m2 canvas mat)
label | 2f9a7e3d-d5ce-54ce-aa94-7cb60505ef8b |  | note | – Average usage test
label | 87d04961-227a-5c28-b85e-383e4ff1dc0d |  | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | dbf1c84d-7a86-52bb-90d7-873fa7d3408c |  | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
label | 57653590-9c6b-516c-a279-6932558a64e3 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 536bec45-b73b-5f21-9596-a8a5cf0e6e3b |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | In-situ mixing - Cut depth
label | 32650744-ad2c-5479-b6e7-dd217db910d1 |  | note | Specification Reference - NZTA B/5:2008, 7.6.1
label | bae74d56-dd4c-5614-8e5b-974abc3e9280 |  | note | Test Required - Maximum variation -5mm and +15mm
label | 588136ca-18d5-5cd7-98e7-07e9e994a91b |  | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | 1656f027-1673-5d51-a228-c79129d7f46f |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | dfa45f7d-bbaf-5194-9313-ed46dff3a8a6 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 42246533-de61-5d4c-bec6-73aed991c33a |  | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
label | 4a58d37f-564d-5f23-9537-04dc09f50c20 |  | note | Test Required - Plateau testing
label | 87242c11-8616-5956-981e-32e35bbf18a9 |  | note | ○ Mean value ≥ 98% of MDD
label | a3dbb30e-1052-5dbc-9b6b-92b1e2d14f0c |  | note | ○ Minimum value ≥ 95% of MDD
label | ad44e4ef-cfe6-56a4-bf1e-0d581bbd3407 |  | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | c6188b2a-889f-5486-8dbe-67ab5fe0b6ed |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 2eef69f2-738c-5dd6-947f-6b9052ca7bf1 |  | note | Measuring Devices or Method - Nuclear Densometer
label | 77f6f1cc-0d6e-536b-a29d-7d1906bd3912 |  | note | Criteria - Minimum value 95% of MDD
label | c53231a0-4f60-5db9-995c-4c3ca7a32764 |  | note | QA Form - Test Reports
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape
label | d18580f7-7c6e-55ea-aa91-ec58605e096c |  | note | Specification Reference - NZTA B/5:2008, 7.8
label | 6c5147bb-96c5-52bf-b016-d0e881a1603b |  | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
label | 87649053-14da-5267-9fd2-981427ea1d76 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 38e49fbf-7333-5a73-9d03-5203d1e4fa86 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 64521cf9-3b2b-5730-a46d-ddc0ff8a227c |  | note | Measuring Devices or Method - Stringing, Tape measure
label | f60edbaa-ceb8-5cd6-a5d0-a660595197ca |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Crossfall
label | 127c39f4-6ce3-5d97-a762-734fff9a4ff1 |  | note | Specification Reference - NZTA B/5:2008, 7.9
label | 6bfb7652-fcac-5bce-a833-efb1e83229e3 |  | note | Test Required - Not less than exisitng crossfall at the start of construction
label | a3e4a174-69c4-5f1c-8d74-7ca543b55ddb |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | cc9511f3-282a-5433-8fd5-6fb61240ebc3 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 21e6eb1c-7102-583d-9f7f-5b99a7e350fb |  | note | Measuring Devices or Method - Stringing, Tape measure
label | c6cd7f96-cb38-5165-82cf-3fbf1018a0c8 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Surface finish
label | 08c43f96-04ad-5a56-8d8f-d63ae0ae982a |  | note | Specification Reference - NZTA B/5:2008, 7.10
label | d2e43b59-296f-5afb-a731-e84965de65d7 |  | note | Test Required - See clause
label | 55657528-67b3-5b13-ac41-3d4675cd0d38 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 1f64fabb-5f3c-5126-9cd0-075ea444cf80 |  | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | a459d50a-9692-53bf-b172-4fffb1cae76f |  | note | Measuring Devices or Method - Visual
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
checkpoint-no-status |  |  | checkpoint | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
checkpoint-group |  |  | section | Chipseal Construction (NZTA P29)
checkpoint-status |  |  | checkpoint | Ensure appropriate TMP used
label | 93b153d5-a53c-5616-bf1d-85c80e700797 |  | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint-status |  |  | checkpoint | Seal design
label | c277b8d3-b3f1-51ac-b3da-c502b2ca6bd5 |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | 1a4cd2f8-e817-5429-91d9-eb463667847c |  | note | Task Assigned To - Project Engineer
label | c36efb57-e365-5437-933a-60950bd68020 |  | note | Criteria - Seal design to be reviewed prior to surfacing
label | 6e7bb9de-19a6-5afe-882f-dae404c38d5a |  | note | QA Form - Seal design template
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Location/Size Confirmation
label | 6dbfdfd3-ae8e-5d47-ac5a-49a4df252ca7 |  | note | Specification Reference - Mark up extent of chipseal
label | fb98a765-c728-55be-8df5-079d02736116 |  | note | Test Required - Prior to surfacing
label | 0424f916-1b27-5cfa-a4ef-b14e5cc0da1c |  | note | Task Timing / Minimum Task Frequency - Project Engineer
label | f5dec31b-eed2-513a-bbc9-d3aa5dcf8848 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Surface Cleanliness
label | e99c5e8d-8dcc-5f24-ac37-354a766bfb25 |  | note | Test Required - Visual Inspection
label | ab97d5d0-3789-513b-bc4d-221663b18be6 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder
label | 0f7d2ec1-5547-5c04-aebf-97fc40d3a251 |  | note | Task Assigned To - Site Foreman
label | af61cbd3-efa8-5a7a-b355-9c3d69fb60ae |  | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | aa46706b-bc29-570c-a12d-a760a69caa33 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Plant Resource
label | fbfc4b7f-363c-5229-9015-ac7ad938364a |  | note | Test Required - Visual Inspection
label | 9010a24e-6ba2-55b0-934f-0202dffa4554 |  | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | db09224c-f8fd-56a7-bc64-8c714cfeee1b |  | note | Task Assigned To - Site Foreman
label | a572a93e-6208-5b8f-84c7-7f3996d8014c |  | note | Measuring Devices or Method - Visual
label | 1880d797-622a-51f3-943b-a3b7e35a306c |  | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | cb8f2187-390f-535c-a3db-15961dbdfd32 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Binder Application
label | 57341a15-50b4-527a-882d-30431dabe391 |  | note | Test Required - Binder type, Cutback, Temp, Application rates
label | 527272b9-7546-567d-b083-c2fc2a70585d |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | 858588d8-6f12-541f-96a7-117dc4a1fe2d |  | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | ce89601e-01a1-5756-af52-0e42d95ae38b |  | note | Measuring Devices or Method - Visual
label | ebe1d09d-245e-58c1-94df-5c091450ff60 |  | note | Criteria - Binder Type = 180/200.
label | dc8ef95d-821e-5baf-84d6-b16944517868 |  | note | ○ Cutback to suit 1st coat seal 4pph kero max.
label | 07576941-5822-57ac-b8c6-96f4f8e980d2 |  | note | ○ Temp = 150deg celcius min
label | d0a4f1ea-bd57-5541-9833-87aa3ba73a3e |  | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
label | d256dfa4-dadb-51af-a465-edb721ebf363 |  | note | QA Form - Bitumen Spray Sheets
checkpoint-status |  |  | checkpoint | Chip Application
label | 9d8a909f-aee1-5fcb-9474-5007ecaeb105 |  | note | Test Required - Chip type, Chip Application
label | b7dad6b4-9534-5cef-8898-739bdfa70b16 |  | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | ef575e0d-11c3-5b03-a25f-87c8b6547c88 |  | note | Task Assigned To - Site Foreman
label | f8856054-65aa-503e-a710-ad43327fadf5 |  | note | Measuring Devices or Method - Visual
label | 10ba5ae0-5900-55e3-b099-c915eaa7f1bd |  | note | Criteria - Trucks loaded with correct chip.
label | 55d1c1b0-a9c5-59f5-b074-4a5ecaa44e0e |  | note | ○ Chip clean. (G4/6 Racked example)
label | 732a3a39-c287-5ed0-abb3-6b2d5f67c99a |  | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | 949c2edd-6753-59b4-91a1-e51d47b383de |  | note | ○ G6 application = Enough to just fill the voids around the G4.
label | 34cc6d1b-2f40-5365-9e20-e1734aa8e14c |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 7922cbe5-31b7-5319-afc4-bda4e9f0a75a |  | note | Test Required - Visual
label | c359c581-60bd-5eba-ae00-2defc2efe4f7 |  | note | Task Timing / Minimum Task Frequency - At completion of rolling
label | d148da6f-d73d-5547-9412-5ddfbf7f0e58 |  | note | Task Assigned To - Site Foreman
label | 7daabc3f-df5c-5a0d-bfb3-86d25933b0a0 |  | note | Measuring Devices or Method - Visual
label | 187f5593-81d2-5422-bac4-fd13dd67aa73 |  | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | b751b84c-d5bb-5471-8db1-a068bedb19ce |  | note | QA Form - 'QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Site Measure
label | 0c953b5e-688b-524a-bb6f-330e3eee8c6e |  | note | Test Required - Record final site measure
label | f0dd5f80-8d8f-520f-9891-c11a704f439c |  | note | Task Timing / Minimum Task Frequency - Completion of works
label | 76bdac05-ef5e-5077-826a-4ef861f1cbbf |  | note | Task Assigned To - Site Foreman
label | 0ec2b717-4363-5277-91eb-f503ab6dd457 |  | note | Measuring Devices or Method - Measuring Wheel or Tape
label | a19974bd-45b9-583f-b653-9dcb8ba40e57 |  | note | Criteria - Sketch and record seal area and QA detail
label | f06f7b0b-ea31-5a69-89d7-9101fd20fa24 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Post Seal Care
label | 3c79a9ea-6925-5c57-a162-3ebd37544c74 |  | note | Test Required - Visual inspection
label | b4e0d90f-81c8-5038-8c23-1c39fc0f2791 |  | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | f796e4c4-8ac7-55ec-95e7-a08ba51a9ac0 |  | note | Task Assigned To - Site Foreman
label | 24133333-0b68-56e8-9882-a3610940293a |  | note | Measuring Devices or Method - Visual
label | 31d85c78-d166-5db6-b0b8-43510db6c8d6 |  | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | 05e5b859-1987-568b-9920-208affcf5d6d |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Chip Removal, Pavement Marking, Traffic Services
checkpoint-status |  |  | checkpoint | Removal of excess chip
label | b4653fe4-0a49-51df-bf7f-f2cd21cf3a75 |  | note | Test Required - Visual Inspection
label | f2ca2c76-7a30-5e05-b504-6e538af7fd11 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | fdd81dd8-33f9-54f9-ba75-2a2542843480 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 4daeece6-a061-54ae-8991-2f90f77d05c4 |  | note | Measuring Devices or Method - Visual
label | c1bac996-2623-54b6-9d9e-a750566703e6 |  | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 4f4f08cd-4134-514d-82eb-bd00f61a8060 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Pavement Marking
label | 72998183-70b0-51c5-b172-1491a7cb35ca |  | note | Test Required - Visual Inspection
label | 3cb495d1-6260-566f-9da1-49e4d3904d87 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 75372e74-aafe-5533-a2e0-2cf14b17b8dd |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 56191d13-57c6-57d7-b994-565175665a18 |  | note | Measuring Devices or Method - Visual
label | 41c730e3-c693-526d-8863-ed90083e6679 |  | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | 2fc807f7-0eda-5ed1-b259-49969d10c6f4 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Removal of TTM
label | 7fb19597-34db-5b4c-8eda-b879a42fce63 |  | note | Test Required - Visual Inspection
label | b7cba2f3-364c-53d3-8cbd-8cad1181c20a |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 09d8cbf6-3efe-5de3-8582-00132305c0c1 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | ca8732ae-377e-589d-b33b-b2fc508c4fe7 |  | note | Measuring Devices or Method - Visual
label | 78f44d45-cbe2-59bd-9924-4afc1b5c1454 |  | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | 54923fc6-51aa-51af-a62f-0480009a2ea8 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Traffic Services
label | e0836c92-a716-5fd0-9d2b-94ae0035e995 |  | note | Test Required - Visual Inspection
label | a267ccca-a2a5-5ba8-a79e-3c2d34d7c31f |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 60dc4f5b-3b1d-599d-892e-682e4f106467 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 17459b7e-6826-5e51-b546-efa462bb24df |  | note | Measuring Devices or Method - Visual
label | 5a91be88-4ee0-5810-bf71-4c2c1d34e411 |  | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | fd0bdc54-3749-5b4e-ad3d-d471b5dd9a41 |  | note | QA Form - Daily Diary
checklist-sectioned |  |  | checklist | 10. HB AWPT ITP - Sainsburry Farm |  |  |  |  | Yes | 10. HB AWPT ITP - Sainsburry Farm | 7e6aee5c-603b-44a0-81e6-0e78bb712df4
checkpoint-group |  |  | section | Preliminary / Establishment
checkpoint-status |  |  | checkpoint | Establish TTM
label | 300426eb-5e25-50dd-b48b-4733d5c709b9 |  | note | Test Required - Visual Inspection
label | 8d0f2ad1-ea6d-5a96-bd14-ba16a7d9f485 |  | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | e415993c-eab3-5747-b2e6-8669db508f93 |  | note | Task Assigned To - STMS/Site Foreman
label | 554bca69-e617-5f7c-bdb4-923634c6e287 |  | note | Measuring Devices or Method - Visual
label | dc74e511-264e-59d6-a058-d80e190555f5 |  | note | Criteria - As per TMP and ensure TMC advised in advance of works.
label | e18442c5-3db7-5a39-a8dd-f8ca2df5cea8 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Permits
label | 80e065f5-61b8-536f-95b0-def94e69c76a |  | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | 2b50a009-d8ee-562f-946f-59cb85d29955 |  | note | Test Required - Document Review
label | 38dc289e-f1f4-509e-aea8-e33d52857671 |  | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | ba7ac953-07f5-5131-94eb-ee839fa16025 |  | note | Task Assigned To - Site Foreman
label | d278ae4c-11bd-5e04-8084-7c3f7866cd35 |  | note | Measuring Devices or Method - Visual
label | df49c2e5-2843-55ba-b4e5-7f0f80f37dbf |  | note | Criteria - Obtain permits and mark outs prior to construction
label | 59ef89df-baaf-5e2c-85e8-d187748e3590 |  | note | QA Form - Copy of Permit on site
checkpoint-status |  |  | checkpoint | Clear-Shoulder and Side drain
label | 2ff65f6c-f088-51f7-b3ef-3c715925f594 |  | note | Test Required - Visual Inspection
label | 63615f0b-589d-5487-8840-916263348b9a |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 0d5521b4-30da-5257-8e32-0cefc2429c06 |  | note | Measuring Devices or Method - Visual
label | 5c94f07a-be93-54f6-9ba0-49717ef8ae44 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Digout Failed Areas
label | 835ff09e-08ff-557f-9395-5549340e5c02 |  | note | Specification Reference - Refer to Design Report for required depth based on Scala results
label | de178b0b-6f51-532b-92f3-9f07b40ef2f4 |  | note | Test Required - Visual Inspection
label | efc85846-2134-54bb-ac07-29a7b8d3dd8c |  | note | Task Timing / Minimum Task Frequency - Prior to Pavement Rehabilitation Construction
label | bbff3182-bc71-5d12-b14d-e9497d0673c5 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 3abe9a1f-bade-5da3-b508-86153785aa9d |  | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | 86f10fef-ece9-5d0a-8113-4fa3bc08caaf |  | note | Criteria - Backfill with Pavement Aggregate
label | a86e2faf-99af-5ded-9b2b-f330d0c928e2 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint-status |  |  | checkpoint | Cement for stabilisation
label | a48fb759-de1f-5d62-a720-4db9a9b734f2 |  | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | f6389dd8-7e73-5169-91aa-b8794e95e7a7 |  | note | Test Required - Certified in accordance with NZS 3122
label | 1a14c3ff-2385-5989-9e08-d6c517519390 |  | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint-status |  |  | checkpoint | Production plan
label | 24b7eedc-34cd-5e87-a603-b4510724be18 |  | note | Specification Reference - NZTA B/5:2008, 7.2.2
label | ff04f72b-f1fd-5663-aa8d-62a47def3cc6 |  | note | Task Timing / Minimum Task Frequency - 1 per site
checkpoint-status |  |  | checkpoint | Stabilisation mix properties (including cement):
label | f1277344-88cf-5fe9-8500-beea1ffe677a |  | note | – Maximum dry density (MDD)
label | a5aa581f-4a17-58cb-a36b-4cc123cdd273 |  | note | – Optimum water conent (OWC)
label | dfa650ac-aa26-559f-811c-8eebb67d5042 |  | note | – Solid density (SD)
label | 79d4350a-9e1d-5f77-8f71-bc9ae05acc97 |  | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | a019ae70-6e41-599c-af3c-212d8a6fc455 |  | note | Test Required - Material properties for compaction verification
label | c8aeea6d-2bd4-5f0f-8726-fcffdb8a7d38 |  | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | 85f1a699-f6df-5f22-81a9-051df8fb9953 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 94deeaa2-e622-5503-bcdc-01f23a78c999 |  | note | QA Form - QA Measurement Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | In-situ moisture content of existing pavement aggregate
label | be660110-2543-5dfd-84e3-8bb9adc3e898 |  | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | df9ffe67-d9ab-58fc-ab0a-b81ee0711ae5 |  | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
label | e630d5f0-67ae-534d-926e-e1b4d6dc8907 |  | note | Task Timing / Minimum Task Frequency - As required
label | 678b8550-2c4b-5661-a42f-e877cdede233 |  | note | Task Assigned To - Inspection - Lab
label | c61088bf-efc9-5866-b0c1-8838b71b8369 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Top-up metal
label | 1bc652b9-7051-5e22-8b67-c17dd7f5ba11 |  | note | Specification Reference - TNZ M/4 Table 4
label | 511c35be-4bc8-5125-9cbc-75ab6da25a3c |  | note | Test Required - Placed to required depth and design levels
label | 26d7e4e6-0b32-5f5d-bbae-6b546eacf4b4 |  | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | 8fccff67-699d-50d8-b68a-62ab07fec6ee |  | note | Task Assigned To - Site Foreman
label | 213b7f1d-7837-5424-a227-8b7de2db4788 |  | note | Measuring Devices or Method - Stringing, Tape measure and or survey
label | 1801c75b-3715-57b3-82d0-808d9898138e |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Cement spreading
label | e95258dc-f589-55f3-a575-f9fbce86517a |  | note | Specification Reference - NZTA B/5:2008, 7.3
label | 87686999-20b5-5aab-a176-b954670d7170 |  | note | – Mat test (1m2 canvas mat)
label | a10db913-4e0b-5fee-8a61-d80b37dd89aa |  | note | – Average usage test
label | dcfa2525-bffc-5013-b9b6-97c0e2af362d |  | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | cc83e796-b855-53d9-94eb-53b06effd6fc |  | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
label | ca8af87e-012e-5670-b69a-3e245711331a |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 75769740-8b8a-525e-b0ac-cefb528cb6f8 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | In-situ mixing - Cut depth
label | cffb4f2a-a978-5747-acac-180d22bf73a6 |  | note | Specification Reference - NZTA B/5:2008, 7.6.1
label | d0dce1af-38df-5785-861f-f30120fe01f6 |  | note | Test Required - Maximum variation -5mm and +15mm
label | db9931a3-dc43-5f9a-b9f6-e0ea40a9057f |  | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | 5e2f4638-cff8-5db2-adc0-b1cf348c65c1 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 416e6364-1b28-5f87-9d11-ed19ef5c6d9f |  | note | Measuring Devices or Method - 250mm Depth
label | 41f0d2d8-a59f-5702-bf33-06d4cf608171 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 73043dbb-e0e4-5588-afb4-4e7e3fb00d50 |  | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
label | a2a4f841-be9b-550b-aa87-825c8ee3adf4 |  | note | Test Required - Plateau testing
label | 2c2a6e20-ba18-5693-a119-eca45908dfa3 |  | note | ○ Mean value ≥ 98% of MDD
label | 8c7d5ee5-9b89-5f36-887c-262701305f7c |  | note | ○ Minimum value ≥ 95% of MDD
label | 31b860aa-85bc-5603-b6a2-1952459c67cf |  | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | e3c441e8-6da4-52ff-a607-9345c1a85560 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 4345fd51-1449-542f-982d-99787e68102d |  | note | Measuring Devices or Method - Nuclear Densometer
label | 585824ce-6977-52f1-873e-93987016164d |  | note | Criteria - Minimum value 95% of MDD
label | 271fc28e-702c-5d68-b0fa-3bb50099c409 |  | note | QA Form - Test Reports
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape
label | 5d297b21-e787-5291-a5c6-258fea77a9f7 |  | note | Specification Reference - NZTA B/5:2008, 7.8
label | f3a1e366-ddd7-5a21-b700-97a47c5b9b8a |  | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
label | 2ad9d198-baac-5127-8703-16692abff198 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 5b1b6311-05a2-56d1-8996-25847a7bc5c2 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 51261395-cdbc-58ef-89cd-5efe4d438960 |  | note | Measuring Devices or Method - Stringing, Tape measure and or survey
label | b8008982-8c97-572e-b2b2-474dcb317a42 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Crossfall
label | 5f48eb59-43a9-5a46-8310-c245a75c57fe |  | note | Specification Reference - NZTA B/5:2008, 7.9
label | cb1b5298-7369-52c2-a959-2bf53852c9c6 |  | note | Test Required - Not less than exisitng crossfall at the start of construction
label | a6f89f8d-25e2-59e3-b845-b23d6a36ebf5 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 844476cc-dcbd-5953-b013-8246630b0d2d |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 4989df29-59cb-5e1f-8ceb-71b62215a78b |  | note | Measuring Devices or Method - Stringing, Tape measure and or survey
label | ba1a6f8e-6f7d-519d-b581-826b1120b7c7 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Surface finish
label | 9f2cb97c-b934-5e39-abcb-227ad74a8232 |  | note | Specification Reference - NZTA B/5:2008, 7.10
label | 9fd4b5bd-5bbc-53b5-b29f-32a70cf95e40 |  | note | Test Required - See clause
label | 5eb457a8-5343-5c07-8cc1-3f99b70c6bf4 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 1327229e-972d-5931-9d5b-8eb1a6a6872a |  | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | 0e87d119-2f24-53d4-befd-82ea698a4c70 |  | note | Measuring Devices or Method - Visual
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
checkpoint-no-status |  |  | checkpoint | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
checkpoint-group |  |  | section | Chipseal Construction (NZTA P29)
checkpoint-status |  |  | checkpoint | Ensure appropriate TMP used
label | cfe9d4b6-124c-5506-bc8b-1a3a58a2cf41 |  | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint-status |  |  | checkpoint | Seal design
label | 32849463-8b6a-52a0-8892-3752adc81e42 |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | f91d6d0a-f93d-5478-b3d3-fad0feeefef2 |  | note | Task Assigned To - Project Engineer
label | ed08c656-2995-5930-bab7-36ff9bdbd438 |  | note | Criteria - Seal design to be reviewed prior to surfacing
label | 57c8aaea-415c-5003-b56a-0805d8c65094 |  | note | QA Form - Seal design template
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Location/Size Confirmation
label | 9f1b9485-8c38-56b1-9ebc-913ca5ac2a2f |  | note | Specification Reference - Mark up extent of chipseal
label | 1faeaf78-8e48-5a11-8d50-30f6589d74c3 |  | note | Test Required - Prior to surfacing
label | f31cc376-0a7d-5a4b-baf5-0777848a5690 |  | note | Task Timing / Minimum Task Frequency - Project Engineer
label | 16f5e106-8d14-5e0d-9f82-0ba0cbca2be3 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Surface Cleanliness
label | 0d8370c2-2e9f-5b8b-bff6-d4bb74033449 |  | note | Test Required - Visual Inspection
label | fd07f54f-a1f2-538e-9268-cc8a1f3e6db9 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder
label | 41b88376-7d61-5537-9cee-3d8bc384d8df |  | note | Task Assigned To - Site Foreman
label | 08498d5b-5a17-592d-a2c7-b5b8d8976356 |  | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | a2c81594-61c3-5785-9121-b99bfbfbd03b |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Plant Resource
label | 5c23c945-638a-5b81-bcbb-8046febf20f1 |  | note | Test Required - Visual Inspection
label | f60b402a-e4f1-5f5c-9ffa-2c2132bef7a4 |  | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | 6d638dd5-3901-5569-8262-6f48556857bc |  | note | Task Assigned To - Site Foreman
label | 1aa886dc-7dd3-5c57-9568-ef1376c94bed |  | note | Measuring Devices or Method - Visual
label | c0a2d0cd-9845-5306-9577-6424d4104ab3 |  | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | 8cd2726a-bee1-58c5-a91e-1b5f7485a6a4 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Binder Application
label | 8e924d56-2313-5e85-8022-e54e82ea0765 |  | note | Test Required - Binder type, Cutback, Temp, Application rates
label | c5b75710-59d4-5421-a6c7-071004658606 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | bfa15d11-7b3a-5833-845a-bd7155e7a8b8 |  | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | 60d643fc-9251-54c4-91af-1e01fdffa0f2 |  | note | Measuring Devices or Method - Visual
label | a94bbe62-d448-5c27-87fe-1e061936bbd3 |  | note | Criteria - Binder Type = 180/200.
label | 91c8cdf3-c4d8-5cc0-b8d6-595180a1bbbb |  | note | ○ Cutback to suit 1st coat seal 4pph kero max.
label | cee66963-aebc-52c7-bdac-10dea2274121 |  | note | ○ Temp = 150deg celcius min
label | 7474a19e-7e0c-5f90-ba24-5c26e20054b1 |  | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
label | b9818c9c-db34-5960-8717-018a7dd2f44f |  | note | QA Form - Bitumen Spray Sheets
checkpoint-status |  |  | checkpoint | Chip Application
label | 01f8e7c8-4eff-5cad-9405-c03407a836d0 |  | note | Test Required - Chip type, Chip Application
label | 1d912813-2f55-553d-9ff6-1d2475048f97 |  | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | 7e7d6360-ed60-562b-ad6d-42ff98f25311 |  | note | Task Assigned To - Site Foreman
label | bc13bed2-1424-50bd-8c05-1a019ec1f1fe |  | note | Measuring Devices or Method - Visual
label | cbe38da2-1960-5db2-b1d0-d18514f840d7 |  | note | Criteria - Trucks loaded with correct chip.
label | 674b4092-2cc6-5382-8acf-4a2ff3a54cd4 |  | note | ○ Chip clean. (G4/6 Racked example)
label | df6d866c-115b-5735-b07b-c61e8c839e09 |  | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | a198fe86-3ebe-5632-8513-c6b46d41d430 |  | note | ○ G6 application = Enough to just fill the voids around the G4.
label | f4346868-f479-5247-a931-b220c51d4f1c |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | da144088-1782-5db0-af09-c1177c001708 |  | note | Test Required - Visual
label | f4001d51-0e2f-5f8b-a01a-0182e0a79628 |  | note | Task Timing / Minimum Task Frequency - At completion of rolling
label | c44358e7-97d9-5efb-8fdd-a5d3fc19e950 |  | note | Task Assigned To - Site Foreman
label | 33b48c1a-7511-54d5-a6a2-184d1210b86a |  | note | Measuring Devices or Method - Visual
label | 5dc966c3-6fa2-5fe7-975d-16fd122b5e49 |  | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | b8456458-7580-53e7-92e6-901ddb33e578 |  | note | QA Form - 'QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Site Measure
label | 2fbe100c-3199-547b-98af-22fa20cadb2a |  | note | Test Required - Record final site measure
label | ccfd4b1b-4972-5b33-9c80-b692b3996c0d |  | note | Task Timing / Minimum Task Frequency - Completion of works
label | a5550fde-a19d-5b5f-af45-eab13bf49735 |  | note | Task Assigned To - Site Foreman
label | bffeeec8-3f1f-5d3f-b249-7e78472afba2 |  | note | Measuring Devices or Method - Measuring Wheel or Tape
label | 0674d7ac-3c75-5659-822a-cd49c979f04f |  | note | Criteria - Sketch and record seal area and QA detail
label | 20e9ef1f-39a9-5b13-923b-c0c347df6e1c |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Post Seal Care
label | 687770d4-6d3f-5704-bd6b-0c4b7121f9bd |  | note | Test Required - Visual inspection
label | 12ee0c14-3b7b-5544-bbef-515733f6853c |  | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | 353e1ad2-2f24-55c1-9252-d7df5b460121 |  | note | Task Assigned To - Site Foreman
label | 8e8a68a2-e0fc-529f-a7da-f13d56e2df38 |  | note | Measuring Devices or Method - Visual
label | de76292b-57d7-5e78-b100-ffb42e5b3d1a |  | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | 3b886f4e-307b-58c1-80fd-7e14cc77fa51 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Chip Removal, Pavement Marking, Traffic Services
checkpoint-status |  |  | checkpoint | Removal of excess chip
label | 39a5fda4-5688-513e-89a5-3a8f46ea51a7 |  | note | Test Required - Visual Inspection
label | 35681b99-36b3-5652-aa5a-5abbaf54a5c3 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | d519be18-f337-5d41-949f-9f854cad6db4 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | bc71c2c3-19cb-5449-8e84-679e10ca0b33 |  | note | Measuring Devices or Method - Visual
label | b4e735c7-8276-5c6d-91f3-6d6db29b4f5e |  | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | aad85a5b-942d-570c-a8a4-07af0328024c |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Pavement Marking
label | cf9caeaf-0c64-56f9-8d0b-83ab567a7e1d |  | note | Test Required - Visual Inspection
label | fd8f0bda-4533-51ef-90be-a84bc6a263e3 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 73c646cf-a413-5fa8-ab2b-58695cac841e |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 46b6cad3-b5e2-5930-b65c-821a8d6ffb0a |  | note | Measuring Devices or Method - Visual
label | f81a7580-ceb0-5e6b-8bf6-fe0658e95739 |  | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | c2f9cd28-c067-53d9-bbaa-11f75c39038c |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Removal of TTM
label | bda7d959-c7d3-5fbb-96ed-f82bdd9920c5 |  | note | Test Required - Visual Inspection
label | 3f6feb51-4d6f-57e2-9b6e-c4d9e7018250 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 8f88b475-5652-50e8-abab-59a86a28fd65 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | b23f0dd0-8e00-51f4-9f06-123bab365b67 |  | note | Measuring Devices or Method - Visual
label | 869d946d-6aea-5667-8cb1-2062e9b6f9fc |  | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | 5bf47d7c-6a86-5200-b6cc-2ff1f017ddb5 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Traffic Services
label | 434022e1-5edd-5cfc-8d86-46c701296683 |  | note | Test Required - Visual Inspection
label | 1d339f4e-0085-5d73-b475-23009238cc00 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 7fea9227-dcc8-549b-91fa-52f6ec9dac56 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 880c3c82-eb3d-5bdb-be2f-a4101e9825fa |  | note | Measuring Devices or Method - Visual
label | ec45f09a-340a-5e1b-b446-2b4280dc7a5c |  | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | a33731ad-d4e1-5bf9-85a7-2cc28570bb77 |  | note | QA Form - Daily Diary
checklist-sectioned |  |  | checklist | 2. HB AWPT ITP - Rakaipaka A |  |  |  |  | Yes | 2. HB AWPT ITP - Rakaipaka A | aa096b80-fe82-4153-bc7c-c4727be03e3f
checkpoint-group |  |  | section | Preliminary / Estabilishment
checkpoint-status |  |  | checkpoint | Establish TTM
label | 9b29814d-eea4-5755-bd3d-77575baec9d1 |  | note | Test Required - Visual Inspection
label | c37b4ade-8c1a-5ea7-a101-02575dd0bb86 |  | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | 22b21397-497a-5a2e-91ea-0423d1ee44e3 |  | note | Task Assigned To - STMS/Site Foreman
label | 2272177a-01bc-5452-a943-916620e49585 |  | note | Measuring Devices or Method - Visual
label | 380a4dbc-edd3-5267-8e03-152ee37b0715 |  | note | Criteria - As per TMP and ensure TMC advised in advance of works.
label | 4b264fa6-1136-53c1-96d5-c63960dbfdd5 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Permits
label | ae063b22-3163-57bf-864c-ae7ad215d0b5 |  | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | b611847f-0de1-508a-8659-f134c6c2b5ea |  | note | Test Required - Document Review
label | 95c1cb24-a130-59d5-9a6c-4f397b7445b1 |  | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | 46b2e041-0e60-50b8-8b09-f2f5b9e5ea5d |  | note | Task Assigned To - Site Foreman
label | 816b1d3e-e339-5e17-baae-4e8def770f3d |  | note | Measuring Devices or Method - Visual
label | c5ce0072-f99e-50df-895a-b71ba4944390 |  | note | Criteria - Obtain permits and mark outs prior to construction
label | 02286de0-2d96-5081-80f6-dec9ca41ad30 |  | note | QA Form - Copy of Permit on site
checkpoint-status |  |  | checkpoint | Clear-Shoulder and Side drain
label | a0981b62-271d-5df0-961c-725a14747d4d |  | note | Test Required - Visual Inspection
label | 8c6dcd87-42b8-5378-94d2-579949f4dec9 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 97990be2-9e53-5263-94bb-f192c5c4d45f |  | note | Measuring Devices or Method - Visual
label | 6e39ea0a-8ae5-559e-87f0-bf5a276cf76c |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Digout Failed Areas
label | 8c3bdde8-7abc-53e5-acb0-c2d6b0607f27 |  | note | Test Required - Visual Inspection
label | d1bd66ce-48ae-5e65-8ebf-1c467410f7a5 |  | note | Task Timing / Minimum Task Frequency - As Requested
label | 6e41ee67-1c68-5033-8fd5-7d6975c887f5 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | b68c274d-8308-5015-816c-eb001bb29272 |  | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | 0668f97c-0e5f-5b82-987a-ae0b8ec7baca |  | note | Criteria - Backfill with Basecourse
label | aa271a66-92c1-51bc-8b8d-101a6f601588 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint-status |  |  | checkpoint | Cement for stabilisation
label | 5503e582-f4dd-52e5-b161-9ce191f32e51 |  | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | 77a1c411-f9dc-5f5c-84d3-827efd33dea7 |  | note | Test Required - Certified in accordance with NZS 3122
label | 24ea3da4-f5e2-5986-8151-c62fbea963ef |  | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint-status |  |  | checkpoint | Production plan
label | 5727d58d-766e-51a8-a545-b3a64a2078b8 |  | note | Specification Reference - NZTA B/5:2008, 7.2.2
label | c54a9b7a-b7d0-5728-a893-95b2112d8fb7 |  | note | Task Timing / Minimum Task Frequency - 1 per site
checkpoint-status |  |  | checkpoint | Stabilisation mix properties (including cement):
label | 7984f5f1-060d-5cf9-8ae3-12bde3de896c |  | note | – Maximum dry density (MDD)
label | d555f958-91bf-5ffd-98ff-7084de334b31 |  | note | – Optimum water conent (OWC)
label | a503c2e8-7969-5e3a-abd4-6f10b988cbb8 |  | note | – Solid density (SD)
label | 547c0b89-5d48-5249-b922-5676bce65145 |  | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | b4e50806-881a-5816-b270-fb01e5a3d66a |  | note | Test Required - Material properties for compaction verification
label | 0b8e90cd-824f-5e76-bea2-f2269026f783 |  | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | db6b5f35-d23e-50f6-b893-3dcc51d5bfc1 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 051f5a78-2b95-58b9-903a-e025df652a5f |  | note | QA Form - QA Measurement Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | In-situ moisture content of existing pavement aggregate
label | 1522ad8a-f6e9-5824-8998-6e19f28d1ca3 |  | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | 00ab3038-c841-5fee-adf5-8145774dd0a1 |  | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
label | 75352996-b104-5c46-8d95-9463b65d68f2 |  | note | Task Timing / Minimum Task Frequency - As required
label | 7d70aa49-2fd8-54fa-8fe3-6dd0d4dbae7a |  | note | Task Assigned To - Inspection - Lab
label | 4dd2578f-308f-5fc6-b5bc-a719f8dc0469 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Top-up metal
label | 963989e4-2c50-55d0-b5c7-863c7227571f |  | note | Specification Reference - TNZ M/4 Table 4
label | 770395d7-ab20-5868-abb7-dbd1ce5b7b4d |  | note | Test Required - Placed to required depth and design levels
label | bd97ef3d-6760-55c2-ba35-e86651379c6c |  | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | 83ba94da-ca12-5f1b-8ad0-f4d02d4d0aa0 |  | note | Task Assigned To - Site Foreman
label | 870722ed-61c2-5083-b9fc-6acd795ae897 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Cement spreading
label | ffdde42c-ade4-5f4b-9d72-3a4d631e1aab |  | note | Specification Reference - NZTA B/5:2008, 7.3
label | b58c834d-ffbc-5bb3-ab18-95a0b7f825b6 |  | note | – Mat test (1m2 canvas mat)
label | 9e0cacfb-9f33-5a60-861d-f36272e751b6 |  | note | – Average usage test
label | 082eff31-4006-5e33-89de-280a57de6784 |  | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | a8974720-59f1-58d1-a0b6-03065be1d0a9 |  | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
label | e9532ce2-a1e7-5d39-bc43-4ecb545388e4 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | c383a181-15fe-527b-96aa-66d4992ce5d9 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | In-situ mixing - Cut depth
label | 2f4ab3cb-2f79-5d8c-8dfc-c62f6cd48f4d |  | note | Specification Reference - NZTA B/5:2008, 7.6.1
label | 368587bc-f100-5ad1-aa3b-3e9c09fe5872 |  | note | Test Required - Maximum variation -5mm and +15mm
label | 40edcddf-ce98-5281-a256-f326b313c258 |  | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | cc10dab1-c06b-50f3-8fec-dadb276be392 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | c9fa802d-3d1d-5a4c-ad59-aaf5a01d2443 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 0cfc082c-5e2b-5072-80a4-cf2537c88082 |  | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
label | d67c36fe-6fe3-5023-aae9-383f73cb1bbd |  | note | Test Required - Plateau testing
label | cfee74a4-8b7a-5c4e-b2fc-9c1d71898b8a |  | note | ○ Mean value ≥ 98% of MDD
label | 10e83193-0254-5012-8577-aa8f4c7f6974 |  | note | ○ Minimum value ≥ 95% of MDD
label | bf3f4cac-caa9-5410-bf78-635b5c0c7197 |  | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | 6da686a1-f4e4-5ef6-9db7-01b0caa3fcf5 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 5db21a97-716c-5126-ab7a-041dc85978cf |  | note | Measuring Devices or Method - Nuclear Densometer
label | 8b92993a-c848-5b4c-aa95-727e50649007 |  | note | Criteria - Minimum value 95% of MDD
label | 0ca9c05c-976f-5959-bccd-005251c27523 |  | note | QA Form - Test Reports
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape
label | e41e36ef-6c63-5b95-be15-a66ca0110077 |  | note | Specification Reference - NZTA B/5:2008, 7.8
label | 315e489f-4332-5443-b33e-f8574c0dd971 |  | note | Test Required - ≤10mm from 3-metre straight edge
label | b32673b0-b328-56b4-a714-8b6f6cbee311 |  | note | – No depression
label | 1267a8fc-5841-5bf5-a281-26eb3328790a |  | note | – Vertical variations -5 + 15mm
label | 19d0bb44-3862-54e2-a803-c1d684b6d2f8 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | a12fdbca-cd26-558e-996a-719b0f80a3da |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 08b5ca5e-3e13-585a-a35d-a4286d0ab932 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | 8554a205-e948-5d01-be2b-b1a2db4665bd |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Crossfall
label | 205937a5-ba29-5511-8a88-da808f778161 |  | note | Specification Reference - NZTA B/5:2008, 7.9
label | 431221cb-d024-5613-bf04-37eb6ceeec51 |  | note | Test Required - Not less than exisitng crossfall at the start of construction
label | 62b11677-885c-550f-bf8c-39a1306f5417 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 668230ae-f930-5843-9f03-2152f4e16b3e |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 8090cd24-52f1-5952-9c2f-d710e5ca8b61 |  | note | Measuring Devices or Method - Stringing, Tape measure
label | d503e1e8-9001-5007-8d5c-3424ee65c436 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Surface finish
label | e892f6d2-f836-57eb-ad52-acbfc576011b |  | note | Specification Reference - NZTA B/5:2008, 7.10
label | d219305b-18e0-5ccb-bfdc-e9a180817672 |  | note | Test Required - See clause
label | a0731827-f3ca-5254-a7f4-2ccdc9ce2c67 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 46f24b38-e0d6-5590-9c63-643d04cc4f97 |  | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | c19b4438-1129-5035-85f3-1f7e86f938c9 |  | note | Measuring Devices or Method - Visual
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | * Normal Risk = < 5 x 106 ESA's (or< 500 HCV per lane per day)
checkpoint-no-status |  |  | checkpoint | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
checkpoint-group |  |  | section | Chipseal Construction (NZTA P29)
checkpoint-status |  |  | checkpoint | Ensure appropriate TMP used
label | 3870fc3c-8e36-5f2d-baea-8a045bac1c49 |  | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint-status |  |  | checkpoint | Seal design
label | c7095aef-a50e-5ee5-9da0-353261e6f6a5 |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | fef122c2-d11f-5be7-99cd-a0390749a80d |  | note | Task Assigned To - Project Engineer
label | 5cb28bf8-f8ec-563f-8aa9-01f45e3c55ff |  | note | Criteria - Seal design to be reviewed prior to surfacing
label | 4aa97448-aea1-5dcd-951e-47b91504505a |  | note | QA Form - Seal design template
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Location/Size Confirmation
label | d884b402-2f34-54c3-a419-827ab9a08a1f |  | note | Test Required - Mark up extent of chipseal
label | 6004e878-ad5f-567e-9e4d-0046ccc0427f |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing
label | 150cf92b-0884-5dda-badb-4d91b6040c1c |  | note | Task Assigned To - Project Engineer
label | f420f6cd-6cde-5cfd-bcae-2c036069f4f6 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Surface Cleanliness
label | dc9dfa49-8e43-5512-894d-bcbd3bea2d9f |  | note | Test Required - Visual Inspection
label | 31a5eea1-c373-5463-9fa9-1641e99c4686 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder
label | e9f13e5c-2e9d-57bf-a7b2-409a120220ba |  | note | Task Assigned To - Site Foreman
label | b51a35b7-3069-5d7b-ab1f-008ce87cbba0 |  | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | 1dd18a88-3023-5f37-89ec-4a927c79c930 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Plant Resource
label | d71212a8-1216-5ce7-82fa-1e812070c472 |  | note | Test Required - Visual Inspection
label | e98ed4e8-d937-505b-b61b-1e46956a7cc9 |  | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | 85f18ef1-cac0-5671-8511-11ff6f8f240c |  | note | Task Assigned To - Site Foreman
label | 60facac9-e4b9-5adc-b271-33c41f2fbc2c |  | note | Measuring Devices or Method - Visual
label | a897a391-e553-522f-b236-30460c297675 |  | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | 70c96c94-98ae-5905-b691-7e18a6cbf3b0 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Binder Application
label | 2594a6c6-3122-5329-9379-e1b349f75320 |  | note | Test Required - Binder type, Cutback, Temp, Application rates
label | 8227d69e-7cd9-57ef-a3ec-c032b3d38d00 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | 3c1a70bb-3754-5c55-8899-8e6800ce8bf2 |  | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | 7e323a8d-f8aa-5c14-aada-91a0be1a2eb1 |  | note | Measuring Devices or Method - Visual
label | 7ee25feb-57b5-5b39-a2a1-b175e78fa5eb |  | note | Criteria - Binder Type = 180/200.
label | 412eef46-d94c-5165-8138-a9cbe0f6afdc |  | note | ○ Cutback to suit 1st coat seal 4pph kero max.
label | 8b0826b0-b41f-516c-b2e2-fd56dadf9bf3 |  | note | ○ Temp = 150deg celcius min
label | 7394a312-b8c3-5da7-b4c0-06f46fe2e6ae |  | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
label | cc290c1b-916b-555c-bd30-846018d0b364 |  | note | QA Form - Bitumen Spray Sheets
checkpoint-status |  |  | checkpoint | Chip Application
label | e7d3f3b3-0718-5341-8ca8-ae52c08481c1 |  | note | Test Required - Chip type, Chip Application
label | 4ef5fe66-b1cf-52bc-8b69-697d46c257ad |  | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | 8a143c4a-6fe4-5e26-8624-de7ad304534d |  | note | Task Assigned To - Site Foreman
label | c58496b6-2166-5368-a09f-f091bc864d5b |  | note | Measuring Devices or Method - Visual
label | a7e7604d-94c1-5e73-b96e-a498fccb9a43 |  | note | Criteria - Trucks loaded with correct chip.
label | 33ac837e-e941-53bf-b18f-3da6ce967f37 |  | note | ○ Chip clean. (G4/6 Racked example)
label | 07ef5ba8-4f18-5a8d-8fa8-2d5a710a7a66 |  | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | 3540168b-b184-5f92-9787-7c2328e36cdc |  | note | ○ G6 application = Enough to just fill the voids around the G4.
label | b0572ccf-48d7-5c4f-83d4-ae55746f8d6e |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 81c339b0-1e56-52af-ae0c-eedd6de3eb6d |  | note | Test Required - Visual
label | 6d0e7bdb-fa1d-543e-b757-bead4571823b |  | note | Task Timing / Minimum Task Frequency - At completion of rolling
label | b7858b7e-f2cb-5d3d-af03-9bdbec8cae74 |  | note | Task Assigned To - Site Foreman
label | 6f2e0a97-8cc6-5254-b7f8-ce0ecab6646c |  | note | Measuring Devices or Method - Visual
label | 4be6c2a5-4992-5487-b143-6c97a1b949c3 |  | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 96c64ba2-c1a5-5feb-92a7-78b99e2fccc5 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Site Measure
label | 5d9f9070-b700-567e-88aa-a6328c8ed9e4 |  | note | Test Required - Record final site measure
label | 22527a1a-dbdc-5e66-8b4f-fe501b92d35e |  | note | Task Timing / Minimum Task Frequency - Completion of works
label | 0c8ccbc6-1f5e-59eb-a038-970e653112f0 |  | note | Task Assigned To - Site Foreman
label | 12fcff64-99de-5705-88a5-800b7ca994d0 |  | note | Measuring Devices or Method - Measuring Wheel or Tape
label | 68c7fa76-a2a5-5772-8826-cdc4c7e76a25 |  | note | Criteria - Sketch and record seal area and QA detail
label | d11824dc-1e81-574b-b32d-cc3c3ffb1648 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Post Seal Care
label | 0eedc156-78f1-5fc6-b0a1-86abe2a8886a |  | note | Test Required - Visual inspection
label | da91b0e8-1d9b-5036-b158-889785b2bc6c |  | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | 4d87d9b5-1f04-5dce-9a85-3fc597725a96 |  | note | Task Assigned To - Site Foreman
label | c82f2e10-3221-548f-8dd9-3eab1be9ca80 |  | note | Measuring Devices or Method - Visual
label | b825313b-de79-509f-aa12-108034f9290f |  | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | 4ff0e745-438b-5947-853a-f963f0e359b0 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Chip Removal, Pavement Marking, Traffic Services
checkpoint-status |  |  | checkpoint | Removal of excess chip
label | f27bf570-65b6-573d-b2cf-cdf6443e77fa |  | note | Test Required - Visual Inspection
label | 5797326c-ecda-513a-a4d3-52a8a3a58802 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | fccae71b-75d7-5151-8ab7-c44a59c9ff3d |  | note | Task Assigned To - Project Engineers/Site Foreman
label | f64a4753-eb6c-51e2-8186-dc673571ec1a |  | note | Measuring Devices or Method - Visual
label | 8c7a193c-dcad-52e4-b54e-59e6c150203f |  | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | 9f869e73-4a03-579f-8de9-4462ff3b6e4e |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Pavement Marking
label | f1cf5a27-80a9-5f5f-a221-f16d05d7de32 |  | note | Test Required - Visual Inspection
label | b86c6901-cca4-5a10-b6cf-c9674b39d2f6 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | ffa12e01-1d98-5de9-8007-6aff58cbe9e0 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | fce1bab9-9e91-500a-9f9c-87a4e505666e |  | note | Measuring Devices or Method - Visual
label | c28c1e68-d676-5cde-837a-134448ee0b17 |  | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | 09411e26-61b5-5d8a-8dc7-50a8cbea9e58 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Removal of TTM
label | 319d963f-2c0e-5879-be82-85a70f931aa0 |  | note | Test Required - Visual Inspection
label | d31e5c7f-321e-52e2-989f-638392c56849 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 71617c45-675e-59de-8cca-88aa94e60123 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 638153f9-cce7-51f6-862e-793cc6c1556b |  | note | Measuring Devices or Method - Visual
label | 5ab9b013-c02a-5d07-b363-c519a275a62c |  | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | f9b4617c-14b1-53cc-9438-5ce315a14953 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Traffic Services
label | 0f573298-85fc-5747-9a6f-ad66f9d99016 |  | note | Test Required - Visual Inspection
label | 66d53b87-019d-581b-aaf3-cf375446a882 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 7ecc9676-5dcb-5d3a-85be-d7648775e396 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 4ac4068e-4209-5dfd-8a74-bfdc1a436653 |  | note | Measuring Devices or Method - Visual
label | e3d13d33-a0db-52d9-b495-6c0bc8a6a6a2 |  | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | 35f1db88-e8de-5ee8-894d-9b3fcca8e006 |  | note | QA Form - Daily Diary
checklist-sectioned |  |  | checklist | 4. HB AWPT ITP - Mahiaruhe Stream Bridge Sth |  |  |  |  | Yes | 4. HB AWPT ITP - Mahiaruhe Stream Bridge Sth | b73a77f7-b84e-48ff-94fc-8c708c7b6437
checkpoint-group |  |  | section | Preliminary / Establishment
checkpoint-status |  |  | checkpoint | Establish TTM
label | 0b4cc237-b98e-5277-bc81-da4dd4ee11fe |  | note | Test Required - Visual Inspection
label | a8ebb2ff-0388-54b6-8774-21e32617a84c |  | note | Task Timing / Minimum Task Frequency - AS per TMP requirements. STMS to check site prior to work start. 2 hourly site checks when site attended. - Record checks on Forms
label | 5b9543cc-1ba4-5a1c-bfc4-08bbc4397e3b |  | note | Task Assigned To - STMS/Site Foreman
label | d12c11e3-6100-546d-8f34-34571c8695fc |  | note | Measuring Devices or Method - Visual
label | 5b5609ee-a920-512a-96c8-7bb6838dd1f3 |  | note | Criteria - As per TMP and ensure TMC advised in advance of works.
label | dea48328-8f60-5e7f-a05e-fdc81be724e5 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Permits
label | 8faa57d2-513e-5079-a290-2b9195ed7b6f |  | note | Specification Reference - Permit to Work,Digging Check list (inc. locating services),Close approach permit
label | 87d71875-a82d-502c-b4f5-c47958cd38ec |  | note | Test Required - Document Review
label | cbf39d8e-634c-5f03-b2f8-2bf83531594b |  | note | Task Timing / Minimum Task Frequency - Before Work begins(only if required)
label | 5ce8eabe-744e-5aaf-b31d-505eadcf6735 |  | note | Task Assigned To - Site Foreman
label | c43f47ee-ac8c-5e0d-87db-a9823d984695 |  | note | Measuring Devices or Method - Visual
label | bfebf68d-c653-5c8e-be5e-0cb3da85b2af |  | note | Criteria - Obtain permits and mark outs prior to construction
label | 40b560ec-fb78-57b0-bd9c-db4416063f20 |  | note | QA Form - Copy of Permit on site
checkpoint-status |  |  | checkpoint | Clear-Shoulder and Side drain
label | bf365de5-a801-591d-b7cd-ecf6740af5f4 |  | note | Test Required - Visual Inspection
label | 71ff8223-6c29-5c22-b090-032269f0ce03 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 3f86778d-2f0a-5a15-aa55-9e4bc5c63660 |  | note | Measuring Devices or Method - Visual
label | d0ec3e12-71d7-5509-97fe-3eff889f4849 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Digout Failed Areas
label | 8a126da5-b38a-57a1-9793-a16ab7c12329 |  | note | Test Required - Visual Inspection
label | 795c8f57-7305-5a4c-8d3a-db98c0fd792f |  | note | Task Timing / Minimum Task Frequency - As Requested
label | d91ffad3-815a-52f0-95e0-fe7c2da336af |  | note | Task Assigned To - Project Engineers/Site Foreman
label | fce77690-7179-51e0-9844-40c670e22795 |  | note | Measuring Devices or Method - Scala Penetrometer testing of Subgrade - record No. blows per 50mm depth.
label | b732cb3a-5907-535b-89e7-c8d52b38ab32 |  | note | Criteria - Backfill with Basecourse
label | 293f4e96-4062-5c4c-9150-914bc261ba2d |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Kerb Construction
checkpoint-status |  |  | checkpoint | Basecourse layer construction (1)
label | e5d826d6-77d0-54ff-9b2e-2cf65d3acd92 |  | note | Specification Reference - TNZ B/2
label | 8eda5303-1a89-5df0-bf73-979982068389 |  | note | Test Required - Level and alignment
label | d0f41214-c464-597a-8301-503e9fe6c23a |  | note | Task Timing / Minimum Task Frequency - Every 20m
label | da24f7a6-763e-5168-af3d-fbfd1be38600 |  | note | Task Assigned To - Project Engineer
checkpoint-status |  |  | checkpoint | Basecourse layer construction (2)
label | 2ac07518-0703-52c8-9073-c73d10072de8 |  | note | Specification Reference - TNZ B/2
label | deac1dd2-186b-5a2f-8436-8b74e6d29753 |  | note | Test Required - Compaction
label | 73d234f1-7e1c-5d38-b274-58b54193390a |  | note | Task Timing / Minimum Task Frequency - Every 20m
label | 2d2c42cd-a07e-5182-9f5c-7ecc24e8e3c3 |  | note | Task Assigned To - Project Engineer
label | 149734ce-3553-5e98-9488-3235f1ee8a27 |  | note | Criteria - 25min on the 4th drop
label | 7d92ea31-f7f1-5351-a53f-d33ab45106d1 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Kerbing
label | 102984e6-031f-5e38-b19f-289699c23f70 |  | note | Test Required - Set-out level and alignment
label | d9393e99-1134-5196-9e1a-cc70e17656f7 |  | note | Task Timing / Minimum Task Frequency - after base construction and prior to placement of concrete
label | 1f14a9f7-8090-56a5-8468-7e442ed22065 |  | note | Measuring Devices or Method - survey check
label | ee54125c-18b0-555d-aa31-fd090224c17e |  | note | Criteria - Horizontal: ± 20mm, Vertical: ± 5mm
checkpoint-status |  |  | checkpoint | Concrete Works
label | 2b327f9e-c5d5-5655-917b-81b233d5b4d0 |  | note | Test Required - 20MPa
label | 8ef0ff6c-7e2e-5f55-999f-1ce371ac37ed |  | note | Measuring Devices or Method - Copy of delivery docket
label | 93a6a3d2-4eec-5932-8eef-b02d07ddb8ac |  | note | Criteria - 20MPa, 28days
checkpoint-group |  |  | section | Inspection Test Plan - In Situ Cement Stabilisation
checkpoint-status |  |  | checkpoint | Cement for stabilisation
label | 7763619c-1907-5390-b99b-70d68336d3e4 |  | note | Specification Reference - NZTA B/5:2008, 4.1.2 NZS 3122
label | fa150408-9032-57d2-8ec3-681845fc83e1 |  | note | Test Required - Certified in accordance with NZS 3122
label | 174d64c6-60c6-5c6a-9265-52e8169576fe |  | note | Task Timing / Minimum Task Frequency - As per NZS 3122 Appendix E
checkpoint-status |  |  | checkpoint | Production plan
label | 7d4f72ae-8a70-5284-bbb1-262441642461 |  | note | Specification Reference - NZTA B/5:2008, 7.2.2
label | bf2193d0-5ed5-52d0-b45d-0185c3d2c1bc |  | note | Task Timing / Minimum Task Frequency - 1 per site
checkpoint-status |  |  | checkpoint | Stabilisation mix properties (including cement):
label | 9b665b30-30c8-5423-81d8-851ee02ab705 |  | note | – Maximum dry density (MDD)
label | 9c4e80bb-c8fd-5032-9d94-055d8e52d4e0 |  | note | – Optimum water conent (OWC)
label | d2cdb56e-59ff-549c-afb1-f1fb83280603 |  | note | – Solid density (SD)
label | 0096c04f-01e6-5ec9-8d94-f800bc9c5faf |  | note | Specification Reference - NZTA B/5:2008, 7.7, NZS 4402 Test 4.1.3, NZS 4407 Test 3.7.1
label | fc3b62f4-c61a-59b1-95ee-2eb898fc28bd |  | note | Test Required - Material properties for compaction verification
label | 65f4e514-26bb-5068-85a5-48b76b59b514 |  | note | Task Timing / Minimum Task Frequency - 1 per 5000m2 of material stabilised
label | 08039f2a-e1c3-54ce-bc78-f3d8b39e4c07 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | 523d5820-25b1-5da6-a19d-c92b13cb5240 |  | note | QA Form - QA Measurement Sheet
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | In-situ moisture content of existing pavement aggregate
label | 51d2664d-18fa-5466-990a-ea14d8b6269a |  | note | Specification Reference - NZTA B/5:2008, 7.5 NZS 4402 Test 41.3
label | 1a8a1f78-f940-5853-83e8-e2e18c988baa |  | note | Test Required - In-situ moisture content, Between 90% to 100% of OWC
label | edc8e114-eac3-5671-aa4b-88d3d031a0e9 |  | note | Task Timing / Minimum Task Frequency - As required
label | 8cd671dc-452f-5473-aa1f-c2da1d23fdd1 |  | note | Task Assigned To - Inspection - Lab
label | 0fbe4119-a3f9-5c6f-8171-d6c802311c11 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Top-up metal
label | 174f2b91-1dc3-581d-b6ca-70e7bc5ceb1a |  | note | Specification Reference - TNZ M/4 Table 4
label | 10beb72a-7e8c-51ee-af40-451e045ff925 |  | note | Test Required - Placed to required depth and design levels
label | efa0aabf-ae7b-5cc6-8fc8-79af45ca200c |  | note | Task Timing / Minimum Task Frequency - 20m intervals - Stringline
label | 93d21e60-d42b-5e16-89d2-f739723d318f |  | note | Task Assigned To - Site Foreman
label | 04563c5a-55f5-5c9f-84fb-5d170d70f8f6 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Cement spreading
label | 1479603d-2580-5b4d-89a5-366dffc262af |  | note | Specification Reference - NZTA B/5:2008, 7.3
label | 8361a513-9afa-599f-822f-e782d623cb9a |  | note | – Mat test (1m2 canvas mat)
label | 45139730-5aa2-55db-8f30-16f810da4b29 |  | note | – Average usage test
label | 4a404ea3-6043-59dc-8002-ac8fa65baa48 |  | note | Test Required - Mat test ± 0.5 kg/m2 of specified rate; Average usage ±2.5% of specified rate
label | 52a595b5-9824-5bef-8475-e1b14d9ced7a |  | note | Task Timing / Minimum Task Frequency - Every 400 m2, Upon emptying spreader and bulk tanker
label | 7a4df1fa-7ba9-54e8-959c-b51679aa2537 |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | fa33b642-65e8-5ed1-b9a4-48d9b979f2a1 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | In-situ mixing - Cut depth
label | f218f0ec-329d-554c-9c3a-541c9a33032c |  | note | Specification Reference - NZTA B/5:2008, 7.6.1
label | ee9f5831-6c7a-5cbd-a7f1-53dabc174353 |  | note | Test Required - Maximum variation -5mm and +15mm
label | 82b1b4e4-fb6d-5363-9d3e-b444f04cc518 |  | note | Task Timing / Minimum Task Frequency - Every 200m along cut length at both ends of the drum
label | b585cd2c-776a-59ca-9270-76d4a34c4b9d |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 1bae00d3-ece8-5249-b9bf-34410bc358b1 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | 8536bb9d-a255-5ced-a187-894b3c652485 |  | note | Specification Reference - NZTA B/5:2008, 7.7.1, NZS 4402 Test 41.3
label | d1741ffd-c4af-5dc4-be0a-854c0be8f03f |  | note | Test Required - Plateau testing
label | 990361ed-43cd-5ffc-a8ec-e13d779f89a8 |  | note | ○ Mean value ≥ 98% of MDD
label | 04a7e2f1-3c28-5aba-8eee-4d45847f8e21 |  | note | ○ Minimum value ≥ 95% of MDD
label | 8f0a77a5-0072-5f60-83d0-a2e8867e383f |  | note | Task Timing / Minimum Task Frequency - 5 Randomly selected locations / lot, Lot size ≤ 1000m2
label | 39c1bd92-b780-51c6-9d63-9c061ec15f81 |  | note | Task Assigned To - Hold Point - Approval required by site engineer
label | ae5d8459-0d68-5f65-a74f-9b17d5422bd8 |  | note | Measuring Devices or Method - Nuclear Densometer
label | 399058f7-8278-5433-83e3-817b5b01290f |  | note | Criteria - Minimum value 95% of MDD
label | e690ca06-3f44-52ee-b413-4575ba530d4a |  | note | QA Form - Test Reports
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Surface shape
label | 9e00678a-a90d-5693-8935-e17555f8c071 |  | note | Specification Reference - NZTA B/5:2008, 7.8
label | d955642f-2b9f-5a69-9873-e22cd43a285b |  | note | Test Required - ≤10mm from 3-metre straight edge, No depression, Vertical variations -5 + 15mm
label | e4d697e4-7e19-5a84-936d-c98e5024666b |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 03aa30cb-91ef-5d3f-a3b1-3fb161b8e01d |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | ac9e1228-9cfd-5014-9814-72786e941d2e |  | note | Measuring Devices or Method - Stringing, Tape measure
label | 74ec2921-7206-5b66-a754-170770d1a3c2 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Crossfall
label | f74a34f4-6a8d-5440-9c00-3c8f5420d5d5 |  | note | Specification Reference - NZTA B/5:2008, 7.9
label | 4eb6a65e-3d64-5474-b566-3c5438116171 |  | note | Test Required - Not less than exisitng crossfall at the start of construction
label | c4f037da-947c-561d-b1d4-40c7cc90b991 |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | a9a1b184-0011-5d00-aa08-f0ea9422c4cc |  | note | Task Assigned To - Inspection & sign off by Site Supervisor
label | 5a075343-e45f-515e-8416-9f961e55301b |  | note | Measuring Devices or Method - Stringing, Tape measure
label | 6da06598-935f-5602-be3a-6162517608d3 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Surface finish
label | f50d118d-bd8b-526e-a4b0-c76aa69ff811 |  | note | Specification Reference - NZTA B/5:2008, 7.10
label | 7e8ad013-9845-5763-b7b3-31d1f2967a65 |  | note | Test Required - See clause
label | 50878e14-bc25-587c-b441-4571104dc4be |  | note | Task Timing / Minimum Task Frequency - 20m intervals
label | 284359a9-3fb5-51cf-a012-bdce94b51074 |  | note | Task Assigned To - Hold Point - Approval required by site engineer prior to Sealing
label | be95931a-c334-5f56-a70b-1ea51928a141 |  | note | Measuring Devices or Method - Visual
holdpoint |  |  | signoff | HOLD POINT
checkpoint-no-status |  |  | checkpoint | * Normal Risk = < 5 x 106 ESA's (or < 500 HCV per lane per day)
checkpoint-no-status |  |  | checkpoint | ** High Risk = > 5 x 106 ESA's (or > 500 HCV per lane per day)
checkpoint-group |  |  | section | Chipseal Construction (NZTA P29)
checkpoint-status |  |  | checkpoint | Ensure appropriate TMP used
label | f9409b1d-71b8-5e37-b96f-9c0c072f5c45 |  | note | Specification Reference - Refer TEMPORARY TRAFFIC MANAGEMENT Section
checkpoint-status |  |  | checkpoint | Seal design
label | 96f9334d-a157-5e3d-9923-766819236bb6 |  | note | Task Timing / Minimum Task Frequency - Prior to surfacing (HOLD POINT)
label | 27bb3a0a-ea9b-5c19-a14c-9daa9445da35 |  | note | Task Assigned To - Project Engineer
label | f82f867f-67ff-54a7-bf74-09ee950528dd |  | note | Criteria - Seal design to be reviewed prior to surfacing
label | 052871cc-7171-5c86-a4bf-eda87ec89940 |  | note | QA Form - Seal design template
holdpoint |  |  | signoff | HOLD POINT
checkpoint-status |  |  | checkpoint | Location/Size Confirmation
label | 36feab03-f525-5dea-b057-8d35f0e05bbb |  | note | Specification Reference - Mark up extent of chipseal
label | b156c35d-d2ec-5cf1-8eb4-121662254af7 |  | note | Test Required - Prior to surfacing
label | f6081ef0-3c2a-5434-a2ac-e0b83dbe9759 |  | note | Task Timing / Minimum Task Frequency - Project Engineer
label | 140ee0b1-42c9-5559-912f-5243828c8b30 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Surface Cleanliness
label | 6749f55c-bbdd-5875-a863-7187e66bc084 |  | note | Test Required - Visual Inspection
label | 88f08790-8261-5961-8a41-2f9ea341b1b7 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder
label | d522e056-1581-55de-96db-546d95fae89f |  | note | Task Assigned To - Site Foreman
label | 2c009dd0-f32e-5963-8e07-3cb121da5012 |  | note | Criteria - To confirm that all loose material is removed from the surface and surrounding area.
label | 411ead23-c3b0-5b1e-bf0e-3ce844755cec |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Plant Resource
label | ba520792-45a0-5876-8fe8-5cfa8c8b6bd6 |  | note | Test Required - Visual Inspection
label | 71ad4ba9-e930-5100-ae79-1d68ebcf5ad2 |  | note | Task Timing / Minimum Task Frequency - Prior to start of Sealing
label | 3038cbc0-dbfa-5b15-a920-83b26bcb5ffd |  | note | Task Assigned To - Site Foreman
label | 04b24b27-6be4-52a3-a802-a94acfe29663 |  | note | Measuring Devices or Method - Visual
label | c4da6684-1d6c-5005-b3dc-b454dc35a8bb |  | note | Criteria - Ensure all plant set ready to go. (i.e. Trucks loaded, Roller ready etc.)
label | 7b477481-b38a-576e-a11f-593b2e54f9e9 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Binder Application
label | 47e36f20-2dd2-5284-89bc-9e5ead67a530 |  | note | Test Required - Binder type, Cutback, Temp, Application rates
label | 014ef88c-05ca-550c-b7f8-27bef178cea5 |  | note | Task Timing / Minimum Task Frequency - Prior to application of binder. Site Foreman/ Bitumen Sprayer Operator to confirm adjustment and record reason to application prior to start.
label | 61193acc-5ab5-5e08-8f4a-e6df36213047 |  | note | Task Assigned To - Site Foreman/ Bitumen Sprayer Operator
label | d1399273-5142-5824-b091-18af2644a834 |  | note | Measuring Devices or Method - Visual
label | de0e30e8-cacb-571f-beba-ca9cb8d106d4 |  | note | Criteria - Binder Type = 180/200.
label | 465d4c23-d201-5b11-b00d-e88f73a0a5a6 |  | note | ○ Cutback to suit 1st coat seal 4pph kero max.
label | b8524b2b-dc7b-5183-8e02-664a1dd510eb |  | note | ○ Temp = 150deg celcius min
label | 944026e2-5d95-5990-9c91-f0f8304f3b49 |  | note | ○ Application = Design l/m2, +/- 0.1 l/m2.
label | bd496121-0f85-5849-bfb2-3069b635e78e |  | note | QA Form - Bitumen Spray Sheets
checkpoint-status |  |  | checkpoint | Chip Application
label | 585c4913-110e-5dfb-abbc-369b002f23a0 |  | note | Test Required - Chip type, Chip Application
label | 18621cec-fc03-5b7c-a209-e4e6aa0f45a8 |  | note | Task Timing / Minimum Task Frequency - Prior to application of chip and preferably prior to application of binder
label | 68977e62-c495-5cc9-b26e-389089697399 |  | note | Task Assigned To - Site Foreman
label | 1c3d4a1a-4e23-5a75-a51a-9034ca3bcbfd |  | note | Measuring Devices or Method - Visual
label | 2a4de28e-c146-51c1-8592-048dfd206af3 |  | note | Criteria - Trucks loaded with correct chip.
label | 85263994-3e52-5777-ace5-dd9f293d3c57 |  | note | ○ Chip clean. (G4/6 Racked example)
label | ab6275d4-3d65-593b-bf5b-c02fde632ce3 |  | note | ○ G4 application = windows big enough for 1-2 G6 chips to fall between G4.
label | 5f6352e0-2bad-5a03-9149-c6d5c661eb78 |  | note | ○ G6 application = Enough to just fill the voids around the G4.
label | 1cc63e38-dc49-5b79-a0d1-20455b12ee01 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Compaction
label | d8929323-454f-5157-b5f7-dd1fb8b5f569 |  | note | Test Required - Visual
label | 18c82faf-5e82-5e33-b1fc-32cd2decced6 |  | note | Task Timing / Minimum Task Frequency - At completion of rolling
label | 21281eac-5d3d-5ced-bc0b-8b35f06915ec |  | note | Task Assigned To - Site Foreman
label | 89bb0789-09c9-5291-a96e-ad180a8ae962 |  | note | Measuring Devices or Method - Visual
label | d86f96e3-8b10-5210-936a-155d5cf63978 |  | note | Criteria - Ensure sufficient passes with roller to embed chip (typically 4-5 passes)
label | 997c8a7d-77b7-5900-a4bc-4e13cd489485 |  | note | QA Form - 'QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Site Measure
label | 9694d6a5-3412-5258-8e2d-6c9d40409370 |  | note | Test Required - Record final site measure
label | 0b5577bf-7e97-522a-989e-b65bcfe2fdb0 |  | note | Task Timing / Minimum Task Frequency - Completion of works
label | 337978e1-4082-5de0-9ab4-6b4ab5986116 |  | note | Task Assigned To - Site Foreman
label | 701999a4-54cd-5b5c-a48c-6712456953f5 |  | note | Measuring Devices or Method - Measuring Wheel or Tape
label | b81e3173-6fc6-59e0-a095-b0777c20a790 |  | note | Criteria - Sketch and record seal area and QA detail
label | e3e0c10a-0281-572f-9d45-c1d2c7f22775 |  | note | QA Form - QA Measurement Sheet
checkpoint-status |  |  | checkpoint | Post Seal Care
label | ebd74920-e012-59e1-a602-ee410cddbc78 |  | note | Test Required - Visual inspection
label | d95f1382-04b3-50bf-87f8-a311653dfcfc |  | note | Task Timing / Minimum Task Frequency - 4 hours after Surfacing
label | 44492a7d-cc40-5b8d-96b5-d77de9f22a6d |  | note | Task Assigned To - Site Foreman
label | 12eff720-709d-5d88-8f18-c4bb3862b75a |  | note | Measuring Devices or Method - Visual
label | cbcd7991-b7fd-5e68-a713-dd60cd153718 |  | note | Criteria - Ensure sufficient resource and positive traffic management in place to protect new seal. Physical management (i.e. Cones used to run traffic off the normal wheel path) mandatory for the first 4 hours.
label | 5db6fe23-4612-5d24-ace0-10779251acd6 |  | note | QA Form - Daily Diary
checkpoint-group |  |  | section | Chip Removal, Pavement Marking, Traffic Services
checkpoint-status |  |  | checkpoint | Removal of excess chip
label | 1e42311d-5f1f-5dca-9a10-a50f45c89033 |  | note | Test Required - Visual Inspection
label | 25de1c67-2dff-50a4-b1ba-e90aff841421 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | bc504528-389c-5b6c-a919-3601480b1aff |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 6f5fd346-5be0-520e-a424-65770d204a1f |  | note | Measuring Devices or Method - Visual
label | 3ff2f5d6-7b59-553c-a6ce-9d5026dd962a |  | note | Criteria - Ensure all excess chip removed from site. No chip windrows left on site in Shoulders.
label | ec54d021-e1e3-59d4-ac7f-2283f489139d |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Pavement Marking
label | acd0b334-c8c3-59d3-bbe3-491987d433df |  | note | Test Required - Visual Inspection
label | 770fe5d4-130c-521d-b856-58818c3f8185 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | 32174133-3bb4-55fd-b832-a6449eb12aa6 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | ade8e1be-e4e1-53d3-ab07-9ff77f24da73 |  | note | Measuring Devices or Method - Visual
label | d4f45d1f-becb-5c7d-aa1c-14198bc1e389 |  | note | Criteria - Linemarking must be completed within 48 hours of surfacing.
label | 653296cc-9113-5e39-8bf7-f8377d66af27 |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Removal of TTM
label | 58796da2-39b0-57cd-9783-d6f7695c5028 |  | note | Test Required - Visual Inspection
label | a0a35e40-613c-58e0-9620-c6c1d1b8d639 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | d2081b7f-91b4-5686-80ec-150c6e0896e6 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 6e250860-6b94-519c-aced-356579d5f3a3 |  | note | Measuring Devices or Method - Visual
label | adfc2e9f-88f0-572c-851a-5f171887b991 |  | note | Criteria - All Temporary Traffic Management must be removed within 48 hours provided site is safe (i.e. excess chip removed, line marking completed).
label | 741ddc98-5834-5800-9e38-b76bb619172a |  | note | QA Form - Daily Diary
checkpoint-status |  |  | checkpoint | Traffic Services
label | 94b1db30-4180-5246-ac46-c159ceb4e1f9 |  | note | Test Required - Visual Inspection
label | 51e1d611-2e20-5c5b-846c-dca5c3c68d77 |  | note | Task Timing / Minimum Task Frequency - Within 48 hours of surfacing
label | c216540e-c3bd-5b6c-ab7e-44c5f9e69780 |  | note | Task Assigned To - Project Engineers/Site Foreman
label | 45b3eb70-b641-5f55-b9e4-953e3f6d72a5 |  | note | Measuring Devices or Method - Visual
label | b3e0c72c-5b25-5db3-8ab5-ac79265586c6 |  | note | Criteria - Completed installation of all EMPs, RRPM's, Signs etc
label | 1f563038-1803-5bd6-8648-5cde48442d33 |  | note | QA Form - Daily Diary
checklist-flat |  |  | checklist | QMP |  |  |  |  | Yes | QMP | d11d2615-699c-4242-a2e7-fdf176a2a6c6
checkpoint-status |  |  | checkpoint | QMP